Reference Number (FP016): Strengthening the resilience of smallholder farmers in the Dry Zone to climate variability and extreme events through an integrated approach to water management

Accredited Entity: United Nations Development Programme

Project/Programme Completion Report (PCR)

TEMPLATE

Version 1 MAY 2021

Submitted to GCF

Please submit the completed PCR to opm@gcfund.org

| SUBMITTED BY |  |
| --- | --- |
| Name and title Aishath Azza, Regional Technical Specialist – Climate Change Adaptation | Date (28-03-2026) |
| Please indicate if this report has been shared with the relevant NDA(s) for this Funded Activity (Yes/No) | Date of submission to NDA: 28 March 2026 |

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Received by: | Signature | Date (DD-MM-YYYY) |

Contents

LIST OF ACRONYMS AND ABBREVIATIONS	i

EXECUTIVE SUMMARY 	ii

SECTION 1.  FUNDED ACTIVITY BACKGROUND AND CONTEXUAL ANALYSIS	1

SECTION 2.  OVERALL PROJECT/PROGRAMME ACHIEVEMENTS 	5

SECTION 3: PERFORMANCE AGAINT THE GCF INVESTMENT CRITERIA .	11

SECTION 4.  IMPLEMENTATION ARRANGEMENTS AND OPERATIONAL PERFORMANCE 	21

SECTION 5:  CHALLENGES AND LESSONS LEARNED	23

SECTION 6.  REPORT ON ENVIRONMENTAL, SOCIAL SAFEGUARDS, AND GENDER 	6

SECTION 7:  SUSTAINABILITY AND RECOMMENDATIONS	32

APPENDICES	36

Annex 1: REPORT ON LOGICAL FRAMEWORK	37

Annex 2: FINANCIAL PERFORMANCE BY CATEGORY	43

Annex 3: CASE STORIES	44

Annex 4: COMPLIANCE WITH LEGAL AGREEMENTS (AMA/FAA)	45

OTHER ATTACHMENTS	47

| PROJECT/PROGRAMME DATA PROFILE (This section provides general information on the funded activity) |  |
| --- | --- |
| - Funded Activity Title: | FPO16 Strengthening the resilience of smallholder farmers in the Dry Zone to climate variability and extreme events through an integrated approach to water management |
| - Accredited Entity | United Nations Development Programme |
| - Executing Entity(ies): | Ministry of Agriculture, Livestock, Land, and Irrigation |
| - Country (ies) | Sri Lanka |
| - Funding Proposal Number: | (FP##) FPO16 |
| - Date of Board Approval - Number: | 30 June 2016 at the 13th meeting of the Board on 28-30 June 2016 -GCF/B.13/32/Rev.01 |
| - Project/Programme Theme / Type | ☐ Mitigation ☒ Adaptation ☐ Cross-cutting |
| - Funded Activity Size Category | ☐ Micro (≤10 Million(M)) ☐ Small (10M<x≤50M) x Medium (50M<x≤250M) ☐ Large (>250M) |
| - Sector: (Public / Private) | ☒ Public sector ☐ Private sector |
| - Date of Signed FAA | 07 June 2017 |
| - Date of FAA Effectiveness | 28 June 2017 |
| - Funded Activity Initial Expected Duration (Years) | 7 years |
| - Funded Activity Actual Duration (Years) | 8 years |
| - Funded Activity Completion Date: | 12/28/2025 |
| - Total Project/Programme Financing: | Grant: USD 52,084,000 |
| - Total amount of GCF Proceeds approved: | Grant: USD 38,084,000 |
| - Total amount of GCF Proceeds disbursed to the Accredited Entity: | Grant: USD 38,084,000 |

# LIST OF ACRONYMS AND ABBREVIATIONS

| ADAP4R | Adaptation for Resilience |
| --- | --- |
| AE | Accredited Entity |
| APR | Annual Performance Report |
| ARPA | Agrarian Research and Production Assistant |
| ASC | Agrarian Service Center |
| AWD | Alternate Wetting and Drying |
| AWP | Annual Work Plan |
| CAS | Climate Action Symposium |
| CBO | Community Based Organizations |
| CKDu | Chronic Kidney Disease of unknown etiology |
| CMC | Cascade Management Committee |
| CResMPA | Climate Resilient Multi-Phase Programmatic Approach |
| CRIWMP | Climate Resilient Integrated Water Management Project |
| CRWSSP | Climate Resilient Water Safety and Security Plans |
| CSA | Climate-Smart Agriculture |
| CSIAP | Climate Smart Irrigated Agriculture Project |
| CSO | Civil Society Organizations |
| CWRD&MP | Cascade Water Resources Development and Management Plan |
| CWSS | Community Water Supply Schemes |
| DAD | Department of Agrarian Development |
| DDMC | Divisional Disaster Management Committee |
| DMC | Disaster Management Center |
| DNCWS | Department of National Community Water Supply |
| DoA | Department of Agriculture |
| DOM | Department of Meteorology |
| DRR | Disaster Risk Reduction |
| DSD | Divisional Secretary Division |
| EDO | Economic Development Officer |
| EOC | Emergency Operations Center |
| FO | Farmer Organization |
| GAP | Gender Action Plan |
| GCF | Green Climate Fund |
| GND | Grama Niladhari Division |
| GOSL | Government of Sri Lanka |
| GRC | Grievance Redress Committee |
| GRM | Grievance Redress Mechanism |
| GWP | Global Water Partnership |
| HACT | Harmonized Approach to Cash Transfer |
| HEC | Hydrologic Engineering Center |
| ID | Irrigation Department |
| IIE | Independent Interim Evaluation |
| IP | Implementing Partner |
| IPNS | Integrated Plant Nutrient System |
| IWMI | International Water Management Institute |
| IWRM | Integrated Water Resources Management |
| LAWF | Large Advanced Filtration Systems |
| M&E | Monitoring and Evaluation |
| MMDE | Ministry of Mahaweli Development and Environment |
| MOD | Ministry of Disaster Management |
| MOE | Ministry of Environment |
| NDA | Nationally Designated Authority |
| NDC | Nationally Determined Contributions |
| NGO | Non-Governmental Organizations |
| NIM | National Implementation Modality |
| NWSDB | National Water Supply and Drainage Board |
| O&M | Operation and Maintenance |
| PCR | Project Completion Report |
| PIR | Preliminary Investigation Report |
| PMU | Project Management Unit |
| RP | Responsible Party |
| RWH | Rainwater harvesting systems |
| RWS | Rural Water Supply |
| SARP | Smallholder Agribusiness and Resilience Project |
| SAWF | Small Advanced Water Filtration Systems |
| SDG | Sustainable Development Goals |
| SECU | Social and Environmental Compliance Unit |
| SLT | Sri Lanka Telecom |
| SOP | Standard Operating Procedures |
| SRM | Stakeholder Response Mechanism |
| TDS | Total Dissolved Solids |
| TWG | Technical Working Group |
| UNDP | United Nations Development Programme |
| UOP | University of Peradeniya |
| VCC | Village Coordination Committee |
| VDMC | Village Disaster Management Committee |
| VIS | Village Irrigation Systems |
| WASH | Water, Sanitation, and Hygiene |

# EXECUTIVE SUMMARY (Maximum Length 2 pages)

(This section should summarize the main contents of the project/programme completion report with a focus on key results achieved, gender-related co-benefits or outcomes, lessons learned, and the exit strategy and may touch upon the Funded Activity’s contributions to GCF’s objectives.) The Climate Resilient Integrated Water Management Project (CRIWMP), financed through a Green Climate Fund (GCF) grant of USD 38.08 million with USD 14 million in Government co‑financing, was approved in 2016 and implemented from 2017 to 2025 following one extension. The project was designed to strengthen the climate resilience of vulnerable smallholder farmers in three Dry Zone river basins through an integrated approach that combined improved irrigation and watershed management, enhanced access to safe drinking water, and strengthened early warning, climate forecasting, and water management systems. The project achieved this through three core outputs: (1) upgrading village irrigation systems and associated watersheds and scaling up climate‑smart agricultural practices; (2) enhancing safe drinking water supply and management; and (3) strengthening early warning, forecasting, and water management systems to enhance the adaptive capacity of smallholder farmers to droughts and floods. A restructuring adjusted several targets and implementation modalities while maintaining the overall objectives and integrated design. Key Results: At completion, the project directly benefited 804,877 people, equivalent to 114% of the target, representing 87% of the population in three selected river basins and 3.7% of the national population. Of this total, 410,411 women benefited directly, reflecting strong delivery against the project’s Gender Action Plan. Despite significant political, economic, and pandemic‑related challenges during implementation, the project met or exceeded nearly all its targets, demonstrating the effectiveness of its integrated, cascade‑based resilience approach. Under Output 1, which focused on upgrading village irrigation systems and scaling climate‑smart agriculture (CSA), 573,212 beneficiaries (F: 292,338 ¦ M: 280,874) were reached (110% of target). The project fully upgraded the headworks of 325 village irrigation systems (VIS) across 20 tank cascades, ensuring more reliable irrigation water, while enhancing associated ecosystems and biodiversity. CSA interventions extended across 484 VISs, enabling cultivation of 10,737.3 hectares (ha) of asweddumized land, with 9,839 ha achieving a cropping intensity (CI) above 1.6, thereby meeting the 9,750‑hectare target. Beyond irrigated areas, climate‑smart home gardening, inland fisheries, livestock development, and fruit and vegetable cultivation contributed to improved livelihood resilience. Market‑oriented measures, including forward sales agreements, farmers’ markets, and mobile markets, helped sustain productivity gains. Under Output 2, the project improved safe drinking water access for 128,537 people (F: 63,881 ¦ M: 64,656) through community-driven solutions (104% of the target). These included 16 pipeline extensions, 7 new Community Water Supply Schemes (CWSS), 12 large advanced filtration systems (LAWF), 89 small advanced filtration systems in schools and health centers (SAWF), 4,003 household rainwater harvesting (RWH) systems, and 49 school RWH systems. The preparation of 104 Climate‑Resilient Water Safety and Security Plans (CRWSSPs) further strengthened long‑term sustainability by integrating source protection, water quality management, and community‑led operation and maintenance. These interventions collectively reduced climate‑induced water insecurity and contributed to improved health and the overall productivity across the cascades. Under Output 3, 465,911 people (F: 237,615 ¦ M: 228,296) benefited from strengthened early warning, forecasting, and water‑management systems (105% of target). Digital agro‑meteorological advisories enabled farmers to make climate‑informed decisions, while a water‑management advisory guideline supported more efficient and sustainable agricultural water use. Community disaster resilience improved through 47 village disaster preparedness plans established across 25 flood‑affected Divisional Secretariat Divisions (DSDs), enhancing anticipatory adaptation to both droughts and floods. The central innovation contributing to the project’s paradigm‑shifting intent was the integrated approach to managing water and associate resources. The establishment of 20 Cascade Water Resources Development and Management Plans (CWRD&MPs) and corresponding Cascade Management Committees (CMCs) strengthened integrated water‑resource management across the project area, with a particular focus on cross‑sectoral governance and planning mechanisms. Their effectiveness was affirmed through Government endorsement via a national Circular in 2023 and a Cabinet decision in 2025 to initiate amendments to the Agrarian Development Act, thereby enhancing the legal standing of the CMCs and enabling replication and scaling. Gender-Related Co-Benefits/Outcomes: Gender‑responsive implementation yielded substantial co‑benefits. The project directly supported 410,411 women, who gained improved access to climate‑resilient agricultural technologies, safe drinking water, and climate information services. Women participated actively in climate smart agriculture, watershed and water‑source conservation, rainwater harvesting, disaster preparedness, and climate‑smart cultivation. Time saved due to improved drinking water access enabled women and children to shift to income‑earning and educational activities. Women‑headed households were prioritized when selecting beneficiaries for drinking water interventions, women’s representation in CMCs and water CBOs was mandatory, and women contributed to VIS upgrading through participatory monitoring committees. Women’s economic empowerment expanded through home gardening, livestock rearing, handicrafts, agricultural value addition, market engagement, and negotiation of forward‑sales agreements. By the end of the project, 33% of water‑supply CBO leaders and 31% of CMC members were women, reflecting strengthened leadership and inclusion in water‑resource governance. Long-Term Sustainability of the Resources & Exit Strategy: The project’s sustainability strategy centered on building institutional capacity at national, provincial, and community levels. A pool of 530 trainers (F: 181 ¦ M: 349), including public officers, was established and integrated into Provincial Council training systems to sustain skills in irrigation O&M, CSA technologies, ecosystem management, safe‑water system maintenance, early warning, and disaster risk reduction. Thousands of community members received technical training across all outputs (Output 1: 150,586, Output 2: 67,958 under Output 3: 23,348), including training on irrigation system upgrading and operation and maintenance, improved climate-smart agricultural technologies, management of ecosystems, improved off-farm and on-farm water management, management and maintenance of rural water supply facilities, drinking water source protection, advanced weather warning, and disaster risk reduction. Training modules, guidelines, SOPs, and user manuals were formally handed over to government institutions. Each upgraded VIS was equipped with an O&M and disaster‑response plan with clearly defined responsibilities and financing arrangements. Agreements with 3 CBOs in Kurunegala and Anuradhapura Districts and operational arrangements with the National Water Supply and Drainage Board (NWSDB) in balance 4 new CWSS in Puttalam, Kurunegala, and Vavuniya Districts ensured that revenue generated from drinking water systems would be allocated for continued operation and maintenance. Lessons Learned: CRIWMP demonstrated that integrated water and associated resource management deliver stronger and more durable climate‑resilience outcomes when institutional and planning elements are initiated early and implemented in parallel with structural investments. The experience showed that cascade‑level governance, through CMCs and CWRD&MPs, provides an effective platform for coordinating irrigation, drinking water, agricultural practices, and disaster preparedness, and that formal policy recognition significantly accelerates sustainability and scaling. The project also highlighted the importance of anticipatory adaptation measures, such as agro‑meteorological advisories and early warning systems, which enhance the value of infrastructure and enable climate‑informed decision‑making by communities. The need for stronger value‑chain and market linkages emerged as essential for sustaining livelihood gains beyond productivity improvements. CRIWMP further demonstrated that gender‑responsive approaches, including women’s leadership in CMCs and water CBOs, significantly improve resource stewardship, community engagement, and overall resilience outcomes. Finally, the establishment of a provincial‑level trainer pool underscored the value of institutionalized capacity building and structured handover mechanisms to ensure continuity of technical support, O&M, and governance functions after project closure. Meeting GCF objectives: Overall, CRIWMP delivered transformative climate action in three highly vulnerable river basins and cascade systems by directly addressing the structural barriers that limit climate resilience—insufficient public financing for climate‑resilient investments, fragmented institutional coordination, gaps in technical guidance for water management, and limited climate‑risk awareness and capacity among local actors. Through improvements in agricultural productivity, access to safe drinking water, livelihood diversification, and empowered community governance, the project significantly strengthened food and water security, health, and well‑being for vulnerable households. Its integrated, cascade‑based approach has been formally endorsed by the Government of Sri Lanka, demonstrating clear paradigm‑shift potential and opening pathways for national replication and policy influence. The project contributed to sustainable development, aligning with the country’s SDG commitments and supporting progress against nine NDCs. Strong country ownership was evident through close engagement of the Government throughout project implementation and decision-making via the regular Project Board meetings, fulfillment of co‑financing requirements and the Government’s ability to sustain implementation during fiscal constraints, including mobilizing additional community and private‑sector resources that helped buffer the impacts of mid‑project economic shocks. Despite political, economic, and COVID‑19‑related challenges, the project remained efficiently implemented, achieving its targets within the adjusted timeframe and validating the effectiveness of integrated climate‑resilient water management as a high‑impact, scalable model for the Dry Zone.

# SECTION 1. FUNDED ACTIVITY BACKGROUND AND CONTEXUAL ANALYSIS (Maximum Length 3 pages)

- Background Sri Lanka’s Third National Communication (2015) highlighted an increasing frequency of climate‑related hazards—including erratic rainfall, prolonged droughts, high‑intensity storms, and flash floods—which have disproportionately affected smallholder farmers in the Dry Zone. These farmers rely on VISs and small tank cascades that are highly sensitive to changes in rainfall and catchment health. Intense rains have accelerated soil erosion and tank siltation, weakening the capacity of these systems to store water. Over 1,950 village reservoirs and diversions breached during floods in 2012 and 2014, and repairs were frequently delayed, further undermining local resilience. Limited maintenance of irrigation infrastructure and insufficient local‑level technical capacity amplified these vulnerabilities. The knowledge and awareness of climate change risks and impacts, and the capacity to incorporate such knowledge for designing and maintaining the infrastructure at the local level were found to be insufficient. Rural communities also faced compound barriers, including limited access to CSA technologies, weak early warning dissemination, inadequate drinking water facilities, and heightened exposure to Chronic Kidney Disease of Unknown Aetiology (CKDu) in several Dry Zone districts. These challenges were especially severe for marginalized groups—women, youth, and the disabled—whose livelihoods were constrained by low agricultural productivity, time burdens associated with water collection, and limited income opportunities. Financial constraints restricted investment in resilient rural water infrastructure, CSA inputs, O&M systems, and climate monitoring stations. Institutional and coordination weaknesses, particularly at the local level, impeded integrated problem‑solving. Previous government efforts to address climate risks were largely sector‑based and lacked the watershed‑scale, community‑centred approach needed for managing interconnected tank cascade systems. Recognising these gaps, the GoSL, with UNDP support, undertook a preparatory study titled “Strengthening the resilience of smallholder farmers in the Dry Zone to climate variability and extreme events through an integrated approach to water management” in 2015. This study was guided by a Technical Working Group (TWG) consisting of the relevant government institutions in the water and agriculture sectors, while selected non-governmental organizations (NGO) also participated in its discussions. The Study identified farmers under VIS as the most vulnerable group (coinciding with the Department of Agriculture's 2013 spatial analysis of climate vulnerability) and confirmed the underutilized potential of traditional tank cascades—where hydrological linkages enable repeated water reuse and offer a natural platform for integrated solutions. The TWG concluded that combining modern techniques with traditional knowledge and establishing formal governance structures for cascade‑level planning would be essential. Considering the diversity of climate‑related vulnerabilities and their inter‑dependencies, the Study concluded that an integrated river‑basin approach—consistent with GoSL policies, strategies, and national priorities—was essential for strengthening climate resilience. It highlighted the tank cascade system as a uniquely suitable framework for integrated water management. These systems, composed of hydraulically linked tanks and anicuts across the upper, middle, and lower catchment, enable multiple reuse of the same water, support natural flow regulation, enhance groundwater recharge, and stabilize ecosystems. The cascades’ inherent integrated nature allows synchronized management of irrigation, agriculture, ecosystems, and flood control. The Study further emphasized that traditional knowledge, embedded in centuries‑old land‑use zoning and water‑sharing practices, represented a valuable and underutilized resource for climate adaptation. Hence, it was agreed that this project should combine modern and traditional techniques, address the entire cascade ecosystem, and be supported by a scientific plan and a formal institutional structure for coordinated implementation and long‑term sustainability. Objective of the project: The objective of the project was to strengthen the resilience of smallholder farmers, particularly women, in the Dry Zone through improved water management to enhance their lives and livelihoods, contributing to Fund Level impacts such as: increased resilience of health and well-being; food and water security; and increased resilience and enhanced livelihoods of the vulnerable smallholder farmers in the Dry Zone of Sri Lanka. Three interconnected outputs were planned in the project design, contributing to achieving the project objective. They are briefly described as follows: Output 1- Upgrading and enhancing the resilience of village irrigation systems and scaling up climate-resilient farming Practices in three river basins of the Dry Zone: This Output focused on strengthening climate-risk-informed water management for agricultural production. It involved upgrading 325 VISs in selected cascade systems and improving associated agricultural practices through the adoption of CSA technologies, incorporating both modern techniques and traditional water management concepts. GoSL co‑financing primarily supported canal‑system improvements. Implementation centered on the participation of FOs, frontline officers of agriculture‑related agencies, community groups, and private‑sector partners, with targeted efforts to build capacity and empower women farmers. The interventions aimed to enhance cropping intensity above 1.6 (160%) across 9,750 ha, supporting more resilient, productive farming systems. Output 2- Enhancing climate-resilient, decentralized water supply and management solutions to provide access to safe drinking water to vulnerable communities: This Output delivered safe drinking water solutions to vulnerable households through an integrated package of source replenishment, storage improvement, water‑quality treatment, and distribution interventions. It addressed the root causes of water‑quality issues, including those contributing to CKDu, medical costs and aimed to reduce the time women and children spent fetching water, thereby enabling opportunities for income generation and education. Because drinking‑water sources—especially groundwater—extend beyond river‑basin boundaries, interventions were planned at the district level across areas intersecting the three target basins. The revised target for this Output was 122,715 beneficiaries. Output 3- Strengthening climate and hydrological observing and forecasting systems to enhance water management and adaptive capacity of smallholder farmers to droughts and floods: This output strengthened access to climate and hydrological information essential for drought and flood preparedness. Interventions included improved seasonal climate advisories for agricultural planning, early‑warning systems for storms and floods, and enhanced decision‑support for water releases from irrigation tanks. Technologies and systems were introduced to provide farmers and communities with timely, actionable information for coordinated operation of water infrastructure and climate‑smart agricultural planning. The project also strengthened Agrarian Service Centres (ASCs) to produce participatory advisories based on forecast data and climate‑resilient agriculture options. Planned investments included five automated stream‑gauging stations to improve flood forecasting and five agro‑meteorological stations to support agricultural decision‑making across the three river basins. A cross‑cutting intervention introduced Cascade Water Resources Development and Management Plans (CWRD&MPs) and Cascade Management Committees (CMCs) to integrate water, agriculture, drinking water, ecosystems, and disaster‑risk management at the cascade level. Rationale for Restructuring: During implementation, a key design assumption—that adequate freshwater sources would be available for Output 2—proved incorrect. Several suitable sources were allocated to new water supply projects before commencement, increasing treatment costs and reducing feasible coverage. As a result: - Output 2 infrastructure beneficiaries were revised from 217,000 to 122,715. - Training on water‑source protection and management reached 74,403 beneficiaries, offsetting reduced infrastructure coverage. - The total direct beneficiary target was thus revised from 770,500 to 705,818. The restructuring proposal was submitted in 2021 and approved in 2022. Target Groups: The project targeted 705,818 direct beneficiaries (359,967 women) and 1,179,874 (601,736 women) indirect beneficiaries (without overlaps) to gain benefits from upgraded irrigation infrastructure, improved water management, resilient agriculture practices, and provision of climate and weather information. This included 520,000 smallholder farmers (254,800 men and 265,200 women) benefiting from CSA‑based diversified livelihood options; 445,500 (226,950 women) beneficiaries of flood advisories; 122,715 (51% women) drinking‑water beneficiaries within cascades; and 7,618(51% women) CKDu‑risk beneficiaries outside basins. Overlaps of beneficiaries across outputs reflected the integrated nature of interventions and benefits received by individual beneficiaries. A brief overview of the project implementation: The project came into effect on 28 June 2017. Implementation began with the selection of 17 cascades, later expanded to 20 through multi‑level coordination structures. COVID‑19, the economic crisis, and restructuring‑related funding delays significantly slowed progress and prompted a no‑cost extension of the project from June 2024 to December 2025. The Independent Interim Evaluation (2021) rated the project Moderately Satisfactory. From late 2022, implementation accelerated, and all revised targets were achieved without additional cost. Stakeholders: The project was implemented as per the National Implementation Modality (NIM) of the UNDP. The Implementing Partner shifted from the Ministry of Mahaweli Development and Environment (MMDE) to the Ministry of Agriculture, Lands, Livestock, and Irrigation n 18th November 2024. Responsible Parties included the Department of Agrarian Development (DAD), Department of Agriculture (DoA), Department of National Community Water Supply (DNCWS), National Water Supply and Drainage Board (NWSDB), and Ministry of Disaster Management (MoD), supported by national agencies and Provincial Councils. Community organizations—Farmer Organizations (Fos), Community Based Organizations (CBOs), and cascade groups—were central actors. UNDP, as Accredited Entity, ensured oversight, compliance, and reporting. Four Civil Society Organizations including Janathakshan Gte Ltd., South Asia Partnership-Sri Lanka (SAPSRI), Sri Lanka Red Cross, and Palm Foundation, supported local mobilization, and private‑sector entities contributed technical services and co‑financed selected activities. Geographical locations: The project focused on Malwathu Oya, Yan Oya, and Mi Oya River basins across Anuradhapura, Polonnaruwa, Vavuniya, Trincomalee, Kurunegala, and Puttalam Districts. The tank cascade served as the spatial planning unit, with VIS upgrading confined to cascades, CSA and water solutions extending district-wide, and climate‑information interventions applied basin‑wide. 1.2 Contextual Analysis and Relevance of Project/Programme Design At formulation, the project design was strongly aligned with the climate‑vulnerability assessments available at the time (2015), which identified the Malwathu Oya, Yan Oya, and Mi Oya basins as highly exposed to climate risks. The subsequent selection of 20 tank cascades drew on evidence‑based criteria—including poverty incidence, CKDu prevalence, and flood exposure—directly linked to the project’s three outputs and to the populations most in need of integrated water‑management solutions. During implementation, the principal contextual shift was the reduced availability of freshwater sources for drinking‑water infrastructure. As several previously identified sources were allocated to new water‑supply schemes to meet urgent Dry Zone needs by the Government, it decreased Output 2 feasibility and increased treatment costs. This necessitated revising Output 2 beneficiaries from 217,000 to 122,715 and reducing overall direct beneficiary targets from 770, 500 to 705,818. Additional training (74,403 people) partially compensated for the reduced infrastructure coverage. This adjustment assisted with maintaining project coherence and ensured resource efficiency. Despite this adjustment, the original project design remained fully relevant. The 2021 update of Sri Lanka’s NDCs provided strong mid‑implementation validation of the project’s strategic direction. Key national priorities introduced in the updated NDCs—including the adoption of CSA guidelines, rehabilitation of small tank cascades and individual tanks, sustainable land and water‑management practices, rainwater harvesting, crop diversification, improved irrigation water‑use efficiency, and strengthened farmer training—were all core components of CRIWMP. The NDCs also emphasized expanded aquaculture to support food security, rainwater harvesting and groundwater recharge to improve drinking‑water supply, and better water‑allocation mechanisms among farmer organizations. Likewise, priorities in climate‑information services—improved seasonal forecasting, simplified communication to farmers, and strengthened early‑warning systems—directly corresponded to activities implemented under Output 3. Notably, Malwathu Oya, Yan Oya, and Mi Oya river basins were identified among the five national priority basins for integrated river‑basin management and flood‑risk reduction, and Malwathu Oya was selected for assessing river floods, mitigation measures, and flash‑flood early warning—locations where the project installed automated stream and rain gauges. This alignment demonstrated that the project not only remained relevant but was actively operationalizing new national climate priorities as they emerged. The project design also aligned with the National Adaptation Plan (NAP) 2015-2025 and contributed to several NAP objectives. They include: increasing the resilience of the small holder agriculture sector and natural resources associated with village irrigation, minimizing the risk of damage caused by projected short and medium-term changes in climate parameters, building the capacities of communities, village irrigation, and associated ecosystems through supportive investments. The project contributed to improving disaster risk reduction systems (preparation of SOPs, forming village disaster management plans and committees), and increased the preparedness to face the threats from climate change through improved monitoring systems at river basin and irrigation system levels, improved forecasting systems, and effective communication. Awareness and training programs also contributed to the adaptation effort. Contextual changes triggered by the COVID‑19 pandemic and the economic crisis from 2021 to 2022 further shaped implementation. Movement restrictions, disrupted supply chains and income losses significantly affected rural and urban low‑income households, leading to rising food insecurity, including among the urban poor. These shocks delayed construction works, strained institutional capacity, and reduced communities’ ability to undertake routine O&M. However, the project’s integrated strategy—combining CSA, local production, and strengthened water governance—proved adaptable and well suited to addressing these compounded vulnerabilities. To respond to emerging needs, the project adopted timely adjustments consistent with the objective of its original design, i.e strengthening the resilience of smallholder farmers in the Dry Zone through improved water management. A no‑cost extension (18 months from June 2024) was requested to accommodate delays resulting from COVID-19 pandemic and funding delays due to restructuring the project, ensuring that revised targets could be achieved. The women‑led home‑gardening programme was expanded from rural cascade areas to urban and peri‑urban communities affected by food shortages, enabling women to improve household nutrition, reduce expenditure, and generate income during a period of heightened economic stress. These adaptive management actions demonstrated the project’s continued relevance and responsiveness to the needs of the recipient, while reinforcing the resilience‑building principles underpinning its integrated water‑management approach.

# SECTION 2. OVERALL PROJECT/PROGRAMME ACHIEVEMENTS (Maximum Length 5 - 10 pages)

Outcome (Results Framework): Strengthened adaptive capacity and reduced exposure to climate risks. The project targeted 705,818 direct beneficiaries (359,967 women) at the outcome level. Assumptions underpinning this outcome included (i) completion and sustained maintenance of VIS infrastructure, (ii) effective outreach by Agrarian Service Centres (ASCs) to all smallholder farmer families with climate‑risk information and agriculture packages, and (iii) continuing uptake and application of this information by targeted communities. By completion, the project exceeded the outcome target, with total direct beneficiaries surpassing the planned figure, and reaching 804,877 direct beneficiaries (410,411 women). Activities that made these assumptions hold in practice are detailed under the three outputs below. Objective and Fund‑Level Impacts: The project’s objective—to strengthen the resilience of smallholder farmers, particularly women, through improved, integrated water management—translated into demonstrable gains in food and water security, health and well‑being, livelihoods, and local governance for climate risk management. Delivery was organized through three mutually reinforcing outputs. Output 1: Village irrigation infrastructure and capacities of smallholder farmers strengthened for climate-resilient water management and agriculture Upgrading village irrigation systems: The project upgraded 325 VISs (297 village tanks; 28 village anicuts), across 20 cascades, climate-proofing headworks (bunds, sluices, spillways, and desilting the tank bed), and canal systems (irrigation, drainage, spill tail canals, and link canals). This restored storage capacity, stabilized releases, improved conveyance, and reduced flood damage and waterlogging in affected areas—foundational conditions for resilient, reliable production (Indicator reference: VIS upgraded — Target: 325; Achieved: 325). Scaling up climate-resilient farming practices: Across 484 VISs, interventions improved 10,737 ha of asweddumized land, including those outside upgraded and non-upgraded VISs, prioritising improved on-farm water management in command areas. By 2025, average cropping intensity rose from a baseline of 1.0 to 1.76, while 9,839 ha exceeded a CI of 1.60—surpassing the 9,750 ha target —and a further 898 ha reached an average of 1.11 (Project Outcome Level Indicator 1.1: area with CI>1.60—target 9,750 ha; achieved 9,839 ha; average CI—increased from 1.0 to 1.76). 569,214 farmers (290,300 women) were reached through disseminating climate resilient agriculture technology packages (Project Output Level Indicator 1.2: target 520,000 farmers, including 265,200 women). Household diversification complemented command‑area gains: 10,332 rural climate‑smart home gardens—benefiting 10,332 women—were established, and in response to post‑COVID food insecurity, 304 urban and suburban home gardens were added with 58 reported female beneficiaries; agroforestry and agrosilvopastoral packages, including backyard poultry linked to market‑oriented home gardening, strengthened food security and income for 4,857 families. Income effects are evidenced by USD 12,561,866 earned in 2025 by 18,857 farmers from 8,400 ha of irrigated command. Institutionalization anchored results for sustainability. CWRD&MPs and CMCs operationalized whole‑cascade governance; women held 245 of 782 officer positions (31%), improving the quality and inclusivity of water‑resource decisions 77 ASCs functioned as knowledge hubs for water and agricultural advisories, closing the loop between agro-met information and field application. Project Activity 1.1. Improve technical capacity and knowledge management targeting ASCs, local field officials, and community organizations for climate-risk-informed water management and climate-smart agriculture. 77 ASCs were capacitated as knowledge hubs to co-develop and disseminate water management and agro-meteorological advisories to farmer organizations and user groups. The ASCs were equipped with computers, communication facilities, and data and information required for improved water management. A district training pool of 164 officers (79 women)was established through training‑of‑trainers, and 13,485 people including 7,247 women received structured training that covered VIS O&M, cascade planning, on‑and-off-farm water management, catchment restoration, input efficiency, and 16 CSA technology packages ( ASCs strengthened—target 77-achieved 77; district TOT—achieved 164; people trained—achieved 13,485, of whom 7,247 women). Out of the total 782 office-bearers of 20 CMCs, 245 (31%) are women, thus enabling effective participation in decision-making related to water resources management. Project Activity 1.2: Improve the resilience of and upgrade village irrigation systems in the identified cascades, including restoration of the upstream watershed The headworks of 325 VISs in 20 tank cascades were upgraded by the end of 2025, including the upstream watershed of tanks. The progress of canal system upgrading lagged behind that of the headworks but recovered after initial mobilization delays and the work was completed with co‑financing. Additional Government support to 11 tanks—six by the Provincial Irrigation Department (North Central Province) and five by the Irrigation Department in Anuradhapura—totaled LKR 137.1 million (USD 442,250), helping sustain implementation momentum during the 2020–2022 funding delays (target references: VIS headworks upgraded—achieved 325; canal systems—completed). Upstream watershed restoration combined tree planting, soil‑conservation bunds and silt‑trapping ponds; boundaries of VIS ecosystems were demarcated through participatory processes, and the ecosystem conservation, management and governance were assigned to CMCs and FOs. Agroforestry systems were introduced in the tree girdles of 47 VIS, benefiting 1,153 people, while interceptor restoration and drainage‑canal rehabilitation downstream reduced salinity risks and waterlogging; agricultural drainage was improved through renovating existing drainage canals and constructing new drainage facilities; and model interceptor agriculture supported income for 2,351 people. The key sub-activities of VIS upgrading that contributed to climate resilience and sustainability of the investments are as follows: The upgrading followed a structured climate-risk informed cycle designed to ensure long-term resilience and sustainability of investments. It started with an investigation phase, which comprised a community-engaged Preliminary Investigation Report (PIR), strengthened to include critical ecosystem attributes, such as catchment size, spill & flood history, hydrological connectivity, and siltation levels. Soil and topographic surveys further informed and quantified climate‑resilient engineering designs & upgrading. During the design phase, government technical guidelines were complemented with enhanced climate resilient design and supervision criteria, in line with international best practices. Environmental safeguards, biodiversity considerations, and drainage improvements were incorporated into the instructions, while spill‑tail structures were redesigned to ensure unobstructed emergency flows. Comprehensive hydrological analyses explicitly incorporated climate‑change impacts. All designs were validated with custodial agencies and farmers and communicated in local languages to ensure ownership. The construction and defect-liability phase followed strengthened environment, health, and safety (ESH) procedures, with partial desilting incorporated to maintain ecological balance. Quality assurance was ensured through joint inspections with FOs and custodian institutions. Following the defect & liability period, completed works were formally handed over for community and institutional stewardship. The Operation and Maintenance (O&M) phase consolidated sustainability. Each upgraded VIS received a detailed O&M plan, outlining scientific operation of the system using depth-area-capacity curves, structural and ecosystem maintenance routines, climate‑informed decision‑making using weather forecasts and advisories, and assigned responsibilities down to the individual farmer. Flood‑safety functions, particularly the unobstructed release of spill waters, were integrated into maintenance protocols. Financial sustainability was supported through structured O&M financing arrangements and the provision of O&M equipment to all 100 FOs across 20 cascades. Gender equality: Gender considerations were systematically integrated throughout the VIS upgrading cycle. Women were trained in FO activities (13,108), construction supervision (345), participatory monitoring (260), water management (6,319), and maintenance of irrigation facilities (2,218), ensuring their direct involvement in planning, design validation, and oversight of works. Participatory monitoring committees required at least 30% women and youth, ensuring their perspectives shaped construction and quality assurance. Infrastructure improvements incorporated gender‑responsive design features, including accessible and gender‑segregated bathing steps. To address barriers limiting women’s participation in traditional FO structures, women’s FOs were formally integrated into CMCs through the DAD Circular of 2023, which enabled the participation of a representative from each of the women's FOs, supporting their sustained leadership in water‑resource governance. Project Activity 1.3: Develop and disseminate climate-resilient agricultural practices with targeted enterprise development for women. Project Activity 1.3 strengthened climate‑resilient agriculture both inside and outside irrigated command areas, while expanding livelihood opportunities—particularly for women—through diversified production systems and targeted enterprise development. Outside the irrigated command, interventions focused on agroforestry, climate‑smart home gardening, and upland cultivation as pathways to diversify household food systems and reduce climate risk. Agroforestry systems were introduced in the upper catchments, benefiting 2,351 people, and improving ecological stability around the VISs. The project established 10,332 rural climate‑smart home gardens, directly benefiting 10,332 women, and in response to COVID‑related food insecurity, an additional 304 urban and suburban home gardens were created, benefiting 58 women. These home gardens contributed directly to household nutrition, reduced food expenditure, and created income‑earning opportunities for women. Across the project’s seven districts, 569,214 farmers (254,395 women) received agricultural technology packages through 77 ASCs. These packages included upstream erosion control, tree girdle development, construction of silt traps, and downstream interceptor improvements, which not only enhanced agricultural practices but also supported the long‑term sustainability of irrigation infrastructure. Inland fish farming was promoted in small tanks and ponds as a complementary livelihood option. A suite of climate‑resilient production systems—including polytunnel‑based agriculture, shaded net‑house cultivation, integrated animal husbandry and biogas production, commercial fruit cultivation, and Chena improvement units—enhanced economic resilience. The agrosilvopastoral system, combining trees, crops, and livestock (poultry, cattle & goat), strengthened household food security and supported market‑oriented home gardening, benefiting 4,857 families. Within the irrigated command, improved water-use efficiency was achieved through AWD in 32 VISs, benefiting 3,755 farmers, supported by floating gauges and sensor‑based lighting systems. Additional on‑farm measures included plot consolidation and land levelling, laser levelling, deep ploughing, row seeding, the parachute method, organic paddy cultivation, and bund cultivation to enhance biodiversity and productivity. The promotion of low‑water‑demand cash crops, such as green gram in the mid‑and-Yala seasons, helped raise cropping intensity. Integrated plant nutrient management improved fertilizer‑use efficiency through combined organic and chemical applications. The project’s climate‑smart home garden model served as a key intervention for women’s empowerment. Market access was strengthened through farmers’ markets (508 beneficiaries at the district level; 885 at the divisional level), mobile markets, and roadside ecological market units (443 beneficiaries). Women engaged in enterprise development through seed and planting‑material units (3,823 beneficiaries), paddy seed units (864 beneficiaries), cereal and spice processing units (777 beneficiaries), and commercial nursery units (8 forest nurseries; 24 vegetable/fruit nurseries). These enterprises enabled women to participate in upstream and downstream agricultural value chains. Wild elephant‑repellent biological fences—benefiting 591 households—reduced human–elephant conflict while incorporating commercially valuable repellent crops. Additional climate‑smart energy solutions included 35 biogas units and solar pumps for agricultural enterprises. Aquaculture development further strengthened food and livelihood security. By project end, aquaculture was introduced or expanded in 60 tanks, benefiting 4,490 people, supported by 20 inland fish ponds and two ornamental fish‑feed processing units, with continued uptake by farmers. Gender equality: Women were central to CSA dissemination and enterprise expansion. By project completion, 290,299 women had benefited from CSA technology packages. To sustain women’s economic participation, the project supported the establishment of a rural women’s business forum, comprising representatives from seven district‑level social enterprises supporting over 1,000 women entrepreneurs. Three mobile markets and two farmers’ markets enhanced value‑chain access for approximately 900 women‑managed home gardens, providing reliable outlets for climate‑smart produce. Women‑headed households were prioritized in beneficiary selection for nursery units and enterprise support, ensuring equity in access to productive assets and market opportunities. These interventions collectively strengthened women’s climate resilience, enhanced their economic agency, and diversified their livelihood portfolios. Output 2: Improved access to safe and reliable drinking water through supply systems able to withstand climate change and variability Output 2 strengthened household and community resilience to climate‑induced water scarcity by delivering safe, reliable water services and the systems to sustain them. By completion, 128,537 people (63,740 women) benefitted—103% of the revised target of 122,715—through a diversified package of climate‑resilient solutions, including community‑involved pipeline extensions (25,842 beneficiaries (13,179 women)), LAWFs (7,197 with 3,670 women), SAWF units for schools and health centres (62,779 in schools (30,203); ), new CWSSs (12,375 with 6.311 women), and household and school RWH systems (16,012 (8,166 women) in households; 4,332 (2,209 women)in schools). These investments reduced exposure to unsafe water (including CKDu‑related risks), improved well‑being and productivity, and created substantial time‑use gains for women and girls. Specifically, 31,326 women collectively saved 5,133,409 hours per year (valued at USD 2,156,032 under agriculture‑related opportunity‑cost assumptions), with additional benefits from children’s time saved for schooling. (Output-Level Indicator: People with climate‑resilient access to safe drinking water — Target: 122,715; Achieved: 128,537(63,740 women) (103%). Project Activity 2.1: Improve the capacity of water-supply support staff at district/divisions, selected partner organizations (NGOs) and CBOs to implement and maintain community-based Drinkwater-related interventions Capacity building underpinned the durability of Output 2 results. A total of 67,958 persons (31,232 female) were trained across the service chain—O&M, water quality management, governance, and safe water behaviours—through programmes delivered with National Water Supply & Drainage Board (NWSDB) and Department of National Community Water Supply (DNCWS). This included district-wise training-of-trainers (TOT) (3,384); field training in O&M of the RWH systems in households and in schools (7,447); and technical/governance training for CBOs, user groups, monitoring committees, and households (24,500 beneficiaries). Teachers and schoolchildren (28,402 participants) received practical WASH and safe‑water training, and 4,225 community representatives participated in the NWSDB pipeline‑extension monitoring process. The TOT cohort included 161 women out of 316, forming district resource pools; cumulatively, by end‑2024, 18,234 women had been trained in drinking‑water management, with 9,241 managing/maintaining CWSS and 1,357 managing RWH systems. Gender impact: Prioritizing women’s participation enabled more women to engage in managing and maintaining water assets at the community level. Time saved from closer water access was reallocated to income generation, household care, and education, reinforcing resilience and agency. Project Activity 2.2: Implement sustainable, climate-resilient drinking water solutions through CBOs and government agencies Delivery focused on fit‑for‑context systems that perform under climate variability and can be locally maintained. The project established 7 new CWSS covering 2,472 households (HH) benefiting 12,375 people (51% female) and completed 16 community-involved pipeline extensions/sub projects, serving 5,874 households (HH) and benefitting 25,842 people (51% female) with GoSL funding in partnership with the NWSDB. Community contribution to pipeline extensions was in providing labour for trench excavations and pipe laying. To augment supply and improve quality in dispersed and water‑scarce locations, the project installed 4,003 household RWH systems benefiting 16, 012 people (51% female) and 49 school RWH systems benefiting 4,332 students. For areas with poor water quality, 12 LAWFs served 7,197 people, while 89 SAWFs enhanced safety for 58,349 persons in schools and 4,430 health‑facility users. The sustainability of the water sources used for drinking was enhanced by Climate Resilient Water Safety and Security Plans (CRWSSP), which improved source protection, quality assurance, and O&M accountability. These plans are proactive risk-based frameworks designed to ensure consistent and adequate water supply despite climate-induced threats like flood and drought, and they are implemented by water CBOs. Groundwater management planning and recharging enhanced aquifer reliability during droughts. Complementary school WASH programmes benefitted 6,225 children, further improving health outcomes and reinforcing safe‑water behaviors. Gender equality: Women‑headed households were prioritized for RWH, new CWSS connections, and pipeline extensions. The project trained 10,598 women to operate and maintain water‑supply systems, including 9,241 women for CWSS and 1,357 for RWH, expanding women’s technical leadership in community water governance. Separate time‑use tracking recorded 28,519 hours saved per day for women and girls on average (~1.3 hours/day per person), reflecting the scale of productivity and education gains enabled by proximate water access; a complementary analysis for a defined cohort found 31,326 women saving 5,133,409 hours/year, valued at USD 2,156,032. Output 2 exceeded its beneficiary target while building the institutional capacity and risk‑management systems needed to keep services safe and reliable under climate stress. Results contribute directly to the GCF Adaptation Core Indicator A1.0 on increased resilience and enhanced livelihoods (contributing to project’s overall direct beneficiaries), and to project‑level outcomes on reduced exposure to waterborne health risks, time savings for women and girls, and enhanced local capacity for climate‑resilient service delivery. The combination of diversified systems (CWSS, filtration, RWH, extensions), CRWSSPs, groundwater planning, and trained O&M cadres demonstrates a fit‑for‑purpose, scalable model for water security under climate variability. Output 3: The capacity of Dry Zone farmers strengthened to use weather and climate information for agricultural and water management Output 3 strengthened the capacity of Dry Zone farmers and institutions to anticipate, prepare for, and respond to climate risks by expanding access to reliable weather, climate, and hydrological information and integrating this information into agricultural and water‑management decisions. By completion, 465,911 people (237,615 women) benefited from these services—achieving the full target for climate‑information beneficiaries (Output-Level Indicator 3.1: Number of female and male farmers reached through seasonal forecast for agriculture planning– Target: 445,500 (265,200 are women); Achieved 465,911 (237,615 are women). The project established the infrastructure, digital platforms, institutional processes, and community‑level systems required for effective drought and flood monitoring, climate‑informed cropping decisions, and risk‑responsive water management. Farmers gained regular access to district‑level agro‑meteorological advisories co‑developed with ASCs; cascade‑level institutions used new tools for flood preparedness; and decision‑makers gained real‑time insights through the Warisoba platform, hydrological models, and monitoring networks. These measures strengthened anticipatory adaptation capacities and reduced exposure to climate hazards. Output 3 contributed directly to Outcome indicators on reduced climate‑risk exposure, enhanced early‑warning reach, and adoption of climate‑informed farming and water‑management practices. Key activities Project Activity 3.1: Establish effective monitoring systems for drought, floods and water management The project delivered a comprehensive hydrometeorological monitoring architecture across the Dry Zone, by installing 23 automated stream gauges and 5 agro‑meteorological stations, combined with manual rain and water‑depth gauges across all upgraded tanks, significantly enhancing flood- and drought‑monitoring precision Linking the project-supported stream gauges with the “Warisoba” mobile application, in close coordination with the Irrigation Department, enabled real‑time river‑level monitoring, supporting both community and institutional flood‑management decisions. During Cyclone Ditwah (November 2025), FOs used these systems to track inflows—and no CRIWMP‑upgraded tanks breached, demonstrating tangible resilience gains. The project collaborated with the Irrigation Department to develop rating curves for key gauging stations, enabling more accurate river discharge measurement and flood-inundation forecasting. Standard Operating Procedures (SOPs) for drought, floods, and reservoir management were completed in all three river basins, strengthening coordination among agencies. The Project supported two major digital systems, which are new approaches in Sri Lanka: - A DMC–Irrigation Department web interface for data sharing and coordinated early warnings. - RiverNet, an upgraded public-facing platform of Warisoba that will allow basin-wide access to real-time flood data. These systems (“Warisoba” application and two digital systems being finalized) are innovative approaches in the DRR system of Sri Lanka, and have significantly improved the capacity of farmers, FOs, cascade committees, and government agencies to make anticipatory, risk‑informed decisions about cultivation timing, reservoir releases, and emergency response. Project Activity 3.2: Co-develop and disseminate weather- and climate-based advisories for agricultural and water management through ASCs and FOs to farmers and village water managers The agro‑met advisory programme institutionalized a co-development process involving ASCs, DoA officers, and farmer leaders. District‑level committees co-developed seasonal advisories for both Yala and Maha, supported by a digital agro‑met advisory portal. The portal integrates weather forecasts, tank water levels, and cropping recommendations and automatically generates district advisories, which officers refine with local knowledge before dissemination. Advisories were then disseminated through ASC-led training programmes, FO meetings, and mobile channels. User‑friendly training materials—including flipcharts, flash cards, and booklets—were provided to the district trainer pool. The project’s innovations were recognized by the Ministry of Environment (UNCCD focal point) and selected as a UNCCD best practice case study, validating their quality and replicability. The system increased farmers’ ability to choose climate‑appropriate crop varieties, manage water efficiently, and avoid losses from extreme events. It also enhanced institutional capacity for routine climate‑risk communication—a critical element of long-term adaptation. Project Activity 3.3: Develop climate-risk management and response measures to advisories and forecasts for agriculture, water management, and flooding in cascade systems Project Activity 3.3 strengthened multi‑level climate‑risk management systems across the three river basins, enabling farmers, cascade institutions, and local authorities to translate weather and hydrological information into clear, actionable responses for agriculture, water management, and flood preparedness. The activity directly contributed to Output 3 results, which reached 465,911 beneficiaries (237,615 women), measuring full achievement under the Output‑level indicator on population using climate information for decision‑making. A major achievement was the development of a comprehensive flood and water‑management model for the Mi Oya basin, completed with the Irrigation Department (ID), the University of Peradeniya (UoP), and the University of Sabaragamuwa (UoS). The model integrates a hydrological model, reservoir‑operation module, hydraulic model, and real‑time simulation capability using open‑source HEC software. It provides real‑time flood forecasts linked to reservoir operations, enabling proactive management of irrigation releases and downstream risks. The model was calibrated using 2024 flood data and verified by the ID. The project provided a full hardware suite—computers, displays, accessories—and conducted a five‑day intensive training for irrigation officials to ensure operational use. This modelling approach is now planned for replication in 22 additional river basins through World Bank support under the CresMPA project, demonstrating strong scalability and national uptake. To reinforce early‑warning capabilities, the project equipped the Disaster Management Centre (DMC) with smart displays, laptops, and printers at the Emergency Operations Centre (EOC) and district units. Mobile numbers of households in flood‑affected GNDs were integrated into the DMC’s automated early‑warning system, enabling direct SMS‑based flood alerts and strengthening last‑mile dissemination. At the divisional level, the project strengthened preparedness systems by supporting DSDs to develop Divisional Disaster Preparedness and Response Plans in 7 project districts, guided by a technical manual prepared under the project. Capacity‑building workshops trained officials to identify local hazards—including floods, droughts, and wild animal attacks—and plan coordinated responses. GND‑level disaster preparedness planning was completed in project cascades and 29 schools, enhancing institutional readiness across vulnerable locations. To institutionalize flood risk governance, flood event management SOPs were prepared for all 3 river basins, clarifying coordination pathways among institutions involved in flood management and to streamline the roles and responsibilities as per the existing mandates of the organization. The SOPs were reviewed and validated by a national-level technical review committee. Comprehensive household‑level flood‑risk assessments were conducted across the three river basins, covering roughly 69,000 households. The assessments identified 25 DSDs (191 GNDs) as flood‑vulnerable. These DSDs subsequently prepared Divisional Disaster Risk Management Plans (25) supported by Divisional Disaster Management Coordination Committees (DDMCs), and each division received emergency response equipment to strengthen preparedness. The resulting Flood Vulnerability Database is now being used for emergency operations, long‑term risk reduction, and development planning. GIS training was provided to district and divisional stakeholders to enable continued use and updating of spatial data. At the community level, the project facilitated the development of 47 GND‑level Disaster Preparedness Plans in the 20 cascades. These plans were supported by training for Village Disaster Management Committees (VDMCs), first‑aid and camp‑management sessions, safety‑location improvements, and early‑warning enhancements. FOs also identified and implemented small‑scale structural mitigation works—including spill‑canal repairs and drainage improvements in Kurunegala, Puttalam, and Trincomalee—that reduced local flood impacts and protected agricultural assets. A cascade‑level Flood Management SOP was developed to integrate upstream–downstream hydrological linkages, and farmer‑training programmes were delivered to operationalize it. The project further strengthened disaster preparedness in education facilities, supporting 29 schools to develop School Disaster Preparedness Plans and form School Disaster Management Committees, completing minor repairs and receiving first‑aid kits and other emergency supplies. Finally, the project developed a TOT Manual for Disaster Preparedness and Flood Response Planning and trained divisional‑level officers, NWSDB and NCWS staff, and Drinking Water CBO members to apply climate‑preparedness practices within their own service areas. Hands‑on guidance ensured these CBOs were able to incorporate emergency‑response procedures into Drinking Water Safety and Security Plans. Integrated approach: The project’s integrated design ensured that all three outputs reinforced each other, generating results far greater than the sum of their parts. Output 1—focused on climate‑resilient agriculture and irrigation—was significantly strengthened by Output 3, which equipped farming communities and government agencies with scientific, localized climate information. Seasonal forecasts, early warnings, and agrometeorological advisories enabled farmers to plan cultivation cycles more strategically, optimize water use, and safeguard critical irrigation structures during extreme weather events. At the same time, Output 2’s improved access to safe, reliable drinking water—particularly for women—created tangible social and economic impacts. With reduced time spent on water collection and improved health and well-being, women were able to participate more actively in income‑generating activities, including agriculture. This, in turn, helped maintain household productivity and strengthened community resilience. Collectively, the outputs worked in harmony to reinforce climate‑smart livelihoods, enhance water security, and increase the overall adaptive capacity of Dry Zone communities. Gender equality: Women, who are disproportionately affected during climate‑induced disasters, experienced a marked improvement in safety, agency, and participation as a result of the project’s targeted gender‑responsive interventions. Through flood preparedness and response systems, women gained timely access to early warnings via mobile alerts and community platforms—empowering them to take proactive measures to protect their families, assets, and livelihoods. Gender‑responsive school disaster preparedness plans further strengthened safety nets for children and enhanced women’s leadership roles in community preparedness. The project also invested in building women’s technical and decision‑making capacities. Women were trained to monitor rainfall and reservoir water levels, operate and maintain equipment, and use climate information to guide agricultural and household decisions. By equipping women with the skills to interpret seasonal forecasts, access agrometeorological advisories, and apply climate‑smart practices, the project fostered greater confidence, economic participation, and leadership. These interventions not only reduced gendered vulnerability but also positioned women as active contributors to climate resilience and community disaster‑risk management. Performance against logical framework indicators Adaptation core indicator 1: “Total number of direct beneficiaries of GCF funded project/programme” and Adaptation Impact Indicator Fund level Impact: A 1.0 Increased resilience and enhanced livelihoods of the most vulnerable people, communities, and regions: Total number of direct beneficiaries By the end of the project, a total of 804,877 (of whom 410,753 are women) direct beneficiaries were reached by the project. This is an achievement of 114% against the target of 705,818. Avoiding overlaps, these beneficiaries were composed of: - Farmers reached through the dissemination of agriculture technology packages in 77 Agrarian Service Centre (ASC) areas, - Drinking water beneficiaries from new CWSS, new RWH facilities, community involved pipeline extensions, and those in schools & hospitals, - Men and women who received water management advisories (i.e., disaster preparedness, flood advisories, water management) (186,364 non-agricultural communities also benefited) - Beneficiaries from various capacity building and training programmes conducted under three outputs Adaptation core indicator 2: Total number of indirect beneficiaries of GCF funded project/programme By the end of the project, a total of 1,179,851 (of which 601,736 are women) indirect beneficiaries were reached by the project. This is an achievement of 102% against the target of 1,157,552. This comprised beneficiaries reached through the 91 Agrarian Services Centres (ASCs) in the seven project districts and outside the river basins by disseminating climate-smart agriculture and drought advisories (465,911), and those who received SMS based early warnings (565,328). Adaptation Core Indicator 3: Number of total beneficiaries relative to total population By the end of the project, the share of direct beneficiaries relative to the total population was 3.7%. The share of female direct beneficiaries relative to the total population was 1.9%. The share of indirect beneficiaries relative to the total population was 5.4%, out of which the female indirect beneficiaries comprised 2.8% of the total population. Fund level Impact A 1.0: “Increased resilience and enhanced livelihoods of the most vulnerable people, communities, and regions”, Indicator 1.2 : “Number of males and females benefiting from the adoption of diversified, climate-resilient livelihood options” The progress against this indicator at the end of the project was 569,214 (of which women were 290,299), against a target of 520,000 (265,200 women). Accordingly, the achievement was 109% of the target. Fund level Impact A 2.0 Increased resilience of health and well-being and food and water security, Indicator 2.3 “Number of males and females with year-round access to reliable and safe water supply despite climate shocks and stresses”: target 453,118 (230,090 women). Achievement 465,911 (235,691 women) Outcome 7.0 Strengthened adaptive capacity and reduced exposure to climate risks. Outcome level indicator A7.1 “Extent to which vulnerable households and businesses use improved strategies and activities to respond to climate variability and climate change” (Target 770,500 392,955 women; Achievement 805,877 of which 410,753 are women) Project-level achievements are summarized as follows: Output 1. Upgrading and enhancing the resilience of village irrigation systems and scaling up climate-resilient farming practices in three river basins of the Dry Zone Indicator 1.1 Outcome Level- The extent of minor irrigation under targeted cascades with increased CI (CI more than 1.6): Target 8,875 ha, achievement 9,839 ha Indicator 1.2 (Output level)-Number of male and female farmers reached through disseminating the climate-resilient agriculture technology packages: Target 520,000, of which 265,200 are women, achievement 569,214 (of which 290,300 are women) Indicator 1.3 No. of women farmers implementing climate-resilient agriculture technologies and practices: Target 16,677, Achievement 21,749 Output 2-Improved access to safe and reliable drinking water through supply systems able to withstand climate change and variability Indicator 2.1 Number of HH with year-round access to reliable and safe water supply: Target 122,715 (62,584 women), Achievement 128,537(63,740 women) Indicator 2.2 Number of women engaged in managing and maintaining community drinking water supply schemes: Target 20,000, Achievement 9,241 Output 3. Capacity of Dry Zone farmers strengthened to use weather and climate information for agricultural and water management Indicator 3.1 Number of female and male farmers reached through seasonal forecast for agriculture planning: Target 520,000, of which 265,200 are women . Achievement 569,214 (290,299 women) Indicator 3.2 Number of female and male farmers receiving advisories for water management: Target 445,500, of which 227,205 are women, Achievement 465,911, of which 237,615 are women Brief description of the performance against the GCF Investment Criteria - Impact Potential The project’s impact is demonstrated by its contribution to transformative adaptation in Sri Lanka. The project delivered demonstrable, measurable, and systemwide climate‑resilience benefits across Sri Lanka’s Dry Zone. By integrating irrigation system upgrading, CSA, ecosystem, surface and groundwater management, decentralized drinking water solutions, and disaster preparedness and risk reduction at the cascade level, the project directly strengthened the adaptive capacities of highly vulnerable smallholder communities. Collectively, these achievements substantiate the project’s strong contribution to GCF’s objective of delivering large‑scale, climate‑resilient development impacts. - Paradigm‑Shift Potential The project catalysed a fundamental shift in Sri Lanka’s approach to climate adaptation by demonstrating that water, agriculture, disaster risk reduction, and ecosystem management can—and must—be planned and executed as a single integrated system. Key transformative achievements include: - Introduction of IWRM-aligned, community-centered cascade governance, bringing all water-users into shared decision-making and resource management. - Mainstreaming groundwater management and drinking water solutions—components rarely included in irrigation-based development projects—into Dry Zone climate planning. - National-level replication driven by evidence: - The World Bank’s Climate Smart Irrigated Agriculture Project (CSIAP) adopted the CMC model. - IFAD’s SARP replicated integrated water management innovations. - The DAD issued a Circular encouraging the establishment of CMCs island-wide. - National guidelines for CSA and Water Safety and Security Planning (WSSP) were informed by CRIWMP and now guide countrywide practices. - The agro-meteorological advisory dissemination system and digital river-level monitoring platform are now positioned for national scale-up. These results reflect a meaningful shift in how climate‑resilient water and agricultural systems are governed, embedding practices and institutions that will continue to guide decision‑making well beyond a one-off project investment, ensuring a paradigm shift in how climate adaptation is approached in Sri Lanka. Independent evaluations confirmed this paradigm shift: - The International Water Management Institute (IWMI) assessment (2024), across six countries, recognised the project’s CMCs and CSA work as transformative adaptation interventions, demonstrating replicability and technical soundness. - The UoP Impact Evaluation (2025) found that upgraded village irrigation systems (VIS) and CSA practices significantly increased agricultural productivity, diversified crop portfolios, and improved household income stability. - Sustainable Development Potential The project delivered substantial and mutually reinforcing environmental, social, and economic co‑benefits, illustrating its strong sustainable development potential. Environmentally, the restoration of the tank‑cascade ecosystems revitalized watershed health by improving natural drainage patterns, enhancing groundwater recharge, and strengthening local climate regulation functions. These ecosystem gains were complemented by the adoption of AWD in paddy cultivation, which not only reduced water consumption but also contributed to lowering greenhouse gas emissions. The project’s interventions in flood‑risk management—particularly improved drainage and protective infrastructure—further reduced climate‑induced damages and strengthened the resilience of vulnerable communities. Social outcomes were equally transformative. By providing reliable, year‑round access to safe drinking water, the project significantly improved community health and reduced the prevalence of water‑borne diseases. School‑based WASH programmes enhanced the well-being of students while embedding good hygiene practices across generations. Investments in disaster preparedness—including the development of school disaster‑management plans and improved access to early warning systems—contributed to heightened community safety and more proactive climate‑risk responses, especially in flood‑prone areas. Economically, the project catalysed a shift toward more resilient and diversified rural livelihoods. Climate‑resilient agriculture technologies, commercial fruit production, integrated livestock systems, and strengthened market linkages enabled households to diversify incomes and increase economic stability. The emergence of micro‑enterprises and eco‑tourism initiatives expanded local economic opportunities beyond traditional agricultural systems. Importantly, the reduced burden of water collection—particularly for women—freed up time for productive activities, enabling greater participation in income‑generation and entrepreneurial ventures. Evidence from the UoP’s Impact Evaluation further underscored these results. Crop diversification increased markedly within project cascades, with fruits and vegetables comprising up to 52% of cultivated area—a sharp departure from the mono‑cropping patterns typical in non‑project cascades. This diversification improved household nutrition, enhanced climate resilience, and strengthened income stability. Women, in particular, benefited from new livelihood avenues, improved access to resources, and increased economic participation, reflecting the project’s strong gender‑responsive design. Taken together, these environmental gains, social improvements, and economic opportunities demonstrate that the project delivered deep and lasting sustainable development benefits. - Needs of the Recipient The project was well‑targeted to address Sri Lanka’s high climate vulnerability, acute rural poverty, chronic water scarcity, and limited climate information services. The selection of project locations—among the country’s most climate‑exposed—was validated during the economic crisis, when these areas faced heightened risks but also significant potential for climate‑resilient transformation. By focusing on vulnerable groups—including people with disabilities and women‑headed households—the project strengthened equity and inclusion. The funding modality allowed continuity of development gains during a period when Sri Lanka faced reduced access to external financing, ensuring uninterrupted progress. - Country Ownership Country ownership was strongly embedded from design to implementation: - The project aligned with major national frameworks—the National Climate Change Policy, National Adaptation Plan, National Climate Change Adaptation Strategy, and both the original and updated NDCs (2021). - Capacity‑building investments were absorbed into institutional systems, with responsible agencies adopting training curricula, guidelines, and operational tools. - The Government fully met its co‑financing commitments, even amidst economic constraints, and allocated additional funding for VIS upgrading after seeing farmer demand and the model’s effectiveness. - Adoption of the CMC model by national authorities for replication across all cascades is a powerful demonstration of ownership and institutionalization. - Partnerships with CSOs strengthened community mobilization, social inclusion, and long‑term sustainability. - Efficiency & Effectiveness The project delivered cost‑effective, high‑impact results through: - Integrated planning that maximized returns across sectors (water, agriculture, disaster, ecosystems). - Energy‑efficient infrastructure: solar‑powered LAWFSs in rural water schemes and 36 schools reduced electricity costs and ensured uninterrupted service delivery in a context of frequent energy shortages. - Strengthened community O&M capacity, which reduced long‑term operational burdens and enhanced sustainability. - Leveraging digital systems for agro‑met advisories and hydrological monitoring, which enhanced service efficiency for government agencies at low incremental cost. Taken together, the project’s achievements reflect a strong overall performance across all GCF Investment Criteria. CRIWMP has generated verifiable and scalable adaptation results, accelerated Sri Lanka’s transition toward integrated climate‑resilient water management, delivered measurable environmental and socio‑economic benefits, responded effectively to the country’s most acute climate risks, and has institutionalized practices and capacities essential for sustained country‑owned adaptation.

# SECTION 3: PERFORMANCE AGAINST THE GCF INVESTMENT CRITERIA (Maximum Length 3-10 pages).

Provide a performance assessment of the project/programme against each of the GCF investment criteria (B.09/05) below along with gender considerations as indicated in the investment criteria. While the initial assessment provided in the Board-approved funding proposal was an ex-ante assessment based on forecasts, this section should give an ex-post assessment of the project/programme based on actual results attained at the time of project/programme completion. Elaborate on any deviations observed between the forecasts and actual results attained and reasons why such deviations occurred. Refer to some additional guiding questions for each criterion. 3.1 Impact Potential Impact potential is referred to the potential of project / programme to contribute to the achievement of GCF's objectives to promote low-emission and or climate-resilient sustainable development pathways via GCF mitigation and or adaptation result areas. Describe how (i.e. in what ways or through which strategies etc.) the project/programme was able to achieve or contribute to the actual results reported in Annex 1.1 (reporting template for Fund-level core and impacts indicators) and whether the targets set for applicable Fund-level core and impact indicators in the funding proposal were realistic along with key reasons for deviations if any. At formulation, the Dry Zone faced increasing climate variability and extremes—more intense rainfall and flash floods, prolonged droughts, shifting monsoon timing, degraded watersheds, and stressed irrigation assets. Inadequate, farmer‑friendly climate and hydrological information services further heightened vulnerability, while limited, timely access to safe drinking water exacerbated food, water, and health insecurity and contributed to temporary migration and social disruption. The project addressed these constraints through an integrated package at cascade level: (i) VIS upgrading and climate‑smart agriculture (CSA) to stabilize production; (ii) decentralized water supply solutions and rainwater harvesting to secure household & community level safe drinking water; and (iii) observing, forecasting and advisory systems to enable risk‑informed decisions in agriculture and water management. This bundle improved water availability and use‑efficiency, reduced climate‑related losses, and enabled farmers and service providers to plan, allocate, and safeguard water based on seasonal and short‑term forecasts. Results against Fund-level core and impact indicators (Annex 1) - Overall, the targets set for applicable Fund-level core and impact indicators in the funding proposal were realistic, and results reported in Annex 1 are relevant. - Direct and Indirect Beneficiaries: The project directly reached 804,877 people (51% women) with measures that enhanced climate resilience and indirectly benefited 1,179,851 people through advisory services disseminated via ASCs in project districts. - Strengthened Adaptive Capacity of Vulnerable Households: In the command area (10,737.3 ha), cropping intensity increased from 1.0 to ~1.76, supported by CSA packages such as AWD, Integrated Plant Nutrient Systems (IPNS), micro‑irrigation, and land levelling. Assessments in 2024 show up to 27% water savings under downstream demonstrations (AWD plot consolidation, laser levelling, deep ploughing), enabling reallocation of saved water to other field crops and, in some locations, an additional short season. - Household Food & Nutrition Security: From 2019 onwards, 10,332 climate‑smart rural and 304 urban home gardens were established; during COVID‑19, these covered ~40% of annual household vegetable needs, improving diet diversity and buffering supply shocks. - Water Security for Livelihoods & Households: VIS upgrading increased storage (≥10% minimum gain), while hydrological analyses optimized spillway discharge to withstand extreme events; upstream ecosystem measures (filter and sediment traps) reduced siltation and sustained tank capacity; recharge interventions supported groundwater availability. On/off‑farm water management instruments (gauges, area‑capacity curves, canal discharge gauges, rain gauges) and seasonal/short‑term advisories enabled risk‑informed cultivation planning and day‑to‑day water decisions. Independent evaluation evidence indicates that higher tank storage stabilized local water tables, supporting domestic and irrigation wells during dry spells and reducing reliance on distant sources. In Etha Bendi Wewa and Kadawala, 36% of households reported using time saved from improved drinking water access for income‑generating activities; in Siwalakulama and Palugaswewa, 76–79% of households used the saved time for essential care and household management, strengthening resilience at the household level. - Health: Extensions to pipe networks, rural water schemes, rainwater harvesting, and filtration improved access to safe drinking water and reduced water‑borne disease risks. The independent evaluation observed better water quality—marked improvements in Total Dissolved Solids (TDS), salinity, and Electrical Conductivity (EC) compared to traditional dug‑well sources—from rainwater harvesting and advanced filtration; emerging research signals downward trends in CKDu in some areas, to which safe water provision plausibly contributed. - Livelihoods and Time‑Use: Year‑round potable water access reduced travel and collection time—particularly for women—freeing time for income‑generating activities; in several cascades, a significant share of households reported using saved time for income or essential care work. The evaluation confirms higher production, incomes, and diversification attributable to project interventions. - Institutional Capacity & Asset Base: 325 VIS were upgraded and handed over to FOs with O&M plans and financing arrangements; equipment packages were provided to 80 FOs. Community assets expanded through farmer/roadside markets, seed and food processing facilities, and drinking‑water infrastructure (AWF units, RWH systems), strengthening service continuity and local value addition. - Gender Equality & Social Inclusion: The project systematically targeted marginalized groups (women‑headed households, persons with disabilities, elderly‑headed households). Agricultural technology packages reached 569,214 women; 21,749 women implemented them in 20 cascades (exceeding the 16,667 target). More than 13,000 women received training on water management, catchment restoration, and O&M of VIS; ~6,300 women and youth were trained on technical allocation SOPs and advisories. By 2025, 245 women served on CMC committees, shaping IWRM decisions; ~2,100 women were trained in VIS O&M, with ~2,400 women actively engaged in O&M roles. Women accessed markets, entered value‑addition and micro‑enterprise, and benefited from time savings and home‑garden yields—translating into improved household consumption and investments in education. - Ecosystem Services: Ecosystem investments (upstream tree belts, reed beds, downstream interceptors, agroforestry) across ~297 tanks improved biodiversity, sediment control, and hydrologic regulation. Fish ladders at spillways supported aquatic connectivity. Critically, the project made ecosystem stewardship an operational responsibility by incorporating conservation tasks for FOs/CMCs in O&M Plans and Cascade Water Resources Development & Management Plans, supported by training—a structural change that sustains ecosystem services beyond the project period. CSA practices (especially AWD) lowered water use and reduced GHG emissions while improving soil health; productivity gains were achieved without bringing significant new land under cultivation, minimizing environmental footprint. Results reported in Annex 1.1 were achieved through integrated, mutually reinforcing interventions, with quantitative outcomes triangulated by administrative records, advisory dissemination logs, and independent evaluation evidence (productivity, diversification, income, water tables). Overall, targets were realistic for the operating context. Where minor deviations occurred, they are explained in Annex 1.1 (e.g., timing effects from macroeconomic disruptions; sequencing constraints between infrastructure completion, advisory uptake, and seasonal calendars), with corrective actions documented. By coupling risk‑informed water management, climate‑smart production systems, and institutionalized O&M and ecosystem stewardship at the cascade level, the project delivered evidence‑based adaptation outcomes at scale and anchored new practices within local institutions. Tangible behavior and time‑use shifts are noted in Etha Bendi Wewa, Kadawala, Siwalakulama, and Palugaswewa cascades. Independent assessment corroborates that these changes—higher and more stable production, diversified livelihoods, improved water security, and strengthened decision systems—reflect durable shifts in adaptation capacity at household, community, and service‑provider levels. 3.2 Paradigm shift potential The project demonstrated clear paradigm shift potential, catalysing systemic changes that extend well beyond a one‑off investment. By operationalising an integrated, climate‑resilient cascade management model, CRIWMP introduced new technical standards, governance mechanisms, and information systems that are now being institutionalised, replicated, and scaled nationally. Scaling up/replication CRIWMP’s integrated approach—bringing together irrigation, drinking water, CSA, ecosystem management, and climate information—was the primary driver of scale. The establishment of CMCs provided a governance mechanism that earlier projects could not sustain. This model gained national legitimacy when the DAD issued Circular 06/2023, directing island‑wide establishment and continuity of CMCs, enabling replication through legal provisions under the Agrarian Development Act and Irrigation Ordinance. This Circular formally legitimises the CMC model and establishes a national pathway for replication. The CMC model and CWRD&MPs have since been adopted by major programmes such as CSIAP and SARP, demonstrating vertical and horizontal replication. CRIWMP‑developed O&M plan formats, CSA guidelines, and drinking‑water training materials (Climate Resilient Water Safety Planning, Climate Resilient Adaptation for Drinking Water, and O&M of Rooftop RWH systems) have likewise been taken up by DAD, the Ministry of Agriculture (MoA), NWSDB, DCNWS, and other national projects from 2023 onwards, reinforcing the model’s transferability. Digital systems—particularly the weather and agro‑met advisory co‑development platform—have been adopted by multiple projects (ADAP4R, World Vision, SARP, USAID‑CAP), expanding reach beyond the project’s geographic scope. The HEC‑based flood model piloted in the Mi Oya basin is now the basis for flood modelling across 22 national river basins under the WB CResMPA project. The Disaster Management Centre also identified the project’s flood‑risk assessment methodology as a best practice for early warning and preparedness, underscoring the model’s relevance for DRR. Knowledge sharing and learning CRIWMP systematically shared implementation evidence, tools, and good practices across national, regional, and GCF‑funded initiatives, contributing to sector learning, cross‑project fertilisation, and sustained institutional uptake. Knowledge from CRIWMP was shared with the GCF‑funded Knuckles Project (FP124), enabling the transfer of integrated water‑management and climate‑resilience practices across GCF’s Sri Lanka portfolio. The project’s Gender Action Plan implementation lessons informed international climate‑finance workshops, demonstrating replicability of gender‑responsive adaptation approaches—a factor that strengthens GCF’s assessment of scalability and transferability. In the water sector, CRIWMP contributed practice‑based learning to the International Water Conference 2023, organised by NWSDB, while its rural water‑supply approaches supported knowledge exchange among sector stakeholders. The project’s contributions to national drought‑preparedness targets were formally recognised during a workshop convened by the Ministry of Environment and FAO, evidencing alignment with national resilience priorities and reinforcing long‑term institutional adoption. The Department of Project Monitoring and Planning invited CRIWMP to present its implementation lessons, challenges, and design improvements for future investment planning—an indication that the project is shaping broader development practice, consistent with GCF’s expectations of systemic influence. Exposure visits—ranging from national line ministries to regional technical experts and university teams—provided high‑level stakeholders with direct exposure to CRIWMP’s integrated model, strengthening confidence in its replicability, and informing the design of related national programmes. These efforts complemented the project’s wider dissemination through academic papers, IWMI working papers, policy‑relevant research, and the Climate Action Symposium (CAS 2025), where a substantial portion of research presented was derived from CRIWMP evidence. This collectively reflects a strong learning ecosystem, enhancing the project’s likelihood of continued replication, informed policy dialogue, and long‑term transformation Creation of an enabling environment CRIWMP made notable contributions to strengthening the enabling environment for climate‑resilient water and agriculture management: - National adoption of CSA guidelines and Water Safety & Security Planning guidelines creates policy‑level continuity. - Integration of automated river gauges and agro‑met stations into national monitoring systems improves long‑term data availability for DRR and agricultural planning. - The project’s advisories and hydrological tools were utilised during Cyclone Burevi (2020) and Cyclone Ditwah (2025) to protect lives and livelihoods, demonstrating operationalisation of new systems within public institutions. These outcomes signal a maturing institutional ecosystem capable of sustaining and expanding CRIWMP’s integrated approach. Contribution to the regulatory framework and policies: The Project activities contributed directly to policy change: - The CMC Circular (2023) is expected to inform amendments to the Agrarian Development Act, embedding integrated water governance within statutory frameworks. - CSA guidelines are already shaping agricultural policy and practice, while project evidence informs policy discussions in water resources, drinking water, and DRR sectors. CRIWMP was implemented in alignment with the National Climate Change Policy, National Adaptation Strategy, and both original and updated NDCs (2021)—reinforcing coherence with national climate commitments. The project’s achievements demonstrate a clear and credible pathway toward long‑term systemic transformation. CRIWMP’s integrated cascade approach, institutionalised governance mechanisms, strengthened digital and hydrological systems, and strong national ownership collectively enable outcomes that reach far beyond the scope of the original investment. The project has already catalysed replication across major government programmes, influenced regulatory and policy development, generated a large body of actionable knowledge, and strengthened institutional and community capacities essential for sustaining transformational adaptation. The high level of engagement—from government ministries to regional experts through exposure visits—further reinforced confidence in the model and accelerated uptake of CRIWMP innovations at scale. Overall, the CRIWMP demonstrates strong paradigm shift potential, with strong evidence that its approaches will continue shaping Sri Lanka’s climate‑resilient development trajectory and informing future investment pipelines across the water, agriculture, disaster‑risk reduction, and environmental management sectors. 3.3 Sustainable Development Potential Environmental co-benefits: Integrated water management, systematic tank‑cascade restoration, water‑quality surveillance, and groundwater recharge delivered substantive environmental gains. Improved water management raised tank water levels in Yala, benefiting flora and fauna and accelerating recharge of shallow aquifers. Restored upstream belts and reed beds with native species increased vegetative cover and biodiversity, reduced evaporation, curbed soil erosion and siltation, and lowered pollutant leakage into command areas. The agroforestry programme further rehabilitated degraded lands, strengthened catchment conservation, and promoted sustainable use. Independent evidence from project sites. - In Mathavaultakulam and Thuduvakaikulam cascades, conservation measures significantly improved water quality (e.g., turbidity and coliform) presented at CAS, confirming upstream interventions translate into measurable downstream benefits. Reduction of turbidity indicates a reduction of soil erosion. - A study conducted in 4 project cascades indicated moderate to high levels of biodiversity in home gardens improved by the project - In Palugaswewa, ecosystem restoration generated net positive economic value, with benefits outweighing investment costs, strengthening the case for replication of the integrated approach. - Thudduwakaikulam cascade: redesign of a diversion structure (anicut) using a landscape approach reclaimed lands long-abandoned due to flooding and waterlogging, using restored traditional drains and earthen bunds, and increased downstream water availability and cropping intensity through improved irrigation facilities and easier gate operations. - Abandoned tanks, including those in forest areas, were restored—improving hydrological regulation across cascades (recharge, flood, and drought mitigation) and with potential to reduce wildlife damage to crops. The project demonstrated measurable results in terms of climate change & resource use efficiency: - CSA—notably Alternate Wetting and Drying (AWD)—reduced water use, lowered GHG emissions, improved soils, and maintained/increased productivity with a lower environmental footprint. - Targeted groundwater recharge at Thalakolawewa WTP diverted rooftop runoff to the source dug well, increasing yield and pumping hours from 8 to 12 per day, while improving chemical quality (lower TDS). Four‑cascade water‑quality surveillance built awareness and enabled managers to evaluate catchment conservation impacts. - Renewable energy use in production systems: 35 biogas units, 89 solar pumps, and 176 solar systems for agri‑enterprises (processing centres, hatcheries), plus solarization of Thalakolawewa, Kachchirawa/Kudethtiyawa, and Ihala Galkulama CWSS. Eight mobile solar pumping units in six districts benefited 8 FOs and 350 farmers—cutting operational emissions while improving service reliability. Social co-benefits: Year‑round access to safe drinking water significantly reduced household exposure to water‑borne diseases, while school‑based WASH initiatives strengthened hygiene and improved child wellbeing. Enhanced disaster‑preparedness capacities further improved community safety and readiness. These social and health gains are substantiated by both community reports and the UOP Impact Evaluation, which observed reductions in CKDu prevalence and common water‑borne illnesses such as diarrhoea—directly linked to improved water quality and reliability. Water‑quality testing confirmed notable improvements in project‑supplied sources, particularly across TDS, salinity, and EC, when compared to traditional dug wells. The project also ensured inclusive access, intentionally prioritising women‑headed households and persons with disabilities, enabling equitable benefits, substantial time savings, and stronger coping capacity during climate shocks. Collectively, these outcomes demonstrate clear, measurable improvements in public health, human wellbeing, and time‑poverty reduction—all of which translate into human‑capital gains and resilience dividends. Economic co-benefits: The project generated substantial and diversified economic co‑benefits, strengthening household incomes, reducing costs, and improving the long‑term sustainability of rural economic systems. CRIWMP’s promotion of CSA practices and diversified livelihood options helped regulate highly seasonal income patterns and buffer households against economic shocks. In irrigated command areas, intensified Yala cultivation and the introduction of a mid‑season enabled more frequent and evenly distributed harvests. Complementary investments in micro‑irrigation and water‑conservation techniques in home gardens and uplands strengthened food availability while reducing input costs. Evidence presented at CAS indicated that 33% of home gardens now operate at commercial scale, with the remainder substantially contributing to household food needs—demonstrating both resilience and market potential. The solarization of the Thalakolawewa, Kachchirawa/Kudethtiyawa, and Ihala Galkulama CWSSs delivered 1,200–1,400 kWh per month in energy savings and generated US$81/month in additional net income for CBOs. These savings directly supported the continued operation of Small Advanced Water Filtration Systems in schools. The installation of rooftop solar PV in 36 schools further strengthened financial sustainability and operational resilience, particularly during periods of grid instability. A total of 12,619 households—through new CWSSs (2,472 HHs), NWSDB extension subprojects (5,874 HHs), and rainwater harvesting systems (4,003 HHs)—gained year‑round access to safe water. Each household saved approximately 39 labour‑hours per month, resulting in a cumulative 427,784 hours saved per month, valued at US$2.16 million annually based on median agricultural-sector wage rates. These are real economic gains, freeing time for income generation, education, caregiving, and community leadership. The project also helped shape rural market ecosystems. A mapping in 2019 identified 300 farmers for PGS/GAP‑aligned production. Among them, 82 women from Sithamu Women Societies expanded home gardens to a commercial scale and launched a Farmers’ Market in Parangiyawadiya, reducing household food expenditure and generating new income streams. This programme scaled rapidly—from 1,167 home gardens in 2020 to 10,322 by 2025—demonstrating strong demand and replication potential. Broader economic diversification included: - Commercial fruit cultivation backed by forward sales agreements. - Cattle farming using cut‑and‑carry systems and grass‑preservation technologies. - Adoption of new animal‑husbandry technologies and productivity‑enhancing practices in traditional paddy systems. - Establishment of micro‑enterprises for value addition. - Expansion of aquaculture across 40 FOs, generating revenue to support ongoing irrigation O&M—a key indicator of long‑term system sustainability. To secure post‑project continuity, the project formulated 219 VIS‑level financing plans and 248 VIS‑level disaster‑risk management SOPs, embedding financial discipline and risk‑responsive management into local institutions. CRIWMP’s economic co‑benefits are broad‑based, verifiable, and durable—spanning income diversification, cost savings, market expansion, energy efficiency, and strengthened institutional financing. Gender-sensitive development: The project delivered substantial gender‑responsive development outcomes by enhancing women’s economic participation, decision‑making power, and role in climate‑resilient resource management. By 2025, a total of 410,411 women had benefited from CRIWMP interventions—reflecting broad and meaningful inclusion across all three project outputs. These gains were achieved through strengthened awareness and capacities in agriculture, irrigation system upgrading, water management, safe drinking‑water access, and disaster preparedness, enabling women to contribute more effectively to household and community resilience. Women‑headed households were prioritized in beneficiary selection, particularly for CSA adoption and rainwater‑harvesting installations, ensuring that the project addressed gender‑specific vulnerabilities while expanding women’s productive and financial roles. Implementation of the 2020 Gender Action Plan ensured that women’s access to assets, financial instruments, markets, and climate information was systematically improved, embedding gender equity into institutional and community‑level processes. A core element of the project’s transformative effect was its focus on targeted livelihood development. 21,749 women adopted agricultural technology packages encompassing soil and water conservation, agronomic practices, and food processing. These interventions were complemented by skills training in beekeeping, cattle and goat rearing, poultry farming, ornamental fish production, handicrafts, and value‑added food processing, opening new pathways for income diversification and economic empowerment. CRIWMP also helped address structural barriers to women’s participation in water governance. The traditional VIS‑based institutional framework often limited women’s direct engagement, as household representation typically defaulted to men. In contrast, CMC structures created formal entry points for women’s organisations and other CBOs, enabling them to take active roles in decision‑making on water and associated natural resources. This represented a significant shift toward inclusive governance. Participatory monitoring mechanisms reinforced this change. The project established committees requiring at least 30% participation of women and youth (2019), ensuring that women’s perspectives were systematically integrated into VIS construction oversight and design processes. This engagement directly influenced infrastructure features—most notably the incorporation of gender‑segregated bathing steps, introduced in response to women’s requests during PIR and design consultations. Together, these interventions strengthened women’s economic security, reduced time and care burdens through improved access to safe water and expanded their influence in local governance and natural‑resource management. The scale of beneficiaries reached, the depth of economic and institutional gains achieved, and the integration of gender considerations across all outputs underscore the project’s strong contribution to gender‑responsive development. The combined impacts contribute meaningfully to SDG 1 (No Poverty), SDG 2 (Zero Hunger), SDG 3 (Good Health and Well‑Being), SDG 5 (Gender Equality), SDG 6 (Clean Water and Sanitation), and SDG 13 (Climate Action), reflecting the project’s broader role in advancing sustainable, equitable, and climate‑resilient development pathways. 3.4 Needs of the Recipient Needs of the recipient is referred to ‘vulnerability and financing needs of the beneficiary country and population’. Describe how and to what extent the project /programme was able to meet the needs of target’s group(s), region, and or country as described in the funding proposal including whether the project/programme was able to overcome specific barriers to climate change finance and or promote opportunities to strengthen capacity in relevant institutions. CRIWMP was designed and implemented in direct response to Sri Lanka’s most critical climate‑vulnerability challenges, using a government‑led and evidence‑based process that ensured strong alignment with both local needs and national adaptation priorities. A Technical Working Group (TWG) convened by the Ministry of Mahaweli Development and Environment guided the design, using comprehensive vulnerability assessments to identify the most climate‑exposed, underserved Dry Zone districts. Additional consultations with district authorities, technical agencies, and community organisations ensured that the project addressed concrete, on‑the‑ground needs—namely, water scarcity, livelihood insecurity, poor service delivery, and limited preparedness for climate extremes. Addressing Structural Barriers to Climate Resilience and Climate-Change Finance At the time of design, Sri Lanka faced a convergence of systemic barriers: - High climate vulnerability and spatial inequality, with the Dry Zone experiencing chronic underinvestment, water scarcity, and low human-development outcomes. - Weak early-warning systems and insufficient climate-information services, limiting farmers’ ability to manage risk. - Limited fiscal space and declining access to external financing, restricting the Government’s ability to fund adaptation at scale. - Outdated technical standards and limited institutional capacity, constraining the implementation of climate-resilient water and agricultural investments. GCF financing enabled the country to overcome these barriers by providing grant-based resources for interventions that would not have been feasible through domestic budgets alone. The project filled critical financing and technical gaps by delivering resilient water-infrastructure upgrades, forecasting systems, institutional capacity-building, and climate-responsive governance structures, all of which directly addressed constraints that had previously limited the country’s ability to mobilize and operationalize climate-change finance. Meeting Community-Level Needs and Reducing Inequities: CRIWMP remained highly responsive to emerging needs throughout implementation. Through CSO partners, the project identified intra-community variations in vulnerability, ensuring that support reached groups traditionally left out of development investments—including women-headed households, persons with disabilities, and remote farming communities. This approach directly reduced access barriers, enhanced inclusion, and helped households adopt more resilient livelihood practices, even during the pandemic and economic crisis. Strengthening Institutional Capacity and Climate-Information Systems A major obstacle to effective climate adaptation was the limited national capacity for generating and using climate information. The project delivered targeted, large-scale capacity-building that substantially strengthened institutional readiness: - 12 Training-of-Trainers programmes and 35 capacity-building programmes strengthened NWSDB and DNCWS capacity in climate-resilient water supply planning, RWH, community mobilization, and financial management (3,384 participants). - The project significantly upgraded the Department of Meteorology with new digital infrastructure, data-management systems, and a single-access portal for agro-climate and water-management data. - District-level agro-met advisories were developed across 7 project districts, allowing farmers and water managers to use granular, localized forecasts—a key precondition for climate-informed decision-making. These investments strengthened the national ecosystem for climate-information services and reduced one of the most significant barriers to absorbing and deploying climate-finance effectively. Improving Technical Standards and Operational Foundations To remedy long-standing constraints in infrastructure planning and operation, the project: - Supported the updating of national irrigation technical guidelines to integrate climate-induced hydrological changes. - Developed flood SOPs, divisional disaster-preparedness plans, and water-safety guidelines to operationalize climate-risk management. - Equipped key agencies—DAD, ASCs, Provincial Councils, NAICC, Ministry of Irrigation—with the ICT tools needed for data sharing, monitoring, and advisory dissemination. These actions significantly improved Sri Lanka’s adaptation planning architecture and strengthened the enabling environment for future climate-finance investments. Promoting Climate-Responsive Services and Local Innovation At the community level, extension services transitioned from traditional, supply-driven approaches to demand-driven, climate-responsive advisory systems. Farmers received support based on seasonal forecasts and crop advisories; women entrepreneurs received training leading to new enterprises; and a Rural Women’s Business Forum was established to support over 1,000 micro-entrepreneurs. Such shifts reduced livelihood risk and strengthened local adaptive capacity. Responding to Critical Safety and Infrastructure Needs The project responded to community requests for improved safety by supporting hydrological boundary demarcation (e.g., Full Supply Levels of tanks) to reduce risks to farmers and infrastructure. Despite fiscal constraints, government co-financing was mobilized quickly for essential infrastructure, demonstrating strong public ownership and alignment with national priorities. CRIWMP effectively met the needs of its target groups and the country by addressing deep‑rooted financial, institutional, technical, and socio‑economic barriers to climate resilience. By strengthening forecasting systems, modernising design standards, enhancing institutional capacity, improving data and service delivery systems, and ensuring inclusive access for vulnerable groups, the project substantially improved Sri Lanka’s ability to access, absorb, and deploy climate‑change finance The project responded directly to key systemic barriers highlighted in national assessments and international diagnostics. Rural poverty, spatial disparities in development, inadequate drinking‑water access, and insufficient early‑warning systems had left Dry Zone communities highly vulnerable to climate shocks. Studies by the World Bank (2015) and the National Human Development Report (2012) confirmed that many Dry Zone districts—still recovering from decades of conflict—experienced chronic underinvestment, low human‑development outcomes, and heightened exposure to economic and environmental shocks. At the time of design, Sri Lanka faced limited fiscal space and shrinking foreign financing opportunities. As noted in the Central Bank Annual Report (2015), budget deficits were rising and external borrowing was constrained. The GCF investment therefore provided essential climate‑change finance that the country could not mobilize domestically—allowing urgently needed adaptation measures to proceed without exacerbating debt pressures. CRIWMP directly addressed the financing barrier by delivering large‑scale, climate‑resilient infrastructure and capacity‑building that the government lacked resources to undertake independently. The project remained highly responsive to emerging needs, particularly through partnerships with CSOs that identified intra‑community variations in vulnerability. This ensured tailored support for highly exposed groups, including women‑headed households, persons with disabilities, and remote farming communities. A major barrier to accessing climate-finance and applying climate information effectively was the limited national capacity in climate forecasting, water management, and community-centred service delivery. The project addressed these gaps through extensive training and institutional strengthening: - 12 ToT programmes and 35 capacity-building programmes for NWSDB and DNCWS enhanced expertise in climate-resilient water-supply planning, RWH, community mobilization, and financial management (3,384 participants trained). - From 2019 onward, the project significantly upgraded the Department of Meteorology’s forecasting capabilities, providing equipment, data-management systems, and a new web portal for agro-meteorological and water-management advisories. - District-level agro-met advisories were developed in all 7 project districts, enabling farmers to plan based on granular, localized information—an essential requirement for long-term adaptation. These investments directly reduced barriers to climate-informed decision-making, a critical precondition for countries to access and use climate finance effectively. CRIWMP effectively met the needs of its target groups and the country by addressing deep‑rooted financial, institutional, technical, and socio‑economic barriers to climate resilience. By strengthening forecasting systems, modernizing design standards, enhancing institutional capacity, improving data and service delivery systems, and ensuring inclusive access for vulnerable groups, the project substantially improved Sri Lanka’s ability to access, absorb, and deploy climate‑change finance 3.5 Country Ownership CRIWMP demonstrates a high degree of country ownership, reflected in its alignment with national climate strategies, strong government leadership throughout design and implementation, and sustained institutional commitment despite fiscal and economic constraints. Alignment with National Priorities and Policy Frameworks The project was fully anchored in Sri Lanka’s national climate and development agenda, aligning with the National Climate Change Policy, National Agriculture Policy, National Adaptation Plan, and the country’s INDCs, further reinforced by the updated NDCs (2021). Its interventions directly contributed to high-priority national commitments for post-COVID recovery, particularly: - Climate-sensitive food production systems, and - Efficient and sustainable water management. CRIWMP supported multiple NDC targets across sectors: - Agriculture: mainstreaming climate considerations, strengthening sustainable land/water management, and enhancing early-warning and risk-management systems. - Fisheries: expanding aquaculture and culture-based fisheries to strengthen climate-resilient food security. - Water and Irrigation: advancing Integrated River Basin Management in priority basins (including Malwathu, Mi, and Yan Oya), promoting climate-resilient water-supply schemes, and supporting alternative water resources and flood-mitigation mechanisms. - Loss and Damage: strengthening national weather and climate forecasting systems. These contributions reinforce the project’s alignment with national policy imperatives and demonstrate Sri Lanka’s commitment to embedding CRIWMP’s integrated approach in long-term adaptation planning. Government and Community Leadership The Secretary to the Ministry (Executive Entity) chaired the Project Board and progress review meetings at the national level throughout the project period. Provincial Secretaries, District Secretaries, and Divisional Secretaries chaired and actively engaged in respective levels of progress review forums and grievance redress mechanisms. Divisional Secretaries or their representatives chaired the CMC meetings, as well. In all such forums, the active participation of the relevant government partners underscored country ownership of the project. Country ownership was further strengthened through the engagement of four CSOs, which played a critical role in community mobilization and local capacity-building. Communities participated from the investigation stage through to implementation, including VIS construction monitoring, design consultations, and CMC operations, reinforcing shared responsibility and local stewardship. The development of financing plans and active participation in CMCs highlight the potential for sustained community ownership when supported by enabling institutions. Government institutions also demonstrated long-term leadership by integrating project-generated tools and approaches into routine operations. Notably: - A pool of trained national-level trainers was embedded within existing institutions, ensuring ongoing capacity development. - Climate-Resilient Water Safety Plans were adopted by NWSDB in new proposals submitted to development partners. - Technical guidelines and advisory mechanisms developed under the project were incorporated into government service-delivery models. These actions indicate that CRIWMP approaches were not stand-alone project outputs, but were absorbed into national systems, supporting long-term sustainability. Financial Commitment and Co-Financing: Despite severe fiscal pressures during the economic crisis (2022–2023) and a temporary suspension of infrastructure investments, the GOSL fulfilled its co-financing commitments, demonstrating sustained prioritization of climate resilience and water security. This continued allocation of domestic funds amid macroeconomic stress is a strong indicator of high political and institutional ownership. Full Government co-financing of USD 17,316,894 was allocated and it contributed to the VIS downstream development under Components 1, supporting capacity building and water quality assessments under component 2, and in-kind contributions for disaster risk reduction and agro-meteorological advisory services under component 3. 3.6 Efficiency and Effectiveness The project demonstrated strong efficiency and effectiveness, delivering results that exceeded most output‑level targets while maintaining economic discipline under highly volatile national and global conditions. Value for Money and Economic Soundness: The project applied a rigorous value-for-money approach throughout implementation. VIS upgrading was conducted with full responsiveness to farmer priorities while ensuring cost-efficiency. For example, desilting—one of the most expensive components in typical irrigation rehabilitation—was limited to critical, heavily silted sections and dead storage only. This targeted approach reduced unnecessary expenditure while increasing hydrological benefits such as drought mitigation and groundwater recharge. Resulting savings were strategically reinvested into water management improvements, irrigation scheduling, ecosystem restoration, cascade-level governance, and strengthened O&M systems, yielding greater long-term resilience than conventional rehabilitation. The integrated CSA programme also demonstrated efficiency by supporting the entire production system of the cascade—irrigated command areas, uplands, Chena lands, and home gardens—ensuring that the benefits of restored VISs translated into improved productivity across the full agricultural landscape. These interventions created more equitable livelihood opportunities, especially for women, and enhanced the economic viability of smallholder systems. Implementation efficiency was strengthened by scheduling irrigation construction during off-seasons, minimizing livelihood disruption, and timing CSA inputs—particularly planting materials—to coincide with rainfall onset to improve success rates. Financial Performance and Resource Mobilization: The project leveraged substantial additional financing, demonstrating resource efficiency and strong partnership value. Between 2023 and 2024, contributions from the Governments of Japan, Luxembourg, Thailand, and private sector partners amounted to USD 3.2 million, followed by a further USD 3 million in 2024 for food and nutrition security interventions. These funds supported home gardening, backyard poultry, and other household-level livelihood measures during Sri Lanka’s economic crisis. Private-sector partners such as Shangri-La Hotel, MAS Holding, and Reforest Sri Lanka contributed to environmental restoration efforts, planting 8,550 forest plants across 20 ha in 2019. These interventions reintroduced keystone species, enhanced biodiversity, and created long-term measures to reduce human–wildlife conflict. In drinking water interventions, communities contributed LKR 200,278,480 (USD 667,595)—equivalent to 4.2% of the total Output 2 investment—through land donations, cash, and labour. Such contributions demonstrate strong ownership, improve sustainability, and reduce long-term public O&M costs. Unanticipated economic benefits also materialized: land values increased in areas newly served by water systems; one CBO official formalized as a pipe-laying subcontractor; and a villager in Rambepitiya developed a no-dig pipe-laying technology, becoming a skilled service provider—reflecting positive private-sector spillovers. Cost Management, Procurement, and Delivery: Procurement and delivery adhered to annual work plans prepared with stakeholders. Aside from 2020 disbursement delays driven by macro-economic instability, planned inputs were delivered on time, and implementation processes remained within budget allocations. Despite unprecedented national challenges, including the economic crisis, inflation, and supply-chain disruptions, the project avoided cost overruns and completed all revised targets without additional funding. Where cost increases occurred (e.g., construction materials during the crisis), these were absorbed through savings generated by redesign efficiencies and reprogramming within the approved budget envelope, maintaining overall cost neutrality. The project’s outputs led directly to the achievement—and in most cases, exceeding—of outcome‑level targets. Upgraded VIS infrastructure, coupled with watershed restoration and CSA adoption, raised cropping intensity, incomes, and water security. Drinking water solutions and community capacity‑building enhanced public health, reduced gendered burdens, and strengthened resilience to CKDu‑linked risks. Climate and hydrological monitoring systems, digital platforms, and basin‑level disaster preparedness improved the anticipatory capacity of farmers, communities, and government institutions. Given the scale of results achieved relative to investment, the integration of ecosystem‑based approaches, community cost‑sharing, and multisector benefits, the project demonstrates excellent value for money and operational effectiveness. Its strong institutional strengthening elements—CMC structures, ASC knowledge hubs, CRWSSPs, and O&M financing plans—contribute to long‑term economic sustainability.

# SECTION 4. IMPLEMENTATION ARRANGEMENTS AND OPERATIONAL PERFORMANCE (Maximum Length 2 -3 pages)

This section should provide an assessment of implementation arrangements and operational performance of the project/programme including the governance structure, human resource management, procurement, monitoring and evaluation, and timeliness of project/programme implementation and disbursements etc. Complete each sub-section below (4.1.-4.3) as well as Annex 4 to provide additional information on compliance matters. 4.1. Governance Structure and Implementation Arrangements Explain whether the project/programme’s governance structure (i.e., steering committee or equivalent) functioned as intended; and how the project/programme adjusted its implementation arrangements/modalities and or human resources, procurement, and technologies to respond to changes in the operational context if applicable. Touch upon any challenges faced and actions taken with regard to the management arrangements with other stakeholders such as the national designated authority (NDA)/focal point and executing entity (EE) as relevant. The project was implemented under UNDP’s National Implementation Modality (NIM) in accordance with the Standard Basic Assistance Agreement and the 2014–2017 Country Programme. As the original Implementing Partner (IP), the Ministry of Mahaweli Development and Environment (MMDE) held overall responsibility for project management, oversight, and achievement of results. As Government portfolios shifted during the project period, IP responsibilities were transferred to successor ministries with mandates covering irrigation, environment, agriculture, and water resources. These transitions were managed smoothly, ensuring continuity of leadership and accountability for project delivery. The IP was responsible for annual and multi‑year workplan approval, certification of annual delivery, financial reporting, and internal monitoring. Despite national‑level challenges—including political transitions, COVID‑19 disruptions, and the economic crisis—the IP consistently maintained oversight functions and facilitated coordination with Responsible Parties. UNDP, as Accredited Entity (AE) and Senior Supplier, provided continuous supervision, technical assurance, fiduciary oversight, and compliance support. UNDP advised the Project Board on feasibility and safeguards, ensured alignment with GCF policies, and resolved procurement, risk, and delivery bottlenecks when national systems came under strain. This role was particularly important during the restructuring process and during the periods of constrained public financing, where adaptive management ensured that implementation quality remained high. Day‑to‑day management was led by the National Project Director (PD) appointed by the IP. The PD supervised a dedicated Project Management Unit (PMU) comprising technical, safeguards, engineering, procurement, finance, communications, field‑level, and M&E personnel. The PMU’s structure enabled coordinated implementation across the three integrated outputs and across multiple administrative levels and districts. Project Board and Strategic Oversight: The Project Board, established in 2017, served as the primary governance and decision-making body, and convened once each year throughout the project’s duration. - Project Board Meetings (PBMs) were held in July 2017, Dec 2017, Jan 2019, Jan 2020, Apr 2022, Dec 2022, Mar 2023, Dec 2023, Sep 2024, May 2025 and Dec 2025 The Board comprised the Secretary of MMDE (and successors), UNDP’s Deputy Country Director (Senior Supplier), the Senior Beneficiary (Additional Secretary – Water Resource Planning), and senior representatives from each Responsible Party—DAD, DoA, DNCWS, NWSDB, and the Ministry of Disaster Management. It was chaired by the Secretary (MMDE). The Board provided strategic direction, reviewed progress, endorsed annual workplans, approved adjustments, and guided risk mitigation. It remained fully functional throughout implementation, including during restructuring and the no-cost extension period. A Technical Working Committee—comprising subject-matter experts on tank cascade management—provided technical review and inputs until 2024. This was chaired by a senior officer of the Ministry and comprised experts on cascade-related subjects. National-level engagement with the President, line ministries, and senior officials strengthened policy alignment and reinforced country ownership. Vertical Coordination at Provincial, District, and Divisional Levels: The project leveraged existing Government coordination mechanisms, ensuring efficient use of institutional structures and reducing administrative burden. These included: - Provincial Steering Committees and reviews with Chief Secretaries; - District Coordinating Committees, District Agricultural Committees, and sectoral senior-officer meetings; - Divisional Coordination Committees and Divisional Agricultural Committees. Embedding the project within these platforms strengthened local ownership, facilitated joint problem-solving, and allowed the project to respond effectively to contextual changes. Community-Level Governance and Participation: Community-level structures were instrumental to implementation quality. CMCs, established in each project cascade, provided multi-stakeholder governance across irrigation, agriculture, drinking water, and disaster preparedness. Participatory processes—including PIRs, design validation meetings, and handover ceremonies—ensured that community priorities shaped VIS upgrading and other interventions. Grievance Redress Committees (GRCs) were established in each cascade at the outset of development work, enabling transparent resolution of issues and strengthening social accountability. A detailed description of the GRC-related mechanism is provided in Section 6.1. The committees at the project level comprise those at village level and Divisional level, comprising government officers and community representatives. Continuous engagement at the FO, CBO, and ASC levels supported inclusive planning, particularly for women and vulnerable groups. Adaptation of Implementation Arrangements to Contextual Challenges: The project demonstrated strong adaptability to the evolving operational context. During COVID-19, the PMU reconfigured fieldwork cycles, introduced digital coordination mechanisms, and maintained community engagement while adhering to health guidelines. Procurement sequencing was adjusted to minimize exposure to price shocks during the economic crisis, and technical designs were rescheduled to maintain continuity amidst fuel and transport shortages. Staffing arrangements within the PMU were adjusted to address workload peaks, especially during restructuring and during Output 2 delivery challenges. Engagement with the NDA and Responsible Parties: Coordination with the National Designated Authority (NDA) remained constructive throughout the project cycle. The NDA provided guidance during restructuring, endorsed workplans and revisions, and participated in oversight processes. Collaboration with Responsible Parties—including DAD, DoA, DNCWS, NWSDB, and MoD—remained strong, with each institution delivering its component of the project’s integrated approach. No major governance or compliance issues were encountered. 4.2. Monitoring and Evaluation Summarize the type of monitoring mechanisms put in place and the extent of its effectiveness as well as the type of interim evaluation undertaken, and reporting arrangements with other stakeholders (e.g., the NDA/focal point and EE as relevant). An Independent Interim Evaluation conducted in April–June 2021 rated the project’s overall performance as Moderately Satisfactory, with Outputs 1 and 3 assessed as Satisfactory and Output 2 as Moderately Unsatisfactory due to cost escalations and drinking water source constraints. The evaluation confirmed the project’s strong relevance, innovative river-basin approach, and positive progress in strengthening climate resilience. It also noted that the project’s Theory of Change and three outputs were valid and the barriers identified and assumptions made were confirmed. Key recommendations focused on project restructuring and prioritizing drinking water interventions, improving co-finance mobilization, strengthening cascade-level governance, and enhancing knowledge sharing. A formal Management Response was prepared to address these recommendations. The draft Final Evaluation identified CRIWMP as a “highly relevant and effective climate adaptation intervention”. The integrated, cascade-based model for strengthening climate resilience in Sri Lanka’s Dry Zone was found to be successful. Its success and sustainability resulted from technically strong project management, stakeholder participation, effective community engagement, high GCF grant utilization, and government co-financing. The evaluation concluded that the future impact will depend on deliberate post-project action to consolidate, institutionalize, and scale CRIWMP’s innovations, especially the institutionalization and mainstreaming of the cascade IWM/CMC model. It further noted that Hydrometeorological investments deliver high-value outputs, but would require sufficient capacity development and formal hosting arrangements for sustainability. Monitoring & evaluation and Assessment of outcomes received a highly satisfactory rating, while the Implementing Agency (IA) & Executing Agency (EA) Execution was satisfactory. The sustainability of the interventions received a “moderately likely” rating. The Participatory Monitoring Plan implemented by IP, UNDP, RP, CSOs, and Community, arranged for the monitoring and annual reporting, and periodic evaluation of the project results. The participatory process facilitated addressing the stakeholder concerns about construction activities implemented for all three outputs. M&E oversight and monitoring responsibilities were shared among the PD, Project Board, IP, UNDP Country Office, and UNDP-Global Environmental Finance Unit (UNDP-GEF). The specific responsibilities were detailed in the Project Document. Quarterly progress review meetings conducted with the stakeholders. The annual audits and spot checks for the implementing partner and responsible partners of the project were conducted according to UN Harmonized Approach to Cash Transfers (HACT) framework and in line with UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects. These audits and spot checks covered the partners engaged by UNDP as implementing and responsible partners to carry out project activities since the inception of the project. The assessments were conducted annually in line with HACT requirements. Depending on the level of expenditure incurred by each partner during the year, either a spot check or a full audit was undertaken. Over the entire project period, a total of approximately 20+ audits and spot checks were conducted across the different partners. In addition, during the project period the UNDP Country Office also underwent two CO-wide audits in 2021 and 2024, within which the GCF project was included as part of the broader audit scope. Based on the findings and recommendations arising from these audits and spot checks, the UNDP Country Office closely followed up with the respective partners to ensure that the recommended actions were implemented in a timely manner. This included strengthening internal controls, addressing identified gaps, and supporting capacity building at the partner level to further enhance financial management, compliance, and accountability in the implementation of project activities. The reporting requirements included the Inception Workshop and Report, GCF Annual Project Report (APR), documenting lessons learned and knowledge generation, monitoring environmental and social risks and corresponding management plans, Independent Interim Evaluation (IIE) Report, and the Final Report comprising the terminal APR/Project Completion Report (PCR), final Independent Evaluation/Terminal Evaluation report. The APR included monitoring of the results framework, gender action plan (GAP), stakeholder engagement plan, addressing environmental and social grievances, and social and environmental risks management. Additional reporting included those of supervision missions, oversight missions, and GCF learning missions. 4.3 Timeliness of project/programme implementation and disbursements Explain whether the project/programme was able to meet its planned implementation and disbursement schedules and reasons for deviations as applicable. If there is any loan component, information on loan approval, subsidiary agreements, disbursement of, and repayment of loans should also be provided. The project was able to meet its planned implementation and disbursement schedules according to the restructuring proposal. The exception was the delay in 4th tranche during 2020-2022. The difficulty in finding good-quality water sources for drinking water supply schemes and resulting higher treatment costs, the change of the Implementing Partner and the inability to meet the co-financing commitment contributed to restructuring the project in 2020. The disbursement of the 4th tranche, which was due in August 2020 was delayed as a result. The Project received a partial tranche of US$ 1.8 million in March 2021 to maintain the Project Management Unit and the CSOs, which helped the Project to maintain its ground presence and continue the activities commenced in 2020. GOSL funds were used to start new VIS upgrading works. There were some concerns between the IP and the AE regarding the fund disbursement, and these were also resolved in 2022. The NDA issued a letter confirming the country's ownership of the project in July 2022 and the co-financing commitment. Subsequently, the 4th tranche was released in October 2022, thus enabling the project to recommence the activities fully. The problems encountered in 2020 resulted in a partial implementation of AWP 2020. The project received an extension until 2025, and it was completed as scheduled, without a cost overrun.

# SECTION 5: CHALLENGES AND LESSONS LEARNED (Maximum Length 3-4 pages)

5.1 Challenges Project implementation took place in an exceptionally dynamic operating environment shaped by political transitions, institutional restructuring, climate variability, and a deep national economic crisis. These contextual shifts created multiple challenges that influenced the pace, sequencing, and coordination of activities across all outputs. Frequent political and administrative changes—including five major elections and repeated reshuffling of Cabinet portfolios between 2018 and 2024—resulted in changes to the Implementing Partner and shifts in the mandates of key Responsible Parties. These transitions caused delays in approvals, required repeated orientation of new officials, and temporarily restricted community gatherings and the use of government facilities during election periods. The reallocation of agencies such as the Disaster Management Centre and Department of Meteorology across several ministries further slowed coordination and required new HACT assessments. The project also faced technical and policy-related challenges, including the absence of nationally accepted guidelines for CSA, groundwater recharge, climate-resilient water-safety planning, and climate-proofed irrigation design. Climate-induced changes to hydrological parameters made it difficult to use historical datasets in engineering calculations. As a result, the project invested significant effort in developing new technical standards and tools to guide field-level implementation. Securing sustainable drinking-water sources proved more complex than anticipated. Many viable water sources identified during formulation were allocated to new national water-supply systems by the time implementation began, increasing treatment requirements and installation costs and limiting feasible coverage. This constraint became a major driver of the Output 2 restructuring. Across all outputs, delays in Government co-financing during the early years affected the progress of civil works, most notably canal rehabilitation, slowing the emergence of cropping-intensity gains. Although this was resolved later, it required ongoing coordination with national Treasury processes. The COVID-19 pandemic caused prolonged disruptions beginning in early 2020, halting construction, delaying training and community mobilization, and restricting the movement of contractors and technical supervisors. School closures prevented the regular operation and maintenance of installed filtration units, leading to periodic breakdowns. The subsequent economic crisis (2022–2024) further challenged procurement and delivery: foreign-exchange shortages, inflation, fuel scarcity, increased construction costs, power outages, and high transport costs caused delays across all components. The project restructuring process itself also slowed implementation, with new activities placed on hold for nearly a year while ongoing interventions continued. Meanwhile, erratic weather patterns, including unseasonal pre-monsoon rains during planned construction windows, disrupted VIS rehabilitation and required frequent rescheduling. From a behavioral and institutional perspective, promoting the paradigm shift toward an integrated cascade approach posed early challenges. Many stakeholders—including farmers and local officials—were accustomed to conventional rehabilitation measures such as desilting, focusing on symptoms rather than system-level drivers like catchment degradation. This slowed uptake of institutional reforms, requiring sustained sensitization and demonstration to build confidence in CMCs and landscape-based approaches. Lastly, human–wildlife conflict, a longstanding challenge in the Dry Zone, affected both agriculture and project infrastructure. Elephant movement damaged crops, home gardens, and monitoring equipment, introducing persistent risks beyond the project’s control. 5.2 Successes and Best Practices Project implementation demonstrated several areas of strong performance, driven by proactive planning, adaptive management, and robust stakeholder engagement. These successes enabled the project to maintain delivery momentum despite political transitions, technical challenges, and external shocks. A key success was the project’s anticipatory approach to managing political and administrative changes. By closely monitoring the national political context, the PMU advanced critical procurement—such as engineering consultancy contracts for VIS upgrading and assessments for drinking‑water sources—before election periods. Election‑related restrictions on gatherings and government facility use were mitigated by planning beneficiary selection and consultations ahead of time, sharing Election Commission guidance across field teams and CSOs, and rapidly orienting newly appointed ministers and officials. Because of these proactive measures and strong coordination platforms established at all administrative levels, changes in Implementing Partners or Responsible Parties had minimal operational impact on project progress. The project also demonstrated leadership in addressing technical and policy gaps that initially hindered implementation. In the absence of national standards for CSA, water‑safety planning, RWH O&M, groundwater recharge, and climate‑resilient irrigation design, the project collaborated with custodian agencies to develop practical guidelines and field tools. These efforts improved engineering consistency, strengthened institutional capacity, and contributed to the Irrigation Department’s update of the national Technical Guidelines for Irrigation Works. Such contributions represent a best practice in institutional strengthening, ensuring long‑term national benefit beyond the project boundary. In response to rising costs and source‑availability constraints under Output 2, the project applied an effective resource‑mobilisation strategy. By engaging RPs, district authorities, and the NWSDB, the project secured priority inclusion of new RWS schemes in Government annual programmes and budget allocations. It also negotiated substantial NWSDB co‑financing for community‑involved pipeline extensions. While Output 2 beneficiary numbers were ultimately revised during restructuring, these measures nonetheless expanded reach and sustainability while ensuring coherence with national investments. The project’s adaptive response to COVID‑19 and the economic crisis offers an important best practice. It rapidly transitioned to ICT‑enabled operations—remote procurement, virtual monitoring, digital consultations, and online training—to maintain continuity despite mobility restrictions. UNDP core resources strengthened the IT capacity of district institutions and partners, enabling steady progress against annual workplans. The decentralized model—engaging CSOs, local officials, ASCs, and community‑based service providers—proved highly resilient, allowing field activities to continue safely and efficiently. Local value chains such as farmers’ markets, strengthened through the project, served as critical safety nets during the crises. The CSA programme was expanded to address emerging urban food insecurity, demonstrating flexibility and responsiveness to national needs. To address construction delays caused by erratic weather patterns, the project coordinated with the Department of Meteorology to share 10‑day medium‑range forecasts with engineers, contractors, and monitoring committees. This climate‑informed scheduling reduced environmental and social risks and enabled rapid rectification of minor weather‑related damages. SOPs and O&M and disaster‑response plans further strengthened community‑level preparedness and minimized flood‑related losses. The co‑development and dissemination of agro‑meteorological advisories, supported by improved data systems and multi‑channel dissemination, significantly enhanced last‑mile access to usable climate information. The project also demonstrated national‑level leadership in advancing the paradigm shift toward an integrated, cascade‑based approach. Sustained engagement through the Technical Working Committee, iterative capacity building, and development of comprehensive CWRD&MPs helped shift stakeholder perspectives from conventional rehabilitation to systemic water‑resource management. This contributed directly to the DAD issuing a national circular in 2023 formally enabling CMCs. Communities increasingly recognised the benefits of integrating irrigation, CSA, drinking water, and early warning—evidenced by strong participation in CMCs and adoption of improved practices. Community empowerment emerged as an important best practice. Because VISs are traditionally community‑owned, the project invested in tools that strengthened local stewardship—such as tank‑level water‑depth gauges, rain gauges, and training in their use. This reinforced community monitoring, enhanced local ownership, and supported long‑term sustainability of the cascade systems—even where national agencies are not yet fully using community‑generated data. Finally, while wildlife‑related challenges remained largely outside the project’s mandate, the project introduced practical mitigation measures, including rehabilitation of forest tanks and biological fencing. These measures were integrated into the Exit Strategy alongside recommendations for alternative water‑level and rainfall‑measurement techniques, reflecting the project’s commitment to supporting communities in managing broader climate–ecosystem risks. 5.3 Lessons Learned Project implementation generated several important lessons that can inform the design and management of future climate‑resilience programmes in Sri Lanka and similar contexts. Frequent changes in ministerial portfolios and implementing responsibilities demonstrated the need for early agreements with stable government institutions—particularly those responsible for fund disbursement and oversight—to ensure continuity during political transitions. While the project team managed changes effectively, future projects would benefit from formal provisions in donor agreements outlining procedures when institutional mandates shift. Challenges encountered in securing suitable drinking‑water sources underscored the importance of conducting comprehensive water‑quality and source‑availability assessments—covering both surface and groundwater—during design. The experience also highlighted the value of water safety and security planning, which proved essential for ensuring sustainability in vulnerable areas and may be integrated more systematically into broader disaster‑risk‑reduction frameworks as climate change heightens water‑security risks. The project operated through unprecedented COVID‑19, political, and economic crises, reinforcing the lesson that rigid delivery models are insufficient in rapidly changing environments. Project experience demonstrated the effectiveness of mobilising multiple funding sources, decentralised implementation, strong supervision, and community‑driven delivery mechanisms. Reliance on local capacity, resources, and simple technologies enabled continuity during lockdowns and supply‑chain disruptions. These approaches proved critical for maintaining progress despite shocks. A major lesson relates to the project’s paradigm‑shifting integrated approach, which was ultimately accepted by both communities and government institutions. Its long‑term sustainability, however, depends on embedding it in policies, legislation, and institutional procedures. The DAD’s 2023 Circular enabling CMC formation, and the Cabinet decision to strengthen their legal status through amendments to the Agrarian Development Act, are important steps. Continued institutionalisation—especially in climate, water, and rural‑development policies—will be key to scaling this model. The experience showed that software components—planning, institutional development, governance structures, and community mobilisation—must receive sufficient priority from the outset. Because tank cascades function as hydrologically integrated systems, early preparation of cascade management plans is essential for sequencing sectoral activities and guiding infrastructure investments. These plans should serve as living documents that evolve throughout implementation. Shifting entrenched practices requires time. Promoting an integrated approach required sustained engagement, demonstration of results, and iterative learning. This illustrates that attitude and behavioural change—central to transformative adaptation—cannot be expected within rigid timeframes. M&E systems should therefore track institutional and behavioural progress, not only physical outputs, and project management should allocate adequate resources to support this shift. Significant lessons emerged from the project’s gender‑responsive approaches. The project exceeded several gender targets, with high levels of women’s participation in technical water‑management training, CSA adoption, value‑addition enterprises, drinking‑water management (including RWH systems), and receipt of agro‑meteorological advisories. Women showed strong engagement in O&M and micro‑irrigation systems—activities that can be continued beyond the project—indicating high potential for sustainability. Lower participation in activities such as VIS design and upgrading suggests that women prefer roles compatible with household responsibilities; however, this did not limit their ability to engage effectively in agricultural value chains. Under the Farmers’ Markets and Contract Farming models, women pooled production, negotiated with buyers, and strengthened their market presence. These findings show that women’s economic empowerment is maximised when projects offer flexible, home‑based or locally managed livelihood options alongside opportunities for value‑chain participation. Future programmes should incorporate these preferences to design gender‑inclusive interventions. In addition, the project documented community experiences and lessons learned through communication materials, including short videos and case stories capturing beneficiary perspectives and livelihood improvements resulting from the cascade restoration approach. These materials were produced in national and local languages, with interpretation where needed, enabling affected communities—including different ethnic groups—to share their experiences and feedback in culturally appropriate ways. This also provided additional evidence of inclusive stakeholder engagement and effective communication with diverse community groups across the project areas, making it an effective way of documenting lessons learned.

SECTION 6: REPORT ON ENVIRONMENTAL, SOCIAL SAFEGUARDS, AND GENDER (Max. Length 2-4 pages)

This section is to provide a summary of the project/programme activities relating to gender equality, environmental and social safeguards. Summarize the actions /activities undertaken in relation to the environmental and social management plan (ESMP) of the project /programme. 6.1: Environmental and Social Safeguards Provide a report on the implementation of ESMP and other plans, as applicable (Resettlement Plan (RP), Indigenous People’s Policy (IPP)) and Environmental and Social Management Framework (ESMFs) describing achievements of objectives and specifying: - key environmental and/or social issues (particularly indigenous peoples (IP) issues if applicable) addressed during implementation, including impacts that were not foreseen at the time of preparing management and action plans. The project activities and impact area did not contain indigenous people. During the project formulation and initiation, several likely environmental and social issues were identified from the previous experiences of the expert team. They included the following: Output 1-Irrigation component - Impacts of biodiversity, especially on the fish population and their movement, and removal of trees - Air pollution due to transport and handling of construction materials and silt from the tank bed - Collection of water in excavations - Soil erosion and pollution of waterways - Increased peak spillway discharge due to improved spillway approach (if any) - Pollution and blockage of waterways resulting from disposing of waste - Increased seepage and percolation due to excessive desilting - Health and safety at the worksite, including gender-focused sanitary facilities - Disturbances during construction, such as noise and temporary obstructions to transport Output 02 – Drinking Water - The impact of the sudden increase in electricity tariffs during the economic crisis on the income from water sales in Community Water Supply Schemes (CWSSs) - Ensuring the sustainability of small advanced filtration systems installed in schools - the mitigation and enhancement measures that were implemented during the project/programme to address issues in (i) above, including reasons for successful implementation or lack thereof and any deviations of the measures that were set out in the management plans and frameworks. The project was screened against UNDP’s and GCF’s Social and Environmental Standards and was identified as having a medium risk (risk rating of Category B). The project developed an Environmental and Social Management Plan (ESMP) highlighting the likely issues and measures to address them and shared the Plan with all the concerned parties, in line with the GSF and UNDP standards. More detailed instructions were issued to the Engineer and Contractor to address the specific issues. The instructions were in accordance with the GCF’s standards, which were based on the International Finance Corporation’s Performance Standards and UNDP’s Social and Environmental Standards. Specifically, the project adopted standards outlined in UNDP’s Social and Environmental Standards. The project was classified as Moderate SES Risk at the design stage, and this risk profile remained unchanged throughout implementation, including following the 2021 restructuring. No new or escalated environmental or social risks emerged over the project lifecycle, as confirmed through annual APR reporting (2019–2024), site-level screening, and continuous implementation of the ESMP. The project design explicitly avoided physical and economic displacement. No land acquisition, involuntary resettlement, or livelihood displacement occurred, as all civil works were undertaken within existing irrigation systems, settlements, and public or community-managed land, consistent with the original SESP and relevant FAA covenants. No Indigenous Peoples were identified in the project area, and no impacts on Indigenous Peoples’ rights, lands, territories, or livelihoods were anticipated or encountered during implementation. Environmental risks were primarily associated with small-scale civil works for Village Irrigation System (VIS) rehabilitation and decentralized drinking water infrastructure. These risks included temporary construction-related impacts such as dust, noise, sediment movement, and localized water quality risks. Across all implementation years, these risks were consistently assessed as site-specific, temporary, and reversible. Mitigation measures defined in the ESMP were systematically applied throughout implementation and refined over time based on field experience and monitoring. Key measures included: - Introduction of fish ladders and maintenance of ecological connectivity in VIS rehabilitation designs; - Avoidance of large tree removal, with screening and approvals obtained from relevant district, divisional, and conservation authorities; - Application of partial desilting criteria, enabling upstream sediment deposition with safeguards to prevent re-entry into tanks; - Scheduling of earthworks to avoid monsoon periods and reduce erosion and downstream sedimentation; - Detailed contractor instructions on air quality, water pollution prevention, waste management, and occupational health and safety. Monitoring across APRs confirms that these mitigation measures were effectively implemented. No significant or unmitigated environmental incidents were reported during the project lifecycle. Where minor issues arose (e.g. construction delays due to rainfall or access constraints), corrective actions were promptly applied without adverse environmental consequences. The main reason behind the successful implementation of these interventions was issuing of practical and clear instructions and monitoring their implementation through the mechanisms set up by the project. The dedication of the project staff also contributed to the success. Output 2 (decentralized drinking water supply) required several technical and operational adjustments during implementation, as documented in the APRs (2019–2024), due to site-specific water availability and water quality conditions. - The risk due to an increase in electricity tariffs was addressed by periodically revising the water tariff of the CWSS and installing rooftop solar systems to reduce the operational cost - The risk related to Advanced Filters was resolved by continuous awareness and engagement of stakeholders to improve the repairs and maintenance. In feasible locations, rooftop solar systems were installed to reduce O&M These adjustments were managed within the scope of the existing SESP and ESMP, and did not result in a change to the project’s overall environmental and social risk classification or require additional safeguard instruments. - description of any positive or beneficial environmental and social impacts of the project/programme and how these were enhanced by the project/programme. Environmental impacts: The project restored some components of the traditional tank ecosystem, such as the upstream tree belt, sediment filter, and downstream interceptor. The positive impacts of restored ecosystems were, as discussed before, improved vegetation cover and the reduction of evaporation from the tank water surface, reduced soil erosion and associated loss of soil fertility, reduced silting up of the tank, and reduced leakage of pollutants to the downstream command area. These impacts are consistent with the project’s ecosystem-based restoration approach and the mitigation measures defined in the ESMP. Planting of native plants in the ecosystem components has improved the biodiversity. In addition to the traditional components, the project implemented an agroforestry programme, positively impacting the catchment of the tank and improving groundwater recharge. The impacts on water availability are not quantified, but can be qualitatively assessed by observing water availability in wells, etc. While quantitative measurement was not undertaken, qualitative observations are consistent with expected outcomes of the implemented measures. Furthermore, evidence shows that the improved ecosystem provided economic benefits from the ecosystem services. The impacts of improved drainage also have not been quantified, but some abandoned lands in the Thudduwakaikulam cascade have been reclaimed, reclaiming lands abandoned for a long time. Restoration of the abandoned Tanks, especially those located in forest areas, was conducted with the agreement and approval of the conservation agencies, and special provisions, such as construction without an irrigation outlet, were used to reduce the risk of encroachment of the forest areas by the farmers. These measures were applied to avoid adverse impacts on protected and conservation areas. There is a potential to reduce wildlife damage to cultivations from restoring forest tanks, a subject to conservation authorities’ mandates and management plans. The safeguards employed by the project enabled these benefits to be sustained without being interrupted by the construction activities. Construction sequencing and site-level management measures were applied to minimize temporary impacts and avoid interference with ecosystem restoration activities. The desilting and silt deposition methods allowed for better biodiversity. The construction activities and ecosystem restoration were programmed so that one activity does not interfere with the other. CSA practices, including the AWD method, were introduced to improve productivity while reducing water demand. These practices also contribute to environmental sustainability by reducing water abstraction pressures. The environmental impacts include its potential to reduce greenhouse gas emissions. This potential is consistent with established evidence on AWD practices, although emissions reductions were not directly quantified under the project. Social impacts: One of the main mechanisms to ensure social benefits and equity was the GRM. The GRM provided a structured and accessible channel for communities to raise concerns and seek resolution throughout implementation. This mechanism improved the community ownership of the development activities, a lack of which has been pointed out by previous post-project evaluations of similar projects. The safeguards framework and GRM helped prevent discrimination by dominant groups and supported the inclusion of marginalized and vulnerable households. Furthermore, the GRM and related safeguards measures enabled equitable targeting of marginalized groups and rectified any errors or exclusion of deserving people from getting targeted benefits such as RWH systems and agricultural technology packages. - compliance with the AE standards that enables it to comply with GCF ESS standards. The compliance with AE (UNDP) project-level standards is discussed below: Biodiversity Conservation and Sustainable Natural Resource Management: The major safeguards included the clear instructions to minimize the removal of large trees during construction by limiting it to only the most essential instances. The project submitted such removals to the District and Divisional level committees comprising representatives from the Forest Department and the Department of Wildlife Conservation for review and approval. A tree planting programme was implemented to compensate the losses. Another conservation measure was to introduce fish ladders, and the need was identified during the PIR process, as identified through project-level monitoring and reporting processes. Furthermore, precautions were taken not to block waterways during the construction process and to ensure the safety of fish populations during the desilting process. The activities avoided the protected areas to the extent possible and strictly complied with the standards set by conservation/protection institutions when working within protected areas. Climate Change and Disaster Risks: Such risks occasionally occur during the construction process, particularly where rainfall coincides with partially completed structures. Most of the construction activities were confined to the dry period between Yala and Maha seasons (July-September), and critical construction items such as cutting the bund open, construction of sluices, spillways bund filing, etc were carried out during this time. Short-term weather forecasts were used to inform construction scheduling and reduce exposure to climate and disaster risks. Community Health, Safety, and Security: The project issued necessary instructions in the site-specific environmental management plan to ensure community health, safety, and security. The instructions include preventive measures against air pollution, water pollution, noise pollution, and temporary disturbance to the community’s transport. These measures were applied during construction to manage temporary and localized risks to surrounding communities. Cultural Heritage: The approval from the Department of Archaeology is a prerequisite for construction activities. Accordingly, the project submitted a comprehensive report to the authorities indicating the location of work sites, water spread areas of the tanks, and other relevant details, in advance of the construction activities, and obtained approval before commencing work. No impacts on known cultural heritage sites were reported during implementation. Displacement and Resettlement: The project design avoided physical and economic displacement. No land acquisition, involuntary resettlement, or livelihood displacement occurred during implementation. Indigenous Peoples: No Indigenous Peoples were identified in the project area, and no impacts on Indigenous Peoples’ rights, lands, territories, or livelihoods were anticipated or encountered during implementation. Labour and Working Conditions: Instructions were issued to ensure the safety of the workers. CIDA Guidelines for Safety and Health in Construction. Occupational health and safety requirements were integrated into construction supervision and contractor obligations. Pollution Prevention and Resource Efficiency: Specific instructions were given to avoid pollution of water bodies, waterways, minimize waste, and waste disposal. These measures were applied to manage construction-related pollution risks and resource use in accordance with the ESMP. - changes of laws/regulations and standards relevant to the project/programme; and National laws, regulations, and standards relevant to the project remained unchanged during the project period. However, based on implementation experience, the project recommended amendments to relevant regulations to strengthen the legal authority and institutional mandate of Cascade Management Committees (CMCs). - recommendations to resolve issues that are still outstanding, and lessons learned for future project/programme operation. All grievances raised during implementation were addressed through the established Grievance Redress Mechanism (GRM) and resolved by 2025. No outstanding grievances remained at project completion. Following resolution of all recorded grievances and completion of project activities, Output 1 and Output 2 teams formally concluded their participation in project-level Grievance Redress Committees (GRCs), in line with the project close-out process. - a list of complaints/grievances received by the AE’s institutional grievance redress mechanism or the AE concerning this project/programme (including sub-projects), action taken by the grievance redress mechanism or AE to address such complaints/grievances and the final outcome of such action, including a description of the grievance redress mechanism, its mandate and capacity to address such complaints/grievances.” Additionally, include a description of the actions undertaken towards continuing stakeholders’ engagement in the project/programme environmental and social elements, and a summary on how grievances received as regards environmental and social standards or gender standards were addressed. The information should also include confirmation of compliance with all applicable laws and regulations of the host country as well as those directly applicable to the project/programme under relevant international treaties and agreements, and a confirmation of compliance with the relevant conditions or covenants under the FAA). As the project operated across seven districts and implemented multisectoral initiatives reaching approximately 750,000 beneficiaries, it received a number of grievances and community concerns during implementation. This was partly due to the project’s strong social mobilisation strategy and stakeholder engagment approach, which created an enabling environment and empowered communities to raise their concerns and seek clarification of project activities. The comprehensive grievance redress mechanism established by the project ensured that all grievances were systematically received, recorded, and addressed. At the local level, Divisional Secretariats and CSOs acted as the first points of contact, responsible for receiving and documenting grievances. Depending on their nature, issues were escalated to Tier 1 or Tier 2 for appropriate action and resolution. Summaries of grievances were presented at Project Board (PB) meetings, while annual reports (APRs) included consolidated updates. In addition, trend analysis was conducted to identify recurring issues and patterns, enabling the project to take proactive measures and strengthen overall responsiveness and communication with affected communities. A summary of the grievances received and resolved is attached. A brief description of the Grievance Redress Mechanism (GRM): The project established and maintained a multi-tier GRM throughout implementation, with defined procedures, roles, and escalation pathways to address environmental, social, and gender-related grievances at community, district, and national levels. The GRM had the mandate and capacity to receive, assess, resolve, and track grievances in a timely and transparent manner. The key areas of grievances during the project period were as follows: - Land-Related Issues - Disturbances from Construction Activities - Construction Methodologies and Structure Locations - Temporary impacts related to infrastructure rehabilitation and community access The following is a summary of the grievances received during project implementation. Year Received Resolved (within reporting year) Pending/Carried Forward 2019 8 6 2 2020 97 85 12 2021 273 217 56 2022 70 51 19 2023 88 88 0 2024 33 32 0 2025 25 25 0 All grievances raised during the project period were resolved by the end of 2025, and no outstanding grievances remained at project completion. Stakeholder engagement, GRM, SES/Gender grievances, and compliance To address these issues, participatory decision-making was emphasized, enabling communities to provide input during the planning and design phases. This engagement supported transparency and early identification of potential concerns related to environmental, social, and gender aspects. Adjustments were made wherever feasible to align with stakeholder expectations and local needs. Monitoring and quality control mechanisms were also strengthened throughout implementation. Community members and stakeholder institutions were involved in periodic participatory monitoring to ensure that project standards were met. To address likely grievances from service providers, the project ensured: - Clear Contractual Guidelines providing transparency about payment schedules and conditions. - Streamlined Payment Processes, reducing delays through improved administrative systems. - Formal avenues for service providers to raise and resolve payment-related concerns through established project mechanisms. Grievance Redress Mechanism (GRM) The project designed and implemented a three-tier Grievance Redress Mechanism (GRM) to address community concerns and ensure effective project implementation. The GRM was accessible throughout implementation and applied to environmental, social, and gender-related grievances. The details of the GRM are outlined below: Tier 1: Village Level At the village level, the GRM was structured as follows: - Chairperson: Grama Niladari (GN) - Secretariat: A representative from the Project Management Unit (PMU), typically the Safeguard Specialist or Field Coordinator from the respective district - Other Members: Economic Development Officer (EDO), Agrarian Research and Production Assistant (ARPA), and representatives from civil society organizations (CSOs), the contractor, and the consultant responsible for construction supervision - Community Representatives: Farmers' organizations and local community members (with gender-balanced selection by the community during the Grievance Redress Committee (GRC) formation meeting. In the case of water supply schemes, the Village Coordination Committee (VCC) or the Executive Committee of the relevant CBO functioned as the first-tier GRC. Tier 2: Divisional Secretary Division Level At the divisional level, the GRM included: - Chairperson: Divisional Secretary or representative - Secretariat: Safeguard Specialist and/or Field Coordinator from PMU - Other Members: Agrarian Development Officer, Agriculture Instructor(s), Divisional Officer or representative from the DNCWS, representatives of NGOs or CSOs active in the area, Grama Niladharis, and representatives from FOs and CBOs, as well as the contractor (site in charge) and consultant Religious leaders or clergy, the chairman/representative of the local mediation board, and representatives from the Forest Department and Department of Wildlife Conservation were included as needed, based on the nature of the grievance. Tier 3: National Level The third tier of the GRM included the following: - Oversight Bodies: Social and Environmental Compliance Unit (SECU) and Stakeholder Response Mechanism (SRM) of UNDP - Independent Mechanisms: The Independent Redress Mechanism of the GCF and formal legal processes within Sri Lanka This tier provided escalation pathways where grievances could not be resolved at local or divisional levels. Status of compliance with applicable laws and regulations, treaties and agreements, and the conditions and covenants in the FAA that is related to ESS Applicable laws and regulations/conditions and covenants; Status of compliance. Condition 1.. Covenant 1. FAA Clause 9.02 In addition to Clause 18.02 of the AMA, the Accredited Entity covenants that as from the Effective Date of this Agreement, it shall: [. . .] (d) Undertake and/or put in place any adequate measures to ensure that the management of the environmental and social risks and impacts arising from the Funded Activity complies at all times with the recommendations, requirements and procedures in the Environmental and Social Management Plan, and Social and Environmental Screening Procedure, which were provided by the Accredited Entity to the Fund before the Approval Decision; (d) Compliant. The work was carried out as per the signed MOUs with DAD/NWSDB/DNCWS, which defined the provisions under ESMP and SESP. The MOU with the Disaster Management Centre (DMC) was renewed on 07.07.2023, which provided ESMP-related provisions.. Covenant 2. (e) Obtain or ensure that the Executing Entity shall acquire all land and rights in respect of land that is required to carry out the Funded Activity and shall promptly furnish to the GCF, upon its request, evidence that such land and rights in respect of the land are available for the purposes of the Funded Activity.; e) Compliant. The executing entity implemented work with the 02 RPs mandated with the legal provisions and with the involvement of the CBOs. No land acquisition or involuntary resettlement was required.. Law or regulation 1. Forest Ordinance – No. 17 (1907) and subsequent amendments; Compliant. Removal of trees for construction works and restoring tanks in forest reservations were carried out with the necessary approvals of the Forest Department.. Law or regulation 2. Fauna and Flora Protection Ordinance Act (1993). This Act provides for the protection, conservation, and preservation of the fauna and flora of Sri Lanka.; Compliant. Removal of trees for construction works and restoring tanks in wildlife reservations were carried out with the necessary approvals of the Department of Wildlife Conservation.. Law or regulation 3. Pradeshiya Saba (Local Authorities) Act, No 15 of 1987, subsequent amendments and regulations. Provincial Road Development Authorities of Wayamba, North Central and Northern Provinces. National Thoroughfare Act, No. 40 of 2008 and Road Development Authority Act, No. 73 of 1981.; Compliant. Approvals were obtained for any construction works interfering with roads.. Law or regulation 4. Factories Ordinance, No. 45 of 1942, with subsequent amendments up to date and relevant regulations; Compliant. Instructions were issued to ensure health, safety, and workers' welfare as needed. Law or regulation 5. Explosives Act no. 21 of 1956 and regulations under the act. (An act to control and enable the prohibition of manufacturing and importation. Exportation, possession, sale, exposure for sale, supply, purchase, use, and transport of any explosives).; Compliant. Explosives were not used for construction works.. Law or regulation 6. Right to Information Act, No. 12 of 2016; Compliant. Extensive measures were taken to keep the community of the development activities carried out by the project, and activities were implemented with their consent. The GRM contained provisions for the public to make complaints if rights were violated.. Law or regulation. 6.2 Gender Action Plan Report on the extent to which gender equity measures were incorporated throughout the intervention. Provide a report on the implementation of the gender action plan developed for the Project/Programme. This will primarily be a report on activities undertaken and results achieved and if the Project/Programme achieved the intended gender outcome(s). Report results against each activity/, sex-disaggregated targets compared to baseline information and indicators in the action plan including other vulnerable groups (e.g., youth, poor, female heads of households, etc.) as would have been identified in the gender analysis and action plan. If activities or targets set in the gender action plan are not achieved as per plan, reasons should be provided. The report should include details on gender-related outcomes and impacts that have been achieved as a result of the project/programme). The project achieved most of the gender action plan (GAP)’s targets by the end of the project. In the process, it focused on four core aspects of IWRM to promote the sustainable use of water resources: environmental sustainability, economic efficiency, social equity, and water governance. Apart from the GAP, the recommendations of the 2023 Gender Audit guided the Key initiatives with a gender focus. Capacity Building and Training: Collaborating with relevant government institutions, a range of capacity-building programs targeted at women and youth were implemented through the project period. Women beneficiaries include: training of Trainers (TOT), operation and maintenance of water facilities, agriculture-related economic activities, technical training related to CSA, agrometeorological advisories, rainwater harvesting, drinking water facilities, water source management, groundwater recharge methods, etc. Women also received training related to economic activities and environmental sustainability, including conservation measures and tree planting. These interventions resulted in improved empowerment of women and social equity. The Interim Evaluation of the project noted that the project is gender responsive in design and implementation. The draft Final Evaluation noted the project interventions that targeted women’s economic empowerment, leadership, and decision-making across multiple result areas. Such result areas included women-led livelihood interventions, agri-processing, seed paddy, groundnut, maize seed production, and poultry farming, where women held primary roles in group formation and leadership, production, financial management, post-harvest processing and marketing. They resulted in measurable income, savings, and food security benefits for women, strong returns on investment, enhanced financial autonomy, and leadership within households and producer groups. Monitoring of the performance of GAP implementation agreed with the Final Evaluation showed that capacity enhancement related to women’s economic empowerment, and those allowed their leadership and decision making received good acceptance by them and reached or exceeded targets. Examples are strengthening women’s FOs, water management, agricultural technologies, climate-resilient crop and land management, home gardening, and climate forecasts and advisories. In the case of cascade management, the project was successful in enabling women's representation in CMCs through implementing relevant government Circulars. However, full engagement of women in CMCs takes time. As the CMCs were fully functional only after VIS upgrading, the cascades where VIS upgrading was completed in 2024-25 will take some more time for women’s full engagement. Women’s participation in many activities improved towards the project closure. On the other hand, existing FO’s elected officials are mainly male. FOs have a mandate to engage in VIS upgrading, and it was difficult to achieve the GAP targets related to such construction activities. However, these shortfalls were adequately compensated by achievements above the target in activities where women had a comparative advantage. The restructuring reduced the number of water supply schemes targeted by the project. However, the government institutions in charge of these schemes did not have gender-disaggregated data of the people who operated and maintained them, at the time of restructuring. As such, the targets could not be revised, and the progress appears as an under achievement. Activities/ actions; Indicators; Baseline; Targets set in the gender action plan, including sex-disaggregated targets; Results achieved at the end of the project/programme, including sex-disaggregated results; Reasons for deviation. 1.1.1: Strengthen women farmers and women’s organizations in these villages to engage in Farmer Organization activities and technical aspects of water allocation, sharing, and irrigation rehabilitation.; 1.1.1.1: In these organisations, 19,200 men and women (9,782 of whom are women) are provided with training and awareness-building programmes on water management, catchment restoration, operations and maintenance of VISs, etc.; 0; 19,200, out of which 9,782 are women; 32,321 of which 13,108 are women; Assurance of women’s leadership and decision-making encouraged exceeding the targets. 1.1.2: Engage, educate, and empower women farmers to plan, implement, and monitor cascade water resource development and management plans with the support of relevant government agencies; 1.1.2.1: 9,782 women (disaggregated by age) engage in cascade water resource development and management planning 1.1.2.2: 200 women and youth in decision-making positions in cascade water user’s organizations; 0; 9,782 women 200 women and youth; 6,319 women 245 women including CMC partner CBOs; The cascades with VISs completed in 2024-25 will take some more time for the full engagement of women.. 1.1.3: Provide women and youth with training to undertake technical aspects, understand and monitor water management and allocation SOPs and advisories; 1.1.3.1: 1,200 women and youth farmers trained on technical aspects of water management and allocation SOPs and advisories; 0; 1200 women; 6,319 women; Activities leading to livelihood improvement received better acceptance. 1.2.1 Promotion of men and women in planning, designing, implementing, and monitoring of project activities. This will enable women's groups to benefit and actively engage in planning and implementing irrigation work.; 1.2.1.1: 6,000 women engaged in designing VIS upgrading, taking CC risks into account 1.2.1.2: Number of women groups engaged in planning, designing, implementing and monitoring irrigation infrastructure development activities; 0; 13,000, out of which 6,630 are women; 7,701 of which 2,920 are women; FOs are mainly comprised of males, and this was a constraint to achieve the target. Women’s participation was improved towards the project closure.. 1.2.2 Conduct preliminary investigations and participatory rural appraisal to engage women to determine upgrading priorities incorporating climate change risks; 1.2.2.1: 6,000 women engaged in designing VIS upgrading, taking CC risks into account; 0; 6000 women; 6,210 of which 3,271 are women; FOs are mainly comprised of males, and this was a constraint to achieving the target.. 1.2.3 Develop maintenance and financing mechanisms for VISs; 1.2.3.1: 8,800 men and women trained on operations and maintenance of VISs 1.2.3.2: 6,600 men and women engaged in the operation and maintenance of VISs; 0; 8,800 (2,376women 6,424men) 6,600 (1782women 4,818men); 6,210 (2,218 women and 3,992 men) 4,831 men and 2,438 women. .2.4 Train women in construction supervision through participatory monitoring committees; 1.2.4.1: 40 % of women (260 minimum) in decision-making positions in the Participatory Monitoring Committees established 1.2.4.2: 4,875 men and women trained in construction supervision 1.2.4.3: 1,462 women included in participatory monitoring committees; 0; 260 Min. 40% of decision-making positions in participatory monitoring committees are held by women 4,875 men and women 1462 women; 260 women 1,179 of which 345 are women 672 women. 1.3.1 Provide agricultural advisories and agriculture extension services for climate-resilient agricultural technological packages for women farmers; 1.3.1.1: 16,677 women farmers are implementing climate-resilient agriculture technologies and practices. 1.3.1.2: 3,335 female-headed households (20% of 16,677) with increased income ranging from 15% to 30% across seven districts 1.3.1.3 100 women producer groups consisting of 4,950 women, established in 7 districts,; 0; 16,677 women 3,335 (i.e., 20% of the beneficiaries, ranging from 15% to 30% across seven districts) 4,950 women in 100 groups; 21,749 5,884 female-headed households 11,065 women in producer groups; Activities leading to livelihood improvement, income generation, and economic empowerment received better acceptance, and resulted in exceeding the targets. 1.3.2 Support women on value addition and inputs to women; 1.3.2.1: 300 women engaged in value-added enterprises; 0; 300 women; 2,601 women; Activities leading to livelihood improvement, income generation, and economic empowerment received better acceptance, and resulted in exceeding the targets. 1.3.3 Improve/increase the technical know-how of Women aimed at reducing chemical inputs, improving efficiency in water use and climate-resilient crops/land management practices.; 1.3.3.1: 4,950 women trained in reducing chemical use and water efficiency, climate-smart agriculture 1.3.3.2 Reduced chemical usage in 4,950 women-led home gardens 1.3.3.3 Improved water use efficiency in 8,250 women-led home gardens by installing Low-Cost Drip Systems; 0; 4,950 women 4,950 women 8,259 women; 15,038 women 5,638 women/ 14,480 women 6,607 women; Activities leading to livelihood improvement, income generation, and economic empowerment received better acceptance, and resulted in exceeding the targets. 1.3.4 Provide inputs to women farmers to establish and strengthen food security in their families; 1.3.4.1: Established 4,950 women-led climate-smart home gardens; 0; 4,950; 4,920 women. 2.1.1: Provide technical and administrative training, including bookkeeping and maintenance of water supply plants- to facilitate capacity development of women’s organizations to become water supply societies/enterprises; 2.1.1.1: 20,000 female and male members in CBOs trained in management and accounting to run profitable and sustainable drinking water supply schemes; 0; 20,000; 23,741 women and A total of 48,114.; Activities leading to livelihood improvement, income generation, and economic empowerment received better acceptance, and resulted in exceeding the targets. 2.1.2: Develop climate-risk-informed, cascade-level water supply source protection plans through water source protection committees; 2.1.2.1: 20,000 women and men receiving information related to water conservation, economizing and the importance of environmental conservation 2.1.2.2: 07 (100%) water source protection plans prepared that include the priorities of women farmers; 0; 20,000 with 10,600 women 9,400 men 07 water source protection plans; 20,214 women and 18,406 men, totalling 38,620 07 climate resilient water safety and security plans that include the priorities of women farmers, prepared. 2.1.3: Train women to understand water quality issues better and protect watersheds; 2.1.3.1: 1,200 men and women received training on integrating climate risks and adaptation options for drinking water access and quality; 0; 1,200 (562 men 638 women); 3,410 women and 3,541men; totalling 6,950.; As drinking water provision is generally an activity engaged by women in households, it received better acceptance, and resulted in exceeding the targets. 2.2.1: Provision of safe drinking water through women-led CBOs; 2.2.1.1: 20,000 women engaged in managing and maintaining community drinking water supply schemes 2.2.1.2: 900 female-headed households with access to safe drinking water; 0; 20,000 900 female-headed households; 9,241 women 1,457 female-headed households; This target could not be revised at the restructuring process because at that time the RPs did not have gender-disaggregated data for managing CWSS.. 2.2.2: Expansion of community water supply scheme enabling a reduction in travel time to collect water for women and children.; 2.2.2.1: Reduction in time spent, emphasising time saved for women and girls. 2.2.2.2: 01-1.3 hours saved per day for women and girls (per family) in water collection for 9,000 families; 0 0; Xx1-1.3 hours saved per day per family for 9,000 families (10,170 hrs) 1-1.3 hours saved per day per family for 9,000 families; 25,238 women and girls in 12,619 families saved 14,259 hours spent on travel time to collect water 25,238 women and girls in 12,619 families saved 14,259 hours per day. 2.2.3: Install rainwater harvesting systems at the household level in women-headed, elderly and disability-disabled disease-affected households.; 2.2.3.1: 4,000 HHs with at-risk groups, particularly children and girls, have access to drinking water through rainwater harvesting. # of women households HH # of HH with elderly and disability # of HH with CKDu patients; 0; 4,000 HH 200 women-headed headed HH 320 of HH with elderly and disability 400 HH with CKDu; 4003 HHs 582 Women-headed HH 337 Elderly and Disability, 375 CKDu,. 2.2.4: Prioritize water supply to schools in consultation with Provincial Education Authorities to improve water/sanitation facilities provided by the National Water Supply and Drainage Board, Ministry of Health and other agencies.; 2.2.4.1: 35 schools with improved water supply 2.2.4.2: 8,750 school children (esp. at-risk children and girls) benefited; 0; 35 8,750; 72 Schools in Project Districts 62,779 children (30,203 girls) benefitted. 3.1.1: Training to farmer organizations, women groups, other livelihood groups, and women-led water supply CBOs to monitor rainfall and stream/reservoir levels; 3.1.1.1: 1,625 men and women trained in monitoring rainfall and reservoir water levels 3.1.1.2: 23 women’s groups or women-led water supply CBOs are in charge of monitoring rainfall and reservoir water levels; 0; 1,625 (829 women 796 men) 23 women’s groups; 956 (674 men and 282 women) 26 women’s groups; FOs are mainly comprised of males, and this was a constraint to achieving the target.. 3.1.2: Train men and women farmers on operations and maintenance of hydrological and meteorological equipment; 3.1.2.1: 1,625 men and women trained in the operations and maintenance of equipment; 0; 1,625 (796 men and 829 women); 2063 (505 men and 1,558 women). 3.2.1. Provide seasonal forecast, agricultural and water management advisories for crop and water management planning · Any specific actions to support getting the advisories to women and men, e.g., do women and men have the same mobile phone account; 3.2.1.1: 520,000 men and women farmers receiving seasonal forecast and water and agricultural advisories; 0; 520,000 265,200 women 254,800 men; 569,214 (290,299 women and 278,915 men). 3.2.2: Sensitize women to understand, interpret and act upon climate advisories provided by the Department of MET; 3.2.2.1: 265,200 women sensitized on accessing, interpreting and applying climate forecasts and advisories; 0; 520,000 265,200 women 254,800 men; 569,214 (290,299 women and 278,915 men). 3.2.3: Sensitize communities through FOs and ASCs for uptake of agro-met information and advisories; 3.2.3.1: 7,000 men and women trained in interpreting and using agricultural and water management SOPs; 0; 7,000 with 3,570 women 3,430 men; 8,473 (4632 men and 3841 women). 3 .2.4: Synthesize and disseminate flood warnings and water-related information through mobile and other platforms; 3.2.4.1: 445,000 men and women receiving flood early warning through mobile and other platforms; 0; 445,500 227,205 women 218,295 men; 558,212 of which 284,688 are women. 3.3.1: Assess the flood risk of at-risk communities in the three river basins; 3.3.1.1: 220,000 men and women covered through flood preparedness and response mechanism 3.3.1.2: 220,000 men and women whose flood risk is assessed; 0; 220,000 112,200 women, 107,800 men 220,000; 154,571 (75,660 men and 78,911 women) Flood risk assessment completed in 2021.. 3.3.2: Develop and establish disaster preparedness and response mechanisms for flood-prone communities; 3.3.2.1: 335 (100%) flood response plans established for VISs and drinking water schemes that incorporate gender-responsive measures 3.3.2.2: 335 (100%) flood response plans established for VISs and drinking water schemes that incorporate priorities of women; 0 Xx0; 335/100% xx335/100%; 325 325. 3.3.3: Share climate advisories with schools to activate preparedness plans for drought (water scarcity) / flooding through school disaster preparedness programmes implemented by the Education and Disaster Management Authority. Authorities’ actions to ensure that the plans are gender-responsive, e.g., special considerations for female students with disabilities; 3.3.3.1: 30 gender-responsive school disaster preparedness plans prepared; 0; 30; 29 gender responsive school disaster preparedness plans.

# SECTION 7: SUSTAINABILITY AND RECOMMENDATIONS (Maximum Length 2-3 pages)

7.1 Sustainability and Exit Strategy The long‑term sustainability of CRIWMP’s interventions has been strongly supported by a comprehensive Exit Strategy developed in 2024 and refined throughout implementation. The strategy focuses on institutionalising the project’s integrated, climate‑resilient water‑management model; strengthening local capacities; securing co‑investments; and ensuring durable operation and maintenance arrangements. - Sustaining the Integrated Technical Approach A key sustainability outcome is the continued use of the project’s combined approach—traditional tank‑cascade knowledge paired with modern climate‑resilient technologies. The project strengthened the technical, organisational, and climate‑risk‑informed planning capacity of government institutions and community organisations across VIS management, drinking‑water systems, and hydro‑agro‑met networks. This includes the transfer of updated Design Criteria for irrigation upgrading, contributions to the Technical Guidelines for Irrigation Works, and national guidelines developed for CSA, rooftop rainwater harvesting, and groundwater recharge. Modern technologies introduced—such as micro‑irrigation systems, climate‑resilient crop varieties, hydrological and meteorological monitoring equipment, and the digital weather‑data portal and mobile advisory tools—remain accessible to communities and institutions through established SOPs, O&M procedures, and toolkits. - Local Capacity and Institutional Ownership Long‑term sustainability relies on strong local governance. The project enhanced the financial and organisational capacity of community groups, especially FOs, CBOs, and CMCs. CMC structures established across all project cascades now oversee Cascade Water Resources Development and Management Plans, guiding climate‑risk‑informed water allocation, ecosystem stewardship, and community‑driven investments. Financing plans for O&M were developed for all cascades, identifying community‑generated revenue streams (e.g., increased production post‑VIS upgrading) to reduce dependence on government budgets. The digital agro‑met advisory system, hosted on the Sri Lanka Telecom Government Cloud, has been institutionalised through planned MoUs between the Department of Meteorology, Department of Agriculture, and DAD, ensuring continuity of data sharing and advisory production. Officers in project districts have gained the capacity to continue issuing Yala and Maha agro‑met advisories beyond the project period, and coordination with parallel projects (e.g., ADAP4R, World Vision Lanka) helps maintain service continuity. Disaster preparedness structures strengthened at Divisional, GND, and school levels—including Disaster Preparedness Committees, flood SOPs, and basin‑level flood‑management procedures—reinforce long‑term risk‑management capacity. All automated hydrological and meteorological stations have been formally handed over to the Department of Meteorology and the Irrigation Department, with discussions underway for continued maintenance. - Co-Investment by Government & Communities Sustainability is reinforced by substantial government and community co‑investment. Government agencies—including DAD, DoA, DNCWS, NWSDB, and the Ministry of Disaster Management—demonstrated commitment through technical support, routine maintenance, and budgetary allocations for new RWS schemes originally designed under the project. Community co‑investment has been particularly strong in drinking‑water systems, formalised through agreements with CBOs for user‑fee management and O&M. Community contributions to Output 2 total LKR 200,278,480 (USD 667,595) and continue post‑project. FO financing plans and initial O&M equipment provision support the sustained operation of VIS assets. Partnerships with microfinance institutions and rural enterprises lay the foundation for continued financing of CSA and livelihood activities. - Post-Project O&M for Monitoring Systems Comprehensive O&M plans for all monitoring equipment—including stream gauges, water‑depth gauges, and automated meteorological stations—were prepared and handed over. Strengthened FO reserve funds, increased agricultural incomes, and CBO revenue models contribute to maintaining these assets. Government staff and trainers developed under the project have been embedded within institutional systems to retain technical capacity. - Private-Sector Engagement and Enabling Environment Private‑sector participation was strengthened through enterprise development and market‑linkage facilitation. The project supported micro‑enterprise growth, value chain integration, and ecologically produced climate‑smart crops. CMCs now play a role in coordinating producer–market linkages and supporting women entrepreneurs who negotiate collectively with buyers. The project also enabled youth‑led digital services—including climate‑information sharing platforms, advisory apps (e.g., Anawaki), and social‑media dissemination channels—which remain operational through the Department of Meteorology. Improvements in ecosystem health and availability of climate information have increased opportunities for agro‑processing, ecotourism, insurance services, and microcredit expansion. - Knowledge Sharing and Transition Knowledge generated by the project has been widely disseminated at national, regional, and international levels. The national symposium held in September–October 2025 consolidated lessons from CRIWMP and other initiatives, informed policy dialogue on climate resilience and integrated water management, and catalyzed south-south learning. These processes have helped institutionalize best practices and create momentum for scale-up. - Operational and Financial Closure Operational and financial closure processes have been initiated, following UNDP procedures for liquidation and documentation. The Terminal Evaluation began three months prior to operational closure to ensure full data availability and will be submitted to the GCF within six months of completion. Additional closure elements include the preparation of the Impact Assessment, the Project Completion Report, and a final Project Board meeting to consolidate lessons and review the scale-up roadmap. 7.2 Recommendations and Next Steps To achieve climate‑resilient water management at scale across the Dry Zone, the integrated cascade‑based model developed under CRIWMP should be refined, expanded, and fully institutionalised. Key recommendations include: - Sustaining dialogue with cascade‑system stakeholders to refine the integrated management model based on implementation experience. - Embedding a strong business orientation within CMCs and community organisations, enabling them to function as financially viable entities supporting agricultural commercialisation and service provision. - Developing new national policies—or amending existing agriculture, water, and environment policies—to formally integrate tank‑cascade systems into river‑basin management frameworks. - Formulating a national strategy for tank cascade development and management, informed by lessons from CRIWMP and similar programmes, and linking it to rural development and basin‑management plans. - Scaling up CRIWMP’s integrated approach to additional cascades under a national programme modality, ensuring coordinated investment, replication of best practices, and strengthened community livelihoods. Collectively, these actions will sustain and scale the project’s contribution to climate‑resilient water management, enhance livelihood security, and advance Sri Lanka’s progress toward relevant SDG targets in the Dry Zone.

# APPENDICES

# Annex 1: REPORT ON LOGICAL FRAMEWORK

1.1 REPORT ON FUND-LEVEL IMPACT INDICATORS OF THE LOGICAL FRAMEWORK

| Fund-level impact indicators (Mitigation) | Baseline | Planned Target | Actual Result | Reason for the variance (if any) | Achievement assessment rating * |
| --- | --- | --- | --- | --- | --- |
| Mitigation Core Indicator 1 Tonnes of carbon dioxide equivalent (tCO2eq) reduced as a result of Fund-funded Project/Programmes/programmes |  | Cumulative (final target) Lifetime | Cumulative (final result) |  |  |
| Mitigation Core Indicator 2 Cost per tCO2eq decreased for all Fund-funded mitigation Project/Programmes/programmes |  |  |  |  |  |
| Mitigation Core Indicator 3 Volume of finance leveraged by Fund funding (Disaggregated by public/private source) | Public | Public | Public |  |  |
|  | Private | Private | Private |  |  |
| Mitigation Impact Indicator 1.1 Tonnes of carbon dioxide equivalent (tCO2eq) reduced or avoided emissions through increased low-emission energy access and power generation |  |  |  |  |  |
| Mitigation Impact Indicator 3.1 Tonnes of carbon dioxide equivalent (tCO2eq) reduced or avoided as a result of Fund-funded projects/programmes – building cities, industries, and appliances) |  |  |  |  |  |
| Etc. |  |  |  |  |  |

* Achievement assessment rating – please fill the last column with a colour based on the below rating scale:

| Green= Achieved | Yellow= Partially achieved | Red= Not achieved |
| --- | --- | --- |

| Fund-level impact indicators (Adaptation) | Baseline | Planned Target | Actual Result | Reason for the variance (if any) | Achievement assessment rating* |
| --- | --- | --- | --- | --- | --- |
| Adaptation Core Indicator 1 Total number of direct beneficiaries of GCF funded project/programme | Total direct beneficiaries (% of female) 0 | Total direct beneficiaries (% of female) 705,818 (51% female) | Total direct beneficiaries (% of female) 804,877 (51% female) |  |  |
| Adaptation Core Indicator 2 Total number of indirect beneficiaries of GCF funded project/programme | Total indirect beneficiaries (% of female) 0 | Total indirect beneficiaries (% of female) 1,179,874 | Total indirect beneficiaries (% of female) 1,179,851(51% female) |  |  |
| Adaptation Core Indicator 3: Number of total beneficiaries relative to total population | Total beneficiaries Number of Total Population 0 | Total beneficiaries 1,950,374 Number of Total Population Year: 2021 | Total beneficiaries 1,985,250 (51% female) 9.12% relative to the total population Number of Total Population 21,763,170 Year: 2024 |  |  |
| Adaptation Impact Indicator 2.1 Number of males and females benefiting from introduced health measures to respond to climate-sensitive diseases) |  |  |  |  |  |
| A 1.0 Increased resilience and enhanced livelihoods of the most vulnerable people, communities, and regions: Number of males and females benefiting from the adoption of diversified, climate-resilient livelihood options | 0 | 520,000 | 569,214 (51% female) |  |  |
| A 2.0 Increased resilience of health, well-being, and food and water security: Number of males and females with year-round access to reliable and safe water supply despite climate shocks and stresses | 0 | 453,118 | 465,911 (51% female) |  |  |

* Achievement Assessment rating – please fill the last column with a colour based on the below rating scale:

| Green= Achieved | Yellow= Partially achieved | Red= Not achieved |
| --- | --- | --- |

Annex: 1.2 REPORT ON PROJECT/PROGRAMME OUTCOME AND OUTPUT LEVEL RESULTS INDICATORS OF THE LOGICAL FRAMEWORK

| Project/Programme outcome and output indicators (Mitigation/Adaptation) | Baseline | Target (Planned) | Results (Actual) | Reason for the variance (if any) | Achievement assessment rating* |
| --- | --- | --- | --- | --- | --- |
| Indicator 1 (Outcome level) (Mitigation/Adaptation) (e.g., 6.3 Mitigation: MWs of low-emission energy capacity installed, generated and/or rehabilitated as a result of GCF support) 7.1: Extent to which vulnerable households, communities, and businesses use improved strategies and activities to respond to climate variability and climate change Indicator 1.1 (Outcome level) (Adaptation) The extent of minor irrigation under targeted cascades with increased CI (CI more than 1.6) | 0 | 770,500 of which 392,955 are women 9750 ha | 804,877 of which 410,753 are women (Output1: 573,212 Output2: 45,301 Output3: 186,364) 9,839 ha |  |  |
| Indicator 1 (Output level) (e.g., Wind power generation plant commissioned) Output 1 Village Irrigation infrastructure and capacities of smallholder farmers strengthened for climate-resilient water management and agriculture |  |  |  |  |  |
| (e.g., Sign Power Purchase Agreement (PPA)) Indicator 1.2 (Output level) Number of male and female farmers reached through disseminating the climate-resilient agriculture technology packages | 0 | 520,000, of which 265,200 are women | 569,214 (of which 290,300 are women) |  |  |
| Indicator 1.3 No. of women farmers implementing climate-resilient agriculture technologies and practices | 0 | 16,677 | 21,749 |  |  |
| Indicator 1.3, etc |  |  |  |  |  |
| Indicator 2 (Outcome level) (Mitigation/Adaptation) |  |  |  |  |  |
| Indicator 2 (Output level) Improved access to safe and reliable drinking water through supply systems able to withstand climate change and variability |  |  |  |  |  |
| Indicator 2.1 Indicator 2.1 Number of HH with year-round access to reliable and safe water supply | 0 | 122,715 | 128,537 (51% female) |  |  |
| Indicator 2.2 Number of women engaged in managing and maintaining community drinking water supply schemes | 0 | 20,000 | 9,241 | Restructuring the project reduced the number of community water supply schemes from 35 to 7. |  |
| Indicator 3. Capacity of Dry Zone farmers strengthened to use weather and climate information for agricultural and water management |  |  |  |  |  |
| Indicator 3.1 Number of female and male farmers reached through seasonal forecast for agriculture planning | 0 | 520,000, of which 265,200 are women | 569,214 (290,299 women) |  |  |
| Indicator 3.2 Number of female and male farmers receiving advisories for water management | 0 | 445,500, of which 227,205 are women | 465,911, of which 237,615 are women |  |  |

* Achievement Assessment rating – please fill the last column with a colour based on the below rating scale:

| Green= Achieved | Yellow= Partially achieved | Red= Not achieved |
| --- | --- | --- |

NNE

# Annex 2: FINANCIAL PERFORMANCE BY CATEGORY

Please provide the information on financial performance using the attached document.

2. For the Final audited financial report that had been completed during the reporting period (where applicable), AE to include an opinion on the financial information submitted here.

Provide a few success short stories from the project/programme. Good short stories typically illustrate how a project/programme has improved people’s lives or made a difference in the host country with results and or key statistics to back up the claim. Stories should contain beneficiaries and beneficiary quotes and should highlight the good work of the project/ programs through the lens of the people impacted by it. A case story should Include: 1) simple, jargon free headline/title which also summarizes the story; 2) body which includes quotes and key results/statistics and the role the project/programme played; 3) captioned photographs that are colourful and depict action or tells the story with at least 300 dpi (dots per inch) resolution. Include the photographer’s name, organization as appropriate.

Ripples is a compilation of CRIWMP’s success stories

Annex 2: FINANCIAL PERFORMANCE BY CATEGORY

The attached annex provides a compilation of YouTube video links featuring success stories from the project.

Annex 3: CASE STORIES

# Annex 3: CASE STORIES

Table – Success stories posted on social media platforms

| Description | Link |
| --- | --- |
| Few success stories posted on our Exposure | https://undpsrilanka.exposure.co/hope-flows-with-water https://undpsrilanka.exposure.co/reviving-tradition-building-resilience https://undpsrilanka.exposure.co/innovative-water-management-techniques-revolutionizing-paddy-cultivation-in-sri-lanka https://undpsrilanka.exposure.co/trusting-the-resilience-of-rural-women-to-build-a-better-tomorrow https://undpsrilanka.exposure.co/integrated-water-resources-management-creating-a-positive-ripple-effect https://undpsrilanka.exposure.co/fighting-inequality-for-a-resilient-future-break-the-cycle |
| LinkedIn | https://www.linkedin.com/posts/undpsrilanka_greenwednesday-activity-7267391380484702208hE6q?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpsrilanka_greenwednesday-water-agriculture-activity-7257395623279173634r8iK?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpsrilanka_srilanka-climatechange-lka-activity-7252173991912603648-3vxC?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpsrilanka_greenwednesday-srilanka-activity-7249672736547954688ZmEw?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpsrilanka_sri-droughtmanagement-droughtresilience-activity-7247561047182606336-NO_A?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undp-in-asia-and-the-pacific_unpredictable-weather-patterns-and-degraded-activity-7251799447334969344-AsxI?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpclimate_unpredictable-weather-patterns-and-degraded-activity-7253344159527264256-aqUU?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpsrilanka_greenwednesday-activity-7244625592732549120-bfIS?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpsrilanka_greenwednesday-activity-7242101124881620992-MHDs?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/posts/undpsrilanka_greenwednesday-sri-activity-7239594476510273536-moHu?utm_source=share&utm_medium=member_desktop |
| X / Twitter | https://x.com/ASteiner/status/1846727927192604941 https://x.com/UNDP/status/1846672472302932116 https://x.com/UNDPasiapac/status/1864545495026397624 https://x.com/UNDPSriLanka/status/1864276795392184705 https://x.com/UNDPasiapac/status/1864196343042068504 https://x.com/UNDPSriLanka/status/1861628860053512703 https://x.com/UNDRR/status/1859507170154361104 https://x.com/UNDPSriLanka/status/1856663353026056315 https://x.com/UNDPasiapac/status/1855779131834962153 https://x.com/UNBiodiversity/status/1854327910796296522 https://x.com/UNDPSriLanka/status/1851627409864602028 https://x.com/UNDP/status/1846672472302932116 https://x.com/UNDPSriLanka/status/1846460902285234402 https://x.com/UNDPasiapac/status/1846031409754112082 https://x.com/UNDPSriLanka/status/1846126204640022862 https://x.com/UNDPSriLanka/status/1843903517410377991 https://x.com/UNDPSriLanka/status/1841787884887507174 https://x.com/UNDPSriLanka/status/1838862684827332839 https://x.com/UNDPSriLanka/status/1836333107852775839 https://x.com/UNDPSriLanka/status/1833832526579970190 https://x.com/UNDPSriLanka/status/1802573601809522800 https://x.com/UNDPSriLanka/status/1792783898935714281 |
| Facebook | https://www.facebook.com/share/1AxhHpPVe9/ https://www.facebook.com/share/1B2Rj5NLFc/ https://www.facebook.com/share/1GJpCKWBpd/ https://www.facebook.com/share/185D3pfWGh/ https://www.facebook.com/share/18a4hXnzD3/ https://www.facebook.com/share/185ebWcoJk/ https://www.facebook.com/share/155XrFHvZc/ https://www.facebook.com/share/18PGt1nAm1/ https://www.facebook.com/share/1BM6SFLjbb/ https://www.facebook.com/share/14nhL8LaQZ/ https://www.facebook.com/share/1KxZ31HVV1/ https://www.facebook.com/share/18TvQx1bnh/ https://www.facebook.com/share/15VqB7rrtt/ https://www.facebook.com/share/18N1hiJEey/ https://www.facebook.com/share/14bjJEZxfv/ |
| Instagram | https://www.instagram.com/p/DDJ5HfaBXwO/?img_index=1 https://www.instagram.com/p/DC3V7lZhHPn/?img_index=1 https://www.instagram.com/p/DCT0wV_I-PV/?img_index=1 https://www.instagram.com/p/DCDwFHPBcli/?img_index=1 https://www.instagram.com/p/DBK_LR-MQFc/?img_index=1 https://www.instagram.com/p/DBI-0exs1NO/?img_index=1 https://www.instagram.com/p/DAVax7Woqn4/?img_index=1 https://www.instagram.com/p/DADcKiOoJpU/?img_index=1 https://www.instagram.com/p/C_xnPtzhti8/?img_index=1 https://www.instagram.com/p/C4ziZptxbze/?img_index=1 |

# Annex 4: COMPLIANCE WITH LEGAL AGREEMENTS (AMA/FAA)

Provide a summary of how the FA has complied with relevant articles as per FAA and AMA obligations. Where there are divergencies, kindly provide the reasons for the deviations using the tables below.

Submission of Annual Performance Reports

Provide a report on how the project has complied with submission of annual performance reports as at and when due.) If there were waivers requested or delays in submission and timely response to GCF feedback, these can be supplemented with justifications.

| APRs | Date Submitted (indicate ‘waived’ if waived) | Date Approved | Remarks |
| --- | --- | --- | --- |
| Year 1 | 1st March 2018 | 28 June 2019 | Responded to all the comments from GCF |
| Year 2 | 1st March 2019 | 31 July 2020 | Responded to all the comments from GCF |
| Year 3 | 28th February 2020 | 21 February 2022 | Responded to all the comments from GCF |
| Year 4 | 26th February 2021 | 9 December 2022 | Responded to all the comments from GCF |
| Year 5 | 28th February 2022 | 7 July 2022 | Responded to all the comments from GCF |
| Year 6 | 27th February 2023 | 31 August 2023 | Responded to all the comments from GCF |
| Year 7 | 29th February 2024 | 3 July 2024 | Responded to all the comments from GCF |
| Year 8 | 27th February 2025 | 10 September 2025 | Responded to all the comments from GCF |

Submission of other reports

| Report | Planned Date for submission if applicable (write NA if not applicable) | Date submitted | Remarks (explain whether any waiver or extension was granted and the reason for waiver/extension.) |
| --- | --- | --- | --- |
| Inception Report | 28th December 2017 | 12th September 2017 | Approved |
| Baseline Assessment | NA |  |  |
| Qualified /audited financial reports |  |  |  |
| Interim Evaluation Report | 28 March 2021 | 15 June 2021 |  |
| Final Evaluation Report | 28 June 2026 |  |  |
| Other reports including AE level reports (e.g., self-assessments, mid-term review, AE baseline framework etc.) |  |  |  |

MENTS

# OTHER ATTACHMENTS

(As applicable, such as detailed budget tables, loan repayment schedules to GCF (interest/principal), equity investment schedules, statements of capital account, valuation reports, credit guarantee agreements, investor reports, and others, as may be specified in the relevant legal agreements (e.g. FAA, Subsidiary Agreement)).

FOR GCF OFFICIALS ONLY

Overall Assessment rating

| Criteria | Weighting (100%) | Rating (5-1) | Comments |
| --- | --- | --- | --- |
| Relevance of project design | 5 |  |  |
| Implementation performance | 15 |  |  |
| Financial management | 20 |  |  |
| Verifiable results (outputs &outcomes) | 30 |  |  |
| Environmental & Social | 15 |  |  |
| Governance Arrangements | 10 |  |  |
| Timeliness of reporting | 5 |  |  |

Ratings - 1 -5 (5 highest and 1 lowest)

Quantifiable rating

4 – 5.00 - Green

3 – 3.99 - Yellow

0 – 2.99 - Red

| Green= Achieved | Yellow= Partially achieved | Red= Not achieved |
| --- | --- | --- |

This Project/Programme Completion Report (PCR) or final APR is a guide to Accredited Entities (AEs) that have oversight of project/ programmes funded by the Green Climate Fund (GCF). The PCR or final APR is required to be delivered in accordance with the relevant Funded Activity Agreement (FAA) and will serve as the basis for the GCF to confirm the completion of the implementation of the Funded Activity. The overall purpose of the PCR (final APR) is to capture learnings covering the total implementation period of the project, and to provide an objective account of the achievement of the Project/Programme objectives and an assessment of its results.

Refers to the date when the implementation of all activities set out in the Funding Proposal by the Accredited Entity is finalized as defined in the relevant Funded Activity Agreement (FAA).

Total Project/Programme budget including co-financing as approved by GCF.

Tree girdle refers to the ecosystem surrounding the tank bed that controls evaporation water losses

A vegetated strip located between the tank bund and paddy fields. It acts as a natural bioremediation barrier to trap salts, agrochemicals, and sediments, maintaining soil health for agricultural sustainability in dry zones.

This Circular, No. 06/2023 dated 23rd August 2023, titled “Cascade Management Committee (CMC) Establishment and Continuity”, is based on the legal provisions contained in the Irrigation Ordnance and the Agrarian Development Act. Therefore, it supports the legality of CMCs and the scaling up and replication of the CMC.

As per the approved Logical Framework in the FAA, provide a report on the relevant indicators in relation to the narrative in Section 2.1.

The final target is the amount of emission reduced up to the end of project/programme implementation period whereas the 'lifetime (i.e. expected lifetime emission reductions overtime)’ is an estimate of emission reduced over the lifetime beyond the project/programme implementation period. If the end of lifetime coincides with the end of implementation period, provide the same value for the ‘cumulative (final target) and ‘lifetime’.

As defined in the FAA.

Please note that the values should be based on total funding (GCF funding and co-financing).

Please note that the values should be based on total funding (GCF funding and co-financing).

Relative to the total population of the country.