## Work Plan format 2025
MLF No. |  | BHU/PHA/95/INV/33
Project Name |  | HCFC phase-out management plan (stage I, fourth tranche)
Quantum Award Number |  | 00081856.2
Quantum Project Number |  | 00081856
EXPECTED CP OUTPUTS and indicators including 12 months' targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs |  |  | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
|  |  |  | 2025 |  |  |  | Implementing Partner | UN | Source of Funds | Budget Description | Amount (US$)
|  |  | Account Code | Q1 | Q2 | Q3 | Q4 |  |  |  |  | 2025 | Total
UNDP outcome 2 (UNSDCF outcome 3). By 2028, Bhutan’s environment remains sustainably managed, and its people are more resilient to disaster risks and climate change | 1 | Recovery and Reclamation Program
|  | 1.1. Safety Gears for Field officers (4 sets) | 72200 |  |  | X |  | NOU | UNDP | MLF | Equipment | 4000 | 4000
|  | 1.2. Recovery Units and Mini-reclaim inventory, and Documentation | 75700 |  |  | X | X | NOU | UNDP | MLF | Training/workshop | 2000 | 2000
| 2 | End user/Retrofitting Incentive Programme
|  | 2.1. ODS Identifier (2 nos) | 72200 |  |  | X | X | NOU | UNDP | MLF | Equipment | 9000 | 9000
|  | 2.2. Technical expertise on ODS identifier training | 75700 |  |  | X | X | NOU | UNDP | MLF | Training/workshop | 2000 | 2000
Sub-total | [11 empty] | 17000 | 17000
Assurance Activities
| 1 | Quarterly and annual review meetings | 75700 |  | X |  | X | NOU | UNDP | MLF | Training/workshop | 1000 | 1000
| 2 | Quarterly and annual review meetings | 75700 |  |  |  | X | UNDP | UNDP | MLF | Training/workshop | 1000 | 1000
Sub-total | [11 empty] | 2000 | 2000
TOTAL | [11 empty] | 19000 | 19000

## Work Plan format 2026
MLF No. |  | BHU/PHA/95/INV/33
Project Name |  | HCFC phase-out management plan (stage I, fourth tranche)
Quantum Award Number |  | 00081856.2
Quantum Project Number |  | 00081856
EXPECTED CP OUTPUTS and indicators including 12 months' targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs |  |  | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
|  |  |  | 2025 |  |  |  | Implementing Partner | UN | Source of Funds | Budget Description | Amount (US$)
|  |  | Account Code | Q1 | Q2 | Q3 | Q4 |  |  |  |  | 2026 | Total
UNDP outcome 2 (UNSDCF outcome 3). By 2028, Bhutan’s environment remains sustainably managed, and its people are more resilient to disaster risks and climate change | 1 | Recovery and Reclamation Program
|  | 1.1. Safety Gears for Field officers (4 sets) | 72200 |  |  | X |  | NOU | UNDP | MLF | Equipment | 4000 | 4000
|  | 1.2. Recovery Units and Mini-reclaim inventory, and Documentation | 75700 |  |  | X | X | NOU | UNDP | MLF | Training/workshop | 2000 | 2000
| 2 | End user/Retrofitting Incentive Programme
|  | 2.1. ODS Identifier (2 nos) | 72200 |  |  | X | X | NOU | UNDP | MLF | Equipment | 9000 | 9000
|  | 2.2. Technical expertise on ODS identifier training | 75700 |  |  | X | X | NOU | UNDP | MLF | Training/workshop | 2000 | 2000
Sub-total | [11 empty] | 17000 | 17000
Assurance Activities
| 1 | Quarterly and annual review meetings | 75700 |  | X |  | X | NOU | UNDP | MLF | Training/workshop | 1000 | 1000
| 2 | Quarterly and annual review meetings | 75700 |  |  |  | X | UNDP | UNDP | MLF | Training/workshop | 1000 | 1000
Sub-total | [11 empty] | 2000 | 2000
TOTAL | [11 empty] | 19000 | 19000