Project Title: Enhancing Peace, Security and Stability in Africa V

Output 4: Enhancing African capacities

in combatting human trafficking and smuggling of migrants

Project Number:

Implementing Partner: Cairo International Center for Conflict Resolution, Peacekeeping & Peacebuilding (CCCPA)

Start Date: March 2019	End Date: 31 March 2021		PAC Meeting date:

Brief Description

Next year presents Egypt and Japan with once-in-a-generation opportunity to elevate their cooperation in Africa to new heights. Preparations are already underway for the TICAD Summit in Yokohama, Japan in August 2019, which will coincide with Egypt’s chairmanship of the African Union (2019-2020). This project will contribute to the attainment of the objectives of the TICAD process, primarily by enhancing African (and Arab) capacities to prevent, manage and resolve conflicts, and to confront other challenges to peace and security. Based on a thorough and comprehensive analysis of the evolving threat environment in Africa (and the Arab World), the project will specifically focus on the following four key areas (project outputs): - Enhancing African and Arab communities’ resilience to radicalization and extremism leading to terrorism and other transnational threats, including capacity building in the field of disarmament, demobilization and reintegration; - Enhancing African and Arab capacities in peacekeeping; - Enhancing African and Arab capacities in peacemaking, peacebuilding and the implementation of the women, peace and security agenda; - Enhancing African capacities in combating human trafficking and smuggling of migrants; - Supporting the expansion of CCCPA’s activities to the Arab world and upgrading its training, convening and research infrastructure. Switzerland will support with funding the implementation of the project output 4 (Enhancing African capacities in combating human trafficking and smuggling of migrants)

Contributing Outcome (UNDAF/CPD, RPD or GPD):

By 2022 Egypt has adopted equitable and sustainable development pathways and remains on track to achieve agreed targets for inclusive, sustainable, resilient and job creating economic development

Indicative Output(s):

| Total resources required: | $1,456,271.34 |  |
| --- | --- | --- |
| Total resources allocated: |  |  |
|  | UNDP: | $316,000 |
|  | Donor Japan: | $803, 571 |
|  | Donor Swiss Confederation | $336,700.34 |
|  | Government: |  |
|  | In-Kind: |  |
| Unfunded: |  |  |

Agreed by (signatures):

| Government | UNDP | Implementing Partner |
| --- | --- | --- |
| H.E. Ambassador Soha Gendi, Director, International Cooperation for Development Department, Ministry of Foreign Affairs | Ms. Randa Aboul-Hosn, Resident Representative. a.i., UNDP Egypt | Ashraf Swelam, Director General, Cairo International Center for Conflict Resolution, Peacekeeping and Peacebuilding (CCCPA) |
| Date: | Date: | Date: |

# Development Challenge

- Next year (2019) presents Egypt and Japan with once-in-a-generation opportunity to elevate their trilateral cooperation in Africa to new heights, in pursuit of their shared commitment to peace, security and development in the continent, including as outlined in successive declarations of the Tokyo International Conference on African Development (TICAD).

- On one hand, preparations are already underway for the return of the (TICAD) Summit to Japan. Twenty-five years after its launch as a forum for high-level policy dialogue between African leaders and development partners, most notably Japan, TICAD VII will be an opportunity to take stock of past accomplishments and lessons learnt, which in turn will inform future initiatives and programs.

- On the other hand, Egypt will assume the chairmanship of the African Union at a time when the continent – including through the African Union and in cooperation with international partners – continues its march towards greater integration and prosperity. The recent launch of the Africa Trade Agreement, an initiative that Egypt has played a significant role in advancing, is a notable example in this regard.

- The Swiss cooperation strategy in Egypt (2017-2020) includes one pillar on migration and protection, with different projects implemented with international organizations and local partners. Switzerland seeks to address migration challenges in a comprehensive manner and establish partnerships with countries of origin and countries of transit. Egypt and Switzerland launched technical discussions on migration issues in Cairo in January 2019.  The role plaid by Egypt, at the crossroads of migratory routes through the African continent to the Mediterranean Sea, is essential. Switzerland intends to contribute to address root causes, to support institutional cooperation for better migration management and assist to respond to refugee challenges. Fighting against human trafficking and smuggling of migrants is a priority for Switzerland and is a central issue in the region.

- Nevertheless, and as highlighted by H.E. Shinzo Abe, Prime Minister of Japan, in his keynote speech before the 2016 Nairobi TICAD VI Summit, Africa continues to be a continent of stark contrasts. While it has seen much political, economic and technological advancement in the last few decades, conflict continues to impede development and interrupt livelihoods. State collapse and weak governance severely complicate post-conflict reconstruction and peacebuilding efforts, often resulting in a relapse to conflict.

- The growing nexus between conflict and terrorism is also a challenge of great concern. According to the 2017 Global Terrorism Index (GTI), much of the growth of the global terrorist threat in the last decade has been inspired by, or a direct outgrowth of, ongoing large-scale armed conflict, with 91 percent of all terrorist attacks and 95 percent of all terrorism-related deaths occurring in countries that are involved in an armed conflict. This couldn’t be truer than in the case of Africa and the Arab world. According to the GTI, six out of the ten countries most impacted by terrorism are either African or Arab, with 84 percent of all terrorist attacks occurring in the Middle East and North Africa, Sub-Saharan Africa and South Asia.

- Similarly, the transnational nexus between terrorism and organized crime is growing in complexity, with dire consequences not only for individual countries, but also for entire regions, most notably the Sahel and the Horn of Africa. Terrorist and criminal groups share networks, tactics and profits and cooperate in kidnapping, smuggling and trafficking of arms, drugs and humans. For example, Al-Shabaab, a terrorist group operating in the Horn of Africa, has also been identified as an organized criminal group involved in illicit activities such as extortion and wildlife crimes.

- In the face of these challenges, there is a growing recognition among policymakers and practitioners of the need for change. Both the United Nations (UN) and the African Union (AU) are pursuing ambitious reform agendas, including significant reforms of their peace and security architectures. Major initiatives are already underway to upgrade the international community’s toolbox for preventing conflict and sustaining peace.

- In the field of peacekeeping, the UN Secretary General António Guterres launched the Action for Peacekeeping (A4P) initiative at a Security Council High-Level Debate on 28 March 2018. The initiative aims to achieve three objectives: a) refocusing peacekeeping with realistic expectations; b) making peacekeeping missions stronger and safer; and c) mobilizing greater support for political solutions and for well-structured, well-equipped, and well-trained forces The A4P initiative and its accompanying Declaration of Shared Commitments on UN Peacekeeping Operations, widely endorsed by UN member states, have generated significant momentum for making peacekeeping more fit for purpose.

- In the field of peacebuilding, there is a growing acknowledgement of the inability of current policies and frameworks to produce durable peace in many countries. In the meantime, there is an evolving recognition of the limitations of current top-down approaches to peacebuilding that tend to ignore the context-specificity of post-conflict situations.

- In this context, the decision of the African Union, during its Summit in Nouakchott, Mauritania (2018), to establish the African Union Centre for Post Conflict Reconstruction and Development (AUC-PCRD) is a major development. The decision – which caps a seven-year effort by Egypt – accepts Egypt’s offer to host the Center and requests that consultations between the Egyptian Government and the AU Commission start immediately, with a view towards submitting a report on the needs of the Center to the ordinary session of the AU Assembly in February 2019. Under Egypt’s chairmanship of the African Union (2019-2020), the establishment of the AU-PCRD, along with other peacebuilding initiatives, will be a major area of focus.

- Similarly, progress in conflict prevention has been uneven at best. While it remains a grossly underestimated tool of the international community, it is also clear that more investments are needed to advance innovative, context-specific, “people-centered” and “inclusive” approaches to early warning/early response, conflict analysis, and crisis management, and to develop new tools that capture the complexity of many of today’s conflicts and crises.

- The same can be said about Disarmament, Demobilization and Reintegration (DDR). Originally envisaged as a vital tool for the transition from conflict to development, DDR programs today are implemented in contexts in which one – if not more or all - of its pre-conditions (namely a peace agreement containing a legal framework for DDR, trust in the peace process, willingness of the parties to engage in DDR, and a minimum guarantee of security) are lacking, and where much of the violence is perpetuated by terrorist and criminal groups, rather than traditional armed groups.

- In recognition of the above, the DDR Interagency Working Group (IAWG) is currently reviewing the Integrated Disarmament, Demobilization and Reintegration Standards (IDDRS). The review is intended to update guidance to DDR practitioners that is more fit for purpose in the new contexts in which they operate. On its part, the AU is finalizing a set of Operational Guidance Notes (OGNs) to provide DDR practitioners with context-specific guidance on a host of DDR-related issues, including guidance on the link between DDR and Countering Violent Extremism, which the Cairo International Center for Conflict Resolution, Peacekeeping and Peacebuilding (CCCPA) took the lead role in developing.

- Moreover, while the implementation of the women, peace and security agenda is receiving new momentum, much is left to be desired. In practice, women continue to be underrepresented in decision-making positions, particularly in the peace and security architecture. In the field of peacekeeping, women make up only 4% of total military and police personnel deployed to UN missions. Out of 11 heads of offices and missions in the African Union, only 4 are women. In Syria’s UN-led peace negotiations, women are significantly outnumbered at merely 15% of the opposition and government delegations.

- Finally, the unprecedented scale and complexity of the current crisis of forced migration, refugee flows, internal displacement and human trafficking present African and Arab countries of origin, transit and destination with enormous challenges. As a result, UN member states proposed the Global Compact for Migration (GCM); the first intergovernmental agreement aimed at improving governance on migration, addressing its challenges, and incorporating it into sustainable development. The GCM has been adopted in December 2018 in Morocco, as a stepping stone in international cooperation. Regionally, the African Union Assembley has designated 2019 as “Year of Refugees, Returnees and Internally Displaced Persons in Africa: Towards Durable Solutions to Forced Displacement”. In advancing these reforms and initiatives, addressing African and Arab capacity gaps and limitations becomes key. As highlighted by recent studies, instability in sub-Saharan Africa and the Arab world is largely driven by lack of/ inadequate capacity to govern.

- This project will contribute to enhancing African national, regional and continental capacities to prevent, manage and resolve conflicts, and to combat transnational threats and other challenges to peace and security. It will also contribute to enriching the international and regional debate about evolving approaches to preventing and resolving conflict and sustaining peace, including by providing a platform for African voices to contribute to these important debates.

- In doing so, the project will contribute to advancing the Sustainable Development Goals (SDGs) in Africa and the Arab World. By facilitating the international partnerships (SDG 17) necessary for the implementation of the proposed activities, the project will contribute to promoting peaceful, just and inclusive societies (SDG 16) in Africa. Moreover, by streamlining gender in all the project’s activities and advancing the implementation of the women, peace and security agenda, it will support women’s empowerment efforts (SDG 5). Finally, the project will also contribute to the advancement of SDG 8, by contributing to efforts to end modern slavery, human trafficking, and the recruitment and use of child soldiers.

- The project will be in line with African strategic priorities to address new and emerging threats to peace and security in Africa, as identified by the African Union and supported by the international community, and as outlined in the African Peace and Security Architecture (APSA) Roadmap 2016 -2020, namely:

- conflict prevention (including early warning);

- crisis/conflict management (including mediation and the African Standby Force);

- post-conflict reconstruction and peacebuilding;

- strategic security issues (most notably countering terrorism, transnational organized crime, and small arms and light weapons); and

- coordination and partnerships.

Cross-cutting issues, including most notably the implementation of the women, peace and security agenda, were also addressed.

- The project will also be in line with the priorities of the TICAD process, as outlined most recently in the Nairobi Declaration (27-28 August 2016), which in addition to reaffirming the Yokohama Plan of Action of TICAD V, resolved “to support enhancing the capacity of national and local government authorities, as well as international and African regional institutions, for peace and stability on the continent”. Congruent with the Nairobi Implementation Plan, the project addresses prevention of radicalization and extremism leading to terrorism (3.2), peacekeeping (3.1.9), peacebuilding (3.1), crisis response (3.1.8), transboundary threats (3.1.7) and women, peace and security (3.1.2). The activities of the project are also in line with Japanese priorities in the Middle East, as outlined in the Japan Middle East Initiative.

# Strategy

- Through the UNDP Country Program Document (CPD), covering the period from 2018-2022, the UNDP will continue to support the CCCPA, as an African center of excellence for training and capacity building. It will also contribute to supporting the next phase of the evolution of the Center, including the expansion of its activities to the Arab world, while leveraging its vast and unique expertise in the African context. The project will contribute to the achievement of Outcome 1 under both the United Nations Partnership Development Framework (UNPDF) (2018-2022) and the UNDP CPD “By 2022 Egypt has adopted equitable and sustainable development pathways and remains on track to achieve agreed targets for inclusive, sustainable, resilient and job creating economic development”

- Based on a thorough and comprehensive analysis of the evolving threat environment in Africa and the Arab World and the critical capacity gaps needed to prevent conflict and sustain peace, this project aims to develop innovative approaches and the critical capacities needed in four key areas (project outputs):

- Enhancing African and Arab communities’ resilience to radicalization and extremism leading to terrorism and other transnational threats, including capacity building in the field of disarmament, demobilization and reintegration;

- Enhancing African and Arab capacities in peacekeeping;

- Enhancing African and Arab capacities in peacemaking, peacebuilding and the implementation of the women, peace and security agenda;

- Enhancing African Capacities in combatting human trafficking and smuggling of migrants.

- Supporting the expansion of CCCPA’s activities to the Arab world and upgrading its training, convening and research infrastructure.

- The project aims to build lasting “national capacities”, which in turn would ensure the sustainability of project results. A participatory and inclusive approach to project development and implementation is applied; one that involves a thorough needs assessment and extensive consultation with target beneficiaries and stakeholders, before, during and following the implementation.

- Out of a belief that the complexity of today’s threats to peace and security necessitates a whole-of-government approach and breaking the silos mentality, the project expands CCCPA’s integrated multidimensional approach to training, bringing together military, police and civilian officials.

- The project complements top-down state-centric approaches, necessary for the extension of state authority, with bottom-up approaches and local knowledge. This attentiveness to the relations between state and society is intended to provide legitimacy to peacebuilding interventions – especially in contexts characterized with weak governance - and to ensure the sustainability of results. Wherever applicable, the project strives to build community resilience and advance partnerships between state and society.

- Given the important role played by the African Union, the League of Arab States, and African regional economic communities/ regional mechanisms in the maintenance of African and Arab peace and security, the project also contributes to building the capacities of these regional and sub-regional organizations. In its totality, this approach is in line with the African – as well as international – call for “African solutions to African problems”, and with the ongoing reforms in the League of Arab States.

- Building on the recent expansion of its mandate, CCCPA will leverage its expertise in Africa to the respond to the ever-growing needs in the Arab world. CCCPA will, however, continue to include the whole of the African continent in its training and capacity building activities. Where applicable Asian countries might also be included in some activities.

- Mindful of the internationalized nature of today’s conflicts and the transnational nature of other threats and challenges to peace and security, the project promotes international cooperation, including through trilateral and South-South cooperation.

- Training material is developed to meet current and emerging practical needs, with the required flexibility to respond to unpredictable developments in the field. Empirical evidence guides and informs training design and implementation. Desktop and field research are complemented by CCCPA’s ability to convene expertise through workshops and review boards of training manuals. This also allows CCCPA to incorporate good practices and lessons learned from successful interventions in other fields and conflict environments, while mindful of the context-specificity of each intervention.

- Gaps, if any, in CCCPA’s in-house capacity are bridged by means of cooperation with national, regional and international partners. Knowledge gained from previous projects, as captured by CCCPA’s monitoring and evaluation systems provide inputs for the development/update of new training material.

- As recognized in UNSCR 1325 and subsequent resolutions, the integration of gender perspective is critical for the effectiveness, sustainability and ownership of peace efforts. In addition to including a full output for advancing the implementation of the women, peace and security agenda in Africa and the Arab world, the project will streamline gender considerations in all its activities.

- In addition to involving all actors and stakeholders, whose engagement is critical for achieving the desired impact, selection of the right trainees is of crucial importance. CCCPA will, for each training develop criteria for selection, depending on the field of training, the intended impact, and the target groups. Where police and military are concerned, CCCPA will request the relevant African ministries to nominate their personnel who meet the criteria outlined by the Center.

- To measure impact, CCCPA’s monitoring and evaluation framework follows the Kilpatrick Model, which identifies four levels of outcomes resulting from a highly effective training course: reaction, learning, behavior and results. To measure immediate impact of training on participants’ knowledge, CCCPA uses a combination of individual and group assessments, as a means of providing quantitative and qualitative measurements of gaining and applying knowledge and skills. Given the nature of beneficiaries of CCCPA’s trainings, specifically police and military participants (where there is no guarantee that participants will be available for a follow-up), the bulk of monitoring and evaluation is conducted immediately following the training courses.

- For others, the Center conducts a yearly impact evaluation trip in two/three countries with the largest participation in trainings. The objectives of this exercise is to evaluate the effectiveness and usefulness of CCCPA’s trainings, based on the experience of participants (behavior) and their employers (results). This helps identify the strengths and weaknesses of the trainings, and provides useful feedback to the training cycle.

- Through this project, UNDP will aim at further strengthening CCCPA’s results-based management, enhancing visibility and communication of results, ensuring the financial sustainability of the Center, and ensuring that the project is gender sensitive. UNDP will also support CCCPA by brokering knowledge and mobilizing comparative experience in the areas of focus. UNDP will also contribute – when applicable - to nourishing the growing relationship between the Center and the UN Department for Peacekeeping Operations (DPKO) and other UN bodies and institutions.

- Good communications with the GoJ and UNDP is essential in developing a shared understanding of how the project is progressing. This will include submissions of quarterly progress reports, an annual project report and a final report describing the achievements, periodic review and amendment of detailed Action Plan and budget allocations with UNDP to ensure that the project is meeting its targets. In the event that there are unavoidable changes to the agreed work plan, the project team will communicate this to UNDP immediately and will jointly develop a viable solution to be communicated by UNDP to the GoJ for consultation. The progress, achievements and challenges will be reviewed and discussed at the Project Board meeting.

- To complement the project's current funding, CCCPA will continue its efforts to diversify the sources of funding to ensure the financial sustainability of all of its activities - either through the Egyptian government or international partners.

# Results and Partnerships (1.5-5 pages recommended)

Expected Results

Output 1: • Enhancing African and Arab communities’ resilience to radicalization and extremism leading to terrorism and other transnational threats, including capacity building in the field of disarmament, demobilization and reintegration;

Activity 1.1: Needs assessment is conducted/updated; training methodology, framework, toolkits, curricula and partnerships are developed/updated Activity 1.2: Workshops/trainings in the area of Preventing Radicalization and Extremism Leading to Terrorism (PRELT), Disarmament, Demobilization and Reintegration (DDR)

- Building on the impressive results of previous years of GoJ-CCCPA-UNDP collaboration, the project will expand and scale up CCCPA’s important contribution to building community resilience to radicalization and extremism leading to terrorism (PRELT) in Africa and the Arab world. With the growing recognition – both internationally and regionally – of the critical role that can/should be played by religious leaders in PRELT, the project will also support the implementation of an advanced version of the training to be devoted for African/Arab religious leaders and influencers.

- The project will support CCCPA’s efforts, in collaboration with the African Union, to translate the AU’s DDR Operational Guidance Notes, including on the link between DDR and CVE, into training material that will form the basis of capacity building activities for African practitioners, including those working in new and asymmetrical environments. Related to the above, the project will also leverage CCCPA’s position as the Chairman of the Integrated DDR Training Group (IDDRTG) to build African and Arab capacities in the field of DDR, based on the newly revised IDDRS (potentially in collaboration with the UNDPKO and the UNDP).

Activities

- 3 foundational/advanced trainings/workshops targeting 45 trainees on preventing radicalization and extremism leading to terrorism and DDR.

Output 2: Enhanced African and Arab capacities in Peacekeeping

Activity 2.1: Training methodology, framework, toolkit, curricula and partnerships are developed/upgraded Activity 2.2: Workshops/trainings in the area of Peacekeeping are conducted

- The growing complexity of peacekeeping environments underscores the need for strengthened capacities and preparedness. Today, the UN is looking to deploy highly qualified personnel that are able to operate safely and effectively in high-risk environments. And with the changing peace and security landscape in the Arab region, the demand for Arab peacekeepers is likely to rise now and in the foreseeable future. Therefore, this project will contribute to building African and Arab peacekeeping capacities to ensure that they perform their functions with the highest levels of professionalism. The project will also support the prevention of sexual exploitation and abuse in peacekeeping operations by providing the necessary trainings to African and Arab peacekeepers.

- The project will facilitate cooperation with international and regional partners, including the UN Department of Peacekeeping Operations (UNDPKO) and the Integrated Training Service (ITS) (or the AU) to organize one training/workshop to respond to emerging training needs. In addition, the project will facilitate CCCPA’s contribution in support of the full operationalization of the African Peace and Security Architecture (APSA).

Activities:

- 11 trainings, targeting 500 trainees:

  - 10 pre-deployment and/or in-mission training for UN/AU peacekeeping missions, including on preventing sexual exploitation and abuse;

  - 1 specialized peacekeeping training/workshop, in partnership with the UN and/or the AU (such as protection of civilians, most notably women and children).

- 1 international/regional workshop on peacekeeping as a tool of sustaining peace.

Output 3: • Enhancing African and Arab capacities in peacemaking, peacebuilding and the implementation of the women, peace and security agenda

Activity 3.1: Needs assessment is conducted; training methodology, framework, toolkit, curricula and partnerships are developed/upgraded Activity 3.2: Workshops and trainings in the areas of Conflict Prevention and Resolution, Peacebuilding and the Implementation of the Women, Peace and Security agenda

- This project will respond to this growing need by capacitating African and Arab stakeholders on the regional and national levels on areas of early warning / early response, crisis management and dialogue, negotiation and mediation, and peacebuilding. Through trainings/workshops, organized with international and regional partners, CCCPA will contribute to enhancing tools of conflict prevention and sustaining peace.

- The project will also seek to enhance women’s protection and participation in the full spectrum of peace engagements in conflict and post-conflict situations in Africa and the Arab world. This will be achieved by means of building Arab and African capacities on women, peace and security and gender mainstreaming in peacemaking, peacekeeping, and peacebuilding.

Activities:

- 3 trainings /workshops targeting 45 African and Arab officials on conflict prevention and resolution, and the implementation of the women, peace and security agenda, including gender mainstreaming in peacemaking, peacekeeping, and peacebuilding

Output 4: Enhanced African capacities in combating human trafficking and smuggling of migrants

Activity 4.1: Needs assessment is updated; training methodology, framework, toolkit, curricula and partnerships are updated Activity 4.2: Workshops and trainings in Combating Human Trafficking and Smuggling of Migrants,

- The scale and complexity of the current crisis of forced migration, refugee flows, internal displacement and human trafficking are unprecedented since World War II. This presents countries of origin, transit and destination with numerous challenges. Africa continues to suffer the most. According to the United Nations Department of Economic and Social Affairs (UN DESA) International Migration Report, there were 36 million African migrants worldwide in 2017. Seven of the ten countries that now account for more than three quarters of the world’s refugees are African (South Sudan, Somalia, Sudan, The Democratic Republic of the Congo, the Central African Republic and Eritrea). Moreover, 63% of movements across borders took place within the continent. As a result, most African countries, today, are either a source, a transit or a destination for migration, or a combination of the above. The net result of this massive movement of people has been taxing the ability of all countries to provide responses to the security, political, economic, social, and environmental challenges it poses.

- According to UNHCR 2017 statistics, Africa is also disproportionately affected by conflict-induced or forced migration, with African refugees constituting 34 % of the global population of concern and three of the top ten refugee accepting countries in the world being in Sub-saharan Africa; and over 26 percent of the world’s refugees residing in Africa .

- To combat human trafficking and smuggling of migrants in Africa, certain preconditions are needed. First, it is crucial that African countries establish the required legal and institutional frameworks. This includes national legislations and laws, strategies and action plans to prevent and combat both crimes, protect victims, prosecute perpetrators and allow for regional and international cooperation to effectively manage migration and harness its potential towards increased development. This is an area where many African countries continue to lag behind.  Second, officials in the African countries (and regional and sub-regional organizations) need to build up their capacities on the different aspects combat this phenomenon, especially given the cross-cutting nature of the phenomenon and the multiple agencie

This project leverages Egypt’s unique position and CCCPA’s subject-matter expertise and established network of national, regional and international partners to respond to the growing need for enhancing African capacities to combat human trafficking and smuggling of migrants.Through trainings/workshops, this project will contribute to capacitating national, regional and continental actors with the necessary knowledge and skills to effectively combat human trafficking and smuggling of migrants, developing necessary legislation and national/regional strategies, and mainstreaming migration in development policies to harness migration benefits for development and mitigate risks as well as increase resilience of migrants, their families and local communities in countries of origin and destination. Activities will cover the African continent, with particular attention to countries along the high-volume routes, whether countries of origin (East, West and North Africa), countries of transit (Sahel and Sahra region and North Africa) or countries of destination (mainly in North Africa) To maximize impact, trainees will also include a select group of officials  from continental and regional bodies, including the African  Union (AU), the Economic Community of West  African States (ECOWAS),  the  Common Market  for Eastern  and Southern  Africa (COMESA),  the Community of  Sahel-Saharan  States (CEN-SAD),  the East  African Community  (EAC), the Economic Community of Central African States (ECCAS), the Economic  Community of West African States (ECOWAS), the Intergovernmental Authority on Development (IGAD), and the International Conference on the Great Lakes Region (ICGLR), African Prosecutors Association (APA), and the G5 Sahel.

Activities:

A. 6 trainings targeting 100 African officials on transnational threats including human trafficking and smuggling of migrants.

B.1 workshop targeting 35 African officials  on enhancing best practices & lessons learned among African officials on design and  implementation of laws, national plans, and national strategies to combat human trafficking & smuggling of migrants.

C. 2 workshop targeting 20 African officials on mainstreaming migration in development policies.

Output 5: Support for upgrading CCCPA’s training, convening and research infrastructure

Activity 5.1: State of the art facilities and equipment are acquired for CCCPA’s new premises

- Efforts are already underway, supported by the GoJ and UNDP, for the relocation of CCCPA to its new premises. This project will continue to support CCCPA’s plans to enhance its training, convening and research infrastructure, including by acquiring state of the art facilities and equipment, participation in key research/training consortia and subscribing to major academic databases and journals.

- The relocation to the new premises will allow CCCPA to conduct its trainings and activities in a more cost-efficient manner at its headquarters instead of resorting to offsite venues. It will also support the current expansion of CCCPA’s activities to the Arab world and beyond.

Resources Required to Achieve the Expected Results

- Aside from financial resources, the most critical inputs needed to achieve expected results are human resources. In addition to CCCPA’s in-house capacities, the project will facilitate the expansion of the Center’s roster of consultants, trainers and facilitators and experts that can contribute to the development and implementation of trainings/workshops. Further enhancing the capacity of CCCPA’s staff in conducting needs assessments, design of trainings, research and development, facilitation of trainings and monitoring and evaluation is also a priority.

- In addition to human capacities, a moderate investment in the physical infrastructure of the center (office space, hardware and software) would be required. This is to address the growing needs of project staff to deliver the desired outcomes.

Partnerships

- Cooperation with various Egyptian Ministries (most notably Foreign Affairs, Defense, and Interior) is key to the success of this project. CCCPA will also partner with regional and international organizations, including most notably the United Nations, the African Union, the League of Arab States, and African RECS/RMs.

- CCCPA will also leverage its current unique position in international and regional associations to secure additional resources/expertise necessary for the implementation of activities, including its presidency of the International Association of Peacekeeping Training Centers (IAPTC) and the IDDRTG, as well as its membership of the Executive Committee of the APSTA and international research consortia, most notably the Challenges Forum.

- CCCPA will continue to seek engaging counterparts from Japan, and to invite Japanese expertise to contribute to activities implemented by the Center, subject to the availability and interest of the Japanese side.

Risks and Assumptions

- Participation: Since CCCPA receives nominations of participants from relevant state ministries and neither selects nor interviews military and police participants in person pre-training, there is a risk that the target audience may not have exact level of knowledge required for the training and/or are not directly working in the relevant discipline.

- However, growing relations with beneficiary institutions have over the years enhanced the quality of candidates sent to the Center and have increased CCCPA’s involvement in the individual selection process. Where civilians are concerned, CCCPA will leverage its alumni and partners networks to target eligible participants for training.

- Logistics: Political and security constraints might hinder participation of target countries. In 2017, participation from Kenya was cancelled at the last minute in a few CCCPA activities due to the elections, resulting in financial penalties and lower target participation. Budget constraints alongside inflation rates may also hinder participation from certain target countries.

- Volatile Exchange Rates: Volatile exchange rates and changes in air ticket prices may result in extra savings or costs to the project.

- Gender Balance: As police and military component in many countries in Africa are predominantly male, there emerges a challenge to balance female participation in the trainings. So far, the majority of participants (84%) in the training are male. CCCPA will continue to engage with nominating institutions to encourage larger female participation.

Stakeholder Engagement

- An inclusive and participatory approach to project design, implementation and evaluation is applied, one that involves beneficiaries and stakeholders. Of particular significance is the latter’s contribution to the needs assessment phase, through extensive consultations, as well as identifying new and emerging needs in the filed during the implementation.

- Selection criteria of trainees are designed with a focus on involving all beneficiaries and stakeholders, especially those whose engagement is critical in achieving the intended impact.

South-South and Triangular Cooperation (SSC/TrC)

- In line with established practice from previous projects, CCCPA will explore and utilize opportunities for collaboration with other leading training and research institutions in Africa, including through its membership of the Executive Committee of the African Peace Support Trainers Association (APSTA), especially those who are funded by the Government of Japan (GoJ). CCCPA will also seek to utilize best practices and lessons learned from the global South.

Knowledge

- The project will contribute to the production of policy briefs, research papers, and workshops and conferences reports. CCCPA’s evidence-based research aims inform policy and decision making on issues of peace and security in Africa.

- Having proved their effectiveness as means of communication, outreach and visibility, CCCPA will continue to upgrade its website, its presence on social media (Facebook, Twitter, YouTube, etc.) and to produce its monthly newsletter, which is sent out to a growing network of partners, alumni, as well as interested citizens in Egypt and Africa. Online presence is also used as a tool to disseminate knowledge products, referred to above.

Sustainability and Scaling Up

- CCCPA’s approach to training is one of building African lasting capacities, as explained in its theory of change. This does not only ensure sustainability of results, but also provide opportunities for scaling up.

# Project Management

Cost Efficiency and Effectiveness

- CCCPA will continue its efforts to achieve cost-efficiency and effectiveness of spending, including by adhering to the relevant clauses outlined in the guidelines provided by UNDP, as well as its own policies and procedures manual.

Project Management

- The project on Enhancing Peace, Security and Stability in Africa IV will be operational at the headquarters of the Cairo International Center for Conflict Resolution, Peacekeeping and Peacebuilding (CCCPA) located at 1 Omar Makram Street in Tahrir Square, Cairo, Egypt.  It will be headed by the Center’s Director General.

- Training activities are held in venues near the CCCPA office where accommodation for participants is also available, and in CCCPA new premises.

- Unless the Government of Japan requests or agrees otherwise, UNDP and the project shall take all appropriate measures to publicize and make visible the partnership and funding from the Government of Japan. Information related to the activities of the project provided to the press and beneficiaries, or posted on CCCPA’s Website, the UNDP’s Website, and social media accounts, as well as all related publicity material, reports and publications shall acknowledge the contribution of the Government of Japan, where applicable, and shall display the development partners’ logo in an appropriate way. A Visibility and Communications Officer will be hired to achieve this.

- Unless the Government of Switzerland requests or agrees otherwise, UNDP and the project shall take all appropriate measures to publicize and make visible the partnership and funding from the Government of Switzerland. Information related to the activities of the project provided to the press and beneficiaries, or posted on CCCPA’s Website, the UNDP’s Website, and social media accounts, as well as all related publicity material, reports and publications shall acknowledge the contribution of the Government of Swizerland, where applicable, and shall display the development partners’ logo in an appropriate way. A Visibility and Communications Officer will be hired to achieve this.

- A Japanese Junior Professional Officer (JPO) will be engaged as part of the UNDP Team overseeing the implementation of the project.

- The CCCPA Board of Directors is presided by the Egyptian Minister of Foreign Affairs and is composed of representatives of the Ministries of Foreign Affairs, Defense, Interior, and Higher Education and Scientific Research, and leading scholars and subject matter experts. The Board is responsible for the management of the center’s affairs and the conduct of its business. CCCPA has also established an International Advisory Board (IAB) comprised of eminent global personalities, leading experts in peace, security and development and representatives of strategic partners and major stakeholders.  The IAB provides strategic guidance to the project management.

- UNDP shall receive and administer the payment in accordance with the regulations, rules and directives of UNDP.

- All financial accounts and statements shall be expressed in United States dollars.

- Any interest income attributable to the contribution from Japan shall be treated in accordance with the Japan-UNDP agreement on Arrangement for the Interest income derived from Japan-UNDP Partnership Fund.

- Any interest income attributable to the contribution from Switzerland shall be treated in accordance with the third party cost-sharing agreement between Switzerland and UNDP.

- Interest income and unspent balance of Japan’s contribution will be handled in line with the policies and procedures of Japan-UNDP Partnership Fund. If there is a necessity to change the period, content, or budget of the project, the CCCPA and UNDP Egypt will consult with the Embassy of Japan in Egypt in advance.

- Interest income and unspent balance of the Switzerland’s contribution will be handled in line with the third party cost sharing agreement between Switzerland and UNDP. If there is a necessity to change the period, content, or budget of the project, the CCCPA and UNDP Egypt will consult with the Embassy of Switzerland in Egypt in advance.

- In accordance with the decisions and directives of UNDP's Executive Board, the contribution shall be charged:

- 8% cost recovery for the provision of general management support (GMS) by UNDP headquarters and country office

- Direct costing will be charged according to the Universal Price List

- Ownership of equipment, supplies and other properties financed from the contribution shall vest in UNDP.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

- The contribution shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP and audit fees shall be charged to the project budget.

# Results Framework

Intended Outcome as stated in the UNDAF/Country [or Global/Regional] Programme Results and Resource Framework:

Outcome indicators as stated in the Country Programme [or Global/Regional] Results and Resources Framework, including baseline and targets:

Applicable Output(s) from the UNDP Strategic Plan:

Project title and Atlas Project Number: Consolidating Peace, Security and Stability in Africa IV

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS (by frequency of data collection) |  |  |  |  |  |  |  | ## FINAL | ## DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | ## Quarter 5 | ## Quarter 6 | ## Quarter 7 | ## Quarter 8 |  |  |
| Output 1: Enhancing African and Arab communities’ resilience to radicalization and extremism leading to terrorism and other transnational threats, including capacity building in the field of disarmament, demobilization and reintegration | 1.1 Number of trained people, gender segregated |  | 0 | 2019-2020 | 0 | 15 | 15 | 15 | NA | NA | NA | NA | 45 |  |
|  | 1.2 Number of trainings/workshops organized on topics related to PRELT, DDR and Transnational Threats |  | 0 | 2019-2020 | 0 | 1 | 1 | 1 | NA | NA | NA | NA | 3 |  |
|  | 1.3 Knowledge improvement |  | 0 | 2019-2020 | 0 | 70% | 70% | 70% | NA | NA | NA | NA | 70% |  |
|  | 1.4 Participant satisfaction |  | 0 | 2019-2020 | 0 | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | NA | NA | NA | NA | Over 60% satisfaction from 70% of participants |  |
| Output 2: Enhanced African & Arab capacities peacekeeping | 2.1 Number of trained people, gender segregated |  | 0 | 2019-2020 | 125 | 125 | 125 | 125 | NA | NA | NA | NA | 500 |  |
|  | 2.2 Number of workshop/trainings organized on topics related to peacekeeping |  | 0 | 2019-2020 | 2 | 4 | 3 | 2 | NA | NA | NA | NA | 11 |  |
|  | 2.3 Knowledge improvement |  | 0 | 2019-2020 | 70% | 70% | 70% | 70% | NA | NA | NA | NA | 70% |  |
|  | 2.4 Participant satisfaction |  | 0 | 2019-2020 | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | NA | NA | NA | NA | Over 60% satisfaction from 70% of participants |  |
| Output 3: Enhancing African and Arab capacities in peacemaking, peacebuilding and the implementation of the women, peace and security agenda | 3.1 Number of trained people, gender segregated |  | 0 | 2019-2020 | 15 | 15 | 15 | 0 | NA | NA | NA | NA | 45 |  |
|  | 3.2 Number of workshop/trainings organized on topics related to peacemaking, peacebuilding and WPS |  | 0 | 2019-2020 | 1 | 1 | 1 | 0 | NA | NA | NA | NA | 3 |  |
|  | 3.3 Knowledge improvement |  | 0 | 2019-2020 | 70% | 70% | 70% | 70% | NA | NA | NA | NA | 70% |  |
|  | 3.4 Participant satisfaction |  | 0 | 2019-2020 | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | NA | NA | NA | NA | Over 60% satisfaction from 70% of participants |  |
| Output 4: Enhancing African capacities in combating human trafficking and smuggling of migrants | 4.1 Number of trained people, gender segregated |  | 0 | 2019-2021 | 20 | 55 | 20 | 20 | 20 | 20 | 20 | 20 | 135 |  |
|  | 4.2 Number of workshop/trainings organized on topics related to migration management including combating human trafficking and smuggling of migrants |  | 0 | 2019-2021 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 9 |  |
|  | 4.3 Knowledge improvement |  | 0 | 2019-2021 | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% |  |
|  | 4.4 Participant satisfaction |  | 0 | 2019-2021 | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants | Over 60% satisfaction from 70% of participants |  |
| Output 5 Support for upgrading CCCPA’s training, convening and research infrastructure | 5.1 State of the art facilities and equipment are acquired for CCCPA’s new premises |  | 0 | 2019-2020 | Renovation of new premises is executed | Renovation of new premises is executed | Renovation of new premises is executed | Renovation of new premises is executed | NA | NA | NA | NA | Relocation to new CCCPA premises |  |
| Percentage of gender segregation from total number of people trained (PRELT, DDR, Peacekeeping, WPS, Peacemaking & Peacebuilding, HT&SM) |  |  |  |  | 68% Male 32% Female | 68% Male 32% Female | 68% Male 32% Female | 68% Male 32% Female | 68% Male 32% Female | 68% Male 32% Female | 68% Male 32% Female | 68% Male 32% Female | 100% |  |
| Percentage of gender segregation from total number of people trained(pre-deployment trainings) |  |  |  |  | 100% Male | 100% Male | 100% Male | 100% Male | NA | NA | NA | NA | 100% |  |
| Percentage of military, police & civilians from total number of people trained (PRELT, DDR, Peacekeeping, WPS, Peacemaking & Peacebuilding, HT&SM) |  |  |  |  | 80% Civilians 12% Police 8% Military | 80% Civilians 12% Police 8% Military | 80% Civilians 12% Police 8% Military | 80% Civilians 12% Police 8% Military | 80% Civilians 12% Police 8% Military | 80% Civilians 12% Police 8% Military | 80% Civilians 12% Police 8% Military | 80% Civilians 12% Police 8% Military | 100% |  |
| Percentage of military, police & civilians from total number of people trained (pre-deployment trainings) |  |  |  |  | 100% Military | 100% Military | 100% Military | 100% Military | NA | NA | NA | NA | 100% |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans:[Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |  |  |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |  |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |  |  |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |  |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |  |  |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Quarterly, and at the end of the project (final report) both narrative and financial to be submitted to the Government of Japan and Switzerland |  |  |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project.In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |  |  |

# Quarterly Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Quarter |  |  |  |  |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 |  | Funding Source | Budget Description | Amount |
| Output 1: Enhancing African and Arab communities’ resilience to radicalization and extremism leading to terrorism and other transnational threats, including capacity building in the field of disarmament, demobilization and reintegration | Activity 1.1: | USD 21,459.22 | USD 21,459.22 | USD 21,459.22 | USD 21,459.22 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 | CCCPA | GOJ UNDP |  | USD 85,836.88 |
|  |  Update needs assessment, identify research areas and conduct research. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Recruit technical staff |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Contract appropriate implementing partners with technical knowledge to assist CCCPA in course design and training delivery. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Partnerships & communications |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2: Implement trainings/ workshops in the area of Preventing Radicalization and Extremism Leading to Terrorism (PRELT), DDR and Transnational Threats | USD - | USD 25,000.00 | USD 25,700.00 | USD 25,000.00 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 |  |  |  | USD 75,700.00 |
|  | Sub-Total for Output 1 |  |  |  |  |  |  |  |  |  |  |  | USD 161,536.88 |
| Output 2: Enhanced African & Arab capacities peacekeeping | Activity 2.1: |  |  |  |  |  |  |  |  | CCCPA | GOJ UNDP |  | USD 75,543.32 |
|  |  Update needs assessment, identify research areas and conduct research. | U,SD 18,885.83 | USD 18,885.83 | USD 18,885.83 | USD 18,885.83 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 |  |  |  |  |
|  |  Recruit technical staff |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Contract appropriate implementing partners with technical knowledge to assist CCCPA in course design and training delivery. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Partnerships & communications |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.2: Implement trainings and workshops on issues related to peacekeeping | USD 5,495.95 | USD 7,931.42 | USD 7,931.42 | USD 80,495.95 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 |  |  |  | USD 101,854.74 |
|  | Sub-Total for Output 2 |  |  |  |  |  |  |  |  |  |  |  | USD 177,398.06 |
| Output 3: Enhancing African and Arab capacities in peacemaking, peacebuilding and the implementation of the women, peace and security agenda | Activity 3.1: | USD 13,495.62 | USD 13,495.62 | USD 13,495.62 | USD 13,495.62 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 | CCCPA | GOJ UNDP |  | USD 53,982.48 |
|  |  Update needs assessment, identify research areas and conduct research. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Recruit technical staff |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Contract appropriate implementing partners with technical knowledge to assist CCCPA in course design and training delivery. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Partnerships & communications |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2: Implement trainings/workshops on issues of Conflict Prevention and Resolution, and Peacebuilding | USD 23,333.33 | USD 23,333.33 | USD 23,333.34 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 |  |  |  | USD 70,000.00 |
|  | Sub-Total for Output 3 |  |  |  |  |  |  |  |  |  |  |  | USD 123,982.48 |
| Output 4: Enhancing African capacities in combating human trafficking and smuggling of migrants | Activity 4.1: |  |  |  |  |  |  |  |  | CCCPA | Swiss |  |  |
|  | Training methodology, curricula and partnerships are developed |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Recruit technical staff | USD 7,780.06 | USD 7,780.06 | USD 7,780.06 | USD 7,780.06 | USD 7,780.06 | USD 7,780.06 | USD 7,780.06 | USD 7,780.06 |  |  |  | USD 62,240.48 |
|  |  Partnerships & communications | USD 0.00 | USD 1,000.00 | USD 0.00 | USD 1,000.00 | USD 0.00 | USD 1,000.00 | USD 0.00 | USD 1,000.00 |  |  |  | USD 4,000 |
|  | 4.2:Implement trainings/workshops on issues of migration management including combating human trafficking and smuggling of migrants | USD 24,863.00 | USD 66,699.06 | USD 25,944.82 | USD 24,750.59 | USD 24,750.59 | USD 24,750.59 | USD 28,760.59 | USD 25,000.00 |  |  |  | USD 245,519.09 |
|  | Sub-Total for Output 4 |  |  |  |  |  |  |  |  |  |  |  | USD 311,759.57 |
| Output 5: Support for upgrading CCCPA’s training, convening and research infrastructure | Activity 8.1: State of the art facilities and equipment are acquired for CCCPA’s new premises | USD 79,861.11 | USD 79,861.11 | USD 79,861.11 | USD 79,861.11 | USD 18,287.04 | USD 18,287.04 | USD 18,287.04 | USD 18,287.03 | CCCPA | GOJ UNDP |  | USD 392,592.59 |
|  | Sub-Total for Output 5 |  |  |  |  |  |  |  |  |  |  |  | USD 392,592.59 |
| Project Management Unit (PMU) |  Recruit project team | USD 39,299.27 | USD 39,299.27 | USD 39,299.27 | USD 39,296.88 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 | CCCPA | GOJ UNDP |  | USD 157,194.69 |
|  |  Provide necessary trainings to project staff |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Partnerships and communications |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Communications and visibility | USD 2,500.00 | USD 2,500.00 | USD 2,500.00 | USD 8,399.40 | USD 0.00 | USD 0.00 | USD 0.00 | USD 0.00 |  |  |  | USD 15,899.40 |
|  |  Host Project Board Meeting |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  Conduct end of project evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Advocacy and visibility |  |  |  |  |  |  |  |  |  |  |  | USD 8,035.71 |
|  | Sub-Total for PMU |  |  |  |  |  |  |  |  |  |  |  | USD 181,129.80 |
| General Management Support (8%) |  |  |  |  |  |  |  |  |  |  |  |  | USD 107,871.96 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | USD 1,456,271.34 |

# Governance and Management Arrangements

- The project will be nationally executed and implemented by CCCPA, in accordance with the UNDP National Implementation (NIM) guidelines. UNDP rules and regulations for recruitment, procurement, and award criteria will be followed for all project activities related to the contracting of services, supplies and grants. The management arrangements for this project are in line with the UNDP requirements as reflected in the UNDP User Guide and are as follows:

Project Manager

Project Organisation Structure

Project Board

Executive

Ministry of Foreign Affairs

Senior Beneficiaries

African Ambassadors to Egypt, Ministries of Foreign Affairs, Interior, Defense

Senior Supplier

CCCPA, Ministry of Foreign Affairs, Government of Japan,  Government of Switzerland, UNDP

Project Assurance

UNDP PO

(UNDP)

Project Management Unit

- The Project Board, which contains three roles (Executive, Senior Supplier and Senior Beneficiary), will be established to take executive management decisions and provide guidance to the Project Manager, including final approval of project revisions and Annual Work Plans. However, any proposed/substantive amendments to the action and/or budget will be first submitted to the GoJ for prior approval. Project assurance reviews by this group will be made at designated decision points during the course of the project when ready, or as necessary when raised by the Project Manager.

- The Project Manager (PM) will act as secretariat for the committee, being responsible for convening the meetings, preparing the agenda, overseeing preparation of materials for presentation to the meeting and for preparing and distributing minutes of the meetings.

- The Project Manager will be responsible for overall management of the project that includes overseeing project (activities) implementation, reviewing/revising work plan, overseeing M&E and reporting, monitoring and controlling budget and communicating with UNDP, Government of Japan and Government of Switzerland, to ensure timely delivery and achievement of the project. The PM will also be responsible for the project’s networking and outreach with potential implementing partners and beneficiary organisations. The PM will manage the PMU.

- The Project Management Unit (PMU) will be responsible for implementation, coordination and overall management of the project, including compliance with financial and progress reporting requirements of the Government of Egypt, UNDP, the Government of Japan and the Government of Switzerland. It is comprised of the Project Manager, the Program Coordinator, and relevant officers (including Operations, Visibility and Communications, Administrative and Financial, etc.).  The PM will manage technical staff such as Technical Advisor(s), Program Officer(s), Program Associate(s) Researcher(s), and short-term consultants, who will be recruited under each output for relevant needs of activities. The PMU is responsible for maintaining budgets as well as for ensuring independent auditing and evaluation of the project, as per the UNDP NIM guidelines. The PMU reports directly to the PM.

- Project Assurance: The role is held by UNDP and supports the Project Board by carrying out objective and independent project oversight and monitoring functions. This role ensures that the project is implemented to achieve results as planned in a timely and efficient manner. UNDP is responsible for designating a person to provide this oversight, which is mandatory for all projects.

# Legal Context and Risk Management

Legal Context Standard Clauses

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

Risk Management Standard Clauses

- Consistent with the Article III of the SBAA [or the Supplemental Provisions], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document [and the Project Cooperation Agreement between UNDP and the Implementing Partner].

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml. This provision must be included in all sub-contracts or sub-agreements entered into under/further to this Project Document.

- Consistent with UNDP’s Programme and Operations Policies and Procedures, social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

# ANNEXES

- Risk Analysis. Use the standard Risk Log template. Please refer to the Deliverable Description of the Risk Log for instructions

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Regional countries may choose not to participate in trainings due to their political or security issues | December 2017 | Political | Probability: 3 Impact: 3 | Expand target beneficiary groups Training restructured to address sensitivities | CCCPA |  |  |  |
| 2 | CCCPA has limited oversight over the selection of trainees particularly regional participants. | December 2017 | Strategic | Probability:3 Impact:3 | Continued communication with counterparts to insist on CCCPA oversight of selection of trainees with appropriate background More comprehensive database of participants being developed with full CV | CCCPA |  |  |  |
| 3 | Some project areas may be sensitive to some governmental partners | December 2017 | Political | Probability: 3 Impact: 3 | Hold workshops with relevant stakeholders to try to resolve sensitive issues so they may be addressed Sensitive use of language | CCCPA |  |  |  |
| 4 | Volatile exchange rate/inflation may result in extra savings or costs | December 2017 | Financial | Probability: 3 Impact: 3 | CCCPA will maintain strict monitoring and will consult with UNDP and Embassy of Japan the targets | CCCPA |  |  |  |

- Project Board Terms of Reference and TORs of key management positions

Annex 1 - Description of Output 4 Activities

CCCPA utilizes its own curriculum tailored specifically and professionally for the courses delivered on the subject. Instructors and lecturers from the CCCPA roaster as well as partners from concerned national authorities (including the Egyptian Ministries of Foreign Affairs, Defense, Interior, Justice and the National Coordinating Committee for Combating and Preventing Illegal Migration and Trafficking In Persons (NCCPIM & TIP)) deliver  different components of the trrainging,  providing a multi-sectorial national perspective on addressing both crimes. CCCPA also partners with experts from international and regional organizations including the International Organization for Migration (IOM), United Nations High Commissioner for Refugees (UNHCR), the European Asylum Support Office (EASO) as well as IGAD, COMESA and the South African Institute for Security Studies (ISS).

Activities:

A. 3 trainings targeting 60 African officials on transnational threats including human trafficking and smuggling of migrants

Target Group

CCCPA’s trainings adopt a unique integrated multidimensional approach, which brings together civilian, police and military mid-career professionals from African national governments with direct responsibilities for combating human trafficking and smuggling of migrants.  Participants in the trainings are nominated based on pre-determined criteria developed by CCCPA, including most notably that they are mid-career professional with direct responsibility for combating human trafficking and smuggling of migrants in their countries/organizations. Nominations for participation are to be presented by national authorities and participating continental and regional organizations through official channels.

Training Objective & Methodology

Acknowledging that human trafficking and smuggling of migrants are interlinked transnational threats, CCCPA trainings adopt the “3P” (+1) paradigm--prevention, protection, and prosecution--the fundamental framework established by the Palermo Protocol for Member States to combat human trafficking. The fourth “P” (or +1)—partnership-- was later introduced to address the need for cooperation between national authorities and the international community to respond to the transnational nature of these threats. Officials trained are expected to utilize this framework to intervene and assess national needs as well as provide context-specific measures whether on the operational, legislative, or policy level in the four different focus areas.

Training Modules

Adopting a victim-centered approach, the trainings will focus on specific key areas, including the basic concepts related to human trafficking  and smuggling of migrants, their different characteristic and forms and the root causes of both crimes using conflict analysis tools.The training also covers international and regional legal frameworks against human trafficking and smuggling of migrants; the role of multilateral and bilateral cooperation in combating human trafficking and smuggling of migrants; exchanging national experiences and best practices as well as acquiring necessary skills for identifying victims and crime scene investigation. The trainings also aim to equip African officials with the necessary tools for effective development of national protection and prevention mechanisms for victims and vulnerable groups especially women and children. The program constitutes a highly interactive, case-based scenario that aims to strengthen the role of regional officials in identifying and interviewing victims; investigating crime scenes; and designing, developing, and reforming national laws, strategies, and action plans to combat both crimes.

B.1 workshop targeting 35 African officials  on enhancing best practices & lessons learned among African officials on design and  implementation of laws, national plans, and national strategies to combat human trafficking & smuggling of migrants.

Target Group

The  workshop will bring together 35 senior government officials from the ministries of Interior, Defense, Foreign Affairs and Justice, in addition to parliamentarians from the North, East and Horn of Africa, West Africa, and Sahel regions.

Training Objective & Methodology

The workshop will be conducted to exchange best practices and lessons learned among countries that already developed legislations and laws, strategies and/or action plans and to capacitate African countries lacking legislation, national action plans and strategies to develop their own.

The aim of the workshop will be achieved through adopting an interactive approach that mixes theory with practice through:

- Presenting the main elements for developing a model law on combating Trafficking in Persons and Smuggling of Migrants.

- Presenting and discussing the Egyptian model as a case study for combating both crimes through: - Analyzing the content and objectives of the new Egyptian legislation and the potential impact of its implementation. - Analyzing the content and objectives of the new Egyptian strategy and action plan as well as the challenges of their implementation.

- 3- Exercise-based activities will be conducted on how to draft a strategy and an action plan as part of building participants capacities on combating both crimes.

- 4- Engaging participants in moderated discussions to exchange knowledge and expertise on combating both crimes.

C. 1 workshop targeting 20 African officials on mainstreaming migration in development policies.

Training Objective

- CCCPA will also organize a workshop for for 20 African officials and practitioners to enhance their capacities on mainstreaming migration in national development policies. The worshops will specifically aim to bolster human development outcomes and mitigate risks as well as increase resilience of migrants, their families and local communities in countries of origin and destination.

Target Group

- The officials will be selected from the top hosting African nations of migrant and refugee communities as well as source countries to offer them support in effectively addressing migration and preventing exploitation in a comprehensive manner through identifying migration linkages with national development priorities.

Training Methodology

- The workshop will cover the impact of migration on development through the 3Ts approach: transfer of people, transfer of knowledge, and transfer of financial assests. The workshops will also cover the various processes that can be utilized for proper integration of migration in the development planning cycle, interventions to maximize migration benefits for development including through employment, education, legal and social protection, health services, awareness raising, targeted research and dissemination of information,  as well as drafting a national action plan and/or a strategic framework adopting a rights-based approach and taking into consideration special needs of vulnerable groups especially women and children.

The Institute for Economics & Peace, “Global Terrorism Index 2017”. P.62. Available at: http://visionofhumanity.org/app/uploads/2017/11/Global-Terrorism-Index-2017.pdf

Ibid

Reitano, T. et al (2017) Examining the Nexus between Organised Crime and Terrorism and its implications for EU Programming, Counter-terrorism Monitoring, Reporting and Support Mechanism (CT Morse)

Institute for Security Studies. “Fem-Wise Africa aims to include more women in peace processes.” May 2018. Available at: https://issafrica.org/pscreport/on-the-agenda/femwise-africa-aims-to-include-more-women-in-peace-processes

Council on Foreign Relations. Women’s participation in peace processes. January 2018. Available at: https://www.cfr.org/interactive/womens-participation-in-peace-processes/syria

The governance capacity index of Sub-Saharan Africa is lower than that for the Middle East and North Africa, and is significantly below the world average.

UN DESA, ‘International Migration Report 2017’

UNHCR Global Report 201700 – Africa Regional Summary

Ibid

According to the US State Department Report on Trafficking in Persons report (2017) and the UNODC database of legislation on Human Trafficking and Smuggling of Migrants, 35 African countries have drafted national legislation on combating Human trafficking and/or Smuggling of Migrants, 34 have developed action plans, 40 have established national bodies/committees to monitor the implementation of their anti-trafficking policies and only 6 have formulated national strategies. See U.S. Department of State, “Trafficking in persons report 2017”. Accessed July 13, 2017. https://www.state.gov/j/tip/rls/tiprpt/2017/index.htm

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

Use bracketed text only when IP is an NGO/IGO