Global Security Fund

2021/2022

Final Report Back

Report to be prepared by agency responsible for implementation, and reviewed by MFAT sponsoring division before submission to the Global Security Fund Manager.

Please attach any additional material you consider relevant for evaluating the project.

| Project Title: Gender-Responsive Peacekeeping Training |  |
| --- | --- |
| Name: Amina Helal | Report Date: 26/10/2022 |
| Division/Post: CAI | Bid Amount: NZD$60,226.85 |
| Position: Women, Peace and Security Program Officer |  |

Date and location of project/activity completion:

- Monday 10 October – Thursday 13 October 2023. - Cairo International Centre for Conflict Resolution, Peacebuilding and Peacekeeping (CCCPA), Cairo, Egypt.

Description of project/activity:

Activity Description - The CCCPA held a bespoke four-day training course for 10 participants from 6 countries, which expanded on the successful Training of Trainers (ToT) course funded under the New Zealand Global Security Fund in 2018 and implemented by CCCPA in 2019 in association with UN Women. - The training focused on Arab male and female officials mandated to train/work in the field of UN Peacekeeping, and covered the topic of Gender and Peacekeeping. The training was delivered in Arabic, the participants native language, for greatest impact. - New Zealand experience and expertise in WPS in peacekeeping was utilised in the training course. Staff Sergent Laura McIntyre, currently deployed with the NZDF contingent to the MFO, attended at led a session during the training. The session focused on New Zealand’s experience advancing the WPS agenda in peacekeeping. - Due to fortuitious timing, the training was opened by New Zealand Minister of Defence Peeni Henare, and CCCPA Director General, Ahmed Abdel-Latif on Monday 10 October, during the Minister’s visit to Egypt. New Zealand Ambassador to Cairo, Greg Lewis, spoke at the official closing ceremony of the training and at the official Reception on Thursday 13 October. Activity Goal - This project sought to advance the implementation of the Women, Peace and Security (WPS) agenda initiated by the UN Security Council Resolution 1325 in 2000, through enhancing Arab countries’ participation in peace operations and advancing gender-responsive peacekeeping. - The project built on ongoing efforts to build national Arab capacity to play meaningful, gender-sensitive roles in the field of peace support and peace keeping. This is particularly important in light of the Arab countries’ significant efforts to enhance their participation in UN Peace Operations and contribute to increasing the protection of civilians, in particular women and girls in these settings. - The project demonstrated New Zealand and Egypt’s commitment to advance the implementation of the WPS agenda, by tackling the issue of gender and the prevention of sexual exploitation and abuse in peacekeeping operations. Activity – Context - UN peacekeepers are deployed to restore and help create the conditions for sustainable peace. Both the WPS agenda and the UN Secretary General’s Action for Peacekeeping (A4P) Initiative shed light on the critical role of female peacekeepers in achieving operational effectiveness in dangerous environments around the world. - Similarly, gender-responsive peacekeeping has been highlighted as a key priority given the need to consider women’s vulnerabilities in these settings, including their exposure to risks of Sexual Exploitation and Abuse (SEA). - Significant efforts are underway in the UN to prevent and eliminate SEA in peacekeeping operations. In 2012, the UN launched its zero-tolerance policy, urging all Member States deploying peacekeepers to hold perpetrators accountable. UN Security Council resolution 2272 (2016) demands the replacement of contingents from countries failing to hold perpetrators accountable for sexual exploitation/abuse. - In 2017, the Secretary-General developed a new strategy to achieve measurable improvements in the prevention and response to SEA. These efforts underscore the importance and significance of enhancing training and capacity building activities for military, police and civilian professionals deployed to UN peacekeeping or peace support missions.

Extent to which activity achieved objectives and outcomes approved by the GSF Committee:

How the objectives and outcomes were achieved - The project sought to achieve the above objectives by building capacities (training) of 10 (both male and female) Arab participants and raising awareness of the centrality of the WPS agenda to efforts aimed at preventing conflict, keeping and sustaining peace. - CCCPA delivered the training over four days to 10 participants (5 male and 5 female) from 6 countries namely: Egypt, Jordan, Morocco, Algeria, Tunisia and Djibouti. This was achieved to ensure a gender-balance as well as the objective of the training, enhancing the understanding of both Arab men and Arab women of the Women, Peace and Security (WPS) agenda, the principles of gender analysis, the standards of conduct and discipline in UN Peacekeeping, the issues of Sexual Exploitation and Abuse including the reporting methods, the investigation process as well as the link between the prevention of such crimes and the effectiveness of peacekeeping operations. - The training covered the following topics relevant to UN peacekeeping mandates (1) WPS-Gender dimension and women empowerment; (2) Protection of Civilians; (3) UN Code of Conduct and Standards on the Prohibition of Sexual Exploitation and Abuse (SEA); and (4) Consequences of SEA, and Reporting SEA. The full agenda of the training is attached for reference. - The Activity capitalised on CCCPA’s regional expertise and network of partners to achieve the following outcomes: 1. Enhancing engagement of Arab components participating in UN Peacekeeping, which contributes to the first GSF objective to enhance New Zealand’s security by supporting bilateral, regional and global initiatives that promote peace and stability. The training sessions were held in Arabic, and for the sessions delivered with the support of UN experts, translation was also provided. 2. Strengthening national Arab capacity in the area of gender in Peacekeeping, which contributes to the second GSF objective to improve the capabilities of partner governments to respond to security threats that could impact regional and global stability. In fact, the criteria put for the nomination of participants covered gender-balance, but also factors of relevance to the topic. Participants are either coming with a background in UN Peacekeeping, or willing to be deployed and participate in peacekeeping missions. 3. Experience-sharing between the different Arab countries and New Zealand (through the participation of NZDF) on challenges and opportunities as it relates to the WPS agenda, which contributes to the third GSF objective to help strengthen bilateral relations and support New Zealand’s participation in regional and global fora in relation to security goals or objectives. - Support for this project will contribute to the Ministry’s strategic objectives in advancing and protecting the security and safety of New Zealand and New Zealanders in particular, through contributing to NZ’s participation in international military and peace support operations contributing to a more stable environment. It also aligns with MEA’s Africa Strategy and is a priority project for MEA this year. - The training course was also covered in different media outlets as a successful partnership with the government of New Zealand, on a significantly important and impactful activity for advancing peace and security. It came at a special timing during the month of October, also known as the Women, Peace and Security month, and the month of the anniversary of the UNSCR1325.

How project contributed to:

GSF fund objectives: (Sophie to complete) - Xxx

Post/Divisional priorities: (Sophie to complete) - Xxx

What follow up is proposed/ provisions made for monitoring, or ensuring the sustainability of, the overall initiative or specific outcomes: clearly note any efforts to ensure that knowledge derived from any training is retained.

Participants have received USBs including the training materials (including the presentations of the UN experts). In addition, participants have completed pre-tests and post-tests with the same questions, as part of the monitoring and evaluation method used at CCCPA. Participants can be provided with the same test in a few months, to test their knowledge.

Feedback from partners or participants

Feedback from training participants and delivery partners Positive Feedback - The participants claimed that the training was successful and they have praised the choice of high-level panelists. - There is no big gap between the pre-deployment training and the real mission which is very good for participants attending the training. - The whole session was very detailed from the beginning until the end. It has also provided convenient and quality data. - The WPS team was cooperative and they had a high level of energy from the first day until the last one. - The program was flexible and the logistics team was attentive and “classy”. - They praised the sessions presented by the Brigadier General Ehab Khedr and how effectively he had delivered the information and interacted with the participants. - They praised the high level of interaction and energy of Assal and Amina and the quality of the sessions presented by them. Negative feedback - The training duration was short relative to the amount of information presented - The training should be inclusive of more Arab countries. - The training was lacking audiovisuals (videos). - The icebreaker, the participants’ and speakers’ presentation were not enough in the beginning of the training to allow participants to get to know each other. - Having two touristic trips at one day is exhausting. Recommendations - Other Arab countries should be invited to attend this training so as to benefit from it. - Give feedback after each session instead of having to rate all sessions at once. - Participants should be given the option to provide feedback online. - The training should begin on Saturday instead of Monday - The duration of the training should be longer (number of days) as the training was dense and beneficial and cannot be digested in just two or three days. - Since the training is intense, each day should end early enough (by 3pm at the lates) to allow participants to absorb the information they received. - More activities and videos should be integrated during the sessions in order to interact with the panelists and stay present and focused. - Egyptian gender advisors in Minusca should be invited to give utilizer experience during the training and to stay updated as the UN missions are in continuous change. - A video discussing the proper way to deal with female peacekeepers who were victims of aggression should be produced and presented during the training. - Videos should be presented to show a simulation of what happens on the ground. Evaluation forms from training participants are attached.

Breakdown of budget and resource outcomes. Clearly note any underspend/overspend at completion

Summary of budget Description; Budget as of 3 October 2022 (USD); Actual Expenditure (USD). Air Tickets; USD 1,353.26; USD 3,882.50. Accommodation, Meals & Parking; USD 2,897.50; USD 4,841.56. A/V Equipment & Branding; USD 6,603.60; USD 4,789.06. Conference Facilities; USD 4,449.85; USD 4,047.44. Ground Transportation; USD 857.60; USD 1,146.65. Other Costs; USD 501.42; USD 1,114.21. Management Fees; USD 1,666.32; USD 2,303.31. TOTAL; USD 18,329.56; USD 22,124.73. TOTAL RECEIVED FROM NZ; USD 37,783.47. BALANCE REMAINING (TO BE REFUNDED TO NZ); USD 15,658.74. Please see full budget document(s) attached.

Are there any plans to re-apply for funding for similar projects in the future? What Lessons have been learnt in the implementation of this project that could be applied in developing possible future projects:

Lessons learned include - For training purposes, CCCPA had prepared some slides using translated key terminology in Arabic to meet the participants needs. Building on this practice, some participants expressed interest having a printed document with key technical words in both languages English and Arabic; a glossary with such terminology could be beneficial if developed as a pocket-guide. - We could have requested more nominations from these countries. Increasing the number of participants could be done as a lesson learned in future activities. - Increasing the duration of the training could allow for full days for application of materials through practical activities and simulation. - Some participants were keen to showcase more cultural examples in their countries to the diverse group of participants in the session on cultural considerations in peacekeeping settings. More slots in the agenda could be assigned- including as ice breakers- to participants’ countries’ presentations- given that the topic could be useful to better understand gender dynamics in each country.

| Contact for further information on the project |  |
| --- | --- |
| Name: | Iman Keira |
| Title/position/organisation: | Program Coordinator CCCPA |
| Phone: | +20 (2) 27 92 89 50, 113 |
| Email: | iman.keira@cairopeacekeeping.org |