Sustainable Cities in Turkmenistan: Integrated Green Urban Development in Ashgabat and Avaza

2024 Annual Project Progress Report

GEF

| Implementing Agency: | United Nations Development Programme (UNDP) |
| --- | --- |
| Project ID: Gender Marker: Digitalization Marker: Project Title: | UNDP PIMS ID: 5452; GEF ID: 9279 Gen2 n\a Sustainable Cities in Turkmenistan: Integrated Green Urban Development in Ashgabat and Avaza |
| Project Duration: | 01 January 2018 – 31 December 2022 |
| Country / Region: | Turkmenistan / Central Asia |
| Funding Partner/s: | GEF Trust Fund |
| Responsible Parties: | State Committee for Environmental Protection and Land Resources of Turkmenistan |
| Reporting Period: | 01 January 2024 – 31 December 2024 |
| Project Manager: | Mr. Batyr Ballyyev (batyr.ballyyev@undp.org); Project Web-site: https://www.undp.org/ru/turkmenistan/projects/ustoychivye-goroda-v-turkmenistane-kompleksnoe-razvitie-zelenykh-gorodov-v-ashkhabade-i-avaze |

<INSERT LOGOS OR FLAGS OF ALL DONORS TO PROJECT / PROGRAMME>

Please use font Proxima Nova and font size 10 for all text on narrative sections. You may refer to UNDP branding guidelines through this link.

Table of Contents

I.	Executive Summary	5

II.	Introduction / Background	7

III.	2024 Progress Review: Key Activities and Results	8

Section 1: Analysis of Theory of Change (ToC)	8

Section 2:  Overall progress against outcomes	8

Section 3: Monitoring and Evaluation of activities.	8

Section 4: Progress against each output	10

Section 5: Cross-Cutting Integration	14

IV.	Partnerships and Sustainability	14

V.	Update on risks and mitigation measures	15

VI.	Key Challenges, Lessons Learned and Recommendations	15

VII.	Financial Summary	16

VIII.	Annexes	18

Annex I: Progress Review: detailed matrix of activities and results	18

Annex II: Updated Risk Log	25

Annex III: Annual Work Plan for (next year)	27

Annex IV: Assets List.	27

Annex V: Knowledge Generation	27

(Note: Please use table of contents maker to ensure automatic updating of pages and content).

Acronyms

| AWP CIS CO CTA EE ERs ESCO GEF GHG IFI INDC IRH kWh LED LPAC M & E MAEP MCA MoE MoU MSW MTR MW MWh NDC NGO NIM PB PIF PIR PM PMU PRF ProDoc RBEC RE RFP RTA SESP ToR TJ UNDAF UNDP UNFCCC | Annual work plan Commonwealth of Independent States Country Office Chief Technical Adviser Energy Efficiency Emissions Reductions Energy Service Company GEF Global Environment Facility Greenhouse gases IFI International Financial Institution Intended Nationally Determined Contributions Istanbul Regional Hub (of UNDP) Kilowatt-hour = 3,600 kilojoules (KJ) = 3.6 megajoules (MJ) Light-Emitting Diodes Local Project Appraisal Committee M & E Monitoring & Evaluation Ministry of Agriculture and Environment Protection Ministry of Construction and Architecture Ministry of Energy Memorandum of Understanding Municipal Solid Waste Mid-Term Review Megawatt Megawatt Hour= 1,000 kWh Nationally Determined Contributions Non-governmental Organization National Implementation Modality Project Board Project Identification Form Project Implementation Review Project Manager Project Management Unit Project Results Framework Project Document Regional Bureau for Europe and the Commonwealth of Independent States Renewable Energy Request for Proposal Regional Technical adviser Social and Environmental Standards Procedure Terms of Reference Terajoule = 278 MWh United Nations Development Assistance Framework United Nations Development Programme United Nations Framework Convention on Climate Change |
| --- | --- |

- Executive Summary

Context and key developments

The population of Turkmenistan has steadily grown during the last decades with the country undergoing a steady shift toward greater urbanization, with an increasing proportion of citizens living in cities. The most notable urban growth has taken place in Ashgabat, the capital of Turkmenistan, and also in the new resort zone of Avaza on the Caspian Sea. The development push in Ashgabat and Avaza has led to increased negative environmental impacts including gradually increasing GHG emissions mainly from increased municipal solid waste (MSW) and the rising use of private motor vehicles. The Project “Sustainable Cities in Turkmenistan: Integrated Urban Development in Ashgabat and Avaza” (otherwise referred to as “Project”) sought to expand on untapped technical potential to: (a) decrease the volume and impact of private vehicle traffic in all cities; (b) further expand efficient street lighting; (c) reduce waste and increase recycling; and (d) introduce “green” practices to hotels. The development challenge of the Project was to measurably reduce the negative impacts of urban growth in Turkmenistan while also advancing social and economic development goals.

Progress against outputs and outcomes

The Project achieved cumulative GHG emission reductions of 952,000 tons of CO2 exceeding the target by 162%.  As of end of this reporting period, a complete phase out of LED lights in Ashgabat and Avaza was achieved along with a switchover from low voltage to medium voltage energy transmission for the city of Ashgabat as a whole. The total amount of avoided energy consumption is 4,227 TJ across all sectors, which represents 67% of the TJ target. Based on projections made on the basis of the most recent measurements, the Project is on track to bring the total energy reductions to 4,613 TJ thereby delivering 74% of the TJ savings.

Relative to Output targets, some of the targets have been achieved or exceeded, such as the following:

- Output 1.1: “Technical justifications were prepared and implemented for energy-efficient street lighting in Ashgabat” as  all of the Ashgabat and Avaza city lights are now LED-based.

- Output 1.4: “Volumes of waste is reduced and recycling was increased in Ashgabat” (a 17% increase from recycled volume share was achieved in 2024)

- Output 2.1 “Improved capacities and enabling conditions in Avaza for integrated low-carbon and climate-resilient tourism development” as half of the hotels underwent energy audits, trainings in EE, RE, and water saving technologies and early participants have seen EE and RE technology installed.

Some of the targets have seen partial achievement, such as the following:

In Output 1.3. (“City plans for sustainable development is developed and approved”) and Output 2.2 (“Reduced GHG emissions and other negative environmental impact through interventions involving tourism facilities and infrastructure in Avaza”), a partial progress was achieved: one city of 60,000 adopted a sustainability plan (vs. two cites with a total population of 175,000 adopting such plans), and a reduction of energy consumption and water consumption in participating Avaza hotels was 6% (against a target of 10%).

Some of the Outputs have been revised (such as for Output 1.2. “Sustainable urban transport solutions in Ashgabat developed and applied”) to preparation of a review of international fuel standards to identify those that might be appropriate for Turkmenistan for the period of up to 2030 and organize a discussion of the proposed standards with the agencies and the expert community.

Outcome 3 (“Nationwide replication and scaling-up of results of first two components via information dissemination, enhancement of capacity of agencies and managers, and adoption of policies and regulation”) saw a partial completion because – although no fuel economy standards were developed due to lack of access to the required level of decision-making in this sector, which had been seriously reshaped after the start of the project by successive government reshuffles, - street lights replacements with LEDs have reached in both urban areas a scale that exceeded the boldest projections.

Key challenges and risks

The key risks have materialized in the hotel and transport sector. In the transport sector, continuous demotion of the urban public transport agency resulted in lack of its capacity to legislate and set standards while the task of standard setting has been split between the customs authorities and statistical agencies setting equipment standards – none of which having GHG KPIs.

Lack of privatization in the hotel sector (the case for which was weakened by the COVID-pandemic after which the country saw a sustainable reduction of international tourists) kept energy and water tariffs as their pre-project low level (the tariffs are subsidized by the state for state-owned building stock). As a result, investments into EE and RE technologies become financially unprofitable as their payback period significantly exceeds the lifetime of any EE/RE measures running into 35-60 years.

The lesson learnt here is that – while government reshuffling and demotion of certain functions is a risk that is hard to predict and impossible to manage, it’s certainly not advisable to plan co-investment / co-financing in an area plagued by extremely low tariffs at the start of the project (such as was the case in the hotel sector).

Utilization status

The utilization rate stands at $5,837,574.08 [96.3% of the total of $6,060,046], including $619,773 [10.2%] utilized in the current reporting period.

Key recommendations

It’s recommended that the UNDP shares results of the project following the end of the Terminal Evaluation with the highest levels of the government in order to ensure that the government is kept abreast of the sustainable results achieved by the project and to praise the stakeholders that were instrumental in achieving the results.

- Introduction / Background

Project Background and Rationale

Population growth and economic development have led to rapid expansion of cities in Turkmenistan over the past two decades, most notably in the capital city of Ashgabat and the resort zone of Avaza on the Caspian Sea.  This growth has had an increasing negative environmental impact – resource consumption, waste, local air and water pollution, and emissions of GHGs. The development challenge of the project is to measurably reduce the negative impacts of urban growth in Turkmenistan while also advancing social and economic development goals in the following sectors: urban transport, hospitality, street lighting, and waste management.

Main objectives and expected outcomes

The main objectives of the project were the following (along with the expected outcomes):

- Improved capacities and enabling conditions

  - in Ashgabat to identify, design and implement integrated low-carbon and climate-resilient solutions in public space (as measured by the number of institutions, covered by capacity building activities to identify and design and implement such integrated low-carbon and climate-resilient solutions)

  - in Avaza hotel sector for integrated low-carbon and climate resilient tourism development (as measured by reduced GHG emissions and other negative environmental impact through interventions involving tourism facilities and infrastructure)

- Reduced GHG emissions (as measured by reduction in electricity consumption from public outdoor lighting in Ashgabat and all of Turkmenistan and by a reduction in landfill waste from Ashgabat and Avaza relative to baseline from recycling and waste reduction programs)

- Nationwide replication and scaling-up of results of first two components via information dissemination, enhancement of capacity of agencies and managers, and adoption of policies and regulation (as measured by existence and content of fuel economy standards and incentives for passenger vehicles, number of cities of Turkmenistan (and total population therein) that formally adopt sustainability practices in transport, lighting, and waste management, and number of citizens reached by public-relations and knowledge-sharing on sustainable urban development).

These objectives relate to the overall national strategy of Turkmenistan on climate change. As part of the outputs, the Project assisted in furthering national climate change policies assisting in the adoption of a new national strategy on the Development of Renewable Energy, now operational until 2030. The objectives of the Project relate to such Sustainable Development Goals (SDGs) as SDG 6 (“Access to clean water and sanitation for all”) by reducing leakage to water sources from landfills thanks to an increase share of recycling), SDG 7 (Affordable and Clean Energy by making street lighting more efficient, widely available and reducing energy losses across the largest urban center), SDG 10 (Reduced inequalities in employment by promoting women-led NGOs), SDG 11 (Sustainable cities and communities by assisting in reducing expense on lighting urban areas), SDG 12 (Sustainable consumption and production by promoting recycling at the points of goods sale), SDG 13 (Climate change impacts by reducing GHG emissions and introducing sustainable development education modules in higher educational programs and respective trainings for policy-makers and facility managers), and SDG 15 (Sustainable land management by reducing the amount of materials destined for landfilling).

Project Approach

The Project was set up in a way to balance implementation efficiency with policy assistance and management checks: the Project Board met once per year and - in the later stages of the project – twice a year to assist the Team in accessing critical policy expertise and to make adjustments to activities and team composition as evidenced by any failures or as recommended by external experts (when a change in the LogFrame and team composition was recommended by the mid-term Project review and a follow-up Strategy review). Regular contact and discussions with the RTA and the RBEC were held throughout the implementation period that help elicit required lessons learned from peer regional and international projects.

The Knowledge Management approach was based on measurable outcomes such as the number of stakeholders and facility managers that participated in dedicated trainings and by monitoring the reach and readership of the public information distribution vehicles (such as newspaper sales, web-site and social media visits).

- 2024 Progress Review: Key Activities and Results

## Section 1: Analysis of Theory of Change (ToC)

The main assumption of the ToC (that urban growth in Turkmenistan leads to increased resource use, infrastructure needs, and pollution, requiring new solutions for long-term sustainability) still holds as the population continues to grow: it grew from 5.9 million at the time of ProDoc approval to over 6.2 million in 2024 bringing along a rise in energy consumption in the nation. The overall growth of the GDP (from $6,355 in current U.S. dollars in 2017 to $9,530) results in higher income levels and a concomitant growth in households energy intensities too. This necessitates intensification of the activities under the aegis of the original assumptions, namely that - while citizens have to gain more equitable access to more affordable energy – national policies have to stress maximum efficiency in delivering of that energy via related infrastructure while public services (such as street lighting, energy grids , or hospitality providers) have to become less wasteful while they embrace quality improvements (such as introduction of better quality lighting via LEDs).

## Section 2:  Overall progress against outcomes

The project has made significant strides toward its goal of accelerating the adoption of low-carbon and climate-resilient solutions in the cities of Avaza and Ashgabat. By piloting demonstration projects in LED lighting and RE in the hotel sector as proof of concept, it has successfully completed its last operational year. A terminal evaluation is currently ongoing with the draft report scheduled to be ready in December 2024. Throughout the past 12 months, the project management team has actively navigated challenges and mitigated risks. While transport-related initiatives faced persistent obstacles from the beneficiary agency in terms of policy adoption and lack of commitment for co-financing, the project strategically shifted focus to advance energy efficiency not just in street lighting but in the household energy delivery infrastructure too, along with good progress in waste management, renewable energy promotion, and continued contributions into draft Energy Efficiency and Renewable Energy bylaws that are being deliberated on the back of the respective national strategies, earlier adopted along the lines of the drafts produced by project-hired experts.

Although collaboration with the "Turkmenavtotransport" Agency – key to transport-related objectives and activities – was limited by the agency itself to token requests for international best practices in identifying “heat-zones”, such information materials (in the form of an Urban Sustainability Atlas that will feature strategies to prioritize investments in climate-resilient transport infrastructure) will prove invaluable to the agency following any change in the mandate of the agency and its potential upgrade to a larger force that it used to be in the ProDoc preparation and approval period.

The team remains dedicated to delivering in a concise form of lessons learnt following the issue of reports on energy audits of remaining hotels in Avaza that had committed to consideration of EE investments thereby creating a body of knowledge that can be scaled up beyond Avaza and Ashgabat to benefit other cities in Turkmenistan.

## Section 3: Monitoring and Evaluation of activities.

The project is currently undergoing a Terminal Evaluation with over 30 meetings with stakeholders planned across Ashgabat and Avaza, including leadership of the ministries that participated in the activities at various stages of the project implementation along with private sector organizations and hotel facility managers. A detailed meetings plan is presented below.

A Visit Program to Turkmenistan of Mr. Roland Wong, International Consultant for the Terminal Evaluation of the Project, (18-26 November, 2024)

| November 18, 2024 | - Meetings at the UNDP Office in Turkmenistan with UNDP Resident Representative/Deputy Resident Representative and UNDP Programme Specialist on Environment and Energy to discuss project activities. - Meting with the Project’s ICTA. |
| --- | --- |
| November 19, 2024 | Meetings with members of the Committee on Environmental Protection, Nature Management and Agro-Industrial Complex of the Mejlis of Turkmenistan: - with Nury Jumashov, Deputy Minister of Environmental Protection, GEF Operational Focal Point. - with D. Yagmurov, Head of the Environmental Protection Department, National Project Coordinator. - with specialists of the Environmental Control Service (ECS) of the Ministry of Environmental Protection. Visit to the ECS laboratories and familiarization with the equipment acquired within the framework of the project. |
| November 20, 2024 | Meetings at the Ministry of Energy of Turkmenistan: - with E. Kakaeva, Head of Department, Member of the Project Council. - with specialists of the State Energy Company "Turkmenenergo" and the Production Association "Ashgabatenergo". - Field visit by R. Wong to the pilot sites of the street lighting system project: Arzuv Bridge; Choganly Bridge; transformer substations and cable power lines of the electric networks of the Kopetdag etrap of Ashgabat. - Field inspection by R. Wong of the street warning system of Ashgabat in the evening (as a result of replicating the positive experience obtained within the framework of the project in pilot areas). - Online meeting of R. Wong with specialists of the State Energy Institute of Turkmenistan (SEIT) of the Ministry of Energy. - Online meeting of R. Wong with specialists of the Scientific and Production Center for Renewable Energy Sources at SEIT. - Online meeting of R. Wong with E. Zhuchenko, International consultant of the project on renewable energy issues. - Online meeting of R. Wong with V. Afanasyev, International consultant of the project on energy efficiency issues. - Online meeting R.Vonga with specialists from the regional EU-funded energy connectivity project (SECCA-II). |
| November 21, 2024 | - Meeting of R. Wong with specialists of the Ozone Center at the Ministry of Environmental Protection. - Meeting of R. Wong with specialists of the NAP project (UNDP/GCF/MOEP). - Meeting of R. Wong with specialists of the Aral project (UNDP/GCF/MOEP). - Meeting of R. Wong with the national employee of the temporary Secretariat (UNEP) Tehran Convention. - Meeting of R. Wong with specialists of the Regional GIZ project "Green - Central Asia." - Meeting of R. Wong with specialists of NPO Bosfor on women’s urban mobility - Meeting of R. Wong with specialists of the Agency "Turkmenavtoulaglary". - Meeting with a national expert on transport issues. |
| November 22, 2024 | - Meeting of R. Wong with A. Amangeldyev, Chief Engineer of the Main Directorate architecture of the Ashgabat City Hall, Member of the Project Council. - Meeting of R. Wong with employees of the Turkmen Society for Nature Conservation (TOOP). - Visit by R. Wong to pilot sites of the waste management project in Ashgabat. - Meeting of R. Wong with specialists of the Ministry of Education. - Meeting of R. Wong with teachers of the Department of Ecology of Turkmen State University. - Meeting of R. Wong with a national expert on energy efficiency issues. - Meeting with a national expert on "green" issues construction. |
| November 25, 2024 | A field visit to Turkmenbashi: - Meeting with the Manager of the Turkmenbashi City Hall. A field visit to Avaza: - Meeting with specialists of the pilot hotel "Khasyl" in Avaza. - Meeting with specialists of pilot hotels "Balkan", "Seyran", "Tolkun" in Avaza. - Inspection by R. Wong of the street signaling system of Turkmenbashi and Avaza in the evening (as a result of replicating the positive experience obtained within the framework of the project in pilot areas). |
| November 26, 2024 | - Debriefing meeting at the UNDP Office in Turkmenistan with UNDP Resident Representative/Deputy Resident Representative and UNDP Programme Specialist on Environment and Energy to discuss the results of the mission. - Final meeting with Project team for discussing the mission conclusions and recommendations. |

## Section 4: Progress against each output

| Project Output 1.1: Energy-efficient public lighting implemented in Ashgabat, with technical justification prepared for replication |  |  |
| --- | --- | --- |
| Output indicators | Targets | Progress against targets |
| Reduction in electricity consumption from public outdoor lighting in Ashgabat and all of Turkmenistan | Baseline: 192 million kWh AWP target: 1.5 million kWh | Reporting period: 40 million kWh Cumulative total: Out of 192 million (baseline), 282 million are achieved (the excess is due to underestimation of the baseline). |
| Project Output 1.2: Sustainable urban transport solutions in Ashgabat developed and applied |  |  |
| Output indicators | Targets | Progress against targets |
| Reduction in number of passenger-km of private car travel, via increased use of alternative modes and carpooling | Baseline: 12.7 billion passenger-km by private motor vehicle per year nationwide AWP target: Reduction by 0.5 percent (60 million passenger-km per year) | Reporting period: 0 km (0%). Cumulative total: 0 km (0%). Lack of progress on this indicator is due to a downgrade of the role Trasport Agency. However, lack of progress under the transport component has been compensated in terms of GHG emissions reduction and energy savings by activities in other sectors thereby exceeding the overall GHG target by over 160%. |
| Project Output 1.3: Waste volumes reduced, and recycling expanded in Ashgabat |  |  |
| Output indicators | Targets | Progress against targets |
| The amount of landfilled waste recycled | Baseline: not available AWP target: no annual targets; the end-of-project target is “Increase in recycling volume by 10 percent”, and “Increase in use of secondary raw materials by 25%”. | Reporting period: The total share of recycling volume reached 8.5% relative to a pre-project situation. The use of secondary raw materials reached 150% against pre-project situation, thereby exceeding the project target by a factor of 6 in Ashgabat. Since the end of the past reporting period, about 100 sets of three-color containers for waste sorting, as well as 70 sets of metal 3-section bins were distributed. Cumulative total: The total share of recycling reached 10% in the city relative to the pre-Project situation. The cumulative volume of collected waste sent for recycling has been as follows: - 1,000 tons of plastic (730 tons for this reporting period alone), - 830 tons of glass (660 tons for the reporting period alone), and - 810 tons of paper (615 for this year alone). |
| Project Output 1.4 City-wide sustainability plans developed and approved |  |  |
| Output indicators | Targets | Progress against targets |
| Number of cities of Turkmenistan (and total population therein) that formally adopt sustainability practices in transport, lighting, and waste management | Baseline: no cities with sustainability plans AWP target: not set. End-of-project target: two cities adopting sustainability plans with a combined population of 175,000. | Reporting period: none Cumulative total: one city (Arkadag) with a population of 60,000 – achieved in 2023. |
| Project Output 2.1: Practices to reduce energy consumption, water use, and waste implemented by hotels in Avaza |  |  |
| Output indicators | Targets | Progress against targets |
| 2.1.1 Development and implementation of green standards for hotels 2.1.2 Energy/water audits 2.1.3 Promotion of successes in green hotel practices in Avaza, including annual awards | Baseline: No green standards exist. No baseline energy use data available (to be obtained from facility managers during audits in first three project years). AWP target: promotion of the adoption of a green hotel standard. End-of-project target: green hotel management standards adopted and implemented by Avaza hotels | Reporting period: savings form Hasyl and Serhat hotels in Avaza achieved 43 MWh of savings in street lighting (LED lights). Water savings exceeded 100 m3 of drinking water, being 12% of the total annual water consumption. Fuel savings amounted to over 1,100 liters of petrol and diesel fuel (thanks to a replacement of petrol lawn mowers with electric ones and due to composting, that cut the need for deliveries of compost to municipal waste dumpers.) Cumulative total: - energy savings: 86 MWh - water savings: 200 m3 - fuel savings: 2,200 litres The progress is estimated at 6% per guest of the total potential savings relative to non-participating hotels in the Avaza district. A green energy standard designed. No green energy hotel standard adopted. |
| Project Output 2.2: Demonstration and replication of solar-powered public lighting |  |  |
| Output indicators | Targets | Progress against targets |
| Solar-powered public lighting installed | Baseline: no baseline exists AWP target: no target End of project target: demonstration in at least six fixtures in two different types of applications | Reporting period: no new system installed Cumulative total: a PV-powered public lighting system installed in Hasyl hotel (in 2022). |
| Project Output 2.3: Optimally efficient surface transportation implemented in Avaza |  |  |
| Output indicators | Targets | Progress against targets |
| Demonstration of solar-powered charging stations in Avaza. | Baseline: No solar-powered charging stations AWP target: No target as the indicator was not recommended to be introduced during the mid-term review | Reporting period: no solar-powered charging stations installed. Cumulative total: No solar-powered charging stations installed due to the fact Avaza city has a contract with a producer of e-buses that doesn’t allow charging at non-proprietary chargers. |
| Project Output 2.4: Managerial and technical capacity of planners, officials, and facility managers in Avaza enhanced via training |  |  |
| Output indicators | Targets | Progress against targets |
| Energy audits / trainings for planners, officials, and facility managers in Avaza | Baseline: No managerial or technical capacity extant. AWP target: 5 energy audits End-of-project target: 24 energy audits / trainings in energy efficiency | Reporting period: 11 energy audits Cumulative total: 15 energy audits and 5 trainings |
| Project Output 3.1: National policies developed and adopted in support of integrated and scaled-up green urban practices, supported by capacity enhancement for responsible agencies and individuals |  |  |
| Output indicators | Targets | Progress against targets |
| Development and adoption of national policies and budgets in support of scaled-up urban sustainability practices along with training and information delivery for capacity enhancement for responsible agencies | Baseline: no standards or incentives exist, except for stipulations on maximum engine capacity (3.5 litres) AWP target: examples of sustainable urban atlases shared with the Transport Agency End-of-project target: verification of actual increase in fuel efficiency of cars by 6 percent (up to 11.3 km/l based on original estimate, with exact target to be verified after project studies | Reporting period: none due to downgrade of the transport agency and lack of information sharing Cumulative total: - a Renewable Energy law adoption - An energy efficiency law adopted - A waste strategy and hazardous wastes classification adopted - No new fuel-savings standards adopted. |
| Project Output 3.2: National incentives and standards adopted for fuel efficiency of imported cars |  |  |
| Output indicators | Targets | Progress against targets |
| Existence and content of fuel economy standards and incentives for passenger vehicles | Baseline: no standards or incentives exist, except for stipulations on maximum engine capacity (3.5 litres) AWP target: examples of sustainable urban atlases shared with the Transport Agency End-of-project target: verification of actual increase in fuel efficiency of cars by 6 percent (up to 11.3 km/l based on original estimate, with exact target to be verified after project studies | Reporting period: none due to downgrade of the transport agency and lack of information sharing Cumulative total: no standards adopted. |

Key Activities:

The project continued to push for upgrades to the public lighting system in Avaza.

In waste collection in both Ashgabat and Avaza, 170 additional containers were placed around the city (for paper, glass, and plastic), expanding the waste collection system to an additional 15,000 people.

The Project continued to support the government on the policy front: the Law on Energy Savings and Energy Efficiency which was designed by the prooject was formally adopted in April 2024.

The project conducted 11 additional energy audits in participating hotels. It additionally organized 17 events, including workshops on renewable energy solutions as well as trainings in the context of waste collection campaigns. The Project provided project coverage on various social media platforms, reaching a wide spectrum of audience and increasing the awareness around the project activities.

Key Results:

- The city of Avaza co-invested around 1.3 million into LED systems.

- Over 2,500 of additional inefficient luminaires were phased out and replaced with LED alternatives in Ashgabat finally bringing the share of LEDs in Ashgabat to 100%. As a result, instead of the target of 9.5 million kWh of energy savings nationwide achieved (i.e. the replacement of about 15,000-20,000 luminaires), 282 million kWh of electric energy savings were achieved.  As a result, the Project achieved a financial leverage factor of 85 to 1:  $508,163 invested by the Project into procurement of 345 luminaires for class A roads resulted in over $43 million of public budget funding allocated for the retrofits.

- About 100 sets of three-color containers for waste sorting, as well as 70 sets of metal 3-section bins were distributed. The cumulative volume of collected waste sent for recycling has been as follows:

-	1,000 tons of plastic (730 tons for this reporting period alone),

-	830 tons of glass (660 tons for the reporting period alone), and

-	810 tons of paper (615 for this year alone).

The total share of recycling volume reached 8.5% (from previous 6.5-7.5%) and is projected/on track to reach 10% share of recycling by the end of the Project in April 2025. The use of secondary raw materials has already reached 150% against baseline, thereby exceeding the project target by a factor of 6 in Ashgabat.

- The city of Arkadag (with population of over 60,000 people as of 2024) adopted a sustainable city development plan in 2024 following the engagement of the staff of Ashgabad mayoral office from where the staffing of the mayoral office of the city of Arkadag was made.

- The Project conducted 11 additional energy audits in hotels with the highest occupancy rate.

- The knowledge management activities amounted to about 1 million people in the reporting period and to 2 million cumulatively (taking into account television programs, news releases on the state channel, as well as taking into account subscribers and circulation of national print and online publications). This includes over 1 million of women and girls reached via a broad-based stakeholder coalition, including educational establishments along with weekly airings of by central television broadcasts.

## Section 5: Cross-Cutting Integration

In the area of Gender Equality and Women’s Empowerment, the project continued to provide renewable energy trainings to students of the Turkmen State Energy University in Mary where the renewable energy minor has the highest share of women-students – over 40%.

The Project expanded its waste recycling activities to the Lebap and Balkan velayats, which have the largest areas of national parks and bio-diversity habitats suffering form uncontrolled expansion of waste landfills.

The project continued to push for the adoption of several Renewable energy bylaws to ensure streamlined connections of RE installations to stet-owned grids.

- Partnerships and Sustainability

Partnerships

The project successfully partners with Nature Protection Society of Turkmenistan which helped it reach 2 million residents by its information campaigns and which helped identify additional interested velayats (such as Lebap and Balkan velayats) for the expansion of waste sorting activities.

The project relies heavily on non-state (private-sector-led) firms that carry out recycling of paper, glass, and plastic materials.

The project partners with the Ministry of Education and women-led Bosfor NGO in order to identify participating schools for identification of priority locations for project-funded bicycle rack-placements.

Sustainability

LED-based street lighting solutions in the two participating cities of Ashgabat and Avaza have become sustainable. LED-based luminaires last over 10 years; they deliver energy savings and system reliability ensuring that following the end of the project, the government will continue to expand it rather than return to a legacy infrastructure at additional capital and running costs (the running costs are several times those of the existing infrastructure).

Waste recycling is another example of a successful sustainability case. The collection of recyclable fractions has already started growing at the initiative of private players in Lebap and Balkanm velayats while recycling activities themselves become only more economically attractive with the expansion of the collection base making such production facilities more attractive to build as the collection infrastructure expands.

Composting and electric lawn-mowers at participating hotels have become self-financing thanks to 40% savings on gasoline-powered refuse truck runs. Publicizing such experience at project-led events draws in new hotel-adopters, several of which are currently procuring new lawn-mowers and allocating land plots for composting.

- Update on risks and mitigation measures

This is the last Annual Report by the project and some conclusions can be already drawn.

The risk of the Transport Agency not being in a position to adopt or promote adoption by other agencies of new fuel efficiency standards has materialized and negatively impacted project results – no fuel economy standards were adopted.

Failed privatization of the hotel sector led to freezing of energy and water tariffs at a very low (subsidized) level, leaving investments into EE and RE tech in the hotel sector well above equipment lifetimes thereby making payback periods unreasonable (paybacks should ideally be shorter than equipment lifetimes, which is not the case under subsidized energy and water rates). As a result, only 2/3 of the total number of hotels participated in energy audits and none co-invested in EE / RE measures.

The project mitigated these materialized risks by doubling down on other sectors where large energy savings could be achieved thanks to motivations to co-invest in reliability and quality of lighting and energy delivery. As a result, GHG savings have been exceeded by over 160% to almost 1 million tons of CO2 while ¾ of energy savings (in TJ) have been delivered. Although no fuel economy standards have been adopted, the project designed two important milestone laws that the country adopted in 2021 and 2024 – the RE Law and the EE Law – laying the groundwork for major climate mitigation projects to come.

- Key Challenges, Lessons Learned and Recommendations

The main challenge faced by the team was a dissolution of a powerful stakeholder in charge of fuel efficiency standards which possessed legislative initiative and wielded sizeable co-financing power. As a result of the said reform, urban transportation issues were demoted to a level of an inter-city transportation agency with no power of legislative initiative and no budget to invest in electric transport.

To counter the challenge – after all, the ProDoc provided that over 80% of GHG ERs should be coming from fuel-economy standards and related public co-investments in the urban transportation sector -  the project increased its stakeholder engagement efforts in the other activity areas, such as street lighting and energy delivery in the urban areas. By drawing on knowledge of international experts and lessons from international smart grid case studies, the team was able to strike a chord with a powerful stakeholder – the Ministry of Energy – that not only possessed the legislative expertise and required budget but that also had a material vested interest in expanding energy delivery infrastructure while cutting losses and improving overall grid and street lighting reliability.

Lesson Learned No. 1: Look for allies in programmatic areas and bring the required expertise to bear on themes that reverberate with new stakeholders.

The lesson learnt here is that – while government reshuffling and demotion of certain functions is a risk that is hard to predict and impossible to manage – it is worth to look for international experience to identify opportunities in the remaining programmatic areas to draw the co-investment required to deliver GHG Ers.

The hotel sector plagued by low tariffs represented another challenge. The ProDoc had high expectations for a privatization process that would have led to ratcheting up of energy and water tariffs in case hotel facilities become privately owned. COVID-19 pandemic destroyed a nascent interest of large international players in this sector and the privatization was halted.

Lesson Learned No. 2: Plan activities on the basis of a no-major-changes environment.

A lesson that can be drawn from the experience with the Turkmenistan’s hotel sector is that it’s not advisable to count at the planning phase on co-investment / co-financing in those areas that are plagued by extremely low tariffs because alternative opportunities to work with the sector (by getting the players interested in improved equipment reliability for example) may not materialize (such as turned out to be the case in the hotel sector).

- Financial Summary

Table 1: Overview of available resources for the project duration

| Donor | Opening Balance | Contribution Received | Available Resources |
| --- | --- | --- | --- |
| GEF-62000 | 939,708.46 | - | 1,045,074.60 |
| TRAC-00012 | - | - |  |
| Total |  |  | 939,708.46 |

Table 2: Overview of allocation and utilization per output

| Output | GEF |  | Track-00012 |  | Total Budget | Total Utilization |
| --- | --- | --- | --- | --- | --- | --- |
|  | Budget | Utilization | Budget | Utilization |  |  |
| Output 1: Energy-efficient public lighting implemented in Ashgabat, with technical justification prepared for replication; Sustainable urban transport solutions in Ashgabat developed and applied; Waste volumes reduced, and recycling expanded in Ashgabat; City-wide sustainability plans developed and approved. | 481,757.84 | 481,757.84 | - | - | 481,757.84 | 481,757.84 |
| Output 2: Practices to reduce energy consumption, water use, and waste implemented by hotels in Avaza; Demonstration and replication of solar-powered public lighting; Optimally efficient surface transportation implemented in Avaza; Managerial and technical capacity of planners, officials, and facility managers in Avaza enhanced via training. | 275,570 | 96,904.64 |  |  | 275,570 | 96,904.64 |
| Output 3: National policies developed and adopted in support of integrated and scaled-up green urban practices, supported by capacity enhancement for responsible agencies and individuals; National incentives and standards adopted for fuel efficiency of imported cars. | 121,284.29 | 47,133.63 |  |  | 121,284.29 | 47,133.63 |
| Total | 878,612.13 | 625,796.11 | - | - | 878,612.13 | 625,796.11 |

- Annexes

## Annex I: Progress Review: detailed matrix of activities and results

| Output 1.1: Energy-efficient public lighting implemented in Ashgabat, with technical justification prepared for replication | Indicators |  | Baseline |  |  |  | Annual target |  |  | Progress / Milestone |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Across the two cities, there occurred a replacement of over 300,000 luminaires in the wake of two pilot projects financed by the project and continued advisory support and oversight of technical specifications and public procurement process. Budget: 301,000 Expenditure to date: 301,000. | - Reduction in electricity consumption from public outdoor lighting in Ashgabat and all of Turkmenistan - Solar energy is used for street lighting and other purposes |  | - 192 million kWh - no solar-based energy is used |  |  |  | - million kWh - not set |  |  | Progress: - 40 million kWh - Solar energy is used for pilot outdoor lighting installation at the Power Engineering University overseen by Ministry of Energy |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Activity 1: Continuation of advisory role for LED retrofits in the cities of Ashgabat and Avaza | 282 million kWh of electric energy savings were achieved (against a target of 9.5 million kWh). The co-financing leverage thereby exceeded the target by a factor of 15 in terms of the number of luminaires and by a factor of 30 in terms of annual savings achieved. Cumulative total: Out of 192 million (baseline), 282 million Kvh are achieved (the excess is due to underestimation of the baseline), with 186,000 tons of GHG ERs delivered. |  |  |  |  |  |  |  |  |  |
| - Development, installation and use of “Smart grid” system for management of street lighting - Documentation on energy efficiency of LED lamps in street lighting and preparation of justification for replication | - Over 2,500 of additional inefficient luminaires were phased out and replaced with LED alternatives in Ashgabat and Avaza finally bringing the share of LEDs in Ashgabat to 100%. - Over 300,000 luminaires have been replaced with LEDs across Ashgabat and Avaza using tech specs for the luminaires prepared by the project. |  |  |  |  |  |  |  |  |  |
| Output 1.2: Sustainable urban transport solutions in Ashgabat developed and applied | Indicators | Baseline |  |  |  |  | Annual target |  |  | Progress / target |
| 1. New practices are adopted on sustainable transport (including public transportation, development of bicycle lanes). 2. Electronic system of passage tickets is improved. 3. New mobile applications are used for riders. Budget: 27,000 Expenditure to date: 24,000. | - Reduction in number of passenger-km of private car travel, via increased use of alternative modes and carpooling - New practices are adopted on sustainable transport (including public transportation, development of bicycle lanes). - Electronic system of passage tickets is improved. - New mobile applications are used for riders. | 12.7 billion passenger-km by private motor vehicle per year nationwide |  |  |  |  | Reduction by 0.5 percent (60 million passenger-km per year) |  |  | Progress: 0 km (0%). |
|  | - New (compensating) indicators: the urban electricity distribution system in Ashgabat is completely switched to medium-voltage from low-voltage along with a phase out of the use of uninsulated wiring and installation of metering to reduce commercial losses to zero while improving reliability of the system and its safety from extreme weather events. | 917 transformers in Ashgabat Avaza are not equipped with metering devices, are of low voltage and with protection type unsuitable for current and forecast climatic conditions of the city. 14 km of overhead wires are uninsulated (permitting commercial losses) and unsafe for maintenance and operation near residential areas. |  |  |  |  | Not set |  |  | Progress: two 35 kV transformers were installed by the Project team (60 already installed in Ashgabat in 2020-H12022 and two procured in 2023 and installed in Avaza in the reporting period). Target: 855 transformers of medium-voltage type; 14 km of last-mile distribution wiring to be of an insulated type; metering installed. |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| As part of MTR recommendations, the Board approved compensating activities: - Introduction of efficient urban energy delivery infrastructure via a switch to modern transformers and higher-voltage networks along with introduction of metering to avoid commercial losses. | A total of 62 transformers installed in Ashgabat and Avaza by the project in 2022-2024 leveraged procurement and installation of additional 855 transformers using public co-financing funds. Cofinancing ration achieved: 1 to 14. The grid modernization component has become a major contributor to the total GHG emissions reduction goal of the Project representing 80% of the GHG ERs - exactly the share that was allocated for ERs to the transport component by the ProDoc. As a result of these activities, it’s estimated that a total of 761,600 tons of CO2 emissions reductions have been achieved from the upgrades in Ashgabat and Avaza. |  |  |  |  |  |  |  |  |  |
| Output 1.3: Waste volumes reduced, and recycling expanded in Ashgabat | Indicators |  |  | Baseline |  | Annual target |  |  | Progress / Milestone |  |
| About 100 sets of three-color containers for waste sorting, as well as 70 sets of metal 3-section bins were distributed. Budget: 98,000 Expenditure to date: 30,000. | - Waste management knowledge is widely spread. - Sorting of household waste is implemented. - Private sector actively processes and recycles the waste. |  |  | not available |  | no annual targets |  |  | Progress: The total share of recycling volume reached 8.5% relative to a pre-project situation. The use of secondary raw materials reached 150% against pre-project situation, thereby exceeding the project target by a factor of 6 in Ashgabat. |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Activity: Continuation assistance to cites in separate waste collection in the following types of activities: - Piloting of sorting for household waste to enable recycling in Ashgabat and Avaza - Preparation and implementation of processing and recycling of household waste Ashgabat with active involvement of private sector - Morphological analysis of waste streams entering the household waste landfill - Public information campaign to reduce solid waste emissions. | 100 sets of three-color containers for waste sorting, as well as 70 sets of metal 3-section bins were distributed. The cumulative volume of collected waste sent for recycling has been as follows: - 1,000 tons of plastic (730 tons for this reporting period alone), - 830 tons of glass (660 tons for the reporting period alone), and - 810 tons of paper (615 for this year alone). Cumulative total: The total share of recycling reached 10% in the city relative to the pre-Project situation. |  |  |  |  |  |  |  |  |  |
| Output 1.4 City-wide sustainability plans developed and approved | Indicators |  |  | Baseline |  | Annual target |  |  | Progress / target |  |
| - Improved capacity in the field of complex plans of sustainable urban development - Pilot plans for sustainable urban development are developed Budget: 170,000 Expenditure to date: 150,000 | - Number of cities of Turkmenistan (and total population therein) that formally adopt sustainability practices in transport, lighting, and waste management |  |  | no cities with sustainability plans |  | not set |  |  | Progress: One city (Arkadag) with a population of 60,000. Target: two cities adopting sustainability plans with a combined population of 175,000. |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| - The Project presented benefits of urban sustainability plans to representatives of mayoral offices of Turkmenbashi and Lebap velayats. | - Lebap velayat and Turkmenbashi authorities included requests for additional funds for financing investments in sustainable urban infrastructure such as e-buses and smart traffic lights. |  |  |  |  |  |  |  |  |  |
| Output 2.1: Practices to reduce energy consumption, water use, and waste implemented by hotels in Avaza | Indicators |  |  | Baseline | Annual target |  |  | Progress / Milestone |  |  |
| Reduced GHG emissions and other negative environment impact through interventions involving tourism facilities and infrastructure in Avaza. Budget: 79,000 Expenditure to date: 115,600 | - “Green practices" are widely applied by hotels of Avaza - Energy/water audit measures implemented and led to reduction in energy and water consumption per guest by an average of 10% - Ecological sustainable practice is introduced. |  |  | No green standards exist. No baseline energy use data available (to be obtained from facility managers during audits in first three project years). | promotion of the adoption of a green hotel standard. |  |  | Progress: Target: green hotel management standards adopted and implemented by Avaza hotels |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Activities: 2.1.1 Development and implementation of green standards for hotels 2.1.2 Energy/water audits 2.1.3 Promotion of successes in green hotel practices in Avaza, including annual awards | Reporting period: savings form Hasyl and Serhat hotels in Avaza achieved 43 MWh of savings in street lighting (LED lights). Water savings exceeded 100 m3 of drinking water, being 12% of the total annual water consumption. Fuel savings amounted to over 1,100 liters of petrol and diesel fuel (thanks to a replacement of petrol lawn mowers with electric ones and due to composting, that cut the need for deliveries of compost to municipal waste dumpers.) - Cumulative total: energy savings: 86 MWh - water savings: 200 m3 - fuel savings: 2,200 litres The progress is estimated at 6% per guest of the total potential savings relative to non-participating hotels in the Avaza district. - A green energy standard designed. - No green energy hotel standard adopted. |  |  |  |  |  |  |  |  |  |
| Output 2.2: Demonstration and replication of solar-powered public lighting | Indicators |  |  | Baseline | Annual target |  |  | Progress / target |  |  |
| Reduced electricity consumption for street lighting. Budget: 27,000 Expenditure to date: 18,000. | - Solar-powered public lighting installed |  |  | no baseline exists | no target |  |  | End of project target: demonstration in at least six fixtures in two different types of applications |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| - Monitoring of solar panel stations operation at Hasyl hotel in Avaza. - Informing 14 other participating in Avaza on the results of operation of the PV station at Hasyl hotel. | Cumulative total: a PV-powered public lighting system installed in Hasyl hotel (in 2022). |  |  |  |  |  |  |  |  |  |
| Output 2.3: Optimally efficient surface transportation implemented in Avaza | Indicators |  |  | Baseline | Annual target |  |  | Progress / Milestone |  |  |
| Demonstration of solar-powered charging stations for EVs in Avaza. Budget: 6,000 Expenditure to date: 6,000 | - The number of solar-powered charging stations in Avaza. |  |  | No solar-powered charging stations | No target (during the mid-term review, the indicator was not recommended to be monitored) |  |  | no solar-powered charging stations installed. |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Activity: Promotion of installation of solar-powered charging stations in Avaza. | No solar-powered charging stations installed due to the fact Avaza city has a contract with a producer of e-buses that doesn’t allow charging at non-proprietary chargers. |  |  |  |  |  |  |  |  |  |
| Output 2.4: Managerial and technical capacity of planners, officials, and facility managers in Avaza enhanced via training | Indicators |  |  | Baseline | Annual target |  |  | Progress / target |  |  |
| Energy audits / trainings for planners, officials, and facility managers in Avaza Budget: 8,000 Expenditure to date: 8,000 | - Energy audits / trainings for planners, officials, and facility managers in Avaza |  |  | No managerial or technical capacity extant. | 5 energy audits |  |  | Progress: 11 energy audits Target: 24 energy audits / trainings in energy efficiency |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Conducting 11 energy audits in participating hotels | Cumulative results: 15 energy audits and 5 trainings on facility use and equipment operations and monitoring. |  |  |  |  |  |  |  |  |  |
| Output 3.1: National policies developed and adopted in support of integrated and scaled-up green urban practices, supported by capacity enhancement for responsible agencies and individuals | Indicators |  |  | Baseline | Annual target |  |  | Progress / target |  |  |
| Support for Energy Efficiency and Renewable Energy Laws. Budget: 38,000 Expenditure to date: 52,878.44 | Number of cities adopted and implement practices on sustainable transport, energy- efficiency, waste management, construction |  |  | No cities with sustainability plans | None set |  |  | Progress: 6 draft by-laws designed by project team and national & international experts and are submitted for parliamentary reviews to implement existing Laws on Renewable Energy and Energy Efficiency. Target: Existing framework laws are operationalized with all the required by-laws. |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Development and adoption of national policies and budgets in support of scaled-up urban sustainability practices along with training and information delivery for capacity enhancement for responsible agencies | Cumulative total: - Law on Renewable Energy designed by the project and signed into law (2021) - Law on Energy Efficiency designed by the project and signed into law (April 2024). |  |  |  |  |  |  |  |  |  |
| Output 3.2: National incentives and standards adopted for fuel efficiency of imported cars | Indicators |  |  | Baseline | Annual target |  |  | Progress / target |  |  |
| New energy-saving standards in force for imported vehicles Budget: 59,000 Expenditure to date: 13,000 | - Existence and content of fuel economy standards and incentives for passenger vehicles |  |  | no standards or incentives exist, except for stipulations on maximum engine capacity (3.5 liters) | none due to downgrade of the transport agency and lack of information sharing |  |  | Progress: Reporting period: none due to downgrade of the transport agency and lack of information sharing Cumulative total: no standards adopted. Target: verification of actual increase in fuel efficiency of cars by 6 percent (up to 11.3 km/l based on original estimate, with exact target to be verified after project studies |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| The project compensated lack of progress in the fuel standards area by working in the area of waste management standards. | Two draft laws submitted for parliamentary review in line with previously adopted Waste strategy and Hazardous wastes classification (designed by experts of the project in 2023). |  |  |  |  |  |  |  |  |  |
| Output 4: Monitoring, Evaluation, and Knowledge Management | Indicators |  |  | Baseline | Annual target |  |  | Progress / target |  |  |
| New energy-saving standards in force for imported vehicles Budget: 59,000 Expenditure to date: 59,000 | - Implementation of the Action Plan for the implementation of the recommendations of the mid-term project evaluation |  |  | Evaluation Action Plan exists | Evaluations completed |  |  | Progress: Preration of Terms of Reference, hiring an international consultant and conducting a terminal assessment of the project. Target: Implementation of recommendations of the project mid-term evaluation |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Terminal Evaluation of the project | Terminal Evaluation mission completed and the Terminal Evaluation Report prepared |  |  |  |  |  |  |  |  |  |
| Output 5: Project management | Indicators |  |  | Baseline | Annual target |  |  | Progress / target |  |  |
| Project service Budget: 27,000 Expenditure to date: 27,000 | - Project service exists |  |  | Project service exists | Project service is effective |  |  | Progress: Service contracts are signed, communications are paid for, office expenditures done, rental costs are is paid. Target: Project service exists and is effective |  |  |
| Activities | Results |  |  |  |  |  |  |  |  |  |
| Project management activities | Service contracts are signed, communications are paid for, office expenditures are made, office rental is paid on time. |  |  |  |  |  |  |  |  |  |

## Annex II: Updated Risk Log

(Refer to project risk log and include it here to show any updates and mitigation measures)

| # | Description | Date Identified | Type | Impact & Probability | Counter-measures / Mngt response | Owner | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hotter spring-summer-autumn seasons make it cycling physically impossible while RE technologies installed in Avaza hotels do not sufficiently off-set increased usage of AC equipment | July 01, 2023 | Environmental and Social | 4 | What actions have been taken/will be taken to counter this risk[[[ | Batyr Ballyyev | October 30, 2023 | no change |
| 2 | The spread of waste recycling by new business entrants increases the rate of occupational injuries. safety concerns, as well as issues of consumer protection for products made with recycled materials, especially when waste streams are not sufficiently uniform or when they contain hazardous wastes | July 01, 2023 |  |  |  | Owner Batyr Ballyyev | October 30, 2023 | no change |
| 3 | Bicycle use will remain low due to inconvenience of this mode of transport for women in traditional attire. | July 01, 2023 |  |  |  | Batyr Ballyyev | October 30, 2023 | no change |
| 4 | Project activity to promote increased carpooling leads to increased personal safety risks for women | July 01, 2023 |  |  |  | Batyr Ballyyev |  | no change |
|  | Project activity to promote bicycle use will expose citizens to increased risks of serious injury, given safety concerns with motor vehicles on the streets of Ashgabat. | July 01, 2023 |  |  |  | Batyr Ballyyev | October 30, 2023 | no change |
|  | Construction activities lead to disruption of public services, safety concerns, and environmental damage. | July 01, 2023 |  |  |  | Batyr Ballyyev | October 30, 2023 | no change |
|  | Piloted technologies and practices prove not to be financially justified in hotel sector. | July 01, 2023 |  |  |  | Batyr Ballyyev | October 30, 2023 | no change |
|  | Implementation of project activities, especially pilot projects, is hampered by administrative delays arising from slow processes of permissions, contracting, and procurement. | July 01, 2023 |  |  |  | Batyr Ballyyev | October 30, 2023 | no change |
|  | Stakeholders lose motivation to invest in scale-up of measures due to low gas prices and reduced public budgets. | July 01, 2023 |  |  |  | Batyr Ballyyev | October 30, 2023 | no change |
|  | Disagreement between key stakeholders on approval of the provisions of the draft HFC phase down strategy. | July 01, 2023 |  |  |  | Batyr Ballyyev | October 30, 2023 | no change |

## Annex III: Annual Work Plan for (next year)

| Delivery and Working Plan (PIMS ID: 5452) for extension period, including Q1 2025 (see red font) Project title: “Sustainable Cities in Turkmenistan: Integrated Green Urban Development in Ashgabat and Avaza” |  |
| --- | --- |

| Outcome 1: Sustainable urban development in Ashgabat Targeted indicators by the end of the project: 1.1 Reduction by 3 percent (180 million passenger-km per year) of private car travels via increased use of alternative modes of transportation and carpooling. 1.2. Reduction of electricity consumption from public outdoor lighting by 1.5 million kWh per year in Ashgabat and 8 million kWh per year in whole Turkmenistan, compared to baseline. 1.3. Reduction in landfill waste in Ashgabat and Avaza relative to baseline of recycling and waste reduction programs. Increase in recycling volume by 10 percent and increase in use of secondary raw materials by 25% an increase in the volume of processing by 10 percent, an increase in the use of secondary raw materials by 25%. | # International Consultant | # 71200 | # 40,000 |
| --- | --- | --- | --- |
|  | # Individual contracts | # 71300 | # 15,000 |
|  | # Service contracts | # 71400 | # 150,000 |
|  | # Travels | # 71600 | # 4,000 |
|  | # Equipment | # 72200 | # 270,000 |
|  | # Printing and publications | # 74200 | # 5,000 |
|  | # Miscellaneous | # 74500 | # 1,000 |
|  | # Trainings and seminars | # 75700 | # 5,000 |
|  | Total on Outcome 1: | 490,000 |  |

| Total on Outcome 1 | Planned activities | Months 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  | Months 2025 |  |  |  |  |  |  | Responsible parties, participants | Budget in USD |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | June | July |  | August |  |  | September |  | October |  | November |  | December |  | January |  | February |  | March | April |  |  | Budget line | SUM |
| OUTPUT 1.1 Energy-efficient Street lighting implemented in Ashgabat and technical justification prepared. Indicators: 1. Electric power consumption reduced for street lighting in Ashgabat 2. Solar energy is used for street lighting and other purposes | Activity 1.1.1. Development, installation and use of “Smart grid” system for management of street lightening |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.1.1.1. Organization and holding of regular meetings of the Project Board. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PT, PM, CO, MAEP | 75700 | 1,000 |
|  | Activity 1.1.1.2. Consultative support on analysis of project documentation and preparation of recommendation with the purpose to introduce energy efficient innovative technologies and operational system based on renewable energies that are applied in project documents of newly constructed buildings on the territory of the of the State Energy Institute of Turkmenistan (SEIT, new educational building, dormitory and indoor sports complex). | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | CTA, PS, PM, ME | 71600 | 1000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 6,000 |
|  | Activity 1.1.1.3. Consultative support in monitoring the introduction of energy efficient innovative technologies and operational system based on renewable energies during the construction of new buildings on the territory of the SEIT (new educational building, dormitory and indoor sports complex). | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PS, CTA, PM, ME | 71600 | 1000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 6,000 |
|  | Activity 1.1.1.4. Procurement and delivery of equipment for the pilot section of street lighting in Ashgabat, with the introduction of modern transformers, power cables and energy-saving lamps equipped with digital technologies (in order to reduce greenhouse gas emissions). | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PM, CTA, PS, PA, ME | 72200 | 160,000 |
|  | Activity 1.1.1.5. Procurement and installation of equipment for the implementation of energy-saving measures and measuring instruments for monitoring the results of energy-saving measures in the pilot hotels. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PM, CTA, PS, PA, HAA | 72200 | 80,000 |
|  | Activity 1.1.2. Documentation on energy efficiency of LED lamps in street lighting and preparation of justification for replication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.1.2.1. Conducting training titled “Studying international experience on introducing energy efficient innovative technologies in energy sector” for the specialists of Ministry of Energy of Turkmenistan and instructors as well as students of the State Energy Institute of Turkmenistan (SEIT). | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PS, PM, PA, ME, MEP | 75700 | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 5,000 |
|  | Activity 1.1.2.2. Working meetings with scientists of SEIT to study and analyze the international experience on applying energy efficient innovative technologies in hot weather, sharply continental climatic conditions. Study of the ways to introduce energy efficient technologies in energy sector of Turkmenistan. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | SP, PM, STA, PIU, ME | 71400 | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71600 | 1,000 |
|  | Activity 1.1.2.3. Conducting education training on study of international experience on development of energy-saving and energy efficient regulatory legal documents for specialists of Ministry of Energy of Turkmenistan, instructors, and students of SEIT. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PS, PM, PA, ME, MEP | 75700 | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 5,000 |
|  | Activity 1.1.2.4. Development of new draft regulatory legal acts (5 pcs.) on energy efficiency to the Law of Turkmenistan "On energy efficiency” by International consultant. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | IC, CTA, PS, PM, ME | 71200 | 20,000 |  |  |  |  |  |  |  |  |
|  | Activity 1.1.2.5. Hiring and work of national consultant on development of draft energy efficiency and energy-saving regulatory and technical documents. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | NC, PM, CTA, PS, PA, ME | 71300 | 4,000 |
|  | Total on Output 1.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 298,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.2. Sustainable urban transport solutions in Ashgabat developed and applied Indicators: 1. New practices are adopted on sustainable transport (including public transportation, development of bicycle lanes). 2. Electronic system of passage tickets is improved. 3. New mobile applications are used for riders. | Activity 1.2.2. Improving the system of e-passes, map updates, and mobile application for riders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2.2.1. Analysis of the situation, preparation of recommendations for improving mobile applications for riders. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PS, PM, TAvTA | 71400 | 7,000 |
|  | Activity 1.2.3 Behavioral choice programs and outreach on sustainable transport |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2.3.1. Conducting the activities for implementing the public information campaign on sustainable transport. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PS, PM, PA, TAvTA, MEP, SMDT, NGO | 74200 | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 5,000 |
|  | Activity 1.2.4. Working out of national long-term roadmap for the use of electric and hybrid vehicles with demonstration design and construction of electric filling ports in Ashgabat and Avaza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2.4.1. Promotion of initiatives with subsequent support of activities for the promotion and use of electric and hybrid vehicles. | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PS, PM, TAvTA, MEP, NGO | 71400 | 4,000 |
|  | Activity 1.2.5. Promotion of Turkmenistan's experience in the use of “green” transport (bicycles, hoverboards, scooters) in Ashgabat and Avaza on global level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2.5.1. Assistance in the implementation of the global cycling initiative (support for Bicycle Day). | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 1 |  | 2 |  | 3 |  |  | 4 | PM, PS, PA, MEP, SMDT, NGO | 71400 | 5,000 |
|  | Total on Output 1.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 23,000 |

| ### OUTPUT 1.3. City plans for sustainable development is developed and approved Indicators: 1. Improved capacity in the field of complex plans of sustainable urban development 2. Pilot plans for sustainable urban development are developed | Activity 1.3.1. Working out of plans for sustainable development in Ashgabat and other cities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Activity 1.3.1.1. Conducting consultations to discuss areas of capacity building in the field of integrated sustainable urban development plans for government officials. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | CTA, PM, PS, MEP, SMDT | 71400 | 9,000 |
|  | Activity 1.3.1.2. Support for the working out of draft of the new National Strategy of Turkmenistan on environmental protection. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PM, PS, PA, MEP | 71400 | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | 8,000 |
|  | Activity 1.3.2. Working out and implementation of plan for development of modern system for monitoring the ecological condition of Ashgabat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.3.2.1. Support of the implementation of the Program to improve the environmental monitoring and control system in cities of Turkmenistan. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, MEP, SMDT | 71400 | 5,000 |
|  | Activity 1.3.2.2. Conducting training on new equipment for monitoring exhaust of gas emissions of vehicles that use petrol and diesel | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, PA, MEP, | 71400 | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 75700 | 1,000 |
|  | Activity 1.3.2.3. Support in development of new legal acts and regulatory documentation in the field of environmental protection, environmental monitoring and waste management | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, MEP, SMDT | 71400 | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | 1,000 |
|  | Activity 1.3.2.4. Continuation of development of user manual for greenhouse gas monitoring (in order to perform calculations of GHG emissions reduction) and development of recommendations on improvement of statistical reporting on greenhouse gas emission calculation. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, MEP | 71400 | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | 1,000 |
|  | Activity 1.3.2.5. Support for preparatory work (Phase 3) on development of GHG gas emissions inventory system in Turkmenistan. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, PA, MEP, SMDT | 71400 | 6,000 |
|  | Activity 1.3.2.6. Support for implementation of measures to implement the Paris Climate Agreement (including NDC) in Turkmenistan. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PM, PS, MEP, SMDT, NGO | 71400 | 6,000 |
|  | Activity 1.3.2.7. Coordination of development of Turkmenistan's Fourth National Communication on Climate Change and the First Biennial Update Report to the UNFCCC (including consultations, indicators identification, completion of analysis, etc.). | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PM, PS, MEP, SMDT, UIET, NGO | 71400 | 7,000 |
|  | Activity 1.3.2.8. Support for the implementation of commitments under the Kigali Amendment to the Montreal Protocol on Ozone depleting substances. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, MEP, SMDT, UIET | 71400 | 2,000 |
|  | Activity 1.3.2.9. Support of environmental protection events and actions, including June 5 - World Environment Day. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PM, PS, PA, MEP, NGO | 74200 | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74500 | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 75700 | 1,000 |
|  | Total on Output 1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74,000 |
| ### OUTPUT 1.4. Volumes of waste is reduced and recycling increases in Ashgabat Indicators: 1. Waste management knowledge is widely spread. 2. Sorting of household waste is implemented. 3. Private sector actively processes and recycles the waste. | Activity 1.4.1. Public information campaign to reduce solid waste emissions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.4.1.1. Continuation of the implementation of the campaign on public awareness and capacity building in the field of waste management. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, PA, MEP, UIET, NGO | 71400 | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | 1,000 |
|  | Activity 1.4.1.2. Organization and conducting of activities for cleaning and landscaping of urban areas. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, PA, MEP, ACM, NGO | 71400 | 7,000 |
|  | Activity 1.4.1.4. Conducting series of educational sessions and activities at schools in Ashgabat and camps in Avaza. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, PA, MEP, NGO | 71400 | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71600 | 2,000 |
|  | Activity 1.4.1.5. Providing advisory support for the Magtymguly Turkmen State University in development of educational manual on Environmental Impact Assessment. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, MEP, MeD | 71400 | 6,000 |
|  | Activity 1.4.2. Piloting sorting for household waste recycling in Ashgabat and Avaza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.4.2.1 Completion of measures at the pilot sites of the project for household waste sorting in Ashgabat and Avaza. Result based analysis and preparation of recommendations. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, MEP, ACM, NGO | 71400 | 7,000 |
|  | Activity 1.4.2.2. Procurement of equipment on waste processing which is part of the waste processing (recyclable materials) and producing products from them. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, AP, MEP, ACM, NGO | 72200 | 30,000 |
|  | Activity 1.4.3. Morphological analysis of waste streams entering the household waste landfill |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.4.3.1. Coordination of the morphological analysis of waste streams entering urban landfills. Hiring international consultant to conduct morphological analysis of waste streams entering urban landfills, with the preparation of recommendations in the field of waste management. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, PA, MEP, ACM, NGO | 71200 | 20,000 |
|  | Activity 1.4.3.2. Report on morphological analysis result on waste streams. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, NGO | 71400 | 6,000 |
|  | Activity 1.4.4. Preparation and implementation of Ashgabat program on utilization, processing and recycling of household waste with active involvement of private sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.4.4.1. Support for the finalization, adoption and implementation of new draft National Concept of Turkmenistan on Waste management. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | PS, PM, AP, MEP ACM, SMDT | 71400 | 8,000 |
|  | Total on Output 1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 95,000 |
| Total on Outcome 1: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 490,000 |
| Outcome 2: Sustainable Tourism Infrastructure and Management Practices in Avaza Targeted indicators by the end of the project: 2.1. Improved capacities and enabling conditions in Avaza for integrated low-carbon and climate-resilient tourism development. 2.2. Reduced GHG emissions and other negative environment impact through interventions involving tourism facilities and infrastructure in Avaza. |  |  |  |  |  |  |  | # International Consultant |  |  |  |  |  |  | # 71200 | # 20,000 |
|  |  |  |  |  |  |  |  | # Individual contracts |  |  |  |  |  |  | # 71300 | # 9,000 |
|  |  |  |  |  |  |  |  | # Service contracts |  |  |  |  |  |  | # 71400 | # 20,000 |
|  |  |  |  |  |  |  |  | # Travels |  |  |  |  |  |  | # 71600 | # 8,000 |
|  |  |  |  |  |  |  |  | # Equipment |  |  |  |  |  |  | # 72200 | # 20,000 |
|  |  |  |  |  |  |  |  | # Printing and publications |  |  |  |  |  |  | # 74200 | # 2,000 |
|  |  |  |  |  |  |  |  | # Miscellaneous |  |  |  |  |  |  | # 74500 | # 1,000 |
|  |  |  |  |  |  |  |  | # Trainings and seminars |  |  |  |  |  |  | # 75700 | # 3,000 |
|  |  |  |  |  |  |  |  | Total on Outcome 2: |  |  |  |  |  |  | 83,000 |  |

| Total on Outcome 2 | Planned activities | Months 2024 |  |  |  |  |  |  | Months 2025 |  |  |  | Responsible parties, participants | Planned budget in US dollars |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | June | July | August | September | October | November | December | January | February | March | April |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Budget line | SUM |
| Output 2.1. Practice on reducing energy consumption, water use, and waste implemented by hotels in Avaza Indicators: 1. “Green practices" are widely applied by hotels of Avaza 2. Energy/water audit measures implemented and led to reduction in energy and water consumption per guest by an average of 10% 3. Ecological sustainable practice is introduced. | Activity 2.1.1. Working out and implementation of "green" standards for hotels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | STA, PM, JPS, MAEP, TCM, HAA, SMDT |  |
|  | Activity 2.1.1.1. Finalization, further approvals and support in adoption of “Green” standards for hotels of Turkmenistan. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | IC, PS, PM, MCA, ME | 71300 | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74200 | 2,000 |
|  | Activity 2.1.2. Conducting an energy/water consumption audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | JPS, SP, PM, TCM, HAA |  |
|  | Activity 2.1.2.1. Conducting practical measures in Avaza hotels by junior project specialist on energy survey issues in pilot hotels. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | JPS, CTA, PM, TCM, HA | 71400 | 3,000 |
|  | Activity 2.1.2.2. Procurement and installation of equipment for the implementation of energy-saving measures and measuring instruments for monitoring the results of energy-saving measures in the pilot hotels in Avaza. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | PM, CTA, JPS, PA, HAA | 72200 | 10,000 |
|  | Activity 2.1.2.3. Guideline on conducting monitoring on energy-saving and project pilot hotels in Avaza. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | CTA, PM, JPS, HAA | 71400 | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | 5,000 |
|  | Activity 2.1.2.4. Conducting seminar on monitoring results on energy-saving activities at pilot hotels. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | PM, JPS, PA, TCM, HAA, MEP, SMDT | 71400 | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71600 | 4,000 |
|  | Activity 2.1.3. Public promotion of successes in application of "green practices" by hotels of Avaza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PM, NC, JPS, MAEP, TCM, ACM, HAA, SMDT |  |
|  | Activity 2.1.3.1. Conducting public awareness to promote the use of “green practices” in Avaza hotels. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | JPS, PM, PA, MEP, TCM, ACM, HAA, NGO | 71400 | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74500 | 1,000 |
|  | Total on Output 2.1. |  |  |  |  |  |  |  |  |  |  |  |  |  | 39,000 |
| Output 2.2. Demonstration and replication of solar-powered public lighting Indicators: 1. Reduced electricity consumption for street lighting | Activity 2.3.1. Piloting solar-powered charging stations for electric vehicles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NC, JPS, PM, TCM, HA, “RE” NEC |  |
|  | Activity 2.3.1.2. Installation and monitoring of solar panel stations for electric vehicles at pilot hotels in Avaza. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | PM, JPS, PA, TCM, HAA | 72200 | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 3,000 |
|  | Activity 2.3.1.3. Conducting working meeting on results of solar panel stations for electric vehicles at pilot hotels in Avaza. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | PM, JPS, PA, TCM, HAA, MEP, SMDT | 71600 | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 75700 | 3,000 |
|  | Total on Output 2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,000 |
| Output 2.4. Managerial and technical capacity of planners, officials, and facility managers in Avaza enhanced via training Indicators: 1. Application of principles of sustainability and new methods and practices in planning and implementation of activities by officials and hotel managers. | Activity 2.4.1. Technical assistance and training of planners, officials, and facility managers in Avaza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NC, JPS, PM, PIU, HAA, PA |  |
|  | Activity 2.4.1.1. Work of international consultant for the preparation of training material for hotel managers in Avaza "Separate collection of wastewater from hotels and their use for irrigation of green spaces (industrial crops)". | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | NC, JPS, PM, PIU, HAA, PA | 71200 | 20,000 |
|  | Activity 2.4.1.2. Development of “Methodical recommendation for hotels in Turkmenistan specifically on expenditure reduction on energy”. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | NC, JPS, PM, PIU, HAA, PA | 71400 | 4,000 |
|  | Total on Output 2.4. |  |  |  |  |  |  |  |  |  |  |  |  |  | 24,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total on Outcome 2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 83,000 |

| Outcome 3: State policy at Municipal and National levels Targeted indicators by the end of the project: 3.1 Spreading of experience and increasing the volume of first two components of the project on nationwide level via spreading of information, capacity building of establishments and managers as well as adopting state policy and legal normative acts | International Consultants | 71200 | 10,000 |
| --- | --- | --- | --- |
|  | Individual contracts | 71300 | 22,000 |
|  | Service contracts | 71400 | 27,000 |
|  | Travels | 71600 | 5,000 |
|  | Printing and publications | 74200 | 3,000 |
|  | Miscellaneous | 74500 | 1,000 |
|  | Trainings and seminars | 75700 | 4,000 |
|  | Total on Outcome 3: | 72,000 |  |

| Total on Outcome 3 | Planned activities (cost description) | Months 2024 |  |  |  |  |  |  |  |  | Months 2025 |  |  |  | Responsible parties, participants | Planned budget in US dollars |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | June | July | August | September | October | November |  | December | January |  | February | March | April |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Budget line | SUM |
| Output 3.1. National policy developed and adopted in support of integrated and scaled-up "green" urban development practices Indicators: 1. Number of cities adopted and implement practices on sustainable transport, energy- efficiency, waste management, construction | Activity 3.1.1. Development and adoption of national policy and budgets in support of implementation for spreading the practice of sustainable urban development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 3.1.1.1. Support in updating of educational programs in “Non-traditional and renewable energy sources”, with concentration on energy audits of the State Energy Institute of Turkmenistan. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 |  | 2 | 3 | 4 | NC, PS, PM, ME, MEP, SMDT | 71200 | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71600 | 5,000 |
|  | Activity 3.1.1.2 Support of the process of finalization of the “Methodology for energy audit of buildings” and “Regulations of rules and procedures for carrying out energy audits in buildings” with concentration on requirements of energy saving and energy efficiency. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 |  | 2 | 3 | 4 | NC, CTA, PS, PM, PA, ME, MCA | 71300 | 8,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 5,000 |
|  | Total to the Output 3.1: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 29,000 |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2.National incentives and standards adopted to improve the fuel efficiency of imported vehicles Indicators: 1. New energy-saving standards in force for imported vehicles | Activity 3.2.1. Working out and implementation of standards and incentives for fuel efficient motor vehicles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 3.2.1.1. Analyzing the current situation and developing incentives for imported vehicles with improved fuel efficiency with the aim to reduce GHG emissions. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 |  | 2 | 3 | 4 | NC, CTA, PM, MEP, SMDT | 71200 | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | 7,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 5,000 |
|  | Activity 3.2.1.2. Organization of working meeting with stakeholders to discuss the recommended incentives for imported vehicles with the aim to reduce GHG emissions. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 |  | 2 | 3 | 4 | NC, CTA, PM, PA, MEP, SMDT | 71300 | 7,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 75700 | 4,000 |
|  | Activity 3.2.1.3. Support of urban bicycle workshops (with the participation of female masters), installation of pilot stations. | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 |  | 2 | 3 | 4 | PS, PM, PA, NGO | 71400 | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74200 | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 74500 | 1,000 |
|  | Total on Output 3.2: |  |  |  |  |  |  |  |  |  |  |  |  |  | 43,000 |  |  |
| Total on Outcome 3: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 72,000 |  |  |
| Outcome 4: Monitoring, Evaluation and Knowledge Management (MEKM) |  |  |  |  |  |  |  | International Consultants |  |  |  |  |  |  |  | 71200 | 25,000 |
|  |  |  |  |  |  |  |  | Individual contracts |  |  |  |  |  |  |  | 71300 | 10,000 |
|  |  |  |  |  |  |  |  | Service contracts |  |  |  |  |  |  |  | 71400 | 6,000 |
|  |  |  |  |  |  |  |  | Service |  |  |  |  |  |  |  | 72100 | 2,000 |
|  |  |  |  |  |  |  |  | Trainings and seminars |  |  |  |  |  |  |  | 75700 | 7,000 |
|  |  |  |  |  |  |  |  | Total for MEKM: |  |  |  |  |  |  |  | 50,000 |  |

| Total for Monitoring, Evaluation and Knowledge Management | Planned activities (cost description) | Months 2024 |  |  |  |  |  |  |  | Months 2025 |  |  |  | Responsible parties, participants | Planned budget in US dollars |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | June | July | August | September | October | November | December | January |  | February | March | April |  | Budget line | SUM |
| Output 4. Implementation of the Action Plan for the implementation of the recommendations of the mid-term project evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 4.1. Implementation of the activities of the Plan for the implementation of the recommendations of the project Mid-term evaluation. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 |  | 2 | 3 | 4 | PM, CTA, UPS, PS, PA, MEP, SMDT | 71200 | 0,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71400 | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 75700 | 7,000 |
|  | Activity 4.2. Preparation of Terms of Reference, hiring an international consultant and conducting a terminal assessment of the project. | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 |  | 2 | 3 | 4 | PM, CTA, UPS, NC, PA, MEP | 71200 | 25,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71300 | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 72100 | 2,000 |
|  | Total for MEKM: |  |  |  |  |  |  |  |  |  |  |  |  |  | 50,000 |  |

| Outcome 5: Project management | Service contracts | 71400 | # 4,000 |
| --- | --- | --- | --- |
|  | Communications | 72400 | # 3,000 |
|  | Office expenditures | 72500 | 4,000 |
|  | Office rental | 73100 | 1,000 |
|  | Service to Project | 74596 | 12,000 |
| Total for Project Management: |  | 24,000 |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Outcome 1 | $490,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Outcome 2 | $83,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Outcome 3 | $72,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Outcome 4 | $50,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Outcome 5 | $24,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL for extension period | $719,000 |

## Annex IV: Assets List.

| Description | Quantity |
| --- | --- |
| The main automated information and measuring board, for the distribution of electrical energy (PD). | 1 pc. |
| Single-core cable termination for outdoor installation 1x150/16mm², 12 kV. | 12 pcs. |
| Single-core cable termination for outdoor installation 1x150/16mm², voltage 36 kV. | 9 pcs. |
| Three-core 3x150/16mm² outdoor cable coupling, 12 kV. | 50 pcs. |
| Outdoor single-core 1x150/16mm² cable coupling, 36 kV. | 60 pcs. |
| Modern power oil transformer with a voltage of 10/0.4 kV, equipped with innovative energy efficiency technologies with a capacity of 400 kVA | 5 pcs. |
| External installation cable end coupling 1x95/16 mm2; voltage 12 kV | 12 pcs. |
| External installation cable end coupling 1x150/16 mm2; voltage 12 kV | 12 pcs. |
| External installation cable end coupling 1x240/25 mm2; voltage 12 kV | 12 pcs. |
| External installation cable end coupling 1x150/16 mm2; voltage 36 kV | 15 pcs. |
| External installation cable end coupling 1x240/25 mm2; voltage 36 kV | 15 pcs. |
| External installation cable coupling 1x95/16 mm2; voltage 12kV | 18 pcs. |
| External installation cable coupling 1x150/16 mm2; voltage 12kV | 18 pcs. |
| External installation cable coupling 1x240/25 mm2; voltage 12kV | 18 pcs. |
| External installation cable coupling 1x150/16 mm2; voltage 36kV | 72 pcs. |
| External installation cable coupling 1x240/25 mm2; voltage 36kV | 45 pcs. |
| Modern, energy-independent LED luminaires, complete with renewable energy generation systems, 132W LED luminaires. | 106 pcs. |
| Batteries for energy-independent LED luminaires, complete with solar panels, 120 W LED luminaire power. | 20 pcs. |
| 4x16 mm² power cable; 0.4 kV. | 1500 m |
| 3x25+16 mm² power cable; 0.4 kV. | 1500 m |
| 3x35+16 mm² power cable; 0.4 kV. | 1500 m |
| 3x70+35 mm² power cable; with 0.4 kV voltage. | 1000 m |
| Modern, high-voltage, single-core 1x150/16mm² power cable, 35kV. | 4500 m |

## Annex V: Knowledge Generation

The project organizes and conducts on a regular basis various trainings and educational webinars for the Government entities. Such trainings were held for the Ministry of Construction and hotel facility managers on green standards in hotels; for students of the main power engineering university in the country (owned by the Ministry of Energy) on design, maintenance, and extending warranty service periods of RE installations; for staff and students of educational establishments on waste sorting, for Hakimlyk offices (mayoral offices) on the benefits of waste separation and sorting from the standpoint of reducing landfilled areas and stimulation of development of small business enterprises in their geographic areas.

The videos of the webinars are kept on the premises of the universities and schools as well as speakers presentations.

Below is a list of sample events and presentations that the project team conducted in the reporting period.

1.	Environmental educational sessions at the Children’s Health Center Dayanch NTZ “Avaza”, dedicated to World Bicycle Day and World Environment Day on June 03, 2023;

2.	Launch of the #BeatPlasticPollution video competition for World Environment Day 2023;

3.	Participation in events on the occasion of Caspian Sea Day on August 11-12, 2023: Conference “Caspian Sea - Sea of Friendship and Harmony”, organization and holding of sports events and environmental lectures at the Dayanch Children’s Health Camp ;

4.	Organization and participation in a 2-day seminar at the National Energy Institute of Turkmenistan on May 15-16, 2023 on the topic “Studying the features of operating energy-saving lamps in the climatic conditions of Turkmenistan. Sorting and processing of solid household waste. Possibility of using waste as an alternative source of energy";

5.	Ecological festival on October 15, 2023 with the assistance of the UNDP Sustainable Cities Project: https://www.instagram.com/p/CyN9a6sKGBZ/?igshid=MTc4MmM1YmI2Ng%3D%3D&img_index=1  and https://turkmenportal.com/blog/68537/v-ashhabade-proshel-vtoroi-klimaticheskii-ekofestival-sohranim-zemlyu-vmeste

6.	As part of the preparation for the Conference of the Parties COP28 and COY18, participation in on-site sessions for students in three cities of Turkmenistan: Mary, Dashoguz and Turkmenabat;

7.	Holding the National Youth Conference of Turkmenistan on November 3, 2023. under the motto “2023 – Happy youth with Arkadag Serdar”;

8.	Conducting an educational lecture on November 22, 2023. on the topic Climate change and waste management

9.	Organization and holding of Sustainable Energy Days in Mary December 14-15, 2023, holding an environmental campaign and determining the Most Energy Efficient School in Mary: https://turkmenportal.com/en/blog/71386/an-international-forum-on-energy-efficiency-in-turkmenistan-was-held-in-mary

10.	Participation in the round table on January 26, 2024. “Youth for Climate Action”, participants: Institute of International Relations, State Energy Institute, International University of Oil and Gas named after. Yagshygeldi Kakaev , Pedagogical Institute, State University named after. Magtymguly: https://turkmenportal.com/blog/77585/mezhdunarodnaya-konferenciya-po-izmeneniyu-klimata-proshla-v-gorode-turkmenbashi

11.	SDG lectures “Tasks of sustainable development of cities and towns, ensuring decent living conditions for the population”, “The role of a reliable and sustainable energy system in ensuring sustainable development. International initiatives and experience of Turkmenistan.”

12.	Brain Ring among 6 Higher Educational Institutions “Women Scientists in the Fight against Climate Change” March 03, 2024: https://www.instagram.com/p/CyN9a6sKGBZ/?igshid=MTc4MmM1YmI2Ng%3D%3D&img_index=1

13.	Conference at the State Energy Institute of Mary March 18-20, 2024: https://orient.tm/en/post/70144/series-events-promote-energy-efficiency-technologies-was-held-mary

14.	Organization of educational training on April 25-26, 2024. within the framework of the Regional Project “Climate Education to Promote SDGs and Action on Climate Change”: https://turkmenistan.gov.tm/ru/post/83200/v-turkmenistane-predstavlen-novyj-uchebnyj-modul-po-izmeneniyu-klimata

15.	From April 27 to May 3, holding Sustainable Energy Days in Ashgabat and Turkmenbashi : lectures at universities, Conference and environmental action in the most energy-efficient school in Turkmenbashi: https://turkmenportal.com/blog/77585/mezhdunarodnaya-konferenciya-po-izmeneniyu-klimata-proshla-v-gorode-turkmenbashi

16.	June 06, 2024 participation in the UNICEF environmental climate camp;

17.	June 12, speech at the Embassy of the United Arab Emirates on the implementation of the Roadmap of the National Youth Conference.

18.	Distribution of 100 sets of three-color containers for waste sorting as well as 70 sets of metal 3-section bins throughout the year: https://sng.fm/ashkhabad/26057-v-stolice-turkmenistana-zapustjat-pilotnyj-proekt-po-razdelnoj-sortirovke-othodov.html

The later if applicable.

Disclaimer 1: Data contained in this financial report section is an extract of UNDP financial records. All financial provided above is provisional. Certified financial statements will be provided on <indicate date (30 June of the following year)>.

Disclaimer 2: Of the USD xxxxx presented above, USD xxxx corresponds to eligible expenses (as per IPSAS terminology), and USD xxxx corresponds to legal commitments in force between UNDP and third parties for the reporting period.