ANNEX 1: PROJECT IMPLEMENTATION PLAN

# Section 1: Project Identification

1.1	Project title:			          Turkmenistan: Preparation of the Fourth National					          Communication and First Biennial Update Report

under UN Framework Convention on Climate Change

(UNFCCC)

1.2	Project number:		           SB-008443.22

1.3	Project type: 				Enabling Activity

1.4	Sub-programme title:

GEF strategic long-term objective:  	Climate Change

Strategic programme for GEF VII:    Enabling Activity

1.5	UNEP Priority :		            Climate Change

1.6	Geographical scope:			 Turkmenistan

1.7	Mode of execution:			 External

1.8	Project executing organization:	 Full Address

1.9	Duration of project:			40 months

Commencing:	 September 2020

Completion:	 December 2023

  - Cost of project (Expressed in US $)932,000

| Cost of project | Year (s) |  |  |  |  | Total amount in US ($) | % |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Expenditure 2020 | Budget 2020 | Budget 2021 | Budget 2022 | Budget 2023 |  |  |
| Cost to the GEF Trust Fund | 20,000 | 87,038 | 289,286 | 298,911 | 156,765 | 852,000 | 91,42 |
| Co-financing In-kind Government Contribution | - | 15,000 | 25,000 | 25,000 | 15,000 | 80,000 | 8,58 |
| Total | 20,000 | 102,038 | 314,286 | 323,911 | 171,765 | 932,000 | 100 |

Project summary

The goal of the project is to prepare the Fourth National Communication (NC4) and the First Biennial Update Report (BUR1) on the implementation of Turkmenistan's obligations under the UN Framework Convention on Climate Change (UNFCCC) (Articles 4 and 12), Decisions 16 and 17 of the Conference of the Parties 1/CP. 16, paragraph 60 and 2/CP.17, paragraph 41 and Annex III to it) (draft FNS/BUR1), as well as assistance in the implementation of the Paris Agreement.

The implementation of the NC4/BUR1 Project will be based on previous studies and evaluations carried out in Turkmenistan and the UNFCCC Guidelines and Methodological Guides.

The preparation of the NC4/BUR1 Project will facilitate the following:

improve the process and reduce the uncertainty of the national GHG inventory;

assess the technological needs of economic sectors; identify priority mitigation measures, explore adaptive capacities and assess the vulnerability of socio-economic sectors and identify adaptation measures;

increase the level of knowledge and public awareness on climate change issues, including climate risk assessments for various territories of the country, that will contribute to increased preparedness for extreme events, building the capacity of early warning systems;

strengthen cooperation between Turkmenistan and other Parties to the UNFCCC, which will increase the effectiveness of activities under the Convention;

contribute to the creation of a framework for the integration of mitigation measures and adaptation to its negative effects in national, sectoral strategies, development plans; and this will be implemented in close collaboration with the key ministries, departments, research institutes, state, joint-stock and private companies, non-governmental organizations.

Table of Contents

# SECTION I: PROJECT IDENTIFICATION

SECTION II: BACKGROUND AND CONTEXT

  - Geography, climate and population

  - Economy and natural resources

  - Environmental management and policies

  - Institutional framework for preparing national communication on a continual basis

SECTION III:

- PROJECT OBJECTIVES, ACTIVITIES, OUTPUTS AND INDICATORS

  - Project Objectives

  - Activities, outputs and indicators

    - National circumstances and institutional arrangements

    - National GHG Inventories

    - General Description of steps

      - Measures to facilitate adequate adaptation

      - Programs to mitigate climate change

    - Mitigation actions and their effects, including associated methodologies and assumptions (BUR)

    - Other information

      - Integrating climate change considerations into social, economic and environmental policies and actions

      - Development and transfer of environmentally sound technologies (ESTs)

      - Climate change research and systematic observation

      - Education training and public awareness

      - Capacity building

      - Information and networking

      - Gender and Climate Change

    - Support received for preparation and submission of biennial update report (BUR)

    - Domestic measurement reporting and verification (BUR)

    - Сonstraints and gaps, and related financial technical and capacity needs

- TECHNICAL ASSISTANCE

- COMPILATION AND PRODUCTION OF NATIONAL COMMUNICATIONS AND BIENNIAL UPDATE REPORT

- STOCKTAKING ASSESSMENT AND INSTITUTIONAL ARRANGEMENTS FOR PREPARATION OF SUBSEQUENT NCS AND BURS

- PROJECT MANAGEMENT

- MONITORING AND REPORTING

Acronyms and Abbreviations

| AS | Academy of Sciences |
| --- | --- |
| BUR1 | First Biennial Update Report |
| CACILM | Central Asian Countries Initiative for Land Management |
| CDM | Clearing Development Mechanism |
| CP | Conference of the Parties |
| CRIL | Complex reconstruction of irrigated land |
| EF | Emission factor |
| FNC | First National Communication |
| GCF | Green Climate Fund |
| GCOS | Global Climate Observing System |
| GDP | Gross domestic product |
| GEF | Global Environment Facility |
| GHG | Greenhouse Gases |
| HFC | Hydrofluorocarbon |
| IPCC | Intergovernmental Panel on Climate Change |
| IWG | Interdepartmental Working Groups |
| LRI | Land reclamation improvement |
| LUCLUF | Land use, land-use changes, forestry |
| MM | Mass media |
| MRV | System of measures, reporting and verification |
| NC | National Communication |
| NC4 | Forth National Communication |
| NCCAAP | National Climate Change Adaptation Action Plan |
| NMVOC | Non‐methane volatile organic compound |
| NPD | National Project Director |
| PaM | Policies and measures |
| PFC | Perfluorocarbons |
| PNC | Predefined National Contribution |
| PSB | Project Supervisory Board |
| PSC | Project steering committee |
| PRC | People's Republic of China |
| QA | Quality assurance |
| QA/QC | Quality Assessment / Quality Control |
| RE | Renewable Energy Sources |
| SDGs | Sustainable Development Goals |
| SNC | Second National Communication |
| SPAs | Specially Protected Natural Areas |
| TNC | Third National Communication |
| UN | United Nations Organization |
| UNCCD | UN Convention to Combat Desertification |
| UN CBD | UN Convention on Biological Diversity |
| UNDP | United Nations Development Program |
| UN ECE | United Nations Economic Commission for Europe |
| UNEP | United Nations Environment Program |
| UN FCCC | UN Framework Convention on Climate Change |

SECTION II: BACKGROUND AND CONTEXT

Turkmenistan is an independent, democratic, legal and secular state governed as a republic, led by the President. The main law of the country is the Constitution, adopted on May 18, 1992 and revised in 2008 and 2017.

On December 12, 1995, the United Nations General Assembly made decision on the "permanent neutrality of Turkmenistan." The decision was unanimously supported by 185 countries. Today, Turkmenistan has diplomatic relations with more than 140 countries around the world and is a member of more than 50 international organizations.

- Geography, climate and population

Geography.

Turkmenistan is a country in Central Asia. It has a common border with the Republic of Kazakhstan in the north, with the Republic of Uzbekistan in the northeast and east, with the Islamic Republic of Afghanistan in the southeast and with the Islamic Republic of Iran in the south. From the west, Turkmenistan is washed by the waters of the Caspian Sea. Administratively, the territory of the country is divided into five velayats (regions) - Akhal, Balkan, Dashoguz, Lebap and Mary. The capital of Turkmenistan is the city of Ashgabat, founded in 1881 and being the largest administrative, political, scientific and cultural center of the country. The northern and central parts of the territory of Turkmenistan are occupied by sandy deserts of the Turan lowland - Central, Zaunguz and Southeast Karakum. In the south and southeast, the country is surrounded by the mountains. The highest point of Turkmenistan is located in the Koytendag ridge - 3139 m above sea level, the lowest - Akchakaya depression - minus 81 m. The area of Turkmenistan is 491.2 thousand km2. The country is located between 35º08’ and 42º48’ n. w. and 52º27’and 66º41’ e.l., north of the Kopetdag mountain range, between the Caspian Sea in the west and the Amu Darya river in the east. The length from west to east is 1100 km, from north to south - about 650 km. The territory of the country belongs to the drainage basins of the Aral and Caspian Seas. It is included in the geographic zone of extratropical deserts of the northern hemisphere and has a general inclination from the southeast to the northwest.

Climate.

Turkmenistan is characterized by a sharply continental and exceptionally dry climate. The average monthly temperature reaches significant values in the extreme south - up to 28–33 ºС. Its largest daily amplitude is observed at the end of summer, when even according to long-term average temperature data in the south it is 18-20 ºС.

The average air temperature varies from 21 to 34 ºС. The coldest month is January. In the warm period of the year (from May to September), the daily air temperature often exceeds 40 ºС. The absolute minimum of air temperature is –36.0 ºС (Dashoguz velayat), and the absolute maximum is +50.1 ºС (Repetek, Southeast Karakum).

The annual temperature amplitude in the northern regions reaches 32ºС, and in the southern - about 26 ºС. The largest diurnal amplitudes are observed at the end of summer and, according to long-term average data, are about 13-16ºС in the northern and 18-22ºС in the southern regions.

The absolute maximum of the surface temperature of the soil (80.0 ºС) was registered in the South-East Karakum (Repetek station).

The frost-free period in the northeastern regions (Dashoguz oasis) of Turkmenistan lasts for 187–200 days, in the rest of the territory - 230–250 days.

The intensity of solar radiation ranges from 606.7 (in the northwest) to 682.0 kJ/cm2 (in the southeast).

The relative humidity reaches its maximum in January and amounts to 70–78%. The driest period is from June to September, when the relative humidity in the Karakum desert is 20–30, and in oases - 30–35%.

On the flat territory of the country, the average annual wind speed is 3.2–4.2 m/s. Over the year, the number of days with dust storms ranges from 35 to 67, and in some years reaches 106–113.

Population.

Turkmenistan is a multinational state with representatives of more 40 nationalities, of which more 90% are Turkmen. Currently, more 6 million people live in the country.

The rural population prevails and accounts for 52.9%. In the structure of the resident population, women make up more 50.2%, and this indicator is almost the same for urban and rural residents.

People younger than working age make up 29.6%, the able-bodied population is 64%, pensioners - 6.4%. Literacy - 99.8%. The population density is 11.5 people/km2.

The administrative division of Turkmenistan is 5 velayats (regions) and 43 etraps (districts). The country has 51 cities, 62 villages (Statistical yearbook 2019).

The sustainable and consistent development of the economy, the growth of human well-being, the preservation of civil peace and harmony in society, and the improvement of the environmental situation have benefited demographic processes in Turkmenistan, which are characterized by high growth rates in the country's population.

- Economy and natural resources.

The current stage of socio-economic development of Turkmenistan is characterized by the large-scale reforms aimed at modernizing the economy in order to accelerate the transfer of the entire national economy to a new industrial and innovative development path. The country has a wide range of natural and socio-economic resources to ensure its sustainable development.

The main goal of the strategy of industrial and innovative development of Turkmenistan is the formation of a modern industry structure, operating on an innovative basis and toward sustainable development.

To do this, the following measures are taken: competiveness of products in the domestic and foreign markets, modernization of the main manufacturing sectors, implementation of legal, organizational and economic measures and conditions necessary for its transfer to the industrial and innovative development path. Structural changes are taking place: new manufacturing industries are being established, modern high-tech production complexes, plants and factories, processing facilities are being put into operation, designed to produce domestic competitive products that meet international quality standards.

The key areas of the new economic strategy are modernization, diversification and general liberalization of the economy, combination of market elements and government regulation. Along with the priority development of the fuel and energy and agro-industrial complex, transport and information and communication infrastructure, significant investments are made into the scientific and educational sphere. High growth rates have become characteristic of the dynamically developing economy of the country. Changes have also occurred in the structure of GDP: the share of industry as of 01.01. 2014 was 48.1%; agriculture - 8.5%; construction - 15.3%; trade - 6.7%; services -16.0%; transport and communications - 5.4%. Turkmenistan is currently marked as an industrial and investment country with the developing infrastructure. The key direction of the economic strategy of Turkmenistan is the establishment of long-term and mutually beneficial trade and economic cooperation with foreign countries, leading foreign companies and financial institutions.The trade and economic ties are laid down with more 100 countries of the world. Importers of technologies and equipment to Turkmenistan are China, the Republic of Korea, Turkey, Japan, Germany, France, Great Britain, the USA, Russia, Ukraine, Belarus, etc. To attract foreign investment to the country's economy and create favorable conditions, a comprehensive program is being implemented to attract new foreign investments, introduce advanced technologies and create the most favorable conditions for investors. This program is developed in accordance with the initiative of the President of Turkmenistan.

The active investment policy and creation of conditions for the development of the construction complex in the country led to economic growth, its diversification, new achievements in science and technology, and the creation of new innovative industries. In the Program of the President of Turkmenistan on the socio-economic development of the country until 2030, the priority of investment policy is the diversification of the sectoral structure of GDP by creating new industries, both export-oriented and import-substituting, industrial and innovative ways of developing the economy, and equalizing the living standards of the urban and rural population. Investments to solve these problems do not only contribute to the growth of the construction and industrial industries, increase employment, but also contribute to their distribution in other sectors of the economy. In order to increase the attractiveness of capital investments to the economy of Turkmenistan, the legislative framework of the investment process is being consistently improved with due regard of international requirements.

One of the first state social programs of independent Turkmenistan was the Water Supply, Gasification and Electrification Program. At the end of 2007, the National Program of the President of Turkmenistan on transforming the social and living conditions of the population of villages, towns, cities of etraps (districts) and etrap centers for the period until 2020 began its implementation. Its main task is to increase the level of social conditions and create high living standards for the rural population, as close as possible to urban conditions. This program covers all the etraps and villages of the country. Its consistent implementation will create a solid foundation for raising the level of social conditions of a significant part of the country's population.

In therelevant section of the TNC, macroeconomic data on Turkmenistan related to social development are presented in sufficient details. However, statistics indicating the level of well-being of the population should be clarified and supplemented. The sections of the chapter related to the economic situation of the country describe in detail the state of the main sectors of the national economy of Turkmenistan.

Many of the data cited in the first chapter “National circumstances” of the Third National Communication of Turkmenistan, especially data relating to the macroeconomic status, could be more clearly presented in tabular form.

Information on the current state of the country's economy should be updated with the latest official data and, if necessary, corrections should be made to the data of previous years to bring them in line with the official statistics.

Tourism is a young developing sector of the Turkmen economy, based on the historical and cultural heritage and the unique nature of Turkmenistan. The country has many ancient monuments of history and culture. The Great Silk Road ran through the territory of Turkmenistan in antiquity - a kind of symbol of the cultural integration of East and West. The history of the Great Silk Road is of great interest. At the present time, a number of countries through which territory it ran are initiating the creation of tourist routes dedicated to sightseeing studies of ancient trade and cultural ties. The industry development is heavily dependent on climate change. Therefore, this section for the first time included the structure of the chapter "National circumstances" of the TNC.

Successfully implemented by the state, industrial policy, investment projects in priority production sectors allow phased approximation of the GDP structure of Turkmenistan to the GDP structure of industrially developed countries. Currently, the industry accounts for more half of GDP. Industrial policy is aimed at the accelerated development of processing industries, creation of new and modernization of existing facilities, the maintenance of investment and innovation activity. High growth dynamics, increase in the capacity of the industry infrastructure, and the production of certified high-quality products are characterized by the production of building materials, chemical industry, the textile and carpet industries, which are rapidly developing in accordance with the comprehensive state and industry programs implemented in the country and plans for industrial diversification. The huge potential and export opportunities are inherent in the country's chemical industry - one of the fastest growing sectors of the national economy. The program goals of the presidential transformation strategy and colossal raw material resources of the country determine the accelerated growth of capacities in the field of production of high-quality mineral fertilizers, the demand for which is constantly growing both in the world and in our country in the context of agricultural reform and achieving food abundance. Recent years have become decisive for the domestic chemical industry, bringing it to the new frames of development, the strategic direction of which is the export of popular and highly competitive products on the world market. In order to create a diversified, competitive industrial production, operating on an innovative basis, it is necessary to launch new import-substituting products, mainly based on our own raw materials and their in-depth processing. The solution to this problem is facilitated by the implementation of regional programs for the development of industries in all velayats (regions) of the country, taking into account the specifics of the region and the availability of labor resources. This, in turn, contributes to the creation of new jobs, attraction of small and medium-sized businesses to this sector of the economy, and an increase in the standard of living of the population.

In general, the industry is represented by enterprises in the electric power industry, oil and gas extraction, oil refining, chemical and petrochemical industries, machine building and metal processing, construction materials production facilities, light and food industries. The reforms being carried out in this area, along with the development of the strategically important fuel and energy complex, were aimed at accelerating the development of processing industries, increasing their export potential, and creating new industries. Over 150 new industrial enterprises were built during the years of independence, most of the previously existing ones were reconstructed. Their technical re-equipment was practically transformed into the construction of new industries using advanced environmental technology.

с. Environmental management and policies

In Turkmenistan, the President is the head of the state and government, acts as a guarantor of national independence, territorial integrity, compliance with the Constitution and implementation of international agreements. The President and the Cabinet of Ministers approve, along with various state acts, environmental programs, being the guarantor of the implementation of state policy in the field of environmental protection. The Ministry of Agriculture and Environment Protection (MAEnv) is responsible for the implementation of all decisions of the President and the Cabinet of Ministers in the country on environmental issues, including climate change. The regulatory legal acts adopted within the framework of this Ministry are binding on the entire territory of Turkmenistan for legal entities and individuals carrying out their activities, regardless of their form of ownership. The Ministry has velayat (regional) departments responsible for the ecological issues in the regions of Turkmenistan. The background monitoring of the pollution of air, water and soil is carried out by the Ecological Control Service of the Center for Environmental Quality Monitoring. Control and monitoring of the Turkmen part of the Caspian Sea is performed by the Environmental Service “HazarEcoControl". Environmental related quality is also monitored by the State Sanitary and Epidemiological Service of the Ministry of Health and Medical Industry, the Land resources service of the Ministry of Agriculture and Environmental Protection of Turkmenistan, divisions of the State Committee for Water Resources of Turkmenistan within the framework of their authority. The Constitution of Turkmenistan guarantees the right of citizens of the country to live in a favorable natural environment. The new version of the Constitution of Turkmenistan (2008) stipulates the responsibility of the state for the preservation of natural environment and control the rational use of natural resources (Articles 11, 36).

After the proclamation of the state sovereignty, it is legislatively fixed that the country's natural resources are a national treasure, and their protection and rational use are a fundamental principle of public policy. Since 1991, the government of Turkmenistan has carried out tremendous efforts to formulate the legislative system, taking into account changes in the political, economic, and social status of the country. Turkmenistan has adopted a number of laws and regulations aimed at the conservation and rational use of natural resources. At the same time, not all available opportunities have been used yet to improve national legislation in the field of regulation of problems related to climate change and to harmonize it with the provisions of multilateral conventions. As part of the preparation of the Third National Communication on Climate Change of Turkmenistan, an analysis of the laws and legislation of Turkmenistan related to the problem of climate change was carried out. The legislative process maintains a development trend and there is every reason to expect that the national legislation and international law in the field of climate change will find the necessary combination. The analysis revealed gaps in the legislation of Turkmenistan and highlighted the main areas of development related to the problem of climate change in all priority social and economic sectors.

One of the first legislative acts of Turkmenistan related to the environment and natural resources adopted after the independence was the Law on Nature Protection (1991), which became the basic document regulating socio-economic and environmental legal norms. In 2014, this Law was revised and published in a new edition. The project to prepare the Third National Communication of Turkmenistan on climate change contributed to the development and inclusion of a new article #47 - “Climate protection and mitigation of its negative consequences” into this Law. It outlines the objectives of mitigating climate change and identifies legal entities and individuals and government agencies responsible for mitigating the effects of climate change. In addition, the Law on Ecological Expertise (2014), Law on Waste (2015) and the Law on Protection the Atmospheric Air (2016) were adopted. In preparation and adoption of these Laws, the climate change experts took an active part. The need to improve normative legal acts in order to bring them in line with the international standards with the mandatory consideration of local climatic features has led to the adoption of a number of new laws: On Hydrocarbon Resources (2008); On the Protection of the Ozone Layer (2009); On Radiation Safety (2009); On Drinking Water (2010); On Fishery and Conservation of Aquatic Biological Resources (2011); On Chemical Safety (2011); On Specially Protected Natural Territories (2012); On Flora (2012); On Fauna (2013); On Pastures (2015), as well as the Land (2004), Sanitary (2009), Forest (2011) and Water (2016) Codes.

On the whole, improvement of legislation taking into account climate change will contribute to sustainable management of natural resources and will be the basis for adaptation measures, measures to reduce greenhouse gas emissions, introduce strongest environmental requirements in the implementation of economic and other activities, and improve the management of natural resources, including involvement of the public.

Legal reform in the field of ecology has had an effect on various areas of the country's economy. The recognition of the diversity of ownership of natural resources is of great importance for their rational use and the creation of prerequisites for the development of a market economy. Climate change, first of all, requires improving legislation in the field of agriculture and water management, oil and gas sector, energy, etc. In this regard, the emphasis should be placed on the implementation of the provisions of the National Climate Change Strategy (2012) and its updated version (signed by President of Turkmenistan on 23 September 2019), where basic adaptation measures, including legal ones, are indicated.

Sustainable agricultural management in the face of climate change dictates the need to increase the rights of Daykhan (farmers) associations as its main link. It is necessary to ensure the improvement of legal regulation in the field of land and water resources management. In particular, in adopted new Water Code of Turkmenistan taked into account the improvement of water resources management and fulfillment of obligations undertaken under the UN conventions (On the protection and use of transboundary watercourses and international lakes, UNECE, Helsinki, 1992).

The leading role in the conservation of biodiversity is played by forests and specially protected natural areas (SPAs). The ecological significance of forests poses challenges to the legislation in assessing their functions such as the conservation of biological diversity, climate regulation, soil protection and water protection, etc. To achieve these goals, it will be necessary, first of all, to take legal measures to conserve forests as an essential component of the biosphere and a source of diverse renewable resources.

The new legislation on protected areas is the basis for its development in the context of solving the problems of expanding the network and the total area of protected areas and the sustainable use of natural ecosystems.

The main volume of greenhouse gas emissions is from the oil and gas industry of Turkmenistan which is caused by fuel combustion, production, transportation and storage of hydrocarbon resources. Intensive economic growth in Turkmenistan, accompanied by an increase in the production and consumption of energy resources, will lead to a further increase in greenhouse gas emissions. Under these conditions, it is advisable in Turkmenistan to adopt the new Law on Energy Saving and Energy Efficiency, in which it is important to provide for legal, economic and organizational issues of stimulating energy conservation and improving energy efficiency, as well as the development of alternative energy sources.

Of the legislative acts adopted recently in order to intensify the activities of the relevant structures in connection with climate change, the following documents should be noted: Regulation on the State Commission to Ensure the Fulfillment of Turkmenistan's obligations arising from the UN conventions and programs on the environment (1999); Decision on the establishment of the State Commission on the CDM (2009); Decision on the approval of the National Strategy of Turkmenistan on Climate Change and its new redaction (June 2012, September 2019).

The international legal framework for national actions on climate change in Turkmenistan is the UN Framework Convention on Climate Change (UNFCCC) and its Kyoto Protocol. Turkmenistan signed and ratified these documents in 1995 and 1999 and timely fulfills its obligations.

Legislative regulation of the use of natural resources and environmental protection in Turkmenistan is implemented by more than 30 laws and government regulations.

The Mejlis (Parliament) of Turkmenistan determines the state environmental policy, adopts environmental legislative acts and partly coordinates the environmental protection activities. The main executive body for environmental protection of Turkmenistan is the Ministry of Agriculture and Environmental Protection. Its authority includes state environmental control over the activities of ministries, departments, enterprises and organizations and compliance with environmental legal norms and standards, conducting state ecological expertise, developing environmental quality standards, issuing and canceling permits for emissions and discharges of pollutants and waste, developing state environmental programs.

Turkmenistan is a party to the UN Convention to Combat Desertification, the UN Convention on the Conservation of Biodiversity, the Vienna Convention and its Montreal Protocol, Kyoto Protocols, the Paris Agreement and other relevant international documents. On October 23 2016, Turkmenistan ratified the Paris Climate Agreement and embarked on ambitious targets for the implementation of the SDGs, including Goal 13: Take urgent action to combat climate change and its consequences, low-carbon development and the need to timely fulfill the obligations of the Paris Agreement. In 2019, the new redaction of the National Climate Change Strategy of Turkmenistan was adopted. The main objectives of environmental policy are as follows: (1) to prevent and reduce the adverse effects of economic actions on the environment, natural resources and public health in the context of national sustainable development and (2) guarantee a safe environment for the people and country. Environmental policy priorities: environmental impact management, pollution prevention and environmental restoration; securing funding for environmental activities; public participation in the environmental decision-making process; integration of environmental requirements; conservation and use of natural resources; providing mechanisms for environmental protection; provision of technical assistance and ongoing investment in environmental projects; international environmental cooperation. In accordance with the principles and objectives of international agreements, the Government of Turkmenistan entrusted the State Commission of Turkmenistan on the fulfillment of obligations of Turkmenistan arising from the UN Conventions and Programs on the Environment, with the function of their implementation with the participation of interested ministries and departments of Turkmenistan. As an example at present time the Ministry of Agriculture and Environmental Protection coordinating the work on adoption by country the Kigali Amendment and ratification expecting in the year 2020.

The Ministry of Agriculture and Environmental Protection is responsible for providing the state government bodies, economic entities and the population of the country with the information on the level of environmental pollution, climate change and weather forecasts, and carry out centralized collection of the results of ecolological monitoring. In this section, it is necessary to update the information related to the state structure of Turkmenistan in connection with the latest changes in the governance structure. In the new edition, this section should take into account all the transformations in the ministries and agencies of Turkmenistan that have occurred in recent years. The Constitution of Turkmenistan establishes the responsibility of the state for the preservation of the natural environment. The protection and rational use of natural resources is a fundamental principle of the state policy of Turkmenistan, compliance with which contributes to the sustainable socio-economic development of Turkmenistan and is one of the essential conditions for the implementation of a balanced environmental policy. Therefore, the development and improvement of environmental legislation remains the main priority of environmental protection activities of the state. The implementation of this activity will ensure a combination of national legislation with the principles and norms enshrined in international ecological law.

At the same time, within the framework of the Fourth National Communication, it is necessary to continue consideration of issues of improving the national legislation of Turkmenistan in the field of regulation of problems related to climate change.

Institutional framework for preparing national communication on a continual basis

Turkmenistan ratified the UN Framework Convention on Climate Change (UNFCCC) on June 5, 1995, and the Kyoto Protocol to it on January 11, 1999. The Paris Agreement was ratified on September 23, 2016. The signing of these documents indicates the country's readiness for active actions aimed at solving a wide range of tasks assigned to them. In addition, Turkmenistan is a party to the following global environmental agreements: the UN Convention to Combat Desertification, Land Degradation and Drought (UNCCD) and the UN Convention on the Conservation of Biodiversity (UN CBD), the Ramsar Convention, Vienna Convention and Montreal Protocol. In accordance with the obligations, plans and multi-year environmental action plans are developed on a regular basis and adopted as directive documents. In 1999, the State Commission was established to ensure the fulfillment of the obligations of Turkmenistan arising from the UN conventions and programs on the environment to solve problems and implement the provisions of the conventions to which Turkmenistan is a Party.

In 2000, Turkmenistan has prepared and submitted to the UNFCCC Secretariat the First National Report on Climate Change, which described national conditions, possible processes caused by it, consequences for ecosystems and the economy, as well as the results of estimation of greenhouse gas emissions for 1994 and measures to reduce their volume. In 2009, an Interdepartmental Commission was established in Turkmenistan as a National Authority for the Clean Development Mechanism to implement the provisions of the Kyoto Protocol. In 2010, the Second National Communication was published, and in 2015, the Third National Communication, which is a logical continuation of the first one and provides for the expansion of activities to address climate change in Turkmenistan. The position of Turkmenistan is reflected in a number of state programs, in particular in the Strategy for the Socio-Economic Development of Turkmenistan until 2030 (2010), and the National Strategy of Turkmenistan on Climate Change (2012) and its updated version. (2019). These documents reflect the state policy in the field of environmental protection and climate change in the near future, taking into account the climatic features of the country.

In order to improve the quality of the NCs and ensure their ongoing preparation, the NC4 is to be carried out in conjunction with the First Biennial Update Report (BUR1) in a three-component basis:

- Evaluation of work carried out as part of previous activities on mitigation of climate change, as well as identifying gaps and proposals, and relevant activities that should be implemented within the framework of the preparation of the NC4/BUR1 draft. Consultations should be held to collect information related to the following components of the UNFCCC guidelines for national communications and updated biennial reports:

2. Preparation of the NC4 and BUR1 of Turkmenistan on the UNFCCC. To this end, it sets out a package of measures and results that should be carried out over three years for the preparation of BUR1 and NC4.

3. Collaboration among the national stakeholders and institutional arrangements for the preparation of subsequent national communications and updated biennial reports. A self-assessment and inventory report may include the analysis of gaps identified in work carried out in previous mitigation activities, lessons learned from the preparation of the NC4 and BUR1, including proposed strategies to strengthen synergies with the related programs; and proposed institutional mechanisms for the preparation of subsequent reports of the NCs and the BRs. This process helps to maintain the institutional capacities created in the process of preparation of the NC and provides preliminary planning at the national level for further reporting.

BUR1 is considered as the previous document to the NC4 and it will be updating the most recent NC of Turkmenistan which is the TNC. In order to avoid duplication of efforts, and to guarantee the efficient use and harmonization of financial and human resources, the BUR1 will be coordinated under the common leadership with the NC4 project and use the existing working groups formed under the TNC.

This will strengthen the existing institutional structure and will ensure that the National Communications submitted by Turkmenistan meet the current requirements of the UNFCCC. The consultation of stakeholders was carried out as part of the preparation of Component I of the project. The key ministries and departments, educational, research and design institutes, the private sector, environmental campaigns, non-governmental organizations are involved in the preparation of the National Communications. The main of them are the following:

- The Ministry of Agriculture and Environmental Protection of Turkmenistan

- The State Committee for Water Resources of Turkmenistan

- The Ministry of Finance and Economics of Turkmenistan

- The Ministry of Education of Turkmenistan

- Academy of Sciences of Turkmenistan

- “Turkmenoil” State Corporation

- “Turkmengas” State Corporation

- The Ministry of Energy of Turkmenistan

- The Ministry of Industry and Building materials of Turkmenistan

- The Ministry of Construction and Architecture of Turkmenistan

- Oil and Gas Institute of “Turkmengas” State Corporation

- The State Committee on Statistics of Turkmenistan

- The National Institute of Deserts, Flora and Fauna of the Ministry of Agriculture and Environmental Protection of Turkmenistan

- Institute of Chemistry of the Academy of Sciences of Turkmenistan

- Institute of Farming of the Ministry of Agriculture and Environmental Protection of Turkmenistan

- Transport and Telecommunication Institute

- The Turkmen State University named after Makhtumkuli

- The Turkmen State Agricultural University named after S.A. Niyazov

Institutional arrangement structure for preparing NC4 and BUR1

NATIONAL PROJECT ADVISORY COMMITTEE (NPAC)

UNEP

National Implementing Partner:

Ministry of Agriculture and Nature Protection

Other National Partners:

See above: List of national partners

Ministry of Foreign Affairs

Project Management & Assurance

UNEP Regional office & UNDP Country Office

Project Manager

TEG onClimate change mitigation

TEG on

GHG Inventory

Project Team Leader

TEG on

Climate change adaptation

TEG on

on general issues

International Consultants

The National Project Advisory Committee (NPAC), which comprises of various representatives will be responsible for supervising the project implementation.  This will include evaluating the project outputs to ensure project activities are being carried out in a timely manner. The NPAC will provide oversight responsibility to ensure a smooth transition from the current to subsequent National Communication reporting and any other follow-up measures.

The NC4/BUR1 project will be implemented and managed under the umbrella of the UNDP project on Development of Sustainable Cities. In this regard, the Project Manager (PM)of the Sustainable Cities Project will be a Manager of the NC4/BUR1 project.   The PM and the Project Assistant will be responsible for solving financial issues of the NC4/BUR1. The National Communication and BUR Project Team Leader will be responsible for the implementation part of the project and work under the guidance of the UNDP’s Sustainable Cities Project Manager. The National Communication and BUR Project Team Leader and experts of the Technical Expert Groups (TEGs) will form the Project Management Support Team. The National Communication and BUR Project Team Leader will manage all technical assistance and recruitment of consultants for day-to-day project work. He/she will carry out research-advisory and methodological support on all main areas of the TEGs.

TEGs will consist of the project specialists from relevant sectors, including government agencies, academic institutions, NGOs, and private sector.  The TEGs will be answerable to the National Communication and BUR Project Team Leader. The TEGs will develop the work plan of the group’s relevant activity areas and sectors.  They will provide technical assistance for project activities and guidance training on scientific or methodological aspects of project work. The quantity of TEGs will be determined during the project life based on findings identified during the Inception Phase of the project.

Project strategy. The Conference of the Parties emphasizes that climate change policies are the part of an integrated development policy, with particular attention on improving coordination between investments, climate ambitions and global development processes. Adaptation and mitigation actions are interlinked with the principles of sustainable development and combating the effects of climate change is included as Goal 13 in the area of sustainable development (SDGs). In Turkmenistan, the process of preparing the NC4 and BUR1 will support the synchronization of efforts in the field of climate change with existing global measures in the context of achieving the Sustainable Development Goals (SDGs). At the same time, Turkmenistan is expected to take part in the regional platforms of Central Asia with the goal of joint positioning on climate change and sustainable development issues.

Recently, Turkmenistan has made some certain progress in developing energy efficiency policies, prioritizing adaptation goals, building capacities and practical measures at the community level. The project will consider how to link the NC4 and BUR1 process with best practices and lessons learned and will assist in a number of studies and inventory activities that will increase the relevance of the process, policy development and contribution to global climate policy. For example, in the context of mitigating climate change and political measures, the project team will try to consolidate the country's existing efforts towards low-carbon development, assess the possibilities for developing a national policy in the field of GHG emissions reduction and carbon sequestration, and evaluate and support mechanisms for establishing internal GHG measuring, reporting and verification (MRV).

SECTION III:

1. PROJECT OBJECTIVES, ACTIVITIES AND OUTPUTS

1.1 Project Objectives

The goal of the project is to prepare the Fourth National Communication on Climate Change (NC4) and the First Biennial Update Report (FBUR) on the Implementation of Turkmenistan's Obligations under the United Nations Framework Convention on Climate Change - UNFCCC (Articles 4 and 12 of the UNFCCC, Decisions 16 and 17 of the Conferences of the Parties 1/CP.16, paragraph 60 and 2/CP.17, paragraph 41 and Appendix III to it). The Fourth National Communication and the First Biennial Update Report - 4NC/FBUR will be based on previous studies and assessments, the UNFCCC Guidelines and Principles. The 4NC/FBUR project should develop and strengthen national capacities and contribute to the process of mainstreaming climate change issues into the national environmental planning and policies that will enable the country to cope with climate change and consider it not only as an environmental problem, but also as a problem of sustainable development.

The project will contribute to a better global understanding of the sources and sinks of greenhouse gases, the potential impacts of climate change and will provide effective measures to achieve the ultimate goal of the UNFCCC, which should “stabilize the concentration of greenhouse gases in the atmosphere at a level that would prevent dangerous anthropogenic impacts on the climate system".

The project will help to identify climate change projects suitable for further funding by donor communities or for co-financing by the GEF and other multilateral or bilateral organizations eligible for funding, including the Paris Agreement Sustainable Development Mechanism. In addition, the project will contribute to increased activity and knowledge on climate change issues and will strengthen dialogue, information exchange and cooperation among all stakeholders, including governmental, non-governmental, academic, and private sectors, in accordance with the Article 6 of the UNFCCC.

1.2 Activities and outputs

1.2.A: National Stocktaking exercise, stakeholder consultations and preparation of the NC4 and BUR1 Project implementation plan

Output 1.2. A.1: Stocktaking and National Consultations undertaken and NC4/BUR1 Project Implementation Plan Prepared

Activities

a1 Undertake stocktaking, national consultations and prepare NC4 and BUR1 project implementation plan

This activity was completed and the project implementation plan for NC4 and BUR1 submitted to UNEP for review and approval.

1.2.1 National circumstances and institutional arrangements

National circumstances in previous National communications (FNC, SNC, TNC) are presented in a separate chapter and are an important introductory section revealing the basic conditions for their favorable or non-favorable circumstances for the implementation of the UNFCCC at the national level.

The chapter “National Circumstances” of the Third National Communication on climate change of Turkmenistan addresses the following issues:

- Geographical location and natural resources, (geographical location, topography, climate, water resources, soil and land resources, biological diversity),

- Socio-economic development model (social policy, population, healthcare, education, tourism and sport),

- The current state of the economy covers the issues of the development of industry, fuel and energy and gas chemical complexes, the electric power industry, the chemical industry, construction, engineering and metalworking, light industry, housing and communal services, agricultural policy, transport, information and communication technologies, public-private partnerships, and investments),

- The section “Management and legislative framework” discusses the issues of management structure and environmental legislation.

It is necessary to note the sections “Geographical location” and “Relief” of this chapter. The content of these sections practically has not been changing from the FNC to the TNC. The "Climate" section includes more information describing the weather over many years of climate change. In this chapter, vivid graphical information about climate processes in Turkmenistan should be added.

Additionally, the section “National Conditions” should have a subsection that describes the current system of accounting and reporting of atmospheric emissions by business entities in the country. On the one hand, this information can serve as the basis for a possible justification of the quality assessments of the inventory of GHG emissions. On the other hand, based on of this subsection, we can draw conclusions about the country's readiness to regularly conduct an inventory of GHG emissions, which may be necessary in determining obligations to reduce emissions. This subsection should be based on both the current situation and the planned directions for the further development of the regulatory and institutional framework for accounting and reporting.

The section “Water Resources” also contains a lot of information, which is repeated in the following chapters of the National Communication. It is necessary to exclude repetitions of information, if there is no needs to solve the tasks in this section.

The sections “Land Resources” and “Biological Diversity” provide very scarce information. It is necessary to describe in detail the size, structure and types of land use systems, changes in land use over several years. In addition, information on biodiversity needs should be provided and its uniqueness emphasized.

In the section "National Circumstances" of the TNC, information on the institutional circumstances related to the preparation of national communications on an ongoing basis in Turkmenistan was presented in a short form.

The content of this section in the TNC covers the time period until 2010 and describes the following thematic areas: geographical location and climate, natural and water resources, socio-economic conditions, the structure of the economy and the institutional and legal framework for environmental protection and the implementation of the UNFCCC.

This section in the TNC illuminated the national conditions in sufficient details and will generally be taken as the basis for the NC4, but according to the opinion of the experts involved, due to the significant changes that have taken place in the country, they need correction and updating.

When preparing the NC4, it is necessary to take into account the changes observed after 2014 in legislation, economy, and the institutional structure. Also new development priorities for the long term, the obligations undertaken by the country in the framework of the signing of the Paris Agreement, as well as the modern requirements of the UNFCCC to provide information should be taken into account.

The information in the section "National Circumstances" will be updated based on all available data, government programs, strategies, projects and studies developed after the preparation of the TNC. Particular attention will be paid to updating information in sectors of the economy that are the main sources of GHG emissions - energy, oil and gas industry, chemical industry and building materials industry.

Particular attention will need to be paid to the sections "Water Resources" and "Agriculture" since these sectors of the economy are most vulnerable to climate change. In connection with the restructuring of the economy and the change in its institutional structure, it is necessary to revise the sections "Socio-economic conditions" and "Structure of the economy".

"Socio-economic conditions" - It is necessary to update and supplement quantitative indicators on demography, education, healthcare and macroeconomic characteristics of economic development based on modern data.

"Sectors of the economy". The following is needed: updating quantitative characteristics of sectoral development indicators in connection with the establishment of new priorities for the country's development, transition to project management and the adoption of new long-term industry programs.

The sections on environmental protection should also be reviewed.

Ecosystems and territories with high anthropogenic load - a certain revision will be required when receiving more up-to-date information on critical ecosystems and species, developing a system of protected natural areas and monitoring biodiversity.

"Waste" - a certain correction of the quantitative indicators for the volume and structure of waste will be required based on more modern data for the period starting from 2010, taking into account the measures and actions taken for waste disposal and projects results.

"Legal and institutional framework for environmental protection and the implementation of the UNFCCC" - a certain correction and revision of environmental legislation will be required in connection with the release of new legislative and regulatory documents for the period from 2010. Particular attention should be paid to the modern institutional structure in the field of environmental protection, the role of individual ministries and departments involved in environmental issues. Describe implemented and current environmental programs.

Currently, the country pays great attention to the development of tourism. The State Committee for Tourism Development has been created. Therefore, the relevant section “National Circumstances” should be expanded.

Expected Outputs and activities:

Output 1.2.1.1: National circumstances, priorities and tasks underlying the solution of problems of climate change analyzed.

Activity:

- Formation of a group of experts.

- Organize a project inception workshop to Launch NC4 and BUR1 project in Turkmenistan

- Review and analysis of changes in the political and economic development of the country in recent years and update relevant information on geography, population, natural resources and economy; and development policies, etc.  relevant to climate change for inclusion in the NC4 and BUR4.

- Preparation of the section "National Circumstances" for the NC4 and BUR1.

Output 1.2.1.2: Institutional arrangement relevant to the preparation of national communications on an ongoing basis described.

Activity:

- Collection and analysis of updated information.

- Description of existing institutional mechanisms relevant to the preparation of the NC of Turkmenistan on an ongoing basis.

- Preparation of the section on institutional arrangements for inclusion in the NC4 and BUR1.

1.2.2 National GHG Inventories

To date, three national inventories have been prepared in Turkmenistan within the framework of three National Communications (FNC, SNC and TNC). They considered anthropogenic sources of GHG emissions and sinks in five areas (sectors) in accordance with the IPCC guidelines: energy (fuel combustion and fugitive emissions), industrial processes, agriculture, waste, LULUCF (land use, land-use change and forestry). The first inventory was carried out only for the year of 1994. The second GHG inventory was carried out for the period 1995-2005. In the framework of the Third National Communication, an inventory of greenhouse gas emissions was carried out for the period 2006-2010. It was a logical continuation and development of the two previous inventories. It presented both calculated and revised estimates of anthropogenic emissions and absorptions of greenhouse gases. Inventory included sources of emissions that were not previously covered.

List of gases covered. The greenhouse gas inventory provides data on emissions of gases with a direct greenhouse effect (carbon dioxide - СО2, methane - СН4, nitrous oxide - N2O, hydrofluorocarbons - HFCs). The inventory provides estimations of gas emissions with an indirect greenhouse effect (carbon monoxide - СО, oxides nitrogen - NOx, sulfur dioxide - SO2, non-methane hydrocarbons). In the third inventory, perfluorocarbons (PFCs) and sulfur hexafluoride (SF6) were not covered due to the lack of activity data. As part of the preparation of the Third National Climate Change Report of Turkmenistan, an inventory of greenhouse gas emissions and sinks was conducted for 2000–2010. At the same time, the results of the inventory for 2000-2004 received earlier under the preparation of the Second National Communication on Climate Change were recalculated. The total greenhouse gas emissions were 50315.63 Gg (CO2-eq.) in 2000 and 66367.2 Gg (CO2-eq.) in 2010. Some decrease was observed in 2009–2010, after stable growth in 2000-2008.

GHG inventory for 1994-2010 is mainly based on the application of Level 1 methodologies of the “Revised Guidelines for National Greenhouse Gas Inventories of the IPCC, 1996”. It uses elements of the "IPCC Guidelines on Good Practices and Uncertainty Factors in National Greenhouse Gas Inventories, 2000”, "IPCC Good Practice Guidance for Land Use, Land Use Change and Forestry, 2003”. To solve intersectoral problems in certain categories of inventories, the methodologies of the “Guidelines for the preparation of national greenhouse gas inventories of the IPCC, 2006” were used.

The emission factors used for the calculations were both by default and national, which were developed for separate source categories, for example, in the Energy sector: to estimate CO2 emissions from fuel combustion, the national calorific value of natural gas was used. The activity data used for the preparation of the GHG inventory were based on the data provided by the State Committee on Statistics, key ministries, departments and companies of Turkmenistan. For a number of source categories, there was a deficit of activity data, which is associated with structural changes that have occurred both in the ministries themselves, departments and organizations, and in the data they provided.

An assessment of the key inventory categories was carried out using the Level 1 methodology of the "IPCC Good Practice Guidelines, 2000". The analysis included greenhouse gases СО2, CH4, N2O and all the evaluated categories, except for the LULUCF sector categories. Assessment of emission levels and trends was carried out for 2005 and 2010. In the SNC, an uncertainty assessment was performed for only part of the greenhouse gas emissions. The TNC has already estimated the uncertainty of all sources of GHG emissions in accordance with the Level 1 "Methodology of the IPCC Good Practice Guidelines, 2000". Uncertainty was estimated at the level of categories, sectors, gases and inventory as a whole. Inventory uncertainty is estimated for 99.81% of GHG emissions, including all key sources.

In preparing the inventory, quality assessment/quality control procedures were regularly conducted as part of an ongoing effort to develop a transparent and reliable inventory. In preparing the inventory, GHG emissions were revised and recalculated for the period 1994-2005 as part of the activities aimed at updating GHG emissions estimates. These actions were performed in all sectors of the inventory, except for the LULUCF, taking into account updated available activity data, inclusion of new sources of emission and exclusion of sources that ceased operations, clarification of the values of used emission factors, application of new methodological approaches and correction of identified errors and assumptions made.

The gaps of the Third inventory include the incompleteness of available data or their absence for a number of source categories (for example, for the category “Use of fluorocarbons and sulfur hexafluoride”) and GHGs (PFCs, sulfur hexafluoride) for various reasons. Despite the efforts made, the inventory does not yet cover all sources of greenhouse gas emissions available in the territory of the country, due to the lack of statistical data and activity data from data holders for such categories as “Emissions of NMVOC and СО from the use of solvents”, etc. The disadvantages of the Third Inventory also include the predominant use of the methodologies of the “Revised Guidelines for National Greenhouse Gas Inventories of the IPCC, 1996” and default emission factors; use of Level 1 methodologies for emission estimates. This circumstance is due to the lack of detailed technical and statistical information on activities related to GHG emissions/absorptions. The process of GHG inventory in the country does not have a continuous nature. The inventory is carried out only as part of the preparation of the National Climate Change Communications. The country has not yet created an appropriate institutional structure.

In connection with the signing of the Paris Agreement with adoption of voluntary obligations by the country to reduce GHG emissions (PNC), the requirements for the reliability and transparency of estimates of greenhouse gas emissions, as well as the quality of statistical information, are increasing. In order to meet these requirements, efforts should be made to (1) strengthen the existing institutional structure and coordinate work at the interdepartmental level to prepare the GHG inventory; (2) expand the database of climate change related statistics; (3) introduce advanced IPCC methodologies and tools; (4) improve inventory management; and (5) increase expert capacity.

In the process of carrying out the next inventory, it is necessary to evaluate as much as possible in the framework of the BUR all the available GHG sources and sinks in the country. According to the Decision of the COP of the UNFCCC 2/CP.17 and Decision 17/CP.8., emission estimates must be performed for the period of 1990-2020. Whenever possible, the national inventory within the framework of the BUR1 and NC4 will be carried out in accordance with the “IPCC Guidelines for the Preparation of National Greenhouse Gas Inventories, 2006”. If activity data are insufficient to apply the 2006 IPCC Guidelines, the methodologies of the 1996 IPCC Guidelines, 2000 and 2003 Good Practice Guides will be used. The research will focus on the transition from the 1996 Guidebook methodologies to the 2006 Guideline methodologies, primarily in the LULUCF sector, as well as transition to the use of the IPCC 2006 software, the study of the UNFCCC materials on the preparation of Biennial reports on updated data.

As part of the preparation of the GHG inventory, the terms of reference will be developed, and all necessary processes launched to create the National GHG Inventory System. This will involve the development of the existing institutional and organizational structure for the GHG inventory of Turkmenistan, as well as the improvement of the documentation system, assessment/quality control, archiving and data storage methods. Particular attention in the preparation of the Fourth Inventory will be given to the development of national emission factors and determination of other necessary parameters, primarily for key inventory categories, as well as for the categories of the "Agriculture, Forestry and Other Kinds of Land Use" (LULUCF) sector and others. This involves additional research, increasing the capacity of the inventory preparation team, broader involvement of national experts and organizations, and consultations of international experts.

Further work is planned to assess and reduce the uncertainty of the national inventory for all categories of sources/sinks, in order to bring methodologies and assessments in line with the latest technical requirements of the UNFCCC to the NC4, which will be reflected in the Work Plan for managing uncertainties. The reduction of uncertainty in the “Waste” and “Agriculture, forestry and other land use” sectors is especially relevant. For the analysis of uncertainties, it is supposed to use the technical capabilities of the IPCC 2006 software. When analyzing key categories, it is planned to switch from the use of Level 1 methodologies to Level 2 methodologies, which will help in the proper prioritization to improve the quality of the inventory. Analysis of key inventory sources will be carried out using the technical capabilities of the IPCC 2006 software based on the methodologies of the 2006 IPCC Guidelines. To improve the accuracy of the GHG emission estimates, if necessary, recalculations will be carried out in certain categories of sources for the 1994–2010 inventory period in connection with the transition to new methodologies, use of updated/new emission factors, activity data, etc. To ensure comparability of information on the GHG emissions at the international level, it is planned to additionally include the sections “Turkmenistan's contribution to global warming” and “GHG emission indicators in Turkmenistan” in the GHG Inventory Report. The implementation of quality control and quality assessment of the inventory will be ensured within the framework of the Fourth GHG inventory based on the positive experience gained in the implementation of previous projects and in accordance with the updated work plan of the QC/QA. Improving the inventory, increasing its transparency will also be focused on improving the system of documentation and archiving of data for the period 1994-2020 within the framework of BUR1 and NC4 in accordance with current requirements of the UNFCCC. The updated and supplemented GHG inventory database will be stored by the executive body for the implementation of the UN Framework Convention on Climate Change.

Improvement of the quality of the GHG inventory will be carried out by continuously increasing the potential of the inventory preparation team, national experts from stakeholder organizations through their participation in trainings, workshops (both at the national level and internationally), the study of modern IPCC methodologies, and the exchange of experience at the international level.

The technical level of the inventory preparation will be increased by using the new IPCC 2006 software, including elements of “good practice” in the inventory preparation, updating the documentation and archiving system, studying the country's experience in preparing previous inventories.

Work with the stakeholders. It is planned to conduct regular consultations and trainings for interested organizations involved in the preparation of information for the GHG inventory in order to increase their potential.

Expected output and activities:

Output 1.2.2.1: GHG inventory and data collection analysis team organized and strengthened.

Activity:

1.2.2.1.1 To identify and mobilize national experts in target sectors and areas relevant to the preparation of the GHG inventory.

1.2.2.1.2 To review existing information and data on previous GHG inventories already archived and documented.

1.2.2.1.3 To identify the specific needs of enterprises in staff training for data collection (with the emphasis on key source sectors, which are the main sources of emissions).

1.2.2.1.4 To develop a national capacity building plan to enable the country to apply the 2006 IPCC Guidelines

1.2.2.1.5 Conduct training for national experts/teams working on GHG inventory including supporting them to participate in relevant regional/international trainings on GHG inventory.

1.2.2.1.6 To review and update the quality assessment and quality control plan (QA/QC).

1.2.2.1.7. To conduct a needs assessment and prepare terms of reference for the creation of a national inventory system with certain institutional mechanisms and a strategy for establishing the system.

1.2.2.1.8. To improve intersectoral collaboration between relevant institutions for the preparation of GHG inventories.

Output 1.2.2.2. Data for the GHG inventory and methodology collected, validated and improved.

Activity:

1.2.2.2.1. To identify new sources of activity data for key source categories and priority sectors not included or explored in other programs.

1.2.2.2.2. To identify new activity data needed to estimate GHG emissions, including, where applicable, recommendations from the UNFCCC In-depth Review Team.

1.2.2.2.3. To use the IPCC best practice methodologies to fill data gaps.

1.2.2.2.4 To identify data sources for source categories (international bunkers, solvents, industrial processes) not covered by the Third National Communication (TNC).

1.2.2.2.5. Identify areas where data may be further improved in future communications through capacity-building where necessary.

Output 1.2.2.3 National inventory of anthropogenic GHGs by sources and removals by sinks for 1994-2020 conducted.

Activity:

1.2.2.3.1 To estimate emissions for new gases (HFCs, PFCs, SF6).

1.2.2.3.2 To assess the applicability of the 2006 IPCC emission factors.

1.2.2.3.3. To develop, as appropriate, the national emission factors for key source categories, such as energy (mainly focusing on subsectors - fugitive emissions and fuel combustion), industry (mainly focusing on cement and lime production subsectors) and LULUCF (mainly focusing on forest, pasture and arable land).

1.2.2.3.4. To recalculate the GHG inventory for 1994-2010 (prepared under the TNC).

1.2.2.3.5. To conduct analysis and inventory of key sources (for 2018) and sensitivity analysis in accordance with the IPCC guidelines.

1.2.2.3.6. To calculate the GHG inventory for all sectors and gases in accordance with the 2006 IPCC Guidelines for the years 2011-2020 for the NC4. The BUR1 will cover the period up to year 2018 and this will be extended to year 2020 under NC4.

1.2.2.3.7. To organize a national seminar to present the results of the GHG inventory and to receive additional comments in accordance with the timing of data submission for the NC4 and BUR1.

1.2.2.3.8. To introduce an uncertainty analysis for all sectors considered under the GHG inventory and provide information on the level of uncertainty associated with inventory data and their underlying assumptions, and describe the methodologies used, if any, for estimating the uncertainties.

1.2.2.3.9. To implement QA/QC procedures for key sectors / source categories.

1.2.2.3.10. Provide information on methodologies used in the estimation of anthropogenic emissions by sources and removals by sinks of GHGs not controlled by the Montreal Protocol, including a brief explanation of the sources of Emission factors and Activity data.

Output 1.2.2.4. GHG inventory completed and archived.

Activity:

1.2.2.4.1. To prepare a National GHG Inventory Report for 1994-2018 (for the BUR1), 1994-2020 (for the NC4).

1.2.2.4.2. To prepare proposals for the establishment of the National Inventory System by 2023.

1.2.2.4.3. To conduct a workshop with decision makers from data source institutions to present the final results of the inventory process.

1.2.2.4.4. To prepare and make archiving of the GHG inventory and describe the procedures and arrangements undertaken to collect and archive data for the preparation of national GHG inventories, as well as efforts to make this a continuous process, including information on the role of the institutions involved.

1.2.3 General Description of steps

1.2.3.1 Measures to facilitate adequate adaptation

Due to its geographical location, Turkmenistan is very vulnerable to climate change. It has the highest temperatures and the lowest rainfall in the region. The expected increase in air temperature and decrease in annual precipitation will have a significant impact on many aspects of the country's socio-economic development in the future. In recent years, the frequency and intensity of such phenomena as heat, drought, dust storms, torrential rains, etc. are increasing.

Vulnerability and adaptation issues were also addressed in the First and Second National Communications of Turkmenistan on Climate Change. In the Third National Communication, these issues were considered in more detail. The general conclusion is that the climate change will primarily affect priority sectors: health, water, agriculture, biodiversity and the coastal zone of the Caspian Sea. In general, Chapter 3 of the TNC of Turkmenistan, devoted to measures to promote adequate adaptation, has been implemented in accordance with the requirements. Previous activities within the framework of the FNC, SNC and TNC allowed starting research in the field of assessing the impact of climate change on the environment and economic sectors, to identify the most vulnerable sectors and priority adaptation measures. The preparation of the TNC allowed further work on vulnerability assessment and adaptation of various sectors; identify adaptation measures to reduce negative consequences; assess the development needs of hazard warning systems; contribute to raising public awareness and knowledge about the impacts of climate change, vulnerability and adaptation. Nevertheless, a number of problems and needs for research and assessment of the impact of climate change by sectors of the economy, assessment of their vulnerability to the development of measures and actions, and providing governments with information to make adequate decisions to increase adaptive capacity have not yet been resolved.

- One of the shortages of this section is the excessive commonness of climate scenarios. It is necessary to carry out calculations and assessments based on such scenarios that more accurately reflect the climatic conditions of the region;

- Adaptation measures are summarized for the whole country and do not take into account the characteristics of individual regions.

Based on the experience in preparing the FNC, SNC, TNC and the requirements of the IPCC guidelines for the Fourth National Communication, the following is proposed:

- to justify the selection of sectors most vulnerable to climate change using indicators that quantify the vulnerability of each sector;

- in all cases, when possible, vulnerability assessment must be obtained using models applied in modern practice;

- using models for assessing vulnerability, to assess the already observed vulnerability from retrospective climate data;

- to estimate the amount of economic damage from the observed and expected climate change, for the case of non-adoption and adoption of measures to adapt to climate change in all possible sectors. At the same time, taking into account climate changes and associated consequences (deterioration of land reclamation conditions, increase of irrigation norms, decrease in pasture feeding capacity), losses of production and income in crop production and animal husbandry will be taken into account;

- vulnerability and adaptation assessment in the Fourth National Communication will be carried out taking into account national requirements and using internationally recognized methodology.

Within the framework of the Fourth National Communication, it is proposed to use the following areas of activity for studying adaptation to climate change in the agricultural sector:

- technological improvement of agricultural processes used;

- economic mechanisms stimulating the activities of individual owners;

- identification of the main ways of state support for agriculture.

As a result of the research, it is supposed to assess current risk and vulnerability to climate change in all of these sectors, and on this basis to assess future risks and vulnerability, and also to analyze the effectiveness of the conducted and planned adaptation measures. The basis for the analysis should be the developed climate, socio-economic and environmental scenarios.

Within the framework of the Fourth National Communication, analysis of the national development priorities will be carried out taking into account climate change.

The main result of the work on the tasks set within the framework of the Fourth National Communication should be the prepared chapter “Assessment of vulnerability and adaptation to climate change”.

In the process of work on this chapter, two workshops should be held: 1 - to present the assessment methodology and raise awareness; 2 - to present the results of the work.

In order to increase the level of knowledge of experts of the national team, it is necessary to ensure participation of national experts in regional and international training workshops.

In preparing the Fourth National Communication, the analysis of the work carried out as part of the Caspian Environmental Program and the preparation of Turkmenistan’s national communications on the UNFCCC should be made, which marked the beginning of the assessment of potential damage associated with sharp change in sea level due to climate change. At the first stage of the project, it will be necessary to carry out activities to build the experts capacity. It is planned to organize a training seminar for potential sectoral experts (who will form the basis of the expert working group) on methodological issues of impact assessment, vulnerability analysis and adaptation, based on the UNFCCC guidelines. Identify training and development needs of appropriate techniques and tools. The methods and tools described by CGE Training Materials for Vulnerability and Adaptation Assessment (2014) will be used; UNFCCC Compendium on Methods and Tools to Evaluate Impacts of, and Vulnerability and Adaptation to, Climate Change (2008); UNFCCC Resource Guide, Module 2: Vulnerability and Adaptation to Climate Change for Preparing the National Communication of Non-annex I Parties (2008); Developing Socio-Economic Scenarios for Vulnerability and Adaptation Assessments; Foundations for decision making. In: Climate Change 2014: Impacts, Adaptation, and Vulnerability. Part A: Global and Sectoral Aspects, Contribution of Working Group II to the Fifth Assessment Report, 2014, Reporting on Climate Change: User Manual for the Guidelines on National Communications from Non-Annex I Parties (2003) and others. FAO approaches and tools (SHARP, AquaCrop, and MOSAICC) are also planned for the agricultural sector.

Expected output and activities:

Output 1.2.3.1.1: National Group on Measures Promoting Adequate Adaptation developed and strengthened.

Activity:

1.2.3.1.1.1. Establishment of the National Group for Measures Promoting Adequate Adaptation and appointment of a Team Leader.

1.2.3.1.1.2. Inclusion of leading experts from ministries and departments related to climate change issues to the National Group on Measures Promoting Adequate Adaptation.

1.2.3.1.1.3. Assessment of risks associated with climate change.

1.2.3.1.1.4. Development of the list of specific adaptation measures with aggregative assessment of costs and benefits of their implementation.

1.2.3.1.1.5. Organization of the first national seminar on measures to promote adequate adaptation in the initial period of the Fourth National Communication with the purpose to consult with relevant stakeholders and identify approaches, tools and methods that will be used during vulnerability and adaptation assessment.

1.2.3.1.1.6. Technical capacity-building of national teams/experts working on vulnerability and adaptation assessments, including supporting their participation in relevant sub regional/regional/international workshops on Vulnerability Assessment and Adaptation as appropriate.

Output 1.2.3.1.2 Approaches, tools and methods to be used during vulnerability assessment and adaptation approved.

Activity:

1.2.3.1.2.1. Identification of necessary data and information, and selection and description of approaches, tools and methods to be used for evaluation of impacts of and vulnerability and adaptation to climate change.

1.2.3.1.2.2. Development and use of methods for calculating costs and benefits in the implementation of specific adaptation measures.

1.2.3.1.2.3. Review of the policy and development process in the context of the chosen field in order to explore how adaptation measures can be implemented in the decision-making agenda and the best mechanisms for their implementation.

1.2.3.1.2.4. Determination of a set of measures to eliminate the water shortage associated with climate change (reducing river flows and changing their hydrograph, increasing irrigation norms with increasing temperature and evapotranspiration growth, expanding evaporation from the water surface).

Development and approval of the action program for adaptation to climate change in the main sectors of the economy:

	public health;

	water management sector;

	agricultural sector;

	biodiversity.

1.2.3.1.2.5. Support the implementation of the Central Asian Land Management Initiative (CACILM).

1.2.3.1.2.6. Assistance in strengthening the activity of the State Commission for Ensuring Fulfillment of the Obligations of Turkmenistan arising from the UN conventions and programs on the environment.

Output 1.2.3.1.3: Vulnerability and Adaptation Assessment Implemented.

Activity:

1.2.3.1.3.1. Identification and description of the scope of vulnerability and adaptation assessment of Turkmenistan and description of vulnerable areas, and the development of reliable indicators (climate and multilateral impact, socio-economic development, etc.). It is supposed to include “prevented damage” as one of the indicators. In various sectors of the economy, this indicator should be calculated independently by the industry experts:

	in public health - the implementation of preventive measures to reduce the cost of treating patients, paying sick leave, etc.

	in the water and agricultural sectors the implementation of measures for land reclamation (LR) and comprehensive reconstruction of irrigated lands (CRIL) will prevent decrease in crop yield and, consequently, income; reduce the cost of water resources for land leaching, etc.

	one of the indicators in agriculture should be the output of products per unit of water, and not per area unit (instead of c/ha - c/m3, c/1000 m3).

	in pastoral livestock breeding (sheep breeding) - the implementation of measures to prevent pasture degradation will help avoid the damage from reducing the grazing capacity of pastures, and reducing the productivity of sheep.

	development of a list of measures aimed at saving fuel and energy resources and stabilizing greenhouse gas emissions by 2030 through the use of energy-efficient and resource-saving technologies.

1.2.3.1.3.2. Under the socio-economic indicator for the rural population, calculate the increase in the standard of living of the population, expressed as an increase in income from agricultural production, subject to the implementation of adaptation measures in the water and agricultural sectors.

1.2.3.1.3.3. Compile relevant information on implementation of sectoral and/or integrated analysis of Turkmenistan's vulnerability to climate change for all relevant sectors of the economy.

1.2.3.1.3.4. For each sector of the economy, performance of vulnerability assessment and identification of risks - material and social - in case of failure to implement possible adaptation measures (reducing crop yields and animal productivity, loss of biodiversity, etc.) will be undertaken.

Output 1.2.3.1.4: Basic scenarios developed.

Activity:

1.2.3.1.4.1. Development of climate scenarios using modern models.

1.2.3.1.4.2. Development of economic scenarios together with the Ministry of Finance and Economics of Turkmenistan.

The main indicators of the country's economic development scenarios will take into account the situation in the water and agricultural sectors. In these sectors, it is necessary to implement a set of measures aimed at reducing water scarcity and developing inter-ministerial plans that define the actions that need to be taken by target ministries in order to move towards a low-carbon economy that is resistant to change climate.

1.2.3.1.4.3. Determination of the cost of implementing these measures and the timing of their implementation in accordance with the considered scenarios of the country's economic development for the future.

1.2.3.1.4.4. Development of recommendations for the implementation of early warning system for the likelihood of drought, floods, and mudflows.

Output 1.2.3.1.5: Adaptation measures assessed and described.

Activity:

1.2.3.1.5.1. Assessment of current climate change adaptation strategies and measures in key areas; future climate risk assessed.

1.2.3.1.5.2. For the specific adaptation measures, describe ways of their implementation, i.e. mechanism for the implementation of these activities, sources of funding, monitoring and timing of their implementation.

1.2.3.1.5.3. Develop new adaptation responses and predict potential impacts and develop multi-level adaptation scenarios.

1.2.3.1.5.4. Assist in the development of National Action Plans for Adaptation to Climate Change in key ministries and departments.

1.2.3.1.5.5. Include in the industry specific NAPAs a list of concrete adaptation measures in the context of the sectors of the economy of Turkmenistan, the timing of their implementation (if necessary, stages), assessment of the costs of their implementation, responsible executives, sources of funding.

1.2.3.1.5.6. Define and establish a policy framework for the implementation of the National Climate Change Adaptation Action Plan (NCCAAP) in Turkmenistan.

1.2.3.1.5.7. Carrying out technical review of the NCCAAP executed by ministries and departments.

Output 1.2.3.1.6:  Chapter 3: "Measures to Promote Adequate Adaptation" of the NC4 developed.

Activity:

1.2.3.1.6.1. Development of the draft Chapter 3: "Measures to promote adequate adaptation" of the Fourth National Communication.

1.2.3.1.6.2. Dissemination of the draft chapter for internal and external review, receipt and inclusion of comments, completion of Chapter 3: "Measures to promote adequate adaptation", as part of the Fourth National Communication.

1.2.3.1.6.3. Inclusion of comments and observations received after the reviews and finalization of Chapter 3: "Measures to promote adequate adaptation" of the NC4.

1.2.3.1.6.4. Organize national workshop on Vulnerability and Adaptation to review and approve activities that promote adequate adaptation

1.2.3.1.6.5. Archiving and documenting all studies and assessments of vulnerability and adaptation.

1.2.3.1.6.6. Creation of database of materials and documents related to climate change issues.

1.2.3.1.6.7. Creation of database of experts and specialists who are directly involved in resolving issues related to climate change.

1.2.3.2. Programs to mitigate climate change

Turkmenistan possesses huge reserves of oil and gas and almost completely provides its own resources for the country's energy needs. In this regard, the assessment of mitigation measures and the development of business-as-usual  and innovative scenarios in previous SNC and TNC national communications was carried out on the basis of the current and forecasted energy consumption in the country, and the interconnections of the development of the economy as a whole, and individual key industries with the level of domestic energy consumption were determined. The main indicators of the effectiveness of PaMs policies were the estimated indicators of energy intensity and carbon intensity of the economy.

After the TNC, several important state documents were adopted in Turkmenistan that contribute to the development of PaMs policies. For example, in 2019, the National Strategy of Turkmenistan on Climate Change (2019) was updated, which is the main document determining the development of the country's climate policy in the near future. The strategy envisages further systematic reduction of energy and resource intensity of the economy, widespread introduction of energy-saving technologies in production, increased use of renewable energy in all sectors, development of transport, standard construction of houses, including in rural areas using new technologies. To implement the Strategy, annual plans / roadmaps are developed defining specific activities that will be evaluated under the NC4 in terms of reducing GHG emissions. The main goal of reducing GHG emissions for the period up to 2030, associated with the fulfillment of obligations under the Paris Agreement (PNC), is to reduce specific GHG emissions (carbon intensity of GDP). It is obvious that the planned measures to reduce emissions should ensure compliance with the obligations undertaken.

Turkmenistan also approved a program for energy conservation for 2018-2024, designed to promote the careful and rational use of the country's natural resources, increase the efficiency and competitiveness of the national economy, protect the environment, and ensure favorable living conditions for the population. The priority areas of energy conservation in this Program are the large-scale introduction of new advanced technologies and the latest achievements of world science in the key energy sectors of the economy. They also include modernization and technical re-equipment of enterprises, introduction of modern resource-saving technologies, and improvement of energy metering and consumption systems in other sectors.

Since the TNC, a number of energy saving projects have been implemented in Turkmenistan granted by several international funds, for example, the GEF project to improve energy efficiency in the housing sector. The results of this project will serve as the basis for assessing mitigation measures in residential and public buildings. Also, soon completion of the following GEF projects is expected: “Efficient use of energy and renewable energy sources for sustainable water management in Turkmenistan” and “Sustainable cities in Turkmenistan: Integrated development of green cities in Ashgabat and Avaza”. The results of the projects will contribute to the evaluation of measures for improvement of energy efficiency in the water sector and the application of “smart” practices for resource conservation, including energy conservation, in the cities of Turkmenistan.

In 2018, with the support of the Asian Development Bank, a project was launched to develop the electricity sector, which will modernize the electricity transmission infrastructure. The declared project results related to mitigation of climate change are to achieve improved planning and forecasting of the energy system, demonstration of the effectiveness of pilot projects on energy efficiency. The results of these projects will be reviewed as part of the NC4.

In 2018, Turkmenistan became a member of the international renewable energy agency IRENA and, together with the agency, prepared a roadmap for the development of renewable energy until 2030. An assessment of the effectiveness of the implementation of the roadmap in Turkmenistan will reveal weaknesses and barriers to the introduction of renewable energy sources.

The assessment of mitigation measures and actions will be presented in accordance with Decision of the UNFCCC COP 17/CP.8., “UNFCCC Guidelines for the Preparation of National Communications from the Countries not included in the Annex I”, using the following documents: «UNFCCC. Resource Guide. Module 4: Measures to Mitigation Climate Change for Preparing the National Communications of Non-Annex I Parties.2008», «Training Handbook on Mitigation Assessment for Non-Annex I Parties. UNFCCC’s Consultative Group of Experts on national communications from Parties not included in Annex I to the Convention. May 2006», IPCC Fifth Assessment Report: Climate Change 2013 (AR5). Working Group III "Mitigation of Climate Change", «IPCC Special Report. Renewable Energy Sources and Climate Change Mitigation. 2011» и «Preparing Low-Emission Climate-Resilient Development Strategies. A UNDP Guidebook – Version 1. UNDP. 2011», «Handbook on Measurement, Reporting and Verification for Developing Country Parties.2014». In preparing the section, experience and lessons learned from the preparation of previous National Communications of the Republic of Turkmenistan and the PNC document will also be taken into account.

Mitigation analysis will be based on the results from previous national communications. The NC4/BUR1 will analyze progress in the implementation of mitigation measures. This will include: progress achieved in the implementation of mitigation measures in accordance with priority sectors (energy, in particular the oil and gas sector and the electricity generation sector, which is the largest contributor to the total GHG emissions in Turkmenistan, waste, industrial processes, transport, construction). The progress will start with the collection, compilation and review of all relevant initiatives undertaken by various national actors, starting especially from the TNC. In the NC4/BUR1, a deeper analysis will be carried out and a basis will be laid for a long-term mitigation strategy, with a focus on the oil and gas and energy sectors. It is planned to conduct an analysis of legislative documents in support of mitigation and to assess changes in the legislation for the period after the submission of the TNC.

The analysis and results available in the TNC will be reviewed, forecasts of GHG emissions for the period up to 2030 will be compiled, and mitigation options will be summarized and analyzed. The main analysis of energy consumption will continue, including energy consumption in transport, industry, as well as in residential and public buildings.

Whenever possible, long-term demographic and macroeconomic scenarios for the country will be used to analyze the planned measures and actions. In order to obtain emission scenarios for various socio-economic development alternatives, it is planned to use the LEAP (Long-range Energy Alternatives Planning system), GACMO or other models recommended by the UNFCCC.

The analysis of existing, completed and planned regional, national and sectoral programs containing measures and actions to reduce GHG emissions will be made; the effectiveness of these programs will be assessed. It is intended to assess the contribution of individual measures to overall mitigation at the sector level and across the whole economy. The new and most effective measures to reduce greenhouse gas emissions and related technologies will be identified, a final table of priority mitigation measures prepared with the relevant information by sectors and individual projects will be presented.

Attention will be given to the development of a roadmap for the establishment of the MRV system. It should be noted that the NC4 will consider general issues about the country's institutional structure (or its individual elements), which could monitor the implementation of relevant measures and actions, while specific information on establishing a full-fledged MRV system will be considered within the BUR1.

The mitigation assessment will be expanded to include relevant information on barriers and opportunities for implementing the proposed measures. Key implementation requirements will be identified, including cost-benefit analysis, timelines, assessment of technology options for various mitigation options in different sectors, institutional capacity-building needs to support mitigation efforts, and an appropriate legal and institutional framework. Appropriate methods and tools will be used by the analysis in the NC4/BUR1 for mitigation options.

The analysis of emission reduction measures will be carried out in the context of Turkmenistan's development priorities in order to ensure that the proposed mitigation options are consistent with development needs.

It is also planned to analyze the results of ongoing, completed and planned international and national projects in support of mitigation.

The section will also provide information on existing gaps, weaknesses, specific financial, technical and institutional needs, as well as capacity-building needs for mitigation measures and actions.

As a result, this section will prepare an updated report on policies and measures (PaMs) for mitigating the effects of climate change, as well as strengthening the capacity to collect and analyze this information on an ongoing basis for the preparation of future reports.

Expected output and activities:

Output 1.2.3.2.1. The necessary data and relevant information for the development of the scenario collected, analyzed and used to develop the scenario.

Activity:

1.2.3.2.1.1. Technical capacity building of national teams/experts working mitigation measures including supporting their participation in relevant regional/international workshops/trainings on mitigation assessment as appropriate

1.2.3.2.1.2. Identify and mobilize national experts in target sectors and areas relevant to the preparation of the PaMs.

1.2.3.2.1.3. Conduct an analysis of the assessment of the inventory for 2011-2020 and fulfill the forecast for GHG emissions by 2030.

1.2.3.2.1.4. Conduct a comparative analysis of the data/estimates obtained in the framework of the GHG inventory for the TNC, with the data projected for the same year within the framework of the NC4.

1.2.3.2.1.5. Collect all relevant macroeconomic data and establish the assumptions, that will be made to develop the emission scenario (based on new data related to the energy balance and recent sectoral economic plans for energy, transport, industry, waste, utilities and agriculture).

1.2.3.2.1.6. To identify any differences / changes in the scenario “business-as-usual scenario” developed in the framework of the TNC.

1.2.3.2.1.7. To identify acceptable models and available software for the development of scenarios (e.g. LEAP, IPCC).

1.2.3.2.1.8. To process the collected data for GHG emission scenarios (business-as-usual and stabilization) using the selected model and software (for example, LEAP, IPCC).

1.2.3.2.1.9. To make cross-check of the results of the scenario to ensure consistency in sectors and timelines with the inventory data from section 1.2.2 (inventory) and section 1.2.3.2 (mitigation), as well as data on policies and measures (PaMs) from section 1.2.4.

1.2.3.2.1.10. Based on the above, prepare the NC4 section/chapter on “measures to mitigate climate change” to include to the extent possible all the relevant information on programmes and measures implemented, or measures being considered by the government of Turkmenistan for future implementation which contribute to mitigating climate change, including, as appropriate, relevant information by key sectors on methodologies, scenarios, results, measures and institutional arrangements.

1.2.4 Mitigation actions and their effects, including associated methodologies and assumptions (BUR)

The preparation of this section of the BUR1 will be carried out in accordance with the requirements for its content and information presentation form provided in Annex III to Decision 2/CP.17, as well as using recommendations prepared by the Consultative Group of Experts of the UNFCCC Secretariat. The BUR1 section will be prepared by the experts in the field of mitigation of climate change.

Information will be provided on UNFCCC commitments made as PNC regarding the reduction of GHG emissions by 2030. Brief description of the scenarios of socio-economic development of the country until 2030 will also be provided. A brief information will be provided on the basic approaches that will be used to develop scenarios for projecting GHG emissions, taking into account mitigation measures and without those (the “business-as-usual” scenario) for the perspective until 2030, which should be developed as part of the NC4.

Data collection for each sector of the economy on activities aimed at mitigating climate change at the national and regional levels will be carried out in cooperation and close collaboration with interested organizations.

Based on the collected information, a Database will be formed containing detailed characteristics of completed, ongoing and planned mitigation measures for major sectors of the economy and greenhouse gases.

The effectiveness of measures aimed at mitigating climate change will be assessed using the methodologies, tools and assumptions recommended by the UNFCCC for each of the sectors of the economy. At the same time, it is supposed to develop progress indicators for each activity, calculate the amount of reduced emissions / increase in GHG removals, evaluate possible other benefits and other related effects based on modern approaches and methods.

It is planned to conduct analysis of the cost of mitigation measures, such as financing, with an indication of investors and the technologies used.

To assess the effect of the implementation of planned and current activities, forecast estimates of GHG emissions for the future until 2030, developed within the framework of the NC4, will be used.

The main section will be presented in a tabular format of the results of the assessment of completed, ongoing and planned mitigation measures in priority sectors of the economy. This will include the name of the event, its characteristics, sectors and GHGs covered, the state program related to this activity, participating organizations, and quantitative indicators of achieved reduction of emissions / increase of GHG removals and progress indicators. Also, the results of the analysis of the cost of mitigation measures and other benefits from their implementation (economic, social, environmental) will be presented in the tabular form.

The assessment of reduced GHG emissions will contribute to the further long-term planning activities at the national level; will assess the effectiveness of ongoing efforts to prevent climate change; increased transparency provided by the UNFCCC reporting.

The section will also provide detailed information on the development and implementation of mitigation projects in Turkmenistan, together with the other international market mechanisms that contribute to the reduction of GHG emissions.

Expected output and activities:

Output 1.2.4.1 climate change mitigation policies and measures (PaMs) updated, strengthened and included in the development of scenarios and reporting in the BUR1.

Activity:

1.2.4.1.1 To assess the status of PaMs reported in the TNC and add any new appropriate PaMs.

1.2.4.1.2 To conduct review of the status of relevant policies and regulatory frameworks and update macroeconomic forecasts and plans presented in the TNC.

1.2.4.1.3 To conduct review and analysis of the relationship of existing international initiatives and projects in Turkmenistan with the preparation of PaMs for the BUR1.

1.2.4.1.4. To prepare a roadmap and a set of recommendations to achieve the INDC goal presented by the UNFCCC by the Government of Turkmenistan, as well as ways to reduce GHG emissions in general.

1.2.4.1.5 To review and make recommendations with a view to attracting international funds and financial mechanisms to assist in mobilizing international assistance and investments aimed at developing and implementing GHG reduction projects.

Output 1.2.4.2: PaMs analysis performed for the period up to 2020 and the subsequent possible period, including new data and new assumptions relating to the period after the TNC.

Activity:

1.2.4.2.1. For each mitigation action or groups of mitigation actions, compile as appropriate, the following information to the extent possible for inclusion in the BUR1: (a) Name and description of the mitigation action, including information on the nature of the action, coverage (i.e. sectors and gases), quantitative goals and progress indicators; (b) Information on: (i) Methodologies (ii) Assumptions  (c) Information on: (i) Objectives of the action, (ii) Steps taken or envisaged to achieve that action and (d) Information on the progress of implementation of the mitigation actions and the underlying steps taken or envisaged, and the results achieved.

1.2.4.2.2. Compile and report in the BUR1 information on Turkmenistan’s participation in International market mechanisms as applicable.

1.2.4.2.3. To develop a draft chapter on “Mitigation actions and their effects, including associated methodologies and assumptions”, which includes a brief comparison of PaMs and the final subsection, which defines the priorities for actions.

1.2.4.2.4. To disseminate the draft chapter on “Mitigation actions and their effects, including associated methodologies and assumptions” for internal review and comments.

1.2.4.2.5. To disseminate the draft “Mitigation actions and their effects, including associated methodologies and assumptions” chapter for external peer review and comments.

1.2.4.2.6. To receive comments and include them in the document.

1.2.4.2.7. To organize a national workshop to highlight the results of the PaMs modeling and analysis and get more comments.

1.2.4.2.8. To finalize the “Mitigation actions and their effects, including associated methodologies and assumptions” chapter, which will be presented within the BUR1 of Turkmenistan.

1.2.4.2.9. To archive and document all studies, model runs, assumptions, and estimates for the “Mitigation actions and their effects, including associated methodologies and assumptions” chapter.

1.2.5 Other information

1.2.5.1 Integrating climate change considerations into social, economic and environmental policies and actions

The main conditions for integrating climate change actions into the national development plans are the alignment of development priorities with the needs for adaptation and mitigation measures; the possibility of reducing the risks caused by climate change when implementing the measures outlined.

The implementation of the UNFCCC in the country is regulated through the National Climate Change Strategy of Turkmenistan aimed at addressing the issues of mitigation and adaptation to climate change, nature management and environmental protection. Thereby, this will provide conditions for practical actions aimed at reducing GHG emissions and adaptation of sectors of the economy and population to the adverse effects of climate change, reflected / integrated into national and sectoral development programs. The analysis carried out within preparation of the TNC showed that despite the fact that the National Program for Adaptation to the Adverse Effects of Climate Change has not yet been developed, a number of measures and actions are integrated into the implemented, ongoing and planned national and sectoral plans. Thus, prerequisites have been created in Turkmenistan for improving approaches, mechanisms and measures that will ensure further harmonious and sustainable implementation of commitments under the UNFCCC. To intensify activities in the field of mitigation and adaptation, organization of a single, common flow of action, capacity building at all levels is necessary. Currently, the main problems are the shortage of funds and coordination at the intersectoral level; and the lack of economic justification for integrating climate change issues into development programs and awareness.

Expected outputs and activities:

Output 1.2.5.1.1: A “Group on Other Issues” Established.

Activity:

1.2.5.1.1.1: To establish a “Group on Other Issues”.

Output 1.2.5.1.2: sustainable development issues and integration of climate change priorities reflected.

Activity:

1.2.5.1.2.1 Gathering, synthesizing and providing complete updated information related to the integration of climate change issues into sustainable development programs, including the results obtained in the TNC. Preparation of a draft report that reflects national efforts to integrate climate change issues into sustainable development programs for review and comments.

1.2.5.1.2.2 Review of the draft on the main comments received and finalize it as part of the NC4 “Section: Integrating Climate Change issues into Sustainable Development Programs”.

1.2.5.2 Development and transfer of environmentally sound technologies (ESTs)

Article 10 of the Paris Agreement emphasizes the importance of the full implementation of technology development and transfer in order to increase resilience to climate change and reduce greenhouse gas emissions and strengthen cooperation activities in the development and transfer of technologies.

The transfer of the economy of Turkmenistan to the industrial-innovative development path necessitated equipping the industrial sectors with the high-tech equipment. In recent years, tremendous work has been done to attract foreign investments to the country's economy to create new industries, modernize and reequip enterprises of priority sectors of the economy.

At the present stage of development of the Turkmenistan’s economy, technology transfer is one of the main sources of transformation.

Turkmenistan considers technology transfer from the developed countries as the main source of innovative transformations. This is the exchange of experience, skills, knowledge, technologies and technological processes, manufacturing methods, industrial designs and means of production.

The main requirement for technologies imported into Turkmenistan is their environmental safety.

Technology transfer to Turkmenistan is carried out in two directions - commercial and non-commercial. It is done in the form of industrial cooperation, establishment of joint ventures, provision of technical assistance, engineering, transfer of know-how and licenses,  holding of international exhibitions and symposiums, publication of scientific and technical literature, exchange of delegations and organization of meetings of scientists, engineers, inventors; training of students and graduate students abroad, cooperation in the field of science and technology with developed countries of the world. At the current stage of development of Turkmenistan, the foundations are laid for the development of domestic technologies and equipment:

– modern technology Center meeting international standards has been created, on the basis of which the most complex fundamental and applied research is carried out;

– priority areas of scientific research in the country are identified;

– the structure of the Academy of Sciences is enhanced;

– the links with scientific institutions of developed countries of the world are established;

– exchange of knowledge and experience at the international and regional levels is being performed;

– training of scientific personnel has been activated; necessary conditions have been created to stimulate invention.

The most important and necessary condition for ensuring the import of modern equipment and technologies, as well as attracting foreign investments into the country, is a reliable legal basis for the protection of intellectual property. In recent years, Turkmenistan has taken a number of organizational measures and adopted legislative acts to strengthen the protection of intellectual property.

The TNC also examined the steps taken by the Government of Turkmenistan to technological re-equipment of all sectors of the economy. Deep transformations in the country's economy, carried out during the years of independence, allowed to re-equip the main industries with the advanced environmentally friendly technologies.

The characteristic feature of the developing economy of modern Turkmenistan is the orientation towards the introduction and application of advanced technologies and equipment used in world practice in all sectors of the economy. The solution to this issue is carried out in two areas of innovation policy: the use of the capabilities of the national scientific, technical and intellectual potential for developing original local technologies and the acquisition of foreign technologies adapted to local conditions.

One of the ways to achieve economic development through the introduction of advanced technologies is the transfer and acquisition of them on a contractual basis. The existing system of industrial property protection in Turkmenistan provides reliable legal protection of industrial property objects, including inventions, technologies, knowhow, utility models, industrial designs and trademarks and guarantees of the security of import of advanced technologies into the country.

The national system of industrial property protection includes the legislative base, patent office with the functions of accepting applications, examining, registering and publishing inventions, the institution of patent attorneys, the appeals commission, the patent information fund, the judicial defense and the society of inventors.

Expected output and activities:

Output 1.2.5.2.1: Opportunities for the "Transfer of environmentally sound technologies" are granted.

Activity:

1.2.5.2.1.1 Collection, synthesis and provision of information on how Turkmenistan executes transfer, access to environmentally friendly technologies and knowhow.

1.2.5.2.1.2 Revision of criteria for assessing and prioritizing technological needs, including environmentally friendly technologies (ESTs), cost-effectiveness, and opportunities for their implementation according to the national criteria for sustainable development.

1.2.5.2.1.3 Assessment of the need to review and revise existing legal and economic instruments / mechanisms to facilitate the transfer of ESTs.

1.2.5.2.1.4 Creation of a database for ESTs, including climate change mitigation and adaptation technologies, using the EST-Information System (ESTIS) developed by the UNEP International Center for Environmental Technology (IETC).

1.2.5.2.1.5 Summarizing all the information collected in the working version (draft) "Sub-head: Actions related to the Transfer of Technologies".

1.2.5.2.1.6 Inclusion of received comments, if any, in the working version of the "Section: Actions related to the Transfer of Technologies" and its completion as part of the "Chapter: Other information considered suitable for achieving the goals of the UNFCCC".

1.2.5.3 Climate change research and systematic observation

Scientific research. The Government of Turkmenistan focuses particular importance to the development of science, quality growth and stimulation of scientific activity. A reliable legal base has been created in the country for the development of domestic science; decisions have been made to improve infrastructure, and a long-term international cooperation has been launched with reputable international organizations and research centers in this area.

All scientific research, including preservation and improvement of the environment, is conducted under the leadership of the Academy of Sciences of Turkmenistan, renewed in 2009.

Research on climate change issues is especially important for Turkmenistan, because this process has a strong impact on all aspects of the country's socio-economic development. The average annual temperature in the country is one of the highest in the region. This adversely affects the functioning of the human body and the development of many sectors of the economy. As the temperature rises in summer, energy costs sharply increase for cooling residential and industrial premises. Reducing the volume of surface water resources exacerbates the already difficult situation with water consumption in the country.

Given the impact of climate change on the activities of various sectors of the economy, research is carried out in the relevant research institutions. These are: the National Institute of Deserts, Flora and Fauna of the State Committee for Environmental Protection and Land Resources of Turkmenistan, Suvylymtaslama Institute, Agriculture Institute of the Ministry of Agriculture and Environmental Protection; and Universities of the country (Makhtumkuli Turkmen State University, Turkmen State Agricultural University, Turkmen Medical University, Turkmen State Institute of Architecture and Civil Engineering, Turkmen State Oil and Gas Institute).

Systematic observations. According to the Law on Hydrometeorological Activities in Turkmenistan, the Cabinet of Ministers of the country and the Hydrometeorology Service (Turkmenhydromet) under the Ministry of Agriculture and Environmental Protection carry out the state regulation and management. The Cabinet of Ministers determines the national policy in the field of hydrometeorological activities, and the Turkmenhydromet directly implements it, being the main organization engaged in systematic observations of the climate. Its activities are aimed at providing information on weather, climate, water resources and the state of the environment; warning about dangerous and natural hydrometeorological phenomena and extremely high levels of environmental pollution.

Turkmehydromet is entrusted with the organization of monitoring the state of weather, the marine environment, surface waters, crops and pastures, and the radiation situation on the Earth's surface. To ensure monitoring, the activities of the observational network, the system of collection, storage, processing, analysis and dissemination of information received are constantly being improved.

Hydrological observations are carried out at stations and posts in rivers, canals and reservoirs. Monitoring is also carried out at 6 marine stations on the eastern coast of the Caspian Sea, where observations are made of sea waves, temperature and salinity.

The agrometeorological network takes into account the features of each agricultural zone of Turkmenistan. Currently, observations are being carried out by velayat (regional) centers for hydrometeorology, weather stations and agrometeorological posts.

Turkmenhydromet is a member of the Global Climate Observing System (GCOS) and transmits SYNOP reports of 11 stations for exchange globally and 20 - regionally. It also transmits CLIMAT reports of 5 and 11 stations, respectively.

Research on climate issues and its changes is especially important for Turkmenistan, because the average annual temperature here is one of the highest in the world. This creates unfavorable conditions for the functioning of the human body, as well as for the development of many sectors of the economy.

Within the framework of the NC4 implementation, in order to assess the likely climate change and its possible consequences, as well as to develop adaptation measures and strategies to prevent climate change, regional climate scenarios for the territory of Turkmenistan were elaborated.

Expected output and activities:

Output 1.2.5.3.1: Information on "Climate Change Research and Systematic Observations" prepared and compiled.

Activity:

1.2.5.3.1.1 Collection, compilation and provision of information on research and systematic observation systems.

1.2.5.3.1.2 Assessment of the general policy and funding of research and systematic observations in the country.

1.2.5.3.1.3 Assessment of efforts undertaken by the Government and formulation of recommendations to institutions regarding the climate process and climate system research. This includes paleoclimatic studies; modeling and forecasting using common circulation models; studies on the effects of climate change; socio-economic analysis, including analysis of the impacts of climate change options and responses; climate change mitigation research, and climate change adaptation technologies.

1.2.5.3.1.4 Assessment of information on the status of government plans, programs and support to the climate monitoring system.

1.2.5.3.1.5 Summarizing all the information collected in the working version (draft/project) of the "Section: Research and Systematic Observations of Climate Change".

1.2.5.3.1.6 Inclusion of comments received, if any, in the draft of the "Section: Research and Systematic Observations of Climate Change" and its completion as part of "Chapter 5: Other information suitable for achieving the goals of the UNFCCC".

1.2.5.4 Education, training and public awareness

An important place among the actions stipulated by the UNFCCC and aimed at involving the general public in activities related to the problem of climate change is occupied by “education, training and public awareness on the problems of climate change and its consequences” (Article 6 of the UNFCCC). In order to actively contribute to the implementation of all the provisions of this article and to involve the public in the adoption and implementation of decisions to achieve the goals of the UNFCCC, the Delhi Work Program was adopted at the 8th Conference of the Parties in 2002 under Article 6 of the UNFCCC. As a country party to the UNFCCC, Turkmenistan is actively developing awareness-raising activities and is training and educating the public on climate change and its consequences. This work is being done at the national, regional and subregional levels. At the same time, the results of the discussion on the problem of global climate change testified to the need to raise awareness among wide sections of society, the lack of qualified personnel and educational materials on climate change.

For implementation of global conventions in Turkmenistan, including the UNFCCC, the State Commission has been created to ensure the implementation of the country's obligations arising from UN conventions and programs on the environment. Activities to raise advocacy and public awareness of the issue of climate change in the country are coordinated by the Ministry of Agriculture and Environmental Protection of Turkmenistan, the responsible body for the implementation of the UNFCCC in Turkmenistan.

The work on raising awareness and public advocacy of the climate change problem in Turkmenistan is coordinated by the Ministry of Agriculture and Environmental Protection, the responsible body for the implementation of the UNFCCC in our country. In order to actively contribute to the implementation of all the provisions of this article and to involve the public in the adoption and implementation of decisions to achieve the goals of the UNFCCC, the Delhi Work Program was adopted at the 8th Conference of the Parties to the UNFCCC (Delhi, 2002). As a member country of the UNFCCC, Turkmenistan is actively implementing this program. This work covers various segments of the population (target groups) - scientists, teachers, schoolchildren, students, decision makers, specialists from ministries and departments of key sectors of the economy, industrial enterprises, representatives of business and the private sector, the media, environmental non-governmental organizations and the public.

Expected output and activities:

Output 1.2.5.4.1: An awareness-raising campaign developed and information on "Education, Training and Public Awareness" prepared.

Activity:

1.2.5.4.1.1 Assessment of the overall level of awareness and understanding of climate change issues and climate change education policies, seminars and public awareness.

1.2.5.4.1.2 Assessment of the National Curriculum and the efforts undertaken by the Government (for example, by the Ministry of Education) with advices for primary, secondary and higher education on climate change.

1.2.5.4.1.3 Assessment of available information regarding implemented or planned public information initiatives, campaigns and programs.

1.2.5.4.1.4 Assessment of available information regarding international cooperation aimed at developing education and public awareness.

1.2.5.4.1.5 Assessment of gaps, needs and priorities for climate change education and public awareness.

1.2.5.4.1.6 Implementation of awareness-raising campaign for a specific audience (politicians, environmental planners, private sector, the public, schoolchildren and students), including the preparation of visual materials on climate change and sustainable development and dissemination through the media (television, radio and newspapers).

1.2.5.4.1.7 Ensuring public access to information on climate change and sustainable development through the updated website of the climate change project in Russian and English related to climate change activities in Turkmenistan.

1.2.5.4.1.8 Collection, compilation and provision of complete information related to "Education, Training and Public Awareness" applicable to activities under Article 6 of the UNFCCC.

1.2.5.4.1.9 Organize two national seminars to raise awareness of national policy makers, especially those involved in national environmental planning processes.

1.2.5.4.1.10 Summarizing all the information collected in the draft of the “Section 5.4: Education, Training and Public Awareness”; inclusion of the comments received and its completion as part of the “Chapter 5: Other information considered appropriate to achieve the objectives of the UNFCCC”.

1.2.5.5 Capacity building

This section of the TNC describes the limitations, gaps and capacity needs identified in all chapters of the TNC. The existing limitations and gaps in the work to achieve the goals of the UNFCCC in Turkmenistan indicate the importance of capacity building in this area. This issue was also raised earlier in such projects as FNC/OPT/SNC, Regional Inventory Project, Self-Assessment Project of National Potential, etc.

The preparation of the Third National Communication (TNC) has shown that many of the capacity needs reflected in these documents are equally vital today. The existing legislative, technical, institutional, methodological, financial and scientific-educational needs of the potential on climate change issues can slow down the pace of development of society towards the use of modern, environmentally sound, energy-efficient and energy-saving technologies.

Expected output and activities:

Output 1.2.5.5.1: Information on “Capacity Building” prepared and compiled.

Activity:

1.2.5.5.1.1 Gathering, compiling and providing complete information on “Capacity Building”. Summarizing all the information collected in the project (working version) "Section 5.5: Capacity Building"; and its distribution for internal review and comments.

1.2.5.5.1.2 Inclusion of comments, if any, in the draft of the "Section 5.5: Capacity Building" and its completion as part of the "Chapter 5: Other information relevant to achieve the goals of the UNFCCC".

1.2.5.6 Information and networking

Expected output and activities:

Output 1.2.5.6.1: Information regarding "Information and Networking" prepared and compiled.

Activity:

1.2.5.6.1.1 Collection, compilation and provision of complete information regarding "Information and Networking". Summarizing all the information collected in the "Section 5.6: Information and Networking" draft and including the comments received, if any, in the "Section 5.6: Information and Networking" draft and completing it as part of "Chapter 5: Other relevant information to achieve the goals of the UNFCCC".

1.2.5.7 Gender and Climate Change

In previous National Communications of Turkmenistan, gender issues and participation of women in adaptation and mitigation activities, the process of developing policies and making decisions in the field of climate change were not considered separately. Over the years of independent development, Turkmenistan has achieved significant success in protecting the rights and interests of women, in ensuring their active participation in socio-political and socio-economic life.

The main document guaranteeing the fundamental rights of women is the Constitution of the country. The list of regulatory documents in support of gender equality includes a number of decrees and resolutions of the President of Turkmenistan and the Cabinet of Ministers. Annually, special state programs are adopted within the framework of which systematic work is carried out to improve the conditions and quality of life of women.

Particular attention is paid to the creation of effective health care system, the priority of which is the comprehensive provision of health for girls and mothers. The country fully ensures the right of girls and women to receive education and there is an effective system of pre-school, secondary, specialized secondary and higher education. Participation of women in public administration and in local government is becoming more and more active. Special attention is paid to the development of entrepreneurship among women, in particular, through the allocation of targeted credit lines for organizing their own business. In preparing the section, an analysis will be made of the gender role in the implementation of adaptation and mitigation activities, the development of policies and knowledge, in particular.

Expected output and activities:

Output 1.2.5.7.1 The role of women in the implementation of adaptation and mitigation measures, the development of policies and knowledge assessed.

Activity:

1.2.5.7.1.1 Analysis of government programs that take into account gender relations and needs of both men and women;

1.2.5.7.1.2 Review of activities aimed at raising the awareness of decision-makers about gender issues and problematic;

1.2.5.7.1.3 Analysis of vulnerability to climate change, taking into account gender characteristics and the specifics of local communities;

1.2.5.7.1.4 Analysis of measures and actions to raise awareness and familiarize women with the possibilities of using environmentally friendly technologies, RE, about available methods of adaptation to climate change in order to attract interested women;

1.2.5.7.1.5 Assessment of assistance to women in implementing entrepreneurial initiatives aimed at earning income using climate-resilient technologies and practices.

1.2.6 Support received for preparation and submission of biennial update report (BUR)

Earlier, in the National Communications on Climate Change of Turkmenistan for the UNFCCC, information on the level of support received was presented in various thematic sections.

Priorities for the preparation of the First Biennial Report.

In accordance with the Decision 2CP./17 of the UNFCCC, the BUR1 will include information on difficulties and gaps, as well as related needs for finance, technology and capacity-building.

Updated information will be provided on the support received during the preparation of the BUR1 in the form of financial resources, technology transfer, capacity building and technical support from the Global Environment Facility (GEF), the country-parties included in the Annexes I and II, international organizations (UNFCCC), cooperation along the South-South line. Collection of information on support received for the preparation of the BUR1 at the national level. The information will be presented in tabular format according to the requirements for the preparation of the BUR1.

Expected output and activities:

Output 1.2.6.1. Analysis of information on the level of support received to ensure the preparation of the first biennial update report.

Activity:

1.2.6.1.1. Assessment of financial resources, technology transfer, capacity building and technical assistance received from the GEF, GCF, Parties included in Annexes I and II, international organizations (UNFCCC), South-South cooperation within the framework of preparation of the BUR1.

1.2.6.1.2. Preparation of the BUR1 section “Information on the level of support received to ensure the preparation of the first report on updated data”.

1.2.7 Domestic measurement reporting and verification (MRV)

Output: Domestic, measurement, reporting and verification system enhanced.

Expected output and activities:

Output 1.2.7.1 The roadmap for establishing a system of measures, reporting and verification (MRV) of GHG emissions identified as part of the preparation of the BUR1.

Activity:

1.2.7.1.1. Technical capacity building on MRV including supporting national teams working on MRV to participate in the relevant sub regional/regional/international workshops/ trainings on MRV as appropriate.

1.2.7.1.2. Identify and assess different options and possibilities for establishment of a domestic MRV system

1.2.7.1.3. Develop proposals for a roadmap with a view to create a national MRV system, taking into account existing sectoral and national conditions and needs to strengthen the capacity of relevant institutions.

1.2.7.1.4. Organize consultations workshop with relevant stakeholders to discuss the proposed roadmap and strategic framework for establishing the MRV system.

1.2.7.1.5. Finalize the roadmap for the development of the MRV taking into account the comments and conduct internal and external review of the document.

1.2.7.1.6. Compile the BUR1 Chapter on “Domestic MRV”

1.2.8 Constraints and gaps, and related financial technical and capacity needs

The previous NCs of Turkmenistan did not contain a separate chapter regarding the limitations, gaps and related needs that faced the implementation of the NCs. However, gaps and limitations were highlighted in the implementation of the TNC and were related to the barriers of the energy sectors. The TNC report also presented technological needs to reduce GHG emissions. In addition, financial, institutional and strategic needs were described as technology options proposed by TNC. Most of these needs were identified by the project concepts.

It is worth mentioning that the National Capacity Self-Assessment Project implemented in Turkmenistan was also designed to strengthen the synergies of the three Rio de Janeiro Conventions: the United Nations Framework Convention on Climate Change (UNFCCC), the Convention on Biological Diversity (CBD) and the Convention to Combat Desertification (CCD). The Project also contributes to the country's long-term sustainable development. The Project identified priorities, needs and barriers for building capacity at the national level in order to fulfill obligations under these global environmental conventions. In the process of preparing the TNC, a number of limitations and gaps in the field of GHG inventory, vulnerability assessment, mitigation and adaptation to climate change were also identified; strategic and specific proposals for the development of national capacities at the institutional, public and individual levels were defined. The process also identified a list of tasks to be solved in the future that will allow to act on a long-term and sustainable basis.

The main restrictions include the following: insufficient close interaction between organizations involved in the process of preparing national communications; poor integration of climate change issues in the educational programs of schools, colleges and universities, lack of educational and informational materials, teaching aids on climate change in the national language. Non-governmental organizations and the public are not actively involved in activities on climate change issues and making significant decisions.

The common need for carrying out any activities and actions related to the fulfillment of obligations under the UNFCCC remains the development of human and information potential, technical and financial support on a regular basis, as well as strengthening coordination with relevant ministries and departments and state statistics organizations.

We consider it appropriate to single out a separate chapter in this direction within the framework of the NC4. The new constraints, gaps and needs, if any are identified in the preparation of each chapter of the NC4, will be described in this section.

Output 1.2.8.1. The analysis of the limitations and gaps associated with financial, technical activities and capacity building carried out.

Activities:

1.2.8.1.1 Analysis of information on difficulties, gaps, financial needs, technologies and capacity-building needs in the preparation of NC4 and BUR1.

1.2.8.1.2 Analysis of the support received for the transfer and implementation of new technologies, assessment of gaps and needs.

1.2.8.1.3 Preparation of the section “Limitations and Gaps; associated financial, technical and capacity-building needs” for inclusion in the BUR1 and NC4.

2. TECHNICAL ASSISTANCE

UNEP, as the GEF Implementing Agency for the BUR1 NC4 project, will provide consultations on all aspects during its implementation. The Implementing Agency will be fully informed on all activities and invited to actively participate in seminars related to the project, so that it can provide useful contributions in order to guarantee successful implementation of the project. If necessary, there will also be the request to other national, regional or international organizations and consultants for technical support.

It should also be noted that two training seminars on the application of integrated methodology for assessing vulnerability and adaptation, including modeling assessment and on the application of methodologies for assessing mitigation of climate change, will be organized with the assistance of national, regional and international consultants. Institutional strengthening and technical capacity building in these areas are a prerequisite for successful work.

Expected output and activities:

Output 2.1: Technical assistance provided.

Activity:

2.1.1 Regional and international consultants will be invited as necessary to provide training or technical assistance to the Vulnerability and Adaptation Assessment Team, GHG inventory team and Mitigation Assessment team in the specific approaches, tools and methods that are used for the Adaptation and Vulnerability Assessment, mitigation assessment and GHG inventory.

3. COMPILATION AND PRODUCTION OF NATIONAL COMMUNICATIONS AND BIENNIAL UPDATE REPORT

The complete results of studies carried out during the implementation of the NC4 Project will be compiled and reported in the form of a national report entitled "The Fourth National Communication of Turkmenistan on the UNFCCC". The structure and capabilities of the report will be developed in accordance with 17/CP8. The draft report will be distributed for comments and will be approved by the PSB.

The report will be published in Turkmen, Russian and English. The electronic version on the CD-ROM will be attached to it. The NC4/BUR1 message will be submitted to the UNFCCC Secretariat and distributed to relevant stakeholders. The report will be presented at a national workshop with the assistance of national and international consultants.

Expected output and activities:

Output 3.1: The Fourth National Communication and BUR1 prepared and submitted to the UNFCCC.

Activity:

3.1.1 Compile the draft BUR1 and NC4 for review and comments

3.1.2 Incorporate the review comments and finalize the BUR1 and NC4 and submit for approval by the PSB.

3.1.3Translation of the BUR1 and NC4 from Russian into English.

3.1.4 Publication and preparation of electronic copies of the BUR1 and NC4 on a CD-ROM and submission of the reports to UNFCCC.

3.1.5 Organize a final national conference on the NC4/ BUR1 project in Turkmenistan.

4. STOCKTAKING ASSESSMENT AND INSTITUTIONAL ARRANGEMENTS FOR PREPARATION OF SUBSEQUENT NCs AND BURs

Due to the fact that the country is actively conducting restructuring of the economy and management, it is proposed to expand the institutional framework for the implementation of the UNFCCC by involving newly created ministries, agencies and companies related to climate change, as well as non-governmental organizations and civil society.

In order to improve coordination of activities and strengthen interagency relations for the preparation of BUR1 and NC4, it is planned to create two Interagency Working Groups (IWGs): (1) for preparation of inventory of greenhouse gases and development of mitigation measures; and (2) for adaptation to the effects of climate change.

It is planned to create separate expert working groups for each thematic section of the NC4 and BUR, led by a leading expert, who will be accountable to the project manager.

Expanding the range of stakeholders involved in the preparation of the NC4 and BUR1 will be carried out on the basis of bilateral and multilateral consultations and will require improved interagency relations and enhanced role for a coordinating organization, including advanced training and a better understanding of issues related to climate change in all segments of the population. Enhanced interagency cooperation will contribute to the efforts to integrate climate change issues into relevant national and sectoral development programs.

Expected output and activities:

Output 4.1. A review analysis carried out, institutional mechanisms for the preparation of subsequent NCs and BURs/BTRs considered.

Activity:

- To conduct a self-assessment and review analysis and prepare a summary of activities and outcomes achieved after completion and submission of the NC4 and BUR1 to the UNFCCC.

- To prepare a strategy to involve all relevant stakeholders, including their potential role in the preparation of the NC and BUR/BTR, and identify key coordinators in the working groups to monitor problems related to funding, constraints and gaps, technical and capacity building needs.

- To propose measures to strengthen and maintain the existing institutional mechanism, including possible technical assistance, as well as strategies to increase synergies with relevant programs and institutions.

5. PROJECT MANAGEMENT

The NC4/BUR1 project will be implemented and managed under the umbrella of the UNDP project on development the sustainable cities. The Team Leader (TL) of the NC4/BUR1 project will work under the guidance of the UNDP’s Sustainable City Project Manager and the TL will be fully responsible for the quality implementation of NC4/BUR1 project interventions.

Expected output and activities:

Output 5.1: The NC4 and BUR1 project management mechanism established and operationalized.

Activity:

- Engage/assign a project manager

- Engage/assign a project implementation unit assistant

- Cover UNDP support costs

- Cover UNDP GMS (8% of the total net costs)

- Cover travel expenses (international) to present NC4/BUR1 at the COP

- Cover travel expenses (local business trip)

- Cover Bank commission charges.

- Annual financial audits

6. MONITORING AND REPORTING

The project cooperation agreement for Turkmenistan has been signed and includes chapters on monitoring and communications (attached) in the project document. The project results will be monitored annually and periodically evaluated during the implementation of the project. This will ensure that the project effectively achieves these results.

Expected output and activities:

Output 6.1. Monitoring and evaluation of the project carried out.

Activity:

6.1.1 Undertake Project Monitoring and evaluation (UNEP).

TABLE 1: PROJECT FINANCING AND BUDGET: BREAKDOWN OF GEF-FUNDS AND CO-FINANCING

| COMPONENTS | GEF contribution US$ | GOV’T contribution US$ (In-kind) | Total US$ |
| --- | --- | --- | --- |
| 1.1. National Consultations and NC & BUR Project Implementation Plan Preparation NC4/BUR1 | 20,000 | - | 20,000 |
| 1.2.1. National circumstances and institutional arrangements | 22,000 | - | 22,000 |
| 1.2.2. National GHG Inventories | 239,000 | - | 239,000 |
| 1.2.3.1. Measures to facilitate adequate adaptation | 94,000 | - | 94,000 |
| 1.2.3.2. Programs to mitigate climate change | 84,000 | - | 84,000 |
| 1.2.4. Mitigation actions and their effects, including associated methodologies and assumptions (BUR) | 100,000 | - | 100,000 |
| 1.2.5. Other information | 29,000 | - | 29,000 |
| 1.2.6. Support received for preparation and submission of biennial update report (BUR) | 5,000 | - | 5,000 |
| 1.2.7. Domestic measurement reporting and verification (BUR) | 45,000 | - | 45,000 |
| 1.2.8 Constraints and gaps, and related financial technical and capacity needs | 14,000 | - | 14,000 |
| 2. TECHNICAL ASSISTANCE | 20,000 | - | 20,000 |
| 3. COMPILATION AND PRODUCTION OF NATIONAL COMMUNICATIONS AND BIENNIAL UPDATE REPORT | 30,000 | - | 30,000 |
| 4. STOCKTAKING ASSESSMENT AND INSTITUTIONAL ARRANGEMENTS FOR PREPARATION OF SUBSEQUENT NCS AND BURS | 10,000 | - | 10,000 |
| 5. PROJECT MANAGEMENT | 120,000 | - | 120,000 |
| Government staff time (2 persons, 20% of staff time) | - | 20,000 | 20,000 |
| Office Space | - | 48,000 | 48,000 |
| Equipment | - | 5,000 | 5,000 |
| Furniture | - | 5,000 | 5,000 |
| Communication (mobile) | - | 2,000 | 2,000 |
| 6. MONITORING AND REPORTING (UNEP) | 20,000 | - | 20,000 |
| TOTAL | 852,000 | 80,000 | 932,000 |

TABLE 2: PROPOSED ACTIVITIES WITH COSTS FOR THE PREPARATION OF THE NATIONAL COMMUNICATION

| NC4/BUR1 Activities per component | Year(s) |  |  |  |  | Amount, USD |
| --- | --- | --- | --- | --- | --- | --- |
|  | Expenditure 2020 | Budget 2020 | Budget 2021 | Budget 2022 | Budget 2023 | Total |
| 1.2.A National consultations and NC4 BUR1 Project Implementation Plan preparation | 20,000 | - | - | - | - | 20,000 |
| Output 1.2.A.1: Stocktaking and National Consultations undertaken and NC4/BUR1 Project Implementation Plan Prepared | 20,000 | - | - | - | - | 20,000 |
| a1 Undertake stocktaking, national consultations and prepare NC4 and BUR1 project implementation plan | 20,000 | - | - | - | - | 20,000 |
| 1.2.1. National circumstances and institutional arrangements | - | 10,000 | 12,000 | - | - | 22,000 |
| Output 1.2.1.1: National circumstances, priorities and tasks underlying the solution of problems of climate change analyzed. | - | 6,000 | 6,000 | - | - | 12,000 |
| 1.2.1.1.1 Formation of a group of experts. | - | 1,000 | - | - | - | 1,000 |
| 1.2.1.1.2 Organize a project inception workshop to Launch NC4 and BUR1 project in Turkmenistan | - | 3,000 | - | - | - | 3,000 |
| 1.2.1.1.3 Review and analysis of changes in the political and economic development of the country in recent years and update relevant information on geography, population, natural resources and economy; and development policies, etc. relevant to climate change for inclusion in the NC4 and BUR4. | - | 2,000 | 2,000 | - | - | 4,000 |
| 1.2.1.1.4 Preparation of the section "National Circumstances" for the NC4 and BUR1. | - | - | 4,000 | - | - | 4,000 |
| Output 1.2.1.2: Institutional arrangement relevant to the preparation of national communications on an ongoing basis described. | - | 4,000 | 6,000 | - | - | 10,000 |
| 1.2.1.2.1 Collection and analysis of updated information. | - | 2,000 | 1,000 | - | - | 3,000 |
| 1.2.1.2.2 Description of existing institutional mechanisms relevant to the preparation of the NC of Turkmenistan on an ongoing basis. | - | 2,000 | 1,000 | - | - | 3,000 |
| 1.2.1.2.3 Preparation of the section on institutional arrangements for inclusion in the NC4 and BUR1. | - | - | 4,000 | - | - | 4,000 |
| 1.2.2. National GHG Inventories | - | 33,100 | 92,800 | 83,300 | 29,800 | 239,000 |
| Output 1.2.2.1: GHG inventory and data collection analysis team organized and strengthened. | - | 11,100 | 11,800 | 7,300 | 1,800 | 32,000 |
| 1.2.2.1.1 To identify and mobilize national experts in target sectors and areas relevant to the preparation of the GHG inventory. | - | 1,000 | - | - | - | 1,000 |
| 1.2.2.1.2 To review existing information and data on previous GHG inventories already archived and documented. | - | 2,000 | - | - | - | 2,000 |
| 1.2.2.1.3 To identify the specific needs of enterprises in staff training for data collection (with the emphasis on key source sectors, which are the main sources of emissions). | - | 1,500 | 1,500 | - | - | 3,000 |
| 1.2.2.1.4 To develop a national capacity building plan to enable the country to apply the 2006 IPCC Guidelines. | - | 2,000 | 2,000 | - | - | 4,000 |
| 1.2.2.1.5 Conduct training for national experts/teams working on GHG inventory including supporting them to participate in relevant regional/international trainings on GHG inventory. | - | 2,500 | 4,500 | 5,000 | - | 12,000 |
| 1.2.2.1.6 To review and update the quality assessment and quality control plan (QA/QC). | - | 1,500 | 1,500 | - | - | 3,000 |
| 1.2.2.1.7. To conduct a needs assessment and prepare terms of reference for the creation of a national inventory system with certain institutional mechanisms and a strategy for establishing the system. | - | - | 1,500 | 1,500 | 1,000 | 4,000 |
| 1.2.2.1.8. To improve intersectoral collaboration between relevant institutions for the preparation of GHG inventories. | - | 600 | 800 | 800 | 800 | 3,000 |
| Output 1.2.2.2. Data for the GHG inventory and methodology collected, validated and improved. | - | 17,000 | 27,000 | 7,000 | - | 51,000 |
| 1.2.2.2.1. To identify new sources of activity data for key source categories and priority sectors not included or explored in other programs. | - | 6,000 | 6,000 | - | - | 12,000 |
| 1.2.2.2.2. To identify new activity data needed to estimate GHG emissions, including, where applicable, recommendations from the UNFCCC In-depth Review Team. | - | 5,000 | 9,000 | - | - | 14,000 |
| 1.2.2.2.3. To use the IPCC best practice methodologies to fill data gaps. | - | - | 6,000 | 6,000 | - | 12,000 |
| 1.2.2.2.4 To identify data sources for source categories (international bunkers, solvents, industrial processes) not covered by the Third National Communication (TNC). | - | 6,000 | 6,000 | - | - | 12,000 |
| 1.2.2.2.5. Identify areas where data may be further improved in future communications through capacity-building where necessary. | - | - | - | 1,000 | - | 1,000 |
| Output 1.2.2.3 National inventory of anthropogenic GHGs by sources and removals by sinks for 1994-2020 conducted. | - | 5,000 | 54,000 | 56,500 | 9,500 | 125,000 |
| 1.2.2.3.1 To estimate emissions for new gases (HFCs, PFCs, SF6). | - | - | 5,000 | 3,000 | - | 8,000 |
| 1.2.2.3.2 To assess the applicability of the 2006 IPCC emission factors. | - | 5,000 | - | - | - | 5,000 |
| 1.2.2.3.3. To develop, as appropriate, the national emission factors for key source categories, such as energy (mainly focusing on subsectors - fugitive emissions and fuel combustion), industry (mainly focusing on cement and lime production subsectors) and LULUCF (mainly focusing on forest, pasture and arable land). | - | - | 4,000 | 4,000 | 2,000 | 10,000 |
| 1.2.2.3.4. To recalculate the GHG inventory for 1994-2010 (prepared under the TNC). | - | - | 10,000 | 8,000 | - | 18,000 |
| 1.2.2.3.5. To conduct analysis and inventory of key sources (for 2018) and sensitivity analysis in accordance with the IPCC guidelines. | - | - | 10,000 | 5,000 | - | 15,000 |
| 1.2.2.3.6. To calculate the GHG inventory for all sectors and gases in accordance with the 2006 IPCC Guidelines for the years 2011-2020 for the NC4. The BUR1 will cover the period up to year 2018 and this will be extended to year 2020 under NC4 | - | - | 15,000 | 20,000 | 4,000 | 39,000 |
| 1.2.2.3.7. To organize a national seminar to present the results of the GHG inventory and to receive additional comments in accordance with the timing of data submission for the NC4 and BUR1. | - | - | - | 6,000 | - | 6,000 |
| 1.2.2.3.8. To introduce an uncertainty analysis for all sectors considered under the GHG inventory and provide information on the level of uncertainty associated with inventory data and their underlying assumptions, and describe the methodologies used, if any, for estimating the uncertainties. | - | - | 5,000 | 6,000 | 2,000 | 13,000 |
| 1.2.2.3.9. To implement QA/QC procedures for key sectors / source categories. | - | - | 5,000 | 4,000 | 1,000 | 10,000 |
| 1.2.2.3.10. Provide information on methodologies used in the estimation of anthropogenic emissions by sources and removals by sinks of GHGs not controlled by the Montreal Protocol, including a brief explanation of the sources of Emission factors and Activity data. | - | - | - | 500 | 500 | 1,000 |
| Output 1.2.2.4. GHG inventory completed and archived. | - | - | - | 12,500 | 18,500 | 31,000 |
| 1.2.2.4.1. To prepare a National GHG Inventory Report for 1994-2018 (for the BUR1), 1994-2020 (for the NC4). | - | - | - | 7,000 | 8,000 | 15,000 |
| 1.2.2.4.2. To prepare proposals for the establishment of the National Inventory System by 2023. | - | - | - | 3,000 | 4,000 | 7,000 |
| 1.2.2.4.3. To conduct a workshop with decision makers from data source institutions to present the final results of the inventory process. | - | - | - | - | 5,000 | 5,000 |
| 1.2.2.4.4. To prepare and make archiving of the GHG inventory and describe the procedures and arrangements undertaken to collect and archive data for the preparation of national GHG inventories, as well as efforts to make this a continuous process, including information on the role of the institutions involved. | - | - | - | 2,500 | 1,500 | 4,000 |
| 1.2.3. General Description of steps | - | 16,950 | 48,300 | 80,800 | 31,950 | 178,000 |
| 1.2.3.1 Measures to facilitate adequate adaptation | - | 15,950 | 30,800 | 30,800 | 16,450 | 94,000 |
| Output 1.2.3.1.1: National Group on Measures Promoting Adequate Adaptation developed and strengthened. | - | 6,500 | 7,000 | 5,000 | 500 | 19,000 |
| 1.2.3.1.1.1. Establishment of the National Group for Measures Promoting Adequate Adaptation and appointment of a Team Leader. | - | 1,000 | - | - | - | 1,000 |
| 1.2.3.1.1.2. Inclusion of leading experts from ministries and departments related to climate change issues in the National Group on Measures Promoting Adequate Adaptation. | - | 1,000 | 1,000 | - | - | 2,000 |
| 1.2.3.1.1.3. Assessment of risks associated with climate change. | - | 1,000 | 2,000 | 1,000 | - | 4,000 |
| 1.2.3.1.1.4. Development of the list of specific adaptation measures with aggregative assessment of costs and benefits of their implementation. | - | 500 | 1,000 | 1,000 | 500 | 3,000 |
| 1.2.3.1.1.5. Organization of the first national seminar on measures to promote adequate adaptation in the initial period of the Fourth National Communication with the purpose to consult with relevant stakeholders and identify approaches, tools and methods that will be used during vulnerability and adaptation assessment. | - | 2,000 | - | - | - | 2,000 |
| 1.2.3.1.1.6. Technical capacity-building of national teams/experts working on vulnerability and adaptation assessments, including supporting their participation in relevant sub regional/regional/international workshops on Vulnerability Assessment and Adaptation as appropriate | - | 1,000 | 3,000 | 3,000 | - | 7,000 |
| Output 1.2.3.1.2 Approaches, tools and methods to be used during vulnerability assessment and adaptation approved. | - | 2,950 | 5,550 | 4,550 | 1,950 | 15,000 |
| 1.2.3.1.2.1. Identification of necessary data and information, and selection and description of approaches, tools and methods to be used for evaluation of impacts of and vulnerability and adaptation to climate change. | - | 1,000 | 1,000 | - | - | 2,000 |
| 1.2.3.1.2.2. Development and use of methods for calculating costs and benefits in the implementation of specific adaptation measures. | - | 500 | 1,000 | 1,000 | 500 | 3,000 |
| 1.2.3.1.2.3. Review of the policy and development process in the context of the chosen field in order to explore how adaptation measures can be implemented in the decision-making agenda and the best mechanisms for their implementation. | - | 500 | 1,000 | 1,000 | 500 | 3,000 |
| 1.2.3.1.2.4. Determination of a set of measures to eliminate the water shortage associated with climate change (reducing river flows and changing their hydrograph, increasing irrigation norms with increasing temperature and evapotranspiration growth, expanding evaporation from the water surface). | - | 500 | 1,500 | 1,500 | 500 | 4,000 |
| 1.2.3.1.2.5. Support the implementation of the Central Asian Land Management Initiative (CACILM). | - | 200 | 300 | 300 | 200 | 1,000 |
| 1.2.3.1.2.6. Assistance in strengthening the activity of the State Commission for Ensuring Fulfillment of the Obligations of Turkmenistan arising from the UN conventions and programs on the environment. | - | 250 | 750 | 750 | 250 | 2,000 |
| Output 1.2.3.1.3: Vulnerability and Adaptation Assessment Implemented. | - | 3,500 | 8,000 | 7,000 | 2,500 | 21,000 |
| 1.2.3.1.3.1. Identification and description of the scope of vulnerability and adaptation assessment of Turkmenistan and description of vulnerable areas, and the development of reliable indicators (climate and multilateral impact, socio-economic development, etc.). It is supposed to include “prevented damage” as one of the indicators. In various sectors of the economy, this indicator should be calculated independently by the industry experts: | - | 1,500 | 3,000 | 2,000 | 500 | 7,000 |
| 1.2.3.1.3.2. Under the socio-economic indicator for the rural population, calculate the increase in the standard of living of the population, expressed as an increase in income from agricultural production, subject to the implementation of adaptation measures in the water and agricultural sectors. | - | 500 | 1,000 | 1,000 | 500 | 3,000 |
| 1.2.3.1.3.3. Compile relevant information on implementation of sectoral and/or integrated analysis of Turkmenistan's vulnerability to climate change for all relevant sectors of the economy. | - | 1,000 | 2,000 | 2,000 | 1,000 | 6,000 |
| 1.2.3.1.3.4. For each sector of the economy, performance of vulnerability assessment and identification of risks - material and social - in case of failure to implement possible adaptation measures (reducing crop yields and animal productivity, loss of biodiversity, etc.) will be undertaken. | - | 500 | 2,000 | 2,000 | 500 | 5,000 |
| Output 1.2.3.1.4: Basic scenarios developed | - | 1,500 | 5,000 | 5,000 | 1,500 | 13,000 |
| 1.2.3.1.4.1. Development of climate scenarios using modern models. | - | 500 | 2,000 | 2,000 | 500 | 5,000 |
| 1.2.3.1.4.2. Development of economic scenarios together with the Ministry of Finance and Economics of Turkmenistan. | - | 500 | 2,000 | 2,000 | 500 | 5,000 |
| 1.2.3.1.4.3. Determination of the cost of implementing these measures and the timing of their implementation in accordance with the considered scenarios of the country's economic development for the future. | - | 250 | 750 | 750 | 250 | 2,000 |
| 1.2.3.1.4.4. Development of recommendations for the implementation of early warning system for the likelihood of drought, floods, and mudflows. | - | 250 | 250 | 250 | 250 | 1,000 |
| Output 1.2.3.1.5: Adaptation measures assessed and described. | - | 1,500 | 5,250 | 6,500 | 2,750 | 16,000 |
| 1.2.3.1.5.1. Assessment of current climate change adaptation strategies and measures in key areas; future climate risk assessed. | - | 250 | 750 | 750 | 250 | 2,000 |
| 1.2.3.1.5.2. For the specific adaptation measures, describe ways of their implementation, i.e. mechanism for the implementation of these activities, sources of funding, monitoring and timing of their implementation. | - | - | - | 1,000 | 1,000 | 2,000 |
| 1.2.3.1.5.3. Develop new adaptation responses and predict potential impacts and develop multi-level adaptation scenarios. | - | 750 | 1,750 | 1,750 | 750 | 5,000 |
| 1.2.3.1.5.4. Assist in the development of National Action Plans for Adaptation to Climate Change in key ministries and departments. | - | 500 | 1,000 | 1,000 | 500 | 3,000 |
| 1.2.3.1.5.5. Include in the industry specific NAPAs a list of concrete adaptation measures in the context of the sectors of the economy of Turkmenistan, the timing of their implementation (if necessary, stages), assessment of the costs of their implementation, responsible executives, sources of funding. | - | - | 1,000 | 1,000 | - | 2,000 |
| 1.2.3.1.5.6. Define and establish a policy framework for the implementation of the National Climate Change Adaptation Action Plan (NCCAAP) in Turkmenistan. | - | - | 500 | 500 | - | 1,000 |
| 1.2.3.1.5.7. Carrying out technical review of the NCCAAP executed by ministries and departments. | - | - | 250 | 500 | 250 | 1,000 |
| Output 1.2.3.1.6: Chapter 3: "Measures to Promote Adequate Adaptation" of the NC4 developed. | - | - | - | 2,750 | 7,250 | 10,000 |
| 1.2.3.1.6.1. Development of the draft Chapter 3: "Measures to promote adequate adaptation" of the Fourth National Communication. | - | - | - | 1,000 | 1,000 | 2,000 |
| 1.2.3.1.6.2. Dissemination of the draft chapter for internal and external review, receipt and inclusion of comments, completion of Chapter 3: "Measures to promote adequate adaptation", as part of the Fourth National Communication. | - | - | - | 500 | 500 | 1,000 |
| 1.2.3.1.6.3. Inclusion of comments and observations received after the reviews and finalization of Chapter 3: "Measures to promote adequate adaptation" of the NC4. | - | - | - | 250 | 750 | 1,000 |
| 1.2.3.1.6.4. Organize national workshop on Vulnerability and Adaptation to review and approve activities that promote adequate adaptation | - | - | - | - | 2,000 | 2,000 |
| 1.2.3.1.6.5. Archiving and documenting all studies and assessments of vulnerability and adaptation. | - | - | - | 500 | 1,500 | 2,000 |
| 1.2.3.1.6.6. Creation of database of materials and documents related to climate change issues. | - | - | - | 500 | 500 | 1,000 |
| 1.2.3.1.6.7. Creation of database of experts and specialists who are directly involved in resolving issues related to climate change. | - | - | - | - | 1,000 | 1,000 |
| 1.2.3.2. Programs to mitigate climate change | - | 1,000 | 17,500 | 50,000 | 15,500 | 84,000 |
| Output 1.2.3.2.1. The necessary data and relevant information for the development of the scenario collected, analyzed and used to develop the scenario. | - | 1,000 | 17,500 | 50,000 | 15,500 | 84,000 |
| 1.2.3.2.1.1. Technical capacity building of national teams/experts working mitigation measures including supporting their participation in relevant regional/international workshops/trainings on mitigation assessment as appropriate | - | 1,000 | 3,000 | 3,000 | 2,000 | 9,000 |
| 1.2.3.2.1.2. Identify and mobilize national experts in target sectors and areas relevant to the preparation of the PaMs. | - | - | 1,000 | - | - | 1,000 |
| 1.2.3.2.1.3. Conduct an analysis of the assessment of the inventory for 2011-2020 and fulfill the forecast for GHG emissions by 2030. | - | - | 9,000 | 7,000 | - | 16,000 |
| 1.2.3.2.1.4. Conduct a comparative analysis of the data/estimates obtained in the framework of the GHG inventory for the TNC, with the data projected for the same year within the framework of the NC4. | - | - | 4,500 | 3,500 | - | 8,000 |
| 1.2.3.2.1.5. Collect all relevant macroeconomic data and establish the assumptions, that will be made to develop the emission scenario (based on new data related to the energy balance and recent sectoral economic plans for energy, transport, industry, waste, utilities and agriculture). | - | - |  | 20,000 | - | 20,000 |
| 1.2.3.2.1.6. To identify any differences / changes in the scenario “business-as-usual scenario” developed in the framework of the TNC. | - | - | - | 2,500 | 2,500 | 5,000 |
| 1.2.3.2.1.7. To identify acceptable models and available software for the development of scenarios (e.g. LEAP, IPCC). | - | - | - | 1,000 | - | 1,000 |
| 1.2.3.2.1.8. To process the collected data for GHG emission scenarios (basic and stabilization) using the selected model and software (for example, LEAP, IPCC). | - | - | - | 8,000 | 6,000 | 14,000 |
| 1.2.3.2.1.9. To make cross-check of the results of the scenario to ensure consistency in sectors and timelines with the inventory data from section 1.2.2 (inventory) and section 1.2.3.2 (mitigation), as well as data on policies and measures (PaMs) from section 1.2.4. | - | - | - | 5,000 | 3,000 | 8,000 |
| 1.2.3.2.1.10. Based on the above, prepare the NC4 section/chapter on “measures to mitigate climate change” to include to the extent possible all the relevant information on programmes and measures implemented, or measures being considered by the government of Turkmenistan for future implementation which contribute to mitigating climate change, including, as appropriate, relevant information by key sectors on methodologies, scenarios, results, measures and institutional arrangements | - | - | - | - | 2,000 | 2,000 |
| 1.2.4. Mitigation actions and their effects, including associated methodologies and assumptions (BUR) | - | - | 63,500 | 36,500 | - | 100,000 |
| Output 1.2.4.1 Climate change mitigation policies and measures (PaMs) updated, strengthened and included in the development of scenarios and reporting in the BUR1 | - | - | 55,000 | 13,000 | - | 68,000 |
| 1.2.4.1.1 To assess the status of PaMs reported in the TNC and add any new appropriate PaMs. | - | - | 10,000 | - | - | 10,000 |
| 1.2.4.1.2 To conduct review of the status of relevant policies and regulatory frameworks and update macroeconomic forecasts and plans presented in the TNC. | - | - | 11,000 | 3,000 | - | 14,000 |
| 1.2.4.1.3 To conduct review and analysis of the relationship of existing international initiatives and projects in Turkmenistan with the preparation of a PaMs for the BUR1. | - | - | 9,000 | 3,000 | - | 12,000 |
| 1.2.4.1.4. To prepare a roadmap and a set of recommendations to achieve the INDC goal presented by the UNFCCC by the Government of Turkmenistan, as well as ways to reduce GHG emissions in general. | - | - | 16,000 | 4,000 | - | 20,000 |
| 1.2.4.1.5. To review and make recommendations with a view to attracting international funds and financial mechanisms to assist in mobilizing international assistance and investments aimed at developing and implementing GHG reduction projects. | - | - | 9,000 | 3,000 | - | 12,000 |
| Output 1.2.4.2: PaMs analysis performed for the period up to 2020 and the subsequent possible period, including new data and new assumptions relating to the period after the TNC. | - | - | 8,500 | 23,500 | - | 32,000 |
| 1.2.4.2.1. For each mitigation action or groups of mitigation actions, compile as appropriate, the following information to the extent possible for inclusion in the BUR1: (a) Name and description of the mitigation action, including information on the nature of the action, coverage (i.e. sectors and gases), quantitative goals and progress indicators; (b) Information on: (i) Methodologies (ii) Assumptions (c) Information on: (i) Objectives of the action, (ii) Steps taken or envisaged to achieve that action and (d) Information on the progress of implementation of the mitigation actions and the underlying steps taken or envisaged, and the results achieved. | - | - | 4,500 | 1,000 | - | 5,500 |
| 1.2.4.2.2. Compile and report in the BUR1 information on Turkmenistan’s participation in International market mechanisms as applicable. | - | - | 1,000 | 500 | - | 1,500 |
| 1.2.4.2.3. To develop a draft chapter on “Mitigation actions and their effects, including associated methodologies and assumptions”, which includes a brief comparison of PaMs and the final subsection, which defines the priorities for actions. | - | - | 3,000 | 2,000 | - | 5,000 |
| 1.2.4.2.4. To disseminate the draft chapter on “Mitigation actions and their effects, including associated methodologies and assumptions” for internal review and comments. | - | - | - | 3,000 | - | 3,000 |
| 1.2.4.2.5. To disseminate the draft “Mitigation actions and their effects, including associated methodologies and assumptions” chapter for external peer review and comments. | - | - | - | 3,000 | - | 3,000 |
| 1.2.4.2.6. To receive comments and include them in the document. | - | - | - | 2,000 | - | 2,000 |
| 1.2.4.2.7. To organize a national workshop to highlight the results of the PaMs modeling and analysis and get more comments. | - | - | - | 5,000 | - | 5,000 |
| 1.2.4.2.8. To finalize the “Mitigation actions and their effects, including associated methodologies and assumptions” chapter, which will be presented within the BUR1 of Turkmenistan. | - | - | - | 2,000 | - | 2,000 |
| 1.2.4.2.9. To archive and document all studies, model runs, assumptions, and estimates for the “Mitigation actions and their effects, including associated methodologies and assumptions” chapter. | - | - | - | 5,000 | - | 5,000 |
| 1.2.5. Other information | - | 3,100 | 4,950 | 13,250 | 7,700 | 29,000 |
| 1.2.5.1 Integrating climate change considerations into social, economic and environmental policies and actions | - | - | 1,500 | 500 | 1,000 | 3,000 |
| Output 1.2.5.1.1: A “Group on Other Issues” Established. | - | - | 1,000 | - | - | 1,000 |
| 1.2.5.1.1.1: To establish a “Group on Other Issues”. | - | - | 1,000 | - | - | 1,000 |
| Output 1.2.5.1.2: Sustainable development issues and integration of climate change priorities reflected. | - | - | 500 | 500 | 1,000 | 2,000 |
| 1.2.5.1.2.1 Gathering, synthesizing and providing complete updated information related to the integration of climate change issues into sustainable development programs, including the results obtained in the TNC. Preparation of a draft report that reflects national efforts to integrate climate change issues into sustainable development programs for review and comments. | - | - | 500 | 500 | - | 1,000 |
| 1.2.5.1.2.2 Review of the draft on the main comments received and finalize it as part of the NC4 “Section: Integrating Climate Change issues into Sustainable Development Programs”. | - | - | - | - | 1,000 | 1,000 |
| 1.2.5.2 Development and transfer of environmentally sound technologies (ESTs) | - | - | 1,000 | 1,450 | 650 | 3,100 |
| Output 1.2.5.2.1: Opportunities for the "Transfer of environmentally sound technologies" are granted. | - | - | 1,000 | 1,450 | 650 | 3,100 |
| 1.2.5.2.1.1 Collection, synthesis and provision of information on how Turkmenistan executes transfer, access to environmentally friendly technologies and knowhow. | - | - | 250 | 250 | - | 500 |
| 1.2.5.2.1.2 Revision of criteria for assessing and prioritizing technological needs, including environmentally friendly technologies (ESTs), cost-effectiveness, and opportunities for their implementation according to the national criteria for sustainable development. | - | - | 250 | 250 | - | 500 |
| 1.2.5.2.1.3 Assessment of the need to review and revise existing legal and economic instruments / mechanisms to facilitate the transfer of ESTs. | - | - | 250 | 250 | - | 500 |
| 1.2.5.2.1.4 Creation of a database for ESTs, including climate change mitigation and adaptation technologies, using the EST-Information System (ESTIS) developed by the UNEP International Center for Environmental Technology (IETC). | - | - | 250 | 250 | - | 500 |
| 1.2.5.2.1.5 Summarizing all the information collected in the working version (draft) "Sub-head: Actions related to the Transfer of Technologies". | - | - | - | 200 | 400 | 600 |
| 1.2.5.2.1.6 Inclusion of received comments, if any, in the working version of the "Section: Actions related to the Transfer of Technologies" and its completion as part of the "Chapter: Other information considered suitable for achieving the goals of the UNFCCC". | - | - | - | 250 | 250 | 500 |
| 1.2.5.3 Climate change research and systematic observation | - | - | 1,500 | 2,800 | 1,700 | 6,000 |
| Output 1.2.5.3.1: Information on "Climate Change Research and Systematic Observations" prepared and compiled. | - | - | 1,500 | 2,800 | 1,700 | 6,000 |
| 1.2.5.3.1.1 Collection, compilation and provision of information on research and systematic observation systems. | - | - | 500 | 500 | - | 1,000 |
| 1.2.5.3.1.2 Assessment of the general policy and funding of research and systematic observations in the country. | - | - |  | 500 | 500 | 1,000 |
| 1.2.5.3.1.3 Assessment of efforts undertaken by the Government and formulation of recommendations to institutions regarding the climate process and climate system research. This includes paleoclimatic studies; modeling and forecasting using common circulation models; studies on the effects of climate change; socio-economic analysis, including analysis of the impacts of climate change options and responses; climate change mitigation research, and climate change adaptation technologies. | - | - | 1,000 | 1,000 | - | 2,000 |
| 1.2.5.3.1.4 Assessment of information on the status of government plans, programs and support to the climate monitoring system. | - | - | - | 500 | 500 | 1,000 |
| 1.2.5.3.1.5 Summarizing all the information collected in the working version (draft/project) of the "Section: Research and Systematic Observations of Climate Change". | - | - | - | 300 | 200 | 500 |
| 1.2.5.3.1.6 Inclusion of comments received, if any, in the draft of the "Section: Research and Systematic Observations of Climate Change" and its completion as part of "Chapter 5: Other information suitable for achieving the goals of the UNFCCC". | - | - | - | - | 500 | 500 |
| 1.2.5.4 Education training and public awareness | - | 3,100 | 250 | 4,250 | 1,100 | 8,700 |
| Output 1.2.5.4.1: An awareness-raising campaign developed and information on "Education, Training and Public Awareness" prepared. | - | 3,100 | 250 | 4,250 | 1,100 | 8,700 |
| 1.2.5.4.1.1 Assessment of the overall level of awareness and understanding of climate change issues and climate change education policies, seminars and public awareness. | - | - | - | 200 | 200 | 400 |
| 1.2.5.4.1.2 Assessment of the National Curriculum and the efforts undertaken by the Government (for example, by the Ministry of Education) with advices for primary, secondary and higher education on climate change. | - | - | - | 100 | 100 | 200 |
| 1.2.5.4.1.3 Assessment of available information regarding implemented or planned public information initiatives, campaigns and programs. | - | - | - | 100 | 100 | 200 |
| 1.2.5.4.1.4 Assessment of available information regarding international cooperation aimed at developing education and public awareness. | - | - | - | 100 | 100 | 200 |
| 1.2.5.4.1.5 Assessment of gaps, needs and priorities for climate change education and public awareness. | - | - | - | 100 | 100 | 200 |
| 1.2.5.4.1.6 Implementation of awareness-raising campaign for a specific audience (politicians, environmental planners, private sector, the public, schoolchildren and students), including the preparation of visual materials on climate change and sustainable development and dissemination through the media (television, radio and newspapers). | - | 50 | 200 | 200 | 50 | 500 |
| 1.2.5.4.1.7 Ensuring public access to information on climate change and sustainable development through the updated website of the climate change project in Russian and English related to climate change activities in Turkmenistan. | - | 50 | 50 | 50 | 50 | 200 |
| 1.2.5.4.1.8 Collection, compilation and provision of complete information related to "Education, Training and Public Awareness" applicable to activities under Article 6 of the UNFCCC. | - | - | - | 100 | 100 | 200 |
| 1.2.5.4.1.9 Organize two national seminars to raise awareness of national policy makers, especially those involved in national environmental planning processes, public health workers and the interested members of the public about the effects of climate change | - | 3,000 | - | 3,000 | - | 6,000 |
| 1.2.5.4.1.10 Summarizing all the information collected in the draft of the “Section 5.4: Education, Training and Public Awareness”; inclusion of the comments received and its completion as part of the “Chapter 5: Other information considered appropriate to achieve the objectives of the UNFCCC”. | - | - | - | 300 | 300 | 600 |
| 1.2.5.5 Capacity building | - | - | - | 750 | 1,250 | 2,000 |
| Output 1.2.5.5.1: Information on “Capacity Building” prepared and compiled. | - | - | - | 750 | 1,250 | 2,000 |
| 1.2.5.5.1.1 Gathering, compiling and providing complete information on “Capacity Building”. Summarizing all the information collected in the project (working version) "Section 5.5: Capacity Building"; and its distribution for internal review and comments. | - | - | - | 750 | 750 | 1,500 |
| 1.2.5.5.1.2 Inclusion of comments, if any, in the draft of the "Section 5.5: Capacity Building" and its completion as part of the "Chapter 5: Other information relevant to achieve the goals of the UNFCCC". | - | - | - | - | 500 | 500 |
| 1.2.5.6 Information and networking | - | - | - | 2,000 | 2,000 | 4,000 |
| Output 1.2.5.6.1: Information regarding "Information and Networking" prepared and compiled. | - | - | - | 2,000 | 2,000 | 4,000 |
| 1.2.5.6.1.1 Collection, compilation and provision of complete information regarding "Information and Networking". Summarizing all the information collected in the "Section 5.6: Information and Networking" draft and including the comments received, if any, in the "Section 5.6: Information and Networking" draft and completing it as part of "Chapter 5: Other relevant information to achieve the goals of the UNFCCC". | - | - | - | 2,000 | 2,000 | 4,000 |
| 1.2.5.7 Gender and Climate Change | - | - | 700 | 1,500 | - | 2,200 |
| Output 1.2.5.7.1 The role of women in the implementation of adaptation and mitigation measures, the development of policies and knowledge assessed. | - | - | 700 | 1,500 | - | 2,200 |
| 1.2.5.7.1.1 Analysis of government programs that take into account gender relations and needs of both men and women; | - | - | 300 | 300 | - | 600 |
| 1.2.5.7.1.2 Review of activities aimed at raising the awareness of decision-makers about gender issues and problematic; | - | - | 200 | 200 | - | 400 |
| 1.2.5.7.1.3 Analysis of vulnerability to climate change, taking into account gender characteristics and the specifics of local communities; | - | - | - | 400 | - | 400 |
| 1.2.5.7.1.4 Analysis of measures and actions to raise awareness and familiarize women with the possibilities of using environmentally friendly technologies, RE, about available methods of adaptation to climate change in order to attract interested women; | - | - | - | 400 | - | 400 |
| 1.2.5.7.1.5 Assessment of assistance to women in implementing entrepreneurial initiatives aimed at earning income using climate-resilient technologies and practices. | - | - | 200 | 200 | - | 400 |
| 1.2.6. Support received for preparation and submission of biennial update report (BUR) | - | 500 | 3,000 | 1,500 | - | 5,000 |
| Output 1.2.6.1. Analysis of information on the level of support received to ensure the preparation of the first biennial update report. | - | 500 | 3,000 | 1,500 | - | 5,000 |
| 1.2.6.1.1. Assessment of financial resources, technology transfer, capacity building and technical assistance received from the GEF, GCF, Parties included in Annexes I and II, international organizations (UNFCCC), South-South cooperation within the framework of preparation of the BUR1. | - | 500 | 2,000 | 500 | - | 3,000 |
| 1.2.6.1.2. Preparation of the BUR1 section “Information on the level of support received to ensure the preparation of the first report on updated data”. | - | - | 1,000 | 1,000 | - | 2,000 |
| 1.2.7 Domestic measurement reporting and verification | - | 5,000 | 23,000 | 17,000 | - | 45,000 |
| Output 1.2.7.1 The roadmap for establishing a system of measures, reporting and verification (MRV) of GHG emissions identified as part of the preparation of the BUR1. | - | 5,000 | 23,000 | 17,000 | - | 45,000 |
| 1.2.7.1.1. Technical capacity building on MRV including supporting national teams working on MRV to participate in the relevant sub regional/regional/international workshops/ trainings on MRV as appropriate. | - | 1,000 | 3,000 | 2,000 | - | 6,000 |
| 1.2.7.1.2. Identify and assess different options and possibilities for establishment of a domestic MRV system | - | 1,000 | - | - | - | 1,000 |
| 1.2.7.1.3. Develop proposals for a roadmap with a view to create a national MRV system, taking into account existing sectoral and national conditions and needs to strengthen the capacity of relevant institutions. | - | 3,000 | 20,000 | 5,000 | - | 28,000 |
| 1.2.7.1.4. Organize consultations workshop with relevant stakeholders to discuss the proposed roadmap and strategic framework for establishing the MRV system. | - | - | - | 4,000 | - | 4,000 |
| 1.2.7.1.5. Finalize the roadmap for the development of the MRV taking into account the comments and conduct internal and external review of the document. | - | - | - | 5,000 | - | 5,000 |
| 1.2.7.1.6. Compile the BUR1 Chapter on “Domestic MRV” | - | - | - | 1,000 | - | 1,000 |
| 1.2.8 Constraints and gaps, and related financial technical and capacity needs | - | - | 5,000 | 6,000 | 3,000 | 14,000 |
| Output 1.2.8.1. The analysis of the limitations and gaps associated with financial, technical activities and capacity building carried out. | - | - | 5,000 | 6,000 | 3,000 | 14,000 |
| 1.2.8.1.1 Analysis of information on difficulties, gaps, financial needs, technologies and capacity-building needs in the preparation of NC and BUR1. | - | - | 2,500 | 2,500 | 1,000 | 6,000 |
| 1.2.8.1.2 Analysis of the support received for the transfer and implementation of new technologies, assessment of gaps and needs. | - | - | 2,500 | 2,500 | 1,000 | 6,000 |
| 1.2.8.1.3 Preparation of the section “Limitations and Gaps; associated financial, technical and capacity-building needs” for inclusion in the BUR1 and NC4. | - | - | - | 1,000 | 1,000 | 2,000 |
| 2. TECHNICAL ASSISTANCE | - | - | 9,000 | 9,000 | 2,000 | 20,000 |
| Output 2.1: Technical assistance provided | - | - | 9,000 | 9,000 | 2,000 | 20,000 |
| 2.1.1 Regional and international consultants will be invited as necessary to provide training or technical assistance to the Vulnerability and Adaptation Assessment Team, GHG inventory team and Mitigation Assessment team in the specific approaches, tools and methods that are used for the Adaptation and Vulnerability Assessment, mitigation assessment and GHG inventory. | - | - | 9,000 | 9,000 | 2,000 | 20,000 |
| 3. COMPILATION AND PRODUCTION OF NATIONAL COMMUNICATIONS AND BIENNIAL UPDATE REPORT | - | - | - | 13,500 | 16,500 | 30,000 |
| Output 3.1: The Fourth National Communication and BUR1 prepared and submitted to the UNFCCC. | - | - | - | 13,500 | 16,500 | 30,000 |
| 3.1.1 Compile the draft BUR1 and NC4 for review and comments | - | - | - | 2,500 | 2,500 | 5,000 |
| 3.1.2 Incorporate the review comments and finalize the BUR1 and NC4 and submit for approval by the PSB. | - | - | - | 500 | 500 | 1,000 |
| 3.1.3 Translation of the BUR1 and NC4 from Russian into English. | - | - | - | 1,500 | 1,500 | 3,000 |
| 3.1.4 Publication and preparation of electronic copies of the BUR1 and NC4 on a CD-ROM and submission of reports to UNFCCC | - | - | - | 9,000 | 9,000 | 18,000 |
| 3.1.5 Organize a final national conference on the NC4/ BUR1 project in Turkmenistan. | - | - | - | - | 3,000 | 3,000 |
| 4. STOCKTAKING ASSESSMENT AND INSTITUTIONAL ARRANGEMENTS FOR PREPARATION OF SUBSEQUENT NCS AND BURS | - | - | - | - | 10,000 | 10,000 |
| Output 4.1. A review analysis carried out, institutional mechanisms for the preparation of subsequent NCs and BURs considered. | - | - | - | - | 10,000 | 10,000 |
| 4.1.1. To conduct a self-assessment and review analysis and prepare a summary of activities and outcomes achieved after completion and submission of the NC4 and BUR1 to the UNFCCC. | - | - | - | - | 4,000 | 4,000 |
| 4.1.2. To prepare a strategy to involve all relevant stakeholders, including their potential role in the preparation of the NC and BUR/BTR, and identify key coordinators in the working groups to monitor problems related to funding, constraints and gaps, technical and capacity building needs. | - | - | - | - | 4,000 | 4,000 |
| 4.1.3. To propose measures to strengthen and maintain the existing institutional mechanism, including possible technical assistance, as well as strategies to increase synergies with relevant programs and institutions. | - | - | - | - | 2,000 | 2,000 |
| 5. PROJECT MANAGEMENT | - | 18,388 | 27,736 | 38,061 | 35,815 | 120,000 |
| Output 5.1: The NC4 and BUR1 project management mechanism established and operationalized. | - | 18,388 | 27,736 | 38,061 | 35,815 | 120,000 |
| 5.1.1 Engage/assign a project manager | - | 695 | 2,085 | 2,085 | 1,390 | 6,255 |
| 5.1.2 Engage/assign a project implementation unit assistant | - | 696 | 2,088 | 2,088 | 1,392 | 6,265 |
| 5.1.3 Cover UNDP support costs, determined in accordance with its cost recovery policy (the clause C, UN2UN UNEP/UNDP Agreement) | - | 4,091 | 5,454 | 5,454 | 5,000 | 20,000 |
| 5.1.4 Cover UNDP GMS (8% of the total net costs) | - | 12,606 | 16,808 | 16,808 | 15,408 | 61,630 |
| 5.1.5 Cover travel expenses (international) to present NC4/BUR1 at the COP | - | - | - | 10,325 | 10,325 | 20,650 |
| 5.1.6 Cover travel expenses (local business trip) | - | - | - | - | - | - |
| 5.1.7 Cover Bank commission charges. | - | 300 | 300 | 300 | 300 | 1,200 |
| 5.1.8. Annual financial audits | - | - | 1,000 | 1,000 | 2,000 | 4,000 |
| 6. MONITORING AND REPORTING (UNEP) | - | - | - | - | 20,000 | 20,000 |
| Output 6.1. Monitoring and evaluation of the project carried out. | - | - | - | - | 20,000 | 20,000 |
| 6.1.1 Undertake Project monitoring and evaluation (UNEP) | - | - | - | - | 20,000 | 20,000 |
| TOTAL: | 20,000 | 87,038 | 289,286 | 298,911 | 156,765 | 852,000 |

TABLE 3 TIMELINE FOR THE IMPLEMENTATION OF PROJECT ACTIVITIES

| NC4 BUR1 Activities per Component | 2020 |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec |
| 1.2.1. National circumstances and institutional arrangements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.1.1: National circumstances, priorities and tasks underlying the solution of problems of climate change analyzed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1.1.1 Formation of a group of experts. | Х |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1.1.2 Organize a project inception workshop to Launch NC4 and BUR1 project in Turkmenistan | Х |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1.1.3 Review and analysis of changes in the political and economic development of the country in recent years and update relevant information on geography, population, natural resources and economy; and development policies, etc. relevant to climate change for inclusion in the NC4 and BUR4. |  | Х | Х |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1.1.4 Preparation of the section "National Circumstances" for the NC4 and BUR1. |  |  | Х | Х | Х | Х |  |  |  |  |  |  |  |  |
| Output 1.2.1.2: Institutional arrangement relevant to the preparation of national communications on an ongoing basis described. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1.2.1 Collection and analysis of updated information. |  | Х | Х |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1.2.2 Description of existing institutional mechanisms relevant to the preparation of the NC of Turkmenistan on an ongoing basis. |  | Х | Х |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1.2.3 Preparation of the section on institutional arrangements for inclusion in the NC4 and BUR1. |  |  |  | Х |  |  |  |  |  |  |  |  |  |  |
| 1.2.2. National GHG Inventories |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.2.1: GHG inventory and data collection analysis team organized and strengthened. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2.1.1 To identify and mobilize national experts in target sectors and areas relevant to the preparation of the GHG inventory. |  | Х |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2.1.2 To review existing information and data on previous GHG inventories already archived and documented. |  | Х |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2.1.3 To identify the specific needs of enterprises in staff training for data collection (with the emphasis on key source sectors, which are the main sources of emissions). |  | Х | Х | Х | Х |  |  |  |  |  |  |  |  |  |
| 1.2.2.1.4 To develop a national capacity building plan to enable the country to apply the 2006 IPCC Guidelines. |  | Х | Х | Х | Х |  |  |  |  |  |  |  |  |  |
| 1.2.2.1.5 Conduct training for national experts/teams working on GHG inventory including supporting them to participate in relevant regional/international trainings on GHG inventory. |  | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.2.1.6 To review and update the quality assessment and quality control plan (QA/QC). |  | Х | Х | Х | Х | Х |  |  |  |  |  |  |  |  |
| 1.2.2.1.7. To conduct a needs assessment and prepare terms of reference for the creation of a national inventory system with certain institutional mechanisms and a strategy for establishing the system. |  |  |  | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.2.1.8. To improve intersectoral collaboration between relevant institutions for the preparation of GHG inventories. |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| Output 1.2.2.2. Data for the GHG inventory and methodology collected, validated and improved. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2.2.1. To identify new sources of activity data for key source categories and priority sectors not included or explored in other programs. |  | Х | Х | Х | Х | X |  |  |  |  |  |  |  |  |
| 1.2.2.2.2. To identify new activity data needed to estimate GHG emissions, including, where applicable, recommendations from the UNFCCC In-depth Review Team. |  | Х | Х | Х | Х | X |  |  |  |  |  |  |  |  |
| 1.2.2.2.3. To use the IPCC best practice methodologies to fill data gaps. |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.2.2.4 To identify data sources for source categories (international bunkers, solvents, industrial processes) not covered by the Third National Communication (TNC). |  | Х | Х | X | X | X |  |  |  |  |  |  |  |  |
| 1.2.2.2.5. Identify areas where data may be further improved in future communications through capacity-building where necessary. |  |  |  |  |  |  | X | X | X | X |  |  |  |  |
| Output 1.2.2.3 National inventory of anthropogenic GHGs by sources and removals by sinks for 1994-2020 conducted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2.3.1 To estimate emissions for new gases (HFCs, PFCs, SF6). |  |  | X | Х | Х | Х | Х | Х | Х | X |  |  |  |  |
| 1.2.2.3.2 To assess the applicability of the 2006 IPCC emission factors. | X | Х |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2.3.3. To develop, as appropriate, the national emission factors for key source categories, such as energy (mainly focusing on subsectors - fugitive emissions and fuel combustion), industry (mainly focusing on cement and lime production subsectors) and LULUCF (mainly focusing on forest, pasture and arable land). |  |  | X | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.2.3.4. To recalculate the GHG inventory for 1994-2010 (prepared under the TNC). |  |  | X | Х | Х | Х | Х | Х | X | X |  |  |  |  |
| 1.2.2.3.5. To conduct analysis and inventory of key sources (for 2018) and sensitivity analysis in accordance with the IPCC guidelines. |  |  | X | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.2.3.6. To calculate the GHG inventory for all sectors and gases in accordance with the 2006 IPCC Guidelines for the years 2011-2020 for the NC4. The BUR1 will cover the period up to year 2018 and this will be extended to year 2020 under NC4 |  |  | X | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.2.3.7. To organize a national seminar to present the results of the GHG inventory and to receive additional comments in accordance with the timing of data submission for the NC4 and BUR1. |  |  |  |  |  |  |  |  |  | Х |  |  |  |  |
| 1.2.2.3.8. To introduce an uncertainty analysis for all sectors considered under the GHG inventory and provide information on the level of uncertainty associated with inventory data and their underlying assumptions, and describe the methodologies used, if any, for estimating the uncertainties. |  |  |  | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.2.3.9. To implement QA/QC procedures for key sectors / source categories. |  |  | X | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.2.3.10. Provide information on methodologies used in the estimation of anthropogenic emissions by sources and removals by sinks of GHGs not controlled by the Montreal Protocol, including a brief explanation of the sources of Emission factors and Activity data. |  |  |  |  |  |  |  |  |  | X | X |  |  |  |
| Output 1.2.2.4. GHG inventory completed and archived. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2.4.1. To prepare a National GHG Inventory Report for 1994-2018 (for the BUR1), 1994-2020 (for the NC4). |  |  |  |  |  |  | X | X | X | Х | Х | X |  |  |
| 1.2.2.4.2. To prepare proposals for the establishment of the National Inventory System by 2023. |  |  |  |  |  |  |  |  | X | Х | Х | X |  |  |
| 1.2.2.4.3. To conduct a workshop with decision makers from data source institutions to present the final results of the inventory process. |  |  |  |  |  |  |  |  |  |  | Х |  |  |  |
| 1.2.2.4.4. To prepare and make archiving of the GHG inventory and describe the procedures and arrangements undertaken to collect and archive data for the preparation of national GHG inventories, as well as efforts to make this a continuous process, including information on the role of the institutions involved. |  |  |  |  |  |  | Х | Х | Х | Х | Х | X |  |  |
| 1.2.3. General Description of steps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1 Measures to facilitate adequate adaptation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.3.1.1: National Group on Measures Promoting Adequate Adaptation developed and strengthened. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.1.1. Establishment of the National Group for Measures Promoting Adequate Adaptation and appointment of a Team Leader. | Х |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.1.2. Inclusion of leading experts from ministries and departments related to climate change issues in the National Group on Measures Promoting Adequate Adaptation. |  | Х | Х |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.1.3. Assessment of risks associated with climate change. |  | X | Х | Х | Х | Х | Х | Х |  |  |  |  |  |  |
| 1.2.3.1.1.4. Development of the list of specific adaptation measures with aggregative assessment of costs and benefits of their implementation. |  | X | Х | Х | Х | Х | Х | Х | Х | Х | X |  |  |  |
| 1.2.3.1.1.5. Organization of the first national seminar on measures to promote adequate adaptation in the initial period of the Fourth National Communication with the purpose to consult with relevant stakeholders and identify approaches, tools and methods that will be used during vulnerability and adaptation assessment. |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.1.6. Technical capacity-building of national teams/experts working on vulnerability and adaptation assessments, including supporting their participation in relevant sub regional/regional/international workshops on Vulnerability Assessment and Adaptation as appropriate |  | X | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| Output 1.2.3.1.2 Approaches, tools and methods to be used during vulnerability assessment and adaptation approved. . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.2.1. Identification of necessary data and information, and selection and description of approaches, tools and methods to be used for evaluation of impacts of and vulnerability and adaptation to climate change. |  | Х | Х | Х | Х | X |  |  |  |  |  |  |  |  |
| 1.2.3.1.2.2. Development and use of methods for calculating costs and benefits in the implementation of specific adaptation measures. |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.2.3. Review of the policy and development process in the context of the chosen field in order to explore how adaptation measures can be implemented in the decision-making agenda and the best mechanisms for their implementation. |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.2.4. Determination of a set of measures to eliminate the water shortage associated with climate change (reducing river flows and changing their hydrograph, increasing irrigation norms with increasing temperature and evapotranspiration growth, expanding evaporation from the water surface). |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.2.5. Support the implementation of the Central Asian Land Management Initiative (CACILM). |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.2.6. Assistance in strengthening the activity of the State Commission for Ensuring Fulfillment of the Obligations of Turkmenistan arising from the UN conventions and programs on the environment. |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| Output 1.2.3.1.3: Vulnerability and Adaptation Assessment Implemented. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.3.1. Identification and description of the scope of vulnerability and adaptation assessment of Turkmenistan and description of vulnerable areas, and the development of reliable indicators (climate and multilateral impact, socio-economic development, etc.). It is supposed to include “prevented damage” as one of the indicators. In various sectors of the economy, this indicator should be calculated independently by the industry experts: | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.3.2. Under the socio-economic indicator for the rural population, calculate the increase in the standard of living of the population, expressed as an increase in income from agricultural production, subject to the implementation of adaptation measures in the water and agricultural sectors. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.3.3. Compile relevant information on implementation of sectoral and/or integrated analysis of Turkmenistan's vulnerability to climate change for all relevant sectors of the economy. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.3.4. For each sector of the economy, performance of vulnerability assessment and identification of risks - material and social - in case of failure to implement possible adaptation measures (reducing crop yields and animal productivity, loss of biodiversity, etc.) will be undertaken. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| Output 1.2.3.1.4: Basic scenarios developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.4.1. Development of climate scenarios using modern models. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.4.2. Development of economic scenarios together with the Ministry of Finance and Economics of Turkmenistan. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.4.3. Determination of the cost of implementing these measures and the timing of their implementation in accordance with the considered scenarios of the country's economic development for the future. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.4.4. Development of recommendations for the implementation of early warning system for the likelihood of drought, floods, and mudflows. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| Output 1.2.3.1.5: Adaptation measures assessed and described. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.5.1. Assessment of current climate change adaptation strategies and measures in key areas; future climate risk assessed. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.5.2. For the specific adaptation measures, describe ways of their implementation, i.e. mechanism for the implementation of these activities, sources of funding, monitoring and timing of their implementation. |  |  |  |  |  |  | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.5.3. Develop new adaptation responses and predict potential impacts and develop multi-level adaptation scenarios. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.5.4. Assist in the development of National Action Plans for Adaptation to Climate Change in key ministries and departments. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.3.1.5.5. Include in the industry specific NAPAs a list of concrete adaptation measures in the context of the sectors of the economy of Turkmenistan, the timing of their implementation (if necessary, stages), assessment of the costs of their implementation, responsible executives, sources of funding. |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.3.1.5.6. Define and establish a policy framework for the implementation of the National Climate Change Adaptation Action Plan (NCCAAP) in Turkmenistan. |  |  | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.3.1.5.7. Carrying out technical review of the NCCAAP executed by ministries and departments. |  |  | X | X | X | X | Х | Х | Х | Х | Х |  |  |  |
| Output 1.2.3.1.6: Chapter 3: "Measures to Promote Adequate Adaptation" of the NC4 developed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.1.6.1. Development of the draft Chapter 3: "Measures to promote adequate adaptation" of the Fourth National Communication. |  |  |  |  |  |  |  |  |  | Х | Х |  |  |  |
| 1.2.3.1.6.2. Dissemination of the draft chapter for internal and external review, receipt and inclusion of comments, completion of Chapter 3: "Measures to promote adequate adaptation", as part of the Fourth National Communication. |  |  |  |  |  |  |  |  |  | Х | Х |  |  |  |
| 1.2.3.1.6.3. Inclusion of comments and observations received after the reviews and finalization of Chapter 3: "Measures to promote adequate adaptation" of the NC4. |  |  |  |  |  |  |  |  |  | Х | Х |  |  |  |
| 1.2.3.1.6.4. Organize two national workshops on Vulnerability and Adaptation to review and approve activities that promote adequate adaptation |  |  |  |  |  |  |  |  |  |  | Х |  |  |  |
| 1.2.3.1.6.5. Archiving and documenting all studies and assessments of vulnerability and adaptation. |  |  |  |  |  |  |  |  |  | X | Х |  |  |  |
| 1.2.3.1.6.6. Creation of database of materials and documents related to climate change issues. |  |  |  |  |  |  |  |  |  | X | Х |  |  |  |
| 1.2.3.1.6.7. Creation of database of experts and specialists who are directly involved in resolving issues related to climate change. |  |  |  |  |  |  |  |  |  |  | Х |  |  |  |
| 1.2.3.2. Programs to mitigate climate change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.3.2.1. The necessary data and relevant information for the development of the scenario collected, analyzed and used to develop the scenario. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3.2.1.1. Technical capacity building of national teams/experts working mitigation measures including supporting their participation in relevant regional/international workshops/trainings on mitigation assessment as appropriate |  | X | X | X | X | X | X | X | X | X | X |  |  |  |
| 1.2.3.2.1.2. Identify and mobilize national experts in target sectors and areas relevant to the preparation of the PaMs. |  |  |  | Х | Х | Х |  |  |  |  |  |  |  |  |
| 1.2.3.2.1.3. Conduct an analysis of the assessment of the inventory for 2011-2020 and fulfill the forecast for GHG emissions by 2030. |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.3.2.1.4. Conduct a comparative analysis of the data/estimates obtained in the framework of the GHG inventory for the TNC, with the data projected for the same year within the framework of the NC4. |  |  |  | Х | Х | Х | Х | Х | X | X |  |  |  |  |
| 1.2.3.2.1.5. Collect all relevant macroeconomic data and establish the assumptions, that will be made to develop the emission scenario (based on new data related to the energy balance and recent sectoral economic plans for energy, transport, industry, waste, utilities and agriculture). |  |  |  |  |  |  | X | Х | Х | Х |  |  |  |  |
| 1.2.3.2.1.6. To identify any differences / changes in the scenario “business-as-usual scenario” developed in the framework of the TNC. |  |  |  |  |  |  |  | Х | Х | Х | Х |  |  |  |
| 1.2.3.2.1.7. To identify acceptable models and available software for the development of scenarios (e.g. LEAP, IPCC). |  |  |  |  |  |  | X | X | X | X | Х |  |  |  |
| 1.2.3.2.1.8. To process the collected data for GHG emission scenarios (basic and stabilization) using the selected model and software (for example, LEAP, IPCC). |  |  |  |  |  |  | X | X | X | X | X |  |  |  |
| 1.2.3.2.1.9. To make cross-check of the results of the scenario to ensure consistency in sectors and timelines with the inventory data from section 1.2.2 (inventory) and section 1.2.3.2 (mitigation), as well as data on policies and measures (PaMs) from section 1.2.4. |  |  |  |  |  |  |  |  | X | X | X |  |  |  |
| 1.2.3.2.1.10. Based on the above, prepare the NC4 section/chapter on “measures to mitigate climate change” to include to the extent possible all the relevant information on programmes and measures implemented, or measures being considered by the government of Turkmenistan for future implementation which contribute to mitigating climate change, including, as appropriate, relevant information by key sectors on methodologies, scenarios, results, measures and institutional arrangements |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| 1.2.4. Mitigation actions and their effects, including associated methodologies and assumptions (BUR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.4.1 Climate change mitigation policies and measures (PaMs) updated, strengthened and included in the development of scenarios and reporting in the BUR1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4.1.1 To assess the status of PaMs reported in the TNC and add any new appropriate PaMs. |  |  |  | Х | Х | Х |  |  |  |  |  |  |  |  |
| 1.2.4.1.2 To conduct review of the status of relevant policies and regulatory frameworks and update macroeconomic forecasts and plans presented in the TNC. |  |  |  | Х | Х | Х | Х |  |  |  |  |  |  |  |
| 1.2.4.1.3 To conduct review and analysis of the relationship of existing international initiatives and projects in Turkmenistan with the preparation of a PaMs for the BUR1. |  |  |  | Х | Х | Х | Х | X | X | X |  |  |  |  |
| 1.2.4.1.4. To prepare a roadmap and a set of recommendations to achieve the INDC goal presented by the UNFCCC by the Government of Turkmenistan, as well as ways to reduce GHG emissions in general. |  |  |  |  | Х | Х | Х | X | X | X |  |  |  |  |
| 1.2.4.1.5 To review and make recommendations with a view to attracting international funds and financial mechanisms to assist in mobilizing international assistance and investments aimed at developing and implementing GHG reduction projects. |  |  |  |  | Х | Х | Х | X | X | X |  |  |  |  |
| Output 1.2.4.2: PaMs analysis performed for the period up to 2020 and the subsequent possible period, including new data and new assumptions relating to the period after the TNC. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4.2.1. For each mitigation action or groups of mitigation actions, compile as appropriate, the following information to the extent possible for inclusion in the BUR1: (a) Name and description of the mitigation action, including information on the nature of the action, coverage (i.e. sectors and gases), quantitative goals and progress indicators; (b) Information on: (i) Methodologies (ii) Assumptions (c) Information on: (i) Objectives of the action, (ii) Steps taken or envisaged to achieve that action and (d) Information on the progress of implementation of the mitigation actions and the underlying steps taken or envisaged, and the results achieved. |  |  | X | X | X | X | X | X | X | X |  |  |  |  |
| 1.2.4.2.2. Compile and report in the BUR1 information on Turkmenistan’s participation in International market mechanisms as applicable. |  |  | X | X | X | X | X | X | X | X |  |  |  |  |
| 1.2.4.2.3. To develop a draft chapter on “Mitigation actions and their effects, including associated methodologies and assumptions”, which includes a brief comparison of PaMs and the final subsection, which defines the priorities for actions. |  |  | X | X | X | X | X | X | X | X |  |  |  |  |
| 1.2.4.2.4. To disseminate the draft chapter on “Mitigation actions and their effects, including associated methodologies and assumptions” for internal review and comments. |  |  |  |  |  |  | X | X | X | X |  |  |  |  |
| 1.2.4.2.5. To disseminate the draft “Mitigation actions and their effects, including associated methodologies and assumptions” chapter for external peer review and comments. |  |  |  |  |  |  | X | X | X | X |  |  |  |  |
| 1.2.4.2.6. To receive comments and include them in the document. |  |  |  |  |  |  | Х | X | X | X |  |  |  |  |
| 1.2.4.2.7. To organize a national workshop to highlight the results of the PaMs modeling and analysis and get more comments. |  |  |  |  |  |  | Х | X | X | X |  |  |  |  |
| 1.2.4.2.8. To finalize the “Mitigation actions and their effects, including associated methodologies and assumptions” chapter, which will be presented within the BUR1 of Turkmenistan. |  |  |  |  |  |  | Х | X | X | X |  |  |  |  |
| 1.2.4.2.9. To archive and document all studies, model runs, assumptions, and estimates for the “Mitigation actions and their effects, including associated methodologies and assumptions” chapter. |  |  |  |  |  |  | Х | Х | X | X |  |  |  |  |
| 1.2.5. Other information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.1 Integrating climate change considerations into social, economic and environmental policies and actions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.5.1.1: A “Group on Other Issues” Established. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.1.1.1: To establish a “Group on Other Issues”. |  |  | X | Х | X | X |  |  |  |  |  |  |  |  |
| Output 1.2.5.1.2: Sustainable development issues and integration of climate change priorities reflected. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.1.2.1 Gathering, synthesizing and providing complete updated information related to the integration of climate change issues into sustainable development programs, including the results obtained in the TNC. Preparation of a draft report that reflects national efforts to integrate climate change issues into sustainable development programs for review and comments. |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.1.2.2 Review of the draft on the main comments received and finalize it as part of the NC4 “Section: Integrating Climate Change issues into Sustainable Development Programs”. |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| 1.2.5.2 Development and transfer of environmentally sound technologies (ESTs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.5.2.1: Opportunities for the "Transfer of environmentally sound technologies" are granted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.2.1.1 Collection, synthesis and provision of information on how Turkmenistan executes transfer, access to environmentally friendly technologies and knowhow. |  |  |  |  | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.2.1.2 Revision of criteria for assessing and prioritizing technological needs, including environmentally friendly technologies (ESTs), cost-effectiveness, and opportunities for their implementation according to the national criteria for sustainable development. |  |  |  |  | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.2.1.3 Assessment of the need to review and revise existing legal and economic instruments / mechanisms to facilitate the transfer of ESTs. |  |  |  |  | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.2.1.4 Creation of a database for ESTs, including climate change mitigation and adaptation technologies, using the EST-Information System (ESTIS) developed by the UNEP International Center for Environmental Technology (IETC). |  |  |  |  | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.2.1.5 Summarizing all the information collected in the working version (draft) "Sub-head: Actions related to the Transfer of Technologies". |  |  |  |  |  |  |  |  |  | X | Х | Х |  |  |
| 1.2.5.2.1.6 Inclusion of received comments, if any, in the working version of the "Section: Actions related to the Transfer of Technologies" and its completion as part of the "Chapter: Other information considered suitable for achieving the goals of the UNFCCC". |  |  |  |  |  |  |  |  |  | Х | Х | Х |  |  |
| 1.2.5.3 Climate change research and systematic observation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.5.3.1: Information on "Climate Change Research and Systematic Observations" prepared and compiled. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.3.1.1 Collection, compilation and provision of information on research and systematic observation systems. |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.3.1.2 Assessment of the general policy and funding of research and systematic observations in the country. |  |  |  |  |  |  | Х | Х | Х | Х | Х | Х |  |  |
| 1.2.5.3.1.3 Assessment of efforts undertaken by the Government and formulation of recommendations to institutions regarding the climate process and climate system research. This includes paleoclimatic studies; modeling and forecasting using common circulation models; studies on the effects of climate change; socio-economic analysis, including analysis of the impacts of climate change options and responses; climate change mitigation research, and climate change adaptation technologies. |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.3.1.4 Assessment of information on the status of government plans, programs and support to the climate monitoring system. |  |  |  |  |  |  |  | Х | Х | Х | Х | Х |  |  |
| 1.2.5.3.1.5 Summarizing all the information collected in the working version (draft/project) of the "Section: Research and Systematic Observations of Climate Change". |  |  |  |  |  |  |  |  | Х | Х | Х | Х |  |  |
| 1.2.5.3.1.6 Inclusion of comments received, if any, in the draft of the "Section: Research and Systematic Observations of Climate Change" and its completion as part of "Chapter 5: Other information suitable for achieving the goals of the UNFCCC". |  |  |  |  |  |  |  |  |  |  | X | Х |  |  |
| 1.2.5.4 Education training and public awareness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.5.4.1: An awareness-raising campaign developed and information on "Education, Training and Public Awareness" prepared. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.4.1.1 Assessment of the overall level of awareness and understanding of climate change issues and climate change education policies, seminars and public awareness. |  |  |  |  |  |  | X | Х | Х | Х | Х | Х |  |  |
| 1.2.5.4.1.2 Assessment of the National Curriculum and the efforts undertaken by the Government (for example, by the Ministry of Education) with advices for primary, secondary and higher education on climate change. |  |  |  |  |  |  | X | Х | Х | Х | Х | Х |  |  |
| 1.2.5.4.1.3 Assessment of available information regarding implemented or planned public information initiatives, campaigns and programs. |  |  |  |  |  |  | X | Х | Х | Х | Х | Х |  |  |
| 1.2.5.4.1.4 Assessment of available information regarding international cooperation aimed at developing education and public awareness. |  |  |  |  |  |  | X | Х | Х | Х | Х | Х |  |  |
| 1.2.5.4.1.5 Assessment of gaps, needs and priorities for climate change education and public awareness. |  |  |  |  |  |  | X | Х | Х | Х | Х | Х |  |  |
| 1.2.5.4.1.6 Implementation of awareness-raising campaign for a specific audience (politicians, environmental planners, private sector, the public, schoolchildren and students), including the preparation of visual materials on climate change and sustainable development and dissemination through the media (television, radio and newspapers). |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.5.4.1.7 Ensuring public access to information on climate change and sustainable development through the updated website of the climate change project in Russian and English related to climate change activities in Turkmenistan. |  | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.5.4.1.8 Collection, compilation and provision of complete information related to "Education, Training and Public Awareness" applicable to activities under Article 6 of the UNFCCC. |  |  |  |  |  |  |  |  | X | Х | Х |  |  |  |
| 1.2.5.4.1.9 Organize two national seminars to raise awareness of national policy makers, especially those involved in national environmental planning processes, public health workers and the interested members of the public about the effects of climate change |  | X |  |  |  |  |  | X |  |  |  |  |  |  |
| 1.2.5.4.1.10 Summarizing all the information collected in the draft of the “Section 5.4: Education, Training and Public Awareness”; inclusion of the comments received and its completion as part of the “Chapter 5: Other information considered appropriate to achieve the objectives of the UNFCCC”. |  |  |  |  |  |  |  |  |  | Х | Х |  |  |  |
| 1.2.5.5 Capacity building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.5.5.1: Information on “Capacity Building” prepared and compiled. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.5.1.1 Gathering, compiling and providing complete information on “Capacity Building”. Summarizing all the information collected in the project (working version) "Section 5.5: Capacity Building"; and its distribution for internal review and comments. |  |  |  |  |  |  |  |  | X | Х | Х |  |  |  |
| 1.2.5.5.1.2 Inclusion of comments, if any, in the draft of the "Section 5.5: Capacity Building" and its completion as part of the "Chapter 5: Other information relevant to achieve the goals of the UNFCCC". |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| 1.2.5.6 Information and networking |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.5.6.1: Information regarding "Information and Networking" prepared and compiled. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.6.1.1 Collection, compilation and provision of complete information regarding "Information and Networking". Summarizing all the information collected in the "Section 5.6: Information and Networking" draft and including the comments received, if any, in the "Section 5.6: Information and Networking" draft and completing it as part of "Chapter 5: Other relevant information to achieve the goals of the UNFCCC". |  |  |  |  |  |  |  |  | X | Х | Х |  |  |  |
| 1.2.5.7 Gender and Climate Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.5.7.1 The role of women in the implementation of adaptation and mitigation measures, the development of policies and knowledge assessed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.5.7.1.1 Analysis of government programs that take into account gender relations and needs of both men and women; |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.7.1.2 Review of activities aimed at raising the awareness of decision-makers about gender issues and problematic; |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.7.1.3 Analysis of vulnerability to climate change, taking into account gender characteristics and the specifics of local communities; |  |  |  |  |  |  | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.7.1.4 Analysis of measures and actions to raise awareness and familiarize women with the possibilities of using environmentally friendly technologies, RE, about available methods of adaptation to climate change in order to attract interested women; |  |  |  |  |  |  | Х | Х | Х | Х |  |  |  |  |
| 1.2.5.7.1.5 Assessment of assistance to women in implementing entrepreneurial initiatives aimed at earning income using climate-resilient technologies and practices. |  |  |  | Х | Х | Х | Х | Х | Х | Х |  |  |  |  |
| 1.2.6. Support received for preparation and submission of biennial update report (BUR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.6.1. Analysis of information on the level of support received to ensure the preparation of the first biennial update report. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.6.1.1. Assessment of financial resources, technology transfer, capacity building and technical assistance received from the GEF, GCF, Parties included in Annexes I and II, international organizations (UNFCCC), South-South cooperation within the framework of preparation of the BUR1. |  | Х | Х | Х | Х | Х | Х | X |  |  |  |  |  |  |
| 1.2.6.1.2. Preparation of the BUR1 section “Information on the level of support received to ensure the preparation of the first report on updated data”. |  |  |  |  | Х | Х | Х | X |  |  |  |  |  |  |
| 1.2.7 Domestic measurement reporting and verification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.7.1 The roadmap for establishing a system of measures, reporting and verification (MRV) of GHG emissions identified as part of the preparation of the BUR1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.7.1.1. Technical capacity building on MRV including supporting national teams working on MRV to participate in the relevant sub regional/regional/international workshops/ trainings on MRV as appropriate. |  | X | X | X | X | X | X | X |  |  |  |  |  |  |
| 1.2.7.1.2. Identify and assess different options and possibilities for establishment of a domestic MRV system |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.7.1.3. Develop proposals for a roadmap with a view to create a national MRV system, taking into account existing sectoral and national conditions and needs to strengthen the capacity of relevant institutions. |  | Х | Х | Х | Х |  | X | X | X | X |  |  |  |  |
| 1.2.7.1.4. Organize consultations workshop with relevant stakeholders to discuss the proposed roadmap and strategic framework for establishing the MRV system. |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| 1.2.7.1.5. Finalize the roadmap for the development of the MRV taking into account the comments and conduct internal and external review of the document. |  |  |  |  |  |  | Х | X |  |  |  |  |  |  |
| 1.2.7.1.6. Compile the BUR1 Chapter on “Domestic MRV” |  |  |  |  |  |  | Х | X |  |  |  |  |  |  |
| 1.2.8 Constraints and gaps, and related financial technical and capacity needs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.8.1. The analysis of the limitations and gaps associated with financial, technical activities and capacity building carried out. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.8.1.1 Analysis of information on difficulties, gaps, financial needs, technologies and capacity-building needs in the preparation of NC and BUR1. |  |  |  | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.8.1.2 Analysis of the support received for the transfer and implementation of new technologies, assessment of gaps and needs. |  |  |  | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 1.2.8.1.3 Preparation of the section “Limitations and Gaps; associated financial, technical and capacity-building needs” for inclusion in the BUR1 and NC4. |  |  |  |  |  |  |  |  |  | X | Х |  |  |  |
| 2. TECHNICAL ASSISTANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1: Technical assistance provided |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 Regional and international consultants will be invited as necessary to provide training or technical assistance to the Vulnerability and Adaptation Assessment Team, GHG inventory team and Mitigation Assessment team in the specific approaches, tools and methods that are used for the Adaptation and Vulnerability Assessment, mitigation assessment and GHG inventory. |  |  |  | Х | Х | Х | Х | Х | Х | Х | Х |  |  |  |
| 3. COMPILATION AND PRODUCTION OF NATIONAL COMMUNICATIONS AND BIENNIAL UPDATE REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1: The Fourth National Communication and BUR1 prepared and submitted to the UNFCCC. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 Compile the draft BUR1 and NC4 for review and comments |  |  |  |  |  | X | X | X |  | X | Х | Х |  |  |
| 3.1.2 Incorporate the review comments and finalize the BUR1 and NC4 and submit for approval by the PSB. |  |  |  |  |  |  | X | X | X | X | X | X |  |  |
| 3.1.3 Translation of the BUR1 and NC4 from Russian into English. |  |  |  |  |  |  | X | X | X | X | X |  |  |  |
| 3.1.4 Publication and preparation of electronic copies of the BUR1 and NC4 on a CD-ROM and submission of reports to UNFCCC |  |  |  |  |  |  | Х | Х | X | X | X | Х |  |  |
| 3.1.5 Organize a final national conference on the NC4/ BUR1 project in Turkmenistan. |  |  |  |  |  |  |  |  |  |  | X | X |  |  |
| 4. STOCKTAKING ASSESSMENT AND INSTITUTIONAL ARRANGEMENTS FOR PREPARATION OF SUBSEQUENT NCS AND BURS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.1. A review analysis carried out, institutional mechanisms for the preparation of subsequent NCs and BURs considered. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1. To conduct a self-assessment and review analysis and prepare a summary of activities and outcomes achieved after completion and submission of the NC4 and BUR1 to the UNFCCC. |  |  |  |  |  |  |  |  |  |  |  |  | Х | Х |
| 4.1.2. To prepare a strategy to involve all relevant stakeholders, including their potential role in the preparation of the NC and BUR/BTR, and identify key coordinators in the working groups to monitor problems related to funding, constraints and gaps, technical and capacity building needs. |  |  |  |  |  |  |  |  |  |  |  |  | Х | Х |
| 4.1.3. To propose measures to strengthen and maintain the existing institutional mechanism, including possible technical assistance, as well as strategies to increase synergies with relevant programs and institutions. |  |  |  |  |  |  |  |  |  |  |  |  | Х | Х |
| 5. PROJECT MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.1: The NC4 and BUR1 project management mechanism established and operationalized. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.1 Engage/assign a project manager | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |
| 5.1.2 Engage/assign a project implementation unit assistant | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |
| 5.1.3 Cover UNDP support costs, determined in accordance with its cost recovery policy (the clause C, UN2UN UNEP/UNDP Agreement) | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |
| 5.1.4 Cover UNDP GMS (8% of the total net costs) | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |
| 5.1.5 Cover travel expenses (international) to present NC4/BUR1 at the COP |  |  |  |  |  |  |  |  | Х |  |  |  | Х |  |
| 5.1.6 Cover travel expenses (local business trip) | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |
| 5.1.7 Cover Bank commission charges. | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х | Х |  |
| 5.1.8. Annual financial audits |  |  |  |  | Х |  |  |  | Х |  |  |  |  | X |
| 6. MONITORING AND REPORTING (UNEP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 6.1. Monitoring and evaluation of the project carried out. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1.1 Undertake Project monitoring and evaluation (UNEP) |  |  |  |  |  |  |  |  |  |  |  |  |  | X |

APPENDIX 1 to Annex 1

UNEP BUDGET CODES

| Project title: Turkmenistan: Preparation of the Fourth National Communication and Initial Biennial Update Report under United Nations Framework Convention on Climate Change |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project executing partner: UNDP Turkmenistan |  |  |  |  |  |  |  |
| Project implementation period: 40 Months |  |  |  |  |  |  |  |
| From: | Sep-20 |  |  |  |  |  |  |
| To: | Dec-23 |  |  |  |  |  |  |
| UNEP Budget Line |  | Expenditure 2020 | Budget 2020 | Budget 2021 | Budget 2022 | Budget 2023 | Total |
|  | STOCKTAKING, NATIONAL STAKEHOLDER CONSULTATION & BUR1 NC4 PIP PREPARATION | 20,000 | - | - | - | - | 20,000 |
|  | Component Total | 20,000 | - | - | - | - | 20,000 |
| 10 | PERSONNEL COMPONENT |  |  |  |  |  |  |
| 1100 | Project personnel |  |  |  |  |  |  |
| 1101 | Project manager | - | 695 | 2,085 | 2,085 | 1,390 | 6,255 |
| 1102 | Project Implementation Unit Assistant | - | 696 | 2,088 | 2,088 | 1,392 | 6,265 |
| 1199 | Sub-total | - | 1,391 | 4,173 | 4,173 | 2,782 | 12,520 |
| 1200 | Consultants |  |  |  |  |  |  |
| 1201 | National circumstance and institutional arrangement: Activities: 1.2.1.1.1, 1.2.1.1.3,1.2.1.1.4, 1.2.1.2.1,1.2.1.2.2 & 1.2.1.2.3, | - | 7,000 | 12,000 | - | - | 19,000 |
| 1202 | National Greenhouse Gas Inventory Activities: 1.2.2.1.1,1.2.2.1.2,1.2.2.1.3,1.2.2.1.4,1.2.2.1.6,1.2.2.1.7,1.2.2.1.8,1.2.2.2.1,1.2.2.2.2,1.2.2.2.3,1.2.2.2.4,1.2.2.2.5,1.2.2.3.1,1.2.2.3.2,1.2.2.3.3,1.2.2.3.4,1.2.2.3.5,1.2.2.3.6,1.2.2.3.8,1.2.2.3.9,1.2.2.3.10,1.2.2.4.1,1.2.2.4.2 & 1.2.2.4.4 | - | 30,600 | 88,300 | 72,300 | 24,800 | 216,000 |
| 1203 | Vulnerability and Adaptation Assessment Activities: 1.2.3.1.1.1,1.2.3.1.1.2,1.2.3.1.1.3,1.2.3.1.1.4,1.2.3.1.2.1,1.2.3.1.2.2,1.2.3.1.2.3,1.2.3.1.2.4,1.2.3.1.2.5,1.2.3.1.2.6,1.2.3.1.3.1,1.2.3.1.3.2,1.2.3.1.3.3,1.2.3.1.3.4,1.2.3.1.4.1,1.2.3.1.4.2,1.2.3.1.4.3,1.2.3.1.4.4,1.2.3.1.5.1,1.2.3.1.5.2,1.2.3.1.5.3,1.2.3.1.5.4,1.2.3.1.5.5,1.2.3.1.5.6,1.2.3.1.5.7,1.2.3.1.6.1,1.2.3.1.6.2,1.2.3.1.6.3,1.2.3.1.6.5,1.2.3.1.6.6 & 1.2.3.1.6.7 | - | 12,950 | 27,800 | 27,800 | 14,450 | 83,000 |
| 1204 | Measures to Mitigate climate change Activities: 1.2.3.2.1.2,1.2.3.2.1.3,1.2.3.2.1.4,1.2.3.2.1.5,1.2.3.2.1.6,1.2.3.2.1.7,1.2.3.2.1.8,1.2.3.2.1.9 & 1.2.3.2.1.10 | - | - | 14,500 | 47,000 | 13,500 | 75,000 |
| 1205 | Mitigation actions and their effects Activities: 1.2.4.1.1,1.2.4.1.2,1.2.4.1.3,1.2.4.1.4,1.2.4.1.5,1.2.4.2.1,1.2.4.2.2,1.2.4.2.3,1.2.4.2.4,1.2.4.2.5,1.2.4.2.6,1.2.4.2.8 &1.2.4.2.9 | - | - | 63,500 | 31,500 | - | 95,000 |
| 1206 | Other information: Activities: 1.2.5.1.1.1,1.2.5.1.2.1,1.2.5.1.2.2,1.2.5.2.1.1,1.2.5.2.1.2,1.2.5.2.1.3,1.2.5.2.1.4,1.2.5.2.1.5,1.2.5.2.1.6,1.2.5.3.1.1,1.2.5.3.1.2,1.2.5.3.1.3,1.2.5.3.1.4,1.2.5.3.1.5,1.2.5.3.1.6,1.2.5.4.1.1,1.2.5.4.1.2,1.2.5.4.1.3,1.2.5.4.1.4,1.2.5.4.1.5,1.2.5.4.1.6,1.2.5.4.1.7,1.2.5.4.1.8,1.2.5.4.1.10,1.2.5.5.1.1,1.2.5.5.1.2,1.2.5.6.1.1,1.2.5.7.1.1,1.2.5.7.1.2,1.2.5.7.1.3,1.2.5.7.1.4 & 1.2.5.7.1.5 | - | 100 | 4,950 | 10,250 | 7,700 | 23,000 |
| 1207 | Support received for preparation and submission of the Biennial Update Report Activities: 1.2.6.1.1 & 1.2.6.1.2 | - | 500 | 3,000 | 1,500 | - | 5,000 |
| 1208 | Domestic measurement reporting and verification: Activities: 1.2.7.1.2,1.2.7.1.3,1.2.7.1.5 & 1.2.7.1.6 | - | 4,000 | 20,000 | 11,000 | - | 35,000 |
| 1209 | Constraints and Gaps, and related financial, technical and capacity need Activities: 1.2.8.1.1,1.2.8.1.2 & 1.2.8.1.3 | - | - | 5,000 | 6,000 | 3,000 | 14,000 |
| 1210 | Technical Assistance: Activities:2.1.1 | - | - | 9,000 | 9,000 | 2,000 | 20,000 |
| 1211 | Compilation, production and submission of the NC4 and BUR1 to the UNFCCC Activities: 3.1.1 & 3.1.2 | - | - | - | 3,000 | 3,000 | 6,000 |
| 1212 | Stocktaking assessment and institutional arrangements for preparation of subsequent NCs and BURs Activities:4.1.1,4.1.2 &4.1.3 | - | - | - | - | 10,000 | 10,000 |
| 1299 | Sub-total | - | 55,150 | 248,050 | 219,350 | 78,450 | 601,000 |
| 1300 | Administrative Support |  |  |  |  |  |  |
| 1301 | UNDP support costs, determined in accordance with its cost recovery policy (the clause C, UN2UN UNEP/UNDP Agreement) | - | 4,091 | 5,454 | 5,454 | 5,000 | 20,000 |
| 1302 | UNDP GMS (8% of the total net costs) | - | 12,606 | 16,808 | 16,808 | 15,408 | 61,630 |
| 1399 | Sub-total | - | 16,697 | 22,262 | 22,262 | 20,408 | 81,630 |
| 1600 | Travel on official business |  |  |  |  |  |  |
| 1601 | Travel expenses (international) to present NC4/BUR1 at the COP | - | - | - | 10,325 | 10,325 | 20,650 |
| 1602 | Travel expenses (local business trip) | - | - | - | - | - | - |
| 1699 | Sub-total | - | - | - | 10,325 | 10,325 | 20,650 |
| 1999 | Component Total | - | 73,238 | 274,486 | 256,111 | 111,965 | 715,800 |
| 30 | TRAINING/ WORKSHOP/MEETING COMPONENT |  |  |  |  |  |  |
| 3200 | Group training/Workshops |  |  |  |  |  |  |
| 3201 | 1.2.1.1.2 Organize a project inception workshop to Launch NC4 and BUR1 project in Turkmenistan | - | 3,000 | - | - | - | 3,000 |
| 3202 | 1.2.2.1.5 Conduct training for national experts/teams working on GHG inventory including supporting them to participate in relevant regional/international trainings on GHG inventory; 1.2.2.3.7. To organize a national seminar to present the results of the GHG inventory and to receive additional comments in accordance with the timing of data submission for the NC4 and BUR1 & 1.2.2.4.3. To conduct a workshop with decision makers from data source institutions to present the final results of the inventory process. | - | 2,500 | 4,500 | 11,000 | 5,000 | 23,000 |
| 3203 | 1.2.3.1.1.6. Technical capacity-building of national teams/experts working on vulnerability and adaptation assessments, including supporting their participation in relevant sub regional/regional/international workshops on Vulnerability Assessment and Adaptation as appropriate & 1.2.3.1.6.4. Organize national workshop on Vulnerability and Adaptation to review and approve activities that promote adequate adaptation | - | 1,000 | 3,000 | 3,000 | 2,000 | 9,000 |
| 3204 | 1.2.3.2.1.1. Technical capacity building of national teams/experts working mitigation measures including supporting their participation in relevant regional/international workshops/trainings on mitigation assessment as appropriate | - | 1,000 | 3,000 | 3,000 | 2,000 | 9,000 |
| 3205 | 1.2.4.2.7. To organize a national workshop to highlight the results of the PaMs modeling and analysis and get more comments. | - | - | - | 5,000 | - | 5,000 |
| 3206 | 1.2.7.1.1. Technical capacity building on MRV including supporting national teams working on MRV to participate in the relevant sub regional/regional/international workshops/ trainings on MRV as appropriate & 1.2.7.1.4. Organize consultations workshop with relevant stakeholders to discuss the proposed roadmap and strategic framework for establishing the MRV system. | - | 1,000 | 3,000 | 6,000 | - | 10,000 |
| 3299 | Sub-total | - | 8,500 | 13,500 | 28,000 | 9,000 | 59,000 |
| 3300 | Meetings/Conferences |  |  |  |  |  |  |
| 3301 | 1.2.3.1.1.5. Organization of the first national seminar on measures to promote adequate adaptation in the initial period of the Fourth National Communication with the purpose to consult with relevant stakeholders and identify approaches, tools and methods that will be used during vulnerability and adaptation assessment; | - | 2,000 | - | - | - | 2,000 |
| 3302 | 1.2.5.4.1.9 Organize two national seminars to raise awareness of national policy makers, especially those involved in national environmental planning processes, public health workers and the interested members of the public about the effects of climate change | - | 3,000 | - | 3,000 | - | 6,000 |
| 3303 | 3.1.5 Organize a final national conference on the NC4/ BUR1 project in Turkmenistan. | - | - | - | - | 3,000 | 3,000 |
| 3399 | Sub-total | - | 5,000 | - | 3,000 | 3,000 | 11,000 |
| 3999 | Component total | - | 13,500 | 13,500 | 31,000 | 12,000 | 70,000 |
| 40 | EQUIPMENT AND PREMISES |  |  |  |  |  |  |
| 4100 | Expendable equipment |  |  |  |  |  |  |
| 4199 | Sub-total | - | - | - | - | - | - |
| 4999 | Component total | - | - | - | - | - | - |
| 50 | MISCELLANEOUS COMPONENT |  |  |  |  |  |  |
| 5200 | Reporting costs |  |  |  |  |  |  |
| 5201 | 3.1.3 Translation of the BUR1 and NC4 from Russian into English. | - | - | - | 1,500 | 1,500 | 3,000 |
| 5202 | 3.1.4 Publication and preparation of electronic copies of the BUR1 and NC4 on a CD-ROM and submission of reports to UNFCCC | - | - | - | 9,000 | 9,000 | 18,000 |
| 5299 | Sub-total | - | - | - | 10,500 | 10,500 | 21,000 |
| 5300 | Sundry |  |  |  |  |  |  |
| 5301 | 5.1.7 Bank commission charges. | - | 300 | 300 | 300 | 300 | 1,200 |
| 5302 | 5.1.8. Annual financial audits | - | - | 1,000 | 1,000 | 2,000 | 4,000 |
| 5399 | Sub-total | - | 300 | 1,300 | 1,300 | 2,300 | 5,200 |
| 5400 | Hospitality and entertainment |  |  |  |  |  |  |
| 5499 | Sub-total | - | - | - | - | - | - |
| 5500 | Monitoring and evaluation |  |  |  |  |  |  |
| 5501 | 6.1.1 Undertake Project monitoring and evaluation (UNEP) | - | - | - | - | 20,000 | 20,000 |
| 5599 | Sub-total | - | - | - | - | 20,000 | 20,000 |
| 5999 | Component total | - | 300 | 1,300 | 11,800 | 32,800 | 46,200 |
| 99 | GRAND TOTAL | 20,000 | 87,038 | 289,286 | 298,911 | 156,765 | 852,000 |

Appendix 2 to Annex 1:

TERMS OF REFERENCES FOR PREPARATION OF NATIONAL COMMUNICATION REPORT

PROJECT MANAGER

Summary of responsibilities:

The Project Manager will be the lead full-time staff person responsible for day-to-day oversight of all program activity and fulfilment of outputs and outcomes elaborated in the Project Document.

Specific duties and responsibilities:

Operational project management in accordance with the Project Document and the UNDP guidelines and procedures for direct implemented projects, including:

•	Management and supervision of project implementation and evaluation across all components.  Assurance of successful completion of the project in accordance with the stated outcomes and performance indicators summarized in the Project Results Framework.

•	Regular communication and coordination with the National Implementing Partner, members of the Project Board, and all other partners and interested stakeholders, with regard to all project activity.  Organization of Project Board meetings at least once, or ideally twice, per year, subject to availability of members.

•	Regular communication with senior UNDP management with regard to all project activity.  Assurance of coordination with other UNDP projects and broad strategic initiatives.

•	Preparation of Annual Work Plans, including monthly targets and deliverables as well as annual spending targets in accordance with the Project Document.  Tracking of work outputs throughout the year in light of these Annual Work Plans.

•	Tracking and managing of project spending in accordance with the project budget, as well as UNDP rules and procedures, to ensure transparency, responsibility, and timely fulfilment of both program targets and budget targets.

•	Preparation and submittal of annual Project Implementation Reviews and other required progress reports to the Project Board, UNDP, and GEF in accordance with applicable requirements, in all required languages (English, Russian, and/or Turkmen, using outside translation as needed).

•	Supervision of the experts working for the project, including the Task Leader for transport and both international and national consultants.

•	Supervision of regular data collection and analysis, as well as reporting and public outreach via the mass media, events, and other means, to disseminate the results of the project and to promote sustainable urban development in Turkmenistan

•	Oversight of the overall administration of the project office.

•	Regular travel within Turkmenistan to organize and monitor project activity; possible travel outside the country for participation in directly relevant international meetings.

•	Support of independent Midterm and Terminal Evaluations of the project.

In addition to all above, the Project Manager of the Sustainable Cities Project will be a Manager of the NC4/BUR 1 project and liaise between the project and the government. The Project Manager will be responsible for solving financial issues of the NC4/BUR1 project.

Expected Qualifications:

•	University degree in management, engineering, marketing, or another field with direct relevance to the project

•	At least 10 years of experience in managing large-scale projects on climate change mitigation, energy efficiency, and/or urban development in Turkmenistan

•	Close familiarity with the roles, activities, and priorities of the Government of Turkmenistan, and particularly the State Committee of Environmental Protection and Land Resources, municipal administrations in Ashgabat, Awaza and other cities, and other national partners

•	Demonstrated ability to work effectively with a broad range of stakeholders

•	Demonstrated ability to work effectively under close supervision, as well as under minimal supervision

•	Superior skills in organization and management, including past experience with planning, tracking, evaluation, and supervision of consultants and/or employees

•	Strong skills in financial tracking and budget management

•	Close familiarity with the operations and rules of UNDP is not a requirement but will be viewed with favour

•	Fluency in Russian and English, in reading, writing, and speaking.

Required application materials:

Candidates should submit a full curriculum vitae, a brief statement of interest and qualifications, and a financial proposal.

NATIONAL COMMUNICATION AND BUR PROJECT TEAM LEADER

A National Communication and BUR Project Team Leader (TL) will be recruited by the EA to oversee project implementation, under the UNEP/UNDP supervision.  He/she will be responsible for the overall management of all aspects of the project and will provide technical assistance to the national technical expert groups.

The candidate should be highly motivated, enthusiastic, and capable of working independently.  He/she should have a strong scientific/technical and policy background.  The TL should have experience in preparation of National Communication on Climate Change and/or in other climate change enabling activities.  The ability to work with a wide variety of people from governments, agencies, non-governmental organizations, and research institutions is essential.

Duties:

The National Communication and BUR Project Team Leader operates under the overall guidance of the UNDP environment Programme specialist and the Manager of the sustainable cities project in collaboration and coordination with international and national consultants, project specialists and organizations.

The TL in consultation with NC steering committee will be responsible for the day- to-day management, co-ordination and supervision of the implementation of the project. The coordinator duties will include among others:

Co-ordinate all project activities with heads of technical expert groups, and a range of institutions and agencies, including UNEP, IPCC, UNFCCC secretariat, GEF, and national institutions to ensure smooth and appropriate execution of project activities

Prepare a detailed project workplan and terms of reference for the project consultants

Liaise with the relevant ministries, national and international research institutes, NGOs, and other relevant institutions in order to involve their staff in the project activities, and to gather and disseminate information relevant to the project.

Identify, interview and recruit national and international consultants to work for the project.

Promote and establish links with related national and regional projects, and other international programmes.

Prepare the periodic progress reports on project implementation and ensure that all national project outputs are sent to UNEP.

Manage the project expenditures according to the project budget.

Identify training needs of the contracted national consultants and other project stakeholders and identify appropriate courses and trainings for national capacity building.

Organize national workshops and trainings according to the project workplan.  Attend, whenever possible, the relevant regional and international workshops, trainings and conferences.

Review all materials generated during the project

Ensure the publication and dissemination of the reports identified as project outputs.

Coordinate negotiations on co-operation with Government and financing institutions in order to identify and mobilize sources for the follow-up activities.

Qualifications:

An advanced degree (at least MSc. or Ph.D.) in environmental science or another related field

Relevant experience in the field of climate change

Familiarity with national communications, and with international negotiations and processes under the UNFCCC

Substantial experience in government and in interdepartmental procedures

Familiarity with computers and world processing

Good command of national and UN and UN official language

Duty Station: The project office will be housed at the offices of the EA

PROJECT ASSISTANT

Organizational context:	The project assistant will work in the project implementation unit, which provides support for the projects in UNDP Turkmenistan

I.	Background:

The new UNDP strategy (Country Programme for 2016-2020) focuses on Low emission development, Climate Change Adaptation, Data revolution, and Rule of Law and Economic Diversification. It will be contributing to the Government and United Nations Partnership for Development 2016-2020, in particular to its intended results:

1.	Outcome “The national policy, legislative and institutional frameworks are aligned to reduce greenhouse gas emissions through promoting sustainable practices on energy efficiency, the use of renewables, urban development and waste management".

2.	Outcome “The national policy, legislative and institutional frameworks is responsive to climate change issues by promoting climate resilience, adaptation, climate risk management and disaster risk reduction measures at sector and community level”.

3.	Outcome, “State institutions implement and monitor laws, national programmes, and strategies in a participatory manner and in line with the country’s human rights commitments” and to the PFD outcome “Strategies and simplified regulations are in place to promote high quality inclusive employment through sustainable economic diversification”

4.	Outcome “Quality data, aligned with international standards, are available to policy makers, legislators, and the interested public to monitor the major goals of National Programmes, the post-2015 SDGs, and PFD and to formulate new national strategies and programmes”.

To achieve these results UNDP will support the implementation of a number of projects that will aim to attain outputs envisaged under the country programme document and its action plan (www.tm.undp.org). Ongoing projects will continue, and new projects will be formulated and implemented throughout the proposed period of 2016-2020.

The UNDP office established a structure, Project implementation unit, which is providing finance, procurement, and other administrative services to the project management in order to reach project objectives and implement project work plans. The project implementation unit consists of a team of individuals, who perform a set of specific duties in accordance with UNDP Programme and Operations Policies and Procedures (POPP) related to project management support. These duties include but are not limited to project financial and budget management, actions aimed at procuring goods and services, organization of project events, maintenance of project records, inventory, other administrative support required by the project management.

The present position focuses on the procurement processes of the NIM/DIM projects.

II.	Tasks and Responsibilities:

Under the overall guidance and direct supervision of the head of project implementation unit, the Project Assistant is responsible for provision of administrative functions.  The Project Assistant will work in close coordination assigned project managers to fully support project managers in implementation of all project activities. The direct supervisor will feed inputs from project managers in SC Performance Evaluation.

Summary of key functions:

	Provide effective financial services and assist in project budget management;

	Provide logistical services and event arrangement and management;

	Provide procurement services;

	Provide administrative services;

III.	Specific Responsibilities

1.	Ensure provision of effective financial services and assistance in project budget management, focusing on achievement of the following results:

•	Create non-PO vouchers; check that vouchers processed, matched and completed, transactions are correctly recorded and posted in Atlas;

•	Ensure timely corrective actions on un-posted vouchers, including the vouchers with budget check errors, match exceptions, unapproved vouchers;

•	 Prepare requests for direct payments, ensuring provision of required supporting documentation, provide timely feedback and follow up on the status of submitted payments;

•	Ensure timely submission of correctly completed travel claims;

•	Undertake cost estimates for different activities according to the needs of projects;

•	 Assist in developing detailed project budgets for all activities and outputs;

•	Monitor project budget in terms of expenditures according to the work plan;

•	Assist in preparing quarterly expenditure reports;

•	Provide detailed information on finance issues during project audit exercise;

2.  Provide effective logistical services to project, focusing on achievement of the following results:

•	Assist project personnel and national/ international consultants to arrange travel within and outside Turkmenistan; more specifically support in development of itinerary, ticket booking/purchasing, arrangement of hotel reservation/apartment, transportation, translation/interpretation services;

•	In coordination with Project Manager and UNDP office arrange preparation of visas for and timely registration of coming visitors making sure that visitors are aware of visas and registration procedures;

•	Arrange foreign visas for project personnel for travels outside Turkmenistan as per approved AWPs;

•	Prepare Travel Authorizations with proper supporting documents;

•	When necessary raise travel related e-requisitions making sure correct use of chart of accounts;

•	In coordination with Project Manager draft and compile necessary documentation such as agenda, compilation of list of participants for seminars, workshops, trainings, and other project related events;

•	Make logistical arrangements for seminars, workshops, trainings and other project related events, including venue reservation, arrangements of meals, translation/interpretation services, and required equipment, office supplies, arrangement of printing handouts materials;

•	Assist in customs clearance procedures by preparation of a package of necessary documents;

•	Make necessary arrangements for registration of projects, publications and other printing materials;

•	Arrange translation of documents when required;

3.  Ensure provision of effective procurement services to project, focusing on achievement of the following results:

•	Assist in development of procurement plan for the project;

•	Assist in announcement and wide dissemination of advertisements among potential suppliers;

•	Act as Secretary for procurement evaluation panels facilitating receipts of offers, clarifications, their analysis, reference check and writing final evaluation report;

•	Create e-requisitions for ICs/ other types of procurement in Atlas and ensure correct use of chart of accounts;

•	Assist Project Manager in preparation of all supporting documents for contract creation;

•	Create receipt of goods in Atlas upon delivery of goods and signing transferring report.

•	Coordinate with Project Manager to complete performance evaluation forms for national and international short terms consultants;

•	Arrange purchases using canvassing method for simple support services and goods including driving, translation/interpretation, maintenance, catering, suppliers, stationary, simple equipment (may include small scale purchase of office equipment and the like not exceeding 5,000 USD threshold);

•	Provide detailed information on procurement issues during project audit exercise;

•	Contribute to weekly summaries on Individual Contracts;

•	Maintain procurement documents filling system;

4.  Ensure provision of administrative services, focusing on achievement of the following results:

•	Serve as a custodian for stationary supplies, distribution stationary and keeping a log of distribution;

•	Provide support to periodic inventory exercise; create matrix for project inventories, such as publication materials, visibility items and monitor in/out flow;

•	Provide support to asset exercise; keep an updated list of project assets;

•	Maintain documents filling system;

•	Prepare minutes of the meetings and translate various documents;

•	Perform other related duties as necessary.

Carries out administrative support to the Climate Change project “Turkmenistan: Preparation of NC4/BUR1 under the UNFCCC” in financial, logistical, procurement and other related matters.

IV.	Competencies

•	Effective listening, verbal and writing communication skills;

•	Ability to work in and with diverse team;

•	Attention to detail and high level of accuracy;

•	Ability to work under time constraints;

•	Time management skills.

V.	Minimum Qualifications:

•	Secondary Education. University Degree in management and other related field is an asset;

•	5 years of substantial administrative experience;

•	Administrative experience in implementing development projects, especially within the UN system or other international development agencies is a strong asset;

•	Good knowledge of English and Russian. Knowledge of Turkmen language is an asset;

•	Good knowledge of Microsoft Office;

•	Knowledge and practical experience in Internet based platform is a strong asset.

TECHNICAL EXPERT GROUPS (TEGs)

A team leader will head each technical group consisting of experts’ consultants from relevant sectors, including government agencies, academic institutions, NGOs, and private sector.  The TEGS will be answerable to the National Communication and BUR Project Team Leader. The National Communication and BUR Project Team Leader and the head of each working group will form the Project Management Team.  The TWG will develop the work plan of the group’s relevant activity areas and sectors.  They will provide technical assistance for project activities and guidance training on scientific or methodological aspects of project work.

The National Communication and BUR Project Team Leader will manage all technical assistance and recruitment of consultants for day-to-day project work. The TEGs will have the following duties:

GHG INVENTORY TECHNICAL EXPERT GROUP

Duties:

Assist the National Communication and BUR Project Team Leader in preparation of a work plan as part of the relevant activity.

Advise on selection and application of appropriate inventory methodologies.

Assist in data quality assistance and key source analysis.

Recommend the ways of improvement of the national emission actors.

Contribute substantially to development of the National Inventory Report and identify the follow-up activities.

Assist the National Communication and BUR Project Team Leader in arrangement of the national review and training workshops on improving quality of the national GHG inventory.

Suggest on technical capacity building and participate in the sub regional, regional and international training on GHG inventory.

VULNERABILITY AND ADAPTATION ASSESSMENT TECHNICAL EXPERT GROUP

Duties:

Assist the National Communication and BUR Project Team Leader in preparation of a work plan as part of the relevant activity.

Advise on selection of appropriate methodologies to assess vulnerability and adaptation.

Oversee the development of climatic scenarios and selection of relevant methodologies.

Supervise an assessment of vulnerability and climate change impact.

Contribute substantially to development of the National Strategy on Adaptation to Climate Change and identify the follow-up activities.

Help organize the national review and training workshops on vulnerability and adaptation measures.

Suggest on capacity building and participate in the sub regional, regional and international trainings on integrated assessment modeling.

3.  MITIGATION ANALYSIS TECHNICAL EXPERT GROUP

Duties:

Assist the National Communication and BUR Project Team Leader in preparation of a work plan relevant to the activity;

Assist the National Communication and BUR Project Team Leader in search and choice of appropriate training courses on applying macro-economic models;

Advise on selection of macro-economic models for evaluating mitigation options and measures for GHG emission reduction;

Overview and select measures to mitigate climate change and identify the follow-up activities;

Assist the National Communication and BUR Project Team Leader in arranging the national review and training workshops on climate change mitigation measures;

Suggest on technical capacity building and participate in the sub regional, regional and international trainings on mitigation measures analysis.

GENERAL INFORMATION RELATED TO CLIMATE CHANGE:

A. TECHNICAL EXPERT GROUP ON FINANCIAL, TECHNOLOGY AND CAPACITY BUILDING NEEDS AND SUPPORT RECEIVED

Duties:

Assist the National Communication and BUR Project Team Leader in preparation of a work plan as part of the relevant activity.

Advise on sources of information on constraints and gaps, and related financial, technical and capacity-building needs

Assist in compiling information on financial resources, technology transfer, capacity-building and technical support received from the Global Environment Facility, Parties included in Annex II to the Convention and other developed country Parties, the Green Climate Fund and multilateral institutions for activities relating to climate change, including for the preparation of the current biennial update report.

Analyze the cost-effectiveness of the technologies and the opportunities for their application.

Assess the existing endogenous technologies for further promotion within the context of national circumstances.

Contribute substantially to the establishment of a database for ESTs, including both mitigation and adaptation technologies.

Identify technology needs, which must be nationally determined, and on technology support received

Assist in arranging the national review and awareness raising workshops on ESTs and participate in the sub regional, regional and international trainings on ESTs.

B. ENVIRONMENTALLY SOUND TECHNOLOGIES (EST) TECHNICAL EXPERT GROUP

Duties:

Assist the National Communication and BUR Project Team Leader in preparation of a work plan as part of the relevant activity.

Advise on selection of priority technological needs.

Analyze the cost-effectiveness of the technologies and the opportunities for their application.

Assess the existing endogenous technologies for further promotion within the context of national circumstances.

Contribute substantially to the establishment of a database for ESTs, including both mitigation and adaptation technologies.

Identify the follow-up activities

Assist in arranging the national review and awareness raising workshops on ESTs and participate in the sub regional, regional and international trainings on ESTs.

C. RESEARCH AND SYSTEMATIC OBSERVATION TECHNICAL EXPERT GROUP

Duties:

Assist the National Communication and BUR Project Team Leader in preparation of work plan in part of the relevant activity.

Assess the existing system for early warning on extreme weather events and methods of seasonal forecasting.

Analyze the existing barriers for development of observation systems and research, and identify the follow-up activities

Contribute substantially to development of the National Information Report on Research and Systematic Observation.

Assist in arranging the national review and awareness raising workshops on research and systematic observation, and participate in the sub regional, regional and international trainings on the matter.

D. EDUCATION, TRAINING AND PUBLIC AWARENESS, INFORMATION AND NETWORKING AND CAPACITY-BUILDING

Duties

Compile and analyze information on activities/tasks relating to the implementation of the New Delhi work program on Article 6 of the Convention;

Compile and analyze information on activities/tasks relating to the implementation of the Capacity-building framework of the UNFCCC;

Identify the needs and priorities for climate change education, training and public awareness and capacity-building as they relate to GHG inventory, vulnerability and adaptation assessment, mitigation, technology transfer, research and systematic observation and other emerging priorities;

Liaise and consult with the various TEG under the NC project and the National Capacity Self-Assessment;

Prepare a draft National plan for implementation of Article 6 of the Convention and the UNFCCC capacity building framework;

Identify technology needs for information and networking;

Conduct a workshop on ways to promote climate change education, training and public awareness;

Prepare a chapter on: (i) Education, Training and Public Awareness, (ii) Information and Networking, (iii) capacity-building for inclusion in the compilation of the NC

Duration: Technical Expert Groups will be engaged according to project workplan and Terms of Reference

NATIONAL PROJECT ADVISORY COMMITTEE (NPAC)

The National Project Advisory Committee (NPAC), which comprises of various representatives, will be responsible for supervising the project implementation.  This will include evaluating the project outputs to ensure project activities are being carried out in a timely manner. The NPAC will perform the following responsibilities:

Monitor, evaluate and provide advice and guidance during the implementation of the project;

Collaborate with the Project Management Team (PMT) in preparing the National Communication Report;

Ensure that the development of the National Communication Document is in conformity with the UNFCCC guidelines relating to the formulation of national communications;

Formulate necessary measures, where appropriate, to ensure that the proposed project activities and outputs accomplish the project’s objectives;

Provide oversight responsibility to ensure a smooth transition from the current to subsequent National Communication reporting and any other follow-up measures.

APPENDIX 3 to Annex 1

THE CORRESPONDENCE OF UNEP AND UNDP BUDGET CODES

(reflecting in the Annexes with budget planning and reporting (APPENDIX 1 to Annex 1, ANNEX 9 and 10) in order to avoid contradictions in budget entry and reporting).

|  | PERSONNEL COMPONENT |  |  |  |
| --- | --- | --- | --- | --- |
| 10 | UNEP account | UNEP Description of account | UNDP account | UNDP Description of account |
|  | 1100 | Project personnel | 71400 | Contractual Services - Individuals |
|  | 1200 | Consultants | 71300/71400 71200 | Local Consultants International Consultants |
|  | 1300 | Administrative Support | 71400 | Contractual Services - Individuals |
|  | 1600 | Travel on official business | 71600 | Travel |
| 20 | SUB-CONTRACT COMPONENT |  |  |  |
|  | 2100 | Sub-contracts (MOUs/LOAs for cooperating agencies) | 72100 | Contractual Services-Companies |
|  | 2200 | Sub-contracts (PCAs/SSFAs for supporting organizations) | 72100 | Contractual Services-Companies |
|  | 2300 | Sub-contracts (for commercial purposes) | 72100 | Contractual Services-Companies |
| 30 | TRAINING COMPONENT |  |  |  |
|  | 3200 | Group training/ Workshops | 75700 | Training, Workshops and Confer |
|  | 3300 | Meetings/Conferences | 75700 | Training, Workshops and Confer |
| 40 | EQUIPMENT AND PREMISES COMPONENT |  |  |  |
|  | 4100 | Expendable equipment | 72200 | Equipment and Furniture |
|  | 4200 | Non-expendable equipment | 72200 | Equipment and Furniture |
| 50 | MISCELLANEOUS COMPONENT |  |  |  |
|  | 5100 | Operation and maintenance of equipment | 73400 | Rental & Maint of Other Equip |
|  | 5200 | Reporting costs |  | No specific account |
|  | 5300 | Sundry | 74500 | Miscellaneous Expenses |
|  | 5400 | Hospitality and entertainment | 72700 | Hospitality/Catering |

____________

* The UNDP budget account 71400 will be used for Key Long-Term Experts, for which the ToRs are prepared as part of the PIP. The UNDP budget account 71300 will be used for Short-Term Consultants, for which ToRs will be developed as required.