Preparation of Kigali HFC implementation plan

Date of signature of the agreement for the project funds with the total amount of funds for which it has been signed (month/year) for projects with agreement signature in the current year and (year) for projects with agreement signature in years prior to 2022;

The KIP project with a cost of US $170,000 was approved by the Executive Committee (ExCom) of the Multilateral Fund at its 87th meeting in July 2021. Agency agreement between the UNEP and UNDP was signed in December 07, 2021.

Project’s Start/End dates: 15 December 2021-31 August 2023

Amount of agreement UN&UN is 64,000 USD

- Activities implemented during the reporting period in terms of activity type (e.g., training conducted for technicians; licenses for entities issued, equipment procured and distributed) in a maximum of 3-4 lines; priority to be given to activities that are essential under the specific project under consideration;

On 9 February 2022 held a TKM KIP project coordination meeting with national experts and online participation of an international KIP expert and UNEP representative.

On 17 February 2022, technical seminar “How to increase the consumption of natural refrigerants in Turkmenistan” with the online participation of an international expert.

On 4 March 2022, held stakeholders meeting related to the launch of KIP project in Turkmenistan, an overview of the goals and objectives of the project and the expected outputs/results upon its completion.

On 28 March 2022, conducted a training for Customs employees and Inspectors related to monitoring and controlling the trade in HFCs in the training center of the Customs service of Turkmenistan.

On 6 April 2022, held an online meeting with online participation of International expert “Identifying the need to modify existing regulations or to create new regulation that would facilitate the HFC phase-down”.

On 6 May 2022, held seminar “New technologies in the refrigeration sector on the international market and emerging opportunities for the refrigeration business” to raising awareness among engineers and technicians of refrigeration and air conditioning servicing field about alternatives to HFCs with low global warming potential (GWP).

On 22 July 2022, held a consultation meeting with the participation of stakeholders to develop and discuss in detail the activities that can be included in the HFC phase-down strategy and energy saving potential in the RAC industry of Turkmenistan.

Analyzed the process on the adoption of international standards. Coordinated with the national standardization organization “Turkmenstandartlary” for adoption of the European Standard on safety and environment requirements for refrigeration systems and heat pumps EN 378 (1-4) 2014. Standard has been adopted and enacted.

Completion of the review of ODS alternatives survey for 2019-2021 with an overview of the refrigeration servicing sector and analysis of the data to estimate the HFC baselines.

Conducted work on the analysis of National strategy on climate change of Turkmenistan to identify measures that are relevant to the phase-down of HFCs and the Kigali Amendment provisions.

On 16 December 2023, held a consultation meeting with main stakeholder to approve prepared HFC phase-down strategy in Turkmenistan. The seminar was attended by Government ministries/authorities and private companies, which work related with supply refrigeration and air-conditioning equipment.

On 19 December 2022, held a training seminar dedicated to creating awareness for newcomer’s engineers and technicians of refrigeration and air conditioning servicing field with local technicians.

On 2 March 2023, conducted a training seminar for new customs inspectors related the licensing system and recording of individual HFCs in the training center of the State Customs service of Turkmenistan.

Meetings and consultations with representatives of the Ministry of Energy and experts of the other international projects on the preparation a draft law on energy conservation and energy efficiency.

From 25 to 28 March 2023, conducted training seminars for technicians on efficient practices of operation, maintenance and installation in RAC systems by international RAC experts.

On 29 March 2023, conducted conference aimed to discuss the activities of the first stage of the phasing-down of Hydrofluorocarbons (HFCs) and present the latest version of the KIP-stage I project proposal with participation of the international experts and stakeholders.

Numerous publications on HFC phase-down were disseminated to RAC technicians and ecology inspectors.

- Equipment procured and distributed during project

Hard drives and USB flash drives were distributed for the purpose of public awareness to Educational Institutions. Different information, videos about climate change and ozone layer, educational materials, technical materials were recorded.

- Gender mainstreaming activities

Number and percentage of women’s participants in trainings/seminars were taken into account. Women’s participation ensured in activities. The share of women at the seminars/activities were 18%.

- Overall assessment of project progress (whether it is satisfactory or delayed; in the case of delays, what actions have been taken to resolve the delays). The route that caused the delays needs to be described.

Project progress was achieved in reviewing the national legislation, policies, development the mandatory reporting by HFC importers, planning reduction steps (quotas allocations), adoption standards, through assessment related to the promotion of energy efficiency in cooling sector, survey of HFC consumption as a preparatory step to ensure future compliance with the HFCs phase-out targets.

Cooperation with the refrigeration sectors in Turkmenistan was enhanced, relevant awareness, trainings and activities.

The successful implementation of the KIP project had the following impacts:

- Disseminated information to promote environmentally-friendly systems where possible adopt low-GWP alternatives.

- Trained of RAC technicians in new and alternative refrigeration and refrigerant technologies.

- Adopted the standard.

- Overviewed for HFC policy and legislative.

- Developed a draft document “On approval of the procedure for the annual quota of the permissible volume of imports and consumption in Turkmenistan of substances included in list “F” of the list of substances under the Kigali Amendment to the Montreal Protocol, the circulation of which is subject to state regulation.

- Developed the mandatory reporting for HFC Importers. “Mandatory reporting of importers and exporters of HFCs”. Order of the Minister of Agriculture and Environmental Protection of Turkmenistan.

- As a result of the project the draft of KIP (stage 1) was prepared and introduced.