## Project Identification
Land Degradation Focal Area - Portfolio Monitoring and Tracking Tool (PMAT) - GEF-6
PROJECT IDENTIFICATION
1. Project Title | Strengthening Forest Area Planning and Management in Kalimantan
2. GEF ID: | 6965
3. Project Implementation Period (Indicate: starting and ending dates) | June 2017 - June 2025
4. PMAT Completion Date
a. Submission of CEO Endorsement/Approval Document | December 2, 2016
b. Annual submission (specify year) – TO BE LINKED TO PIR | June 2018 (anticipated)
c. Submission at Project Closure (specify year) | June 2025 (anticipated)
5. Person Responsible for Completing the PMAT (Indicate Name, Position, Institution): | Anton Sri Probiyantono, Technical Officer, UNDP Indonesia
6. Scale of Project - Refer to Guidelines for definition and check (x) only the most appropriate.
a. Global
b. Regional
c. Sub regional/ Transboundary
d. National | Indonesia
e. Sub national - district, provincial | West Kalimantan, Central Kalimantan, East Kalimantan, Jakarta, Ketapang, Sintang, Kotawaringin Barat, Kutai Timur
f. Site - landscape, watershed/catchment, river basin (specify) | X (covering portions of West, Central and East Kalimantan provinces)

## Project Context
PART I – PROJECT CONTEXT
1. Agro-ecological context – Characterization of area in which project is located & Land Degradation Problem
1.a | What agroecological zone(s) is the project situated? Select the most appropriate from the drop down menu. | v. Humid | Select | Notes
1.b | What production system(s) will the project target? Please provide an estimated coverage of the area targeted.
| i. Agriculture (including food crop, tree crop, and crop-livestock) | 3055000 | Hectares | Not available
| ii. Rangeland |  | Hectares
| iii. Pastoral |  | Hectares
| iv. Forestry |  | Hectares
| v. Mixed Systems |  | Hectares
| TOTAL area of production systems targeted | 3055000 | Hectares
1.c | What is the extent of land degradation within the project boundary?
| i. Agriculture (including food crop, tree crop, and crop-livestock) |  | Hectares
| ii. Rangeland |  | Hectares
| iii. Pastoral |  | Hectares
| iv. Forestry | 1384148 | Hectares
| v. Mixed Systems |  | Hectares
1.d | What is the nature of land degradation to be addressed directly? Please refer to guidelines and check (X) only the most relevant and provide relevant data where applicable and available
| i. Loss of vegetative cover | X
| ii. Degradation of vegetation (biomass, health, damage, age structure) | X
iii. Degradation of soil properties (chemical, physical and biological)
| iv. Soil loss by wind / water erosion |  | Tons/ Hectare
v. Loss of land by soil deposits and moving sand dunes
| vi. Loss of above-ground carbon | X | Tons/ Hectare
| vii. Loss of soil carbon |  | Tons/ Hectare
| viii. Declining land productivity - based on Net Primary Productivity measure |  | Kg C/ha/year
| ix. Loss of biodiversity characterized at habitat level - based on Biodiversity Intactness Index | Nil | Index
x. Loss of biodiversity characterized at species level
xi. Increase in invasive, harmful or less useful species
xii. Loss/reduced water supply (surface and ground water)
xiii. Loss/reduced water quality (surface and ground water)
xiv. Lowering of groundwater table / reduced aquifer
xv. Loss of wetlands and their functions
xvi. Increased extent and severity of flood, drought, storm damage
2. Socio-economic context - Characterization of affected communities and populations
2.a. | Number of affected people within the project boundary
| Male | NA | Number
| Female | NA | Number
2.b. | Average annual household income of affected population within the project boundary
| i. Average annual household income from crop and livestock production | 400 | US$
| ii. Average annual household income from forest and tree products | 200 | US$
| iii. Annual household income from PES schemes | 0 | US$

## GEBs & Development benefits
PART II – GLOBAL ENVIRONMENTAL BENEFITS & DEVELOPMENT BENEFITS
3. Measurable global environmental benefits in the targeted project area (Baseline at CEO endorsement stage; Actual values at MTR & TE)
a. Land cover
| i. Vegetative cover (natural & cultivated cover such as forest, shrubs, herbaceous, incl. crops) | 674899 | Hectares | Untuk 4 Kabupaten Lokus
b. Avoided emissions
| i. Carbon stocks | 73117865 | Tons/Hectare | Untuk 4 Kabupaten Lokus
| ii. Other GHG gases | 244812900 | Tons CO2 e/ Ha | Untuk 4 Kabupaten Lokus
c. Carbon sequestration
| i. Above ground biomass | 0 | Tons CO2 e/ Ha | Untuk 4 Kabupaten Lokus
| ii. Soil Carbon | 0 | Tons CO2 e/ Ha | Not Applicable
4. Development benefits in the targeted project area (Baseline at CEO endorsement stage; Actual values at MTR & TE)
| i. Average annual household income from crop and livestock production | 0 | US$
| ii. Average annual household income from forest and tree products | 0 | US$
| iii. Annual household income from PES schemes | 0 | US$

## Outcomes & DLDD advocacy
PART III – PROJECT OUTCOMES AND DLDD ADVOCACY
Outcome Monitoring (Baseline at CEO endorsement stage; Actual values at MTR & TE)
LDFA Objectives and Outcomes |  | Indicators and Measures |  |  | Notes/Units
LD1 – Ecosystem services in production landscapes (agriculture, rangeland) - PROGRAM 1 & PROGRAM 2
i. Improved agricultural, rangeland and pastoral management
|  | Land area under effective agricultural, rangeland and pastoral mgmt practices and/or supporting climate-smart agriculture |  |  | Hectare
ii. Functionality and cover of agro-ecosystems maintained
|  | Land area under effective management in production systems with improved vegetative cover |  | 674899 | Hectare
iii. Increased investments in SLM |  | Value of resources flowing to SLM from divers sources (incl. climate change adaptation and mitigation) |  |  | US Dollar
LD2 – Ecosystem services in forest landscapes - PROGRAM 3
i. Support mechanisms for forest landscape management and restoration established |  | Types of (innovative) mechanisms, institutions, legal and regulatory frameworks to support SFM and restoration |  |  | Types
|  | Number of (innovative) mechanisms |  |  | Number
ii. Improved forest management and/or restoration |  | Land area under sustainable forest management and/or restoration practices |  |  | Hectare
iii. Increased investments in SFM and restoration |  | Value of resources flowing to SFM from divers sources (e.g. PES, small credit schemes, voluntary carbon market) |  |  | US Dollar
LD3 – SLM in wider landscapes (integrated management) - PROGRAM 4
i. Support mechanisms for SLM in wider landscapes established |  | Demonstration results strengthening cross-sector integration of SLM |  | 0 | Number of demonstrations
ii. Integrated landscape management practices adopted by local communities |  | Application of INRM practices in the wider landscape |  | 100000 | Hectare
iii. Increased investements in integrated landscape management |  | Increased resources flowing to INRM and other land uses form divers sources |  | 0 | US Dollar
LD4 – Adaptive management and SLM learning - PROGRAM 5
i. SLM mainstreamed in development investments and value chains across multiple scales |  | Increased investments in SLM |  |  | US Dollar
ii. Innovative mechanisms for multi-stakeholder planning and investment in SLM at scale |  | Type of mechnisms, institutions, legal and regulatory frameworks |  |  | Types
|  | Number of innovative mechanisms |  |  | Number
DLDD advocacy, awareness raising and education
a. Number and size of information events organized on the subject of desertification, land degradation and drought (DLDD) and/or DLDD synergies with climate change and biodiversity, and audience reached by media addressing DLDD and DLDD synergies
i. Number of events | No. of national events | 0 | No. of regional events |  | No. of global events
ii. Qualitative assessment (provide info as needed on type and size of events) | [5 empty] | Fasiltasi seminar/COP/Equator Prize

## Sheet1
Tracking Tool for GEF 6 SFM Projects
Section A. General Data
Project Title | Strengthening Forest Area Planning and Management in Kalimantan
GEF ID | 6965
GEF Agency | UNDP
Agency Project ID | 5029
Country | Indonesia
Region | EAP
Date of Council/CEO Approval | April 28, 2015 |  | Month DD, YYYY (e.g., May 13, 2014)
GEF Grant (US$) | 9000000
Date of submission of the tracking tool/MTR | December 2, 2016 |  | Month DD, YYYY (e.g., May 13, 2014)
Section B. Quantitative Data (targets at CEO Endorsement, Actual values at MTR & TE)
SFM Objectives and Outcomes | Indicators and Measures
SFM-1: Maintained Forest Resources: Reduce the pressures on high conservation value forests by addressing the drivers of deforestation.
Outcome 1: Cross-sector policy and planning approaches at appropriate governance scales, avoid loss of high conservation value forests. | Indicator 1: Area of high conservation value forest identified and maintained. | 674899 |  | Hectare
Outcome 2: Innovative mechanisms avoid the loss of high conservation value forest. | Indicator 2: Number of incentive mechanisms to avoid the loss of high conservation value forests implemented. | 4 |  | Number of mechanisms
SFM-2: Enhanced Forest Management: Maintain flows of forest ecosystem services and improve resilience to climate change through SFM.
Outcome 3: Increased application of good management practices in all forests by relevant government, local community (both women and men) and private sector actors. | Indicator 3: Area of sustainably managed forest, stratified by forest management actors. | 583303 |  | Hectare
Outcome 4: Increased contribution of sustained forest ecosystem services to national economies and local livelihoods of both women and men. | Indicator 4: The number of forest policies that include valuation and accounting of economic, social and environmental benefits and services. | 52 |  | Number of policies
SFM-3: Restored Forest Ecosystems: Reverse the loss of ecosystem services within degraded forest landscapes.
Outcome 5: Integrated landscape restoration plans to maintain forest ecosystem services are implemented at appropriate scales by government, private sector and local community actors, both women and men. | Indicator 5: Area of forest resources restored in the landscape, stratified by forest management actors. |  |  | hectare
SFM-4: Increased Regional and Global Cooperation: Enhanced regional and global coordination on efforts to maintain forest resources, enhance forest management and restore forest ecosystems through the transfer of international experience and know-how.
Outcome 6: Improved collaboration between countries and across sectors on the implementation of SFM. | Indicator 6: Development and strengthening of networks to promote regional and global cooperation. | 390 |  | Number of networks
Reporting on lifetime emissions avoided Lifetime direct GHG emissions avoided: Lifetime direct GHG emissions avoided are the emissions reductions attributable to the investments made during the project's supervised implementation period, totaled over the respective lifetime of the investments. Lifetime indirect GHG emissions avoided (top-down and bottom-up): indirect emissions reductions are those attributable to the long-term outcomes of the GEF activities that remove barriers, such as capacity building, innovation, catalytic action for replication.
For LULUCF projects, lifetime length is defined to be 20 years, unless a different number of years is deemed appropriate. For emission or removal factors (tonnes of CO2eq per hectare per year), use IPCC defaults or country specific factors.
Total Lifetime Direct and Indirect GHG Emissions Avoided overBaseline (target at CEO Endorsement, Actual values at MTR & TE) |  |  | Identify source (conservation, avoided deforestation, reforestation), type of low GHG Management Practice and describe estimation methodology used
Lifetime direct GHG emissions avoided |  | tCO2eq | FAO EXACT
Lifetime indirect GHG emissions avoided | 73117865 | tCO2eq
Area under low GHG Management Practices | 674899 | Hectares

## Sheet2
Tracking Tool for GEF-6 Biodiversity Projects
GEF 6: Objective 4, Program 9: Managing the Human-Biodiversity Interface
Objective: To measure progress in achieving the impacts and outcomes established at the portfolio level under the biodiversity focal area. Rationale: Project data from each phase of the GEF will be aggregated for analysis of directional trends and patterns at a portfolio-wide level to inform the development of future GEF strategies and to report to GEF Council on portfolio-level performance in the biodiversity focal area and submitted to the GEF Secretariat. Structure of Tracking Tool: Each tracking tool requests background and coverage information on the project and specific information required to track portfolio level indicators in the GEF-6 biodiversity strategy. Guidance in Applying GEF Tracking Tools: GEF tracking tools are applied three times: at CEO endorsement for FSPs, CEO approval for MSPs, and at project mid-term and project completion for all projects. Submission: The finalized tracking tool will be cleared by the GEF Agencies as being correctly completed.
PLEASE NOTE THAT THIS TOOL IS ONLY FOR USE FOR GEF-6 PROJECTS.
I. General Data | Please indicate your answer here | Notes
Project Title | Strengthening Forest Area Planning and Management in Kalimantan
GEF Project ID | 6965
Agency Project ID | 5029
Implementing Agency | UNDP
Project Type | FSP | FSP or MSP
Country | Indonesia
Region | Kalimantan
Date of submission of the tracking tool | December 2, 2016 | Month DD, YYYY (e.g., May 12, 2010)
Name of reviewers completing tracking tool and completion date | Anton Sri Probiyantono, 30 Nov 2016 | Completion Date
Planned project duration | 8 | years
Actual project duration |  | years
Lead Project Executing Agency (ies) | Ministry of Environment and Forestry (MoEF)
Please identify production sectors directly targeted by project:
Agriculture | 2 | 1: Primarily and directly targeted by the project 2: Secondary or incidentally affected by the project
Fisheries |  | 1: Primarily and directly targeted by the project 2: Secondary or incidentally affected by the project
Forestry | 1 | 1: Primarily and directly targeted by the project 2: Secondary or incidentally affected by the project
Tourism | 2 | 1: Primarily and directly targeted by the project 2: Secondary or incidentally affected by the project
Mining |  | 1: Primarily and directly targeted by the project 2: Secondary or incidentally affected by the project
Oil & gas |  | 1: Primarily and directly targeted by the project 2: Secondary or incidentally affected by the project
Infrastructure |  | 1: Primarily and directly targeted by the project 2: Secondary or incidentally affected by the project
Other (please specify)
II. Project Landscape/Seascape Coverage
1. What is the extent (in hectares) of the landscape or seascape where the project will directly or indirectly contribute to biodiversity conservation or sustainable use of its components?
Foreseen at project start (to be completed at CEO approval or endorsement). Please enter the coverage in area as measured in hectares that the project aims to achieve.
Landscape/seascape[1] area directly[2] covered by the project (ha) | 500000
Landscape/seascape area indirectly[3] covered by the project (ha) | 9500000
Explanation for indirect coverage numbers: | Total area of four pilot districts within which landscape-level demonstrations, dialogue and policy change will take place
Actual at mid-term. Please enter the coverage in area as expressed in hectares that the project achieved at the mid-term.
Landscape/seascape[1] area directly[2] covered by the project (ha)
Landscape/seascape area indirectly[3] covered by the project (ha)
Explanation for indirect coverage numbers:
Actual at project completion. Please enter the coverage in area as expressed in hectares that the project achieved at project completion.
Landscape/seascape[1] area directly[2] covered by the project (ha)
Landscape/seascape area indirectly[3] covered by the project (ha)
Explanation for indirect coverage numbers:
[1] For projects working in seascapes (large marine ecosystems, fisheries etc.) please provide coverage figures and include explanatory text as necessary if reporting in hectares is not applicable or feasible.
[2] Direct coverage refers to the area that is targeted by the project’s site intervention. For example, a project may be mainstreaming biodiversity into floodplain management in a pilot area of 1,000 hectares that is part of a much larger floodplain of 10,000 hectares.
[3] Using the example in footnote 2 above, the same project may, for example, “indirectly” cover or influence the remaining 9,000 hectares of the floodplain through promoting learning exchanges and training at the project site as part of an awareness raising and capacity building strategy for the rest of the floodplain. Please explain the basis for extrapolation of indirect coverage when completing this part of the table.
2. Are there Protected Areas within the landscape/seascape covered by the project? If so, names these PAs, their IUCN or national PA category, and their extent in hectares
III. Managing the Human-Biodiversity Interface: Management Practices Applied
Within the scope and objectives of the project, please identify in the table below the management practices employed by project beneficiaries that integrate biodiversity considerations and the area of coverage of these management practices. Please also note if a certification system is being applied and identify the certification system being used. Note: this could range from farmers applying organic agricultural practices, forest management agencies managing forests per Forest Stewardship Council (FSC) guidelines or other forest certification schemes, artisanal fisherfolk practicing sustainable fisheries management, or industries satisfying other similar agreed international standards, etc. Please add rows if needed if more than one management practice is being applied.
e.g. Foreseen at Project Start | E.g., Sustainable management of pine forests | Please indicate specific management practices that integrate BD
| FSC | Name of certification system being used (insert NA if no certification system is being applied)
| 120,000 hectares | Area of coverage
Foreseen at project start / Project Targets (to be completed at CEO approval or endorsement) | Sustainable palm oil production methods; conservation of HCV forest in production landscape | Please indicate specific management practices that integrate BD
| FSC, SVLK, RSPO, and ISPO | Name of certification system being used (insert NA if no certification system is being applied)
| 150,000 hectares | Area of coverage
Actual at mid-term |  | Please indicate specific management practices that integrate BD
Name of certification system being used (insert NA if no certification system is being applied)
Area of coverage
Actual at project completion |  | Please indicate specific management practices that integrate BD
Name of certification system being used (insert NA if no certification system is being applied)
Area of coverage
Part IV. Managing the Human-Biodiversity Interface: Policy and Regulatory frameworks
For those projects that have identified addressing policy, legislation, regulations, and their implementation as project objectives, Please complete these tables for each sector that is a primary or a secondary focus of the project. Please answer Yes or No for each statement under the sectors that are a focus of the project (as noted in Part I). Note that the questions are sequential, therefore a "Yes" cannot come after a "No".
Sequential steps in mainsteaming biodiversity into policy and regulatory frameworks | Status (yes/no) | Comments (optional)
Step 1: Biodiversity considerations are mentioned in sector policy
Agriculture | Yes
Fisheries
Forestry | Yes
Tourism | Yes
Mining
Oil & gas
Infrastructure
Other (please specify)
Step 2: Biodiversity considerations are mentioned in sector policy through specific legislation
Agriculture | Yes
Fisheries
Forestry | Yes
Tourism | Yes
Mining
Oil & gas
Infrastructure
Other (please specify)
Step 3: Regulations are in place to implement the legislation
Agriculture | Yes
Fisheries
Forestry | Yes
Tourism | Yes
Mining
Oil & gas
Infrastructure
Other (please specify)
Step 4: The regulations are under implementation
Agriculture | Yes
Fisheries
Forestry | Yes
Tourism | Yes
Mining
Oil & gas
Infrastructure
Other (please specify)
Step 5: The implementation of regulations is enforced
Agriculture | Yes
Fisheries
Forestry | Yes
Tourism | Yes
Mining
Oil & gas
Infrastructure
Other (please specify)
Step 6: Enforcement of regulations is monitored
Agriculture | Yes
Fisheries
Forestry | Yes
Tourism | Yes
Mining
Oil & gas
Infrastructure
Other (please specify)
Komentar:
Penafsiran yang berbeda dengan kondisi eksisting atau policy saat ini. Secara point of view yang membuat prodoc dengan ditjen planologi lain.
Outputnya mengira2 dan tidak banyak impact ke kebijakan Planologi, sehingga Apa yang ditentukan jg belum tentu pas buat KLHK
Scope, kerangka atau figure angka indikator yang dimention sepertinya diluar scope luasan project, Cuma angka targetnya seperti level nasional yang bahkan gubernur juga belum tentu bisa achieve. Seakan2 target di kabupaten site project yang sudah achieve berimpact dengan kabupaten lain, sedangkan belum tentu selama belum jadi policy.
Target terlihat tidak make sense, sehingga tidak terlihat dengan jelas tujuan project yang menunjang ditjend planologi
Action:
1. Memperbaiki dan mendefinisikan kembali kerangka yang sudah ada supaya bisa flowing, karena memang pembahasan pada FGD sebelumnya tidak sampai detail dan mendalam. Next Technical Adviser akan datang untuk membantu meluruskan penafsiran yang project result framework.
2. Perlu minta orang lain yang tidak terlibat dengan penyusunan prodoc membantu review dan memberikan masukan berdasarkan persepsi dan pengertiannya
3. Melengkapi data kembali yang sesuai dengan kondisi eksisting dan memperjelas dasar untuk mendapatkan data/output yang ada sehingga lebih jelas
4. Memperjelas alokasi kegiatannya ditujukan untuk sektor apa?
5. Planologi: Jika tujuan project yang tidak sesuai dengan ditjen planologi lebih baik di scrap