# CARISECURE 1.0

Final Report (2016 – 2023)

United Nations Development Programme Barbados and the Eastern Caribbean

AID-538-IO-16-00001

SUBMITTED: FEBRUARY 2023

CariSECURE is made possible by the generous support of the American people through the United States Agency for International Development (USAID). The views expressed in this publication do not necessarily reflect the views of USAID or the United States Government.

# ​Contents

Acronyms and Abbreviations	5

1.0	Project Overview/Summary	7

2.0	Activity Overview	8

2.1	Project Background	9

2.2	Theory of Change	10

2.3	Executive Summary	11

2.4	Project Adjustments (Documented Changes)	13

3.0	Project Achievements by Outputs	18

3.1	Output 1: Standardized and disaggregated crime data reporting within and among national authorities to foster the reliance on valid, reliable and comparable data on citizen security.	18

3.2	Output 2: Utilization of evidence-based analysis of crime data to inform citizen security strategies, programmes and policies.	22

3.3	Output 3: Improved decision-making on youth crime and violence based on available evidence at national level.	25

3.4	Output 4: Trafficking in Persons (TIP)	25

3.5	Summary of Major Challenges	27

4.0	Final Country Updates	28

4.1	Barbados…… .	29

4.2	Grenada	30

4.3	St Vincent and the Grenadines	33

4.4	Antigua and Barbuda	34

4.5	Guyana			37

4.6	St Kitts and Nevis	40

4.7	St Lucia			42

4.8	Suriname	45

5.0	Sustainability Mechanisms	47

6.0	Progress on Implementation	53

6.1	OUTCOME 1: Standardized and disaggregated crime data reporting within and among national authorities to foster the reliance on valid, reliable, and comparable data on citizen security	53

6.2	OUTCOME 2: Reliance on evidence-based analysis of crime and violence data to inform national citizen security policymaking	65

6.3	OUTCOME 3 - Piloting of national citizen security policies and crime victimization surveys to facilitate gathering of survey data indicators, and the development of targeted policymaking to reduce likelihood of youth involvement in crime and violence.	68

6.4	TIP Indicators 	70

7.0	Challenges, Management And Administrative Issues	72

8.0     Lessons Learnt	75

9.0	Actions Taken In Response To Previous Aor/Cor Feedback	77

10.0	Additional Sections Per Your Agreement Or Contract	79

11.0	Annexes	80

11.1 Financials as of 31 December 2022	81

11.2  Summary of Indicator Results	81

11.2  Project Achievements	92

# Acronyms and Abbreviations

ACRO		Agency of Criminal Records

AOR		Agreement Officer’s Representative

ATLAS		Enterprise Resource Planning (ERP) system used by UNDP and other UN agencies

AWP		Annual Work Plan

BPS		Barbados Police Service

CARICOM	Caribbean Community

CDC		Center for Disease Control and Prevention

CIMS               	Crime Information Management Systems

CVDW		Crime Violence Data Warehouse (IMPACS)

CSI		Citizen Security Indicator

CSO 		Central Statistical Office

CSP		IADB Citizen Security Program

GIS		Geographic Information System

GPF		Guyana Police Force

ICCS		International Classification of Crime for Statistical Purposes

ICVS		International Crime and Victimization Survey

IADB		Inter-American Development Bank

IMPACS		Implementation Agency for Crime and Security

ICT		Information and Communications Technology

KPS		Korps Politie Suriname

M&E		Monitoring and Evaluation

OECS		Organisation of Eastern Caribbean States

PIF		Police Incident Form

POPP		Program and Operation Policies and Procedures

SRCO		Sub-Regional Crime Observatory

PRMIS 		Police Reporting Information Management System

RBPF		Royal Barbados Police Force

RPFAB		Royal Police Force of Antigua and Barbuda

RSLPF		Royal St Lucia Police Force

RSCNPF		Royal St Christopher and Nevis Police Force

RSVGPF		Royal St Vincent and the Grenadines Police Force

RSS		Regional Security System

SKNDF		St Kitts and Nevis Defence Force

SLNCVS		St. Lucia National Crime Victimization Survey

SDG		Sustainable Development Goals

SOP		Standard Operating Procedures

TOR		Terms of Reference

UNDP		United Nations Development Program

UNODC 		United Nations Office on Drugs and Crime

USAID		United States Agency for International Development

WHO		World Health Organisation

YES		Youth Empowerment Services

# Project Overview/Summary

| Programme Name: | CariSECURE – Strengthening Evidence Based Decision Making for Citizen Security in the Caribbean |
| --- | --- |
| Activity Start Date and End Date: | 14 July 2016 to 31 October 2022 |
| Name of Implementing Partner: | United Nations Development Programme (UNDP) for Barbados and the Eastern Caribbean |
| [Contract/Agreement] Number: | AID-538-IO-16-00001 |
| Name of Subcontractors/Sub awardees: | Governments of 8 Eastern and Southern Caribbean countries (Antigua and Barbuda, Barbados, Grenada, Guyana, St Kitts and Nevis, St Lucia, St Vincent and the Grenadines, and Suriname |
| Geographic Coverage (cities and/or countries) | Eight eastern and southern Caribbean countries (Antigua and Barbuda, Barbados, Grenada, Guyana, St Kitts and Nevis, St Lucia, St Vincent and the Grenadines, and Suriname) |
| Reporting Period: | 14 July 2016 to 31 October 2022 |

# Activity Overview

PROJECT TITLE: CariSECURE - Strengthening Evidence Based Decision Making for Citizen Security within the Caribbean

GOAL: To improve youth crime and violence prevention and response policymaking and programming in ten southern and eastern Caribbean countries using quality, comparable and reliable national citizen security information.

PROJECT OUTPUTS:

Output 1: Standardized and disaggregated crime data reporting within and among national authorities to foster the reliance on valid, reliable and comparable data on citizen security.

Output 2: Utilization of evidence-based analysis of crime data to inform citizen security strategies, programmes and policies.

Output 3: Improved decision-making on youth crime and violence based on available evidence at national levels.

PROJECT APPROACH: The Project relies on the Center for Disease Control (CDC) Public Health Approach to Violence Prevention. This model is comprised of four essential steps – (1) identifying the problem; (2) identifying risk and protective factors; (3) developing and testing prevention strategies; and (4) ensuring widespread adoption of these strategies.

PROJECT STRATEGY: The Project is one of three components under the broader USAID Youth Empowerment Services (YES) Project which aims to increase the institutional and technical capacity of regional bodies, selected national government systems and community stakeholders to reduce risk factors that drive youth crime, violence and victimization.

CariSECURE contributes to the achievement of this goal by strengthening the capacity of national and regional institutions in eight eastern and southern Caribbean states, to collect, analyse and rely on standardized and disaggregated citizen security data to develop targeted, evidence-based policies and programmes.

## Project Background

CariSECURE is a key activity under USAID’s larger Youth Empowerment Services (YES) Project. The purpose of the YES Project is to increase the institutional and technical capacity of regional bodies, select national government systems and community stakeholders to reduce risk factors that drive youth crime, violence, and victimization.  It has a specific goal of reducing youth involvement in crime and violence in target communities. Accordingly, the YES Project has three (3) expected results under its relevant Activities:

- CariSECURE Project – Strengthened Evidence-based Decision-making in Youth Crime and Violence Prevention Policy and Programming.

- Community, Family and Youth Resilience (CFYR) Project – Communities, families, and youth strengthened to withstand, mitigate, and recover from crime and violence.

- Juvenile Justice Reform Project (JJRP) – The rehabilitation and reintegration of youth in conflict with the law in society.

CariSECURE is a regional project executed across eight (8) countries: Antigua and Barbuda, Barbados, Grenada, Guyana, St Kitts and Nevis, St Lucia, St Vincent and the Grenadines, and Suriname. The project is implemented by the UNDP Barbados multi-country office in cooperation with UNDP Offices in Guyana and Suriname, with specific oversight from the UNDP Regional Bureau for Latin America and the Caribbean (RBLAC).

CariSECURE’s three (3) Approaches:

- National Approach – Led by stakeholders (National Task Force mandate) and facilitated by interagency protocols for sharing data

- Regional Approach – Standardized regional indicators, data platforms and crime analysis methodology and citizen security framework

- International Approach – International Classification of Crime for Statistical Purposes (ICCS), UN-Crime trends survey and the SDG 16

The primary objective is to improve national capacities in the beneficiary countries to collect citizen security data, based on an agreed set of core citizen security and juvenile justice indicators. The expected result of this is the availability of quality and comparable citizen security data that can be analyzed to inform the design and implementation of policies and programmes that aim to reduce crime and violence.

At the national level, the Project engaged partners and stakeholders including national security ministries, police forces and statistical offices. CARISECURE works with regional institutions such as the Regional Security System (RSS) and the Caribbean Community (CARICOM) Implementation Agency for Crime and Security (IMPACS). In the case of the former, the Project supported the establishment of a Regional Crime Observatory (RCO), while the latter serves as the regional data warehouse for the Police Records Management Information System (PRMIS) which was developed through the Project.

## Theory of Change

The Project’s Theory of Change illustrates that a disaggregated and standardized way of reporting and sharing crime administrative and survey data by and across national authorities will incentivize an ongoing reliance on this data. It is envisioned that this will foster a culture of evidence-informed approaches to citizen security policymaking generally, and youth crime and violence prevention more specifically. The pathway to this is through increased institutional and technical capacities of national governments for crime and violence prevention and protection of vulnerable groups.

Figure 1- Project Theory of Change Diagram

## Executive Summary

CariSECURE was an ambitious project in both scope and scale. Since its inception in 2016 to its closure in 2022, significant reshaping, adjustments and lessons learned and applied have taken place. However, fundamentally the project has succeeded in its core goal: laying the foundations for a robust and sustainable information management system on crime and citizen security data to inform policy, and fostering evidence-based decisions on youth crime and violence, with a special focus on gender-based violence.

More specifically, throughout its lifecycle and across its country footprint, the programme established a first-of-its-kind regional Citizen Security Toolkit and helped partner countries map nearly 10,000 offenses to international standards as a critical step to ensuring crime data comparability. With this extensive mapping completed, the programme brought together global technology expertise and regional skill to designed and develop a powerful crime data management system, capable of capturing and managing crime data and facilitating crime analysis and tactical decision-making at sub-national, national and regional levels. To institutionalize this platform at the national level, the programme  trained over 1,300 police officers in its use and empowered a dozen officers to undertake specialized crime data analysis.

Regarding the deployment of PRMIS, an independent Terminal Evaluation of the project surmised:

“Considering that actual implementation (of PRMIS) only started this year (2022) with Grenada, and had to confront several challenges, advances are remarkable, and prospects are positive. PRMIS is showing it will deliver. The leading countries, that had higher previous capabilities, are doing the harder trial and error inevitable in any ICT system, paving the way for the followers. One can expect faster learning curves for these. Country coordination challenges lay ahead, however nothing that the installed capabilities of actors cannot successfully address, under the umbrella of an adequate and vigorous sustainability strategy.”

The independent assessor also concluded that there were several successes beyond PRMIS, noting:

“…the project did not only consist of the installation of the PRMIS system, but also developed other activities that promoted the digitalization of information on crime in the participating countries. Also, the project worked on different initiatives to improve the availability of information, the analysis of knowledge about crime, and the possibility that public policies on citizen security are formulated more based on evidence.

Regionally, and in partnership with the Regional Security System, the programme supported the establishment of a Regional Crime Observatory to aggregate data across countries and identify opportunities for regional cooperation on crime response and prevention. The programme also focused on strengthening the region’s use of non-administrative data, including through the completion of St. Lucia’s first ever Crime Victimisation Survey that paved the way for decision-makers to understand the full extent of the national experience with crime.

As a multi-country programme with many activities, partners and objectives, CariSecure faced several challenges. The project suffered significant delays and modifications, most often due to factors outside of its control including major budget cuts, the impact of the COVID-19 pandemic, fluctuations in national ownership/engagement due to elections and changes in political momentum, and natural disasters. In this regard, the evaluation report confirmed that the project schedule and efforts were affected at various times by hurricanes (Dominica) and other force majeure (eruption of Soufriere volcano in St Vincent and the Grenadines) and by the COVID pandemic (both in terms of in-person interaction and travel and the adverse effect on supply chains which significantly delayed the rollout of PRMIS). High staff turnover and – in the latter part of project activities – reduction in the number of core staff, all of which severely affected delivery.

Ultimately, these impacts slowed progress, but did not prevent the programme from achieving many of its targets and CariSecure was able to deliver on its promise to set the foundations of full digitalization of police operations, and full statistical standardization of crime data, that can be available at the regional level.

## Project Adjustments (Documented Changes)

2018

CariSECURE was originally designed and approved with a US$14 million budget to implement its activities. However, financial constraints and budget cuts across all YES Projects led to a reduction of the CariSECURE award from US $ 14M to US $ 9.5M (a 32% reduction), necessitating a substantive revision of the programme. This revision reduced the scale and scope of project activities in line with the reduced funding envelope for the Award and was completed and approved by the Project Board in November 2018.

These significant modifications included a reduction in the number of target countries from ten (10) to eight (8), a reduction in the number of national beneficiaries from five (5) to three (3) in each country (Police, Prisons, Director of Prosecutions), and the elimination of some key activities, leading to revised project outputs and indicators. The proposed realignment did not alter the strategic focus on youth but allowed a more targeted focus with unique in-country stakeholders for ensuring the realization of the project’s outputs. Specifically, it was decided that, using a phased approach, the project would focus firstly on the police by piloting a police incident form (PIF) that would later be expanded into a complete Police Reporting Management Information System (PRMIS) in at least two pilot police stations and police headquarters in each country. Phases two and three would roll out similar systems for both the Prison Service and Director of Public Prosecutions Office.

In deciding which beneficiary countries would no longer remain direct beneficiaries of the programme, it was necessary to strategically focus reduced resources in countries where the demand and pace of implementation could be optimized in realizing the project outputs.

Despite endorsements of the original Project Document by Trinidad and Tobago on 13 March 2017, the level of national ownership of, and engagement with, the programme was comparatively low. Based on this, and in consultation with the Donor, the decision was made that it was no longer practicable to include Trinidad and Tobago as a beneficiary. In the case of Dominica, the Project faced a significant setback following the passage of Hurricane Maria in September 2017, which devastated most of the island. As a result of prioritizing recovery efforts in Dominica, CariSECURE was unable to progress further in that country and it was therefore removed as a beneficiary.

2020

At the end of 2019, USAID expressed concern that, while eight countries had formally (publicly) announced support for the PRMIS and began piloting the police incident form, the project had only 10 months remaining, with only one of three phases partially rolled out, a high pipeline and consistently low burn rates. Consequently, USAID requested the implementing partner to submit three project scenarios for consideration that included a further $1M budget cut, no cost, and costed extension options. The scenario options were received on 24 January 2020. USAID then conducted a Rapid Assessment during the period 24 January to 6 March 2020 to five beneficiary countries: Antigua and Barbuda, Grenada, St Lucia, St Kitts and Nevis, and St Vincent and the Grenadines. Site visits to the remaining countries were prematurely terminated due to the COVID19-related travel restrictions in the region.

Specific findings of this assessment included a recognition of the complexity and labor intensity of rolling out the PRMIS activity and the great impact of project procurement delays. The exercise concluded several in-country challenges were stymieing project progress, including:

- Limited evidence of a proactive approach being adopted to manage or mitigate risks

- Low country capacity and technical expertise to fully support project activities

- Insufficient and poor communication seemingly contributing to unrealistic expectations (For example, there was widespread confusion and misgivings about the police incident form, which was only one module of the wider PRMIS. These misunderstandings resulted in complaints about system inadequacies.)

- Senior government officials with very superficial knowledge of what was being delivered and their responsibilities in addressing network issues, preventing operationalization of the software

- Frustration from other project stakeholders such as the Prison Services and Directors of Public Prosecutions (DPP) over delays in receiving their system or lack of awareness of the systems they were going to receive

It also noted "a sparse, but highly skilled project team with two critical leadership project positions being vacant (Team Leader, and Deputy Team Leader) and a high turnover of other key project staff.”

Overall, the assessment found that it was

“…highly unlikely that the project will succeed under [the] existing contractual timeline and available funds. Furthermore, given the high level of time investment required by the project to complete phases two and three (software for both prisons and DPP) this may require a substantial amount of additional time, no less than 24 months extension which is not allowable under USAID’s current RDCS ending December 2020. Additional funding would also be required, which is not currently available. Consequently, it is recommended that CariSECURE receives an extension of twelve 12 months, with a new end date of September 30, 2021. Funding allocation of $1M should be issued from FY19 funds (by July 2020) and along with existing project pipeline funds estimated at $1.2 (as at March 30 2020) totaling $2.2M”

The findings of the rapid assessment were augmented by a subsequent internal Country Readiness Assessment which assessed and categorized beneficiary countries based on their level of commitment, institutional capacity, and competency. Based on these two analyses, the project pivoted from the original Priority Country Approach (which prioritized Guyana, St Kitts and Nevis, and St Lucia) to a Tiered Approach, based on the level of commitment and capacity existing in each beneficiary country. This approach recognized that benefits could be amplified if there was significant commitment to the implementation of the project at the national level, therefore allowing more ‘buy-in.’ It is important to note that this tiered approach gave a systematic structure to the phased deployment of the PRMIS platform to regional beneficiary countries, but all beneficiary countries would receive and benefit from CariSECURE’s PRMIS platform.

Table 1: Matrix of Proposed Tier System for Beneficiary Countries

| Tier | Country | Project Support | September 2021 |
| --- | --- | --- | --- |
| 1 | Grenada, Barbados, St Vincent and the Grenadines | Additional investment of ICT to 75% of police stations and mobile technology for Police; Training and technical support for police applications. | - Signed commitments secured from Tier 1 countries’ governments to complete the roll out of ICT prior to the project’s investment - Additional investment of ICT to police stations and mobile technology for the widespread use of the PRMIS platform - Data sharing agreements with RSS (SRCO) and CARICOM IMPACS approved and signed with countries capable of producing crime analysis data/ using data to inform policing strategies - Deployment of the PRMIS and relevant Training - Signed government approval of tailored sustainability plans for Tier 1 Countries |
| 2 | Guyana, Saint Kitts and Nevis, Antigua and Barbuda | Production of ICT Roadmaps; Training and technical support for police applications; Assistance to secure donor funding to roll out applications in police stations beyond the pilots | - Funding Support leveraged from donors and partnerships to rollout PRMIS to additional Police stations - ICT Roadmaps - Data sharing agreements with RSS (SRCO) & CARICOM IMPACS approved and signed with countries capable of producing crime analysis data/ using data to inform policing strategies - Deployment of the PRMIS and relevant Training |
| 3 | Suriname | Production of ICT Roadmaps; Training and technical support for police applications; Assistance to secure donor funding to roll out applications in police stations beyond the pilots | - Funding Support leveraged from donors and partnerships to rollout PRMIS to additional Police stations - ICT Roadmaps - Data sharing agreements with RSS (SRCO) & CARICOM IMPACS approved and signed with countries capable of producing crime analysis data/ using data to inform policing strategies - Deployment of the PRMIS and relevant Training |

Based on the review exercise, a second strategic realignment was approved in July 2020 to extend the project duration to 30 September 2021, reduce the fund award to US$9,165,000.00 (a further 2% reduction, and to reduce the number of national beneficiaries from three (3) to one (1) in each country. During this strategic realignment, discussions with USAID led to an agreement that CariSECURE would extend support to Barbados in the area of Trafficking in Persons (TIP), reflecting the needs identified in the US State Department Trafficking in Persons report.

In August 2020, and due to the impacts of the COVID-19 global pandemic on the Information Communication Technology (ICT) supply chain, a further extension was approved to 30 September 2021 which included an agreement to incrementally fund the award in the amount of US$1,450,000.00 for the total obligated amount of US$9,165,000.00, along with an update to the programme description.

Two subsequent modifications, the first a 7-month extension to April 2022 and a request for US$200,000 additional funds towards the delivery of PRMIS and the second US$600,000 extension through to October, 2022, were approved to ensure the full deployment of PRMIS, allow the continuation of work with national counterparts to expand data use in advocacy and decision-making and also allow for the continuation of work within Barbados in trafficking in persons (TIP).

These extensions also allowed adequate time to mitigate the risk associated with delays to the PRMIS centralized solution at CARICOM IMPACS, while also presenting an opportunity to partner with RSS to bolster national crime analysis capacity and standardize crime analysis reporting in the beneficiary countries where crime analysis units were established. Additionally, sustainability measures focused on extending the PRMIS Service Level Agreement (SLA) with the software vendor and addressing some of the national level gaps identified in the sustainability framework and ICT Roadmaps that would support the deployment and uptake of the PRMIS system.

# Summary of Project Achievements by Outputs

## Output 1: Standardized and disaggregated crime data reporting within and among national authorities to foster the reliance on valid, reliable and comparable data on citizen security.

CariSECURE Toolkit

Arising from CariSECURE’s Regional Data Collection Conference in Year 1, the Caribbean Citizen Security Toolkit was developed. This Toolkit emphasizes citizen security data collection, sharing, and evidence-based policymaking. It includes the Caribbean Composite Citizen Security Indicator Framework (CCSIF); the Citizen Security Data Collection Form and Coding Structure; Information Sharing Agreement; and the Guidance Notes on Citizen Security Data Collection and Dissemination.

The finalization of the Toolkit was a milestone achievement for the Project as it was the first package of this nature to be designed specifically for the Caribbean and, in its development, saw collaboration between ten (10) Caribbean governments, the Caribbean Community (CARICOM Secretariat), CARICOM IMPACS, the CARICOM Advisory Group on Statistics (AGS), the Regional Security System (RSS), the OECS, USAID partners and UNDP.

The collection of instruments within the Toolkit provided governments with the tools to enhance the quality, integrity, and accuracy of citizen security data through improved data collection processes. Their use also increases the capacity of governments to accurately monitor citizen security and, by extension, the effectiveness of crime reduction and prevention strategies. CariSECURE’s Citizen Security Toolkit was endorsed by all beneficiary countries.

Standardization and the ICCS

To facilitate one of CariSECURE’s main objectives of data standardization to support across the subregion, the Project supported the development of tables of equivalencies to map criminal offences in each country to the International Classification of Crimes for Statistical Purposes (ICCS). The ICCS is the first international classification of crime for statistical purposes. It is built on behavioural descriptions and not on legal code, hence it is applicable across jurisdictions. The ICCS is also a tool to understand crime patterns and characteristics and the implementation of the ICCS improved data consistency within and between countries.

CariSECURE held a Regional ICCS Workshop in September 2018 to build the capacity of national counterparts in the mapping process required for the development of correspondence tables. Through the support of CariSECURE, national ICCS working groups in eight (8) countries mapped over 9,000 criminal offences to ICCS categories to develop draft ICCS correspondence tables for each country. These tables aid with standardization and provide a means for comparing crime statistics regionally and internationally. The ICCS correspondence tables have also been integrated into the backend of the digital policing applications – the Police Incident Form (PIF) and the Police Records Management Information System (PRMIS) – developed through the CariSECURE Project.

PIF, PRMIS and the CVDW

CariSECURE also delivered two digital policing platforms for beneficiary countries. The Police Incident Form (PIF) was developed and deployed during Year 4 as an application for capturing police incident data and preparing police forces for the transition from paper to digital. The application’s user interface was broadly based on the fields from CariSECURE’s Data Collection Form and Coding Structure that formed part of the Citizen Security Toolkit. PIF was piloted in all beneficiary countries. Insights and lessons learned from the deployment and use of the PIF by police forces were subsequently used in the deployment plans for CariSECURE’s robust policing application, the Police Records Management Information System (PRMIS).

The development process for the PRMIS application, which commenced in 2020, included a current state analysis of existing policing systems, followed by phases of requirements gathering, technical design and review, user acceptance testing, validation and handover. CariSECURE began the delivery of PRMIS for regional police forces in the final quarter of 2021.

PRMIS, in its final iteration, systematizes forms and workflows to gather crime incident data and is bolstered in the backend by countries’ International Classification of Crime for Statistical Purposes (ICCS) Correspondence Tables to support further standardization of offence data for regional comparison.

Over the course of its development, PRMIS was tested by police readiness teams, administrators and users, and was found to meet the requirements of the police in six (6) of the seven (7) beneficiary countries for which it was intended, namely Antigua and Barbuda, Barbados, Grenada, Guyana, St Kitts and Nevis, and St Vincent and the Grenadines. In total, approximately 1,100 officers from the aforementioned countries were trained in data collection and crime analysis in preparation of the national launches of PRMIS. In addition, 31 officers were trained as trainers to support sustainability.

The Crime Victimization Data Warehouse (CVDW) at CARICOM IMPACS is another significant achievement of CariSECURE. The CVDW hosts the PRMIS application and provides a centralized solution for the housing of country crime data.

The CVDW was formally established through an MOU signed between USAID and CARICOM IMPACS during CariSECURE’s Citizen Security Conference of September 2021. The MOU outlined the areas of collaboration around the provision of data security, data management and warehousing support for beneficiary countries. Equipment for the CVDW was received by IMPACS in mid-2022. Installation and configuration of servers was completed, and countries are able to connect to PRMIS through the CVDW.

As of 31 October 2022, five (5) of the beneficiary countries had deployed PRMIS. Of these, all three (3) of the Tier 1 countries were collecting live data through PRMIS to varying degrees. Specifically, in Grenada, where a national instance of the PRMIS system was piloted, the application was deployed in over 75% of the police Stations, exceeding its target as a Tier 1 Country. In Barbados, another Tier 1 jurisdiction, 58% of the stations are live and in St Vincent and the Grenadines, 10% of stations have deployed the application. Among Tier 2 countries, in St Kitts and Nevis, 21% target stations operationalized the live connection to the CVDW. Notably, Antigua and Barbuda, a Tier 2 country has reached 100% deployment of PRMIS. All other beneficiary countries are at various stages of preparations to begin live data inputs.

As a sustainability measure for PRMIS, ICT Roadmaps were developed by the Project. These Roadmaps, which chart the way forward for continued digitalization of crime and violence data in the police forces, were presented to national technical experts in all beneficiary countries for validation and have been officially shared with senior officials for endorsement. As of 31 October 2022, the ICT Roadmaps for Antigua and Barbuda and Suriname had been officially endorsed.

As a further element of the sustainability of the Project, the PRMIS platform has been assessed by the Digital Public Goods Alliance and is now on track to becoming a global UNDP Digital Public Good.

Citizen Security Conference

The CariSECURE Citizen Security Conference was hosted over a period of two days from 31 August to 1 September 2021 via a virtual conferencing and hybrid events platform, made necessary by the COVID pandemic. It consisted of a series of live events, meetings and round table discussions with a variety of targeted project beneficiaries, partners, stakeholders and donors. High-profile activities included Memorandum of Understanding (MOU) signing ceremonies between USAID and the Regional Security System, as well as CARICOM IMPACS, the launch of two regional crime observatories and a regional crime data warehousing solution.  Citizen security experts provided information and best practices on evidence-based decision making though panel discussions with moderated Q&A sessions.

The conference was used to highlight CariSECURE’s achievements, and the products developed through the project, while providing a forum to share knowledge, experiences and lessons learned as well as opportunities for collaboration within the context of strengthening evidence-based decision-making in the region’s citizen security sector. Virtual information booths allowed project beneficiaries to display project results and literature, and to perform software demonstrations.  The virtual conference saw over 400 participants registered and over 20 speakers and presenters from the regional citizen security sector engaged for this event.

The event had the following outcomes:

- Increased understanding of the contribution of CariSECURE, its donors and partners in strengthening systems for crime and violence data collection and evidence-based decision making for citizen security in the region;

- Improved stakeholder knowledge of CariSECURE’s tools, lessons learned and approaches for institutionalizing the culture of data-driven decision making in the citizen security sector;

- Strengthened alliances and collaborations among regional and international agencies towards post-project sustainability measures;

- Support leveraged from donors and partners for select beneficiary countries to expand the Police Reporting Management Information Service (PRMIS) and use of CariSECURE tools.

## Output 2: Utilization of evidence-based analysis of crime data to inform citizen security strategies, programmes and policies.

Assessments

During the project’s first year, three (3) comprehensive assessments in the form of comparative cross-sectional case studies were executed. The first focused on the legal and regulatory environment that circumscribes administrative data sharing among the core entities of the criminal justice system. The second assessment focused on the institutional capacities of these core entities as well as others such as National Statistical Offices – these institutions constituting the mechanisms by which administrative and survey data are managed. The third assessment made the shift towards crime prevention and sought to audit crime prevention policies, programmes, and strategies in the countries, to determine how the Project could strategically give assistance in this regard, specifically to youth crime and violence prevention.

Belize Study Tours and Knowledge Exchanges

The project’s first study tour and technical exchange took place in Belize from the 27 to 29 March 2017 with participants from Antigua, Barbados, Grenada, Guyana, St Kitts & Nevis, Saint Lucia, St Vincent and the Grenadines, Suriname and Trinidad and Tobago. The tour exposed participants to the processes and practices in Belize that support automated data collection, analysis, and sharing amongst government agencies and with the public. It also offered participants key opportunities to learn more about the data sharing capacities of the Police Information Technology Unit, the Belize City Prosecution Unit; the National Forensic Science Services; the Belize City Crime Analysis Unit; the National Security Council Secretariat; the Joint Intelligence Coordinating Centre; and the Ministry of Human Development, Social Transformation, and Poverty Alleviation.

To incentivize knowledge exchange and sustainability for the participants, the methodology was to split the group into three (3) working Groups; Data/Statisticians; Policing; and Policy. These groups were invited to give feedback and suggestions at the end of each day for CariSECURE to obtain more specific information on how best to target its project activities relevantly at the national level. The key feedback from these groups centred on the need to have a crime-reporting database that is shared by all via a network, and which permits access by different users. They all agreed that this would constitute the backbone for incentivized data sharing among national and regional authorities and foster a reliance on evidence-based approaches. This key feedback allowed CariSECURE to embark with confidence on the design and deployment of subsequent tools and products including the PIF and PRMIS.

Following the success of the tour, which was targeted at the technical officer level, discussions with national counterparts led to the organization of an additional high-level tour to Belize, targeting Ministers with responsibility for National Security and their Permanent Secretaries from the USAID priority countries. A two-day ministerial exchange was hosted by the Government of Belize and CariSECURE from 28-29 August 2017. This enabled the Ministers and their Permanent Secretaries to see firsthand the work being done in another CARICOM Member State to make decisions through quality and reliable citizen security statistics and analysis.  During this technical exchange, participants were able to observe the decision-making processes of agencies within the criminal justice system in Belize responsible for the collection, processing and dissemination of citizen security data, and to engage in high-level discussions with their Ministerial counterparts on some of the evidence informed polices, strategies and initiatives being implemented to reduce youth crime and violence in communities in Belize, as well as share some of their lessons learnt from the experience.

Arizona High-Level Citizen Security Study Tour

This tour took place from 15 to 17 May 2018 in two cities in Arizona – Phoenix and Chandler and participants included Ministers of Home Affairs and National Security from St Lucia and Guyana; Permanent Secretary of the Department of Home Affairs and National Security for Saint Lucia; Commissioners of Police from St Vincent and the Grenadines, St Kitts and Nevis, and Guyana; and the Executive Director of the Regional Security System (RSS).

Featured sessions included discussions with the Phoenix Mayor and members of Chandler’s City Council on the benefits of using police data in the development of city laws. Participants also attended meetings with Phoenix and Chandler’s Police Chiefs to find out how executive leadership interprets data and uses it to create strategy and policy. In a session with Crime Gun Intelligence Center staff, they learned how the agency synthesizes its crime gun intelligence and data to make case-level decisions and broader strategies to combat gun crime. They also explored police open data initiatives as landmark examples which could be used to model their own CIMS.

Regional Crime Observatory and Crime AnalysisCariSECURE provided technical support and equipment towards the establishment of the Regional Crime Observatory at RSS. As a first step to the establishment of the RCO, the Project designed and shared terms of reference and an organigram and procured equipment for a three-member regional crime observatory. The RCO, which was formally launched during CariSECURE’s Citizen Security Conference in September 2021, has been staffed, commenced the gathering of crime and violence data from RSS member states and created its first, region-wide situation report which provides a standardized comparative crime analysis of its member states for the year 2020. This report is the first of its kind in the region and signals the first step toward filling regional crime data gaps by statistically benchmarking the regional crime landscape.

The Project also made strides in building capacity towards the institutionalization of crime analysis regionally. Under CariSECURE, 32 participants from nine (9) countries as well as RSS and IMPACS completed a crime analysis training programme facilitated by Arizona State University’s (ASU) Center for Violence Prevention and Community Safety. Additionally, five (5) participants from RSS and IMPACS completed a separate Training of Trainers session with ASU which focused on crime analysis and adult learning, to prepare them for roles in facilitating regional crime analysis training. Antigua and Barbuda, Grenada, St Kitts and Nevis and St Vincent, and the Grenadines have endorsed the formation of crime analysis units within their police forces and CariSECURE provided ICT equipment and software (SPSS licenses) to support the formation of these units.

The linkages to catalyze the institutionalization of crime analysis have been bolstered by the combined efforts of CariSECURE and the RCO at RSS. In partnership with the RCO, crime analysis training for 31 police officers across Grenada (12), St Kitts (13) and St Vincent (6) was held during August and September 2022. Antigua and Barbuda, Grenada, St Kitts and Nevis, and St Vincent and the Grenadines have committed to the formation of crime analysis units within their police forces and CariSECURE provided ICT equipment and software to support the continued functioning of these units.

## Output 3: Improved decision-making on youth crime and violence based on available evidence at national levels.

Use of Non-Administrative Data

Through the support of CariSECURE, St Lucia became the first country in the English-speaking Eastern Caribbean to conduct a crime victimization survey (CVS) using United Nations international standards. The 2020 St Lucia National Crime Victimization Survey (SLNCVS) surveyed over 1,700 households to establish the prevalence of victimization and offences; crimes reported to the authorities; perceptions of safety; the impact of crime on society and the level of public confidence in the criminal justice system within the population.

The St Lucia National Crime Victimization Survey (SLNCVS) also served as a reference and guidance document for the development of St Lucia’s Youth Policy Action Plan (draft).  This was achieved through CariSECURE’s sharing of recommendations for citizen security with St Lucia’s National Task Force and the consultants for St Lucia’s 2022 Youth Policy Action Plan. The recommendations were developed from the results of the SLNCVS and a review of available administrative crime data.

CariSECURE also collaborated with the Statistical Bureau of Guyana, UNWOMEN and IDB on the Guyana Women’s Health and Life Experiences Survey 2018. The Survey is the first report to provide a comprehensive examination of the nature and prevalence of violence against women and girls in Guyana. The data from this survey was referenced for the development of Spotlight Guyana, which delivers evidence-based programmes that prevent and respond to violence against women and girls. It has also been used by UNICEF as background for legislative and policy reform under Spotlight Regional and for specific review of domestic violence acts and other work such as drafting laws on harassment.

## OUTPUT 4: Trafficking in Persons (TIP)

Following discussions with USAID related to the Project’s extension in 2020, CariSECURE extended their support to Barbados in the area of Trafficking in Persons (TIP). More specifically, CariSECURE supported activities in Barbados focused on addressing Trafficking in Persons (TIP) in order to improve the country’s Tier 2 Watch List standing on the US State Department’s TIP Report. The collaborative efforts of the Government of Barbados, CariSECURE, and other key partners on TIP have enabled Barbados to improve its standing on the most recent US TIP Report.

The Government of Barbados, through the Office of the Attorney General, has been able to implement several activities targeted at building capacity of actors within the criminal justice system to tackle the issue of trafficking in persons. These interventions included building capacity among 66 Barbados Police Service (BPS) officers in basic (51) and advanced (15) TIP identification and investigative techniques.

CariSECURE also commissioned the TIP Knowledge and Perception Survey in Barbados in July 2021. The survey report of September 2021 examined the levels of awareness and knowledge concerning human trafficking, perceptions, views and attitudes towards human trafficking and victims, suggested recommendations to tackle the problem of human trafficking locally, and presented key informational and educational needs. In February 2022, Barbados’ Anti-Trafficking National Task Force launched a public education campaign, publicly presenting the results of this survey.

CariSECURE also completed additional work in October 2022 around the development of standard operating procedures (SOPs) for TIP and training for police and key agencies on these SOPs.

## Summary of Major Challenges

Over the lifetime of the project, a number of challenges delayed and hindered the Project’s timely delivery of key activities and achievement of targets. Donor funding limitations significantly reduced the available budget and narrowed the scope and reach of the Project and resulting in a strategic realignment in 2018.

Natural disasters including hurricane Maria which hit Dominica in September 2017, and the eruption of La Soufrière volcano in St Vincent and the Grenadines in April 2021 also affected project delivery in a number of ways, including the need for national governments to redirect human resources towards disaster relief and recovery efforts. In the case of Dominica, as mentioned above, this resulted in the country being removed from the project entirely.

Additionally, the combined impact of the COVID-19 pandemic and the Russia-Ukraine conflict on global supply chains, particularly for ICT equipment, created substantial delays in the shipment of hardware necessary for police forces in the Project’s Tier 1 countries, crime analysis units and most critically the CVDW at CARICOM IMPACS. Travel restrictions and physical distancing protocols also prevented planned face-to-face activities and further delayed some activities including training and capacity building sessions, PRMIS requirements gathering, training and testing, among others. National level challenges, including lingering impacts from climate related events, coupled with national elections and shifting local priorities also proved to be major hurdles.

In terms of the Project Management Unit, high staff turnover negatively affected project delivery and institutional memory during the life of the project. Indeed, the USAID Rapid Assessment Report noted that “As at January 2020, there was still a significant amount of work outstanding to complete phase one, as well as commencement of phases two and three; a sparse, but highly skilled project team with two critical leadership project positions being vacant (Team Leader, and Deputy Team Leader) and a high turnover of other key project staff.”

CariSECURE mitigated some of the impacts of these challenges through an adaptive management approach.

The continuation of the virtual strategy established during the pandemic allowed for the Project team to maintain engagement with stakeholders and conduct training (of trainers and users) and testing sessions for PRMIS. Moreover, and notwithstanding the delays to the arrival of equipment for the CVDW at IMPACS, CariSECURE was able to work with partners to deploy alternative virtual spaces for testing and training for the roll-out of PRMIS. The Project Team deepened their collaboration with national stakeholders, particularly readiness managers, engaging them on a weekly basis to identify and provide remote support quickly in instances where there were gaps. Meanwhile, a series of national in-person monitoring missions delivered in-person capacity building and support at key stages of PRMIS development and deployment to maximize the uptake of the application. This work included collaborating with the Regional Security System (RSS) to deploy in-country refresher training and bolster the momentum of the programme.

# Final Country Updates

TIER ONE COUNTRIES

Tier 1 countries are those that have demonstrated high commitment, high capacity, and high competency. CariSECURE has assessed these countries to be Grenada, Barbados, and Saint Vincent and the Grenadines.

## Barbados

| Barbados |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 1722 |
| Personnel Trained on Crime Analysis | 2 |
| Police Officers Trained on PRMIS | 375 |
| No. of Stations with PRMIS Deployed | 7 |
| Police Officers Trained on TIP (Basic) | 51 |
| Police Officers Trained on TIP (Advanced) | 15 |

The Government of Barbados officially endorsed CariSECURE in 2016 and the CariSECURE Toolkit in 2018. As a Tier 1 beneficiary of CariSECURE, Barbados received additional equipment to facilitate the deployment PRMIS at police stations throughout the country. Through support from CariSECURE, Barbados also successfully completed their ICCS correspondence table, which mapped 1722 criminal offences to the international classification.

Three (3) officers from the Barbados Police Service (TBPS) also completed CariSECURE's Crime Analysis Training Programme in 2020. They produced a strategic crime analysis report, focusing on homicides recorded in Barbados between January 2010 and December 2019. This report provided a comprehensive examination of the age grouping, gender and weapons used in the commission of the homicides for the period under review. Further analysis was conducted on the homicide rates, station districts and stations relating to the homicides.

CariSECURE also procured and delivered ICT equipment to TBPS during Y6 Q1, to support the implementation of PRMIS in police stations throughout the island. The BPS received 14 workstations, 14 monitors, 14 power supplies, 7 black laser printers and 22 tablets. TBPS officers also participated in PRMIS training of trainers and administrators in 2021 and regional PRMIS training exercises in Y6 Q2 (March 2022).

Major progress was made during the final year of implementation, with PRMIS-readiness advanced and additional officers trained.  All twelve (12) police stations were assessed as PRMIS-ready and five (5) officers from the Barbados Police Service (BPS) were trained as PRMIS trainers. By the close of the Project, seven (7) stations had commenced inputting live data into PRMIS. Despite the progress on PRMIS deployment in Barbados, implementation was delayed as a result of an increase in violent crimes, in particular gun-related incidents, which resulted in reallocation of personnel and resources away from programme implementation. Nonetheless, by the end of the reporting period, BPS PRMIS trainers had trained 375 officers on the application with an additional 20 officers scheduled to be trained on a weekly basis.

During Y5 and Y6, the CariSECURE Project provided special support to Barbados in the area of Trafficking in Persons (TIP). During Y5 Q4, 51 Officers from the Barbados Police Force (TBPS) completed UNODC-facilitated basic TIP training, while 15 Officers completed advanced TIP training in Y6 Q1. Furthermore, the Project collaborated with the Office of the Attorney General in Barbados to conduct a TIP Knowledge and Perception Survey, the results of which provided insights into the public's awareness and perceptions of TIP, which were subsequently used to inform the development of public education products and materials around TIP. In March 2022, the Government of Barbados launched a TIP public education campaign. As a result of the collaborative efforts of the Government of Barbados, CariSECURE and other key partners on TIP, Barbados was able to improve its standing on the most recent US TIP Report.

FINAL STATUS: BARBADOS

At the end of project, out of a targeted nine (9) stations, PRMIS was live in seven (7). This was due in large part to the delays in the deployment of PRMIS to the CVDW, coupled with personnel originally working on PRMIS deployment being redirected by the Police Commissioner in order to address an unprecedented spike in crime during the Project’s final year.

Additionally, internal challenges, resource constraints and insufficient equipment (such as computers), resulted in CariSECURE hardware intended for the rollout of PRMIS at police stations being used at central locations for training of officers on the use of the application. This created a delay in the deployment of the equipment to targeted police stations.

Furthermore, while 22 mobile devices and vehicle mounts were supplied to enable BPS officers to access PRMIS in the field, the BPS put a greater emphasis on training and deploying the system to stations, with field deployment considered a secondary priority to be undertaken following the application’s deployment to stations. The inability to deploy PRMIS to mobile devices was also due to the previously mentioned resource constraints including the cost implications of providing data bundles, which had not been factored into the annual police budget.

Despite this, CariSECURE aided the BPS in their efforts to deploy PRMIS to as many stations as feasible. The Project supported the formation of a communication plan that would help with both internal and external communication related to the PRMIS implementation, and to generate support from all ranks. Moreover, valuable feedback and lessons learned from the PRMIS pilot in Grenada were shared with police leadership during introductory meetings with the new Police Commissioner and the readiness team.

CariSECURE also presented the ICT Roadmap for Barbados to the Office of the Attorney General, the national task force and key representatives at the technical level who were supportive of the document and its contents.

## Grenada

| Grenada |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 1157 |
| Personnel Trained on Crime Analysis | 2 |
| Police Officers Trained on PRMIS | 241 |
| No. of Stations with PRMIS Deployed | 11 |
| Police Officers Trained on TIP (Basic) | NA |
| Police Officers Trained on TIP (Advanced) | NA |

Grenada endorsed the CariSECURE Project in 2016 and the CariSECURE toolkit in 2018. Grenada is a Tier 1 beneficiary country under the Project and has become CariSECURE’s flagship country due to its displayed level of commitment. The country completed its draft ICCS correspondence table and mapped 1157 local offences to the international crime classification framework.

In 2020, two (2) officers from the Royal Grenada Police Force (RGPF completed CariSECURE's Crime Analysis Training Programme, with an additional ten (10) officers receiving crime analysis training in 2022, from the regional trainer at RSS, through support from CariSECURE. The RGPF also endorsed the establishment of a crime analysis unit which is housed at the Criminal Records Office in St Georges. To support the unit, CariSECURE supplied the RGPF with four (4) workstations with accompanying monitors, one (1) laptop, four (4) Uninterruptible Power Supplies (UPS) devices for power supply, one (1) Network Attached Storage (NAS) for storage, two (2) laser colour printers, and a projector. Additionally, a two-year subscription to SPSS was provided to assist the unit in their data analysis needs.

Grenada was also at the forefront of CariSECURE’s efforts to transition police forces to digitized incident recording and the RGPF was able to deploy the PIF application in 100% of its stations. It was noteworthy that CariSECURE’s support of Grenada’s PRMIS transition not only contributed to the country exceeding the Tier 1 target of transitioning 75% of police stations to PRMIS and building extensive local capacity within the Royal Grenada Police Force (RGPF) for data capture and analytics, but the national programme also provided substantial insights on PRMIS’ functionality in the field, allowing developers to make necessary changes, bug fixes, and improvements that benefited the wider region.

By the end of October 2022, eleven (11) of the fourteen (14) police stations were fully transitioned to PRMIS. To support this, eleven (11) police executive members including the Commissioner were trained on the use of PRMIS and 80% of station commanders and divisional commanders have been trained on the platform. Fourteen (14) RGPF officers were trained as trainers, and the readiness team was proactive in the implementation of their training plans and awareness building efforts. The RGPF took the initiative to develop training materials and knowledge documents including a training guide and printed manual on PRMIS specifically geared to Station and Divisional Chiefs, the Police Commissioner, and his upper command. The documents provided an overall system approach and offered key insights on all aspects of the platform and samples have also been shared with readiness teams from other islands to support their roll out and training efforts.

These achievements built on a strategic pilot that took place during the earlier part of 2022 to mitigate against the COVID 19-induced delayed delivery of equipment for the CVDW at CARICOM IMPACS. The pilot involved a local, rather than regional, installation of the PRMIS application at the national data center which was found to be adequately equipped for the deployment of the application. As mitigation, the St Georges, St David’s, and Sauteur’s Police Stations commenced with PRMIS piloting in Y6 Q1 and PRMIS was officially launched in Grenada at an event held during February 2022.

The pilot provided the opportunity to finetune the technical, ICT-related aspect of deployment and to document lessons learned and best practices for the implementation of PRMIS. The RGPF’s deployment efforts included a focus on training.

FINAL STATUS: GRENADA

At the end of project, Grenada achieved its target for PRMIS deployment to eleven (11) police stations. The successful deployment of PRMIS in Grenada was the result of the collaborative efforts of the Project and national counterparts who worked in tandem to ensure the target was met. Grenada also had the added advantage of starting the piloting of PRMIS earlier than the other countries owing to an existing national data center with the capacity to house the application. There have been some challenges with the deployment of PRMIS in stations off the mainland, for example Petit Martinique. However, the Project’s end, the general outlook for the full deployment of PRMIS in Grenada was positive.

The vocal support of the Commissioner of Police for the CariSECURE Project and data driven policing in general was a catalyst to the RGPF’s uptake of PRMIS. Additionally, the RGPF’s level of commitment was also evident in the initiative shown by the readiness team, who developed training materials for ranks and station chiefs, hosted interactive virtual training sessions for officers and developed communications products around PRMIS that have been used as a best practice

## St Vincent and the Grenadines

| St Vincent and the Grenadines |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 480 |
| Personnel Trained on Crime Analysis | 2 |
| Police Officers Trained on PRMIS | 161 |
| No. of Stations with PRMIS Deployed | 2 |
| Police Officers Trained on TIP (Basic) | NA |
| Police Officers Trained on TIP (Advanced) | NA |

In 2017, St. Vincent and the Grenadines officially endorsed the CariSECURE Project, and in 2018 they endorsed the project's Citizen Security Toolkit. CariSECURE also provided technical assistance to support the completion of the country’s ICCS correspondence table which mapped 480 offences to the international classification. Additionally, the Project deployed the Police Incident Form (PIF) and subsequently the Police Records Management Information System (PRMIS) and trained 161 officers on the application.

In 2019, CariSECURE installed a server at the RSVGPF headquarters to facilitate the introduction of PIF. A local internet service provider was engaged to deploy a government WAN to connect pilot locations to police headquarters and testing revealed connectivity issues. CariSECURE provided support to RSVGPF to rectify this. Subsequently, progress on PRMIS roll-out was limited due to the late identification of major infrastructure gaps within several stations preventing these stations from operationalizing the application. CariSECURE held meetings with the Permanent Secretary of the Ministry of National Security in the third quarter of Year 6 to address connectivity and infrastructural issues that had limited the deployment of PRMIS. Following these dialogues and commitments to resolve the station-level readiness, 16 of the island’s 21 stations were ready to receive the PRMIS application by September 2022.

Additionally, in preparation for the roll-out in the last month of the programme, CariSECURE delivered training for seven (7) PRMIS trainers and administrators from the RSVPF in March 2022. The Force was specifically targeted for this training due to their low participation in the regional training held in the 4th Quarter of Year 5. One hundred and sixty-one (161) of the targeted six hundred (600) RSVGPF officers have since been trained as users on PRMIS. In large part, St. Vincent and the Grenadines’ challenges and slow uptake of PRMIS have been caused by the La Soufriere volcanic eruption of 2021, compounded by the COVID pandemic, a change in the readiness manager towards the end of the Project and delays in the deployment of the CVDW.

FINAL STATUS: ST VINCENT AND THE GRENADINES

While the deployment of PRMIS in St. Vincent and the Grenadines has not reached the 75% target, there are nonetheless some positives to note. An additional PRMIS training session, led nationally, was held from 15th to 16th September 2022, after which the Commissioner gave authorization for it to become operational at stations. At the close of the Project in October 2022, PRMIS was implemented at Central and Questelles stations, two of the largest stations on the island, which account for a significant proportion of reported incidents. Moreover, these stations also contain important police departments, such as the Criminal Investigation Department, Major Crimes Unit, and Telecom (911 Operators), which are all using PRMIS.

TIER TWO COUNTRIES

Tier 2 countries are those countries that demonstrated high commitment, medium capacity and high competency. CariSECURE assessed these countries to be Guyana, Saint Kitts and Nevis, and Antigua and Barbuda.

## Antigua and Barbuda

| Antigua and Barbuda |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 756 |
| Personnel Trained on Crime Analysis | 2 |
| Police Officers Trained on PRMIS | 120 |
| No. of Police Stations with PRMIS Deployed | 7 |
| Police Officers Trained on TIP (Basic) | NA |
| Police Officers Trained on TIP (Advanced) | NA |

Antigua and Barbuda endorsed the CariSECURE Toolkit in 2018. Over the course of the Project, CariSECURE supported national counterparts in Antigua and Barbuda in building capacity, providing tools to support evidence-based decision making and bolstering data driven policing in the country.

While challenged by a lack of existing digitized legislation, the ICCS Working Group in Antigua and Barbuda mapped 756 offences from the country’s criminal legislation to the ICCS. To support standardization and regional and international comparability of crime data, the correspondence tables have also been integrated into the backend of PRMIS for the RPFAB and ICCS reports can be generated from PRMIS.

Through the support of CariSECURE, the RPFAB also incorporated crime analysis into its policing efforts. A Senior Sergeant of the RPFAB, along with a representative from the Statistics Division completed 320 classroom hours as part of CariSECURE’s Crime Analysis Training Programme in 2020. During the graduation ceremony, the team from Antigua and Barbuda were recognized for their production of an administrative crime analysis report, which focused on the reported occurrences of three types of crimes - homicides, robberies and wounding for the years 2017 to 2019.

Following from the training, the RPFAB also endorsed the establishment of a Crime Analysis Unit in August 2020. Following from this, CariSECURE provided hardware and software for the establishment of the Unit at the RABPF’s St John Police Station. This included four (4) workstations and monitors, one (1) laptop, four (4) UPS for power supply, one (1) NAS device for storage, one (1) colour printer and a projector. A two-year subscription to SPSS was also provided to support the data analysis needs of the RPFAB.

The RPFAB deployed PRMIS at seven (7) of the island’s thirteen (13) police stations and is poised for full deployment at all stations by the end of 2022. Antigua and Barbuda, during 2022, focused on institutional capacity building, deployment of ICT infrastructure and preparing for the roll-out of the PRMIS platform. Twelve (12) of the island’s thirteen (13) stations have been assessed as ICT ready for the deployment of PRMIS during the year. The remaining station is located off the mainland in Barbuda, and experienced challenges with the provision of internet services. The PMU has discussed solutions with national counterparts which may involve the deployment of a dedicated internet uplink.

Five (5) officers of the Royal Antigua and Barbuda Police Force (RABPF) took part in the regional training exercises in March 2022 following on from those completed in the previous year. The officers were trained as part of CariSECURE’s PRMIS Training of Trainers and Administrators (Y5 Q4), under the guidance of the RPFAB’s Readiness Manager. Through these efforts, a total of 120 of the targeted 150 officers have received training on the application.

The Readiness Manager flagged that the frequent occurrence of officers being rotated to different stations within the same division has made it difficult to ensure that a minimum number of PRMIS-trained officers are available in each station to trigger the roll-out. In response, the RPFAB’s PRMIS training and implementation plan evolved to a divisional approach in which all officers in a division will be trained, so that rotation within the division does not compromise the roll-out.

The RPFAB also officially committed to pursuing the establishment of a Crime Analysis Unit. CariSECURE provided the equipment for the establishment the Crime Analysis Unit at the RABPF’s St John Police Station, including the deployment of hardware and data analysis software.

FINAL STATUS: ANTIGUA AND BARBUDA

By the end of the project Antigua and Barbuda had exceeded the target of PRMIS rollout to 5 stations to achieve this in 7 stations and was poised to reach full deployment early 2023. This was achieved through the support of the Readiness Manager and his team who took ownership and initiative during the deployment.

To facilitate the training process, the Readiness Manager developed a system guide with bullet point steps based on the Police workflow to facilitate the training process, which encouraged “on the job” training and learning, significantly reducing the number of calls for support. The Readiness Manager also maintained regular contact with trainers from Grenada and St Kitts and Nevis, consulting with them on matters pertaining to the workflow before involving developers or members of the CariSECURE management team. This type of regional collaboration is a prime example of what can be achieved through the standardization of crime data collection processes and the development of regional networks for knowledge sharing and communities of practice around the use of PRMIS.

During the Project’s final monitoring mission in October 2022, the Police Commissioner also reiterated his support for PRMIS and the CVDW centralized solution and signaled the intent to increase the number of trainers to achieve 100% deployment within the next six months and thereafter disband the use of manual log books and station diaries once it is confirmed that information from PRMIS is admissible in court. Impetus to fully deploy the PRMIS application was also received at the highest level in Antigua and Barbuda with the endorsement of the ICT Roadmap by the Minister for Legal Affairs

## Guyana

| Guyana |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 1419 |
| Personnel Trained on Crime Analysis | 3 |
| Police Officers Trained on PRMIS | 300 |
| No. of Police Stations with PRMIS Deployed | 0 |
| Police Officers Trained on TIP (Basic) | NA |
| Police Officers Trained on TIP (Advanced) | NA |

Guyana endorsed CariSECURE in 2016 as one of three priority countries, and subsequently approved the CariSECURE Toolkit in 2018. Through CariSECURE’s support, the country successfully mapped 1419 national offences to the ICCS and had three (3) law enforcement and statistical personnel trained in crime analysis. The Guyana Women’s Health and Family Life Experiences Survey (2018) was another notable early CariSECURE accomplishment, which provided a rich source of non-administrative data about the nature and prevalence of violence against women in Guyana. The Project also provided technical support to generate CariSECURE’s citizen security indicators for the years 2015 to 2018 and successfully deployed the Police Incident Form (PIF) at ten (10) pilot stations.

To support the roll out of PIF, a server was installed in police headquarters and workstations installed at two (2) pilot stations in October 2019. With technical assistance from the Project, connectivity issues at the Fort Wellington Station were resolved and members of the statistics and IT departments were provided with guidance to update the list of offences to facilitate full use of the application. The PIF application was eventually deployed to seven (7) pilot stations in Guyana, however, due to challenges at the country level, the PRMIS application was ultimately not deployed in country.

While engagement with Guyana stakeholders started off very encouragingly, with the Minister of Public Security a powerful and enthusiastic champion for the project, political events affected progress greatly. In December 2018, the President, whose party held a one seat majority in the Parliament, called a snap election in March 2020. The results of the election were hotly disputed and there ensued a 5-month period during which there was no clear government. Eventually the elections resulted in a change of government, creating the need for CariSECURE to engage in awareness raising and advocacy with a new government at a critical juncture in the project.

An example of how these events affected CariSECURE delivery was the discussions around the rollout of PRMIS. The New Minister questioned why PRMIS was being introduced rather than a homegrown system that he had been told existed. Additionally, the CARICOM Crime Observatory (CCO) and the intention to host PRMIS at the Crime and Violence Data Warehouse established with IMPACS raised concerns about data security.

However, while there was limited progress on the roll-out of PRMIS, three hundred (300) GPF officers completed training. Additionally, CariSECURE was able to provide technical specifications to counterparts at IDB and the Government of Guyana to facilitate the integration between PRMIS and the digital justice platform being developed for Guyana.  Unfortunately, although the Government of Guyana and the Guyana Police Force (GPF) had initially been receptive and engaged in CariSECURE’s activities and interventions, implementation of PRMIS was stalled when they raised concerns about the CVDW and the security of hosting national crime data in an out-of-country warehouse.

In response, CariSECURE facilitated high-level discussions on this issue with the support of CARICOM IMPACS, with both the Minister of National Security in April 2021 and the Commissioner of Police in August 2022. Both officials subsequently expressed satisfaction with the security provided by IMPACS and the data management provisions covered under the MOU between the Government of Guyana and CARICOM IMPACS. While the interventions with both the new Minister and subsequently the new Commissioner of Police won their support, they were time-consuming and led to further slippage in activities. Additionally, there appears to have been continued lack of enthusiasm for both PRMIS and the Data Warehouse on the part of interlocutors assigned to implement these activities.

The major delays in deployment meant that no stations had fully operationalized PRMIS by the end of the Project.

FINAL STATUS: GUYANA

Through CariSECURE’s efforts, the Guyana Police Force (GPF) has access to an instance of PRMIS at the CVDW at IMPACS, which is configured for their use and ready for deployment. However, due to the issues noted previously, at the end of the project, Guyana had not met its target for PRMIS deployment nor has there been a confirmation on a timeline for implementing the application.

Additionally, correspondence by the Project about scheduling a presentation of the ICT Roadmap with the Ministry of Home Affairs and technical level stakeholders was not acknowledged. Notwithstanding, CariSECURE presented the draft roadmap for Guyana to the newly appointed Police Commissioner and his team during CariSECURE’s meeting with him in August 2022. The Commissioner expressed his general satisfaction with the document and pointed to the importance of aligning it with the GPF’s ICT roadmap which the GPF promised to share with the Project. Again, despite efforts on the part of CariSECURE to obtain the GPF’s roadmap, the document was ultimately not shared for comparison.

It has however been noted that the Guyana government is expanding its LTE network, and this may provide an opportunity to facilitate the deployment of PRMIS in the future, especially if the country’s preference is for local hosting of the application and data.

While the Guyana Women's Health Life Experiences Survey 2018 was completed earlier on during the project, it is a good example of how non-administrative or survey data can contribute to national responses to crime and violence. The survey was the first of its kind in Guyana and provided a thorough and comprehensive source of information on the scope and prevalence of violence against women and girls in Guyana. Its results were utilized in the formulation of Spotlight Guyana and were further referenced by UNICEF in order to provide evidence for the implementation of new laws and policies, such as alterations to the Domestic Violence Act and the drafting of laws on harassment, under the Spotlight Regional program.

## St Kitts and Nevis

| St. Kitts and Nevis |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 1774 |
| Personnel Trained on Crime Analysis | 2 |
| Police Officers Trained on PRMIS | 122 |
| No. of Police Stations with PRMIS Deployed | 3 |
| Police Officers Trained on TIP (Basic) | NA |
| Police Officers Trained on TIP (Advanced) | NA |

CariSECURE was endorsed in St. Kitts and Nevis in 2016 and the CariSECURE Toolkit in 2018. The Project also supported the development of ICCS correspondence tables for St. Kitts and Nevis which mapped 1774 national offences to the international classification.

CariSECURE also provided equipment and training to support the establishment of a Crime Analysis Unit at the Royal St. Christopher and Nevis Police Force (RSCNPF). Two (2) personnel from the RSCNPF and the Statistics Department respectively, graduated from CariSECURE’s Crime Analysis training program facilitated by ASU in July 2020. Subsequently, 13 officers from the RSCNPF received training on introductory crime analysis facilitated by the CariSECURE-trained trainer from the Regional Crime Observatory at RSS.

The PIF was deployed at three (3) stations in St. Kitts and Nevis, though network connectivity issues impacted the implementation of the platform. In September 2019 the server was installed at police HQ. Problems appeared during installation of the database which required extensive support from the CariSECURE team. These issues were resolved in December 2019. Problems were also encountered due to the police having no private network, therefore there was no network connection between pilot stations and HQ. The Project also provided guidance and an alternative network configuration that assisted in the resolution of these issues.

Previously reported internet service provider (ISP) connection challenges were resolved as police stations upgraded to fibre networks. As at 31 October 2022, all twelve (12) of the country’s stations were ready for the introduction of PRMIS, and the Commissioner of Police has commissioned the Force’s ICT Unit to upgrade the internal ICT infrastructure to support operationalizing PRMIS in every station.

FINAL STATUS: ST KITTS AND NEVIS

By the end of the Project, the Royal St Christopher and Nevis Police Force (RSCNPF) deployed PRMIS in three (3) of the targeted (5) stations and continued the planning for further deployment and use of PRMIS. The RSCNPF employed a more targeted approach which focused training efforts on the two (2) districts where PRMIS was launched with the intention of expanding to other districts later. Four (4) trained PRMIS trainers at RSCNPF had trained 122 officers in St Kitts and Nevis on the application.

One of the noted challenges in St. Kitts and Nevis for the deployment of the police information management systems has been the issues with connectivity at the stations. While technical guidance from CariSECURE was key to resolving some of the earlier issues identified through the PIF deployment process, the support of the Police Commissioner was instrumental in getting the necessary upgrades to the ISP connection at police stations. Additionally, he has commissioned the Force’s ICT Unit to upgrade the internal ICT infrastructure to support PRMIS deployment at all stations. Moreover, during the final monitoring mission on October 27, 2022, he challenged the Readiness Manager to have all stations running PRMIS by January 2023 and requested a budget from his IT team for outfitting the RSCNPF’s vehicles with tablets to support the capturing of data in the field.

The Project has also noted that there are no impediments foreseen to the admissibility of PRMIS outputs and data in court in St. Kitts and Nevis. This can be viewed as an opportunity with the potential to improve the chances of uptake by officers, as it removes the necessity of manual/written diary entries and ultimately facilitates their work.

## St Lucia

| St. Lucia |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 1495 |
| Personnel Trained on Crime Analysis | NA |
| Police Officers Trained on PRMIS | NA |
| No. of Police Stations with PRMIS Deployed | NA |
| Police Officers Trained on TIP (Basic) | NA |
| Police Officers Trained on TIP (Advanced) | NA |

St. Lucia formally endorsed CariSECURE in 2016 and the CariSECURE Toolkit was endorsed by the Cabinet of St. Lucia in 2018. The ICCS working group in St. Lucia also completed the mapping of 1495 local offences including the entire Criminal Code for St. Lucia’s draft ICCS correspondence table.

Regrettably, the Project was unable to use United States Government (USG) resources to implement PRMIS in St. Lucia as the Leahy Law has been invoked against the Royal St. Lucia Police Force. Consequently, as a way of delivering on the Project’s regional Outcome, the UNDP and the SRO agreed with the USAID-ESC to use (UNDP) TRAC-2 funding when working with the Royal St. Lucia Police Force. The timely release of these resources enabled the Barbados and the Eastern Caribbean Multi-country Office to create and manage a St. Lucia project which complemented and supported the wider regional CariSECURE project in all other priority countries. The total disbursement to CariSECURE was US$150,000.00. The project also negotiated with HQ the release of an additional US $35,000 through Track-1 funding for a Crime Information Management System (CIMS) for St. Lucia.

Digital police applications aside, CariSECURE supported St Lucia in the implementation of St. Lucia National Crime Victimization Survey (SLNCVS) between April 2019 and May 2020. A Letter of Agreement (LOA) between UNDP and the Central Statistical Office of St. Lucia was signed during the launch of the SLNCVS, which marked the commencement of the first CVS Workshop facilitated by UNODC and held with key stakeholders on April 9 to 12, 2019.

A CVS Questionnaire Workshop facilitated by UNODC followed on June 11 to 14, 2019 where a technical working group looked at the Latin America and the Caribbean Crime Victimization Survey Initiative (LACSI) core questionnaires and adapted them to the St. Lucian context.  CariSECURE also procured 25 tablets to support data collection of the CVS. A pre-test using the adapted questionnaire was undertaken between June 28 and July 5, 2019, and the final versions of the questionnaires and model manual were completed following that activity. CariSECURE also supported training of the enumerators in the use of the finalized questionnaire and fieldwork for the SLNCVS commenced in November 2019. The CVS in St. Lucia surveyed over 1700 households and culminated in the virtual presentation of results to key national stakeholders on July 3, 2020.

Additional work by CariSECURE in St. Lucia focused on building capacity in the use of data including non-administrative data for crime and violence prevention programming.  Specifically, the Project utilized the results of the St Lucia Crime Victimization Survey (SLNCVS) in developing the country’s Youth Policy Action Plan. The new action plan includes inputs from CariSECURE’s citizen security recommendations including the use of disaggregated citizen security data and the establishment of an evidence-based juvenile justice system based on data.

CariSECURE also implemented two webinars in October 2021 geared towards developing strategies and programming using citizen security data by citizen security practitioners in St Lucia. The sessions engaged 37 policy analysts and social development practitioners from several organizations including the Department of National Security and Home Affairs, Probation and Parole Services, Bordelais Correctional Facility, and the Division of Human Services. The webinars provided an opportunity to highlight recommendations for St Lucia’s citizen security strategy and to build and strengthen existing networks among colleagues in citizen security in St Lucia. They also served to sensitize attendees on the types of citizen security available in the country and allowed participants to practically explore ways to use data to inform their programmes or interventions for improved citizen security.

FINAL STATUS: ST LUCIA

While the imposition of the Leahy Law prevented the police in St. Lucia from benefiting directly from PRMIS, with CariSECURE’s support, the country completed the SLNCVS, which is the first crime victimization survery completed in the English-speaking Eastern Caribbean using United Nations international standards. Additionally, the Project was also instrumental in using some of the recommendations findings from the SLNCVS to inform elements of the National Youth Policy Action Plan.

This achievement synthesizes CariSECURE’s work around using non-administrative data from surveys to develop strategies and policies around citizen security. The SLNCVS of 2020 involved a national survey of over 1,700 households to establish the prevalence of victimization and offences, crimes reported to the authorities, perceptions of safety, the impact of crime on society, and the level of public confidence in the criminal justice system within the population of St Lucia.

Through exposure to the CVS questionnaire and participation of key personnel in the questionnaire adaptation process, Saint Lucia’s Central Statistical Office (CSO) has included two questions from the Saint Lucia National Crime Victimization Survey (SLNCVS) in the ongoing National Census. These questions focus on the levels and type of victimization experienced in the population and the results can be compared with data from the SLNCVS to provide information on changes over time. This best practice and the specific questions were also shared with Statistical Departments for possible inclusion in their own recurring surveys and censuses.

Notwithstanding, while capacities in the area of the CVS methodology and the use of data for citizen security programming were built, there is still a need for consistent and coordinated use of data for planning and programming around citizen security in St. Lucia.

TIER THREE COUNTRY

Tier 3 countries are those with medium commitment, medium capacity and high competency. CariSECURE assessed this country to be Suriname.

## Suriname

| Suriname |  |
| --- | --- |
| CariSECURE Toolkit Endorsed | Yes |
| No. of Offences Mapped to ICCS | 564 |
| Personnel Trained on Crime Analysis | 2 |
| Police Officers Trained on PRMIS | NA |
| No. of Police Stations with PRMIS Deployed | NA |
| Police Officers Trained on TIP (Basic) | NA |
| Police Officers Trained on TIP (Advanced) | NA |

As the independent Terminal Evaluation Report notes, the success of PRMIS as a regional solution for the digitalization of police operation was helped because in the six countries where the implementation (was) underway, the same language and the same legal and police management tradition were shared. Suriname, on the other hand, inherits the Dutch legal tradition and language, which makes the implementation of an English-based regional system in that country much more complex. In addition, the police tradition is quite different, even in basic matters of authorization and validation by superiors – functionalities that make up the essence of the PRMIS management mechanics.

Although reconciliation of national realities, political organization, policing culture and lexicon posed a great challenge even in beneficiary countries which shared legal and police traditions and a common language, these challenges were multiplied in Suriname. In addition, national elections held in May 2020 resulted in a change of government, necessitating a duplication of engagement, this time with new stakeholders.

The work in Suriname during the final year of implementation was focused primarily on identifying the differences in the policing workflow and the changes needed for PRMIS to meet the requirements of a digital solution for the police in Suriname. CariSECURE conducted a mission to Suriname in Y6 Q3, held working sessions with Korps Polite Suriname (KPS) representatives and was able to gain an in-depth understanding of their policing workflow and the effort and resources required to make changes and adapt PRMIS to their requirements.

Based on the stage of project implementation and the financial and technical requirements for these changes, a version of PRMIS for the KPS was not feasible under CariSECURE 1.0. However, the resources required for adapting PRMIS for the KPS have been included within the country’s ICT Roadmap and a Dutch language instance of PRMIS for Suriname is available on the CVDW’s servers at IMPACS, once the country can mobilize resources to adapt the application in the future.

PIF, which was piloted by the KPS, is suitable for their incident recording and they agreed to deploy this solution in the interim.

FINAL STATUS: SURINAME

CariSECURE was unable to deploy PRMIS in Suriname owing to differences in the policing workflow of the KPS, which, at the late stage could not be integrated into the development scope for PRMIS. As highlighted, the participation of the KPS in project activities including requirements gathering and training was a challenge given the language barrier and was compounded by the Project’s pivot to virtual training during the height of the COVID-19 pandemic.

Against this backdrop, CariSECURE informed the Government and proposed to adjust the PIF application which was deemed a suitable digital incident reporting application for the police.   Upon country approval, CariSECURE commissioned the changes to the reporting module for PIF which were completed in October 2022.

Additionally, the ICT Roadmap for Suriname was presented to the Minister for Justice and the Police in September 2022 and endorsed in October 2022. The document provides a technical and financial plan for the deployment of PRMIS for the KPS inclusive of the cost of the changes to be made to address the workflow issues.  It is hoped that this will facilitate resource mobilization for the future implementation of the application at the KPS.

# Sustainability Mechanisms

Sustainability has been a critical issue for CariSECURE 1.0. This is particularly important with regards to the implementation of PRMIS, which involves the deployment of new software, the requisite installation of hardware and networking solutions to facilitate this and the building of capacity to use, maintain and improve upon these interventions.

To ensure sustainability of project deliverables, CariSECURE worked with partners such as RSS and CARICOM IMPACS to build their capacity to provide long-term system maintenance and quality assurance for the CariSECURE systems and tools. During the reporting period the project team had several substantive engagements with other strategic partners. These include:

CARICOM IMPACS:

The project team held several discussions with representatives of CARICOM IMPACS about sheltering the USAID funded CariSECURE application and databases. This arrangement will see all critical crime data being securely stored regionally and will significantly reduce regional security and maintenance cost for beneficiary countries. The initial investment will see CariSECURE investing in hardware to support the expansion of existing capacity within CARICOM IMPACS It will also involve the agencies’ participation in the systems development process to better understand the technical specifications and to enhance its ability to provide long term maintenance, modification and upgrade systems support as may be dictated by beneficiary countries.  These discussions were stalled owing to delays in the award of the systems development contract.

The sustainability of the CVDW at CARICOM IMPACS involves both medium and long-term solutions. On the former, support is required for countries in troubleshooting and resolving issues that will invariably arise with PRMIS as they move to full mainstream the system and complete the transition away from the legacy, paper-based system to the fully digitized platform. This will involve periodic but consistent engagement with the vendor to address issues quickly to ensure that the integrity of the software is maintained and encourage uptake. This will be facilitated by the 2-year SLA which will be executed by the vendor, with UNDP providing overall management and quality assurance.

This period will also facilitate the transition of the system’s oversight and management to CARICOM IMPACS. This process will involve enhancing the capacity of CARICOM IMPACS to manage and oversee PRMIS over the long-term and to establish a sustainable business model for the maintenance and expansion of the platform. While discussions on this are still in the early stages, UNDP, IMPACS and RSS have expressed keen interest and support for the process at the most senior levels of each Agency. These discussions will be continued with the support of CariSECURE 2.0 with the aim of developing an effective solution by mid-project.

Inter-American Development Bank (IDB)

The project team held several discussions with representatives of the Inter-American Development Bank (IDB) in Guyana on possible synergies between the USAID funded CariSECURE project, and IDB-funded Citizen Security Strengthening Programme (CSSP) and Support for Criminal Justice System Programme (SCJS). This collaboration will see the agencies taking a more integrated approach to the development of comprehensive information systems across justice sector agencies within Guyana. The ensuing discussions have led to a concrete partnership with IDB towards the development of a Prisons Information System. The systems source codes, training material and other critical documentation will be shared and adopted for other CariSECURE beneficiary countries. A MoU will be developed between USAID and Government of Guyana (IDB funding recipients) to manage the systems development and ensure compliance with the CariSECURE regional technical requirements.  These are all expected to be completed in Q1 Y4, once the contract is awarded.

Government and National investments in Public Security

CariSECURE engaged with national level stakeholders to better understand and to identify opportunities for collaboration on improving connectivity and ICT use at police stations. Given the high demand for e-services among government agencies and the presence of ICT and connectivity projects in beneficiary countries, this Project has initiated discussion with national agencies for prioritizing connectivity and equipment for public security, specifically with regards to outfitting modern police stations. These discussions will be ongoing as it will have implication for interoperability of the CariSECURE systems with other government systems

National Task Force (NTF)

The National Taskforce (NTF) gave the project access to various partners under one umbrella. While NTF meetings lagged from the last two quarters of Y4, as countries sought to establish suitable options for meeting within the context of physical distancing during the COVID-19 pandemic. Further successful approaches were developed in the form of the Regional Readiness Managers Working Group (RMWG) and the national Project Working Groups (PWG) both held virtually.

NTFs across beneficiary countries also served as key interlocutors for the verification and endorsement of key project outputs such as the Citizen Security Toolkits and ICT Roadmaps and for country level mobilization around project activities and events.

Regional Readiness Managers Working Group (RMWG)

The Regional Readiness Managers Working Group (RMWG) was established in Y4 Q4 with the CariSECURE Readiness Managers from each of the CariSECURE beneficiary countries and additional invited stakeholders, on request, from within the citizen security ecosystem. Meetings of the RMWG took place regularly and were convened monthly.

The objective of the Regional RMWG was to ensure proper communication and collaboration between beneficiary countries and the CariSECURE Project team towards the development, implementation and evaluation of the Police Record Management Information System (PRMIS). In addition, the RMWG was instrumental in ensuring there was a standardized approach towards the management of citizen security data. The intention was for regional and comparable crime data analysis and reporting among national authorities, thus leading to a more sustainable future for a regional Police Record Management Information System.

Project Working Groups

At the national level, CariSECURE also recognized the need to develop partnerships which would aid the project to meet its targets. Saint Lucia provides an example of these partnerships. In order to undertake the ICCS extraction and coding exercise, the project sought to increase stakeholder participation by reaching out to the Eastern Caribbean Supreme Court, the Central Statistical Office and the RSLPF. These agencies agreed to commit human resources to the exercise. CariSECURE facilitated virtual training and each agency was assigned Acts from which to extract offences.

Country project working groups (PWGs) were established with individuals from each of the data producing units under CariSECURE. Meetings of the PWG were intended to be regular (e.g. every four (4) weeks), and the objective of the Project Working Group (PWG) was to address the data and system gaps of CariSECURE at the national level and to complement the efforts of the National Task Force (NTF) to implement CariSECURE’s activities in beneficiary countries.

The PWG meeting was principled as the basis for the achievement of their mandate on the following:

- To establish goals and objectives for the CariSECURE evidenced based policy making process;

- To enable the provision of a list of data, information, knowledge and resources that are currently available, and, too, valuable to the CariSECURE project;

- To enable discourse in the assessment of the national crime and security data management capability, constraints and opportunities for improvement in country.

Communications efforts were also increased in Y4 with refreshed high-quality printed project brief material and the project launched quarterly newsletters. This proved valuable in highlighting the significance of introducing technology in agencies like the Police Force. The Project  further supported beneficiary governments on internal communication and advocacy for Project activities and goals.

CariSECURE sought to maintain its momentum with its various partners through frequent engagement and consultation. While the NTF provided an overarching forum for dialogue among various national partners, the project continued to utilize other opportunities for more responsive information sharing and dialogue presented through the Regional Readiness Managers Working Group (RMWG) and the national Project Working Group (PWG). The RMWG continued its monthly virtual meetings which provided a forum to share regional experiences about the PIF, provide feedback on the development process for PRMIS and dialogue on a standardized approach towards the management of citizen security data.

The primary focus of stakeholder engagement during Y5 Q1 was to facilitate participation and solicit feedback in the process of elaborating the requirements for the PRMIS. To this end, the software development vendor SoftEngi initiated a series of consultations, firstly with a core group of countries as a more streamlined approach, then with the wider group of beneficiary countries. Initial consultations were held with representatives from Barbados, Grenada, Guyana and Suriname between 23 - 30 October 2020 to gather information pertaining to the current state of police information management systems in those territories. Additional consultations were held with this core group of countries between 17 - 25 November to elicit inputs and information on the requirements for PRMIS. Requirements gathering workshops were also held on 10 and 14 December to demonstrate and discuss how key processes will be implemented in PRMIS including incident registration, processing, person registration and features of the implementation of crime cases. CariSECURE also facilitated discussions with SoftEngi and the UK Criminal Records Office (ACRO) around their biometrics requirements and with The United Nations Regional Centre for Peace, Disarmament and Development in Latin America and the Caribbean (UNLIREC) around the requirements for the firearms module of PRMIS. SoftEngi has developed a Business Requirements Document from these consultations that outlines user requirements for PRMIS. This was shared with country stakeholders for review and approval.

The User Acceptance Testing (UAT) Phase spread over Y5 Q3 - Q4, also heightened stakeholder participation and involvement in the development process. The 4-day UAT workshop held from 8 - 11 June, was successful in bringing together Readiness Mangers and other police users from Antigua and Barbuda, Grenada, Saint Kitts and Nevis and Saint Vincent and the Grenadines and regional and international partners to test the first iteration of the PRMIS platform. While the workshop was virtual, there was considerable interaction, and the dialogue and discussion provided a great deal of insight that informed the development of the application. During UAT Phase 2, the SoftEngi team walked the participants through the modules from the Change Requests list, including practical exercises with each, and reviewed updates to already implemented modules requested by the stakeholders during the first UAT sessions. Phase 3 of the UAT period was divided into 3 rounds of testing to facilitate the receipt of testing results with frequency and react on the requested modifications/fixes quickly with the SoftEngi team updating the application in the UAT environment as necessary and notifying stakeholders of modifications.

The PRMIS Training of Trainers and Administrators held from 27 September to 1 October 2021 provided another opportunity for stakeholder engagement around the development and deployment of the PRMIS application. Initially planned as a face-to-face activity, the training session instead  pivoted to a hybrid format following a fresh COVID-19 wave in the region. The SoftEngi team joined the Royal Barbados Police Force participants in Barbados, while participants from all other beneficiary countries except Suriname participated virtually via the CBSI platform. The latest and most stable version of the PRMIS solution was deployed and prepared for testing during the TOT Sessions, giving users an opportunity to familiarize themselves with the application, dialogue about PRMIS with police colleagues from around the region and convey feedback in real time to the development team.

The CariSECURE Citizen Security Conference was another significant stakeholder engagement activity. The virtual conference saw over 400 participants registered and over 20 speakers and presenters from the regional citizen security sector engaged for this event. The Project also engaged regional security organisations such as RSS and IMPACS during its planning and execution and encouraged partnership and promotion of their mandates. The conference provided impetus for increased dialogue around the finalisation of MOUs between USAID and IMPACS to establish the data warehousing solution and Crime Observatory at IMPACS and the MOU between USAID and RSS to launch the Regional Crime Observatory at RSS.

# Detailed Implementation Status at Project-end

## OUTCOME 1: Standardized and disaggregated crime data reporting within and among national authorities to foster the reliance on valid, reliable, and comparable data on citizen security

#### Number of countries with government approved Caribbean Security Toolkit

The Caribbean Citizen Security Toolkit was endorsed by all eight (8) beneficiary countries. The collection of instruments will enhance the quality, integrity, and accuracy of citizen security data through improved data collection processes. It will also increase the capacity of the government to accurately monitor citizen security and, by extension, the effectiveness of crime reduction and prevention strategies. The CariSECURE Citizen Security Toolkit is the backbone of the institutional strengthening support through the project and comprises the following items:

Terms of Reference  –  National Task Forces are guided by Terms of Reference (ToR) that have been endorsed and signed by national governments. The ToR provides guidance to the Task Force on its Objectives and Scope; Membership and Reporting Relationships; Meeting Procedures and Governance Arrangements; Appointment and Tenure; Roles and Responsibilities; and Confidentiality, Impartiality, and Termination. It also provides guidance on the establishment of sub-committees for specific technical issues.

Caribbean Citizen Security Indicator Framework (CCSIF) – This allows for the collection and reporting of key citizen security indicators across the whole range of key national rule of law institutions (Police, Prosecutions, Courts, and Rehabilitation) at different levels as follows:

- Primary – Embodies indicators from immediate data capture, which foster data process management from Police through to Courts and Rehabilitation. These are based on individual national legislation and practices

- Secondary – Embodies process indicators to analyze performance and effectiveness specific to each agency and by thematic area

- Policy – Embodies indicators to gauge medium and long-term preventative and sustainable policy measures

- Regional – These are primary indicators, but from data consistent with international standards and conventions (e.g. ICCS, ICD-10, and UNCRC, etc.)

- 3.    Guidance Notes on Citizen Security Data Collection and Dissemination – This document is a single set of guidelines that coherently enhances the capacity of national authorities to use citizen security data to engage in evidence-based decision-making. It embodies the CCSIF and comprises of key guidelines around concepts and definitions, privacy and confidentiality, counting rules, missing data, data quality, and transparency, guided by international standards.

- Data Sharing Agreement – This functions as a working memorandum of understanding among key institutional partners, establishing mutual accountabilities around the sharing of data to facilitate national reporting around the citizen security indicators. All institutions represented on the Task Forces are parties to the Agreement. This has been a notable achievement for the Project because for the first time it reposes significant ownership at the country level around data sharing.

- Citizen Security Data Collection Form and Coding Structure – This allows national law enforcement officials to capture data on victims, alleged perpetrators and circumstances around the event. It is the starting point for data disaggregation and standardization. Gender and child protection bureaus can also integrate this tool with their data sources to help improve the validity of their databases. It has been integrated into CariSECURE’s PRMIS and PIF digital solutions and forms the basis of the fields available in the system for capturing data related to crime incidents.

- With the delivery and endorsement of the Caribbean Citizen Security Toolkit, the project has laid a solid foundation upon which data standardization and disaggregation can be achieved, which is the basis of Output 1.

#### Number of countries with draft Correspondence Tables for International Classification of Crime for Statistical Purposes (ICCS)

Through support from CariSECURE, all eight (8) beneficiary countries completed draft National Correspondence Tables around the International Classifications of Crime for Statistical Purposes (ICCS) through a UN Agency to UN Agency Contribution Agreement with the United Nations Office on Drugs and Crime (UNODC). Correspondence Tables (CTs), which are country-specific, allow for national criminal codes to be mapped around the statistical categories set out within the ICCS. A correspondence table is a simple tool that countries can adopt for crime data reporting without changes in the legal framework, and it allows for the comparison of crime statistics at the national, regional, and international levels. The CT is an appendage of the Citizen Security Toolkit coding structure and allows for standardized and disaggregated capture, sharing, and analysis of citizen security data.

CariSECURE hosted a Regional ICCS Workshop in September 2018 and provided training to key stakeholders on the ICCS framework and the development of correspondence tables.  Following on from this, national ICCS working groups comprising representatives from central statistical offices, police, courts, probation and parole services and Ministries of National Security examined national offences and developed ICCS correspondence tables for their respective countries. All countries have completed and submitted draft correspondence tables with common offences (i.e. those most frequently occurring in their jurisdictions).

To support fine tuning and sustainability of ICCS Correspondence Tables, CariSECURE facilitated an ICCS virtual workshop in January 2022. The workshop focused on practical examples of national correspondence tables, showcasing common practices and opportunity areas, the use of disaggregating variables to strengthen the use of correspondence tables, and updating and maintaining of the tables.

The development of the ICCS correspondence tables supports CariSECURE’s Objective 1 around standardization and comparability of crime data. Moreover, the correspondence tables have been integrated into the backend of CariSECURE’s digital policing applications (PRMIS and PIF) to support standardized reporting of national crime incident data.

Table 2: ICCS Status Update

| Countries | Number of Offences Mapped |  |
| --- | --- | --- |
|  | Number of Common Offences Mapped to ICCS | Total Number of Offences Mapped to ICCS |
| Antigua and Barbuda | 227 | 756 |
| Barbados | 206 | 1,722 |
| Grenada | 382 | 1,157 |
| Guyana | 232 | 1,419 |
| St Kitts and Nevis | 85 | 1,774 |
| St Lucia | 387 | 1,495 |
| St Vincent and the Grenadines | 249 | 480 |
| Suriname | 67 | 564 |

#### Number of Countries with Digitized Applications for Police as a result of CariSECURE’s Assistance

CariSECURE developed two (2) digital applications to support beneficiary police forces in gathering police incident data and reports. The PIF was deployed at 56 stations in Antigua and Barbuda, Barbados, Grenada, Guyana, St Kitts and Nevis, St Vincent and the Grenadines, Suriname, and St. Lucia (with funds mobilized by UNDP). The development and piloting of PIF was a strategic intervention by the Project to transition police stations nationally from paper-based reporting to a digital format. While the application was not as robust and all-encapsulating as its successor, PRMIS, it allowed for police forces to understand some of the technical nuances, connectivity and networking issues around the transition to digital applications, and to develop standard operating procedures, in some instances, to adjust to this change.

The development of PRMIS commenced in October 2020 with the signing of the contract with the Ukrainian software development firm Softengi. CariSECURE and the Softengi team engaged national counterparts in continuous consultations, training, testing and validation over a two-year period, to advance the development of the PRMIS application and its full suite of crime incident recording and case management modules. PRMIS was a significant step up from the PIF application, as it was built not only for incident reporting/recording but also with functionality for case management and a broader range of fields and options for data capture. As the focus shifted to the implementation of PRMIS and training on the new platform, the use of PIF was discontinued in beneficiary countries. PRMIS development was completed in August 2022 and the application was deployed at the data warehouse at CARICOM IMPACS the following month.

To build and sustain capacity around the use of PRMIS in the region, CariSECURE employed a train-the-trainer approach and held its first PRMIS Training of Trainers and Administrators in September 2021. Following on from the PRMIS Training of Trainers and Administrators, the cohort of PRMIS trainers submitted practical work forms – a list of tasks that are recommended to be completed as practical work to solidify the knowledge obtained during the PRMIS training of trainers sessions and a prerequisite for the issuing of training completion certificates. Participants also submitted training plans for their respective police forces. Feedback from these and other consultations with users and readiness managers was captured by the development team in a list of most essential requested functionality and issues for fixing in version 1.0 which was released for the Grenada PRMIS pilot.

Grenada PRMIS Pilot

Grenada, through a local installation of the application, commenced a pilot of the PRMIS platform at three (3) stations in November 2021. The pilot was another strategic intervention by the Project to streamline implementation processes for PRMIS, by deploying it in a real-world scenario. The Grenada pilot, Q&A sessions, regional PRMIS training and consultations with country readiness teams resulted in feedback on necessary bugs and fixes to the application, which were actioned by Softengi. Through an iterative process of consultation and development, the Softengi team finalized PRMIS version 1.3 with the functionality and fixes that were agreed upon with stakeholders. PRMIS development is complete, and the application was deployed at the IMPACS data warehouse in September 2022, and connections tested.

Suriname
While an instance of PRMIS has been deployed for Suriname at IMPACS, CariSECURE’s mission to the country in May 2022, revealed that because of the differing policing workflow in Suriname, a number of changes to the application were required to make it a usable solution for the KPS. An indicative cost has been received by Software developers Softengi and this has been included in the country’s ICT Roadmap. A letter was sent to Suriname’s Minister for Justice and the Police explaining the situation and he and the KPS approved the proposal for the use of PIF as an interim solution for the KPS, on the condition that the minor adjustments previously highlighted to the developer were addressed. The PIF developer was reengaged and completed the updates to PIF for Suriname in October 2022.

Table 3: PRMIS Deployment Status

| Countries | Stations |  | Officers Trained |  |
| --- | --- | --- | --- | --- |
|  | Number of Stations in Country | Number of Stations using PRMIS | Number of Officers targeted | Number of Officers Trained |
| Antigua and Barbuda | 13 | 7 | 150 | 140 |
| Barbados | 12 | 7 | 280 | 375 |
| Grenada | 14 | 11 | 500 | 301 |
| Guyana | 124 | 0 | 2500 | 300 |
| St Kitts and Nevis | 11 | 3 | 120 | 120 |
| St Vincent and the Grenadines | 21 | 2 | 600 | 161 |
| Suriname | 65 | NA | NA | NA |

Antigua and Barbuda

Twelve (12) of the thirteen (13) stations in Antigua and Barbuda are ICT ready, with the 13th station in Barbuda experiencing some ISP challenges. 140 of 150 officers targeted have received training on PRMIS. The RABPF has confirmed that it is taking a divisional approach to the deployment of PRMIS and have commenced use of the application at seven (7) stations.

Communication with the Royal Police Force of Antigua and Barbuda (RPFAB) has improved with the appointment of a new Readiness Manager. The pace of deployment has also increased and the RABPF is anticipating 100% deployment by the end of 2022.

Barbados

By the end of the reporting period, seven (7) stations in Barbados were using PRMIS, with 375 officers trained on PRMIS, and the BPS targeting training of an additional 20 officers every week.  All twelve (12) stations are IT ready and officers from each are among those trained.

The Barbados Police Service continued to use the PIF application to populate live crime data until the end of Y6 Q1 when the Project shifted focus to the implementation of PRMIS.  Through the final year of implementation, The Barbados Police Service (TBPS) also continued to participate fully in CariSECURE’s PRMIS training activities including User Acceptance Testing (UAT) sessions, training of trainers and providing feedback to developers on the application. In November 2021, the Softengi team processed requests and comments expressed by Barbados for inclusion in PRMIS version 1.1.

Additionally, the Senior command team of BPS were updated during Y6 Q2 with respect to PRMIS. More specifically, the project team met with the newly appointed Police Commissioner Richard Boyce and made a presentation on CariSECURE, the PRMIS application and the support required from the Commissioner and the Senior Command team for implementation. BPS also invited CariSECURE to make a similar presentation on the Project during their Annual Grand Conference held on 31 March 2022.

BPS developed their PRMIS training plan and have also been proactive in seeking out opportunities to build awareness among the force regarding the implementation of PRMIS. CariSECURE supported the BPS in developing a communications plan targeting internal and external stakeholders, based on lessons learned from the Grenada pilot.

Grenada

Eleven (11) out of fourteen (14) stations in Grenada are currently using PRMIS to input live data.

Overall, the RGPF has expressed satisfaction with the PRMIS platform and has expanded the use of the platform from the 3 initial pilot stations to a total of eleven (11) stations. They have also been proactive in the implementation of their training plans and awareness building efforts and have taken the initiative to develop training guides and a printed manual on PRMIS specifically geared to Station and Divisional Chiefs, the Police Commissioner and his upper command. Eleven (11) police executive members including the Commissioner were trained on the use of PRMIS during the month of September 2022 and 80% of station commanders and divisional commanders have been trained on the platform.

Grenada was able to officially launch PRMIS at an event held on 24 February 2022. Softengi also facilitated refresher training for the RGPF during 22 - 23 February in the lead up to the launch. The trained trainers of the RGPF displayed a solid understanding of the PRMIS platform during this exercise and were able to ask pertinent questions and provide useful feedback to the Softengi team on the changes incorporated in

PRMIS 1.1. Additionally, the Grenada trainers also facilitated sessions in the regional, role-based PRMIS training and have shown themselves to be extremely competent and dedicated.

Planning has commenced for a case study exercise that will document Grenada’s experience with the deployment of PRMIS and distil this into a concise knowledge document that can be instructive for future deployments of PRMIS and similar applications.

Guyana

No stations in Guyana are inputting live data into PRMIS.

Given Guyana’s size, there are uniquely high bandwidth demands due to the significant number of police stations. Presently, 70 of Guyana’s 124 stations are ICT ready and 300 out of 2,500 officers have been trained on the PRMIS application.

Guyana has endorsed the PRMIS data warehousing solution at IMPACS, and the Ministry of Legal Affairs and UNDP have signed a data sharing agreement to support their Criminal Justice System Programme and the Data Interoperability dialogue for data exchange from PRMIS to other Criminal Justice Management Information Systems in Guyana. The Guyana Police Force continued to participate in CariSECURE Training activities. Additionally, CariSECURE and the Softengi Team continued to support Guyana’s efforts to digitize within the criminal justice system and presented the functionality of PRMIS to focal points from the SIGOB Project which is focusing on digitization of systems at the Office of the Director of Public Prosecution.

St Kitts and Nevis

The St Kitts and Nevis are inputting live data on PRMIS at three (3) of the five (5) targeted stations.

All twelve (12) stations on the islands are ICT ready and 122/326 officers have been trained on PRMIS. The Force has adopted a more targeted approach to training officers which increased training efforts in the two (2) districts where PRMIS will be initially deployed (90% trained).

Additionally, St Kitts and Nevis continues to work towards the implementation of national fiber rollout for police stations as the force is challenged with poor internet service at some branches to improve network connectivity for the functionality of PRMIS. Despite setbacks due to poor internet service, the RSCNPF continued to participate in UAT sessions and other Project activities and made some excellent contributions for PRMIS development, with detailed analysis, and suggestions towards improved workflow.

The RSCNPF PRMIS trainers also facilitated sessions during CariSECURE’s regional PRMIS training from 21 - 24 March 2022, which was led by selected trainers from beneficiary countries with support from Softengi.

St Vincent and the Grenadines

Due to the infrastructure related delays, only two (2) stations in St Vincent and the Grenadines had begun collecting live data with PRMIS by the end of Y6. However, 161/600 officers have been trained on the application.

A meeting on 13 October 2021 with the Permanent Secretary of the Ministry of National Security revealed the need for some specific actions to improve the RSVGPF’s progress and engagement with the Project. Stemming from this, a four-day PRMIS demonstration and train-the-trainers session was facilitated by Softengi and held virtually for seven (7) officers of the Royal St Vincent and the Grenadines Police Force (RSVGPF) from 28 - 31 March 2022. The training allowed the RSVGPF team to gain a better understanding of the functionality available in PRMIS. The training was devoted to the available modules and their peculiarities, and the developers addressed questions and concerns from the RSVGPF users during and after their training sessions. This was a positive step in the engagement of the RSVGPF as they had previously been behind with training activities and engagement, owing to La Soufriere’s volcanic eruption and other factors. A new Readiness Manager was appointed and worked extensively with the project team to ensure the RSVGPF’s participation in project activities.

Lack of ICT-readiness was subsequently cited by the Readiness Manager as a major obstacle for the implementation of PRMIS there. He determined that only five (5) of the 21 stations in St Vincent and the Grenadines were ICT-ready due to issues with connectivity, availability of equipment and furniture. A meeting with the Permanent Secretary in the Ministry of National Security was held in July to discuss these issues and their resolution. The Readiness Manager reported subsequently that these issues have been largely resolved with 16 of the island’s 21 stations ready to receive the PRMIS application.

Additional nationally-led PRMIS training was held on 15 – 16 September 2022, with the Commissioner subsequently giving authorization for it to go live at stations. PRMIS is deployed at the Central and Questelles stations, two of the largest stations on the island which record a large percentage of the incidents reported. Additionally, these stations also house important police departments including the Criminal Investigation Department, Major Crimes Unit, and Telecom (911 Operators) which are all using PRMIS.

Suriname

The Project conducted a mission to Suriname from 18 – 20 May 2022 in order to understand the KPS requirements for ensuring that PRMIS is a workable solution for them. CariSECURE’s System Analyst met with Minister for Justice and the Police and members of the National Task Force to discuss the impact and potential benefits the CariSECURE project can bring to the country, including timely crime statistics, crime analysis and evidence-based policy making. The Minister reaffirmed Suriname’s commitment to the project. The mission also held fruitful technical working sessions with KPS where they described their workflow to the development team, allowing for a more in-depth understanding of the changes required for PRMIS to meet the requirements for the KPS.

Through these discussions the project gained a better understanding of the effort and resources required for this. The Softengi team has provided a quotation based on this for the Project’s consideration. However, based on the stage of implementation and the financial requirements for these changes, it is unlikely that these workflow changes for PRMIS for the KPS will be feasible.

The Project has held preliminary discussions with the KPS around redeploying PIF as a solution for the police in Suriname. The response has thus far been positive, with correspondence sent to the Minister for Justice and Police indicating the challenges with the deployment of PRMIS, the cost for adapting the application for the KPS and the option of redeploying PIF. Discussions have also commenced with the PIF developer and Suriname’s e-Gov representatives around making the necessary changes to the application to facilitate use by the KPS. There have been some challenges with the developer accessing the server. However, further dialogue regarding the way forward is anticipated.

#### Number of Tier I countries with 75% of Police stations with digitized Police application capable of collecting and producing crime statistics report

Up to the end of October 2022, Grenada has been able to deploy PRMIS to 11 (80%) of their police stations.  Barbados is using PRMIS at seven (7) of its twelve (12) police stations (58%) while St Vincent and the Grenadines commenced inputting live incident data into the application at two (2) of the island’s largest police stations.

Barbados recorded a surge in gun-related and other violent crime over during 2022 and redeployed officers, including the Readiness Manager away from PRMIS deployment. This slowed the pace of implementation. Notwithstanding, BPS put in place a training and deployment schedule and had implemented PRMIS at seven (7) stations by the end of the Project on 31 October 2022.

St Vincent and the Grenadines had challenges with training, connectivity and station readiness. Due to challenges and low participation in the regional PRMIS training of trainers and administrators, CariSECURE delivered training virtually for trainers from the RSVGPF in March 2022. The Project also met with the Permanent Secretary at the Ministry of National Security along with the readiness team to discuss solutions to station readiness challenges. These have subsequently been resolved and 16 stations are ICT ready for PRMIS deployment. The RSVGPF commenced retroactive incident capture from 3 October 2022 and has deployed PRMIS at two (2) of its 21 stations. Of note, the two stations where PRMIS is deployed house key RSVGPF units responsible for incident data capture and investigation. As such, PRMIS has been deployed within the Criminal Investigation Department, Major Crimes Unit, Telecom (911) as well as the General Police Stations. Telecom (or 911 Unit) is noteworthy in that all 911 calls for service to the police are now being logged with PRMIS.

#### Number of Tier I countries with 75% of police stations utilizing mobile technology

This has not been met as police forces have prioritized in-station PRMIS deployment before its use in the field. Information on device requirements and costs has been included in the ICT Roadmaps of Tier 1 countries to support post project deployment. Beneficiary police forces were also encouraged to explore existing agency and/or government negotiated relationships with internet service providers to provide data packages and sim cards to facilitate the use of PRMIS on mobile devices in the field.

#### Number of partnership events implemented which expose Tier 2 and 3 countries to funding for sustainable interventions to scale up the technological rollout for police applications

As part of the CariSECURE Citizen Security Conference in September 2021, the Project held a Donor Roundtable event which brought together representatives from the donor community to discuss opportunities for expanding support for data driven decision making for citizen security in the region. A presentation on CariSECURE’s achievements, country status and key components of ICT roadmap and recommendations for donor consideration was part of this session.

#### Number of Tier 2 and 3 countries with Government endorsed Roadmap for the independent roll-out of the police application post CariSECURE

A key milestone for the Project was the development of ICT Roadmaps for Antigua and Barbuda, Barbados, Grenada, Guyana, St Kitts and Nevis, St Vincent and the Grenadines and Suriname. The Roadmaps hold the potential to further bolster their capacities to capture and use crime data by charting a pathway for each country to build its own digital infrastructure for standardized crime data reporting. The Roadmaps were developed through a consultative process with national police forces and provide beneficiary countries with technical guidance on the requirements for the full deployment of the PRMIS application at all police stations, including a country specific financial plan based on the resources required and recommendations around uptake and sustainability of the application. To ensure that the Roadmap is institutionalized, a series of technical validation sessions were held with focal points in Antigua and Barbuda, Barbados, Grenada, St Kitts and Nevis and St Vincent and the Grenadines and Suriname, where the reports were informally validated.  The ICT Roadmaps were presented virtually to country representatives at two tiers:

- Technical sessions – virtual presentations of roadmap and sustainability framework to national task forces and technical representatives from beneficiary countries for feedback and buy-in.

- Ministerial/Executive sessions – high-level, virtual presentations of roadmap and sustainability framework to Ministers and executive team to solidify support and endorsement of finalized roadmaps.

Presentations to key national technical representatives were held with all beneficiary countries except Guyana; Ministerial presentations were held with the Minister of Justice and Attorney General of Antigua and Barbuda on 30 September 2022, and the Minister for Justice and the Police in Suriname on 14 October 2022. Both Ministers subsequently shared official correspondence to confirm their endorsement of the roadmaps.

## OUTCOME 2: Reliance on evidence-based analysis of crime and violence data to inform national citizen security policymaking

#### A Regional Crime Observatory with the capacity to analyse security data received from countries

Through the support of CariSECURE, the Regional Crime Observatory (RCO) at RSS has been operationalized. The Project developed and shared terms of reference and an organigram, and procured equipment and software for a three-member regional crime observatory. The RCO was officially launched with the signing of the MOU between RSS and USAID at CariSECURE Regional Citizen Security Conference in August 2021. The Observatory continues with the gathering of crime and violence data from RSS member states, which feeds into the region-wide situation report that compares crime statistics in each member state by integrating the ICCS.

CariSECURE also supported the building of data analysis capacity within the RCO at RSS by providing funding for three (3) staff members of the RCO to complete training in IBM Advanced Statistical Analysis using SPSS. Two (2) of the RCO staff completed the SPSS training during Year 6, and the final training opportunity remains valid for the next RCO staff member who is onboarded.

#### Number of Countries capable of producing analysis using the Citizen Security Indicators

All beneficiary countries have completed the exercise of collating police crime statistics (per 10,000 and per 100,000 of pop.) for 5 to 10 years up to 2019, thus generating CariSECURE’s Primary Police Citizen Security indicators for this period. These statistics have also been mapped to the ICCS for a format that is internationally comparable.

The Caribbean Composite Citizen Security Indicator Framework (CCSIF) was developed by CariSECURE following a Regional Citizen Security Data Collection Protocol Conference in June 2017 in Suriname.

The Framework is a multidimensional tool for collecting and reporting citizen security data and monitoring the development and impact of national crime prevention policies. The CCSIF has the capacity to foster data capture and reporting consistent with international standards, such as the International Classification of Crime for Statistical Purposes (ICCS) and the United Nations Convention of the Rights of the Child (UNCRC). It feeds into the work of international agencies such as the United Nations Office on Drugs and Crime (UNODC) and the United Nations Children’s Fund (UNICEF) and can be a tool for tracking national progress towards meeting Sustainable Development Goal (SDG)16.

The CCSIF facilitates crime and violence data collection and reporting along four levels (primary, secondary, policy, and regional) and by key thematic area by country. The thematic areas include police, courts, and prisons, as well as other specialized areas addressing issues such as incest, smuggling, illegal migration, and trafficking in persons.

As CariSECURE’s work pivoted to focus primarily on police forces in the region, the indicators generated were primary police indicators for the period 2010 – 2019. However, as more national data becomes available from various agencies and at other points along the chain of criminal justice, the robustness and adaptability of the framework allow it to expand to meet the data needs at the national, agency and regional level. This augers well for the sustainability and longevity of the framework since institutions will have the option to add agency-specific indicators where necessary. Simply put, the adaptability of the Framework reduces the need for the creation of another tool in future to measure the effectiveness of policies and strategies at various levels.

The CCSIF provides functionality to the ICCS framework since the indicators generated by the CCSIF allow for the global comparability of crime data and trends.  Through the creation and development of national policies and programmes to tackle crime and violence tied to local context and trends, the CCSIF through the ICCS framework provides an opportunity for countries to learn "best practices" or operational/ tactical approaches from countries with similar cultures and crime rates.

#### Number of Countries with the Police Force having Crime Analysis Units with the capability of generating intelligence reports

CariSECURE supported the establishment of Crime Analysis Units in four (4) beneficiary countries – Antigua and Barbuda, Grenada, St Kitts and Nevis and St Vincent and the Grenadines – by facilitating training to bolster regional capacity in the collection and analysis of crime data and providing ICT equipment and software over the course of the Project.

To support the institutionalization of crime analysis, training was completed virtually for 28 representatives of CariSECURE beneficiary countries, RSS and CARICOM IMPACS through a partnership with Arizona State University’s Center for Violence Prevention and Community Safety. Further training of trainers was conducted with five (5) regional trainers from RSS and CARICOM IMPACS on adult learning and facilitation as a sustainability action to integrate crime analysis into the regional capacity-building efforts of these two regional security agencies.

The training programme started initially with both on-site and online delivery in November 2019. This blended approach was used for the first two modules: (1) Crime Analysis Fundamentals and (2) Crime Analysis Process, Data and Purpose. In April 2020, due to the COVID-19 pandemic, the training pivoted to virtual delivery and participants were trained in (3) Spatial Analysis and (4) Applied Strategic, Tactical and Administrative Analysis. As part of the training, participants produced and submitted practical crime analysis reports based on country crime data. The advantage of this approach was that participants were able to develop useful crime analysis products and reports, as the exercises were based on actual country data. It also provided trainees with an appreciation for  available country data. On 14 September 2020, a virtual graduation ceremony was held to recognize the 28 participants who successfully completed the course.

CariSECURE’s Crime Analysis Training of Trainers (TOT) was held virtually for five (5) representatives of RSS and CARICOM IMPACS from November 2020 to February 2021. The TOT trained master trainers from the two regional security agencies in order to facilitate continuing training in crime analysis, provide technical assistance to previously trained crime analysts, and train more analysts throughout the region. A virtual graduation ceremony was held on 23 February 2021 where the Operation’s Manager of the RCO at RSS made a presentation on behalf of the trainers on the 3-year vision for the institutionalization of Crime Analysis regionally.

Building on the CariSECURE Crime Analysis Training of Trainers, a Regional Crime Analysis Trainers working group has been formed by RSS and is working towards developing basic, intermediate, and advanced Crime Analysis Training Courses to be delivered 2 or 3 times annually through the CBSI platform to support the institutionalization of crime analysis within regional police forces.

Additionally, CariSECURE and RSS also partnered on the delivery of on-site Crime Analysis refresher sessions during August and September 2022, to support Grenada, St Kitts and Nevis and St Vincent and the Grenadines in building their crime analysis capacity. The refresher sessions were delivered by an Operations Manager of the RCO who was one of two RCO staff who participated in CariSECURE’s Crime Analysis training of trainers.

The facilitation of the sessions by one of the trained trainers is seen as a natural progression from this and provided an opportunity for RSS to cement themselves as the regional center of excellence for crime analysis.

ICT equipment for crime analysis units was delivered to Antigua and Barbuda, Grenada, St Vincent and the Grenadines and St Kitts and Nevis at the end of 2021. Additionally, SPSS software subscriptions were provided to Crime Analysis Units in Antigua and Barbuda, Grenada and St Vincent and the Grenadines and to the RCO at RSS.

## OUTCOME 3 - Piloting of national citizen security policies and crime victimization surveys to facilitate gathering of survey data indicators, and the development of targeted policymaking to reduce likelihood of youth involvement in crime and violence.

#### Number of Countries with developed response strategies and tactical responses to crime and violence due to information sharing between the Police and relevant agencies and the coordinated support of CariSECURE

No beneficiary countries have achieved this; the delayed PRMIS roll out has severely hindered the results for this indicator. Unfortunately, PRMIS has not had the time to fully realize its potential as its deployment is in its infancy and needs more time to be more extensively used and yield more data for analysis.

In Grenada, however, there is an example of basic use of statistical information from PRMIS at the station level at the South St Georges Police Station, where a customized crime map is used to set up the monthly Action Plan of the station.

At Project closure, CariSECURE was finalizing the Grenada Crime analysis dashboard as a solution for producing more streamlined information to support data-driven policing. This is also viewed as a solution that can also be expanded to other countries once completed.

Synergies have been created between police and other agencies through the Project and forums such as the NTF, the Readiness Managers Working Group, User Acceptance Testing (UAT) sessions and regional training. These synergies support the development of a PRMIS Community of Practice (COP) which has the potential to expand to areas of developing strategies, based on information and data obtained from police and other sources.

#### Number of countries utilizing non-administrative or survey data with the help of CariSECURE to inform national crime and violence strategies with Youth and Gender considerations

CariSECURE has supported both St Lucia and Guyana in using non-administrative data to inform national crime and violence strategies.

St Lucia has utilized the results of the CariSECURE-supported St Lucia National Crime Victimization Survey (2020) to develop a number of recommendations which were shared with the National Task Force, the Department of Youth and their Youth Policy Consultant in St Lucia.

The draft Youth Policy Action Plan’s includes the use of disaggregated citizen security data and the establishment of an evidence-based juvenile justice system based on data, programming to support reintegration of young offenders into communities, community policing initiatives, projects around safe spaces, peaceful communities and environments and initiatives to address cyber bullying and gender-based violence. This draft action plan also mentions CariSECURE as a supporting agency.

The CariSECURE-supported Guyana Women’s Health Life Experiences Survey 2018 provided a rich and detailed source of data on the nature and prevalence of violence against women and girls in Guyana. The survey was cited in the design of Spotlight Guyana and by UNICEF as evidence to support legislative and policy reform under Spotlight Regional and for specific review of domestic violence acts and other work such as drafting laws on harassment.

## TIP Indicators

#### Number of Police Officers with basic TIP skills and training to respond to Trafficking in Persons

CariSECURE completed Basic Training on the modalities of Human Trafficking for 51 officers of the Barbados Police Service in August 2021.

#### Number of Police Officers with enhanced specialized TIP skills and training to respond to Trafficking in Persons

Advanced Investigative Training carried out on 1 - 5 November 2021 for 15 police officers of BPS. The 5-day training included training on Investigative Techniques for the Prevention of Trafficking in Persons.

#### National Survey completed on public knowledge and perception of TIP

CariSECURE completed the TIP Knowledge and Perception survey, and the findings and recommendations were previously shared with the Barbados National Task Force for the Prevention of Trafficking in Persons and the Office of the Attorney General (OAG) during the last quarter of 2021. Additionally, a synopsis of the results was shared with the public during a presentation at the launch of the TIP Public Awareness Materials and Campaign in March 2022.

CariSECURE’s Crime Analysis Training of Trainers (TOT) was held virtually for five (5) representatives of RSS and CARICOM IMPACS from November 2020 to February 2021. The TOT trained master trainers from the two regional security agencies in order to facilitate continuing training in crime analysis, provide technical assistance to previously trained crime analysts, and train more analysts throughout the region. A virtual graduation ceremony was held on 23 February 2021 where the Operation’s Manager of the RCO at RSS made a presentation on behalf of the trainers on the 3-year vision for the institutionalization of Crime Analysis regionally.

Building on the CariSECURE Crime Analysis Training of Trainers, a Regional Crime Analysis Trainers working group has been formed by RSS and is working towards developing basic, intermediate, and advanced Crime Analysis Training Courses to be delivered 2 or 3 times annually through the CBSI platform to support the institutionalization of crime analysis within regional police forces.

# Challenges, Management and Administrative Issues

CariSECURE faced several challenges related primarily to the impact of COVID-19 at a key stage in project implementation, significant delays in the delivery of equipment for the CVDW at IMPACS and police forces, staff retention and management changes, country elections and changes in administrations that resulted in shuffling of key national focal points, hurricanes and other natural events compounded with national counterparts’ capacity challenges.

Departure of Key Project Staff

The Project faced challenges due to the departure of key project team members at various points during the life of the Project. Most recently, this included the Team Lead in January 2022 and the Project Associate in March 2022. The Project has also been without an ME Analyst and Procurement Associate for long periods.  The departure of key project personnel near the end of the project is documented in the risk register and has become a challenge as the project team has been stretched during the implementation of various project activities. The project has flagged this issue, and support from the wider UNDP country office, specifically the Poverty and Governance cluster has allowed for the continuity of project activities.

Presently, staff of the Poverty and Governance cluster are supporting activities of both CariSECURE 1.0 and the operationalization and implementation of the follow-on project CariSECURE 2.0, and this transition has resulted in overlaps while recruitment takes place for CariSECURE 2.0

Impact of the COVID-19 Pandemic on CariSECURE implementation

The impact of the COVID-19 pandemic posed a major challenge to the Project’s activities. CariSECURE continued to implement via its virtual strategy, making the necessary adjustments by engaging in remote working sessions and using web conferencing technologies such as Zoom and Microsoft Teams to conduct and host meetings, workshops, and training sessions. While the pivot to virtual has allowed activities to continue, the preference for face-to-face delivery and the level of engagement it offers has been noted by participants and facilitators.

Limited Human Capital in Beneficiary Countries

Beneficiary countries experienced challenges from increased demand on human capital as a result of the pandemic and required policing action. The pandemic has been a national priority in all beneficiary countries and the Police Forces, a key stakeholder group for the project, are on the frontlines of the response efforts.  The challenge of maintaining support and responsiveness of focal points and other key partners was a challenge in this environment, particularly during periods of heightened national activity where these agencies have been doubly overwhelmed by national demands.

IMPACS Data Warehousing Technical Design and Procurement of Equipment

The pandemic’s impact on supply and shipping logistics have continued to affect the delivery of the data warehousing solution at CARICOM IMPACS. Given the delays to the delivery of the required servers and other ICT equipment, IMPACS initially extended their contracts with their vendors to 28 February 2022 and subsequently to 31 May 2022. This situation was also exacerbated by ICT storage manufacturer’s (DELL) mandating that their engineers deploy/install all storage related equipment as a requirement to validate and activate the system warranty. Additionally, DELL supports and services the Caribbean Region with their resources deployed/based in Panama; given the existing Covid-19 protocols in Trinidad and Tobago, there were additional mandatory quarantine periods for technical personnel.

The rollout of PRMIS to countries was dependent on the delivery of the crime and violence data warehouse (CVDW) at IMPACS. These delays forced the Project to amend timelines for the delivery of PRMIS and amend the contract with the software developers.

Station Connectivity Issues

St Vincent and the Grenadines, St Kitts and Nevis and Antigua and Barbuda faced challenges around station readiness and connectivity over the course of the Project. Issues have been related primarily to the quality of the ISP network, cabling, access to existing servers and switches and a need for designated furniture to house equipment at some of the older stations. CariSECURE dialogued with key country focal points and Readiness Managers to address these issues and most of the stations across the beneficiary countries are PRMIS-ready.

Commitment/Buy-in in Suriname

Suriname also presented a special challenge over the course of the Project. The language difference, coupled with differences in policing systems led to issues with engagement. Concerns also arose about the level of commitment and buy-in in Suriname. These communication challenges and responsiveness issues with the KPS necessitated substantial changes to be made to PRMIS in order to meet the requirements of the KPS. Given the change in scope, these changes came at a cost which the Project was unable to accommodate as it approached closure. CariSECURE confirmed with the Ministry of Justice and the Police in Suriname that it may be incumbent on the Surinamese government to mobilize resources for these changes to be made and for PRMIS to be a workable solution for the KPS.

Mount Soufriere Eruption in St Vincent and the Grenadines

The eruption of Mount Soufriere Volcano in St Vincent presented a major challenge during the period. This disaster had far reaching effects with ashfall experienced as far off as Barbados and other islands of the Eastern Caribbean, forcing evacuation of certain parts of the island. Under these circumstances, working with this beneficiary country was challenging as already stretched police resources had to support emergency efforts as well as ensure their own wellbeing during the period of the disaster. This was particularly concerning as the island is a Tier 1 country.

Leahy Law and the Royal Saint Lucia Police Force (RSLPF)

The Leahy Law was imposed on the Royal St. Lucia Police Force for the duration of the Project. This prohibited the use of United States Government funding on activities related to the RSLPF and CariSECURE could not apply Project funding from USAID to support, training or equipment to any members of the RSLPF. The Project was able to source alternative funding to provide a functional Crime Information Management System (CIMS) to the Government of St. Lucia but the RSLPF was unable to benefit from the wider training and support and has struggled to deploy the application.

# Lessons Learnt

- The scale and scope of the results and resources framework for the project needs to be reflective of the idiosyncrasies of the various countries and beneficiaries and should be attainable with the available resources and the allotted time. Moreover, managing expectations of stakeholders – national counterparts, donors and other development partners – by adapting project targets to changing realities on the ground is paramount to project success and should be embedded in the stakeholder engagement strategy.

- Connected to this, project results targets should reflect both end-of-project expectations as well as well-defined interim milestones that represent key steps to achieving the final objective. In the case of CariSECURE, project targets were mainly at the outcome and impact levels, making it difficult to track progress objectively throughout implementation. These milestones should be appropriate to the context of the countries, the timeline of the project and the available resources. This approach has been taken to the design of CS2.0 and annual workplans include clearly articulated interim targets.

- Results-based management should be mainstreamed throughout implementation. Such an approach would have allowed more iterative activities that would have produced results earlier. For example, a more strategic focus on capacity building on development of strategies from existing data (Outcome 3), rather than waiting on data from PRMIS.

- Project champions at all levels e.g. Commissioners, Trainers, Readiness Managers, Permanent Secretaries are crucial to sustain government buy-in and commitment to results. The success of CariSecure was attributable in part to the strong team of readiness managers who drove the project at the national level and supported the project management unit (PMU) by providing important intelligence on what was happening locally. The design of CariSecure 2.0 has sought to build on this success by leveraging the engagement of the readiness managers and expanding this approach to identify strong national focal points involved in youth crime prevention and response.

- Sustainability needs to be embedded in all elements of the programme. The project focused on the sustainability of some important outputs, including capacity building. A Training of Trainers approach was taken and RSS was capacitated to take on the role post-project. In other areas, some gaps in sustainability of other key outputs, including the PRMIS platform, created some uncertainty regarding roles and responsibilities post-project. This knowledge has been reflected in the design of CS2.0, which will focus on identifying and engaging local, regional and international partners from project inception to ensure that a sustainability plan for phasing out, down and over of key outputs is agreed early in the project lifecycle.

# Actions Taken in Response to Previous AOR/COR Feedback

The AOR has provided feedback to improve Project delivery and sustainability. More specifically the following actions were undertaken on the advice of the AOR:

- Temporary solution for CVDW at CARICOM IMPACS. On the advice of the AOR, CariSECURE approached CARICOM IMPACS to allow temporary use of their existing servers to mitigate delays in delivery of equipment for the CVDW. IMPACS supported this and commenced communication with CariSECURE and Softengi around the technical requirements and the configuration of servers. Ultimately, the temporary solution was not required but the process jump-started dialogue around server configuration which expedited the deployment of PRMIS at the CVDW.

- High-level Endorsement of the ICT Roadmaps. The AOR also guided the Project towards Cabinet endorsement of ICT Roadmaps. This influenced the two-tiered approach resulting in the presentation of Roadmaps at both the technical and Ministerial levels in beneficiary countries. While securing presentations with focal point Ministers was a challenge, the endorsement of the Attorney General in Antigua and Barbuda, provided the impetus to deploy PRMIS in all police stations by December 2022.

- Dialogues with key stakeholders in Guyana.  Based on feedback from the AOR, CariSECURE actioned presentations and discussions on the Project to Guyana’s Minister for Home Affairs in April 2021 and subsequently to the Guyana Police Force’s newly appointed Commissioner in August 2022, to address concerns about the CVDW.  These engagements prompted written approval for CariSECURE’s data warehousing solution from the Minister of Home Affairs and verbal approval from the new Commissioner subsequently.

CariSECURE also engaged with and supported IDB in the design/development of their Criminal Justice System Programme in Guyana. The AOR prompted monthly meetings to share updates and discuss synergies. Discussions centered on the integration of the PRMIS with the IDB’s Digital Justice Platform. The teams demonstrated the key functions of the systems and touched upon the technical points that should be additionally studied to facilitate interoperability between the systems.

- Recommendations for the Caribbean Citizen Security Conference. The AOR shared feedback  around the concept and content of CariSECURE’s Virtual Citizen Security Conference, such as guidance on the inclusion of presenters and participants for the Donors and Partners Forum which was a key partnership-building activity during the conference. Additionally, the project actioned AOR suggestions around the formation of a planning committee, invited key stakeholders to be a part of the planning and organizing process and signed a letter of agreement with the Organisation of Eastern Caribbean States (OECS) to provide technical support with the virtual fair platform being used for the event.

- Senior Management meetings between UNDP and CARICOM IMPACS. To improve communication between UNDP and CARICOM IMPACS. The Project implemented monthly management level meetings with CARICOM IMPACS in recognition of their centrality to the sustainability of PRMIS.

# Annexes

## Financials as of 31 December 2022

| 1. Award Modification | 9,965,000.00 |
| --- | --- |
| 2. Actual Expenditure | 2016-2022 |
| Contractual Services | 3,947,083.43 |
| Staff and other personnel costs | 1,779,251.55 |
| Travel | 1,086,026.39 |
| General Operational Costs and Direct Costs | 1,507,402.45 |
| Material and Equipment | 665,238.10 |
| Programme Support Costs | 723,971.17 |
| Total Expenditures | 9,710,681.36 |

As per UNDP policy, a final financial report will be submitted to USAID by Global Shared Services Center Unit.

## Summary of Indicator Results

| OUPUT INDICATORS | COUNTRY LEVEL |  |  |  |  |  |  |  |  | REGIONAL |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | EASTERN AND SOUTHERN CARIBBEAN |  |  |  |  |  |  |  |  | PROJECT TARGETS |  | RESULTS to Date (JULY 2016 – OCTOBER 2022) |  | VARIANCE |  | COMMENTS/REMARKS |
|  | GUY | SLU | SKN | ANB | GRN | SVG | BAR | SUR |  |  |  |  |  |  |  |  |
| Output 1: Standardized and disaggregated crime data reporting within and among national authorities to foster the reliance on valid, reliable, and comparable data on citizen security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Number of countries with government approved Caribbean Security Toolkit | * | * | * | * | * | * | * | * | 8 |  | 8 |  | 0 |  | Achieved. All project countries have endorsed the Project Tool Kits. |  |
| 1.2 Number of countries with draft Correspondence Tables for International Classification of Crime for Statistical Purposes (ICCS) | * | * | * | * | * | * | * | * | 8 |  | 8 |  | 0 |  | Achieved. All countries have completed and submitted draft correspondence tables with common offences (i.e. those most frequently occurring in their jurisdictions). |  |
| 1.3 Number of Countries with Digitized Applications for Police as a result of CariSECURE’s Assistance | * | * | * | * | * | * | * | * | 7 |  | 7 |  | 0 |  | Achieved. PRMIS development is now complete, and the application has been deployed for police across all beneficiary countries at the IMPACS data warehouse. A staging environment for testing and training and a production (live) environment for PRMIS has been created for each country on the servers at the CVDW and connections tested for all countries. |  |
| 1.4 Number of Tier I countries with 75% of police stations with digitized police application capable of collecting and producing crime statistics report |  |  |  |  | * | * | * |  | 3 |  | 1 |  | 0 |  | Partially Achieved. In Grenada, PRMIS is live and in use at 11 stations and have met their 75% target. In Barbados, seven (7) stations have deployed PRMIS (56%). Upsurge in gun violence and other crimes has pulled police human resources away from PRMIS deployment. St Vincent has completed training but is yet to go fully live with PRMIS. The RSVGPF has been impacted by connectivity and station readiness issues. PRMIS deployed at two (2) of the island’s largest stations and at key departments. |  |
| 1.5 Number of Tier I countries with 75% of police stations utilizing mobile technology |  |  |  |  | * | * | * |  | 3 |  | 0 |  | -3 |  | Not Achieved. Police Forces have opted to finalize in-station PRMIS deployment before its use in the field. The Project has been primarily focused on supporting Police Forces in these efforts. While the tablets have received some use for the training of officers, the devices are yet to be utilized by countries in the field. The Project advocated for the use of the systems once PRMIS goes live, including relevant recommendations in the ICT roadmaps that are being presented to government for validation and endorsement. |  |
| Output 2: Utilization of evidence-based analysis of crime data to inform citizen security strategies, programmes, and policies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 A sub-regional crime observatory with the capacity to analyse security data received from countries |  |  |  |  |  |  |  |  | 1 |  | 1 |  | 0 |  | Achieved. The RCO is operationalized with full staffing. |  |
| 2.2 Number of countries capable of producing analysis using the Citizen Security Indicators | * | * | * | * | * | * | * | * | 8 |  | 8 |  | 0 |  | Achieved. All beneficiary countries have generated citizen security indicators for Police (per 10,000 afnd per 100,000 of pop.) for at least 5 years, further refined with the use of the ICCS Correspondence Tables. Therefore, CariSECURE’s primary police crime indicators are available in a format that is internationally comparable. |  |
| 2.3 Number of Countries with the Police force having Crime Analysis Units with the capability of generating intelligence reports |  |  | * | * | * |  |  |  | 3 |  | 4 |  | 1 |  | Achieved. Police forces in Antigua and Barbuda, Grenada, St Vincent and the Grenadines and St Kitts and Nevis have established Crime Analysis (CA) Units. Equipment for units was delivered to countries by RSS and software (SPSS) licences procured. |  |
| Output 3: Improved decision-making on youth crime and violence based on available evidence at national levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Number of Countries with developed response strategies and tactical responses to crime and violence due to information sharing between the Police and relevant agencies and the coordinated support of CariSECURE | * | * | * | * | * | * | * | * | 8 |  | 0 |  | -8 |  | Not Achieved. The delayed PRMIS roll out significantly impacted this indicator, as data from PRMIS is not yet available to develop strategies and tactical responses to crime and monitor trends. PRMIS deployment is in its infancy with most countries commencing implementation between August and September 2022. The Project is working closely with countries and RSS to institutionalize the use of PRMIS data. In Grenada, a dashboard is under development to spur PRMIS reports being used to develop crime response strategies. The Project is working to develop a framework for PRMIS outputs, to be utilized by RSS. |  |
| 3.2 Number of countries utilizing non-administrative or survey data with the help of CariSECURE to inform national crime and violence strategies with Youth and Gender considerations | * | * |  |  |  |  |  |  | 1 |  | 2 |  | 1 |  | Achieved. St Lucia’s (draft) Youth Policy Action Plan’s section on Safety Security and Peaceful Coexistence includes activities from CariSECURE’s recommendations, developed from analysis of the results of the SLNCVS and existing administrative crime data. The Action Plan mentions the work of CariSECURE as a supporting agency. Data from the Women’s Life and Health Survey (WLHS, Guyana) which was supported by CariSECURE was referenced for the development of Spotlight Guyana and has been used by UNICEF as background for legislative and policy reform under Spotlight Regional and for specific review of domestic violence acts and other legislative work; WLHS also referenced in advocacy initiatives. |  |
| TIP Indicator 3.3: # of Police Officers with basic TIP skills and training to respond to Trafficking in Persons |  |  |  |  |  |  | * |  | 60 |  | 51 |  | -9 |  | Partially Achieved. 51 officers (85%) of the targeted 60 officers were trained on basic TIP skills. |  |
| TIP Indicator 3.4: # of Police Officers with enhanced specialized TIP skills and training to respond to Trafficking in Persons |  |  |  |  |  |  | * |  | 40 |  | 15 |  | -25 |  | Partially Achieved. Advanced Investigative Training on TIP delivered to 15 (38%) of targeted 40 officers of BPS. The number of officers who could participate in this training was reduced due to COVID-19 health and safety protocols. Training around drafting of TIP SOPs will be delivered in October 2022. |  |
| TIP Indicator 3.5: National Survey completed on public knowledge and Perception of TIP |  |  |  |  |  |  | * |  | 1 |  | 1 |  | 0 |  | Achieved. TIP knowledge and perception survey completed, with results/findings disseminated and shared with National Task Force for the Prevention of TIP and subsequently with the public during the launch of the Government’s TIP Public Awareness Campaign during Y6 Q2. |  |

## project achievements

Terminal Evaluation of the Project: “Strengthening Evidence Based Decision Making for Citizen Security in the Caribbean (CariSECURE)”, SANCHIS MUNOZ, G., 2022 (internal)

Rapid Assessment of CariSECURE’s Police Reporting Crime Information System (PRMIS), Ramsaran, S., USAID Rule of Law Specialist, CariSECURE Agreement Officer’s Representative (AOR), 2020 (internal)