745附件Annex 1.   南南合作援助基金项目季度简报

GDF Project Quarterly Update

项目名称 Project title：

Towards decent work for people with disabilities in Turkmenistan: transforming social enterprises into meaningful training and employment opportunities

项目预算Project budget：

USD 1,500,000.00 (including USD 60000 contribution by UNDP Turkmenistan)

报告期Report Period:       Year 2023      Quarter 1

提交日期 Reporting Date：年（2023）月（11）日（04）

- 花费情况	Estimated expenditure:

1.1本季度花费	Estimated expenditures of reporting period (no need to be certified)：

USD:  71,210.03

1.2累计花费	Accumulated expenditures：

USD:  770,603.71, of which 136,470 actual expenditure and 634,133.74 commitment (combined for 2020-2023)

- 受益情况		Beneficiary Statistics

2.1本季度受益人数 Beneficiary number of reporting period:

No new beneficiaries in the reporting period

2.2累计受益人数Accumulated beneficiary number:

66 members of the Blind and Deaf Society of Turkmenistan, of which 43 are women, trained online by Chinese experts and in person by trained trainers of the BDST on disability equality issues in Ashgabat, Mary and Turkmenabat.

- 本季度主要项目活动 Milestone project activities:

- Procurement and delivery of printing equipment for the printing workshop of the BDST in Ashgabat has been completed. Once the company provides all custom clearance documents, the payment for the printing equipment will be finalized.

- Reconstruction of the BDST printing workshop in the city of Ashgabat was completed.

- Contracts for reconstruction of the remaining two BDST workshops in the cities of Mary and Turkmenabat are to be awarded to the same winning bidder following the receipt of the second tranche.

- Sewing equipment for two BDST workshops in the cities of Mary and Turkmenabat were partially received and are to be kept at the warehouse of the BDST sewing workshops until completion of reconstruction works to be started after the receipt of the second tranche.

- Two national consultants were selected for technical supervision of the BDST production facilities in Mary and Turkmenabat. Contracts will be raised following the allocation of the second tranche and the start of reconstruction of the two facilities.

- 本季度重大事件 Major event(s)

  - 高级别访问Is there any high-profile visit? If so, please brief.

No high-profile visits in Q1.

4.2 对项目实施产生重大影响的外部环境变化或内部挑战Is there any event, incident, challenge and change that significantly affected project implementation? If so, please brief.

The project’s remaining balance is insufficient to cover the total cost of civil works at two production facilities of the BDST in the cities of Mary and Turkmenabat. Despite the project applied for the allocation of the second tranche in November 2022, funds were not received.  The project had to re-apply for the 2nd trance in early 2023 again. Implementation of the remaining activities depends on allocation of funds. Activities under Output 3 related to vocational skills training, supported employment and transition to an open market employment for people with disabilities, which were not initialized in 2022 due to the concern of budget overruns on purchase of equipment and major overhaul of the BDST production facilities, will be finalized after the receipt of the second tranche and making contracts of reconstruction of sewing workshops.

4.3下季度主要活动Planned key activities of the next quarter

Output 1: Capacity of the BDST to help its members gain access to quality vocational training and decent work increased

All activities under this output were completed in 2021

Output 2:  Three selected Training and Production Enterprises (TPEs) of the BDST modernized and reequipped

- Completion of delivery sewing equipment to the BDST sewing workshops in the cities of Mary and Turkmenabat

- Completion of installation of printing equipment at the BDST printing workshop in Ashgabat.

- Awarding contracts to the winning bidder and starting reconstruction (overhaul works) of the BDST sewing workshops in the cities of Mary and Turkmenabat following the receipt of the second tranche

- After the overhaul works are completed, installation of sewing equipment at the BDST sewing workshops in the cities of Mary and Turkmenabat

Output 3: Transformation plan for selected enterprise to become sustainable models of vocational skills training, supported employment and transition to an open market employment for people with disabilities

- Contracting a national expert to develop a manual on apprenticeship (hiring, induction training, on-job training, accessibility of workplace) for newly hired blind and deaf people under mentorship of BDST production specialists.

- Sending the draft manual to Chinese experts for review and sharing Chinese experience on mentorship for inclusion into the manual

- Contracting two national experts for review of the existing gaps and development of recommendations to promote vocational education for people with disabilities at the state level and review of the existing gaps and development of recommendations to promote employment of PWDs in the open labor market by the state-owned and private organizations, considering the social model of disability. Holding relevant workshops to discuss the recommendations with relevant national stakeholders.

- Sending draft reports to Chinese experts for review and sharing Chinese experience.

- Contracting a national expert for development of a training programme and training of staff to operate new sewing equipment

- Development of a training programme and training of staff to operate new printing equipment by the already contracted national expert.

- 其他您认为可以报告的事项Other issue(s)

All existing contracts with national experts and international companies were extended into 2023.

In 2022, UNDP in Turkmenistan made a contribution from TRAC in the amount of USD 13 985 to the project activities under Output 2 at the expense of its commitment to the project management budget on condition of reversing this amount in 2023 from the donor funds for the project management budget. Therefore, in 2023, project management expenditure will be 13, 985.

报告编制说明：

乙方应对照项目文件中的活动计划，向甲方提交书面季度简报。

乙方须按规定格式完整准确填写,简报内容应至少涵盖到报告季度最后一个月的25号。甲方将对照工作计划等依据文件审核后，编报南南基金项目进展情况报告。

除非双方另有书面协定，否则简报必须在每季度结束后5天内（自然日）提交。

Guidance:

Party B shall submit to Party A quarterly updates according to the work plan of the project documents.

Party B shall completely and accurately finish the updates in the form as required. The updates shall cover the period to the 25th of the last month of the reporting quarter.Party A shall prepare the GDF Project Progress Report after reviewing the updates in accordance with the work plan and other documents.

Party B shall submit the updates within 5days (calendar days) after each quarter unlessotherwisespecified by the parties inany written agreement