745附件Annex 1.   南南合作援助基金项目季度简报

GDF Project Quarterly Update

项目名称 Project title：

Towards decent work for people with disabilities in Turkmenistan: transforming social enterprises into meaningful training and employment opportunities

项目预算Project budget：

USD 1,500,000.00 (including USD 68,000 contribution by UNDP Turkmenistan)

报告期Report Period:       Year 2023      Quarter 2

提交日期 Reporting Date：年（2023）月（July）日（10th）

- 花费情况	Estimated expenditure:

1.1本季度花费	Estimated expenditures of reporting period (no need to be certified)：

USD: 587,740.95 as per AAA report (Q1 was 71,210.03)

1.2累计花费	Accumulated expenditures for 2023：

USD: 1 003 328.66, of which 662,389.95 is actual expenditure 340,938.72 is commitment as per PBB report.

- 受益情况		Beneficiary Statistics

2.1本季度受益人数 Beneficiary number of reporting period:

About 25 personnel of the printing workshop of the Training and Production Enterprises (TPEs) of the BDST in Ashgabat are trained on operating and maintaining the new printing equipment, other than the paper bag making equipment. Training will be continued once paper bag making equipment is commissioned.

2.2累计受益人数Accumulated beneficiary number:

Accumulated beneficiary number is about 91 people:

- 66 members of the Blind and Deaf Society of Turkmenistan, of which 43 are women, trained online by Chinese experts and in person by trained trainers of the BDST on disability equality issues in Ashgabat, Mary and Turkmenabat;

- About 25 personnel of the TPE BDST completed training on all installed and commissioned printing equipment, other than paper-bag making machine

- 本季度主要项目活动 Milestone project activities:

- Installation, start-up, and commissioning of equipment at the printing workshop of the BDST in Ashgabat have almost been completed, other than one equipment, a paper-bag making machine. Payment (95% of the contract) for the delivery of equipment (in accordance with the technical specifications) has been completed and the remaining of the payment will be accomplished after completion of all installation, start-up and commissioning of equipment, and provision of an official document on the warranty maintenance of equipment.

- Training has been completed on all installed and commissioned printing equipment, other than paper-bag making machine.

- The winning company has been awarded a contract after the project received the 2nd tranche, and it started the reconstruction of the BDST sewing workshops in the cities of Mary and Turkmenabat. The reconstruction works are expected to be completed by September 30, 2023.

- 2 national consultants were hired to accomplish the quality supervision of the reconstructions works being implemented in two BDST enterprises located in different regions of the country (Mary and Turkmenabat)

- Sewing equipment for two BDST workshops in the cities of Mary (Mary region) and Turkmenabat (Lebap region) were fully delivered and are to be kept at the warehouse of the BDST sewing workshops until completion of reconstruction works. Payment for delivery completed and the remaining payment will be made after installation and commissioning of sewing equipment.

- 本季度重大事件 Major event(s)

  - 高级别访问Is there any high-profile visit? If so, please brief.

No high-profile visits in Q2.

4.2 对项目实施产生重大影响的外部环境变化或内部挑战Is there any event, incident, challenge and change that significantly affected project implementation? If so, please brief.

The second tranche was received too late that caused delay in starting reconstruction works at two Training and Production Enterprises of the BDST (Mary and Turkmenabat).

4.3下季度主要活动Planned key activities of the next quarter

Output 1: Capacity of the BDST to help its members gain access to quality vocational training and decent work increased

All activities under this output were completed in 2021

Output 2:  Three selected Training and Production Enterprises (TPEs) of the BDST modernized and reequipped

- Complete start-up and commissioning of the remaining printing equipment at the BDST printing workshop in Ashgabat

- Completion of the overhaul works in BDST sewing workshops in Mary and Turkmenabat

- Completion of installation and commissioning of sewing equipment at the BDST sewing workshops in the cities of Mary and Turkmenabat

- Hiring a consultant to implement the quality supervision of the installation, start-up and commissioning of sewing equipment at the BDST sewing workshops in the cities of Mary and Turkmenabat

Output 3: Transformation plan for selected enterprise to become sustainable models of vocational skills training, supported employment and transition to an open market employment for people with disabilities

- Recruitment process was completed and the contract to be signed with a national expert to develop a manual on apprenticeship (hiring, induction training, on-job training, accessibility of workplace) for newly hired blind and deaf people under mentorship of BDST production specialists.

- The draft manual on apprenticeship (hiring, induction training, on-job training, accessibility of workplace) for newly hired blind and deaf people to be sent to Chinese experts for review and sharing Chinese experience on mentorship for inclusion

- Recruitment process was completed for two national experts for review of the existing gaps and development of recommendations to promote vocational education for people with disabilities at the state level and review of the existing gaps and development of recommendations to promote employment of PWDs in the open labor market by the state-owned and private organizations, considering the social model of disability. Contracts to be concluded and relevant workshops to be held to discuss the recommendations with relevant national stakeholders.

- The draft reports to be sent to Chinese experts for review and sharing Chinese experience.

- Contracting a national expert for conducting a training of staff to operate new sewing equipment

- Onsite training of BDST personnel on operating and maintenance was completed by the already contracted national expert. Once paper-making machine is commissioned, its training will also be completed.

- 其他您认为可以报告的事项Other issue(s)

The expenses of running the project in Turkmenistan (Project staff) were put under Activity 2 and Activity 3, which sums up to USD 13,985.

报告编制说明：

乙方应对照项目文件中的活动计划，向甲方提交书面季度简报。

乙方须按规定格式完整准确填写,简报内容应至少涵盖到报告季度最后一个月的25号。甲方将对照工作计划等依据文件审核后，编报南南基金项目进展情况报告。

除非双方另有书面协定，否则简报必须在每季度结束后5天内（自然日）提交。

Guidance:

Party B shall submit to Party A quarterly updates according to the work plan of the project documents.

Party B shall completely and accurately finish the updates in the form as required. The updates shall cover the period to the 25th of the last month of the reporting quarter. Party A shall prepare the GDF Project Progress Report after reviewing the updates in accordance with the work plan and other documents.

Party B shall submit the updates within 5days (calendar days) after each quarter unless otherwise specified by the parties in any written agreement