745附件Annex 1.   南南合作援助基金项目季度简报

GDF Project Quarterly Update

项目名称 Project title：

Towards decent work for people with disabilities in Turkmenistan: transforming social enterprises into meaningful training and employment opportunities

项目预算Project budget：

USD 1,500,000.00 (including USD 60,000 contribution by UNDP Turkmenistan)

报告期Report Period:       Year 2023      Quarter 3

提交日期 Reporting Date：年（2023）月（October）日（13th）

- 花费情况	Estimated expenditure:

1.1本季度花费	Estimated expenditures of reporting period (no need to be certified)：

USD: 544,523.99

1.2累计花费	Accumulated expenditures:

USD: 1,147,094.05 of which 1,049,462 (including all years) is actual expenditure and 97,631.97 – commitment. For 2023, actual expenditure - 984,202.12, commitment - 97,631.97.

- 受益情况		Beneficiary Statistics

2.1本季度受益人数 Beneficiary number of reporting period:

A round-table on promoting employment and vocational education for people with disabilities gathered about 25 government officials on September 15, 2023. Recommendations were drafted on promoting employment and vocational education for people with disabilities in Turkmenistan.

On October 17, 2023, a roundtable was conducted to finalize the recommendations on promoting employment and vocational education for people with disabilities gathered about 25 people.

Cardboard and printing equipment procured within the project was transferred to the BDST, where currently 27 people work. In the future, it is expected that BDST printing workshop will increase its employees from 27 to about 45 in the coming 12 months. Including the families of currently employed beneficiaries are 135 (27x5).

Trainings on working with cardboard and printing equipment were continued during the month of August – October, 2023 benefitting about 27 currently employed staff of the BDST. Training were conducted to individual employees to improve their skills to work on specific equipment, such as paper bag making and offset machines, as well as in group formats.

Overhaul works at the venues of sewing workshops are almost complete. Installation and commissioning act for Mary was signed, which means they are ready to operate. Turkmenabat will be completed in coming weeks. Better working conditions, with proper ventilation, cooling and heating systems, were created to employees of both sewing workshops: 87 (45+42)

Sewing equipment for Mary sewing workshop was installed and commissioned, where currently 45 employees and their income will be improved with the new capacity of the sewing workshop. Thus, indirect number of beneficiaries 225 (45x5). BDST envisaged to increase the number of its employees from 45 to 55 in coming 12 months.

“Strategy for developing the capacity of the BDST and plans and business strategies for marketing activities for three Training and Production Enterprises of the BDST” and “Manual on mentoring in the workplace for visually and hearing impaired people of the Training and Production Enterprises of the Society of the Blind and Deaf of Turkmenistan” benefitted all members of the BDST. The manual on mentoring will be integrated to all 10 enterprises of the BDST benefitting all members. Currently BDST has 3826 members, as of October 1, 2023.

2.2累计受益人数Accumulated beneficiary number:

Accumulated beneficiary number is about 4197, including beneficiaries from previous activities:

- 66 members of the Blind and Deaf Society of Turkmenistan, of which 43 are women, trained online by Chinese experts and in person by trained trainers of the BDST on disability equality issues in Ashgabat, Mary and Turkmenabat;

- Training for the BDSP employees – 45 (25 in June, 2023).

- 本季度主要项目活动 Milestone project activities:

- Start-up and commissioning of the printing equipment at the BDST printing workshop in Ashgabat is completed and Transfer of Title for printing equipment was officially signed by BDST and UNDP.

- Installation of sewing equipment at BDST workshops in Mary and Turkmenabat is completed. Works on start-up and commissioning of the sewing equipment is being continued. Payment (95% of the contract) for the delivery of sewing equipment (in accordance with the technical specifications) has been completed and the remaining of the payment will be accomplished after completion of all start-up and commissioning of sewing equipment, and provision of an official document on the warranty maintenance of equipment.

- Reconstruction of the BDST sewing workshops in the cities of Mary and Turkmenabat is in final stages. Reconstruction works are expected to be completed by November 30, 2023, due to requested by BDST additional works in Turkmenabat sewing workshop on repairing corridors and halls that connect sewing workshop rooms.

- Two construction engineers are implementing the quality supervision of the reconstructions works being implemented in two BDST enterprises located in different regions of the country (Mary and Turkmenabat).

- A national consultant was hired to supervise installation, start-up and monitoring of sewing equipment in Mary and Turkmenabat.

- A national consultant was hired to develop training materials for trainings at sewing workshops in Mary and Turkmenabat.

- Manual on Apprenticeship at workplace for people with disabilities was completed by the UNDP hired national consultant and shared with Chinese experts for their input

- Round-tables on promoting vocational education and employment for people with disabilities were conducted on September 15, 2023 and October 17, 2023 and draft recommendations developed was shared officially with national partners for their inputs. Feedback from Mejlis of Turkmenistan, Institute of State, Law, and Democracy and Ministry of Labour and Social Protection of Population of Turkmenistan was received on behalf of national partners.

- 本季度重大事件 Major event(s)

  - 高级别访问Is there any high-profile visit? If so, please brief.

Visit of Chinese delegation is planned for October 23 -26, including the South-South Forum on October 26 with in-person participation of 70 government official and representatives of civil society organizations.

4.2 对项目实施产生重大影响的外部环境变化或内部挑战Is there any event, incident, challenge and change that significantly affected project implementation? If so, please brief.

4.3下季度主要活动Planned key activities of the next quarter

Output 1: Capacity of the BDST to help its members gain access to quality vocational training and decent work increased

All activities under this output were completed in 2021

Output 2:  Three selected Training and Production Enterprises (TPEs) of the BDST modernized and reequipped

- Start-up and commissioning of the sewing equipment at the BDST sewing workshops in Turkmenabat. Handover of the equipment to the BDST for both Mary and Turkmenabat.

- Completion of the overhaul works in BDST sewing workshop in Turkmenabat. Handover to the BDST.

Output 3: Transformation plan for selected enterprise to become sustainable models of vocational skills training, supported employment and transition to an open market employment for people with disabilities

- Training of the BDST management by the Chinese experts

- South-South Forum

- Trainings at sewing workshops in the cities of Mary and Turkmenabat, planned for November.

- 其他您认为可以报告的事项Other issue(s)

报告编制说明：

乙方应对照项目文件中的活动计划，向甲方提交书面季度简报。

乙方须按规定格式完整准确填写,简报内容应至少涵盖到报告季度最后一个月的25号。甲方将对照工作计划等依据文件审核后，编报南南基金项目进展情况报告。

除非双方另有书面协定，否则简报必须在每季度结束后5天内（自然日）提交。

Guidance:

Party B shall submit to Party A quarterly updates according to the work plan of the project documents.

Party B shall completely and accurately finish the updates in the form as required. The updates shall cover the period to the 25th of the last month of the reporting quarter. Party A shall prepare the GDF Project Progress Report after reviewing the updates in accordance with the work plan and other documents.

Party B shall submit the updates within 5days (calendar days) after each quarter unless otherwise specified by the parties in any written agreement