Project Progress Report

January to June 2026

Prepared by 
the Project Management Unit

June 2026

Index

Introduction	3

Project Information	3

Objective of the project	3

Project Funding Entity	3

Project Executor	3

The entity supervising the follow-up of the implementation of the project	3

Project Implementation Period	4

Project work and activities during the reporting period	4

The first component: protection works in the Delta	4

Component Two: Preparation of the Integrated Coastal Zone Management Study	4

Evaluation Study of the First Phase of Community Development Projects in Kafr El-Sheikh	9

Community Development Projects in Kafr El Sheikh	9

Coastal Forecast System	9

Early Warning System	9

Coastal Modeling:	10

Activities of the project's communications component	10

	Community Awareness Plan:	10

	Gender Plan:	10

# Introduction

This report provides a summary of the work and activities carried out  in light of the tasks approved within the annual workplan of the project from January to June 2026, including a presentation of those works and activities carried out during the reporting period to achieve the project objectives and the problems faced by the project with what was done to address them.

# Project Information

## Objective of the project

This project seeks to support Egypt's adaptation efforts in the northern coasts, especially the Nile Delta, an area identified by the International Panel on Climate Change in its fourth assessment report as one of the most vulnerable places to the negative effects of climate change in the world.

The project aims to reduce the risk of coastal flooding on Egypt's north coast due to rising sea levels and frequent extreme weather events. The first component of the project focuses on protecting 69 kilometers in the Nile Delta region using a set of earthen bridges in five (5) Nile Delta regions. The second component of the project focuses on developing an integrated coastal zone management plan for the entire North Coast, to manage the risks of climate change in the long term, and to provide Egypt with the capacity to adapt to coastal flood risks.

## Project Funding Entity

The Ministry of Water Resources and Irrigation (MWRI), the Green Climate Fund (GCF) and the United Nations Development Programme (UNDP) with funding of approximately US$ 105 million.

## Project Executor

Shore Protection Authority

## The entity supervising the follow-up of the implementation of the project

United Nations Development Programme in Cairo.

## Project Implementation Period

Start Date: May 29, 2018

Scheduled completion date: end of November 2026

# Project work and activities during the reporting period

## The first component: protection works in the Delta

- The implementation of the landscape pilot project towards the new city of Damietta has been completed

- The process of protecting the low-lying areas east of the heads, towards the industrial city in Motobas – Kafr El-Sheikh Governorate, is underway with a completion percentage of 62%

- The process of protecting the low-lying areas towards the city of Idku – Beheira Governorate is underway with a completion percentage of 80%

- A number of (2) signs were installed for the protection site west of the Burlus power station - Kafr El-Sheikh Governorate & towards the new city of Mansoura - Dakahlia Governorate

- The implementation of the extension of the landscape pilot project towards the new city of Damietta has begun and the completion percentage is 5%.

## Component Two: Preparation of the Integrated Coastal Zone Management Study

- Institutional Framework for Integrated Coastal Zone Management

- The institutional framework was approved by the Council of Ministers and the Decision Support Center in the Council of Ministers, and we were informed of the issuance of the decision on the institutional framework by His Excellency the Prime  Minister last October  , and we are now following  up on the issuance of the decision in the Official Gazette to start its entry into force.

- A meeting was held with Her Excellency the Minister of Environment and the Minister of Local Development to discuss the outputs of the project and the roles and responsibilities of the Ministry of Environment in light of the laws on which the project was based in setting the legal and institutional framework for the integrated management of the Mediterranean coastal areas.

- A full copy of the Strategic Plan for Integrated Coastal Zone Management has been sent to the main partners: the Ministry of Water Resources and Irrigation, the Minister's Office, the Egyptian General Authority for Coastal Protection, the Ministry of State for Environment-Environmental Affairs Agency, the Ministry of Housing, the Minister's Office, the Public Authority for Urban Communities and New Cities, the Ministry of Local Development, and the Minister's Office.

- Prepare for a workshop in July 2026 in the presence of international experts to present and discuss the components of the plan to the partners and receive their feedback to formulate the final version of the plan that will be presented to the decision makers.

- Capacity Building Program for Activating the Institutional Framework

- Two meetings were held with His Excellency the Minister of Environment and His Excellency the Minister of Water Resources and Irrigation  , during which they discussed  the preparation of a capacity building plan for the governorate committees and the Technical Secretariat for Integrated Management of Coastal Zones as soon as the Prime Minister's decision was issued in the Official Gazette.

- An integrated presentation was sent to the Minister's Office, which includes the logical, practical and technical reasons for the need to issue the Prime Minister's decision in the entire institutional framework.

- The first pilot project in Damietta

- A meeting was held on 31/3/2026 to discuss the executive roles of the Integrated Coastal Zone Management Committee, its limits of authority, and its relationship with the Licensing Committee at the Ministry of Water Resources and Irrigation, and to clarify the executive steps to approve projects within ten kilometers of the coastline in accordance with the decision of His Excellency the Governor in his capacity as Chairman of the Integrated Coastal Zone Management Committee in the governorate.

- A decision was made by His Excellency, the Governor of Damietta, on the steps to be followed in the event of requesting approvals for new projects within the boundaries of the coastal zone.

- The Second Pilot Project in Matrouh Governorate

- Matrouh Governorate was determined in the meeting of the Steering Committee on 30/12/ 2025 to be the governorate in which the second pilot project will be implemented.

- The first preliminary meeting was held in the presence of His Excellency the Governor of Matrouh and members of the Integrated Management Committee for Coastal Areas in the Governorate, where the outputs of the first pilot project in Damietta were presented, and then the risk maps in Matrouh Governorate were presented and the requirements were discussed from each partner entity in the governorate, including site maps for all facilities affiliated to each directorate or company, in addition to the roles of specialized departments within the Governorate Office

- A schedule of visits was agreed during the month of April to compile spatial data and sign it on risk maps

- The visits to the cities and districts of Matrouh Governorate were carried out from 4/4/2026 to 9/4/2026 and the submission of risk maps for each partner entity, and then the request to collect spatial data for each entity to sign the hazard maps

- A meeting of the Integrated Coastal Zone Management Committee was held on Monday 22/6/2026 in the presence of the Deputy Governor, the Secretary General and all the partner entities, during which the maps of the effects of sea level rise on facilities, infrastructure and soil nature from 2024 to 2100 were presented to help the various entities in identifying the most affected places and linking them to their development plans

- Ambassadors Program

- The fourth group of climate ambassadors was launched with the participation of 40 new candidates representing partner ministries and governorates, and the third group of ambassadors was honored for completing the training program, where the eight habits training for the most influential people was held in January 2026.

- The Effective Communication Skills Program for Climate Ambassadors Group IV was implemented on April 15, 2026, in the presence of 36 ambassadors of the project.

- The Conflict Management Skills Program for Climate Ambassadors Group IV was implemented in New Damietta on June 29 and 30, 2026, in the presence of 38 ambassadors of the project.

- Building the Capacity of Governorate Committees

- A copy of the Integrated Coastal Zone Management Manual has been sent to all governorate committees for study and to send comments or suggestions on the methodology for activating and operating the institutional framework for integrated coastal zone management

- Once the comments and comments are received, preparations will be made for the training of the eight governorate committees on the Integrated Coastal Zone Management Manual in the presence of all members of the relevant committees and departments of the governorates' offices.

- Preparations are now underway to train the committees in the eight governorates on the methodology of monitoring and evaluation.

- Preparations are being made to train the applications of the guidelines for the eight governorate committees during the month of July 2026 to activate and operate the institutional framework for integrated coastal zone management.

- Issuing the Egyptian Urban Code for Coastal Areas

- Participated in the meetings of the Fourth Subcommittee on Integrated Management of Coastal Zones in the Egyptian Urban Code and contributed to the project's outputs in forming a comprehensive vision of the integrated coastal zone management methodology in the applications of the Urban Code.

- The final version of the environmental, social and economic impact assessment study for the development projects of communities affected by climate change in the Burlus and Tubas centers in Kafr El-Sheikh Governorate, which was implemented during 2023 in cooperation with the Desert Research Center and Misr El Kheir Foundation, is being completed. Preparations are currently underway for the implementation of the second phase of the projects based on the results of the study, in cooperation with the Food Bank. This phase included the implementation of field visits to beneficiaries and projects within the scope of the project's protection works in the coastal area of Kafr El-Sheikh, within the framework of coordination between the project team, the consultant and the governorate officials. A meeting was also held with the Governor of Kafr El-Sheikh and members of the Coordinating Committee for the Implementation of Projects, with the aim of presenting the results of the study and discussing and arranging the next executive steps.

- The first draft of the urban requirements for the protection of uses and activities related to the blue and green economy in the Mediterranean coastal region has been completed within the framework of the work of the Subcommittee of   the "Urban Committee" on the preparation of the Egyptian Urban Code for the Coastal Areas.

- The second draft of the Integrated Coastal Zone Management Committee has been completed within the framework of the work of the Sub-Committee of   the "Urban Committee" on the preparation of the Egyptian Urban Code for Coastal Areas.

- The first listening and discussion committees were held to review the first draft of the urban requirements for adaptation to climate change in the Mediterranean coastal region, within the framework of the work of the subcommittee of the "Urban Committee" on the preparation of the Egyptian Urban Code for the coastal areas.

Component II: National Coastal Observation System

- Two additional monitoring stations have been installed, bringing the total number of sea level measurement stations to (7) stations, including: Damietta Port, Burlus Fishing Port, El Alamein Water Desalination Plant, Ras El Tin Marine Base in Alexandria, El Arish Power Plant, Idku Sea Port, and 3rd of July Base in Jarjoub – west of Marsa Matrouh.

- Practical training was carried out to manage and operate the meteorological reception program from all sea level measurement stations (7).

- 3 groundwater quality meteorological wells were implemented in the Manzala area at depths of (50 m), (200 m) and (400 m).

- 5 wells were carried out to monitor the quality of groundwater in Wadi Al-Arish with depths of up to 65 meters per well.

- The procedures for obtaining a license to use radio waves from the Telecommunications Regulatory Authority to transmit the meteorology of the wavemeters have been completed in preparation for the completion of customs clearance, and the shipment of buoys (3) and some components of the wave monitoring station have been released.

- The cooperation protocol between the various entities is being prepared for the operation and management of the National Coastal Monitoring System.

- 3 meteorological stations were installed in Burlus, Rashid and Al-Arish, the state of the Meteorological Authority.

- Coordination is underway to install 1 meteorological station in El Alamein, and it was handed over to the Meteorological Authority

- A number of 2 rubber boats with motors and the necessary equipment for marine surveying (bathymetric) were supplied to the Egyptian General Authority for Beaches and the Shore Research Institute at the National Water Research Center.

- Spare parts have been provided to qualify existing coastal devices to be included in the National Coastal Monitoring System, including the sea level measurement device in Port Said of the Survey Research Institute to ensure the sustainability of monitoring and the real-time transmission of meteorology to the server of the National Water Research Center.

- A workstation unit  has been supplied to collect, manage and store all coastal meteorology for the National Coastal Monitoring System, which will be connected to  the main server of the Ministry as well as to  the National Water Research Center  to carry out the task of auditing and revising the meteorology before making it available for circulation.

## Evaluation Study of the First Phase of Community Development Projects in Kafr El-Sheikh

- The final phase of the study "Lessons Learnt and Way Foreword" is being completed.

## Community Development Projects in Kafr El Sheikh

- The contract was signed with the Food Bank Foundation to start implementation starting from June 2026 until November 2026.

## Coastal Forecast System

- The contract was signed with the Deltares Institute, to start the implementation of the coastal forecasting system from June 2026 until November 2026.

## Early Warning System

- The evaluation of bids submitted by local companies to select the company that will design and implement the Early Warning System is being completed from June 2026 to November 2026.

## Coastal Modeling:

- The coastal modeling expert: Dr. Samir Abu Hadima has been contracted, and the following tasks are being implemented:

  - Shoreline Evolution

  - Enhanced Digital Height Model - Enhanced DTM

  - Flood Hazard - Flood Hazard

  - Coastal Risk Framework and Valuation Matrix

  - Saltwater Intrusion Technical Note

  - Final Coastal Risk Profile

## Activities of the project's communications component

## Community Awareness Plan:

- The community awareness campaign of the project was completed, following the completion of the activities of the third phase (post-campaign) in the governorates of Dakahlia and Beheira, thus achieving success on a geographical scale that included five coastal governorates: (Kafr El-Sheikh, Damietta, Beheira, Dakahlia, and Port Said).

## Gender Plan:

- Integrated Documentation: A comprehensive documentary film has been prepared highlighting the project's outputs, highlighting the criteria for gender representation and inclusive community inclusion.

- International Marketing:   An "Executive Brief" (4-7 minutes) for international participants is being produced to review the project's leadership in the sustainable development file in accordance with international standards.