| Enhancing Adaptation Action in Turkey TR2017 ESOP MI A3 04 |  |  |
| --- | --- | --- |
| 4th & 5th PROGRESS REPORT Reporting Period: 06.10.2022–08.10.2024 |

This project is funded by the European Union and Republic of Türkiye and implemented by the United Nations Development Programme. The beneficiary of the project is the Ministry of Environment, Urbanization and Climate Change. General Directorate of European Union and Foreign Relations is the Contracting Authority of this Project.

October 2024

United Nations Development Programme

Türkiye

This publication has been produced with the assistance of the European Union and the Republic of Türkiye. The contents of this publication are the sole responsibility of UNDP and can in no way be taken to reflect the views of the European Union and the Republic of Türkiye.

TABLE OF CONTENTS

TABLE OF CONTENTS	iii

LIST OF ANNEXES	v

ABBREVIATIONS	vi

1.	DESCRIPTION	1

2.	ASSESSMENT OF IMPLEMENTATION OF ACTIVITIES OF THE ACTION	4

2.1.	Executive Summary	4

2.2.	Progress in Activities and Achievement of Results	5

2.2.1.	Recruitment of Technical Assistance Team (TAT), KEs and STEs	5

2.2.2.	Meetings and Events	12

2.2.3.	Monitoring and Reporting	14

2.2.4.	Project Components	14

2.2.5.	Grant Management	41

2.2.6.	The Concrete Results of the Project Components	48

2.3.	Risks, Risk Mitigation and Adaptive Management	56

2.3.1.	Effects of COVID-19	56

2.3.2.	Plans for next coming period	69

2.4.	Project Management and Coordination Activities	90

2.4.1.	Building Up Management Structure and Exercising Its Functions	90

2.4.2.	Complying Obligations Regarding Information and Reporting	90

2.4.3.	Running Control and Evaluation Mechanisms	90

2.5.	Methodology	91

2.6.	Logical Framework	92

2.6.1.	Current Anticipated Problems, Planned Remedial Actions and Lessons Learned from Encountered Problems	92

2.6.2.	Project Indicators	92

2.7.	Work Plan	102

2.8.	Budget	102

2.9.	List of Contracts	102

3.	PARTNERS AND COOPERATION	103

3.1.	Relation with the End Recipient	103

4.	LINK WITH SUSTAINABLE DEVELOPMENT GOALS AND GENDER EQUALITY	103

4.1.	Project Contribution to SDGs	106

5.	VISIBILITY	108

ANNEXES	109

LIST OF ANNEXES

| Annex No | Heading |
| --- | --- |
| Annex 01 | Terms of References |
| Annex 02 | CCAGP Training Reports and Guidelines |
| Annex 03 | Risk Log |
| Annex 04 | Logical Framework Matrix |
| Annex 05 | Workplan |
| Annex 06 | Study Visit |
| Annex 07 | Financial Table |
| Annex 08 | Communication and Visibility |
| Annex 09 | Meetings |
| Annex 10 | National Adaptation Strategy (NASAP) |
| Annex 11 | Draft Finance Strategy |
| Annex 12 | Adaptation Action Plans |
| Annex 13 | Urban Adaptation Strategy (UASAP) |
| Annex 14 | Trainings |
| Annex 15 | FIF |
| Annex 16 | Management Declaration |

ABBREVIATIONS

| AR5 | IPCC 5th Assessment Report |
| --- | --- |
| CA | Contracting Authority |
| CCAGP | The Climate Change Adaptation Grant Programme |
| DGEUFR | The Directorate General of European Union and Foreign Relations |
| DoA | Description of Action |
| DoEUI | The Department of European Union Investments |
| ER | End Recipient |
| ESOP | Environmental Sectoral Operational Programme |
| EU | European Union |
| EUD | Delegation of the European Union to Türkiye |
| FAQ | Frequently Asked Questions |
| GESI | Gender Equality and Social Inclusion |
| KE | Key Expert |
| M&E | Monitoring and Evaluation |
| MIS | Management Information System |
| MoEUCC | The Ministry of Environment, Urbanization and Climate Change |
| NASAP | National Adaptation Strategy and Action Plan |
| NGO | Non-Governmental Organizations |
| OCU | Operation Coordination Unit |
| PSC | Project Steering Committee |
| SBO | Strategy and Budget Office of the Presidency of the Republic of Türkiye |
| SMART | Specific Measurable Achievable Realistic Time-bound |
| STE | Short-Term Expert |
| TAT | Technical Assistance Team |
| UASAPs | Urban Adaptation Strategy and Action Plans |
| UNDP | United Nations Development Programme |

# DESCRIPTION

| Action Title: | Enhancing Adaptation Action in Turkey |
| --- | --- |
| Contribution Agreement Number: | TR2017 ESOP MI A3 04 |
| Total eligible cost: | 4.225.000 EUR |
| Starting Date: | 09.10.2019 |
| End Date: | 08.04.2025 |
| Duration: | 66 months |
| Contracting Authority: | Ministry of Environment and Urbanization and Climate Change, Department of European Union Investments |
| Project Manager: | Dr. İsmail Raci BAYER |
| Address: | Mustafa Kemal Mah. Eskişehir Devlet Yolu 9.km No: 278, Ankara, Türkiye |
| Telephone: | + 90 312 474 03 50-51 |
| Fax: | + 90 312 474 03 52-53 |
| Contract Expert: | Ceren UNCU AĞAÇDİKEN |
| e-mail: | ceren.uncuagacdiken@csb.gov.tr |
| Beneficiary: Address: Fax: SROB: Telephone: e-mail: OCU Coordinator: Telephone: e-mail: | Ministry of Environment, Urbanisation and Climate Change, Directorate of Climate Change - Çamlıca Mahallesi Anadolu Bulvarı No: 64/2, 06630 Yenimahalle/Ankara, Türkiye +90 312 591 44 00 Orhan SOLAK, Deputy Head of Directorate of Climate Change +90 312 591 44 00 orhan.solak@csb.gov.tr |
| Organization: | United Nations Development Programme (UNDP) Türkiye Country Office Meral MUNGAN ARDA Climate Change and Environment Portfolio Manager Oran Mah., Mustafa Fehmi Gerçeker Sokak No:12 06450 Çankaya, Ankara/Türkiye +90 312 454 1100 meral.mungan@undp.org Oran Mah., Mustafa Fehmi Gerçeker Sokak No:12 06450 Çankaya, Ankara/Türkiye Gizem BAL +90 312 454 11 00 gizem.bal@undp.org |
| Project Director: |  |
| Address: |  |
| Telephone: |  |
| e-mail: |  |
| Project office address: |  |
| Project Manager: |  |
| Telephone: |  |
| e-mail: |  |
|  | PROGRESS REPORT |
| Reporting period: | 06.10.2022–08.10.2024 |
| Report elaborated by: | Gizem Bal, Project Manager |
| Report reviewed by: | Meral Mungan Arda, Portfolio Manager |
| Draft Progress Report submitted on: | N/A |
| EU, TR and UNDP financing as a percentage of total budget of the Action: | Considering the total budget of the action as 4.225.000 EUR EU: 84,50%; TR: 14,91%; UNDP:0,59% |
| Objectives of the action: | The overall objective of the Project is to build societal resilience by strengthening climate change adaptation, particularly at sector and urban level. The specific purpose of this Project is to establish an enabling environment for climate change adaptation in Türkiye by developing the policy, technical and operational baselines, including (i) better decision-making tools for national climate change adaptation policies, (ii) urban adaptation planning solutions (urban adaptation strategies and action plans), (iii) capacity building and networking activities for climate change adaptation with the EU and the international community, and (iv) a climate change adaptation grant programme to implement climate change adaptation action. |
| Target groups: | The target groups of the Project are the relevant public institutions, local governments and municipalities, regional and provincial directorates, regional development agencies, chambers, unions, professional and business organizations, universities, research institutes and civil society organizations. The target groups of the operation include all relevant non-state stakeholders and citizens. |
| Final beneficiaries: | The final beneficiaries of the Project are national and local stakeholders and citizens. |
| Estimated results: | 1. Develop better decision-making tools for climate resilient sustainable development. 2. Develop adaptation and resilience planning in urban areas 3. Develop capacity for climate change adaptation action 4. Improve operational capacity for climate change adaptation action through a climate change adaptation grant programme |

# ASSESSMENT OF IMPLEMENTATION OF ACTIVITIES OF THE ACTION

## Executive Summary

The Project commenced on 9 October 2019, following the signature of the Grant Contract TR2017 ESOP MI A3 04. This progress report covers the fourth and fifth years of the contract. (06.10.2022–08.10.2024).

The report mainly outlines the progress in project activities currently being implemented. While the details of each action taken for the project implementation are given under section 2 of this report, the brief overview is hereunder:

- The details of the contractual changes of KE & STEs in line with UNDP’s newly introduced contractual modalities.

- Information on the meetings and events consisting of the consultative meetings, series of Operation Coordination Unit (OCU) Meetings and the Eighth Project Steering Committee Meeting to be organized within the Activity Report period are shared.

- The detailed process regarding the administrative reports submitted within the reporting period was given.

- Since the establishment of the new project team as of July 2024, weekly meetings with DCC have been initiated. As per negotiations, weekly meetings will be held every other week at DCC premises with the in person participation of TAT. Additionally TAT will be present at DCC premises 2 days a week.

- Updates on the implementation of the activities within the reporting period is presented in the context of the expected outcomes and deliverables and expected times of completion.

- Risk assessment, mitigation measures and adaptive management practices are presented along with the details regarding the activities in the next reporting period.

- The details regarding project implementation elements such as methodology, logical framework, and work plan are presented.

- The updates on the activities contributing to the Sustainable Development Goals (SDGs) are presented.

- Detailed updates on the communication and visibility activities are presented.

## Progress in Activities and Achievement of Results

### Recruitment of Technical Assistance Team (TAT), KEs and STEs

The Technical Assistance Team was fully established.

Updates with regards to the recruitment of KEs and STEs

In an effort to retain the expertise and experience developed during the four years of implementation of the “Enhancing Adaptation Action in Turkey” project, UNDP has  recruited, in line with its rules and procedures, to undertake lateral moves for two staff members to the new “EU Partnership for Local Climate Action in Turkey” project,;

- Diren Ertekin was assigned as Project Manager for EU Partnership for Local Climate Action in Turkey Project,

- Kemal Yeşil was assigned as Project Associate for EU Partnership for Local Climate Action in Turkey Project,

- Burcu Uysal was assigned as Project Associate for EU Partnership for Local Climate Action in Turkey Project,

- Seçil Kocatepe was assigned as Project Manager for Enhancing Adaptation Action in Turkey” Project.

After the addendum request has been rejected, the project team’s contracts were terminated on October 2023.  After the addendum request was approved in February 2024, the new Technical Assistance Team (TAT) mobilized in line with the UNDP rules and procedures. As a result of the competitive selection of the TAT members information is indicated below:

- Gizem Bal was assigned on 1 July 2024 as Project Manager for “Enhancing Adaptation Action in Turkey” Project.

- Ayşe İlke Gürbüzer Akgün was assigned on 1 August 2024 as Project Associate for “Enhancing Adaptation Action in Turkey” Project.

- Simay Erdi was assigned on 20 May 2024 as Project (Grant) Associate for “Enhancing Adaptation Action in Turkey” Project, and resigned as of September 2024.

- Göksu Demircan was assigned on 31 May 2024 as Project Assistant and Interpreter for “Enhancing Adaptation Action in Turkey” Project.

- Grant Manager is expected to start as of 1 November 2024.

Updates with regards to the contractual modalities of consultants

To maintain transparency and effective project management, this section shares updates on recent changes to consultant contracts, prompted by a new contractual modality introduced by UNDP.

Previously, Individual Contracts (IC) were used to establish framework agreements with consultants for intermittent and repetitive services. Under this system, contracts specified a daily fee for services, and financial obligations were only created when services were requested through a signed 'service request' document. However, as of 31 March 2022, UNDP introduced the Personnel Services Agreement (PSA) to replace framework-based IC contracts for both international and local consultants. The only exemption to this transition involved lump-sum deliverable-based arrangements.

The key difference between the previous framework-based IC contracts and the new lump-sum deliverable-based contracts is the financial proposal requirement. Consultants now provide a lump-sum fee for each deliverable, based on the estimated number of days needed to complete each task outlined in the terms of reference (ToR). This new approach links payments to specific, measurable deliverables, allowing the project team to make more detailed budget calculations and forecasts.

In response to UNDP's updated policies, the Project Team transitioned consultant contracts from framework-based ICs to lump-sum deliverable-based arrangements.

After the approval of the Addendum 1, amendments were prepared to extend their contracts according to their Terms of Reference. The information about amendments is indicated below.

- Ceren Ballı Gözen, Key Expert-1 - Consultancy on Climate Impacts and Modelling, on 23.04.2024

- Ela Babalık, Consultancy Services on Sectoral Adaptation to Climate Change on 22.04.2024

- Doğan Dursun, Key Expert-3 - Consultancy on Urban Adaptation to Climate Change, on 23.04.2024

- Yahya Akdağ, Key Expert-4- Software Development and Database Management Expert, 24.03.2023

- Özgür Pehlivan, Key Expert-5- Consultancy on Climate Finance, 30.04.2024

- Adnan Deniz Özdemir Consultant on Monitoring and Evaluation and Water Resources in the Context of CCA on 24.05.2024

- Ayşe Özge Kepenek Bozkırlıoğlu, Consultant on CCA and Industry Sector on 28.05.2024

- Doğanay Tolunay, Consultant on Climate Change Adaptation and Ecosystem Services, on 13.05.2024

- Emre Ege Smekal, Consultant on Climate Change Adaptation and Management Information System, 26.03.2024

- Emine Didem Evci Kiraz, CCA and Health Sector, on 24.05.2024

- İlkay Dellal, Consultant on Climate Change Adaptation and Agriculture Sector, on 10.06.2024

- Levent Aydın, Consultancy on Climate Change Adaptation and Energy Sector, 26.06.2024

- Süleyman Toy, Consultancy on Climate Change Adaptation and Tourism Sector, on 16.05.2024

- Haydar Uğur Dağ, Grant Programme Expert, 01.03.2024

- Barış Uysal, Grant Programme Expert, 30.09.2021

- Mikdat Kadıoğlu, Disaster Risk Management and Resilience Expert, expected to be signed on October 2024.

- Zeynep Eren, Social Development Expert, 09.09.2024

For further details on the experts’ names, scope of their contract and working days (including key experts, local junior, local senior and international short-term experts) please see Table 1 below.

Table 1. Expert Contract Details

| Contract Reference | Contractor | Procedure Followed | USD Contract Amount | Working Days | Scope of the Contract |  |
| --- | --- | --- | --- | --- | --- | --- |
| Consultant on Monitoring and Evaluation and Water Resources in the Context of CCA | Adnan Deniz ÖZDEMİR | UNDP’s Rules and Regulations on Procurement | USD 33,950.00 | 97 | The main scope of the assignment is to provide a set climate change adaptation indicators, monitoring and evaluation systems, as well as technical inputs to conduct vulnerability assessments, prepare climate change adaptation strategies and action plans at national and local level to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Consultant on CCA and Industry Sector | Ayşe Özge KEPENEK BOZKIROGLU | UNDP’s Rules and Regulations on Procurement | USD 20,400.00 | 51 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Key Expert-1 - Consultancy on Climate Impacts and Modelling | Ceren BALLI GÖZEN | UNDP’s Rules and Regulations on Procurement | USD 20,680.00 | 50 | The main scope of the assignment is to provide technical inputs, develop implementation strategies, guide other consultants, conduct analyses / assessments and prepare technical reports and other project related documents. |  |
| Key Expert-3 - Consultancy on Urban Adaptation to Climate Change | Doğan DURSUN | UNDP’s Rules and Regulations on Procurement | USD 27,250.00 | 109 | The main scope of the assignment is to provide technical inputs, develop implementation strategies, guide other consultants, conduct analyses / assessments and prepare technical reports and other project related documents from urban adaptation viewpoint. |  |
| Consultant on Climate Change Adaptation and Ecosystem Services | Doğanay TOLUNAY | UNDP’s Rules and Regulations on Procurement | USD 15,300.00 | 51 | The main scope of the assignment is to provide technical inputs, to conduct vulnerability assessments, prepare of climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Consultant on Climate Change Adaptation and Management Information System | Emre Ege SMEKAL | UNDP’s Rules and Regulations on Procurement | USD 12,900.00 | 43 | The objective of the assignment is the provision of technical expertise on the launch and implementation of the Grant Programme (CCAGP). The IC as senior short- term expert on Management Information System will provide technical and administrative assistance and develop a web-based grant Management Information System (MIS) and monitoring and evaluation (M&E) system during grant application design, implementation, monitoring and review process. |  |
| Consultancy Services on Sectoral Adaptation to Climate Change | Ela BABALIK | UNDP’s Rules and Regulations on Procurement | USD 57,150.00 | 107 | The main scope of the assignment is to provide technical inputs, develop implementation strategies, guide other consultants, conduct analyses/assessments and prepare technical reports and other project related documents from sectoral adaptation viewpoint. |  |
| CCA and Health Sector | Emine Didem EVCİ KİRAZ | UNDP’s Rules and Regulations on Procurement | USD 10,710.00 | 51 | The main scope of the assignment is to provide technical inputs, to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Consultant on Climate Change Adaptation and Agriculture Sector | İlkay DELLAL | UNDP’s Rules and Regulations on Procurement | USD 19,950.00 | 51 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Consultancy on Climate Change Adaptation and Energy Sector | Levent AYDIN | UNDP’s Rules and Regulations on Procurement | USD 20,400.00 | 51 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Key Expert-4- Software Development and Database Management Expert | Yahya AKDAĞ | UNDP’s Rules and Regulations on Procurement | USD 42,000.00 | 239 | The main scope of the assignment is to provide software development and update support, technical inputs, develop implementation strategies, cooperate with other consultants, conduct analyses/assessments and prepare technical reports and other project related documents. |  |
| Key Expert-5- Consultancy on Climate Finance | Özgür PEHLİVAN | UNDP’s Rules and Regulations on Procurement | USD 50,400.00 | 120 | The main scope of the assignment is to provide technical inputs on climate financing, develop strategies, conduct analyses/assessments and prepare technical reports and other project related documents. |  |
| Consultancy on Climate Change Adaptation and Tourism Sector | Süleyman TOY | UNDP’s Rules and Regulations on Procurement | USD 5,700.00 | 51 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Grant Programme Expert | Haydar Uğur Dağ | UNDP’s Rules and Regulations on Procurement | USD 9,909.91 | 130 | The objective of the assignment is the provision of technical expertise on the implementation of the Climate Change Adaptation Grant Programme during the project lifetime. As senior short-term expert on Climate Change Adaptation Grant Programme, The Grant Programme Expert will provide technical and administrative assistance during implementation, monitoring and review process for grant projects, develop training modules-training sessions, prepare project related documents. |  |
| Grant Programme Expert | Barış UYSAL | UNDP’s Rules and Regulations on Procurement | USD 13,567.83 | 130 | The objective of the assignment is the provision of technical expertise on the implementation of the Grant Programme during the project lifetime. The Grant Programme Expert will provide technical and administrative assistance during implementation, monitoring and review process for grant projects, develop training modules-training sessions, prepare project related documents. |  |
| Consultancy on Climate Change Adaptation and Disaster Risk Management | Mikdat Kadıoglu | UNDP’s Rules and Regulations on Procurement | tbc | 42 | The main scope of the assignment is to provide technical inputs to prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |
| Consultancy on Climate Change Adaptation and Social Development | Zeynep Eren | UNDP’s Rules and Regulations on Procurement | USD 3,800.00 | 40The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |  |

The names of experts supporting the project are listed as per the commencement dates of their contracts specified in the above table. Following the discontinuation of framework-based individual contracts, which used to allow provision of expertise though ‘working-day’ requests from consultants, the contracts of the previously hired consultants were converted into ‘delivery based’ contracts. The main difference between the framework and delivery-based contracts is the method of the provision of expertise. While framework-based contracts require separate working day calculations for each activity, the delivery-based contracts openly and clearly list all activities with their details and the provision of expertise will be required. This method enables Project teams to make very precise calculations with regards to consultancy costs. For other types of consultancies needs, such as continuous support on a specific topic, UNDP also have introduced the ‘NPSA – National Personnel Services Agreement’ modality, which allows for regular and/or part-time support through a monthly compensation depending on the volume of work / grade agreed for a certain period.

Terms of References for KEs and short-term experts are presented in Annex 01.

### Meetings and Events

Several administrative and consultative meetings were held within the 4th and 5th Progress period. The presentations, minutes, and participant list of the meetings are attached in Annex 09.

#### Project Steering Committee (PSC) Meeting

The seventh PSC Meeting was held on 4 April 2023. Since the Project team has been established following the latest Addendum signed on February 2024, the eighth PSC Meeting is held on 7 October 2024 in the premises of DCC with the participation of UNDP Türkiye CO, DCC, Presidency of Strategy and Budget and European Delegation, full participants can be seen in Annex 09.

#### Operation Coordination Unit (OCU) Meetings

Five Operation Coordination Unit meetings were held during the reporting period to provide information regarding the progress on the recruitment of short-term experts, reporting and monitoring events and activities, communication and visibility activities and grant management.

#### Weekly Meetings

Throughout the reporting period, weekly meetings were held with UNDP TAT and the DCC to monitor project progress, address challenges, and ensure alignment with project objectives. These meetings facilitated effective communication between team members, allowing for timely updates on ongoing activities and the resolution of any issues encountered. The consistent engagement during these meetings has been instrumental in maintaining project momentum, ensuring that all activities are conducted in accordance with the project timeline, and fostering collaboration among the different teams involved.

4th Weekly meeting has been sent to the DCC’s approval as the 5th Weekly meeting by mistake, weekly meeting numbers will be corrected during next meetings.

#### Study Visit to Valladolid and Madrid in Spain

The Project’s first study visit to Madrid and Valladolid, Spain, took place between 28 November and 1 December 2022, providing participants with an opportunity to explore diverse climate change adaptation practices in metropolitan and medium-sized cities. The visit brought together representatives from 4 metropolitan municipalities as well as the Ministry of Environment, Urbanization and Climate Change to enhance their knowledge and experience through on-site examinations, meetings, and information exchanges with local municipality officials in Madrid and Valladolid. The primary focus was on understanding the challenges, opportunities, and best practices across different scales of climate change adaptation projects.

Throughout the visit, participants engaged in sharing of best practices and toured various sites that showcased nature-based solutions, green and blue infrastructure, urban space evaluation, and exemplary practices in the transportation sector.

#### Study Visit to Denmark and Sweden

Study visits to Denmark and Sweden took place between 8 and 11 May 2023. The Copenhagen and Stockholm municipalities, which are highly strong in combating climate change, were visited and their local adaptation actions and policy processes were observed. The visit brought together representatives from pilot cities and the Directorate of Climate Change as well as Dr. Tuğba Dinçbaş, Vice President.

Study visits provide the opportunity to examine the work of other municipalities, communities, and organizations that have implemented successful climate change adaptation projects or policies for local governments. It offers the chance to see the implementation of projects and policies in other cities, observe the challenges and successes of these actions on-site, and learn from them.

Study Visit to the Netherlands

A study visit in Netherlands was organized between 18-23 August 2024 to increase experience sharing, conduct meetings with different institutions and departments. This visit also aimed to increase opportunities for data sharing of Türkiye with Netherlands, with the intention to be visible in technical publications of these institutions. Official visits were held in institutions such as Ministry of Infrastructure and Water Management, National Institute for Public Health and the Environment (RIVM), Rotterdam City Hall,  Municipality of Middleburg, Port of Rotterdam, Delta Climate Center (DCC), Royal Haskoning DHV, Global Centre on Adaptation and etc. for the scope of knowing more about climate adaptation actions as well as some site visit in different plants as mentioned in the program. In total, 5 people (3 men and 2 women) from DCC . 2 UNDP personnel Climate Change and Environment Portfolio Manager Meral Mungan Arda and Project Manager Gizem Bal, Expert Roelie Mulder, and Expert Roel van de Loo (1 men 3 women) participated to the visit.

#### Consultative Meetings on Activity 2.3.4

The Sector-specific Adaptation Plan Implementation Guidelines Consultative Meetings took place between 10-14 July 2023. The purpose of the meetings is to identify institutional and technical needs for adaptation to be implemented successfully. In these meetings, representatives of public institutions, academic institutions, civil society, and the private sector come together to discuss the actions specified in NASAP and their implementation steps.

Following sectors were discussed during the meetings held between 10-14 July 2023: Public Health, Energy, Agriculture and Food Security Social Development, Urban, Biodiversity and Ecosystem Services, Transportation and Communication, Water Resources Management, Tourism and Cultural Heritage, Disaster Risk Management, and Industry. The meeting report is under preparation.

Sectoral Awareness Raising Trainings on Activity 3.2.3

The sector specific awareness raising trainings has been initiated in different provinces. The main purpose of those trainings on climate adaptation is to enhance the capacity of public authorities and NGOs to support the development and implementation of local climate change adaptation strategies and action plans. Representatives of public institutions, academic institutions and civil society participated in those trainings.

The list and dates of events and meetings are presented in the table below.

Table 2. List of dates and events

| Meeting | Date |
| --- | --- |
| #### Study Visit to Valladolid and Madrid in Spain | 28 November -1 December 2022 |
| SV to Valladolid & Madrid in Denmark and Sweden | 8-11 May 2023 |
| Study Visit to the Netherlands | 18-24 August 2024 |
| CM on Activity 2.3.4 | 10-14 July 2023 |
| 34th Operation Coordination Unit Meeting | 3 May 2023 |
| 35th Operation Coordination Unit Meeting | 5 July 2023 |
| 36 th Operation Coordination Unit Meeting | 9 August 2023 |
| 37 th Operation Coordination Unit Meeting | 11 September 2023 |
| 38th Operation Coordination Unit Meeting | 31 May 2024 |
| First Weekly Meeting | 4 July 2024 |
| 39th Operation Coordination Unit Meeting | 11 July 2024 |
| Second Weekly Meeting | 18 July 2024 |
| Third Weekly Meeting | 25 July 2024 |
| 1st Sectoral Awareness Raising Training in Ankara | 30-31 July 2024 |
| 2nd Sectoral Awareness Raising Training in Eskişehir | 13-14 August 2024 |
| 40th Operation Coordination Unit Meeting | 17 August 2024 |
| Study Visit (SV) to Netherlands | 18-23 August 2024 |
| 3rd Sectoral Awareness Raising Training in Van | 9-10 September 2024 |
| Fourth Weekly Meeting | 19 September |
| 41st Operation Coordination Unit Meeting | 23 September 2024 |
| 4th Sectoral Awareness Raising Training in Trabzon | 30 September-01 October 2024 |
| 8th Project Steering Committee Meeting | 7 October 2024 |

### Monitoring and Reporting

#### 8th ,9th and 10th Activity Report

The draft 8th, 9th and 10th (combined) Activity Report was submitted for the review by the Contracting Authority (CA), End Beneficiary (ER) and EUD on 15 August 2024.  DCC has shared comments as of 20.09.2024. The final version including the comment of DCC, together with the official letters will be shared with the partners after approval by the Beneficiary in the last quarter of 2024.

#### 3rd Progress Report

The draft of the 3rd Progress Report was submitted for the review of the CA, ER and EUD on 26 December 2022. The draft report (in English) was approved by the ER on 23 March 2023. Revised report was submitted on 16 May 2023 both in Turkish and English. The report and its translation were approved by the ER on 12 July 2023.  Official letter for the 3rd Progress Report was submitted on 19 July 2023.

### Project Components

The progress in the activities under each component within the reporting period is presented as follows.

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 1.1. Review of existing climate change adaptation works and best practice catalogue | Report including the comparative assessment, multi-parameter analysis framework, classification system, compilation of existing work and list of best practices | October 2020 (completed) | The draft report including the working papers on Activity 1.1.1, 1.1.2, 1.1.3, 1.1.4 and 1.1.5 was submitted on 22 October 2020 in line with the decision taken at OCU Meeting No. 8 and approved by the ER on 4 January 2021. The translation of the document was submitted for review on 22 March 2021 and approved on 13 April 2021. The approved final report was submitted as an annex to AR3. |
| Activity 1.2. Comprehensive climate change impact and vulnerability assessment for five priority sectors | Report including sensitivity analysis, updated climate projections, vulnerability assessment scoping, vulnerability assessment and estimation of economic impacts | December 2022 (completed) | The draft report including the working papers on Activity 1.2.1, 1.2.2, 1.2.3, 1.2.4, 1.2.5 and 1.2.6 was submitted on 8 December 2022 in line with the decision taken at OCU Meeting No.23 (for 1.2.6) and approved by the ER on 12 January 2023. The translation of the document was submitted for review on 2 May 2023 and approved on 24 July 2023. The approved final report (except for 1.2.5) was submitted as an annex to AR7. |
| Activity 1.3. Activity 1.3. Adaptation options for updating the NASAP (completed) |  |  |  |
| Activity 1.3.1. A desk review of NASAP prioritization methodologies (i.e. cost-benefit, cost-effectiveness analysis, multi-criteria analysis, etc.) among EU member states, including good practices and lessons learned (including maladaptation practices) A stock-taking exercise on national strategies and policies for priority sectors, and international commitments and developments under multilateral environmental processes, such as the Paris Agreement, Sendai Framework and SDGs. | Desk review | April 2021 (completed) | The draft working paper was submitted on 15 April 2021 in line with the decision taken at OCU Meeting No. 12. Report was approved by the ER on 28 May 2021. The translation of the document was submitted for review on 16 August 2021 and approved on 23 March 2023. The final report was submitted as an annex to AR7. |
| 1.3.2 11 sector adaptation strategies for the priority sectors including structural and non-structural adaptation measures and using the vulnerability index map developed in Activity 1.2 | Desk review | December 2021 Completed | Preliminary studies has been completed right before the initiation of the NASAP studies. |
| Activity 1.3.3. A comparative analysis of the Turkish NASAP with selected EU member states, including (i) elaboration and update process, (ii) organizational and financial aspects, (iii) methodologies used for developing the strategy and prioritizing the actions, and (iv) recommendations for improvement in the context of Türkiye with linkages to the SDGs. 2 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to discuss the update methodologies for NASAP. Meetings will be held in Ankara; 50 to 60 representatives are expected to attend each meeting. | Desk review | December 2021 (completed) | The draft working paper was submitted on 22 April 2021 in line with the decision taken at OCU Meeting No. 12. Report was approved by the ER on 6 May 2021. The translation of the document was submitted for review on 16 August 2021 and approved on 23 March 2023. The final report was submitted as an annex to AR7. In line with the consultations with the ER, a two-day consultative meeting was held on 24-25 November 2021 (instead of 2 one-day meetings) to ensure in-depth discussions on the NASAP update methodologies. The meeting report was submitted on 10 March 2022 and approved on 12 January 2023. Translation of the report was submitted on 28 March 2023. The final report was submitted as an annex to AR7. |
| Activity 1.3.4. Adaptation options identified as a long list by stakeholders. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to discuss and identify adaptation measures for each priority sector. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each meeting. This activity will be an input to Activity 1.4.3. | 5 one-day consultative meetings | September 2022 (completed) | Consultative meetings under this activity were held between 18-22 April 2022. The draft meeting report was submitted for review on 24 August 2022 and approved on 6 September 2022. The final report was submitted as an annex to AR6. |
| Activity 1.3.5. A final report including findings and meeting proceedings. | Final report | September 2022 (completed) | The draft report was submitted for review on 8 September 2022 and approved by the ER on 22 August 2023. |
| Activity 1.4. Updated NASAP through multi-stakeholder process (ongoing) |  |  |  |
| Activity 1.4.1. An action plan for the NASAP update process, including identification of key stakeholders and detailed work schedule. | Action plan for the NASAP update process | October 2022 (completed) | The draft report was submitted for comments on 26 September 2022. Comments were received on 11 October 2022. The revised document was submitted for approval on 18 October 2022 and approved on 25 October 2022. The draft translation of the report was submitted for comment on 2 May 2023. The final report was submitted as an annex to AR7. |
| Activity 1.4.2. Dissemination of reports elaborated under activities 1.1, 1.2 and 1.3 among key stakeholders and series of sector specific working meetings to identify priority adaptation activities. | Dissemination of reports | April 2023 (completed) | Reports prepared under the project shared with the stakeholders and consultations were held. |
| Activity 1.4.3. 10 one-day, and 3 two-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders for the prioritization of adaptation activities. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each one-day meeting and 50 to 100 are expected to attend each two-days meeting. | 10 1-day & 3 2-day consultative meetings | January 2023 (completed) | Ten one-day consultative meetings were held between 19-30 September 2022. The meeting report was submitted for review on 6 December 2022 and approved on 23 March 2023. The translation of the report was submitted to the opinion on 21 June 2023 and approved on 13 July 2023. The final report was submitted as an annex to AR7. Three two-day consultation meetings were held on 7-9 and 13-15 December 2022. The meeting report was submitted for review on 12 January 2023 and approved on 23 March 2023. The translation of the report was submitted to the opinion on 16 May 2023 and approved on 12 July 2023. The final report was submitted as an annex to AR7. |
| Activity 1.4.4. An updated NASAP, including: (i) strategic priorities and areas of intervention in accordance of SDGs, (ii) an action plan with a list of selected climate change adaptation solutions, (iii) capacity building activities of relevant stakeholders, and (iv) a coordination mechanism among national entities (public, private, academia, civil society) at different levels and with international organizations. | Updated NASAP | November 2024 | These studies were launched in June 2022. The updated NASAP was submitted for comments on 9 January 2023. In accordance with the comments received, the actions were revised, and the total number of actions was limited to 150 and submitted for review by the stakeholder institutions through the DCC on 11 May 2023. Another revision was conducted upon comments received in the consultative meetings held in July 2023, the revised NASAP submitted for a second round of comments on 31 July 2023. The updated version of the NASAP was submitted for the final round of comments in August. To obtain consensus from all stakeholders, a two-day working group meeting was held on 19-20 September 2023 and the NASAP is being finalized accordingly. The Turkish version was approved by DCC, CA and the EUD. The English version was shared with DCC for approval. |
| Activity 1.4.5. Submission to the higher authorities of the MOEUCC for its endorsement and processing through the legislative body | NASAP submission | October 2024 (Completed) | Although the NASAP has been completed, the record and supporting documentation will be finalized in Q4 2024. E-mail received by DCC has been submitted as an annex to this report. |
| Activity 1.4.6. Dissemination campaign of the NASAP among central and local authorities, civil society, academia, the private sector and the international community. | Dissemination campaign of the NASAP | December 2024 | The design was completed and shared via social media which can be found in Annex 08. The dissemination campaign is ongoing. The brochures and printed version of NASAP will be shared during COP, meetings and trainings. |
| Activity 1.5. M&E system for the NASAP (ongoing) |  |  |  |
| Activity 1.5.1. A desk review (i) to take stock of existing adaptation indicators and governance mechanisms (e.g. SMART indicators) from EU member states, (ii) to identify relevant indicators already existing in national and local M&E systems, and (iii) to identify different M&E governance models (e.g. climate M&E officer, assigned staff under climate change unit) applicable for Türkiye and staff time, budget and capacity development required for these models. | Desk review | November 2020 (completed) | The draft report was submitted on 12 November 2020 in line with the decision taken at OCU Meeting No. 8 and approved by the ER on 21 February 2021. The approved report is submitted as an annex to AR4. The relevant expert is working on the final updates. |
| Activity 1.5.2. An online M&E system for the NASAP that encompasses the identified set of indicators and will require all involved stakeholders to report into | Online M&E system | Aug 2024 (Completed) | The draft M&E system was presented to the ER on 14 September 2023. The respective expert revised the online M&E for the NASAP based on consultations with DCC in July 2024. The revisions were accepted by DCC on 28 August 2024. |
| Activity 1.5.3. A training module on the use of M&E systems and 4 two-days online training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the NASAP. 150 staff in total are expected to receive the training. | Training Module on the use of M&E system | February 2025 | A meeting was held with the software expert on 19.09.2024 The preparation of the training module is underway. The training sessions will be organized on 5-6 November 2024 for 4 2 days online sessions. Planning has been started. |
| Activity 1.5.4. A regular review of the priorities and activities identified in the NASAP to assess progress, effectiveness and gaps. The review process will consist of one baseline assessment and 1 annual progress evaluations during the lifetime of the project. | Baseline assessment/ Annual Progress Evaluation | December 2024 | A preliminary meeting was held with the software expert. The activity completion date has been revised as December 2024. |
| Activity 1.5.5. Outreach of the NASAP and the progress reports at national level through national communications and various media tools. | Outreach | December 2024 | A preliminary meeting was held with the software expert. Outreach activities were initiated during the trainings going to be conducted with the software expert under activity 1.5.3. The first entrance of the documents expected under the responsible institutions will be monitored during the training going to be conducted in Q42024. |
| Activity 1.6. Climate financing strategy for the NASAP |  |  |  |
| Activity 1.6.1. A desk review (i) to take stock of existing and expected future climate financing mechanisms at international and national level, (ii) to analyze climate financing strategies of selected EU member states with national adaptation strategies, and (iii) to evaluate existing finance mechanisms for other themes for best practices and lessons learned. | Desk review | February 2022 (completed) | The draft working paper was submitted on 8 February 2022. The comments from ER were received on 27 May 2022. The revised document, along with its translation, was submitted on 27 July 2022. It was approved on 4 October 2022. The final report was submitted as an annex to AR7. |
| Activity 1.6.2. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders from priority sectors to discuss existing and expected future financial models and mechanisms and priorities for climate financing. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each meeting. | 5 1-day consultative meetings | November 2022 (completed) | Consultative meetings under this activity were held in 10-14 October 2022. The meeting report was submitted for review on 6 December 2022 and approved by ER on 10 January 2023. The translation of the report was submitted for comment on 22 May 2023 and approved on 17 July 2023. The final report was submitted as an annex to AR7. |
| Activity 1.6.3 A financing framework including (i) objectives, (ii) trend analysis of past climate financing and future scenarios, (iii) sector specific financing and budgets for the priority sectors, (iv) resource availability from the public, private sectors, at national and international level, and (v) modalities and institutional arrangements | A financing framework | December 2022 (completed) | Financial framework studies have been initiated on 9 February 2022 to collect data. The report was submitted on 13 December 2022 and comments received on 21 March 2023. The revised document was submitted on 11 April 2023 and approved by the ER on 22 August 2023. |
| Activity 1.6.4. A climate finance action plan for priority sectors including (i) institutional responsibilities, (ii) scenarios with total cost needed as per the NASAP, resources likely to be available, (iii) assessments of benefits of adaptation activities, (iv) recommendation for phasing, and (v) any institutional reform or innovation required to manage climate funding in the sector, including an assessment of capacities and limitations. | Climate finance action plan | March 2023 (completed) | Studies to collect data initiated in September 2022. The anaylsis report was submitted for review on 10 January 2023. Comments were received on 20 February 2023, revisions were made in line with the comments, submitted for approval on 22 March 2023 and approved on 22 March 2023. The translation of the document was submitted for review on 9 May 2023 and approved on 24 July 2023. The final report was submitted as an annex to AR7. |
| Activity 1.6.5. A final climate finance strategy by combining the financing framework and the climate finance action plans, together with the inputs and feedback from the consultative meetings. | Final climate finance strategy | January 2025 | Studies to collect data are initiated in December 2022. It was prepared following the finalization of the National Climate Change Adaptation Strategy and Action Plan and submitted for review on 23 May 2023. The final climate finance strategy was submitted to DCC on 10.07.2024. Relevant expert updated the financial strategy. A meeting was held with the expert and DCC to clarify the expectations. Another meeting with sectoral experts held on 19.09.2024 to receive sectoral updates. The expert plans to submit the updated version by the end of October 2024. |
| Activity 1.7. Adaptation plan implementation guidelines for priority sectors (ongoing) |  |  |  |
| Activity 1.7.1. A desk review (i) to take stock of existing sector specific guidelines among EU member states and countries with similar socio-economic profiles, and (ii) to evaluate ongoing reforms and implementation mechanisms (i.e. policy making and project lifecycle) within the priority sectors. | Desk review | May 2023 (completed) | The draft working paper was submitted for review on 15 May 2023 and approved on 18 July 2023. |
| Activity 1.7.2. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to identify institutional and technical needs for adaptation to be implemented successfully. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each meeting. | Consultative Meetings | July 2023 (completed) | Consultative meetings were held between 10-14 July 2023 with participation of 280 representatives from the relevant public, private, academic and civil society stakeholders. |
| Activity 1.7.3 5 sector specific adaptation plan implementation guidelines including (i) tools and methodologies for different types of adaptation work (structural, non-structural), (ii) connections with the existing sectoral strategy and investment plan, (iii) connections with the climate finance strategy, and (iv) criteria for decision-making and evaluation. The finance section of the guidelines will be integrated with activity 1.6 | Sector -specific Adaptation Plan Implementation Guidelines | December 2024 | The activity is ongoing. Updated adaptation plans are being reviewed by 11 sector experts and expected to be shared with the Ministry by December 2024. |
| Activity 1.7.4. A training module on the use of the guidelines and 5 two-days training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the NASAP. Training sessions will be held in Ankara, 250 staff in total are expected to receive the training. | Training Module | Q1 2025 | The activity completion date was revised as Q1 2025 based on the Addendum. |

Component 2

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 2.1. Adaptation guidelines and urban typology framework for cities | Report including desk review, adaptation guidelines and urban typology framework | November 2020 (completed) | The draft report including the Activity 2.1.1, 2.1.2, 2.1.3 and 2.1.4 was submitted on 5 November 2020 in line with the decision taken at OCU Meeting No. 8 and approved by the ER on 26 November 2020. Translation was also approved on 15 January 2021. The approved final report was submitted as an annex to AR3. |
| Activity 2.2. Climate change impact and vulnerability assessment for 4 pilot metropolitan municipalities | Report including updated climate projections, vulnerability assessment scoping, vulnerability assessment for pilot cities | February 2022 (completed) | The draft report including Activity 2.2.1, 2.2.2, 2.2.3 and 2.2.4 was submitted on 8 February 2022 and approved on 27 March 2023. The translation of the report was submitted on 16 May 2023 and approved on 30 May 2023. The final report (except for 2.2.4) was submitted as an annex to AR7. |
| Activity 2.3. Preparation of UASAPs for 4 pilot metropolitan municipalities (ongoing) |  |  |  |
| Activity 2.3.1. A desk review of city-wide adaptation actions based on vulnerability assessments through stakeholder engagement at EU level and within EU member states. Solutions catalogue and experience from EU and other Turkish cities can feed into this activity, while innovative solutions will also be sought. | Desk review | June 2021 (completed) | The draft report was submitted on 15 June 2021 in line with the decision taken at OCU Meeting No. 14 and approved by the ER on 29 June 2021. The translation of the document was submitted for review on 13 September 2021 and approved 20 January 2022. The final report is submitted as an annex to AR7. |
| Activity 2.3.2. 4 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders at city level to discuss the scope of the UASAPs. Meetings will be held in pilot cities; 50 to 60 representatives are expected to attend each meeting. | 4 1-day consultative meetings | July 2021 (completed) | Consultative meetings were held between 7-10 June 2021. Draft meeting report was submitted on 8 September 2021 and approved on 22 September 2021. The translation of the report was submitted for review on 19 April 2023 and approved on 24 April 2023. The final report is submitted as an annex to AR7. |
| Activity 2.3.3. 4 UASAPs for the pilot cities including structural and non-structural adaptation measures and using the vulnerability index map developed in Activity 2.2. The UASAPs will include adaptation goals, indicative timeframe, budget and funding options, baseline and performance indicators and responsible organisation(s) for each goal/action. | 4 UASAPs 4 two-day consultative meetings | December 2024 | UASAPs were revised in line with comments of the ER, and the consultative meetings held in pilot cities in June 2023. The revised plans were again sent for review by the local stakeholders to finalize. Currently, UASAPs are under revision. DCC has provided their final comments. Experts will reflect them on the action plans and UASAP's for each sector in 4 pilot provinces. The draft UASAPs can be reviewed under Annex 13. |
| Activity 2.3.4. A media launch in Ankara for 200 people about each city and dissemination materials in different formats for different target audiences/stakeholders. | Media launch | Q1 2025 | The media launch is planned to be held following the approval of the UASAPs for four pilot cities. |
| Activity 2.4. M&E system for the UASAPs (ongoing) |  |  |  |
| Activity 2.4.1. A desk review (i) to take stock of existing adaptation indicators and governance mechanisms (e.g. SMART indicators) from EU cities, (ii) to identify relevant indicators already existing in national and local M&E systems, and (iii) to identify different M&E governance models (e.g. climate M&E officer, assigned staff under climate change unit) applicable for cities in Türkiye and staff time, budget and capacity development required for these models. | Desk Review | February 2021 (Completed) | Final report date is 03.02.2021 (Completed) |
| Activity 2.4.2. An online M&E system for cities that encompasses the identified set of indicators and will require all involved stakeholders to report into. | Online M&E system | In DoA Cancelled / deleted by mistake during Addendum No1 approved on Feb 2024. However, as per OCU decision, this activity will be conducted. | Ongoing; the contracted expert has started the analysis phase for development of the M&E system. This was scheduled for Q3 2024 in the addendum approval yet expected to be completed in Q4 2024 as the addendum approval was realised in Feb 2024. It is also agreed to hold 1 day M&E training in pilot municipalities instead of discussing M&E system layout under Activity 2.4.2 during the first quarter of 2025. |
| Activity 2.4.3. A regular review of the priorities and activities identified in the UASAPs to assess progress, effectiveness and gaps. The review process will consist of one baseline assessment and 1 annual progress evaluation during the lifetime of the Project. | 1 baseline assessment and 1 annual progress evaluation | Q2 2025 | The contracted expert started the analysis phase for the M&E system. This activity has been planned for Q3 of 2024 but the estimated completion time for the activity will be updated to Q2 2025 according to up-to-date AWP due to the approval of the latest Addendum was completed in February 2024. Following the completion (or depending on the progress) of Activity 2.4.2, this activity will be initiated. |
| Activity 2.4.4. A training module on the use of M&E systems and 4 one-day online training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the UASAPs. 100 staff in total are expected to receive the training. | A training module on the use of M&E systems and 4 one-day online training sessions | Q1 2025 | To be initiated |
| Activity 2.4.5. Outreach of the UASAPs and the progress reports at national level through national communications and various media tools | Outreach | Q1 2025 | To be initiated |
| Activity 2.5. Urban climate financing strategy (ongoing) |  |  |  |
| Activity 2.5.1. A desk review (i) to take stock of existing climate financing mechanisms at city level among EU member states, (ii) to analyze climate financing strategies of selected EU member states with UASAPs, and (iii) to evaluate existing finance mechanisms in Turkish cities for other themes for best practices and lessons learned. | Desk review | February 2022 (Completed) | The draft working paper was submitted on 8 February 2022. The comments from ER were received on 27 May 2022. The revised document, along with its translation was submitted on 27 July 2022. It was approved on 4 October 2022. The final report was submitted as an annex to AR7. |
| Activity 2.5.2. An assessment of different financial solutions, including financial viability and operational sustainability, potentials and constraints for their implementation and uptake (e.g. regulatory context, pricing failures). | Assessment of different financial solutions | April 2023 (Completed) | The report was submitted for review on 28 March 2023, and approved on 11 April 2023. The translation of the document was submitted for approval on 22 May 2023, and approved on 30 May 2023. The final report was submitted as an annex to AR7. |
| Activity 2.5.3. A conference bringing IFIs and local authorities together to explore IFIs’ global experience in urban climate financing, and discuss suitable solutions for Turkish cities. This conference will complement the national level consultative stakeholder meetings from Activity 1.6 with local level perspectives. The meeting will be held in Istanbul attended by approximately 30 people, from IFIs, Municipalities, MoEUCC and relevant other institutions. | Conference | April 2025 | This activity has been postponed to Q1 2025 as it is highly linked to Activity 1.6.5. This activity will be revised during Addendum No2 to reach out more participants since it was reported as 30 people during Addendum No 2. |
| Activity 2.5.4. An estimation of adaptation financial needs for each city and potential market for adaptation at national scale, with a baseline “business as usual” scenario for comparison. These assessments will take into consideration costs associated with circumventing existing or planned mal-adaptation measures to inform the development of no-regret and low-regret adaptation measures.​ | Urban climate financing needs report | March 2025 | Ongoing. The relevant expert has been contracted. Activity completion date revised to April 2025. |
| Activity 2.5.5. An urban climate financing strategy for the implementation of UASAPs | Urban Climate finance strategy for the implementation of the UASAPs. | April 2025 | This activity has been postponed to Q1 2025 as it is highly linked to Activity 2.3.3. |
| Activity 2.5.6. A training module on the financial mechanisms and 4 two-days training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the UASAPs. Training sessions will be held in pilot cities, 100 staff in total are expected to receive the training. | A training module on the financial mechanisms and 4 two-days training sessions | Q1 2025 | To be initiated on Q1 2025. |

Component 3

| Activity |  | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- | --- |
| Activity 3.1. Policy and stakeholder capacity and need assessment (completed) |  |  |  |  |
| Activity 3.1.1. A desk review of existing institutional framework among EU member states, including regulatory tools, decision-making processes, and roles and responsibilities, including the identification of best practices. |  | Desk review | July 2020 (Completed) | Completed |
| Activity 3.1.2. A desk review (i) to take stock of existing climate change adaptation training material among EU member states and countries with similar socio-economic profiles, (ii) to evaluate ongoing training programs and mechanisms at national and local level for similar target audiences, (iii) to identify areas with high demand for exchange of knowledge and experience from Turkish actors and centers and institutions within the EU that correspond to these needs, and (iv) to map the existing collaboration on climate change adaptation between EU and national stakeholders. |  | Desk review | July 2020 (Completed) | Draft working paper was submitted on 8 July 2020. |
| Activity 3.1.3. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders at city level to identify strategic entry points for capacity building. Meetings will be held in Ankara and 4 cities; 20 30 representatives are expected to attend each meeting. |  | 5 1-day consultative meetings | June 2021 (Completed) | Consultative meetings were held between 14-16 and 21-22 June 2021. Draft meeting report was submitted on 30 June 2021. |
| Activity 3.1.4. A technical capacity and need assessment including bilateral interviews and a survey with key public, private, academic, civil society stakeholders on motivation and interest, availability of and accessibility to information, priorities in decision-making, challenges for implementation, etc. The findings will be analyzed and published. |  | Capacity and need assessment | June 2021 (Completed) | The capacity and need analysis survey was shared on 15 February 15 2021 and was kept available until 15 April 15 2021. Draft working paper submitted on 30 June 2021 in line with the decision taken at OCU Meeting No.14. |
| Activity 3.1.5. A final assessment report including findings of the desktop reviews, analysis of the survey and interviews and meeting proceedings. |  | Final report | July 2021 (Completed) | The draft report was submitted on 8 July 2021. |
| Activity 3.2. Capacity building and networking (ongoing) |  |  |  |  |
| Activity 3.2.1. A capacity building plan based on the findings of 3.1. Below numbers for training modules, training sessions and study visits are indicatively identified for calculations purposes. They may be revised according to these findings and budget availability. |  | Capacity building plan | September 2021 (Completed) | The draft report was submitted on 8 September 2021. The comments were received on 22 September 2021. |
| Activity 3.2.2. At least 10 customized climate change adaptation training modules (including initial and follow up sessions) on topics such as (i) awareness raising on climate change, (ii) use of climate scenarios and models, (iii) impact and vulnerability assessment, (iv) adaptation planning, and (v) Sector specific adaptation, etc. |  | 11 Training modules including each NASAPs sector | Ongoing | Presentations of three modules were submitted for review on 15 September 2023. The training modules will be prepared as per the know-how in Ankara Pilot Training conducted on 30-31 July 2024. |
| Activity 3.2.3. At least 20 two-days training sessions to relevant stakeholders from public, private, academia and civil society. Training sessions will be held in Ankara and the pilot cities, 600 staff in total are expected to receive the training. |  | Training sessions | April 2025 | The pilot training was held on 30-31 July in Ankara. 23 women, 15 men attended the training. 38 participants were given certificates for successfully completing the training. The second training was held on 13-14 August in Eskişehir. 24 women and 20 men attended the training. Participants were asked Menti and evaluation questions to measure their level of knowledge and learning throughout both training. 44 participants were given certificates for successfully completing the training. Please refer to Annex 14 for the training content, attendance and photographs. - The 3rd training was held on 9-10 September in Van (14 women 27 men). - The 4th training was held on 30 September-01 October in Trabzon (15 women 34 men). - The 5th training will be organized for 15-16 October in Antalya. - The 6th training will be organized for 12-13 November in Nevşehir. - The 7th training will be organized for 10-11 December in Diyarbakır. |
| Activity 3.2.4. At least 7 study visits for 10 participants to promote knowledge exchange between Participants will be selected from the target audience (i.e. MOEUCC staff working within the scope of the project, relevant local authorities, NGOs/associations, and academia), each will fill a report indicating how the study visit was (or was not) useful to the activities in Türkiye. The list of study visit participants shall be notified to EUD before MOEUCC approval, and EUD is to clear the list of attendance within two weeks after submission. MOEU approval shall only be sought after “no objection” is received from EUD. |  | 7 study visits | March 2025 | The first of the study visits was conducted in Valladolid and Madrid, Spain, between 28 November and 1 December 2022. The second visit was carried out between 8-11 May 2023 in Copenhagen, Denmark (8-9 May) and Stockholm, Sweden (10-11 May). The project team, experts from the Ministry of Environment, Urbanization and Climate Change, the end recipient and representatives of the pilot municipalities of the project, Konya, Muğla, Sakarya and Samsun Metropolitan Municipalities, attended to the visit. On 18-23 August 2024, Netherlands was visited. The last Study visit planning is initiated. Last study visit expected to be conducted in 2025 to Germany. The estimated completion time for the activity will be updated according to the need. |
| Activity 3.2.5. 4 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to present their experience with different city networks and advise on membership. Meetings will be held in online; 50 to 60 representatives are expected to attend each meeting. |  | 4 1-day consultative meetings (online), 2 meetings remaining | Q1 2025 | In line with the decision taken at OCU Meeting No. 18, the first set of meetings were held online with broader participation from municipalities at national level on 28-29 September 2021. The remaining meetings are postponed to Q1 2025. |
| Activity 3.2.6. 7 awareness raising conferences in all regions, including the pilot cities, to promote the central and local climate change adaptation agendas, and facilitating networking and partnership building between relevant stakeholders. The event will be in form of town-hall meeting, where the level of interaction between the parties will be strengthened and the key areas of planning, action, financing for climate change adaptation will be discussed in line with innovative and inclusive communication techniques as highlighted in Section 1.4. Methodology. At least 608 local actors are expected to participate. |  | 7 awareness raising conferences | March 2025 | DCC and UNDP are discussing the possibility of merging this with Activity 3.2.3.UNDP will prepare proposals for possible topics related to this activity. |
| Activity 3.2.7. A series of success and human stories from the training and awareness raising events to be used on website and social media. |  | Success and human stories | March 2025 | The planning of the activity will be initiated as of the first quarter of 2025. During the training to be conducted as per Activity 3.2.3 success stories will be recorded and disseminated. |
| Activity 3.2.8. A series of 10 documentary style short movie (3 to 6 minutes), whose content will aim to familiarize the target audience and public at large on the work done in 5 priority sectors and 4 pilot municipalities on climate change adaptation (and 1 general content). The short movies will be broadcasted within the public institutions and municipalities as well as shared with private firms, academia and the civil society. |  | 10 Short Movies | Q1 2025 | The first video in the series started with the transport and communications sector, which was approved on 19 September 2022. Videos on agriculture and food security and water resources management were submitted for review on 21 August 2023. The remaining seven scripts were also submitted for review on 1 September 2023. At previous OCU meetings this activity was reported as completed. However, it is noted that a biodiversity sector video needs to be prepared based on consultations with DCC. The DCC sent an email on 19 July 2024 stating that the activity was incomplete. Since there are 11 sectors in NASAP, additional 1 sector will be added. |
| Activity 3.3. National Adaptation Platform (ongoing) |  |  |  |  |
| Activity 3.3.1. A desktop review and meetings with related stakeholders (i) to take stock of similar national platforms among EU member states and at EU-level (such as climateADAPT) and provide recommendations for the national adaptation platform, (ii) to identify knowledge gaps and communication issues among Turkish stakeholders, and (iii) to identify international and national networks and online platforms and libraries of relevance and interest. |  | A desktop review and meetings with related stakeholders | December 2023 (Completed) | Completed. |
| Activity 3.3.2. Software design, test runs and maintenance of the platform, including key components such as: FAQ, contact list, publication and activity database, search function, metadata download and report/map making services. |  | The initial version of the architecture and design of the platform | October 2023 (Completed) | The initial version of the architecture and design of the platform has been developed and improved. |
| Activity 3.3.3. Content upload to the platform (publications, reports, media, etc.) and links with relevant networks and online platforms. |  | Content upload | March 2025 | Data entry has begun and will continue until the end of the project. |
| Activity 3.3.4. Media launch and technical presentation of the platform to key stakeholders; presentation of climate change adaptation work per sector and development of sector specific infographics and presentation material; organization of two public events (i.e. contest, exhibition) on climate change adaptation work. Media launch will be in Ankara with participation of 200 people. | Media launch |  | December 2024 | It is planned to be organized by November 2024, the draft agenda has been developed. |
| Activity 3.3.5. Regular evaluation of the efficiency and effectiveness of the platform and its use for the NASAP, for sector specific climate change adaptation and for urban climate change adaptation through an annual web-based survey | Web based survey |  | March 2025 | A survey will be prepared to measure efficiency and the effectiveness of the Portal. |

### Grant Management

The Climate Change Adaptation Grant Programme (CCAGP) was opened as of 14 October 2020 and closed for applications as of 28 December 2020. Applications were received between these dates and the evaluation process for concept notes was completed as of March 2022.

Following the completion of evaluation process for concept notes, information days for the candidates who are eligible to submit a full application were organized on 22 and 23 March 2022 and related training report with its annexes was submitted on 1 June 2022 and approved by ER on 29 August 2022. English translation of the approved report was approved by ER on 18 January 2023.

As per the meeting held on 28 May 2022 with the CA, a draft MIS was established and shared (website https://mis.iklimeuyum.org/ ) on 21 October 2022 and comments from the CA were received on 25 January 2023. The system was updated accordingly. Another meeting was held on 24 March 2023 with the participation of the ER, CA and EUD to discuss features of drafted MIS.

The Grant Projects have been started to be implemented in December 2023.

After the approval of the addendum, the Grant Programme Experts were mobilized and started to carry out the 1st round of monitoring visits.

The progress in the activities related to the grant programme within the reporting period is presented as follows:

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 3.4.1. A desk review (i) to take stock of existing climate change adaptation grant programs among EU member states and countries with similar socio-economic profiles, such as EU’s LIFE funding and (ii) to evaluate ongoing grant programs and their mechanisms at national and local level for similar target audiences. The findings will guide the identification of activity scope and eligibility criteria for applications. | Desk review | 15 July 2020 (completed) | Approved on 30 November 2020 and submitted officially within the scope of the 1st Progress Report. |
| Activity 3.4.2. A training module on managing grants for the MOEUCC/DGEUFR staff and 2 one-day training session covering: The first training* will be on “Grant Scheme Implementation Process” including guidelines development, launch, evaluation and contracting. The second training** will be on “Grant Projects Management and Monitoring” including implementation rules, contract management and monitoring and evaluation. Training sessions will be held in Ankara, 20 people in total are expected to receive the training. | 2 Training modules (i)Grant Scheme Implementation Process (ii)Grant Projects Management and Monitoring 2 1-day trainings | i) May 2021 ii) February 2022 (completed) | The first two sessions were conducted as a half-day on 24 and 25th December 2021 with participation of 42 people. The training Report was submitted on 18 January and approved on 2 February 2022. The translation is submitted as an attachment to this Activity Report. |
| Activity 3.4.3. A set of guidelines include (i)Grant guidelines and the application package (ii)* Evaluation manual and annexes(iii) **Grant implementation manual, procurement manual, visibility manual and annexes and (iv)** Monitoring manual. | Set of guidelines | August 2021 (Completed) | Monitoring Guideline and its annexes were submitted on 6 April 2021. Turkish translation of Grant Implementation, Visibility, Procurement and Monitoring Guidelines were submitted on 21 June 2021. Comments on translations of other guidelines such as Evaluation Manual received on 23 August 2021; revised guidelines were submitted on 31 August 2021. |
| Activity 3.4.4. A training module on the use of the guidelines and 12 one-day training sessions to relevant stakeholders from public, private, academia and civil society. Training sessions will be held in Ankara and the pilot cities, 1,000 people in total are expected to receive the training. | Training Sessions | March 2022 (completed) | 2 one-day training sessions were held on 22 and 23rd March 2022 for second step applicants. |
| Activity 3.4.5. A web-based grant management information system (MIS) for grantees to follow up their notification/amendment requests for grant projects, share project deliverables, reporting inputs for M&E, and visibility. The system will also be used for conducting interim and final evaluations of grant projects by MOEUCC/DGEUFR. | Web-based grant program | April 2025 | The draft MIS was developed on the https://mis.iklimeuyum.org/ website for trial and testing purposes and shared with the CA on 21 October 2022. As planned this activity will be ongoing till Q1 2025. MIS system is expected to include interim and final evaluations of grant projects by MOEUCC/DGEUFR. |
| Activity 3.4.6. Opening and closure events of the grant programme, there will be two large events (one opening and one closure) in Ankara, with the participation of 150 people to each. | Opening and closure event | Q1 2025 but will be cancelled | The budget allocated for this line will be spared for reporting training. A notification will be prepared on this matter. |
| Activity 3.4.7. Technical and administrative assistance during grant application design, daily grant implementation, preparation of necessary implementation documents and letters (MOEUCC/DGEUFR is accountable for the execution of the grant contracts per se) and review, including monitoring visits. After the award of the grant contracts, a risk assessment and monitoring programme for the grant programme will be prepared in alignment with the MoEUCC. The number of monitoring visits will be planned accordingly; however, for calculation purposes in the budget, it is envisaged that 2 monitoring visits will be done to each project. 1 expert from the MOEUCC Directorate of Climate Change and the Grant Manager will attend each visit. There could be additional staff to these visits, such as staff from Contracting Authority and the EUD; however, only costs of visits for 1 expert from the MOEUCC Directorate of Climate Change and the Grant Manager will be covered from the project budget. A monitoring report will be prepared for each project after each monitoring visit and submitted to the Beneficiary, Contracting Authority and the EUD no later than 1 month after completion of each monitoring visit. | Technical support + monitoring visit reports | April 2025 | Technical assistance has been provided since October 2020. Grant Programme Experts regularly checks the MIS system for determining the questions pending for response, notifications and change requests of Grant Beneficiaries. - Answering the questions by getting in touch with the Beneficiaries if needed. - Determining the notification requests of the Grant Beneficiaries. - Processing the requests by completing the necessary supporting documents and checklists. - Making the requests ready for the approval of the Contracting Authority. The 1st round of monitoring visits has been completed. The general evaluation report has been prepared and submitted to all parties; the report was approved on 27 June 2024. The report includes the following information: - An executive summary, - Detailed findings, - Conclusions - Recommendations - Risk Assessment The 2nd Monitoring visits have been started in August 2024, 25 grant projects have been visited until 8 October. The second round of monitoring visits will be completed in November 2024. During Addendum No 1 , there was 2 monitoring visits and 1 spot check cost allocated in the budget and mentioned in the logical framework. However, in DoA of Addendum No 1, this detail was not mention by mistake. As per OCU, this issue has been clarified as 2 monitoring visit + 1 spot check. |
| Activity 3.4.8. Establishment of an M&E system including: (i) definition of metrics for documenting progress, measuring and communicating levels of effectiveness, (ii) an online M&E system for the Contracting Authority that encompasses the identified set of indicators in grant projects and will require all involved stakeholders to report into and (iii) regular reviews of activities undertaken as part of the grant. | M&E System | March 2025 | Studies to collect data were initiated in October 2020 and are still in progress. The indicators have been identified by grant programme expert and presented to all parties on 7th June 2024. The indicators have been updated during the monitoring visits by grant programme experts. The M&E system will be built into the MIS system. The MIS expert is currently working on the M&E system and entering relevant data into the system. Software expert will update MIS system covering the indicators defined under Activity 3.4.8. |
| Activity 3.4.9. Monitoring and Evaluation system and MIS will be used to measure the progress of grant projects in terms of realizing their activities, targets, indicators indicated in the grant projects. | Measures of grant projects | March 2025 | Once the M&E system is in place, the data collected will be entered into the system by the grant programme experts. This activity will continue until the end of the project. |
| Activity 3.4.10. 4 one-day consultative meetings throughout the course of the grant program to exchange information, assess progress and encourage collaboration among grant nominees. Meetings will be held in selected cities close to awarded grants, 40 to 50 representatives are expected to attend each meeting. | 4 consultative meeting | March 2025 | The first consultative meeting was organized on 28 August 2024 in İzmir with the hybrid participation of 76 number of people (32 men and 44 women). The grant projects were invited with relevant stakeholders such as universities, public institutions, civil society organizations. Grant projects shared their experiences during the implementation process of their projects. |
| Activity 3.4.11. A report on lessons learned and a dissemination strategy of grant activities. | Lessons Learnt | March 2025 | The preparation of the lessons learnt document will start in December 2024. However, as the end date of the Climate Change Adaptation Grant Programme is after the project, it will not be possible to prepare a comprehensive lessons learnt document. The TAT and relevant experts will work on this activity until the end of the project. This activity will be completed according to the developments in grant projects. |
| Activity 3.4.12. A compendium and a short documentary video for the grant programme, which consists of the outputs, results, achievements, and lessons learnt of the grant programme. | Compendium and a short documentary video | March 2025 | Preparation of the compendium and a short video will start in December 2024. However, since the end date of the CCAGP date is after the end of the project, it will not be possible to prepare a comprehensive compendium. The TAT and relevant experts will work on this activity until the end of the project. During the 1st consultative meeting, interview videos were recorded with grant beneficiaries. These videos will be used as an input for a short video for this activity. This activity will be completed according to the developments in grant projects. |
| Activity 3.4.13. Support in communication activities of grant beneficiaries. | An online workshop | March 202 | The support to the grant projects for their communication activities is ongoing and will continue until the end of the project. An online workshop is planned to be organized in September 2024 to inform Grant projects about communication activities, visibility guidelines and social media management. |
| Activity 3.4.14. Carry out portfolio level outreach and communication activities of the grants programme. | Outreach and communication activities | March 2025 | A Grant Brochure is prepared and shared the Directorate of Climate Change’s website and UNDP Türkiye’s social media accounts. The English version of the brochure is being prepared. Relevant outreach and communication activities will continue during the project. |

### The Concrete Results of the Project Components

The following outputs indicatively identified in section 1.6.2 of the DoA were achieved under each component during the reporting period:

#### Component 0 – Inception

|  | Main activities | Expected output | Result(s) / Comment(s) |
| --- | --- | --- | --- |
| 0.1 | Establishment of Technical Assistance Team (TAT) and office | Project Website Inception Report Envisaged delivery date: 12 weeks after the project start date. | Please see Notification No 1 for the extension of inception period. Project website was created & revised Inception report was submitted and approved Launch event was held Sectors and 4 metropolitan municipalities were identified Delivered |
| 0.2 | Kick-off meeting (first management meeting) |  |  |
| 0.3 | Launch event |  |  |
| 0.4 | The identification of priority sectors under five main sectors, and 4 metropolitan municipalities |  |  |

#### Component 1 - The “Adaptation Toolbox”: Decision-Making Tools for Climate Resilient Sustainable Development

|  | Main activities | Expected output | Result(s) / Comment(s) |
| --- | --- | --- | --- |
| 1.1 | Review of existing climate change adaptation works and best practice catalogue | Report including the comparative assessment, multi-parameter analysis framework, classification system, compilation of existing work and list of best practices Envisaged delivery date: 12 months after the project start date. | Envisaged delivery date was postponed as ’13 months after the project start date’. The report was submitted on 22/10/2020 and approved by the ER on 4 January 2021. The translation of the document was submitted for review on 22 March 2021 and approved on 13 April 2021. The approved final report was submitted as an annex to AR3. Delivered |
| 1.2 | Comprehensive climate change impact and vulnerability assessment for five priority sectors | Report including sensitivity analysis, updated climate projections, vulnerability scoping for sectors, sector climate vulnerability assessments, estimation of adaptation financial needs and meeting proceedings 5 sector climate change adaptation plans Envisaged delivery date: 24 months after the project start date. | Envisaged delivery date was postponed as ‘37 months after the project start date’. Submission date was revised as 8 November 2022 in accordance with the revised submission date of Activity 1.2.6 Delivered |
| 1.3 | Adaptation options for updating the NASAP | Report including desk review, comparative analysis, sector specific climate change adaptation strategies, adaptation options and meeting proceedings Envisaged delivery date: 30 months after the project start date. | Envisaged delivery date was postponed as ‘35 months after the project start date’. Draft report was submitted for review on 8 September 2022. Delivered |
| 1.4 | Updated NASAP through multi-stakeholder process | Report including action plan, dissemination activities and meeting proceedings Envisaged delivery date: 15 months after the project start date. | Envisaged delivery date was postponed as ‘40 months after the project start date’. The Turkish version was approved by DCC; approval awaited from CA. The English version was shared with DCC for approval. The English version of NASAP has been prepared and shared with DCC for review and approval. Updated NASAP submitted to the relevant authorities. Dissemination campaign will be initiated. |
| 1.5 | M&E system for the NASAP | Report including desk review, dissemination activities Envisaged delivery date: 9 months after the project start date. | Envisaged delivery date was postponed as ’13 months after the project start date’. Report was submitted on 12/11/2020 and approved by the ER on 21 February 2021. Delivered |
|  |  | Report: 1 Baseline and 2 annual progress reports for the NASAP Envisaged delivery date: 48 months after the project start date. | - |
|  |  | Training: Training module and reports Envisaged delivery date: 48 months after the project start date. | - |
|  |  | Tool: National online M&E system for the NASAP Envisaged delivery date: 36 months after the project start date. | Envisaged delivery date was postponed as ‘40 months after the project start date’. The M&E system was approved on 28 August 2024. Delivered |
|  |  | Outreach: dissemination material for the UASAPs Envisaged delivery date: 48 months after the project start date. | - |
| 1.6 | Climate financing strategy for the NASAP | Report including desk review, climate finance framework and action plan, and meeting proceedings Envisaged delivery date: 33 months after the project start date. | Envisaged delivery date was postponed as ‘41 months after the project start date’. DCC provided their comments on the finance strategy on 26.08.2024. A meeting was held with the Expert on 16 September 2024. Finance Strategy will be updated according to the meeting until the end of the October 2024. |
| 1.7 | Adaptation plan implementation guidelines for 5 priority sectors | Report including desk review, sector specific adaptation guidelines and meeting proceedings Envisaged delivery date: 39 months after the project start date. | Envisaged delivery date was postponed as ‘45 months after the project start date’ Delivered. |
|  |  | Training: training module and reports Envisaged delivery date: 39 months after the project start date. | Envisaged delivery date was postponed to Q1 2025. |

#### Component 2 - The “urban planning solution catalogue”: climate knowledge and adaptation planning for cities

|  | Main activities | Expected output | Result(s) / Comment(s) |
| --- | --- | --- | --- |
| 2.1 | Adaptation guidelines and urban typology framework for cities | Report including desk reviews, adaptation guideline for cities, typology framework/matrix and meeting proceedings Envisaged delivery date: 12 months after the project start date. | Envisaged delivery date was postponed as ’13 months after the project start date’. Draft report was submitted on 5 November 2020 and approved by the ER on 26 November 2020. Translation was also approved on 15 January 2021. The approved final report was submitted as an annex to AR3. Delivered. |
| 2.2 | Climate change impact and vulnerability assessment for 4 pilot metropolitan municipalities | Report including desk review, updated climate projections, vulnerability scoping for cities, urban climate vulnerability assessments, estimation of adaptation financial needs and meeting proceedings Envisaged delivery date: 21 months after the project start date. | Envisaged delivery date was postponed as ’28 months after the project start date’. The draft report was submitted on 8 February 2022. Delivered. |
| 2.3 | Preparation of UASAPs for 4 pilot metropolitan municipalities | Report including desk review, urban climate change adaptation strategies and action plans, and meeting proceedings Envisaged delivery date: 27 months after the project start date. | Envisaged delivery date was postponed as ’36 months after the project start date’. UASAP revisions are ongoing based on DCC's comments. |
|  |  | Outreach: media launch Envisaged delivery date: 27 months after the project start date. | Envisaged delivery date was postponed as ’39 months after the project start date’. Planning for the Media Launch has been initiated as of September 2024. The competition time of the activity will be revised. |
| 2.4 | M&E system for the UASAP | Report including desk review, dissemination activities Envisaged delivery date: 9 months after the project start date. | Envisaged delivery date was postponed as ’13 months after the project start date’. Report was submitted on 12/11/2020 and approved by the ER on 21 February 2021. Delivered. |
|  |  | Report: 1 Baseline and 2 annual progress reports for the UASAP Envisaged delivery date: 48 months after the project start date. | The contracted expert started the analysis phase for the M&E system. This is planned for Q3 of 2024 in addendum approval and we foresee that this will be completed in Q2 of 2025 due to approval of the addendum being realized in Feb 2024. |
|  |  | Training: Training module and reports Envisaged delivery date: 48 months after the project start date. | To be initiated, 2025 Q1, during third weekly meeting DCC informed UNDP that this activity is highly interrelated to activity 2.4.2. Following the completion 2.4.2 (or slightly progress) this activity will be initiated. |
|  |  | Tool: urban online M&E system for the UASAP Envisaged delivery date: 33 months after the project start date. | Envisaged delivery date was postponed as ‘41 months after the project start date’. |
|  |  | Outreach: dissemination material for the UASAPs Envisaged delivery date: 48 months after the project start date. | - To be initiated, 2025 Q1 |
| 2.5 | Urban climate financing strategy | Report including desk review, assessment and urban climate financing strategy Envisaged delivery date: 33 months after the project start date. | Envisaged delivery date was postponed as ‘43 months after the project start date’. The draft working paper on climate financing mechanisms was submitted on 8 February 2022. The comments from ER were received on 27 May 2022. The revised document was submitted on 27 July 2022. Delivered. |
|  |  | Training: Training module and reports Envisaged delivery date: 33 months after the project start date. | Envisaged delivery date was postponed as ‘44 months after the project start date’ To be initiated, this activity is postponed to Q1 202, because it is highly interrelated to activity 1.6.5. |

#### Component 3 - The “network”: build capacity through trainings and networking

|  | Main activities | Expected output | Result(s) / Comment(s) |
| --- | --- | --- | --- |
| 3.1 | Policy and stakeholder capacity and need assessment | Report including desk reviews, technical capacity and need assessment and meeting proceedings Envisaged delivery date: 9 months after the project start date. | Envisaged delivery date was postponed ‘21 months after the project start date’ The report was submitted on 08/07/2021. Delivered. |
| 3.2 | Capacity building and networking | Report including capacity building plan and meeting proceedings Envisaged delivery date: 48 months after the project start date. | Envisaged delivery date was revised ‘23 months after the project start date’ Report was submitted on 08/09/2021 and was approved on 24/05/2022. Turkish translation was submitted on 23/09/2022. Delivered. |
|  |  | Training: Training modules and reports Envisaged delivery date: 48 months after the project start date. | The training modules will be updated as per the knowhow in Ankara pilot training conducted on 30-31 July 2024. |
|  |  | Study visits: study visit reports Envisaged delivery date: 48 months after the project start date. | A study visit to the Netherlands was organized on 19-23 August 2024. Another study visit will be organized in Q1 2025. |
|  |  | Training: Awareness raising material and reports Envisaged delivery date: 48 months after the project start date. | - |
|  |  | Outreach: success and human stories for media outreach Envisaged delivery date: 48 months after the project start date. | - |
|  |  | Outreach: series of documentary style short movies Envisaged delivery date: 48 months after the project start date. | - |
| 3.3 | National Adaptation Platform | Report including desk review Envisaged delivery date: 48 months after the project start date. | Report including desk review (3.3.1) was submitted and approved on 06/10/2020. Delivered. |
|  |  | Tool: running national adaptation platform Envisaged delivery date: 48 months after the project start date. | Delivered. |
|  |  | Report: 1 Baseline and 2 annual progress reports Envisaged delivery date: 48 months after the project start date. | Delivered. |
|  |  | Outreach: media launch Envisaged delivery date: 48 months after the project start date. | It is planning to be organized in Q4 2024, agenda has been developed to be discussed with DCC. |
| 3.4 | Technical Assistance for Implementation of the Climate Change Adaptation Grant Programme (CCAGP) | Report including desk review, set of guidelines, lessons learned and meeting proceedings Envisaged delivery date: 48 months after the project start date. | Report including desk review (3.4.1) was submitted and approved on 16/10/2020. A set of grant guidelines was submitted and approved as of 28/04/2021 Delivered. |
|  |  | Training: Training modules and reports Envisaged delivery date: 48 months after the project start date. | Information Days were held between 23 October 2020 and 6 November 2020 and related training report was submitted and approved on 01/02/2021. The first two sessions of EU Grant Scheme Implementation Process training were held on 24 and 25 December 2020 and related training report was submitted and approved on 02/02/2021. 2 one-day training sessions on the use of the guidelines were held on 22 and 23rd March 2022 for second step applicants. Last sessions of ‘Grant Scheme Implementation Process’ Training were held on 25 April 2022. ‘Grant Projects Management and Monitoring’’ Training were held in premises of MoEUCC on 12 and 13 September 2022. Reports for above-mentioned trainings were submitted and approved. The first round of monitoring visits was completed in July 2024. The general evaluation report of 1st round monitoring visits was prepared and approved by CA and DCC. The second round of monitoring visits have been started in August 2024. The 2nd round will be completed in November. |
|  |  | Tool: Web-based grant programme information system Envisaged delivery date: 48 months after the project start date. | The web-based grant programme information system has been developed. Regular updates will continue until the end of the project. |
|  |  | Meeting: opening and closure events Envisaged delivery date: 48 months after the project start date. | The budget allocated for the opening event will be reallocated for a reporting training. A notification will be prepared on this matter. |
|  |  | Tool: M&E system for the grant programme Envisaged delivery date: 48 months after the project start date. | The M&E system has been developed and the indicators of the grant projects are currently being compiled by the grant experts. |
|  |  | Outreach: One compendium and a short documentary style video Envisaged delivery date: 48 months after the project start date. | Interview videos were shot with grant beneficiaries. These videos will be used as an input for a short video for this activity. This activity will be completed until the end of the project. |

## Risks, Risk Mitigation and Adaptive Management

As the project advances, it is critical to continuously reassess and manage the risks and assumptions that may influence the achievement of our objectives. During this reporting period, a detailed evaluation has identified new risks that could impact the project’s timeline, and overall success. These emerging risks, in conjunction with those previously recognized, necessitate the development of robust mitigation strategies to ensure the project remains on course.

One significant risk that has been identified pertains to the potential delays in meeting the project’s activity deadlines, which can be classified as a high-risk factor. This concern arises primarily due to the timing of key project milestones: the addendum was approved in February 2024, leading to the subsequent establishment of the Project Management Unit (PMU) under UNDP’s accountable and transparent HR rules. The PMU was not fully operational until July 2024. Although the pace of activities has recently accelerated, there is still a tangible risk that the project may not be successfully completed by the 8 April 2025 deadline.

Given the importance of adhering to the project timeline, it is crucial to acknowledge this risk and take proactive steps to mitigate it. The following section provides a detailed overview of this and other newly identified risks, along with the assumptions underlying them, and the strategies proposed to manage these risks effectively.

Grant projects implemented under CCAGP started in December 2023. Most of the grant projects end in June 2025, hence it will not be possible to prepare the evaluation of the final reports compendium and the report on lessons learnt during the project’s implementation period. In addition, regular support to grant projects via MIS and phone/email will not be provided after April 2025.  In the case of project closure in April 2025, there is a need for specific planning to ensure continuation and sustainability of grant projects.

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Risk event: Appearance of a new viral infection Risk cause: Declaration of coronavirus (COVID-19) outbreak as a pandemic Risk impact: Delivery of results may be affected negatively. Meetings/ trainings/workshops, may not be realized within the scope of the projects in the planned dates | 09-Nov-2021 | Environmental (Community health, safety and security) | Impact: 4 Probability: 3 Risk Level: Substantial | The project team has been conducting online/hybrid events to minimize community transmission and to continue organizing consultative meeting and trainings although there were lack downs. Although there had to be some adjustments to the project’s annual work plan as a result of the pandemic, no major challenges have been encountered to this date. The project team continues to follow the advisory of the Government and UNDP and ensures that the risk kept minimized. | UNDP | 31-Dec-2021 | Closed |
| 2 | Risk event: In the case of new restrictive measures imposed by the government due to a new variant of the COVID-19 pandemic Risk cause: Meetings/trainings/workshops may not be physically held or may be held in a hybrid manner within the scope of the project in the planned dates. Risk impact: Pandemic conditions may affect project workplan more than expected. Such effects can be too catastrophic to continue project activities | 01-Dec-2021 | Environmental (Community health, safety and security) | Impact: 3 Probability: 2 Risk Level: Low | Official travels, meetings, and consultations within the institutions, attendance to meetings/workshops can be postponed until the normalization period begins. Meetings and events can be conducted via online meeting tools when possible. Study visits may be transformed into virtual tours and presentations if necessary. | UNDP | 16-Aug-2024 | Closed |
| 3 | Risk event: Possible delays may cause extended durations Risk cause: Delays in tendering process for Grant Programme due to prolonged review/evaluation durations Risk impact: Inability to complete activities within the current deadline | 01-Dec-2021 | Operational (Responsiveness to audit and evaluations (Delays in the conduct of and implementation of recommendations)) | Impact: 3 Probability: 4 Risk level: Moderate | Elevation of the issue to higher level managers through the PSC and OCU meetings have been utilized to address and mitigate this risk. Close coordination between the PSC and technical team is assured by Operation Coordination Unit (OCU) for proactive management of risks and outside factors. Informal talks with CA have been kicked off for an 18- month extension with the new proposed deadline of 08/04/2025. | Contracting Authority | 16-Aug-2024 | Updated risk |
| 4 | Risk event: If the government ownership will be low and institutional coordination will not be effective timely implementation of the regulations will be affected. Risk cause: Insufficient institutional coordination at national and local level to effectively implement key policies and regulations on climate change adaptation Risk impact: Ineffective implementation of regulations. | 16-Jan-2020 | Strategic (Stakeholder relations and partnerships) | Impact: 3 Probability: 2 Risk Level: Low | The overall strategic direction of the project will be provided by a Project Steering Committee (PSC), consisting of representatives of the MoEUCC/Presidency of Climate Change, the contracting authority (MoEUCC/DGEUFR), UNDP and the relevant members of the CBCCA and other stakeholders when deemed necessary. While this multi-sectoral structure will enhance the coordination among institutions at several levels, it is also planned to specifically promote an inter-sectoral coordination mechanism, which will serve as the primary mitigation measure to this risk. A coordination among national and urban level will also be enhanced through National Adaptation Platform to be established by the Project. Coordination will be established through regional meetings, workshops and consultation meetings. In addition to those efforts, Strategy and Budget Office (SBO) of the Presidency will join the PSC meetings as a natural member to assist coordination and governance function. | Beneficiary | 07-Dec-2022 | Ongoing |
| 5 | Risk event: Lack of close coordination Risk cause: Factors outside the control area of the Project Risk impact: Insufficient output-outcome linkages | 16-Jan-2020 | Strategic (Government commitment) | Impact: 3 Probability: 2 Risk Level: Low | The PSC will operate several functions where verifying the achievement of the outputs and results of the project is the main one as a primary mitigation measure to this risk. Close coordination between the PSC and technical team will be assured by Operation Coordination Unit (OCU) for proactive management of risks and outside factors. The OCU will be formed by the MoEUCC/Presidency of Climate Change representative, technical assistant team (TAT) and Contracting Authority (when necessary) and meet monthly basis to effectively manage the progress of the projects to take corrective measures deem necessary. Following the preparation of the National Adaptation Strategy and Action Plan, the PSC members will submit the strategy to higher planning council, in coordination with the SBO, for approval. | Government | 07-Dec-2022 | Ongoing |
| 6 | Risk event: No adequate and sufficient data collected Risk cause: Lack of data at national and urban level for detailed analysis Risk impact: Lack of data will effect the level of analysis | 16-Jan-2020 | Operational (Knowledge management) | Impact: 2 Probability: 3 Risk Level: Low | The lack of high-quality data and information is highlighted by the NASAP along with other challenges such as lack of concordance of available information, the insufficiency of scientific research, difficulties in producing projects, determining the effects of climate change at sector and urban context. Since then, there are several studies undertaken by academia focusing on paleoclimate studies, modelling and prediction including general circulation models, climate change impacts and response options, research and development on mitigation and adaptation technologies. As highlighted by the Climate-Adapt, there are over 60 projects and nearly 170 theses carried out in Türkiye. Expert judgment and literature are thoroughly utilized to compensate for the lack of data. The project will mitigate this to the extent possible by undertaking stocktaking activities for all outputs in collaboration with ministries, municipalities, research centers, universities and EU institutions. Moreover, the project will establish a National Adaptation Platform to facilitate knowledge and expertise sharing and networking while providing information on climate impacts and adaptation information, adaptation policies, climate data, impact and vulnerability assessments, research programmes, adaptation options, local actions, case studies, etc. | Beneficiary | 07-Dec-2022 | Ongoing |
| 7 | Risk event: Not enough technical approaches in the field Risk cause: Insufficiently robust technical approaches in the field of climate change adaptation due to lack of experience and know-how at national and urban context in Türkiye Risk impact: Lack of experience will effect the technical approaches and key solutions. There is a risk that some project activities could be delayed or could face unexpected problems due to inadequate technical experience. | 16-Jan-2020 | Operational (Accountability) | Impact: 4 Probability: 2 Risk Level: Moderate | Although Türkiye has a number of high-quality academic institutions and many highly qualified scientists, the field of climate change adaptation is still essentially a new realm of building resilience at national and urban context in Türkiye. Therefore, there is little direct experience with real-world implementation of many of the technical aspects of climate change adaptation activities that will be necessary to achieve the project objective. Therefore, there is a risk that some project activities could be delayed or could face unexpected problems due to inadequate technical experience. The project will mitigate this by ensuring that the project draws on the best international and EU practices known that are relevant for the Turkish context. This will include, for example, conducting conferences and seminars with invited international experts. The project also plans to possibly undertake study tour activities to other EU countries and institutions with more extensive experience in this realm, as long as they are relevant for the Turkish context. Moreover, the project will adopt the latest assessment report of the IPCC (AR5) on the definition and framework to propose a risk and vulnerability assessment (RVA) for cities. | Beneficiary | 07-Dec-2022 | Ongoing |
| 8 | Risk event: Turnover in government/local administrations staff due to reshuffling or elections Risk cause: Slowdown in administrative processes and inadequate stakeholder and technical expertise engagement related to potential institutional change. Risk impact: Prolonged output review and approval durations, slowed down grant implementation and delayed high-level visibility events | 16-Jan-2020 | Strategic (Change/turnover in government) | Impact: 3 Probability: 4 Risk Level: Moderate | Addressing climate change adaptation in a comprehensive manner requires involvement of multiple national institutions, as well as coordination at the field level. The project has built in specific mechanisms to support this coordination and interaction. However, there is a high turnover rate in Türkiye in government/local administrations staff. Additionally, turnovers in the management positions at DCC is expected in near time. In this context of institutional change, it may be difficult for the project to effectively engage all necessary stakeholders and government experts during project implementation. The project will continuously monitor this risk and take adaptive management measures as necessary if this risk appears to negatively affect the project’s operational approach and effectiveness. New staff and administrators are engaged effectively to be integrated into the project management structure. | Beneficiary | 07-Dec-2022 | Ongoing, |
| 9 | Risk event: Climate change may affect ecosystems in the Country more than expected. Risk cause: Climate change affects Türkiye’s ecosystems and socio-economic systems in a manner that overwhelms the project efforts. Risk impact: Such effects can be too catastrophic to continue project activities at national and urban level. | 16-Jan-2020 | Environmental (Climate change and disaster risks) | Impact: 2 Probability: 2 Risk Level: Low | There is no question that climate change is occurring and affecting Türkiye’s ecosystems, and socio-economic systems. Such effects can be too catastrophic to continue project activities at national and urban level. Nonetheless, the project will mitigate this risk by tracking some climate change risk indicators (e.g. floods, forest fires, etc.), and will continually assess if climate change is leading to any catastrophic changes in relation to the project activities. If it is identified that catastrophic changes are occurring, the project will re-direct and re-plan project resources and activities, as appropriate, to address these challenges in close consultation with the MoEUCC and the EUD. The PSC will make any decision along these lines, with technical input from the project Technical Assistant Team. | Government | 07-Dec-2022 | Ongoing |
| 10 | Risk event: Delays in Project Activities Risk cause: the late approval of the project addendum in February 2024 and the delayed operationalization of the Project Management Unit in July 2024, resulting in a compressed timeline for completing activities. Risk impact: Failure to complete project activities with fully effective manner on time may result in unmet project objectives and goals | 12/08/2024 | Operational (Implementation Arrangements) | Impact: 3 Probability: Risk Level: Moderate | The risk of project delays is primarily caused by the late approval of the project addendum in February and the delayed operationalization of the Project Management Unit in July 2024, resulting in a compressed timeline for completing activities. To address the risk of delayed project activities, the project team will implement an accelerated work plan, prioritizing critical tasks to ensure timely completion of key deliverables. Additionally, regular communication with stakeholders will be maintained to manage expectations and provide updates on progress. | UNDP | 12/08/2024 | New |

### Plans for the upcoming period

#### Component 1

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 1.4. Updated NASAP through multi-stakeholder process (ongoing) |  |  |  |
| Activity 1.4.4. An updated NASAP, including: (i) strategic priorities and areas of intervention in accordance of SDGs, (ii) an action plan with a list of selected climate change adaptation solutions, (iii) capacity building activities of relevant stakeholders, and (iv) a coordination mechanism among national entities (public, private, academia, civil society) at different levels and with international organizations. | Updated NASAP | November 2024 | These studies were launched in June 2022. The updated NASAP was submitted for comments on 9 January 2023. In accordance with the comments received, the actions were revised, and the total number of actions was limited to 150 and submitted for review by the stakeholder institutions through the DCC on 11 May 2023. Another revision was conducted upon comments received in the consultative meetings held in July 2023, the revised NASAP submitted for a second round of comments on 31 July 2023. The updated version of the NASAP was submitted for the final round of comments in August. To obtain consensus from all stakeholders, a two-day working group meeting was held on 19-20 September 2023 and the NASAP is being finalized accordingly. The Turkish version was approved by DCC, CA and the EUD. The English version was shared with DCC for approval. |
| Activity 1.4.6. Dissemination campaign of the NASAP among central and local authorities, civil society, academia, the private sector and the international community. | Dissemination campaign of the NASAP | December 2024 | The design was completed and shared via social media which can be found in Annex 08. The dissemination campaign is ongoing. The brochures and printed version of NASAP will be shared during COP, meetings and trainings. |
| Activity 1.5. M&E system for the NASAP (ongoing) |  |  |  |
| Activity 1.5.3. A training module on the use of M&E systems and 4 two-days online training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the NASAP. 150 staff in total are expected to receive the training. | Training Module on the use of M&E system | February 2025 | A meeting was held with the software expert on 19.09.2024 The preparation of the training module is underway. The training sessions will be organized on 5-6 November 2024 for 4 2 days online sessions. Planning has been started. |
| Activity 1.5.4. A regular review of the priorities and activities identified in the NASAP to assess progress, effectiveness and gaps. The review process will consist of one baseline assessment and 1 annual progress evaluations during the lifetime of the project. | Baseline assessment/ Annual Progress Evaluation | December 2024 | A preliminary meeting was held with the software expert. The activity completion date has been revised as December 2024. |
| Activity 1.5.5. Outreach of the NASAP and the progress reports at national level through national communications and various media tools. | Outreach | December 2024 | A preliminary meeting was held with the software expert. Outreach activities were initiated during the trainings going to be conducted with the software expert under activity 1.5.3. The first entrance of the documents expected under the responsible institutions will be monitored during the training going to be conducted in Q42024. |
| Activity 1.6. Climate financing strategy for the NASAP |  |  |  |
| Activity 1.6.5. A final climate finance strategy by combining the financing framework and the climate finance action plans, together with the inputs and feedback from the consultative meetings. | Final climate finance strategy | January 2025 | Studies to collect data are initiated in December 2022. It was prepared following the finalization of the National Climate Change Adaptation Strategy and Action Plan and submitted for review on 23 May 2023. The final climate finance strategy was submitted to DCC on 10.07.2024. Relevant expert updated the financial strategy. Please refer to Annex 11. A meeting was held with the expert and DCC to clarify the expectations. Another meeting with sectoral experts held on 19.09.2024 to receive sectoral updates. The expert plans to submit the updated version by the end of October 2024. |
| Activity 1.7. Adaptation plan implementation guidelines for priority sectors (ongoing) |  |  |  |
| Activity 1.7.3 5 sector specific adaptation plan implementation guidelines including (i) tools and methodologies for different types of adaptation work (structural, non-structural), (ii) connections with the existing sectoral strategy and investment plan, (iii) connections with the climate finance strategy, and (iv) criteria for decision-making and evaluation. The finance section of the guidelines will be integrated with activity 1.6 | Sector -specific Adaptation Plan Implementation Guidelines | December 2024 | The activity is ongoing. Updated adaptation plans are being reviewed by 11 sector experts and expected to be shared with the Ministry by December 2024. Please refer to Annex 12. |
| Activity 1.7.4. A training module on the use of the guidelines and 5 two-days training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the NASAP. Training sessions will be held in Ankara, 250 staff in total are expected to receive the training. | Training Module | Q1 2025 | The activity completion date was revised as Q1 2025 based on the Addendum. |

#### Component 2

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 2.3. Preparation of UASAPs for 4 pilot metropolitan municipalities (ongoing) |  |  |  |
| Activity 2.3.3. 4 UASAPs for the pilot cities including structural and non-structural adaptation measures and using the vulnerability index map developed in Activity 2.2. The UASAPs will include adaptation goals, indicative timeframe, budget and funding options, baseline and performance indicators and responsible organisation(s) for each goal/action. | 4 UASAPs 4 two-day consultative meetings | December 2024 | UASAPs were revised in line with comments of the ER, and the consultative meetings held in pilot cities in June 2023. The revised plans were again sent for review by the local stakeholders to finalize. Currently, UASAPs are under revision. DCC has provided their final comments. Experts will reflect them on the action plans and UASAP's for each sector in 4 pilot provinces. The draft UASAPs can be reviewed under Annex 13. |
| Activity 2.3.4. A media launch in Ankara for 200 people about each city and dissemination materials in different formats for different target audiences/stakeholders. | Media launch | Q1 2025 | The media launch is planned to be held following the approval of the UASAPs for four pilot cities. |
| Activity 2.4. M&E system for the UASAPs (ongoing) |  |  |  |
| Activity 2.4.2. An online M&E system for cities that encompasses the identified set of indicators and will require all involved stakeholders to report into. | Online M&E system | In DoA Cancelled / deleted by mistake during Addendum No1 approved in Feb 2024. However, as per OCU decision, this activity will be conducted. | Ongoing; the contracted expert has started the analysis phase for development of the M&E system. This was scheduled for Q3 2024 in the addendum approval yet expected to be completed in Q4 2024 as the addendum approval was realised in Feb 2024. It is also agreed to hold 1 day M&E training in pilot municipalities instead of discussing M&E system layout under Activity 2.4.2 during the first quarter of 2025. |
| Activity 2.4.3. A regular review of the priorities and activities identified in the UASAPs to assess progress, effectiveness and gaps. The review process will consist of one baseline assessment and 1 annual progress evaluation during the lifetime of the Project. | 1 baseline assessment and 1 annual progress evaluation | Q2 2025 | The contracted expert started the analysis phase for the M&E system. This activity has been planned for Q3 of 2024 but the estimated completion time for the activity will be updated to Q2 2025 according to up-to-date AWP due to the approval of the latest Addendum was completed in February 2024. Following the completion (or depending on the progress) of Activity 2.4.2, this activity will be initiated. |
| Activity 2.4.4. A training module on the use of M&E systems and 4 one-day online training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the UASAPs. 100 staff in total are expected to receive the training. | A training module on the use of M&E systems and 4 one-day online training sessions | Q1 2025 | To be initiated |
| Activity 2.4.5. Outreach of the UASAPs and the progress reports at national level through national communications and various media tools | Outreach | Q1 2025 | To be initiated |
| Activity 2.5. Urban climate financing strategy (ongoing) |  |  |  |
| Activity 2.5.3. A conference bringing IFIs and local authorities together to explore IFIs’ global experience in urban climate financing, and discuss suitable solutions for Turkish cities. This conference will complement the national level consultative stakeholder meetings from Activity 1.6 with local level perspectives. The meeting will be held in Istanbul attended by approximately 30 people, from IFIs, Municipalities, MoEUCC and relevant other institutions. | Conference | April 2025 | This activity has been postponed to Q1 2025 as it is highly linked to Activity 1.6.5. This activity will be revised during Addendum No2 to reach out more participants since it was reported as 30 people during Addendum No 1. |
| Activity 2.5.4. An estimation of adaptation financial needs for each city and potential market for adaptation at national scale, with a baseline “business as usual” scenario for comparison. These assessments will take into consideration costs associated with circumventing existing or planned mal-adaptation measures to inform the development of no-regret and low-regret adaptation measures.​ | Urban climate financing needs report | April 2025 | Ongoing. The relevant expert has been contracted. Activity completion date revised to April 2025. |
| Activity 2.5.5. An urban climate financing strategy for the implementation of UASAPs | Urban Climate finance strategy for the implementation of the UASAPs. | April 2025 | This activity has been postponed to Q1 2025 as it is highly linked to Activity 2.3.3. |
| Activity 2.5.6. A training module on the financial mechanisms and 4 two-days training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the UASAPs. Training sessions will be held in pilot cities, 100 staff in total are expected to receive the training. | A training module on the financial mechanisms and 4 two-days training sessions | Q1 2025 | To be initiated on Q2 2025. |

Component 3

| Activity |  | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- | --- |
| Activity 3.2. Capacity building and networking (ongoing) |  |  |  |  |
| Activity 3.2.2. At least 10 customized climate change adaptation training modules (including initial and follow up sessions) on topics such as (i) awareness raising on climate change, (ii) use of climate scenarios and models, (iii) impact and vulnerability assessment, (iv) adaptation planning, and (v) Sector specific adaptation, etc. |  | 11 Training modules including each NASAPs sector | Ongoing | Presentations of three modules were submitted for review on 15 September 2023. The training modules will be prepared as per the know-how in Ankara Pilot Training conducted on 30-31 July 2024. |
| Activity 3.2.3. At least 20 two-days training sessions to relevant stakeholders from public, private, academia and civil society. Training sessions will be held in Ankara and the pilot cities, 600 staff in total are expected to receive the training. |  | Training sessions | April 2025 | The pilot training was held on 30-31 July in Ankara. 23 women, 15 men attended the training. 38 participants were given certificates for successfully completing the training. The second training was held on 13-14 August in Eskişehir. 24 women and 20 men attended the training. Participants were asked Menti and evaluation questions to measure their level of knowledge and learning throughout both training. 44 participants were given certificates for successfully completing the training. Please refer to Annex 1 for the training content, attendance and photographs. - The 3rd training was held on 9-10 September in Van (14 women 27 men). - The 4th training was held on 30 September-01 October in Trabzon (15 women 34 men). - The 5th training will be organized for 15-16 October in Antalya. - The 6th training will be organized for 12-13 November in Nevşehir. - The 7th training will be organized for 10-11 December in Diyarbakır. |
| Activity 3.2.4. At least 7 study visits for 10 participants to promote knowledge exchange between Turkish and European cities on climate change adaptation. Participants will be selected from the target audience (i.e. MOEUCC staff working within the scope of the project, relevant local authorities, NGOs/associations, and academia), each will fill a report indicating how the study visit was (or was not) useful to the activities in Türkiye. The list of study visit participants shall be notified to EUD before MOEUCC approval, and EUD is to clear the list of attendance within two weeks after submission. MOEUCC approval shall only be sought after “no objection” is received from EUD. |  | 7 study visits | March 2025 | The first of the study visits was conducted in Valladolid and Madrid, Spain, between 28 November and 1 December 2022. The second visit was carried out between 8-11 May 2023 in Copenhagen, Denmark (8-9 May) and Stockholm, Sweden (10-11 May). The project team, experts from the Ministry of Environment, Urbanization and Climate Change, the end recipient and representatives of the pilot municipalities of the project, Konya, Muğla, Sakarya and Samsun Metropolitan Municipalities, attended to the visit. On 18-23 August 2024, Netherlands was visited. Please refer to Annex 06. The last Study visit planning is initiated. Last study visit expected to be conducted in 2025 to Germany. The estimated completion time for the activity will be updated according to the need. |
| Activity 3.2.5. 4 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to present their experience with different city networks and advise on membership. Meetings will be held online; 50 to 60 representatives are expected to attend each meeting. |  | 4 1-day consultative meetings (online), 2 meetings remaining | Q1 2025 | In line with the decision taken at OCU Meeting No. 18, the first set of meetings were held online with broader participation from municipalities at national level on 28-29 September 2021. Please refer to Annex 09. The remaining meetings are postponed to Q1 2025. |
| Activity 3.2.6. 7 awareness raising conferences in all regions, including the pilot cities, to promote the central and local climate change adaptation agendas, and facilitating networking and partnership building between relevant stakeholders. The event will be in form of town-hall meeting, where the level of interaction between the parties will be strengthened and the key areas of planning, action, financing for climate change adaptation will be discussed in line with innovative and inclusive communication techniques as highlighted in Section 1.4. Methodology. At least 608 local actors are expected to participate. |  | 7 awareness raising conferences | March 2025 | .UNDP will prepare proposals for possible topics related to this activity. Planning will be initiated. |
| Activity 3.2.7. A series of success and human stories from the training and awareness raising events to be used on website and social media. |  | Success and human stories | March 2025 | The planning of the activity will be initiated as of the first quarter of 2025. During the training to be conducted as per Activity 3.2.3 success stories will be recorded and disseminated. |
| Activity 3.2.8. A series of 10 documentary style short movie (3 to 6 minutes), whose content will aim to familiarize the target audience and public at large on the work done in 5 priority sectors and 4 pilot municipalities on climate change adaptation (and 1 general content). The short movies will be broadcasted within the public institutions and municipalities as well as shared with private firms, academia and the civil society. |  | 10 Short Movies | Q1 2025 | The first video in the series started with the transport and communications sector, which was approved on 19 September 2022. Videos on agriculture and food security and water resources management were submitted for review on 21 August 2023. The remaining seven scripts were also submitted for review on 1 September 2023. At previous OCU meetings this activity was reported as completed. However, it is noted that a biodiversity sector video needs to be prepared based on consultations with DCC. The DCC sent an email on 19 July 2024 stating that the activity was incomplete. Since there are 11 sectors in NASAP, additional 1 sector will be added. |
| Activity 3.3. National Adaptation Platform (ongoing) |  |  |  |  |
| Activity 3.3.3. Content upload to the platform (publications, reports, media, etc.) and links with relevant networks and online platforms. |  | Content upload | March 2025 | Data entry has begun and will continue until the end of the project. |
| Activity 3.3.4. Media launch and technical presentation of the platform to key stakeholders; presentation of climate change adaptation work per sector and development of sector specific infographics and presentation material; organization of two public events (i.e. contest, exhibition) on climate change adaptation work. Media launch will be in Ankara with participation of 200 people. | Media launch |  | December 2024 | It is planned to be organized by November 2024, the draft agenda has been developed. |
| Activity 3.3.5. Regular evaluation of the efficiency and effectiveness of the platform and its use for the NASAP, for sector specific climate change adaptation and for urban climate change adaptation through an annual web-based survey | Web based survey |  | March 2025 | A survey will be prepared to measure efficiency and the effectiveness of the Portal. |

Grant Programme

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 3.4.5. A web-based grant management information system (MIS) for grantees to follow up their notification/amendment requests for grant projects, share project deliverables, reporting inputs for M&E, and visibility. The system will also be used for conducting interim and final evaluations of grant projects by MOEUCC/DGEUFR. | Web-based grant program | April 2025 | The draft MIS was developed on the https://mis.iklimeuyum.org/ website for trial and testing purposes and shared with the CA on 21 October 2022. As planned this activity will be ongoing till Q1 2025. MIS system is expected to include interim and final evaluations of grant projects by MOEUCC/DGEUFR. |
| Activity 3.4.6. Opening and closure events of the grant programme, there will be two large events (one opening and one closure) in Ankara, with the participation of 150 people to each. | Opening and closure event | Q1 2025 but will be cancelled | The budget allocated for this line will be spared for reporting training. A notification will be prepared on this matter. |
| Activity 3.4.7. Technical and administrative assistance during daily grant implementation, preparation of necessary implementtaion documents and letters, implementation (MOEUCC/DGEUFR is accountable for the execution of the grant contracts per se) and review, including monitoring visits. After the award of the grant contracts, a risk assessment and monitoring programme for the grant programme will be prepared in alignment with the MoEUCC. The number of monitoring visits will be planned accordingly; however, for calculation purposes in the budget, it is envisaged that 2 monitoring visits will be done to each project. 1 expert from the MOEUCC Directorate of Climate Change and the Grant Manager will attend each visit. There could be additional staff to these visits, such as staff from Contracting Authority and the EUD; however, only costs of visits for 1 expert from the MOEUCC Directorate of Climate Change and the Grant Manager will be covered from the project budget. A monitoring report will be prepared for each project after each monitoring visit and submitted to the Beneficiary, Contracting Authority and the EUD no later than 1 month after completion of each monitoring visit. | Technical support + monitoring visit reports | April 2025 | Technical assistance has been provided since October 2020. Grant Programme Experts regularly checks the MIS system for determining the questions pending for response, notifications and change requests of Grant Beneficiaries. - Answering the questions by getting in touch with the Beneficiaries if needed. - Determining the notification requests of the Grant Beneficiaries. - Processing the requests by completing the necessary supporting documents and checklists. - Making the requests ready for the approval of the Contracting Authority. The 1st round of monitoring visits has been completed. The general evaluation report has been prepared and submitted to all parties; the report was approved on 27 June 2024. The report includes the following information: - An executive summary, - Detailed findings, - Conclusions - Recommendations - Risk Assessment The 2nd Monitoring visits have been started in August 2024, 25 grant projects have been visited until 8 October. The second round of monitoring visits will be completed in November 2024. During Addendum No 1 , there was 2 monitoring visits and 1 spot check cost allocated in the budget and mentioned in the logical framework. However, in DoA of Addendum No 1, this detail was not mention by mistake. As per OCU, this issue has been clarified as 2 monitoring visit + 1 spot check. |
| Activity 3.4.8. Establishment of an M&E system including: (i) definition of metrics for documenting progress, measuring and communicating levels of effectiveness, (ii) an online M&E system for the Contracting Authority that encompasses the identified set of indicators in grant projects and will require all involved stakeholders to report into and (iii) regular reviews of activities undertaken as part of the grant. | M&E System | March 2025 | Studies to collect data were initiated in October 2020 and are still in progress. The indicators have been identified by grant programme expert and presented to all parties on 7th June 2024. The indicators have been updated during the monitoring visits by grant programme experts. The M&E system will be built into the MIS system. The MIS expert is currently working on the M&E system and entering relevant data into the system. Software expert will update MIS system covering the indicators defined under Activity 3.4.8. |
| Activity 3.4.9. Monitoring and Evaluation system and MIS will be used to measure the progress of grant projects in terms of realizing their activities, targets, indicators indicated in the grant projects. | Measures of grant projects | March 2025 | Once the M&E system is in place, the data collected will be entered into the system by the grant programme experts. This activity will continue until the end of the project. |
| Activity 3.4.10. 4 one-day consultative meetings throughout the course of the grant program to exchange information, assess progress and encourage collaboration among grant nominees. Meetings will be held in selected cities close to awarded grants, 40 to 50 representatives are expected to attend each meeting. | 4 consultative meeting | March 2025 | The first consultative meeting was organized on 28 August 2024 in İzmir with the hybrid participation of 76 number of people (32 men and 44 women). The grant projects were invited with relevant stakeholders such as universities, public institutions, civil society organizations. Grant projects shared their experiences during the implementation process of their projects. Please refer to Annex 09. |
| Activity 3.4.11. A report on lessons learned and a dissemination strategy of grant activities. | Lessons Learnt | March 2025 | The preparation of the lessons learnt document will start in December 2024. However, as the end date of the Climate Change Adaptation Grant Programme is after the project, it will not be possible to prepare a comprehensive lessons learnt document. The TAT and relevant experts will work on this activity until the end of the project. This activity will be completed according to the developments in grant projects. |
| Activity 3.4.12. A compendium and a short documentary video for the grant programme, which consists of the outputs, results, achievements, and lessons learnt of the grant programme. | Compendium and a short documentary video | March 2025 | Preparation of the compendium and a short video will start in December 2024. However, since the end date of the CCAGP date is after the end of the project, it will not be possible to prepare a comprehensive compendium. The TAT and relevant experts will work on this activity until the end of the project. During the 1st consultative meeting, interview videos were recorded with grant beneficiaries. These videos will be used as an input for a short video for this activity. This activity will be completed according to the developments in grant projects. |
| Activity 3.4.13. Support in communication activities of grant beneficiaries. | An online workshop | March 2025 | The support to the grant projects for their communication activities is ongoing and will continue until the end of the project. An online workshop is planned to be organized in September 2024 to inform Grant projects about communication activities, visibility guidelines and social media management. |
| Activity 3.4.14. Carry out portfolio level outreach and communication activities of the grants programme. | Outreach and communication activities | March 2025 | A Grant Brochure is prepared and shared the Directorate of Climate Change’s website and UNDP Türkiye’s social media accounts. The English version of the brochure is being prepared. Relevant outreach and communication activities will continue during the project. |

## Project Management and Coordination Activities

### Building Up Management Structure and Exercising Its Functions

UNDP as the Organization is responsible for the efficient and effective implementation of the project through the Contribution Agreement concluded with the MoEUCC – DGEUFR Department of European Union Investments (DoEUI) acting as the Contracting Authority on behalf of the EU. MoEUCC- DGEM is the End Recipient of the Project. There is not any deviation in the implementation arrangements of the project that is described in the Description of Action (DoA).

As indicated in the DoA, the Project has a two-layered structure for the project coordination, namely; PSC overseeing the overall implementation of the Project and provides strategic guidance, and OCU. The frequency of PSC meetings is  bi-annual, whilst OCU Meetings are conducted on a monthly basis.

### Complying Obligations Regarding Information and Reporting

For the period between 9 October 2021 - 6 April 2022 and 7 April 2022 – 6 October 2022, all aspects of the implementation of the Action were reported through the Fifth and Sixth Activity Reports to the Contracting Authority, End Beneficiary, and EUD.

The draft of the 5th Activity Report was submitted for the review of the Contracting Authority (CA), End Beneficiary (ER) and EUD on 25 March 2022. The reviews from the CA were received on 31 March 2022. The revised document was submitted on 18 May 2022, and approved by the CA on 24 May 2022. The Turkish translation of the document was submitted on 23 September 2022. The translation of the report was approved by both the CA and ER on 4 October 2022.

The draft 6th Activity Report was submitted for the review of the Contracting Authority, End Beneficiary and EUD on 26 September 2022. Necessary revisions were made, and the revised document was submitted on 1 November 2022. The revised document was approved by the ER on 17 February 2023. The Turkish translation of the document was submitted on 28 March 2023.

Two notifications (Notification No: 8 and Notification No: 9) regarding the update of workplan were given during this reporting period with the 5th and 6th Activity Reports.

The 7th Activity Report was submitted for the review of the Contracting Authority, End Beneficiary and EUD on 29.03.2023 and the revised document was approved by 12.07.2023.

The draft 8th ,9th and 10th Combined Activity Report was submitted for the review of the End Beneficiary on 15 August 2024. On 20 September DCC provided comments UNDP will revise accordingly.

### Running Control and Evaluation Mechanisms

Monitoring and evaluation (M&E) exercises will be undertaken in compliance with the provisions of the Financial and Administrative Framework Agreement (Article I. Focus on results) and the General Conditions (Article 10. Monitoring and Evaluation of the Action). The expected results, activities, objectively verifiable indicators, sources of verification, and assumptions listed in the Logical Framework constitute the basis of the Project's M&E system. It was further refined during the Inception Phase. The Organization continuously tracks the progress of the project based on the agreed indicators and all reporting will be carried out accordingly. Indicators are based on objectives that are specific, measurable, attainable, realistic, and time-based. Indicators for the contribution-specific agreement are linked to the more general indicators relevant for the whole Action, wherever possible.

EUD representatives shall be invited to participate in the main monitoring and evaluation missions. The results of M&E exercises shall be reported to the MOEUCC and the EUD. Moreover, as far as possible and appropriate, UNDP and the EUD will explore carrying out the M&E activities jointly.

The Project will be evaluated (technical evaluation) independently.

The assessment will be on the substance and immediate concrete results of the Project, and will, by no means, include any form of expenditure verification (or Audit), etc. As a result of the assessment, the impacts of the results achieved, lessons learned and good practices in terms of substance will be assessed in a report. Besides, the level of communication and visibility, as well as recommendations for sustainability, will also be explored in the said assessment.

#### M&E Plan of the Project:

| Name of Report | Time of submission | Recipients |
| --- | --- | --- |
| Inception Report (Turkish & English) | Within 4 months of commencement of the Project. | MOEUCC & EUD |
| Activity Report (Turkish and English) | Two weeks before each Steering Committee Meeting, to summarize all completed activities within the period covered for the Steering Committee supported with annexes and the planned activities for the next coming period, if applicable. | MOEUCC & EUD |
| Progress Report (Narrative and Financial) (Turkish & English) | Within 60 days after the period covered by such report. (as per Article 3.9 of the General Conditions) | MOEUCC & EUD |
| Final Report (Narrative and Financial) (Turkish & English) | Not later than 6 months after the end of the implementation period of the Project (as per Article 3.9 of the General Conditions) | MOEUCC & EUD |

The project results as outlined in the project results framework are monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. While these UNDP requirements are not outlined in this project document, the UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. To follow closely on the projects, its results and achievements, UNDP regularly carries out internal M&E activities through an ‘Evidence Based Progress Report’, and a ‘Results and Targets Table’ updated regularly during the year.

#### Project Audit

The latest audit was conducted through document review and an online meeting by Mr. Vadim Kuzyk from ROM in Türkiye Phase III Monitoring of IPA Projects on 13 August 2021, and the audit result was conveyed through 4th AR and 2nd PR. Project progress has been scored as good/very good -in terms of relevance, efficiency, effectiveness and sustainability- in the ROM mission report received on 20 September 2021.

In line with the Financial and Administrative Framework Agreement (FAFA) and the General Conditions, the financial transactions and financial statements shall be subject to the internal and external auditing procedures laid down in the Financial Regulations, Rules and directives of UNDP. The project audit will be carried out in line with UNDP’s policies.

## Methodology

There is no significant change in the methodology, as per the DoA.

## Logical Framework

An updated copy of the logical framework was submitted with the Second Progress Report. There have not been any changes to the latest logical framework during the reporting period.

### Current Anticipated Problems, Planned Remedial Actions and Lessons Learned from Encountered Problems

Because of the earthquakes, the Project’s timelines and agendas regarding the media launches and other interconnected activities have also been impacted. Key personnel from the MoEUCC have been temporarily reassigned to disaster relief efforts, which has led to lessened focus on the implementation of project activities. Furthermore, the affected regions may now require additional environmental assessments and remediation efforts, which may further affect the Project’s timeline.

To address these challenges, the project team adjusted project timelines to account for the reallocation of key staff members and the potential need for additional environmental assessments in the affected areas. Since the emergence of the COVID-19 pandemic, the established contingency plans also have been ensuring the Project remains on track, despite unforeseen circumstances and potential future disruptions.

Lessons learned from the encountered problems include:

- The importance of having a robust risk management plan in place to address unforeseen events, such as natural disasters, and their potential impact on the Project’s timelines and objectives.

- The need to maintain open and transparent communication with all Project stakeholders to ensure they are informed of any changes in the Project's progress and any necessary adjustments to the Project’s goals or timelines.

- The value of establishing strong partnerships with stakeholders to ensure the implementation of the Project is not affected dramatically particularly in times of crisis.

Moving forward, the project team will continue to monitor the situation and adapt its plans and strategies as necessary to ensure the successful implementation of the project's objectives.

Additionally, as conveyed in previous reports, considering the extended application deadline, delay occurred during the evaluation process and duration of the grant projects as 12-18 months, the implementation period of grant projects will be beyond the completion date of Enhancing Adaptation Action in Turkey Project and there will be a necessity for the extension of Project’s implementation period. Accordingly, a request for 24-months of extension of the project duration was submitted on 19 July 2023.  Until the new addendum was approved, the project was suspended.  A new addendum was submitted for 18 months of extension and approved February 2024.

### On 9 May 2024, an early warning letter was received from the Contracting Authority about delay of project activities. A comprehensive response including detailed project current updates and updated work plan was submitted to CA on 27 May 2024. The Project learned that the scheduling of grant components must take into realistic timeframes for tender processes. In this sense, during the meetings and e-mail communication; UNDP is suggesting to merge several activities which have the same target audience and province in order to save time and ensure tight planning. However, since the effectiveness and benefit of the activities is also significant  for the Beneficiary, the final decision regarding the activity merge will be up to their final decision and preference.

There is a risk of unsatisfactory performance of already contracted consultants that may occur during the delivery of activities.  This situation may result in incomplete activities in fully manner.

### Project Indicators

The progress towards achieving targets of the project is given in the table below.

|  | Intervention logic | Objectively verifiable indicators of achievement | Baseline (2019) | Milestone (2021 | Target (End of Project) | Progress until 08.10.2024 | Sources and means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Objectives | Build societal resilience by strengthening climate change adaptation, particularly at sector and urban level, with strategies, tools and financing | ▪ Increased awareness of climate change impact among ministries and local authorities |  |  |  |  | ▪ European Commission’s Regular Reports ▪ European Environment Agency’s State of Environment Reports ▪ Statistical data on environment and climate change ▪ Progress in the implementation of Sector Operational Programme: Environment and Climate Action ▪ Progress in the implementation of National Action Plan for EU Accession ▪ Progress in the implementation of Multi-Annual Action Programme for Türkiye on Environment and Climate Action ▪ Eight National Communications to the UNFCCC | ▪ Institutional coordination at national and local level to effectively implement key policies and regulations on climate change adaptation is sufficient. ▪ Factors outside the control area of the project have manageable impact on the output-outcome linkage. ▪ Data at national and urban level is sufficient enough for detailed analysis. ▪ Robust technical approaches are sufficient in the field of climate change adaptation at national and urban context in Türkiye. ▪ Stakeholder and technical expertise engagement are adequate. ▪ The Project has no negative impacts to critical habitats or environmentally sensitive areas. ▪ Climate change does not affect Türkiye’s ecosystems and socio-economic systems in a manner that overwhelms the project efforts. |
|  |  | ▪ Reduction of direct disaster economic loss in relation to global GDP, damage to critical infrastructure and number of disruptions to basic services, attributed to disasters |  |  |  |  |  |  |
|  |  | ▪ Increase in resilience among key sectors and selected cities |  |  |  |  |  |  |
|  |  | ▪ Improved cooperation between national and local stakeholders on climate change adaptation |  |  |  |  |  |  |
|  |  | ▪ Increased availability of decision-making tools and planning solutions to enhance society resilience and reduce adverse effects of climatic events |  |  |  |  |  |  |
|  |  | ▪ Communication of the establishment or operationalization of an integrated policy/strategy/plan which increases national ability to adapt to the adverse impacts of climate change, and foster climate resilience and low greenhouse gas emissions development in a manner that does not threaten food production (including a national adaptation plan, nationally determined contribution, national communication, biennial update report or other |  |  |  |  |  |  |
| Specific Objective | Establish an enabling environment for climate change adaption in Turkey by developing the policy, technical and operational baselines, including (i) better decision-making tools for national climate change adaptation policies, (ii) urban adaptation planning solutions (urban adaptation strategies and action plans), (iii) capacity building and networking activities for climate change adaptation with the EU and the international community, and (iv) a climate change adaptation grant programme to implement climate change adaptation action | ▪ Entry of updated National Adaptation Strategy and Action Plan (NASAP) into force | No | No | Yes | On target (85%) | ▪ European Commission’s Regular Reports ▪ Statistical data on environment and climate change ▪ Updated and published NASAP ▪ UASAPs for four pilot metropolitan municipalities ▪ Adaptation action reports under CCAGP ▪ Monitoring Reports ▪ Project Progress Reports ▪ Project Final Reports ▪ Project Evaluation Reports |  |
|  |  | ▪ Entry of Urban Adaptation Strategy and Action Plans (UASAPs) into force | No | No | Yes | On target (85%) |  |  |
|  |  | ▪ Number of officials at national and local level with improved climate change adaptation knowledge and technical skills | 0 | 20 | 2120 | 340 |  |  |
|  |  | ▪ Number of national and local tools (e.g. software, guidelines) developed to facilitate climate change adaptation | 0 | 1 | 8 | 4 |  |  |
|  |  | ▪ Number of entities benefiting from grant programme | 0 | 0 | 75 | 29 |  |  |
| Expected Results | Result 1. Develop better decision-making tools for climate resilient sustainable development | ▪ Number of sectors with planning and investment decisions take climate change adaptation into consideration | 0 | 0 | 11 | 11 | ▪ Review report of existing studies ▪ Expert report on climate change threats, opportunities, risks and uncertainties ▪ Expert report on climate vulnerabilities for five priority sectors ▪ Expert report on climate financing ▪ Updated NASAP ▪ Monitoring and Evaluation system for the updated NASAP | ▪Institutional coordination at national and local level to effectively implement key policies and regulations on climate change adaptation is sufficient ▪Factors outside the control area of the project have manageable impact on the output-outcome linkage. ▪Data at national and urban level is sufficient enough for detailed analysis; ▪Robust technical approaches are sufficient in the field of climate change adaptation at national and urban context in Türkiye ▪Stakeholder and technical expertise engagement are adequate ▪The project has no negative impacts to critical habitats or environmentally sensitive areas. ▪Climate change does not affect Türkiye’s ecosystems and socio-economic systems in a manner that overwhelms the project efforts. |
|  |  | ▪ A strategy document (Updated NASAP) developed | No | No | Yes | Yes |  |  |
|  |  | ▪ A finance tool to support implementation developed | No | No | Yes | Yes |  |  |
|  |  | ▪ Number of stakeholder engagement events organized | 0 | 8 | 35 | 35 |  |  |
|  |  | ▪ Number of participants engaging in consultative meetings, workshops…etc. | 0 | 350 | 1000 | 3159 |  |  |
|  |  | ▪ A dissemination campaign for raising public and stakeholder awareness | No | No | Yes | Yes |  |  |
|  |  | ▪ Number of reports (e.g. studies, analyses, assessments) developed | 0 | 2 | 110 | 8 |  |  |
|  |  | ▪ A monitoring and evaluation (M&E) system developed | No | No | Yes | 0 |  |  |
|  |  | ▪ Number of trainings delivered (e.g. M&E, adaptation planning guidelines) | 0 | 0 | 9 | 0 |  |  |
|  |  | ▪ Number of officials/stakeholders trained | 0 | 0 | 300 | 0 |  |  |
|  |  | ▪ Number of training modules produced | 0 | 0 | 2 | 1 |  |  |
|  | Result 2. Develop adaptation and resilience planning in urban areas | ▪ Number of strategies developed | 0 | 0 | 4 | 4 | ▪ Review report of existing studies ▪ Expert report on climate change threats, opportunities, risks and uncertainties ▪ Adaptation planning guidelines for five priority sectors ▪ Adaptation planning guidelines for cities ▪ Urban typology framework for Turkish cities ▪ Expert report on urban vulnerabilities for priority sectors in four selected pilot cities ▪ Expert report on climate financing at city level ▪ Financing strategy for UASAP implementation |  |
|  |  | ▪ A finance tool to support implementation developed | No | No | Yes | 0 |  |  |
|  |  | ▪ Number of stakeholder engagement events organized | 0 | 10 | 15 | 22 |  |  |
|  |  | ▪ Number of participants engaging in consultative meetings, workshops…etc. | 0 | 440 | 840 | 3417 |  |  |
|  |  | ▪ Number of reports (e.g. studies, analyses, assessments) developed | 0 | 2 | 13 | 9 |  |  |
|  |  | ▪ Number of dissemination campaigns for raising public and stakeholder awareness | 0 | 0 | 4 | 0 |  |  |
|  |  | ▪ Number of trainings delivered (e.g. M&E, adaptation planning guidelines) | 0 | 0 | 8 | 0 |  |  |
|  |  | ▪ Number of officials/stakeholders trained | 0 | 0 | 200 | 0 |  |  |
|  |  | ▪ A monitoring and evaluation (M&E) system developed | No | No | Yes | 0 |  |  |
|  |  | ▪ Number of training modules produced | 0 | 0 | 2 | 0 |  |  |
|  | Result 3. Develop capacity for climate change adaptation action Result 4. Improve operational capacity for climate change adaptation action through a climate change adaptation grant programme | ▪ A national platform (National Adaptation Platform) developed | Yes | Yes | Yes | Yes | ▪ Review report of existing studies ▪ Expert report on climate change threats, opportunities, risks and uncertainties ▪ Expert report on policy and stakeholder capacity and need assessment ▪ Capacity building strategy ▪ Study visit materials, evaluation report and participants list ▪ Training materials, evaluation report and participants list ▪ Dissemination materials for public and stakeholder awareness raising ▪ Annual M&E Reports ▪ Web-based grant programme information system |  |
|  |  | A set of guidelines for the grant programme delivered | Yes | Yes | Yes | Yes |  |  |
|  |  | Number of stakeholder engagement events organized | 0 | 39 | 39 | 21 |  |  |
|  |  | Number of reports (e.g. studies, analyses, assessments) developed | 0 | 7 | 7 | 4 |  |  |
|  |  | Number of trainings delivered | 0 | 22 | 22 | 2 |  |  |
|  |  | Number of training modules produced | 0 | 12 | 12 | 2 |  |  |
|  |  | Number of officials/stakeholders trained | 0 | 640 | 640 | 120 |  |  |
|  |  | Number of officials/stakeholders participating in the study visits | 0 | 100 | 100 | 35 |  |  |
|  |  | Number of study visits | 0 | 7 | 7 | 6 |  |  |
|  |  | Number of dissemination materials produced for raising public and stakeholder awareness | 0 | 13 | 13 | 3 |  |  |
|  |  | Number of participants engaging in consultative meetings, workshops etc. | 0 | 1948 | 1948 | 2453 |  |  |
|  |  | Number of tools developed under grant programme | 0 | 2 | 2 | 1 |  |  |
|  |  | Number of monitoring visits | 0 | 3 (2 monitoring visits 1 spot check as per project budget) | 3 (2 monitoring visits 1 spot check as project budget) | 54 |  |  |

## Work Plan

The latest Workplan was considered as conveyed through 8-9-10th Activity Report. Please refer to Annex 05 for the Work Plan.

## Budget

#### The latest Budget of the Action, which can be found in Annex 6, was considered as conveyed through 4rd PR, which serves as the budget forecast for the next reporting period (G.C. Article 3.7.i).  No additional changes were made to the Project’s Budget since Notification No: 12.

## Minor modifications

There has been a change in the default UNDP EUR bank account of the UNDP Brussels Office used for the contribution agreements with the European Union. Therefore, the renewed Financial Identification Form will also be notified under Notification 13. Please refer to Annex 15. The revised information in the Financial Identification Form will be read as follows:

## List of Contracts

The list of the current contracts have been submitted in the previous sections.

# PARTNERS AND COOPERATION

## Relation with the End Recipient

## UNDP’s relationship with the End Beneficiary, namely the Ministry of Environment, Urbanisation and Climate Change, Directorate of Climate Change had been fruitful until October 2023 where suspension had been received to the project. Following the rejection of Addendum No 1, project implementation has been frozen. Later on, following the approval of re-submission of the Addendum received in February 2024, the project implementation has been re-initiated. Project management unit has been established to better track the remaining activities. Since then, relations with the End Beneficiary have been re-established. No problem has been experienced in establishing smooth communication, sharing of information, and good practices since the project team was established.

# LINK WITH SUSTAINABLE DEVELOPMENT GOALS AND GENDER EQUALITY

Adopted by all United Nations Member States in 2015, the 2030 Agenda for Sustainable Development provides a shared blueprint for peace and prosperity for people and the planet. The 17 Sustainable Development Goals (SDGs) are at the center of the 2030 Agenda, which is an urgent call for action by all countries – developed and developing – in a global partnership. SDGs recognize that ending poverty and other deprivations must go hand-in-hand with strategies that improve health and education, reduce inequality, and spur economic growth – all while tackling climate change and working to preserve our oceans and forests. Strategies for sustainable development and climate change adaptation have many common elements. Thus, they are vital to insert to adaption actions and strategies.

Within this framework, project actively promotes localizing SDGs by central and local authorities and the public at large through the following interventions:

- Involvement of specific sessions on SDGs in the capacity development programs addressing the municipalities, MOEUCC and other ministries, Union of Municipalities of Türkiye and other associations, as well as social service units such as Women Centers, Child Development Centers at the local level,

- Integration of the policies on effective climate change adaptation with reference to specific SDGs,

- Mainstreaming the SDGs in basic standards and principles of service delivery and performance management tools to be developed under the Project.

Project makes direct contribution to SDG 11: Sustainable Cities and Communities and SDG 13: Climate Action in line with the below mentioned targets and indicators.

SDG-11: Sustainable Cities and Communities

| SDG Target 11.5 | By 2030, significantly reduce the number of deaths and the number of people affected and substantially decrease the direct economic losses relative to global gross domestic product caused by disasters, including water-related disasters, with a focus on protecting the poor and people in vulnerable situations |
| --- | --- |
| Indicators | 11.5.2 Direct disaster economic loss in relation to global GDP, damage to critical infrastructure and number of disruptions to basic services, attributed to disasters [Tier I] |
| SDG Target 11.b | By 2020, substantially increase the number of cities and human settlements adopting and implementing integrated policies and plans towards inclusion, resource efficiency, mitigation and adaptation to climate change, resilience to disasters, and develop and implement, in line with the Sendai Framework for Disaster Risk Reduction 2015-2030, holistic disaster risk management at all levels. |
| Indicators | 11.b.2 Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategies [Tier II] Note: this can be implemented but with a selective scope, covering only climatic hazards. |

SDG-13: Climate Action

| SDG Target 13.1 | Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries |
| --- | --- |
| Indicators | 13.1.2 Number of countries with national and local disaster risk reduction strategies 13.1.3 Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategies |
| SDG Target 13.2 | Integrate climate change measures into national policies, strategies and planning |
| Indicators | 13.2.1 Number of countries that have communicated the establishment or operationalization of an integrated policy/strategy/plan which increases their ability to adapt to the adverse impacts of climate change, and foster climate resilience and low greenhouse gas emissions development in a manner that does not threaten food production (including a national adaptation plan, nationally determined contribution, national communication, biennial update report or other) |
| SDG Target 13.3 | Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning |
| Indicators | 13.3.2 Number of countries that have communicated the strengthening of institutional, systemic and individual capacity-building to implement adaptation, mitigation and technology transfer, and development actions |

Project also makes indirect contribution to several SDGs such as SDG-5: Gender equality, SDG-6: Clean water and sanitation (specifically on water use efficiency), SDG-7: Affordable and clean energy, SDG-9: Industry, innovation and infrastructure, SDG-10: Reduced Inequalities, SDG-12: Responsible consumption and production, SDG-15: Sustainably manage forests, combat desertification, halt and reverse land degradation, halt biodiversity loss, and SDG-17: Partnerships for goals.

SDG-5: Gender Equality

UNDP’s development mandate is centered on gender equality and women’s empowerment.  Attaining human development requires multifaceted approaches that will encompass not only economic prosperity but also improve people’s well-being by ensuring an equitable, sustainable and stable planet and which aims to greater wellbeing for all. As a globally recognized norm for UNDP, gender equality and women’s empowerment integral to every aspect of its work to support countries to eradicate poverty and reduce inequalities and exclusion.

Although it has greater adverse effects on the section whose life relies on natural resources and who is unable to respond to natural disasters, women are facing higher risks and greater burdens from the impacts of climate change in situations of poverty. The inequality is often accelerated by the unequal participation of women in decision-making processes and labor markets, and results in the exclusion of women from climate-related policy-making practices.

Women’s involvement in the response to climate change is crucial due to their local knowledge and capacity in leadership at sustainable practices and brings about a higher level of readiness for the impacts of climate change. Hence, gender equality is one of the core values with which climate change adaptation policies and projects should be incorporated. In terms of project results, the project targets that all results are inclusive and gender responsive through:

- Integration of GESI (Gender Equality and Social Inclusion) to policy framework (systematic uttering and inclusion of the perspective)

- Identification of the relevant entry points in local and sectoral fields and dissemination of such knowledge via reports, workshops, and NAP

- Generation of the tools and procedures of inclusiveness and gender mainstreaming in climate adaptation action and exemplification of their use

At the work-plan level, gender equality and social inclusion dimension is mainstreamed via GESI expertise, gender-disaggregated data, women participation, reference to GESI best practices, GESI sessions in the meetings, GESI-focused participatory assessments, trainings or GESI modules in the trainings and GESI chapters in the reports.

## Project Contribution to SDGs

SDG 11 - Cities have a significant role in the planning process, by formulating and implementing adaptation actions that use limited resources to produce maximum common benefits, while avoiding the adverse consequences of climate change. This project specifically aims to develop adaptation and resilience planning in urban areas through urban adaptation planning on broad scale, involving disaster risk reduction, sustainable development, and poverty reduction, while also integrating existing planning processes and objectives with adaptation actions.

Through Component 2, activities were organized to discuss the impacts of climate change and highly vulnerable sectors and areas, and assess vulnerabilities, risk, data needs and availability, adaptation capacity, and the needs of each selected pilot city. Outcomes will be employed to develop urban strategy and adaptation action plans for climate change at the local level.

SDG 13 - Climate action includes mitigating climate change and adapting to the impact of climate change by building resilience to phenomena such as flooding, droughts and other extreme weather events, while including foci on strengthening resilience and integrating climate change measures into national policies and planning.

The project promotes Climate Action across all project components. In the reporting period, consultative meetings were organized to develop vulnerability and risk analysis methodology within the framework of climate hazards, exposure, sensitivity, adaptation capacity factors to be integrated into national adaptation policies.

SDG 5 - The project implementation process follows the umbrella scope of the UNDP’s approach towards gender equality and social inclusion. Therefore, the gender equality aspect of UNDP is extended in all project activities, including but limited to the composition of TAT and UNDP Direct Project Costed Staff, selection of short-term experts, women’s participation in meetings/trainings/events to be organized under each component.

The GESI aspect of the project was also reflected in Social Development section of the currently drafted reports as part of the sectoral vulnerability and risk assessments conducted for local climate change adaptation strategy and action plans for pilot cities and the national adaptation strategy and action plan to be updated.

The project also follows UNDP’s Gender Mainstreaming Tools for Programme Management. In line with the UNDP Türkiye Gender Screening Tool for Project Development and Implementation, the gender screening of the project including the gender analysis during the project stages was previously prepared and presented as Annex to the 2nd PR. No changes have been made to the document since the time of the submission.

# VISIBILITY

All necessary measures are taken to ensure the visibility of the European Union and the Republic of Türkiye. All visibility actions are carried out following the General Conditions (ANNEX- II - General Conditions to the Contribution Agreements, Article 8). The actions on the visibility of the Project follows the Joint Action Plan on Visibility of EU-UN external action programs (2006) and the ''Visibility Guidelines for EC-UN Actions in the Field (2014)''.

A social media presence and active interaction with the follower’s networks is an important channel to disseminate information about the project goals, activities and events. Using social networks allows the project to reach a larger group of people nearly instantly while supporting awareness about the Project among its followers.  Twitter and Instagram accounts offer the most dynamic way of communicating project news and cross-posting relevant news items.

Twitter: https://twitter.com/iklimeuyum

Instagram: https://www.instagram.com/iklimeuyum/?hl=tr

Twitter and Instagram accounts are used to publish project news and coverage of events in which the project is involved. Total number of Instagram followers 553. During the reporting period, the number of likes for these posts is 90.  The total number of Twitter followers is 839. During the reporting period, 28 tweets were sent from the Twitter account. Total tweet impression is 19,3K.

The project website https://iklimeuyum.org  is one of the main channels for dissemination of project information. The main purpose of the website is to be the public image of the project as well as the main online access point for the different target groups.  It serves as a place to provide access to announcements, surveys, news, and newsletters.

The project website statistics have been analyzed since 26 November 2020 via Google Analyst, and data is collected on a regular basis. During the period (7 September 2023 - 4 September 2024) the project website was visited 2.933 times by 1.335 unique users.

| Month | User | Page view |
| --- | --- | --- |
| 7 April 2023- 7 May 2023 | 392 | 351 |
| 7 May 2023- 7 June 2023 | 824 | 771 |
| 7 June 2023- 7 July 2023 | 1,1K | 1K |
| 7 July 2023- 7 August 2023 | 487 | 413 |
| 7 August 2023- 7 September 2023 | 374 | 330 |
| 7 September 2023 – 7 October 2024 | 1.335 | 2.933 |

Visibility rules were applied at the meetings. Flag, swallow flags, roll up and spider stands were used in the meeting hall. Visibility materials were distributed at the meeting. The distributed set includes a notebook, pen, file, brochure, and bag.

Communication activities and visibility materials related to the project are submitted in Annex 08.

ANNEXES