| ENHANCING ADAPTATION ACTION IN TURKEY TR2017 ESOP MI A3 04 |  |
| --- | --- |
| FINAL REPORT Reporting Period: 09.10.2019-08.10.2025 |

This project is funded by the European Union and Republic of Türkiye and implemented by the United Nations Development Programme. The beneficiary of the project is the Ministry of Environment, Urbanization and Climate Change. General Directorate of European Union and Foreign Relations is the Contracting Authority of this Project.

08 April 2026

United Nations Development Programme

This publication has been produced with the assistance of the European Union and the Republic of Türkiye. The contents of this publication are the sole responsibility of UNDP and can in no way be taken to reflect the views of the European Union and the Republic of Türkiye.

TABLE OF CONTENTS

TABLE OF CONTENTS	iii

LIST OF ANNEXES	v

ABBREVIATIONS	vi

1.	DESCRIPTION	1

2.	ASSESSMENT OF IMPLEMENTATION OF ACTIVITIES OF THE ACTION	2

2.1.	Executive Summary	2

2.2.	Progress in Activities and Achievement of Results	3

2.2.1.	Recruitment of Technical Assistance Team (TAT), KEs and STEs	3

2.2.2.	Meetings and Events	3

2.2.3.	Monitoring and Reporting	5

2.2.4.	Project Components	6

2.2.5.	Grant Management	24

2.3.	Risks and Risk Mitigation	27

2.3.1.	Effects of COVID-19	28

2.3.2.	Plans for the next coming period	29

2.4.	Project Management and Coordination Activities	40

2.4.1.	Building Up Management Structure and Exercising Its Functions	40

2.4.2.	Complying Obligations Regarding Information and Reporting	40

2.4.3.	Running Control and Evaluation Mechanisms	40

2.5.	Methodology	41

2.6.	Logical Framework	41

2.6.1.	Current Anticipated Problems, Planned Remedial Actions and Lessons Learned from Encountered Problems	41

2.6.2.	Project Indicators	43

2.7.	Work Plan	52

2.8.	Budget	55

2.9.	List of Contracts	55

3.	PARTNERS AND COOPERATION	56

3.1.	Relation with the End Recipient	56

4.	LINK WITH SUSTAINABLE DEVELOPMENT GOALS AND GENDER EQUALITY	57

4.1.	Project Contribution to SDGs	59

5.	VISIBILITY	61

ANNEXES	62

LIST OF ANNEXES

| Annex No | Heading |
| --- | --- |
|  | Project Reports and Meetings |
|  | Terms of references of the Contractors (ICs, RLAs, NPSAs) |
|  | Visibility and Communication |
|  | Updated Workplan |
|  | Addendum No. 2 |
|  | NASAP M&E System Guideline |
|  | E-books |
|  | Activity 3.2.3 Reports |
|  | Activity 3.2.6 Awareness Conferences |
|  | Technical report |
| 11. | General Conditions to the Contribution Agreements |
| 12. | Sectoral Training |
| 13. | Activity Report 11 |
| 14. | A.1.7.4 Training Module on the Use of the Implementation Guidelines |
| 15. | Deliverable 3-Deliverable-3_ Participation and technical contribution training sessions on the adaptation plan implementation guidelines |
| 16. | A.2.3.3 Consultative Meetings for M&E System |
| 17. | CCAGP Consultative Meeting |
| 18 | Activity 3.2.5. Consultative Meeting & Activity 1.5.3 E-IDUSEP M&E |
| 19 | Financial Table until 08.10.2025 |
| 20 | Notification 14 |

ABBREVIATIONS

| AR5 | IPCC 5th Assessment Report |
| --- | --- |
| CA | Contracting Authority |
| CCAGP | The Climate Change Adaptation Grant Programme |
| DGEUFR | The Directorate General of European Union and Foreign Relations |
| DoA | Description of Action |
| DoEUI | The Department of European Union Investments |
| ER | End Recipient |
| ESOP | Environmental Sectoral Operational Programme |
| EU | European Union |
| EUD | Delegation of the European Union to Türkiye |
| FAQ | Frequently Asked Questions |
| GESI | Gender Equality and Social Inclusion |
| IC | Individual contract |
| KE | Key Expert |
| M&E | Monitoring and Evaluation |
| MFA | Ministry of Foreign Affairs |
| MIS | Management Information System |
| MoEUCC | The Ministry of Environment, Urbanization and Climate Change |
| NASAP | National Adaptation Strategy and Action Plan |
| NGO | Non-Governmental Organizations |
| NPSA | National Personnel Services Agreement |
| OCU | Operation Coordination Unit |
| PSC | Project Steering Committee |
| RLA | Reimbursable Loan Agreement |
| SBO | Strategy and Budget Office of the Presidency of the Republic of Türkiye |
| SDGs | Sustainable Development Goals |
| SMART | Specific Measurable Achievable Realistic Time-bound |
| STE | Short-Term Expert |
| TAT | Technical Assistance Team |
| UASAPs | Urban Adaptation Strategy and Action Plans |
| UNDP | United Nations Development Programme |

# DESCRIPTION

| Action Title: | Enhancing Adaptation Action in Türkiye |
| --- | --- |
| Contribution Agreement Number: | TR2017 ESOP MI A3 04 |
| Total eligible cost: | 4.225.000 EUR |
| Starting Date: | 09.10.2019 |
| End Date: | 08.10.2025 |
| Duration: | 72 months |
| Contracting Authority: | Ministry of Environment, Urbanization and Climate Change, Department of European Union Investments |
| Project Manager: | Dr. İsmail Raci BAYER |
| Address: | Mustafa Kemal Mah. Eskişehir Devlet Yolu 9.km No: 278, Ankara, Türkiye |
| Telephone: | + 90 312 474 03 50-51 |
| Fax: | + 90 312 474 03 52-53 |
| Contract Expert: | Ceren UNCU AĞAÇDİKEN |
| e-mail: | ceren.uncuagacdiken@csb.gov.tr |
| Beneficiary: Address: Fax: SROB: Telephone: e-mail: OCU Coordinator: Telephone: e-mail: | Ministry of Environment, Urbanisation and Climate Change, Directorate of Climate Change - Çamlıca Mahallesi Anadolu Bulvarı No: 64/2, 06630 Yenimahalle/Ankara, Türkiye +90 312 591 44 00 - Orhan SOLAK, Deputy Head of Directorate of Climate Change +90 312 591 44 00 orhan.solak@csb.gov.tr |
| Organization: | United Nations Development Programme (UNDP) Türkiye Country Office Meral MUNGAN ARDA– Climate Change and Environment Portfolio Manager Oran Mah., Mustafa Fehmi Gerçeker Sokak No:12 06450 Çankaya, Ankara/Türkiye +90 312 454 1100 Meral.mungan@undp.org Oran Mah., Mustafa Fehmi Gerçeker Sokak No:12 06450 Çankaya, Ankara/Türkiye Gizem BAL +90 312 454 11 00 gizem.bal@undp.org |
| [Project Director]: |  |
| Address: |  |
| Telephone: |  |
| e-mail: |  |
| Project office address: |  |
| Project Manager: |  |
| Telephone: |  |
| e-mail: |  |

# ASSESSMENT OF IMPLEMENTATION OF ACTIVITIES OF THE ACTION

## Executive Summary

The Project commenced on 9 October 2019, following the signature of the Grant Contract TR2017 ESOP MI A3 04. This final report covers the period between 09.10.2025-08.10.2025. The report mainly outlines the progress in project activities currently being implemented. While the details of each action taken for the project implementation are given under section 2 – Assessment of Implementation of Activities of the Action of this report, the brief overview is hereunder:

- The details of the contractual changes in KE & STEs in line with UNDP’s newly introduced contractual modalities.

- Information on the meetings and events consisting of the consultative meetings, series of Operation Coordination Unit (OCU) Meetings and the Project Steering Committee Meetings to be organized within the Activity Report period are shared.

- The detailed process regarding the administrative reports submitted within the reporting period was given.

- Since the establishment of the new project team as of July 2024, weekly meetings with DCC have been initiated and conducted until January 2025. As per negotiations, weekly meetings was held every other week at DCC premises with the in-person participation of TAT. Additionally, TAT was mostly present at DCC premises 2 days a week when there was no mission abroad. Due to the intensity of project travels outside Ankara province, weekly meetings no longer conducted.

- Updates on the implementation of the activities within the reporting period are presented in the context of the expected outcomes and deliverables and expected times of completion.

- Risk assessment, mitigation measures and adaptive management practices are presented along with the details regarding the activities in the next reporting period.

- The details regarding project implementation elements such as methodology, logical framework, and work plan are presented.

- The updates on the activities contributing to the Sustainable Development Goals (SDGs) are presented.

- Detailed updates on the communication and visibility activities are presented.

## Progress in Activities and Achievement of Results

### Recruitment of Technical Assistance Team (TAT), KEs and STEs

Updates with regards to the recruitment of Technical Assistance Team

After the addendum request has been rejected, the project team’s contracts were terminated in October 2023.  The addendum request was approved in February 2024, and the new Technical Assistance Team mobilized in line with the UNDP rules and procedures. New TAT members information is indicated below:

- Gizem Bal was assigned on 1 July 2024 as Project Manager for “Enhancing Adaptation Action in Turkey” Project.

- Ayşe İlke Gürbüzer Akgün was assigned on 1 August 2024 as Project Associate for “Enhancing Adaptation Action in Turkey” Project and resigned as of 04 July 2025.

- Simay Erdi was assigned on 20 May 2024 as Project (Grant) Associate for “Enhancing Adaptation Action in Turkey” Project and resigned as of September 2024.  Following September 2024, Grant Associate position was not re-filled as per request of project partners.

- Göksu Demircan was assigned on 31 May 2024 as Project Assistant and Interpreter for “Enhancing Adaptation Action in Turkey” Project and supported the project until 08 October 2025.

- Candan Avcı was assigned on 1 November 2024 as Grant Manager for “Enhancing Adaptation Action in Turkey” Project and supported the project until 08 October 2025.

- Sebahat Düzleyen was assigned on 10 June 2025 as Project Implementation Support Analyst to “Enhancing Adaptation Action in Turkey” Project and supported the project until 08 October 2025.

- Hüseyin Akbulut was assigned on 10 July 2025 as Project Associate for “Enhancing Adaptation Action in Turkey” Project and supported the project until 08 October 2025. (Terms of References-Annex 02)

The contracts of the TAT members have been extended to October 8, 2025, following the approval of Addendum No. 2.

Updates with regards to the contractual modalities of consultants

To maintain transparency and effective project management, this section shares updates on recent changes to consultant contracts, prompted by a new contractual modality introduced by UNDP.

Previously, Individual Contracts (IC) were used to establish framework agreements with consultants for intermittent and repetitive services. Under this system, contracts specified a daily fee for services, and financial obligations were only created when services were requested through a signed 'service request' document. However, as of 31 March 2022, UNDP introduced the Personnel Services Agreement (PSA) to replace framework-based IC contracts for both international and local consultants. The only exception to this transition involved lump-sum deliverable-based arrangements.

The key difference between the previous framework-based IC contracts and the new lump-sum deliverable-based contracts was the financial proposal requirement. Consultants now provide a lump-sum fee for each deliverable, based on the estimated number of days needed to complete each task outlined in terms of reference (ToR). This new approach linked payments to specific, measurable deliverables, allowing the project team to make more detailed budget calculations and forecasts.

In response to UNDP's updated policies, the Project Team transitioned consultant contracts from framework-based ICs to lump-sum deliverable-based arrangements. This change did not affect overall financials, as the detailed ToRs allowed consultants to offer prices in line with their previous daily fees.

After the approval of Addendum No:2, amendments were prepared to extend the contracts until October 2025 according to their Terms of Reference. Please refer to Annex 02 for the respective ToRs. The information about amendments is indicated below.

- Ceren Ballı Gözen, Key Expert-1 - Consultancy on Climate Impacts and Modelling, until 08.10.2025Ela Babalık, Consultancy Services on Sectoral Adaptation to Climate Change until 08.10.2025

- Doğan Dursun, Key Expert-3 - Consultancy on Urban Adaptation to Climate Change, until 08.10.2025

- Yahya Akdağ, Key Expert-4- Software Development and Database Management Expert, until 08.10.2025

- Özgür Pehlivan, Key Expert-5- Consultancy on Climate Finance, until 08.10.2025

- Adnan Deniz Özdemir Consultant on Monitoring and Evaluation and Water Resources in the Context of CCA until 08.10.2025

- Ayşe Özge Kepenek Bozkırlıoğlu, Consultant on CCA and Industry Sector until 08.10.2025

- Doğanay Tolunay, Consultant on Climate Change Adaptation and Ecosystem Services, until 08.10.2025

- Emre Ege Smekal, Consultant on Climate Change Adaptation and Management Information System, 26.03.2024

- Emine Didem Evci Kiraz, CCA and Health Sector, until 08.10.2025

- İlkay Dellal, Consultant on Climate Change Adaptation and Agriculture Sector, until 08.10.2025

- Levent Aydın, Consultancy on Climate Change Adaptation and Energy Sector, until 08.10.2025

- Süleyman Toy, Consultancy on Climate Change Adaptation and Tourism Sector, until 08.10.2025

- Haydar Uğur Dağ, Grant Programme Expert, 01.03.2024. Mr. Dağ’s contract was extended until 08-10-2025. The expert resigned in June 2025.

- Barış Uysal, Grant Programme Expert, 30.09.2021. Mr. Uysal’s contract was extended until 29.09.2025

- Mikdat Kadıoğlu, Disaster Risk Management and Resilience Expert, until 08.10.2025

- Zeynep Eren, Social Development Expert, 09.09.2024. Ms. Eren’s contract was terminated on 13.02.2025.

- Ayşe İlke Gürbüzer Akgün resigned from her position on 4 July 2025.

- Rest of the Technical Assistance Team supported the project until 08 October2025.

- Sebahat Düzleyen has supported the project until 08 July 2025.

- The translator served as junior consultant, Ahmet Şerif Saman supported to the project until 08.10.2025.

### Meetings and Events

Several administrative and consultative meetings were held within the eleventh Activity Report period. The presentations, minutes, and participant list of the meetings are attached in Annex 01.

#### Project Steering Committee (PSC) Meeting

The Eighth PSC Meeting was held on 07 October 2024. The representatives from the Ministry of Environment, Urbanization and Climate Change General Directorate of European Union and Foreign Relations Department of European Union Investments, the Ministry of Environment, Urbanization and Climate Change Directorate of Climate Change (MoEUCC), The Presidency of Strategy and Budget Office (SBO),  Presidency of Turkey, Presidency of Strategy and Budget, the Delegation of EU to Türkiye (EUD) and UNDP Türkiye were participated in the meeting. Meeting minutes have been shared with the participants and approved.

The Nineth PSC Meeting was held on 2 May 2025. The representatives from the Ministry of Environment, Urbanization and Climate Change Directorate of Climate Change (MoEUCC), Presidency of Türkiye, Presidency of Strategy and Budget, the Delegation of EU to Türkiye (EUD), Ministry of Foreign Affairs Directorate for EU Affairs, Ministry of Foreign Affairs Directorate General for International Economic Affairs and UNDP Türkiye participated in the meeting.

The 10th PSC Meeting was held on 8 October 2025 through online means. Minutes of the meeting is given in Annex 01.

#### Operation Coordination Unit (OCU) Meetings

Three Operation Coordination Unit meetings were held during the reporting period to provide information regarding the progress on the recruitment of short-term experts, reporting and monitoring events and activities, communication and visibility activities and grant management.

#### Weekly Meetings

Throughout the reporting period, weekly meetings were held with UNDP TAT and the DCC to monitor project progress, address challenges, and ensure alignment with project objectives. These meetings facilitated effective communication between team members, allowing for timely updates on ongoing activities and the resolution of any issues encountered. The consistent engagement during these meetings had been instrumental in maintaining project momentum, ensuring that all activities were conducted in accordance with the project timeline, and fostering collaboration among the different teams involved.

Study Visit to the Netherlands

A study visit to the Netherlands was organized between 18-24 August 2024 to increase experience sharing, conduct meetings with different institutions and departments. This visit also aimed at increasing opportunities for data sharing of Türkiye with Netherlands, with the intention to be visible in technical publications of these institutions. Official visits were held in institutions such as Ministry of Infrastructure and Water Management, National Institute for Public Health and the Environment (RIVM), Rotterdam City Hall,  Municipality of Middleburg, Port of Rotterdam, Delta Climate Center (DCC), Royal Haskoning DHV, Global Centre on Adaptation  and etc. for the scope of knowing more about climate adaptation actions as well as some site visit in different plants as mentioned in the program. In total, 5 people (3 men and 2 women) from DCC. 2 UNDP personnel, Climate Change and Environment Portfolio Manager Meral Mungan Arda and Project Manager Gizem Bal, Expert Roelie Mulder, and Expert Roel van de Loo (1 man ,3 women) attended the visit. The study visit report was approved by DCC on 26 February 2025.

Study Visit to Germany

A study visit to (seventh) the Germany was organized between 6-11 July 2025 to increase experience sharing, conduct meetings with different institutions and departments. This visit also aimed at increasing opportunities for data sharing of Türkiye with Germany, with the intention to be visible in technical publications of these institutions. Official visits were held in institutions such as German Environment Agency (UBA), Climate adaptation hub (KOMPASS team), Dessau, Regenwasser Agentur Berlin, German Climate Computing Center (DKRZ), Hamburg, Universität Hamburg, Cluster of Excellence “Climate, Climatic Change, and Society” (CLICCS)* , ICLEI – Local Governments for Sustainability, Bonn, City of Bonn, a global resilience hub and Department of International Affairs and Global Sustainability, UNU EHS, Bonn (UN University), Research Center of Post-Mining and Land Use, THGA Bochum, City of Bochum – Stabsstelle Klima und Nachhaltigkeit, Regionalverband Ruhr (RVR), Essen / Bottrop (Regional planning, environmental stewardship, and climate adaptation in Ruhr metropolitan area), Network on Climate Adaptation & Business.NRW, Düsseldorf (Rebel Group office). In total, 6people (3 men and 3 women) from DCC. 1 UNDP personnel, Project Manager Gizem Bal, one international expert from Germany attended the visit. The study visit report was approved by DCC on October 2025. The list and dates of events and meetings are presented in the the annex.

Table 1. List of Meetings

| Meeting | Date |
| --- | --- |
| #### Kick-off meeting | 8 November 2019 |
| #### PSC Meeting No.1 | 29 May 2020 |
| #### PSC Meeting No.2 | 07 October 2020 |
| #### PSC Meeting No.3 | 14 April 2021 |
| #### PSC Meeting No.4 | 8 October 2021 |
| #### PSC Meeting No.5 | 6 April 2022 |
| #### PSC Meeting No.6 | 6 October 2022 |
| #### PSC Meeting No.7 | 12 April 2023 |
| #### PSC Meeting No.8 | 07 October 2024 |
| PSC Meeting No.9 | 02 May 2025 |
| PSC Meeting No.10 | 08 October 2025 |
| 1st Operation Coordination Unit Meeting | 26 December 2019 |
| 2nd Operation Coordination Unit Meeting | 29 January 2020 |
| 3rd Operation Coordination Unit Meeting | 18 February 2020 |
| 4th Operation Coordination Unit Meeting | 6 May 2020 |
| #### 5th Operation Coordination Unit Meeting | 3 June 2020 |
| 6th Operation Coordination Unit Meeting | 1 July 2020 |
| 7th Operation Coordination Unit Meeting | 29 July 2020 |
| 8th Operation Coordination Unit Meeting | 2 September 2020 |
| 9th Operation Coordination Unit Meeting | 5 November 2020 |
| 10th Operation Coordination Unit Meeting | 2 December 2020 |
| 11th Operation Coordination Unit Meeting | 6 January 2021 |
| 12th Operation Coordination Unit Meeting | 3 February 2021 |
| 13rd Operation Coordination Unit Meeting | 10 March 2021 |
| 14th Operation Coordination Unit Meeting | 5 May 2021 |
| 15th Operation Coordination Unit Meeting | 2 June 2021 |
| 16th Operation Coordination Unit Meeting | 8 July 2021 |
| 17th Operation Coordination Unit Meeting | 4 August 2021 |
| 18th Operation Coordination Unit Meeting | 1 September 2021 |
| 19th Operation Coordination Unit Meeting | 3 November 2021 |
| 20th Operation Coordination Unit Meeting | 1 December 2021 |
| 21st Operation Coordination Unit Meeting | 5 January 2022 |
| 22nd Operation Coordination Unit Meeting | 2 February 2022 |
| 23rd Operation Coordination Unit Meeting | March 2022 |
| 24th Operation Coordination Unit Meeting | 11 May 2022 |
| 25th Operation Coordination Unit Meeting | 1 June 2022 |
| 26st Operation Coordination Unit Meeting | 6 July 2022 |
| 27th Operation Coordination Unit Meeting | 10 August 2022 |
| 28th Operation Coordination Unit Meeting | 8 September 2022 |
| 29th Operation Coordination Unit Meeting | 7 November 2022 |
| 30th Operation Coordination Unit Meeting | 19 December 2022 |
| 31st Operation Coordination Unit Meeting | 11 January 2023 |
| 32nd Operation Coordination Unit Meeting | 1 February 2023 |
| 33rd Operation Coordination Unit Meeting | 1 March 2023 |
| 34th Operation Coordination Unit Meeting | 3 May 2023 |
| 35th Operation Coordination Unit Meeting | 5 July 2023 |
| 36 th Operation Coordination Unit Meeting | 9 August 2023 |
| 37 th Operation Coordination Unit Meeting | 11 September 2023 |
| 38th Operation Coordination Unit Meeting | 31 May 2024 |
| 39th Operation Coordination Unit Meeting | 11 July 2024 |
| 40th Operation Coordination Unit Meeting | 17 August 2024 |
| 41st Operation Coordination Unit Meeting | 23 September 2024 |
| 42nd Operation Coordination Unit Meeting | 29 November 2024 |
| 43rd Operation Coordination Unit Meeting | 24 January 2025 |
| 44th Operation Coordination Unit Meeting | 13 February 2025 |
| First Weekly Meeting | 4 July 2024 |
| Second Weekly Meeting | 18 July 2024 |
| Third Weekly Meeting | 25 July 2024 |
| Fourth Weekly Meeting | 19 September 2024 |
| Fifth Weekly Meeting | 24 October 2024 |

| Table 2. List of Events, Trainings, Conferences | Date |
| --- | --- |
| Launch Event | 26 February 2020 |
| Inception Workshop | 26 February 2020 |
| Consultative Meeting on Grant Management Consultative Meeting on National Adaptation Platform Consultative Meetings on Activity 2.1.2 | 27 April 2020 21 May 2020 22-23 July 2020 |
| Consultative Meeting on Analysis of Climate Change Models No.1 | 19 August 2020 |
| Consultative Meeting on National Adaptation Platform No.2 | 30 July 2020 |
| Consultative Meeting on National Adaptation Platform No.3 | 19 August 2020 |
| Consultative Meeting on Activity 2.2.3 | (Muğla) 7-8 December 2020 (Samsun) 14-15 December 2020 (Konya) 21-22 December 2020 (Sakarya) 28-29 December 2020 |
| CM on Activity 2.2.3 | (Samsun) 19-20 August 2021 (Muğla) 23-24 August 2021 |
| CM Activity 1.2.4 | (Main Session – Water Resources) 15 March 2021 (Agriculture – Tourism & Cultural Heritage) 16 March 2021 (Social Development – Health) 17 March 2021 (Industry – Urban) 18 March 2021 (Transportation, Communication – Energy) 19 March 2021 (Ecosystem Services (Land) – Ecosystem Services |
| CCAGP “EU Grant Scheme Implementation Process” Training | 24-25 December 2020 |
| Information Days for CCAGP | CCAGP 23 October 2020 CCAGP 26 October 2020 CCAGP 28 October 2020 CCAGP 30 October 2020 CCAGP 2 November 2020 CCAGP 4 November 2020 CCAGP 6 November 2020 |
| CM on Activity 3.1.3 | (Public Institutions) 14 June 2021 (Academia) 14 June 2021 (NGO) 15 June 2021 (Private Sector) 15 June 2021 (Municipalities) 16 June 2021 (Konya) 21 June 2021 (Muğla) 21 June 2021 (Sakarya) 22 June 2021 (Samsun) 22 June 2021 (Sakarya) 6-7 July 2021 |
| CM on Activity 2.3.2 | (Sakarya) 7 June 2021 (Konya) 8 June 2021 (Muğla) 9 June 2021 (Samsun) 10 June 2021 |
| CM on Activity 2.2.3 (Konya) 12-13 July 2021 | 12-13 July 2021 |
| CM on Activity 3.2.5 | 28-29 September 2021 |
| #### CM on Activity 3.1.3 #### CM on Activity 3.1.3 #### CM on Activity 3.1.3 #### CM on Activity 3.1.3 #### CM on Activity 2.2.3 | Activity 3.1.3 (Konya) 21 June 2021 Activity 3.1.3 (Muğla) 21 June 2021 Activity 3.1.3 (Sakarya) 22 June 2021 Activity 3.1.3 (Samsun) 22 June 2021 Activity 2.2.3 (Sakarya) 6-7 July 2021 |
| Grant Projects Management and Monitoring Training | 12-13 September 2022 |
| CM on Activity 143 | 19-30 September 2022 |
| CM on Activity 233 - Konya 16-17 May 2022 CM on Activity 233 - Sakarya 30-31 May 2022 CM on Activity 233 – Samsun 14-15 June 2022 CM on Activity 233 - Muğla 22-23 June 2022 | Konya 16-17 May 2022 Sakarya 30-31 May 2022 Samsun 14-15 June 2022 Muğla 22-23 June 2022 |
| CM on Activity 134 | 18-22 April 2022 |
| CM on Activity 1.3.3 | 24-25 November 2022 |
| Grant Programme Implementation Process Training | 25 April 2022 |
| Information Days on Full Application Form Preparation for CCAGP | 22-23 March 2022 |
| #### Study Visit to Valladolid and Madrid in Spain | 28 November -1 December 2022 |
| SV to Valladolid & Madrid in Denmark and Sweden | 8-11 May 2023 |
| Study Visit to the Netherlands | 18-24 August 2024 |
| CM on Activity 2.3.4 | 10-14 July 2023 |
| 1st Sectoral Awareness Raising Training in Ankara | 30-31 July 2024 |
| 2nd Sectoral Awareness Raising Training in Eskişehir | 13-14 August 2024 |
| Study Visit (SV) to Netherlands | 18-23 August 2024 |
| 3rd Sectoral Awareness Raising Training in Van | 9-10 September 2024 |
| 4th Sectoral Awareness Raising Training in Trabzon | 30 September-01 October 2024 |
| Fourth Weekly Meeting | 19 September 2024 |
| 5th Sectoral Awareness Raising Training in Antalya | 15-16 October 2024 |
| 6th Sectoral Awareness Raising Training in Nevşehir | 12-13 November 2024 |
| 7th Sectoral Awareness Raising Training in Diyarbakır | 11-12 December 2024 |
| Grant Projects Reporting Training in Ankara | 23-24 December 2024 |
| 8th Sectoral Awareness Raising Training in Adana | 7-8 January 2025 |
| 9th Sectoral Awareness Raising Training in Şanlıurfa | 21-22 January 2025 |
| 10th Sectoral Awareness Raising Training in İstanbul | 18-19 February 2025 |
| 1st Awareness Raising Conference in İstanbul-Health | 20 February 2025 |
| 2nd Awareness Raising Conference in İzmir-Biodiversity | 6 March 2025 |
| 11th Sectoral Awareness Raising Training in Bursa | 25-26 February 2025 |
| 12th Sectoral Awareness Raising Training in Aydın | 4-5 March 2025 |
| 2nd Consultative Meeting in İstanbul | 18 March 2025 |
| 13th Sectoral Awareness Raising Training in Sivas | 25-26 March 2025 |
| 14th Sectoral Awareness Raising Training in İzmir | 8-9 April 2025 |
| Samsun UASAP Finance Training | 15-17 April 2025 |
| Konya UASAP Finance Training | 28-30 April 2025 |
| 15th Sectoral Awareness Raising Training in Çanakkale | 6-7 May 2025 |
| 3rd Awareness Raising Conference in Çanakkale - Urban Adaptation | 8 May 2025 |
| Sakarya UASAP Finance Training | 20-22 May 2025 |
| 16th Sectoral Awareness Raising Training in Edirne | 21-22 April 2025 |
| 17th Sectoral Awareness Raising Training in Denizli | 13-14 May 2025 |
| 4th Awareness Raising Conference in Antalya - ARA | 21 May 2025 |
| 5th Awareness Raising Conference in Mardin - Tourism | 28 May 2025 |
| 18th Sectoral Awareness Raising Training in Erzurum | 3-4 June 2025 |
| 19th Sectoral Awareness Raising Training in Zonguldak | 11-12 June 2025 |
| 3rd Grants Consultative Meeting in Antalya | 17 June 2025 |
| 1st Awareness Raising Conference in Antep-Energy | 25 June 2025 |
| 20th Sectoral Awareness Raising Training in Giresun | 3-4 July 2025 |
| SV to Germany | 7-11 July 2025 |
| 1st IDUSEP - Ankara | 17-18 June 2025 |
| 2nd IDUSEP - Ankara | 30 June-1 July 2025 |
| 3rd IDUSEP - Ankara | 7-8 July 2025 |
| 4th IDUSEP - Ankara | 16-17 July 2025 |
| 5th IDUSEP - Ankara | 21-22 July 2025 |
| Muğla UASAP Finance Training | 23-25 July 2025 |
| 7th Awareness Raising Conference in Antalya - Transportation | 31 July 2025 |
| Samsun Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training on M&E | 4 August 2025 |
| Konya Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training on M&E | 5 August 2025 |
| Sakarya Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training on M&E | 6 August 2025 |
| Muğla Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training on M&E | 7 August 2025 |
| 4th Grants Consultative Meeting in Antalya | 28 August 2025 |
| IFI Conference | 11 September 2025 |
| E-NASAP Online M&E Training | 15-16 September 2025 |
| A3.2.5 Consultative Meeting | 17 September 2025 |
| Grant Fair and Information Day | 25 September 2025 |
| Closure Event | 3 October 2025 |

### Monitoring and Reporting

The revision and approval process of the administrative and technical reports and working documents are submitted in the annexes to this report.

#### 11th Activity Report

The draft of the 11th  Activity Report, which can be found in Annex 1, was submitted for the review of the Contracting Authority (CA), End Beneficiary (ER) and EUD prior to Steering Committee meeting. Revised version was submitted to DCC on 19 June 2025. DCC approved the report on 3 July 2025 via e-mail. It was submitted to all parties in hard copy on 15 August 2025. The report approved on 11.08.2025 by ER. The official approval letter was received on 04.09.2025 by the Contracting Authority.

#### 4th-5th (Combined) Progress Report

The draft of the 4th-5th (Combined) Progress Report, which can be found in Annex 1, was submitted for the review of the CA, ER and EUD on 5 December 2024. The report was approved by the DCC on 5 December 2024. The translation of the report together with the English version was submitted on 20 December 2024 via official letter.  The official approval letter was received on 27.02.2025 by the Contracting Authority.

### Project Components

The progress in the activities under each component within the reporting period is presented as follows:

#### The progress in the activities under each component within the reporting period is presented as follows:

#### Component 1

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 1.1. Review of existing climate change adaptation works and best practice catalogue 1.1.1. A comparative assessment based on literature review from EU member states on methods and best practices to compile adaptation related work and studies. 1.1.2.A compilation of existing climate change adaptation work in Türkiye carried in the public and private sector, in universities and among the civil society. The compilation will aim to capture the majority of work, including studies, research, funding, project/program, events. 1.1.3. A multi-parameter analysis framework to review the material for relevance, technical quality, etc. 1.1.4 A list of best practices among existing work to serve as reference for future work. 1.1.5.A user-friendly filing classification system and a final report including findings and meeting proceedings. | Report including the comparative assessment, multi-parameter analysis framework, classification system, compilation of existing work and list of best practices | October 2020 (completed) | The draft report including the working papers on Activity 1.1.1, 1.1.2, 1.1.3, 1.1.4 and 1.1.5 was submitted on 22 October 2020 in line with the decision taken at OCU Meeting No. 8 and approved by the ER on 4 January 2021. The translation of the document was submitted for review on 22 March 2021 and approved on 13 April 2021. The approved final report was submitted as an annex to AR3. |
| Activity 1.2. Comprehensive climate change impact and vulnerability assessment for five priority sectors 1.2.1.A sensitivity analysis to understand the performance of the models used by, inter alia Directorate General of Meteorology and DG Water Management of the Ministry of Agriculture and Forestry, ITU Eurasia Earth Sciences Institute, to develop recommendations towards the update and/or improvement of the models. 1.2.2 Climate projections updates for sector use using Global Circulation Models outputs with regional models and available Intergovernmental Panel on Climate Change scenarios, including sector specific multi-hazard assessments with summary likelihood/severity tables. 1.2.3.An indicator based climate vulnerability assessment scoping including a synopsis of the sectors, key stakeholders, and a methodology for a vulnerability index map in line with IPCC (AR5). 1.2.4.5 one-day consultative meeting with the participation of the relevant public, private, academic and civil society stakeholders to discuss the findings, methodology and scope. Meetings will be held in Ankara, 50 to 60 representatives are expected to attend each meeting. 1.2.5.-10 sector climate vulnerability assessment covering: (i) a brief sector overview with trends, volume, affinities, opportunities, threats and uncertainties , (ii)main vulnerability factors to different climatic hazards, (iii) existing adaptive capacity, and (iv) annualized impact estimation, including any potential domino impact (within the same sector) and cascading impact (to other sectors). 1.2.6.An estimation of economic impacts of climate change and cost of adaptation measures for priority sectors, with a baseline “business as usual” scenario for comparison, which will be an input to the activity 1.4.3., and linked with activity 1.6.4. 1.2.7. A final report including findings and meeting proceedings. | Report including sensitivity analysis, updated climate projections, vulnerability assessment scoping, vulnerability assessment and estimation of economic impacts | December 2022 (completed) | The draft report including the working papers on Activity 1.2.1, 1.2.2, 1.2.3, 1.2.4, 1.2.5 and 1.2.6 was submitted on 8 December 2022 in line with the decision taken at OCU Meeting No.23 (for 1.2.6) and approved by the ER on 12 January 2023. The translation of the document was submitted for review on 2 May 2023 and approved on 24 July 2023. The approved final report (except for 1.2.5) was submitted as an annex to AR7. |
| Activity 1.3. Activity 1.3. Adaptation options for updating the NASAP (completed) |  |  |  |
| Activity 1.3.1. A desk review of NASAP prioritization methodologies (i.e. cost-benefit, cost-effectiveness analysis, multi-criteria analysis, etc.) among EU member states, including good practices and lessons learned (including maladaptation practices) A stock-taking exercise on national strategies and policies for priority sectors, and international commitments and developments under multilateral environmental processes, such as the Paris Agreement, Sendai Framework and SDGs. | Desk review | April 2021 (completed) | The draft working paper was submitted on 15 April 2021 in line with the decision taken at OCU Meeting No. 12. The report was approved by the ER on 28 May 2021. The translation of the document was submitted for review on 16 August 2021 and approved on 23 March 2023. The final report was submitted as an annex to AR7. |
| 1.3.2 11 sector adaptation strategies for the priority sectors including structural and non-structural adaptation measures and using the vulnerability index map developed in Activity 1.2 | Desk review | December 2021 (Completed) | Preliminary studies were completed right before the initiation of the NASAP studies. |
| Activity 1.3.3. A comparative analysis of the Turkish NASAP with selected EU member states, including (i) elaboration and update process, (ii) organizational and financial aspects, (iii) methodologies used for developing the strategy and prioritizing the actions, and (iv) recommendations for improvement in the context of Türkiye with linkages to the SDGs. 2 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to discuss the update methodologies for NASAP. Meetings will be held in Ankara; 50 to 60 representatives are expected to attend each meeting. | Desk review | December 2021 (completed) | The draft working paper was submitted on 22 April 2021 in line with the decision taken at OCU Meeting No. 12. The report was approved by the ER on 6 May 2021. The translation of the document was submitted for review on 16 August 2021 and approved on 23 March 2023. The final report was submitted as an annex to AR7. In line with the consultations with the ER, a two-day consultative meeting was held on 24-25 November 2021 (instead of 2 one-day meetings) to ensure in-depth discussions on the NASAP update methodologies. The meeting report was submitted on 10 March 2022 and approved on 12 January 2023. Translation of the report was submitted on 28 March 2023. The final report was submitted as an annex to AR7. |
| Activity 1.3.4. Adaptation options identified as a long list by stakeholders. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to discuss and identify adaptation measures for each priority sector. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each meeting. This activity will be an input to Activity 1.4.3. | 5 one-day consultative meetings | September 2022 (completed) | Consultative meetings under this activity were held between 18-22 April 2022. The draft meeting report was submitted for review on 24 August 2022 and approved on 6 September 2022. The final report was submitted as an annex to AR6. |
| Activity 1.3.5. A final report including findings and meeting proceedings. | Final report | September 2022 (completed) | The draft report was submitted for review on 8 September 2022 and approved by the ER on 22 August 2023. |
| Activity 1.4. Updated NASAP through multi-stakeholder process (ongoing) |  |  |  |
| Activity 1.4.1. An action plan for the NASAP update process, including identification of key stakeholders and detailed work schedule. | Action plan for the NASAP update process | October 2022 (completed) | The draft report was submitted for comments on 26 September 2022. Comments were received on 11 October 2022. The revised document was submitted for approval on 18 October 2022 and approved on 25 October 2022. The draft translation of the report was submitted for comment on 2 May 2023. The final report was submitted as an annex to AR7. |
| Activity 1.4.2. Dissemination of reports elaborated under activities 1.1, 1.2 and 1.3 among key stakeholders and series of sector specific working meetings to identify priority adaptation activities. | Dissemination of reports | April 2023 (completed) | Reports prepared under the project were shared with the stakeholders and consultations were held. |
| Activity 1.4.3. 10 one-day, and 3 two-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders for the prioritization of adaptation activities. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each one-day meeting and 50 to 100 are expected to attend each two-days meeting. | 10 1-day & 3 2-day consultative meetings | January 2023 (completed) | Ten one-day consultative meetings were held between 19-30 September 2022. The meeting report was submitted for review on 6 December 2022 and approved on 23 March 2023. The translation of the report was submitted to the opinion on 21 June 2023 and approved on 13 July 2023. The final report was submitted as an annex to AR7. Three two-day consultation meetings were held on 7-9 and 13-15 December 2022. The meeting report was submitted for review on 12 January 2023 and approved on 23 March 2023. The translation of the report was submitted to the opinion on 16 May 2023 and approved on 12 July 2023. The final report was submitted as an annex to AR7. |
| Activity 1.4.4. An updated NASAP, including: (i) strategic priorities and areas of intervention in accordance of SDGs, (ii) an action plan with a list of selected climate change adaptation solutions, (iii) capacity building activities of relevant stakeholders, and (iv) a coordination mechanism among national entities (public, private, academia, civil society) at different levels and with international organizations. | Updated NASAP | November 2024 (completed) | These studies were launched in June 2022. The updated NASAP was submitted for comments on 9 January 2023. In accordance with the comments received, the actions were revised, and the total number of actions was limited to 150 and submitted for review by the stakeholder institutions through the DCC on 11 May 2023. Another revision was made upon comments received in the consultative meetings held in July 2023, the revised NASAP submitted for a second round of comments on 31 July 2023. The updated version of the NASAP was submitted for the final round of comments in August. To obtain consensus with all stakeholders, a two-day working group meeting was held on 19-20 September 2023 and NASAP was finalized accordingly. The Turkish and English version was approved by DCC, CA and the EUD. |
| Activity 1.4.5. Submission to the higher authorities of the MOEUCC for its endorsement and processing through the legislative body | NASAP submission | October 2024 (Completed) | The record and supporting documentation were finalized in Q4 2024. |
| Activity 1.4.6. Dissemination campaign of the NASAP among central and local authorities, civil society, academia, the private sector and the international community. | Dissemination campaign of the NASAP | December 2024 | English copies of the E-IDUSEP brochure and booklet had been made visible during COP-29 2024. IDUSEP was shared with participants during Sectoral Awareness Raising Training and 7 Awareness Raising Conferences in different provinces. The dissemination campaign has been ongoing. The brochures and printed version of NASAP were shared during COP-29, meetings and training. |
| Activity 1.5. M&E system for the NASAP (ongoing) |  |  |  |
| Activity 1.5.2. An online M&E system for the NASAP that encompasses the identified set of indicators and will require all involved stakeholders to report into | Online M&E system | Aug 2024 (Completed) | The draft M&E system was presented to the ER on 14 September 2023. The respective expert revised online M&E for the NASAP based on consultations with DCC in July 2024. The revisions were accepted by DCC on 28 August 2024. |
| Activity 1.5.3. A training module on the use of M&E systems and 4 two-days online training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the NASAP. 150 staff in total are expected to receive the training. | Training Module on the use of M&E system | Q3 2025 | The first online training session was organized on 5-6 November 2024. The second 2-day online training was organised on 10-11 February 2025. The third 2-day online training was completed on 5-6 March 2025. The 4th training was completed on 15-16 September 2025. The training was merged with the Consultative Meeting under A.3.2.5 which was held on 17 September 2025. The NASAP guideline and training module have been approved by DCC. Please refer to Annex 06 for the M&E system guidelines; please also refer to Annex 18 for the agenda, presentation, certificates, and participation list. |
| Activity 1.5.4. A regular review of the priorities and activities identified in the NASAP to assess progress, effectiveness and gaps. The review process will consist of one baseline assessment and 1 annual progress evaluations during the lifetime of the project. | Baseline assessment/ Annual Progress Evaluation | Q3 2025 | A preliminary meeting was held with the software expert. The activity completion date had been revised as December 2024. Menti questions and reviews on the system were received during the 4 two-day training. |
| Activity 1.5.5. Outreach of the NASAP and the progress reports at national level through national communications and various media tools. | Outreach | Q3 2025 | NASAP was disseminated during COP-29 as well as the sectoral training in the provinces and 7 one-day conferences. It continues to be disseminated on the project website and through human stories. |
| Activity 1.6. Climate financing strategy for the NASAP |  |  |  |
| Activity 1.6.1. A desk review (i) to take stock of existing and expected future climate financing mechanisms at international and national level, (ii) to analyze climate financing strategies of selected EU member states with national adaptation strategies, and (iii) to evaluate existing finance mechanisms for other themes for best practices and lessons learned. | Desk review | February 2022 (completed) | The draft working paper was submitted on 8 February 2022. The comments from ER were received on 27 May 2022. The revised document, along with its translation, was submitted on 27 July 2022. It was approved on 4 October 2022. The final report was submitted as an annex to AR7. |
| Activity 1.6.2. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders from priority sectors to discuss existing and expected future financial models and mechanisms and priorities for climate financing. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each meeting. | 5 1-day consultative meetings | November 2022 (completed) | Consultative meetings under this activity were held on 10-14 October 2022. The meeting report was submitted for review on 6 December 2022 and approved by ER on 10 January 2023. The translation of the report was submitted for comment on 22 May 2023 and approved on 17 July 2023. The final report was submitted as an annex to AR7. |
| Activity 1.6.3 A financing framework including (i) objectives, (ii) trend analysis of past climate financing and future scenarios, (iii) sector specific financing and budgets for the priority sectors, (iv) resource availability from the public, private sectors, at national and international level, and (v) modalities and institutional arrangements | A financing framework | December 2022 (completed) | Financial framework studies were initiated on 9 February 2022 to collect data. The report was submitted on 13 December 2022 and received comments on 21 March 2023. The revised document was submitted on 11 April 2023 and approved by the ER on 22 August 2023. |
| Activity 1.6.4. A climate finance action plan for priority sectors including (i) institutional responsibilities, (ii) scenarios with total cost needed as per the NASAP, resources likely to be available, (iii) assessments of benefits of adaptation activities, (iv) recommendation for phasing, and (v) any institutional reform or innovation required to manage climate funding in the sector, including an assessment of capacities and limitations. | Climate finance action plan | March 2023 (completed) | Studies to collect data were initiated in September 2022. The analysis report was submitted for review on 10 January 2023. Comments were received on 20 February 2023, revisions were made in line with the comments, submitted for approval on 22 March 2023 and approved on 22 March 2023. The translation of the document was submitted for review on 9 May 2023 and approved on 24 July 2023. The final report was submitted as an annex to AR7. |
| Activity 1.6.5. A final climate finance strategy by combining the financing framework and the climate finance action plans, together with the inputs and feedback from the consultative meetings. | Final climate finance strategy | Q2 2025 | The draft Finance Strategy document was approved by the DCC on 10.03.2025. The document was shared with public institutions to receive their final feedback and finalize the document. |
| Activity 1.7. Adaptation plan implementation guidelines for priority sectors (ongoing) |  |  |  |
| Activity 1.7.1. A desk review (i) to take stock of existing sector specific guidelines among EU member states and countries with similar socio-economic profiles, and (ii) to evaluate ongoing reforms and implementation mechanisms (i.e. policy making and project lifecycle) within the priority sectors. | Desk review | May 2023 (completed) | The draft working paper was submitted for review on 15 May 2023 and approved on 18 July 2023. |
| Activity 1.7.2. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to identify institutional and technical needs for adaptation to be implemented successfully. Meetings will be held in Ankara; 20 to 30 representatives are expected to attend each meeting. | Consultative Meetings | July 2023 (completed) | Consultative meetings were held between 10-14 July 2023 with participation of 280 representatives from the relevant public, private, academic and civil society stakeholders. |
| Activity 1.7.3 11 sector specific adaptation plan implementation guidelines including (i) tools and methodologies for different types of adaptation work (structural, non-structural), (ii) connections with the existing sectoral strategy and investment plan, (iii) connections with the climate finance strategy, and (iv) criteria for decision-making and evaluation. The finance section of the guidelines will be integrated with activity 1.6 | Sector -specific Adaptation Plan Implementation Guidelines | Q3 2025 (completed) | Adaptation plans were shared with DCC on 27.01.2025. DCC provided feedback and approved the plans on 13.02.2025. The experts reviewed and accepted the additions. The guidelines were presented during the five 2-day training. Please refer to Annex 16 for the guidelines. |
| Activity 1.7.4. A training module on the use of the guidelines and 5 two-days training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the NASAP. Training sessions will be held in Ankara Ilbank premises, 250 staff in total are expected to receive the training. | Training Module | Q3 2025 (completed) | This activity was completed in July 2025. 1st Training: 17-18 June 2025 2nd Training: 30 June-1 July 2025 3rd Training: 7-8 July 2025 4th Training: 16-17 July 2025 5th Training: 21-22 July 2025. Please refer to Annex 15 for the training module. Since ILBANK premises was not availbale for the determined date and times, the meetings were conducted in hotels. This change has been reflected to Notification No 14. |

#### Component 2

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 2.1. Adaptation guidelines and urban typology framework for cities | Report including desk review, adaptation guidelines and urban typology framework | November 2020 (completed) | The draft report including the Activity 2.1.1, 2.1.2, 2.1.3 and 2.1.4 was submitted on 5 November 2020 in line with the decision taken at OCU Meeting No. 8 and approved by the ER on 26 November 2020. The translation was also approved on 15 January 2021. The approved final report was submitted as an annex to AR3. |
| Activity 2.2. Climate change impact and vulnerability assessment for 4 pilot metropolitan municipalities | Report including updated climate projections, vulnerability assessment scoping, vulnerability assessment for pilot cities | February 2022 (completed) | The draft report including Activity 2.2.1, 2.2.2, 2.2.3 and 2.2.4 was submitted on 8 February 2022 and approved on 27 March 2023. The translation of the report was submitted on 16 May 2023 and approved on 30 May 2023. The final report (except for 2.2.4) was submitted as an annex to AR7. |
| Activity 2.3. Preparation of UASAPs for 4 pilot metropolitan municipalities (ongoing) |  |  |  |
| Activity 2.3.1. A desk review of city-wide adaptation actions based on vulnerability assessments through stakeholder engagement at EU level and within EU member states. Solutions catalogue and experience from EU and other Turkish cities can feed into this activity, while innovative solutions will also be sought. | Desk review | June 2021 (completed) | The draft report was submitted on 15 June 2021 in line with the decision taken at OCU Meeting No. 14 and approved by the ER on 29 June 2021. The translation of the document was submitted for review on 13 September 2021 and approved 20 January 2022. The final report is submitted as an annex to AR7. |
| Activity 2.3.2. 4 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders at city level to discuss the scope of the UASAPs. Meetings will be held in pilot cities; 50 to 60 representatives are expected to attend each meeting. | 4 1-day consultative meetings | July 2021 (completed) | Consultative meetings were held between 7-10 June 2021. Draft meeting report was submitted on 8 September 2021 and approved on 22 September 2021. The translation of the report was submitted for review on 19 April 2023 and approved on 24 April 2023. The final report is submitted as an annex to AR7. |
| Activity 2.3.3. 4 UASAPs for the pilot cities including structural and non-structural adaptation measures and using the vulnerability index map developed in Activity 2.2. The UASAPs will include adaptation goals, indicative timeframe, budget and funding options, baseline and performance indicators and responsible organisation(s) for each goal/action. | 4 UASAPs 4 two-day consultative meetings | April 2025 (Completed) | UASAPs were revised in line with comments of the ER, and the consultative meetings held in pilot cities in June 2023. The revised plans were again sent for review by the local stakeholders to finalize. DCC provided their final comments. Experts reflected them on the action plans and UASAP's for each sector in 4 pilot provinces. Final UASAPs were approved by DCC on 27.02.2025. Small revisions requested for Sakarya on 27.02.2025. Samsun UASAP design was shared with DCC on 28.02.2025. Designs for the UASAPs were approved by CA on 24.02.2025. |
| Activity 2.3.4. A media launch meetings in 4 pilot cities for at least 25 people in each provinces, about each city and dissemination materials in different formats for different target audiences/stakeholders | Media launch | Q2 2025 | The media launch events were held in Samsun and Konya in April 2025, in Sakarya in May 2025, and in Muğla in July 2025. |
| Activity 2.4. M&E system for the UASAPs (ongoing) |  |  |  |
| Activity 2.4.1. A desk review (i) to take stock of existing adaptation indicators and governance mechanisms (e.g. SMART indicators) from EU cities, (ii) to identify relevant indicators already existing in national and local M&E systems, and (iii) to identify different M&E governance models (e.g. climate M&E officer, assigned staff under climate change unit) applicable for cities in Türkiye and staff time, budget and capacity development required for these models. | Desk Review | February 2021 (Completed) | Final report date was 03.02.2021, this activity is completed. |
| Activity 2.4.2. An online M&E system for cities that encompasses the identified set of indicators and will require all involved stakeholders to report into. | Online M&E system | In DoA Cancelled / deleted by mistake during Addendum No1 approved in Feb 2024. However, as per OCU decision, this activity was conducted. Q3 2025 | Ongoing; the contracted expert has started the analysis phase for development of the M&E system. This activity was scheduled for Q3 2024 in addendum approval yet expected to be completed in Q4 2024 as the addendum approval was realised in Feb 2024. It is also agreed to hold 1 day M&E training in pilot municipalities instead of discussing M&E system layout under Activity 2.4.2 during the first quarter of 2025. Yahya Akdağ, software development specialist, has prepared the system. The draft version of the system and under the review of DCC. The expert will provide a presentation on the UASAP media launch. |
| Activity 2.4.3. A regular review of the priorities and activities identified in the UASAPs to assess progress, effectiveness and gaps. The review process will consist of one baseline assessment and 1 annual progress evaluation during the lifetime of the Project. | 1 baseline assessment and 1 annual progress evaluation | Q3 2025 | The contracted expert started the analysis phase for the M&E system. This activity was planned for Q3 of 2024 but the estimated completion time for the activity will be updated to Q2 2025 according to up-to-date AWP due to the approval of the latest Addendum that was completed in February 2024. It was also agreed to hold 1 day M&E training in pilot municipalities instead of discussing M&E system layout under Activity 2.4.2 during the first quarter of 2025. Following the completion/progress of Activity 2.4.2., this activity was initiated. The finance trainings were held face to face in Samsun 15-17 April 2025, in Konya on 28-30 April 2025, in Sakarya 20-22 May, in Muğla 23-25 July 2025. Apart from that the online NASAP training were held between 4-7 August 2025. Demo data entries were completed, and all the questions regarding the indicator entry were answered accordingly. Apart from that another training regarding IDUSEP M&E system was held on 15-17 September 2025 regarding the monitoring system. The expert will write a detailed report on it and will present it to responsible parties regarding the completed trainings. |
| Activity 2.4.4. A training module on the use of M&E systems and 4 one-day online training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the UASAPs. 100 staff in total are expected to receive the training. | A training module on the use of M&E systems and 4 one-day online training sessions | Q3 2025 (completed) | This activity was completed in August 2025. 1st Training, Samsun Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training, was held on 4 August 2025. 2nd Training, Konya Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training, was held on 5 August 2025. 3rd Training, Sakarya Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training, was held on 6 August 2025. 4th Training, Muğla Local Climate Change Adaptation Strategy and Action Plan and Sectoral Indicator Input Training, was held on 7 August 2025. |
| Activity 2.4.5. Outreach of the UASAPs and the progress reports at national level through national communications and various media tools | Outreach | Q3 2025 | UASAPs had been uploaded to the Project Website and shared with both DCC's and UNDP's official accounts. In addition, printed version with the UASAP booklets were disseminated during media launch of UASAP and finance training. |
| Activity 2.5. Urban climate financing strategy (ongoing) |  |  |  |
| Activity 2.5.1. A desk review (i) to take stock of existing climate financing mechanisms at city level among EU member states, (ii) to analyze climate financing strategies of selected EU member states with UASAPs, and (iii) to evaluate existing finance mechanisms in Turkish cities for other themes for best practices and lessons learned. | Desk review | February 2022 (Completed) | The draft working paper was submitted on 8 February 2022. The comments from ER were received on 27 May 2022. The revised document, along with its translation was submitted on 27 July 2022. It was approved on 4 October 2022. The final report was submitted as an annex to AR7. |
| Activity 2.5.2. An assessment of different financial solutions, including financial viability and operational sustainability, potentials and constraints for their implementation and uptake (e.g. regulatory context, pricing failures). | Assessment of different financial solutions | April 2023 (Completed) | The report was submitted for review on 28 March 2023 and approved on 11 April 2023. The translation of the document was submitted for approval on 22 May 2023 and approved on 30 May 2023. The final report was submitted as an annex to AR7. |
| Activity 2.5.3. A conference bringing IFIs, national and local authorities together to explore IFIs’ global experience in urban climate financing, and discuss suitable solutions for Turkish cities. This conference will complement the national level consultative stakeholder meetings from Activity 1.6 with local level perspectives. The meeting will be held in İstanbul and attended by approximately 60 people, from IFIs, Municipalities, MoEUCC and relevant other institutions. A brief conference report reflecting the results of the conference will be prepared. | Conference | Q3 2025 (completed) | The conference was organized on September 11, 2025, in İstanbul with the participation of 84 attendants from national and international institutions. Participating institutions: IBRD (World Bank), EBRD, TSKB (Industrial Development Bank of Türkiye), IsDB (Islamic Development Bank), and JICA. Topics addressed: access to finance for a green, resource-efficient and inclusive local transition; the global climate-finance gap (incl. COP29 context); innovative finance, risk-sharing and co-financing via IFIs with technical assistance/capacity development; Türkiye’s limited access to direct UNFCCC climate funds and cooperation programmes with IFIs; strengthening municipalities’ own-source revenues and local financing mechanisms; TSKB’s Green Finance Project and Adapt-Tool Kit; new initiatives by IsDB and JICA. Please refer to Annex 10 for the conference content, attendance and report. |
| Activity 2.5.4. An estimation of adaptation financial needs for each city and potential market for adaptation at national scale, with a baseline “business as usual” scenario for comparison. These assessments will take into consideration costs associated with circumventing existing or planned mal-adaptation measures to inform the development of no-regret and low-regret adaptation measures.​ | Urban climate financing needs report | Q3 2025 | Ongoing. Awaits approval from DCC. |
| Activity 2.5.5. An urban climate financing strategy for the implementation of UASAPs | Urban Climate finance strategy for the implementation of the UASAPs. | Q3 2025 | It was finalized upon the confirmation of Activity 2.5.4 on September 2025. |
| Activity 2.5.6. A training module on the financial mechanisms and 4 two-days training sessions to relevant stakeholders from public, private, academia and civil society. The relevant staff assigned to the elaboration and implementation of the activities laid out in the UASAPs. Training sessions will be held in pilot cities, 100 staff in total are expected to receive the training. | A training module on the financial mechanisms and 4 two-days training sessions | Q3 2025 (completed) | The training were delivered in 4 provinces along with the media launch. On 15-17 April in Samsun On 28-30 April in Konya On 20-22 May in Sakarya On 23-25 July in Muğla in July |

Component 3

| Activity |  | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- | --- |
| Activity 3.1. Policy and stakeholder capacity and need assessment (completed) |  |  |  |  |
| Activity 3.1.1. A desk review of existing institutional framework among EU member states, including regulatory tools, decision-making processes, and roles and responsibilities, including the identification of best practices. |  | Desk review | July 2020 (Completed) | Completed |
| Activity 3.1.2. A desk review (i) to take stock of existing climate change adaptation training material among EU member states and countries with similar socio-economic profiles, (ii) to evaluate ongoing training programs and mechanisms at national and local level for similar target audiences, (iii) to identify areas with high demand for exchange of knowledge and experience from Turkish actors and centers and institutions within the EU that correspond to these needs, and (iv) to map the existing collaboration on climate change adaptation between EU and national stakeholders. |  | Desk review | July 2020 (Completed) | The draft working paper was submitted on 8 July 2020. |
| Activity 3.1.3. 5 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders at city level to identify strategic entry points for capacity building. Meetings will be held in Ankara and 4 cities; 20 30 representatives are expected to attend each meeting. |  | 5 1-day consultative meetings | June 2021 (Completed) | Consultative meetings were held between 14-16 and 21-22 June 2021. The draft meeting report was submitted on 30 June 2021. |
| Activity 3.1.4. A technical capacity and need assessment including bilateral interviews and a survey with key public, private, academic, civil society stakeholders on motivation and interest, availability of and accessibility to information, priorities in decision-making, challenges for implementation, etc. The findings will be analyzed and published. |  | Capacity and need assessment | June 2021 (Completed) | The capacity and need analysis survey was shared on 15 February 15, 2021, and was kept available until 15 April 15, 2021. Draft working paper submitted on 30 June 2021 in line with the decision taken at OCU Meeting No.14. |
| Activity 3.1.5. A final assessment report including findings of the desktop reviews, analysis of the survey and interviews and meeting proceedings. |  | Final report | July 2021 (Completed) | The draft report was submitted on 8 July 2021. |
| Activity 3.2. Capacity building and networking (ongoing) |  |  |  |  |
| Activity 3.2.1. A capacity building plan based on the findings of 3.1. Below numbers for training modules, training sessions and study visits are indicatively identified for calculations purposes. They may be revised according to these findings and budget availability. |  | Capacity building plan | September 2021 (Completed) | The draft report was submitted on 8 September 2021. The comments were received on 22 September 2021. |
| Activity 3.2.2. At least 10 customized climate change adaptation training modules / e-book (including descriptive and comparative information on thematic areas) on topics such as (i) awareness raising on climate change (addressing citizens), (ii) use of climate scenarios and models, (iii) impact and vulnerability assessment, (iv) adaptation planning, and (v) Sector specific adaptation, (vi) urban resilience vii) negotiations on adaptation viii) green blue infrastructure ix) transformational adaptation etc. |  | 11 Training modules including each NASAPs sector | (Q3 2025) (completed) | UNDP shared proposed outline for the training modules studied with the Project experts to DCC on 06.02.2025, DCC recommended different topics on 19.02.2025. A meeting with the expert requested by the UNDP to clarify their expectations. DCC changed the topics, experts are working on the current topics. The topics are as follows: - Global Climate Change, Vulnerability and Risk Analysis - Sector Specific Climate Change Adaptation - Transformational Adaptation Approach to Climate Change Adaptation Strategies - Climate Modelling and Scenarios - Public Awareness Raising of Climate Change Adaptation - Fundamentals of Climate Change Adaptation - Climate Change Adaptation Policy Cycle - International Climate Change Adaptation Policies and Negotiations - Climate Adaptation Finance Strategies - Climate Change and Energy: The Synergy of Adaptation and Mitigation Please refer to Annex 07 for the e-books. |
| Activity 3.2.3. At least 20 two-days training sessions to relevant stakeholders from public, private, academia and civil society. Training sessions will be held in Ankara and the other determined cities & geographically in overall Türkiye, 600 staff in total are expected to receive the trainings. |  | Training sessions | Q3 2025 (completed) | - The 15th training was organized on 21-22 April in Edirne. (49w 41m) - The 16th training was organized on 6-7 May in Çanakkale. (34w 18m) - The 17th training was organized on 13-14 May in Denizli. (16w 27m) - The 18th training was organized on 3-4 June in Erzurum. (24w 30m) - The 19th training was organized on 10-11 June in Zonguldak. (27w 31m) - The 20th training was organized on 3-4 July April in Giresun. (21w 25m) Please refer to Annex 13 for the training content, attendance and photographs. Please refer to Annex 08 for the combined reports. The increment in the number of participants has been reflected to Notification 14 which was share earlier during OCU meetings. |
| Activity 3.2.4. At least 7 study visits for 10 participants to promote knowledge exchange between Participants will be selected from the target audience (i.e. MOEUCC staff working within the scope of the project, relevant local authorities, NGOs/associations, and academia), each will fill a report indicating how the study visit was (or was not) useful to the activities in Türkiye. The list of study visit participants shall be notified to EUD before MOEUCC approval, and EUD is to clear the list of attendance within two weeks after submission. MOEU approval shall only be sought after “no objection” is received from EUD. The remaining 6th and 7th Study Visits are planned to be conducted to 5 participants for 5 days. |  | 7 study visits | Q3 2025 (completed) | The last study visit was made to Germany on 7-11 July 2025 with the participation of 6 officials from DCC. Please refer to Annex XXX for study visit reports to Germany and Netherlands |
| Activity 3.2.5. 4 one-day consultative meetings with the participation of the relevant public, private, academic and civil society stakeholders to present their experience with different city networks and advise on membership. Meetings will be held online; 50 to 60 representatives are expected to attend each meeting. |  | 4 1-day consultative meetings (online), 2 meetings remaining | Q3 2025 (completed) | The last consultative meeting was held online with the participation of various stakeholders on 17 September 2025. This meeting was merged with the training under A.1.5.3 which was held on 15-16 September 2025. |
| Activity 3.2.6. 7 awareness raising conferences in all regions, to promote the central and local climate change adaptation agendas, and facilitating networking and partnership building between relevant stakeholders. The event will be in form of town-hall meeting, where the level of interaction between the parties will be strengthened and the key areas of planning, action, financing for climate change adaptation will be discussed in line with innovative and inclusive communication techniques as highlighted in Section 1.4. Methodology. At least 608 local actors are expected to participate. Conference topics might be considered such as; climate change and public health, Resilience Increasing and Adaptation Actions in Municipalities Against Disasters and Risks Resulting from Climate Change, biodiversity, sustainable agriculture and climate resilience, cultural heritage, green finance and climate adaptation, livelihoods and climate change and etc. |  | 7 awareness raising conferences | Q3 2025 (completed) | The 3rd ARC on “Resilient Cities: Transforming Cities for Climate Change Adaptation” was held in Çanakkale on 8 May 2025. The 4th ARC on “disaster risk management and discussed the disasters impacts of climate change” was held in Antalya on 21 May 2025. The 5th ARC on “Impacts of Climate Change on Cultural Heritage Conservation: Challenges and Solutions” was held in Mardin on 28 May 2025. The 6th ARC on “Climate Change Resilient Energy Systems: Infrastructure, Governance and Adaptation Finance” was held in Gaziantep on 25 Jun 2025. The 7th ARC on “Climate Change and the Transportation and Communication Sector”” was held in Antalya on 31 July 2025 Please refer to Annex 09 for the training content, attendance and reports. |
| Activity 3.2.7. A series of success and human stories from the training and awareness raising events to be used on website and social media. |  | Success and human stories | Q3 2025 | Success stories have been recorded under A.3.2.3 and A.3.2.6. These stories were edited by UNDP communication unit. DCC approved the video. Subtitles were edited accordingly, and the videos were disseminated through YouTube channel. Please refer to Annex XX - Visibility for the videosç |
| Activity 3.2.8. A series of 11 documentary style short movie (3 to 6 minutes), whose content will aim to familiarize the target audience and public at large on the work done in 11 priority sectors on climate change adaptation (and 1 general content). The short movies will be broadcasted within the public institutions and municipalities as well as shared with private firms, academia and the civil society. |  | 10 Short Movies | Q3 2025 Completed | The final video on biodiversity has been prepared and approved. Please refer to Annex 03 for the video. |
| Activity 3.3. National Adaptation Platform (ongoing) |  |  |  |  |
| Activity 3.3.1. A desktop review and meetings with related stakeholders (i) to take stock of similar national platforms among EU member states and at EU-level (such as climateADAPT) and provide recommendations for the national adaptation platform, (ii) to identify knowledge gaps and communication issues among Turkish stakeholders, and (iii) to identify international and national networks and online platforms and libraries of relevance and interest. |  | A desktop review and meetings with related stakeholders | December 2023 (Completed) | Completed. |
| Activity 3.3.2. Software design, test runs and maintenance of the platform, including key components such as: FAQ, contact list, publication and activity database, search function, metadata download and report/map making services. |  | The initial version of the architecture and design of the platform | October 2023 (Completed) | The initial version of the architecture and design of the platform were developed and improved. |
| Activity 3.3.3. Content upload to the platform (publications, reports, media, etc.) and links with relevant networks and online platforms. |  | Content upload | Q32025 (Completed) | Data entry was completed. The project website has been integrated within the determined section of Climate Portal as per DCC demand. |
| Activity 3.3.4. Media launch and technical presentation of the platform to key stakeholders; presentation of climate change adaptation work per sector and development of sector specific infographics and presentation material; organization of two public events (i.e. contest, exhibition) on climate change adaptation work. Media launch will be in Ankara with participation of 200 people. | Media launch |  | November 2024 (Completed) | Completed in November 2024. |
| Activity 3.3.5. Regular evaluation of the efficiency and effectiveness of the platform and its use for the NASAP, for sector specific climate change adaptation and for urban climate change adaptation through an annual web-based survey | Web based survey |  | Q3 2025 (Completed) | It has been increased through the official letters sent to the institutions. Menti questions were applied before and after the training to evaluate the efficiency of the training. Post-evaluation forms were applied during the training and the conferences to evaluate the competency. Please refer to Annex XXX for Software Developement Expert reports for details of the system. |
| Closure Event | One day event |  | October 2025 | 321 people has attended to the meeting conducted in Ankara for one day on 3 October 2025. Following the opening speeches, a presentation which summarizes the project activities and topics was held, and a panel session titled “International Climate Change Adaptation Platforms, Data Collection and Monitoring Methods” completed. In the afternoon, another panel session titled “Climate Law and Climate Change Adaptation and Sustainability” was held. Following completion of the panel sessions, information regarding the final evaluation of the project and the roadmap has been shared. |

### Grant Management

The Climate Change Adaptation Grant Programme (CCAGP) was opened as of 14 October 2020 and closed for applications as of 28 December 2020. Applications were received between these dates and the evaluation process for concept notes was completed as of March 2022.

Following the completion of evaluation process for concept notes, information days for the candidates who are eligible to submit a full application were organized on 22 and 23 March 2022 and related training report with its annexes was submitted on 1 June 2022 and approved by ER on 29 August 2022. English translation of the approved report was approved by ER on 18 January 2023.

As per the meeting held on 28 May 2022 with the CA, a draft MIS was established and shared (website https://mis.iklimeuyum.org/ ) on 21 October 2022 and comments from the CA were received on 25 January 2023. The system was updated accordingly. Another meeting was held on 24 March 2023 with the participation of the ER, CA and EUD to discuss features of drafted MIS.

After the approval of the addendum, the Grant Programme Experts were mobilized and started to carry out the 1st round of monitoring visits.  1st round monitoring visits started in March 2024 and completed in July 2024. The 2nd round of monitoring visits was started in August 2024. It was completed in February 2025. The general reports and risk assessment studies regarding the second monitoring reports were prepared. Grant beneficiaries are supported during grant visits. Beneficiaries' questions regarding implementation, notifications, reports, visibilities addendums and many other subjects are also answered through MIS. Consultative meetings were also used as a tool for the communication activities for grantees.

Interim reports of grant projects were received. Checklists were prepared to support the assessment of technical and financial reports by DCC and CA. The checklists were prepared and followed up on MIS. All hard copy interim reports submitted to the DCC by the Grant Manager were reviewed, and both financial and technical checks were carried out. The checklists prepared were uploaded to the MIS following the approvals of the TAT and the DCC through the MIS. In addition, the Final Reports submitted via the MIS before the expiration of the TAT contract were also reviewed, and feedback was provided to the Beneficiaries. 11 spot-checks have beenorganized for the grant projects, whose selection was made based on the risk assessment of the projects (see Annex XXX).

Several meetings were convened with the MIS expert and CA to finalize the Monitoring & Evaluation and Reporting modules of the system. The MIS wasupdated and  revisions requested by the CA, TAT and DCC have been incorparated. An indicator follow-up module has been developed. Overall project indicators and grant projects' indicators have been linked, and outcome of the 2nd monitoring results were also be uploaded to MIS. Screen modules for these reports were designed.  The support for maintainance and relevant updates provided till the end of the project since it is a routine process that should be carried out as long as the project is implemented. Some modifications on the monitoring and evaluation module has been requested by DCC and CA, related revisions will be reflected to the system. The MIS system handed over to the Contracting Authority before the end date of the project implementation period (see Annex XXXX). The progress in the activities related to the grant programme within the reporting period is presented as follows:

| Activity | Expected Outputs/Deliverables | Estimated Completion Time | Remarks |
| --- | --- | --- | --- |
| Activity 3.4.1. A desk review (i) to take stock of existing climate change adaptation grant programs among EU member states and countries with similar socio-economic profiles, such as EU’s LIFE funding and (ii) to evaluate ongoing grant programs and their mechanisms at national and local level for similar target audiences. The findings will guide the identification of activity scope and eligibility criteria for applications. | Desk review | 15 July 2020 (completed) | Approved on 30 November 2020 and submitted officially within the scope of the 1st Progress Report. |
| Activity 3.4.2. A training module on managing grants for the MOEUCC/DGEUFR staff and 2 one-day training session covering: The first training* will be on “Grant Scheme Implementation Process” including guidelines development, launch, evaluation and contracting. The second training** will be on “Grant Projects Management and Monitoring” including implementation rules, contract management and monitoring and evaluation. Training sessions will be held in Ankara, 20 people in total are expected to receive the training. | 2 Training modules (i)Grant Scheme Implementation Process (ii)Grant Projects Management and Monitoring 2 1-day trainings | i) May 2021 ii) February 2022 (completed) | The first two sessions were conducted as a half-day on 24 and 25th December 2021 with participation of 42 people. The training Report was submitted on 18 January and approved on 2 February 2022. The translation is submitted as an attachment to this Activity Report. |
| Activity 3.4.3. A set of guidelines include (i)Grant guidelines and the application package (ii)* Evaluation manual and annexes(iii) **Grant implementation manual, procurement manual, visibility manual and annexes and (iv)** Monitoring manual. | Set of guidelines | August 2021 (Completed) | Monitoring Guideline and its annexes were submitted on 6 April 2021. Turkish translation of Grant Implementation, Visibility, Procurement and Monitoring Guidelines were submitted on 21 June 2021. Comments on translations of other guidelines such as Evaluation Manual received on 23 August 2021; revised guidelines were submitted on 31 August 2021. |
| Activity 3.4.4. A training module on the use of the guidelines and 12 one-day training sessions to relevant stakeholders from public, private, academia and civil society. Training sessions will be held in Ankara and the pilot cities, 1,000 people in total are expected to receive the training. | Training Sessions | March 2022 (completed) | 2 one-day training sessions were held on 22 and 23rd March 2022 for second step applicants. |
| Activity 3.4.5. A web-based grant management information system (MIS) for grantees to follow up their notification/amendment requests for grant projects, share project deliverables, reporting inputs for M&E, and visibility. The system will also be used for conducting interim and final evaluations of grant projects by MOEUCC/DGEUFR. | Web-based grant program | September 2025 (Completed) | A module was developed for notifications and amendments. The system is in use for the grant beneficiaries, DCC and CA for project deliverables, reporting inputs and visibility. An indicator follow-up module has been developed. Overall project indicators and grant projects' indicators have been linked, and outcome of the 2nd monitoring results were uploaded to MIS. Screen modules for these reports were designed. Monitoring and Evaluation and Reporting modules were integrated. The system was also updated/developed in line with the CA and DCC requests. Reporting cycle defined in the MIS has been revised by the tailor-made approach to the CA requests. The hand-over stage of the source codes of the system is completed. Please refer to Annex XXX for the official letter of the handover |
| Activity 3.4.6. One day event in Ankara (such as Grant Programme Fair/Infoday etc.) with 150 participants (40 people from outside of Ankara) and Two-days hybrid grant reporting training in Ankara will be delivered with the participation of 50 participants in hybrid means (including grantees, MOEUCC/DGEUFR and DCC. 26 people will be attending outside of Ankara Province. Training aims to deliver the reporting procedures (administrative and financial) to the Participants. | Opening and closure event | September 2025 (Completed) | This activity was changed to a 2-day reporting training through Notification No. 13 and a Grant Fair- Info Day replaced the closing event. 261 people has been attended to the event. Please refer to Annex XXX for details of the event where several panel discussions and presentations have been conducted. |
| Activity 3.4.7. Technical and administrative assistance during grant application design, daily grant implementation, preparation of necessary implementation documents and letters (MOEUCC/DGEUFR is accountable for the execution of the grant contracts per se) and review, including monitoring visits. After the award of the grant contracts, a risk assessment and monitoring programme for the grant programme will be prepared in alignment with the MoEUCC. The number of monitoring visits will be planned accordingly; however, for calculation purposes in the budget, it is envisaged that 2 monitoring visits for each project and 1 spot check will be done for risky projects as per need of DCC or CA. 1 expert from the MOEUCC Directorate of Climate Change and the Grant Manager /Experts will attend each visit. There could be additional staff to these visits, such as staff from Contracting Authority and the EUD; however, only costs of visits for 1 expert from the MOEUCC Directorate of Climate Change and the Grant Manager will be covered from the project budget. A monitoring report will be prepared for each project after each monitoring visit and submitted to the Beneficiary, Contracting Authority and the EUD no later than 1 month after completion of each monitoring visit. | Technical support + monitoring visit reports | September 2025 (Completed) | Technical assistance has been provided since October 2020. Grant Programme Experts regularly checks the MIS system for determining the questions pending for response, notifications and change requests of Grant Beneficiaries. - Answering the questions by getting in touch with the Beneficiaries if needed. - Determining the notification requests of the Grant Beneficiaries. - Processing the requests by completing the necessary supporting documents and checklists. - Making the requests ready for the approval of the Contracting Authority. The 1st round of monitoring visits has been completed. The general evaluation report has been prepared and submitted to all parties; the report was approved on 27 June 2024. The report includes the following information: - An executive summary, - Detailed findings, - Conclusions - Recommendations - Risk Assessment The 2nd round of monitoring visits was completed in February 2025. 29 projects have been visited. A comprehensive report summarizing the overall situation regarding grants was prepared. A risk Assessment Study based on the 2nd monitoring reports were prepared. The below listed content was also covered by the 2nd monitoring report. The 3rd round of monitoring visits has been changed to on-the-spot visits for the grant beneficiaries that need extra attention in their implementation when deemed necessary by the parties. 11 spot checks were finalized by June-July and August 2025. Please refer to Annex XXX for all monitoring visit reports and Anex XXX for risk assessment report |
| Activity 3.4.8. Establishment of an M&E system including: (i) definition of metrics for documenting progress, measuring and communicating levels of effectiveness, (ii) an online M&E system for the Contracting Authority that encompasses the identified set of indicators in grant projects and will require all involved stakeholders to report into and (iii) regular reviews of activities undertaken as part of the grant. | M&E System | July 2025 (Completed) | The M&E system has been developed, and the indicators of the grant projects are currently compiled by the grant experts. Project indicators were entered into the MIS. The outcomes of the 2nd monitoring visits in terms of indicator realizations were updated. Monitoring Reports also uploaded to the system. The system enables encoding the project progress level based on the interim and final reports, as per indicators. Some minor revisions/modifications realized to the system and the system handed over to CA. The modifications on the indicator tracking module have been made based on the study that was conducted by a project key expert. Key expert reviews the coding links defined for the program and grant project indicators and the system updated based on experts’ analysis (see Annex XXX). |
| Activity 3.4.9. Monitoring and Evaluation system and MIS will be used to measure the progress of grant projects in terms of realizing their activities, targets, indicators indicated in the grant projects. | Measures of grant projects | July 2025 (Completed) | The module included in the MIS system regarding to measure the progress at project indicators level. Some minor modifications was integrated into system based on the requests of DCC and CA. |
| Activity 3.4.10. 4 one-day consultative meetings throughout the course of the grant program to exchange information, assess progress and encourage collaboration among grant nominees. Meetings will be held in selected cities close to awarded grants, 40 to 50 representatives are expected to attend each meeting in hybrid means to be more inclusive and ensure effectiveness | 4 consultative meeting | September 2025 (Completed) | The 3rd Consultative Meeting was organized on 17 June in Antalya. The meeting was attended by 19 participants in person, and 57 online. The 4th Consultative Meeting was organised on 28 August 2025 in Antalya. The meeting was attended by 22 participants in person, and 66 online. Please refer to Annex 18 for the meeting agenda, attendance and presentations. |
| Activity 3.4.11. A report on lessons learned and a dissemination strategy of grant activities for all grant projects. | Lessons Learnt | September 2025 | A lessons learned report prepared following the 3rd consultative meeting. This report was integrated into the compendium document. A brochure has been prepared in Turkish and English. The Turkish and English versions are available on the project website. Newsletters covering the news about the grant visits are prepared (Annex 05). The reports were written regarding the outcomes and analysis of the 1st and 2nd monitoring visits. 4 videos featuring the stories of 8 grant beneficiaries have been finalized and published on the website. The shooting of 5 projects had been realized during the 3rd consultative meeting by the end of interviews with the project representatives. 4 videos covering 5 grant projects prepairede and they were published on the web site.. For the rest of the 15 grant projects one long vide prepared . The inputs of these videos have been mainly collected from the interim reports and grant beneficiary feedback collected through e-mails, MIS documents, etc. The videos covering all the 28 grant projects (1 grant contract terminated) have been presented to the DCC and CA and following their approval all of them published at the web site. |
| Activity 3.4.12. A compendium and a short documentary video for the grant programme, which consists of the outputs, results, achievements, and lessons learnt of the grant programme including all grant projects. | Compendium and a short documentary video | September 2025 (Completed) | Preparing a compendium document that covers all projects and contains the final data was quite challenging and time-consuming in a programme that has not yet entered the final reporting stage. The data for this document—were being compiled from the information presented in the interim reports and from the visuals and data individually obtained from the grant beneficiaries. Lessons learned report has been compiled to the compendium document. Turkish version of the compendium document printed and handed over to the participants during the Gant Fair and Info Day. Both English and Turkish versions are available at the project web site. During the 1st and 2nd consultative meetings, interview videos were recorded with grant beneficiaries. These videos have been used as an input for the short videos of 13 grant beneficiary. A vshort ideo covering the overall grant programme has been prepared. One longvideo prepared for the 15 grant beneficiaries a. In this way, videos was produced for all 28 projects under implementation and shared on the website. Please refer to Annex XXX for short documentary videos Please refer to Annex XXX which also disseminated during 25 September Information Day. |
| Activity 3.4.13. Support in communication activities of grant beneficiaries. | An online workshop | September 2025 (Completed) | Support to grantees for their communication activities was anongoing process that was continued until the end of the project. Grant beneficiaries are supported through the MIS questions module and during grant visits. Beneficiaries' questions regarding implementation, reporting, notifications and addendums are also answered through MIS. This was a continuous activity of the Grant Programme and beneficiaries supported until the end of the project. Reviews and controls were continued with the grantee reports and TAT comments shared with the beneficiaries to reach a mature and correct report submission status. Consultative meetings were also used as a tool for the communication activities for grantees. |
| Activity 3.4.14. Carry out portfolio level outreach and communication activities of the grants programme. | Outreach and communication activities | Q2 2025 (Completed) | A grant brochure was prepared and shared the Directorate of Climate Change’s website and UNDP Türkiye’s social media accounts. The English version of the brochure was also prepared (Annex 5). They were also handed over during the consultative meeting that was held in İstanbul 18 March 2025 and grant fair- info day event. Newsletters covering the news about the grant visits are prepared. The videos featuring the stories of grant beneficiaries have been finalized and published on the relevant social media sources. All related program visibility outputs were published on the project web site. |

## Risks and Risk Mitigation

As the project advanced, it was critical to continuously reassess and manage the risks and assumptions that might influence the achievement of the project objectives. During the previous reporting period, a detailed evaluation has identified new risks that could impact the project’s timeline, and overall success. These emerging risks, in conjunction with those previously recognized, had necessitated the development of robust mitigation strategies to ensure the project remains on course.

One significant risk that had been identified pertained to the potential delays in meeting the project’s activity deadlines, which could be classified as a high-risk factor. This concern arised primarily due to the timing of key project milestones: the first Addendum was approved in February 2024, leading to the subsequent establishment of the Project Management Unit (PMU) under UNDP’s accountable and transparent HR rules. The PMU, on the other hand, was not fully operational until July 2024. Although the pace of activities had been accelerated, there was still a tangible risk that some of the project activities may not be fully completed by the 8 April 2025 deadline considering tight schedule of the activities.

Given the importance of adhering to the project timeline, it was crucial that we acknowledge this risk and take proactive steps to mitigate it.

Grant projects implemented under the Climate Change Grant Programme started in December 2023. The end date of most grant projects was June 2025. This timing constraint means that the evaluation of final reports, compendium and report on lessons learnt would not be possible to be conducted comprehensively during the project's implementation period. In addition, regular support to grant projects via MIS and phone/email would not be possible after April 2025.  In the event of project closure in April 2025, planning for the continuation and sustainability of grant projects would be necessary.

Therefore, the second Addendum was prepared for the 6 months of extension of the project, and it was officially approved on 9 April 2025. With the approval of the second Addendum, the project completion date was changed to 8 October 2025.

### Risk Table

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Risk event: Appearance of a new viral infection Risk cause: Declaration of coronavirus (COVID-19) outbreak as a pandemic Risk impact: Delivery of results may be affected negatively. Meetings/ trainings/workshops, may not be realized within the scope of the projects in the planned dates | 09-Nov-2021 | Environmental (Community health, safety and security) | Impact: 4 Probability: 3 Risk Level: Substantial | The project team had been conducting online/hybrid events to minimize community transmission and to continue organizing consultative meeting, and trainings although there were lack downs. Although there had to be some adjustments to the project’s annual work plan as a result of the pandemic, no major challenges have been encountered to this date. The project team continued to follow the advisory of the Government and UNDP and ensured that the risk kept minimized. | UNDP | 31-Dec-2021 | Closed |
| 2 | Risk event: In the case of new restrictive measures imposed by the government due to a new variant of the COVID-19 pandemic Risk cause: Meetings/trainings/workshops may not be physically held or may be held in a hybrid manner within the scope of the project in the planned dates. Risk impact: Pandemic conditions may affect project workplan more than expected. Such effects can be too catastrophic to continue project activities | 01-Dec-2021 | Environmental (Community health, safety and security) | Impact: 3 Probability: 2 Risk Level: Low | Official travels, meetings, and consultations within the institutions, attendance to meetings/workshops were postponed until the normalization period begins. Meetings and events could be conducted via online meeting tools when possible. Study visits were transformed into virtual tours and presentations when necessary. | UNDP | 16-Aug-2024 | Closed |
| 3 | Risk event: Possible delays may cause extended durations Risk cause: Delays in tendering process for Grant Programme due to prolonged review/evaluation durations Risk impact: Inability to complete activities within the current deadline | 01-Dec-2021 | Operational (Responsiveness to audit and evaluations (Delays in the conduct of and implementation of recommendations)) | Impact: 3 Probability: 4 Risk level: Moderate | Elevation of the issue to higher level managers through the PSC and OCU meetings had been utilized to address and mitigate this risk. Close coordination between the PSC and technical team was assured by Operation Coordination Unit (OCU) for proactive management of risks and outside factors. With the second Addendum that was officially approved in April 2025, the project was extended to 8 October 2025. | Contracting Authority | 21- Sep--Aug-2025 | Closed |
| 4 | Risk event: If the government ownership will be low and institutional coordination will not be effective timely implementation of the regulations will be affected. Risk cause: Insufficient institutional coordination at national and local level to effectively implement key policies and regulations on climate change adaptation Risk impact: Ineffective implementation of regulations. | 16-Jan-2020 | Strategic (Stakeholder relations and partnerships) | Impact: 3 Probability: 2 Risk Level: Low | The overall strategic direction of the project provided by a Project Steering Committee (PSC), consisting of representatives of the MoEUCC/Presidency of Climate Change, the contracting authority (MoEUCC/DGEUFR), UNDP and the relevant members of the CBCCA and other stakeholders when deemed necessary. While this multi-sectoral structure would enhance the coordination among institutions at several levels, it was also planned to specifically promote an inter-sectoral coordination mechanism, which would serve as the primary mitigation measure to this risk. During the implementation period, coordination among national and urban level wereenhanced through National Adaptation Platform that was established by the Project. Coordination was established through regional meetings, workshops and consultation meetings. In addition to those efforts, Strategy and Budget Office (SBO) of the Presidency joined the PSC meetings as a natural member to assist coordination and governance function. | Beneficiary | 21-Sep-2025 | Closed |
| 5 | Risk event: Lack of close coordination Risk cause: Factors outside the control area of the Project Risk impact: Insufficient output-outcome linkages | 16-Jan-2020 | Strategic (Government commitment) | Impact: 3 Probability: 2 Risk Level: Low | The PSC would operate several functions where verifying the achievement of the outputs and results of the project is the main one as a primary mitigation measure to this risk. Close coordination between the PSC and technical team were assured by Operation Coordination Unit (OCU) for proactive management of risks and outside factors. The OCU meetings were formed by the MoEUCC/Presidency of Climate Change representative, technical assistant team (TAT) and Contracting Authority (when necessary) and meet monthly basis to effectively manage the progress of the projects to take corrective measures deem necessary. Following the establishment of National Adaptation Strategy and Action Plan, the PSC members submitted the strategy to higher planning council, in coordination with the SBO, for approval. | Government | 21-Sep-2025 | Closed |
| 6 | Risk event: No adequate and sufficient data collected Risk cause: Lack of data at national and urban level for detailed analysis Risk impact: Lack of data will effect the level of analysis | 16-Jan-2020 | Operational (Knowledge management) | Impact: 2 Probability: 3 Risk Level: Low | The lack of high-quality data and information was highlighted by NASAP along with other challenges such as lack of concordance of available information, the insufficiency of scientific research, difficulties in producing projects, determining the effects of climate change at sector and urban context. Since then, there were several studies undertaken by academia focusing on paleoclimate studies, modelling and prediction including general circulation models, climate change impacts and response options, research and development on mitigation and adaptation technologies. As highlighted by the Climate-Adapt, there were over 60 projects and nearly 170 theses carried out in Türkiye. Expert judgment and literature are thoroughly utilized to compensate for the lack of data. The project helped to mitigate this to the extent possible by undertaking stocktaking activities for all outputs in collaboration with ministries, municipalities, research centers, universities and EU institutions. Moreover, the project helped to establish a National Adaptation Platform to facilitate knowledge and expertise sharing and networking while providing information on climate impacts and adaptation information, adaptation policies, climate data, impact and vulnerability assessments, research programmes, adaptation options, local actions, case studies, etc. | Beneficiary | 21-Sep-2025 | Closed |
| 7 | Risk event: Not enough technical approaches in the field Risk cause: Insufficiently robust technical approaches in the field of climate change adaptation due to lack of experience and know-how at national and urban context in Türkiye Risk impact: Lack of experience will effect the technical approaches and key solutions. There is a risk that some project activities could be delayed or could face unexpected problems due to inadequate technical experience. | 16-Jan-2020 | Operational (Accountability) | Impact: 4 Probability: 2 Risk Level: Moderate | Although Türkiye has a number of high-quality academic institutions and many highly qualified scientists, the field of climate change adaptation is still essentially a new realm of building resilience at national and urban context in Türkiye. Therefore, in this project there was little direct experience with real-world implementation of many of the technical aspects of climate change adaptation activities that would be necessary to achieve the project objective. Therefore, there was a risk that some project activities could be delayed or could face unexpected problems due to inadequate technical experience. The project helped to mitigate this by ensuring that the project draws on the best international and EU practices known that were relevant for the Turkish context. For example, conducting conferences and seminars with invited international experts. The project helped to y undertake study tour activities to other EU countries and institutions with more extensive experience in this realm, as long as they are relevant for the Turkish context. Moreover, the project helped toadopt the latest assessment report of the IPCC (AR5) on the definition and framework to propose a risk and vulnerability assessment (RVA) for cities. | Beneficiary | 21-Sep-2025 | Closed |
| 8 | Risk event: Turnover in government/local administrations staff due to reshuffling or elections Risk cause: Slowdown in administrative processes and inadequate stakeholder and technical expertise engagement related to potential institutional change. Risk impact: Prolonged output review and approval durations, slowed down grant implementation and delayed high-level visibility events | 16-Jan-2020 | Strategic (Change/turnover in government) | Impact: 3 Probability: 4 Risk Level: Moderate | Addressing climate change adaptation in a comprehensive manner requires involvement of multiple national institutions, as well as coordination at the field level. The project had built specific mechanisms to support this coordination and interaction. However, there was a high turnover rate in Türkiye in government/local administrations staff. In this context of institutional change, it might be difficult for the project to effectively engage all necessary stakeholders and government experts during project implementation. The project had been continuously monitoring this risk and taking adaptive management measures as necessary if this risk appears to negatively affect the project’s operational approach and effectiveness. Eventually, the new staff and administrators were engaged effectively to be integrated into the project management structure. | Beneficiary | 21-DSep-2025 | Closed |
| 9 | Risk event: Climate change may affect ecosystems in the Country more than expected. Risk cause: Climate change affects Türkiye’s ecosystems and socio-economic systems in a manner that overwhelms the project efforts. Risk impact: Such effects can be too catastrophic to continue project activities at national and urban level. | 16-Jan-2020 | Environmental (Climate change and disaster risks) | Impact: 2 Probability: 2 Risk Level: Low | There is no question that climate change is occurring and affecting Türkiye’s ecosystems, and socio-economic systems. Such effects can be too catastrophic to continue project activities at national and urban level. Nonetheless, the project helped to mitigate this risk by tracking some climate change risk indicators (e.g. floods, forest fires, etc.) and helped to assess when climate change was leading to any catastrophic changes in relation to the project activities. If it was identified that catastrophic changes were occurring, the project would re-direct and re-plan project resources and activities, as appropriate, to address these challenges in close consultation with the MoEUCC and the EUD. The PSC made any decision along these lines, with technical input from the project Technical Assistant Team. | Government | 21-DSep-2025 | Closed |
| 10 | Risk event: Delays in Project Activities Risk cause: the late approval of the project addendum in February 2024 and the delayed operationalization of the Project Management Unit in July 2024, resulting in a compressed timeline for completing activities. Risk impact: Failure to complete project activities with fully effective manner on time may result in unmet project objectives and goals | 12/08/2024 | Operational (Implementation Arrangements) | Impact: 3 Probability: Risk Level: Moderate | The risk of project delays is primarily caused by the late approval of the project addendum in February and the delayed operationalization of the Project Management Unit in July 2024, resulting in a compressed timeline for completing activities. To address the risk of delayed project activities, the project team will implement an accelerated work plan, prioritizing critical tasks to ensure timely completion of key deliverables. Additionally, regular communication with stakeholders maintained to manage expectations and provide updates on progress. Another important not be able to provide good quality of translations which usually takes months, is also a critical task under this risk. The documents that were presented as a result of this project, presented in international areas and social media, therefore; the correct terminology and effective translations are highly critical. The draft translation presented by October 2025, but the finalized version of the translation added as Annex of the Final Report of the project. | UNDP | 12/08/2024 | Closed |

### Plans for the next coming period

A Project Steering Committee Meeting held on 8 October 2025 to discuss Project timeline (AWP), ongoing activities, future planning and etc. In the meanwhile, project activities completed. In addition, the AWP activities have been revised in accordance with the adjustments introduced under Addendum 2. The revised AWP is provided in Annex 4.

## Project Management and Coordination Activities

### Building Up Management Structure and Exercising Its Functions

UNDP as the Organization is responsible for the efficient and effective implementation of the project through the Contribution Agreement concluded with the MoEUCC – DGEUFR Department of European Union Investments (DoEUI) acting as the Contracting Authority on behalf of the EU. MoEUCC- DGEM is the End Recipient of the Project. There is not any deviation in the implementation arrangements of the project that is described in the Description of Action (DoA).

As indicated in the DoA, the Project has a two-layered structure for the project coordination, namely; PSC overseeing the overall implementation of the Project and provides strategic guidance, and OCU. The frequency of PSC meetings is determined on a bi-annual basis, whilst OCU Meetings are on a monthly basis.

### Complying Obligations Regarding Information and Reporting

UNDP complies with all the obligations regarding information and reporting as indicated in the DoA. All aspects of the project implementation since the initiation of the project have been reported to the CA, ER and EUD through the annual Progress Reports and biannual Activity Reports.

### Running Control and Evaluation Mechanisms

Monitoring and evaluation (M&E) exercises undertaken in compliance with the provisions of the Financial and Administrative Framework Agreement (Article I. Focus on results) and the General Conditions (Article 10. Monitoring and Evaluation of the Action). The expected results, activities, objectively verifiable indicators, sources of verification, and assumptions listed in the Logical Framework constitute the basis of the Project's M&E system. It was further refined during the Inception Phase. The Organization continuously tracks the progress of the project based on the agreed indicators and all reporting carried out accordingly. Indicators are based on objectives that are specific, measurable, attainable, realistic, and time-based. Indicators for the contribution-specific agreement are linked to the more general indicators relevant for the whole Action, wherever possible.

EUD representatives shall be invited to participate in the main monitoring and evaluation missions. The results of M&E exercises shall be reported to the MoEUCC and the EUD. Moreover, as far as possible and appropriate, UNDP and the EUD will explore carrying out jointly the M&E activities.

The Project evaluated (technical evaluation) independently. The assessment on the substance and immediate concrete results of the Project, and will, by no means, include any form of expenditure verification (or Audit), etc. As a result of the assessment, the impacts of the results achieved, lessons learned and good practices in terms of substance assessed in a report. Besides, the level of communication and visibility, as well as recommendations for sustainability, gender equality aspects, also be explored in the said assessment.

#### M&E Plan of the Project:

| Name of Report | Time of submission | Recipients |
| --- | --- | --- |
| Inception Report (Turkish & English) | Within 4 months of commencement of the Project. | MoEUCC & EUD |
| Activity Report (Turkish and English) | Two weeks before each Steering Committee Meeting, to summarize all completed activities within the period covered for the Steering Committee supported with annexes and the planned activities for the next coming period, if applicable. | MoEUCC & EUD |
| Progress Report (Narrative and Financial) (Turkish & English) | Within 60 days after the period covered by such report. (as per Article 3.9 of the General Conditions) | MoEUCC & EUD |
| Final Report (Narrative and Financial) (Turkish & English) | Not later than 6 months after the end of the implementation period of the Project (as per Article 3.9 of the General Conditions) | MoEUCC & EUD |

The project results as outlined in the project results framework are monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.

Project-level monitoring and evaluation undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. While these UNDP requirements are not outlined in this project document, the UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. To follow closely on the projects, its results and achievements, UNDP regularly carries out internal M&E activities through the ‘Logical Framework Table’ updated regularly during the course of the year.

A draft term of reference has been prepared and under the review of all parties. An international independent consultant recruited to review the project indicators and results.

#### Project Audit

The latest audit was conducted through document review and online meeting by Mr. Vadim Kuzyk from ROM in Türkiye Phase III Monitoring of IPA Projects on 13 August 2021, and the audit result was conveyed through 4th AR and 2nd PR. Project progress has been scored as good/very good -in terms of relevance, efficiency, effectiveness and sustainability- in the ROM mission report received on 20 September 2021.

In line with the Financial and Administrative Framework Agreement (FAFA) and the General Conditions, the financial transactions and financial statements shall be subject to the internal and external auditing procedures laid down in the Financial Regulations, Rules and directives of UNDP. The project audit  carried out in line with UNDP’s policies.

Final evaluation of the project has also been completed as of October 2025. One to one independent interviews have been conducted between the instituitons and the evaluator. The inception report and the final evaluation report can be found in Annex XXX. All reports prepared by the evaluator have been shared with all partners by UNDP via e-mail. No comment was received from partners.

## Methodology

There is no significant change in the methodology, as per the DoA.

## Logical Framework

An updated copy of the logical framework was submitted with the Fourth/Fifth Progress Report. There have not been any changes to the latest logical framework during the reporting period.

### Current Anticipated Problems, Planned Remedial Actions and Lessons Learned from Encountered Problems

On 6 February 2023, a devastating Mw 7.7 earthquake struck southern and central Turkey, followed by a Mw 7.6 earthquake a few hours later. These disasters led to widespread damage and tens of thousands of fatalities. Because of the earthquakes, the Project’s timelines and agendas regarding the media launches and other interconnected activities have also been impacted. Key personnel from the MoEUCC have been temporarily reassigned to disaster relief efforts, which has led to lessened focus on the implementation of project activities. Furthermore, the affected regions may now require additional environmental assessments and remediation efforts, which may further affect the Project’s timeline.

To address these challenges, the project team adjusted project timelines to account for the reallocation of key staff members and the potential need for additional environmental assessments in the affected areas. Since the emergence of the COVID-19 pandemic, the established contingency plans also have been ensuring the Project remains on track, despite unforeseen circumstances and potential future disruptions.

Lessons learned from the problems encountered include:

- The importance of having a robust risk management plan in place to address unforeseen events, such as natural disasters, and their potential impact on the Project’s timelines and objectives.

- The need to maintain open and transparent communication with all Project stakeholders to ensure they are informed of any changes in the Project's progress and any necessary adjustments to the Project’s goals or timelines.

- The value of establishing strong partnerships with stakeholders to ensure the implementation of the Project is not affected dramatically particularly in times of crisis.

Moving forward, the project team will continue to monitor the situation and adapt its plans and strategies as necessary to ensure the successful implementation of the project's objectives.

Additionally, as conveyed in previous reports, considering the extended application deadline, delay occurred during the evaluation process and duration of the grant projects as 12-18 months, the implementation period of grant projects beyond the completion date of Enhancing Adaptation Action in Turkey Project and there was a necessity for the extension of Project’s implementation period. Accordingly, a request for 24-months of extension of the project duration was submitted on 19 July 2023.  Until the new addendum was approved, the project was suspended.  A new Addendum was submitted for 18 months of extension and approved as Addendum No:1 in February 2024. During this period, a new Addendum No. 2 request has been submitted together with Annexes as of 17 February 2025. Please see the details in Annex 05.

On 9 May 2024, an early warning letter was received from the Contracting Authority about delay of project activities. A comprehensive response including detailed project current updates and updated work plan was submitted to CA on 27 May 2024. The Project learned that the scheduling of grant components must take into realistic timeframes for tender processes. In this sense, during the meetings and e-mail communication, UNDP has suggested merging several activities which have the same target audience and province in order to save time and ensure tight planning.

There is a risk of the unsatisfactory performance of already contracted consultants that may occur during the delivery of activities.  This situation may result in activities not being completed in full.

Please find the updated workplan in Annex 04 which was also submitted as an Annex to Addendum No 2.

Following a one-year period without a Head of Adaptation to Climate Change and Local Policies Department, the appointment of a new Head at the end of August 2025 has enabled the introduction of more standardized, inclusive, and solution-oriented management practices. This development is regarded as an important lesson learned and holds particular significance for the effective implementation of forthcoming DCC projects.

Due to limited human resources utilized to TAT, the management of a substantial number of remaining activities and the associated budget/delivery processes created significant operational constraints. To address these issues, ensure efficient resource allocation and timely communication of the activities, the Project Manager proposed an eight-month extension; however, the request was not approved by partners, considering the other priorities. Therefore, UNDP has submitted the no cost extension in March 2025 for 6 months.

### Project Indicators

The progress towards achieving targets of the project is given in table below

|  | Intervention logic | Objectively verifiable indicators of achievement | Baseline (2019) | Milestone (2021) | Target (End of Project) | Sources and means of verification |  | Assumptions |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Objectives | Build societal resilience by strengthening climate change adaptation, particularly at sector and urban level, with strategies, tools and financing | ▪ Increased awareness of climate change impact among ministries and local authorities |  |  |  | ▪ European Commission’s Regular Reports ▪ European Environment Agency’s State of Environment Reports ▪ Statistical data on environment and climate change ▪ Progress in the implementation of Sector Operational Programme: Environment and Climate Action ▪ Progress in the implementation of National Action Plan for EU Accession ▪ Progress in the implementation of Multi-Annual Action Programme for Türkiye on Environment and Climate Action ▪ Eight National Communications to the UNFCCC |  | ▪ Institutional coordination at national and local level to effectively implement key policies and regulations on climate change adaptation is sufficient. ▪ Factors outside the control area of the project have manageable impact on the output-outcome linkage. ▪ Data at national and urban level is sufficient enough for detailed analysis. ▪ Robust technical approaches are sufficient in the field of climate change adaptation at national and urban context in Türkiye. ▪ Stakeholder and technical expertise engagement are adequate. ▪ The Project has no negative impacts to critical habitats or environmentally sensitive areas. ▪ Climate change does not affect Türkiye’s ecosystems and socio-economic systems in a manner that overwhelms the project efforts. |  |
|  |  | ▪ Reduction of direct disaster economic loss in relation to global GDP, damage to critical infrastructure and number of disruptions to basic services, attributed to disasters |  |  |  |  |  |  |  |
|  |  | ▪ Increase in resilience among key sectors and selected cities |  |  |  |  |  |  |  |
|  |  | ▪ Improved cooperation between national and local stakeholders on climate change adaptation |  |  |  |  |  |  |  |
|  |  | ▪ Increased availability of decision-making tools and planning solutions to enhance society resilience and reduce adverse effects of climatic events |  |  |  |  |  |  |  |
|  |  | ▪ Communication of the establishment or operationalization of an integrated policy/strategy/plan which increases national ability to adapt to the adverse impacts of climate change, and foster climate resilience and low greenhouse gas emissions development in a manner that does not threaten food production (including a national adaptation plan, nationally determined contribution, national communication, biennial update report or other |  |  |  |  |  |  |  |
| Specific Objective | Establish an enabling environment for climate change adaption in Türkiye by developing the policy, technical and operational baselines, including (i) better decision-making tools for national climate change adaptation policies, (ii) urban adaptation planning solutions (urban adaptation strategies and action plans), (iii) capacity building and networking activities for climate change adaptation with the EU and the international community, and (iv) a climate change adaptation grant programme to implement climate change adaptation action | ▪ Entry of updated National Adaptation Strategy and Action Plan (NASAP) into force | No | No | Yes | ▪ European Commission’s Regular Reports ▪ Statistical data on environment and climate change ▪ Updated and published NASAP ▪ UASAPs for four pilot metropolitan municipalities ▪ Adaptation action reports under CCAGP ▪ Monitoring Reports ▪ Project Progress Reports ▪ Project Final Reports ▪ Project Evaluation Reports |  |  |  |
|  |  | ▪ Entry of Urban Adaptation Strategy and Action Plans (UASAPs) into force | No | No | Yes |  |  |  |  |
|  |  | ▪ Number of officials at national and local level with improved climate change adaptation knowledge and technical skills | 0 | 20 | 2878 |  |  |  |  |
|  |  | ▪ Number of national and local tools (e.g. software, guidelines) developed to facilitate climate change adaptation | 0 | 1 | 8 |  |  |  |  |
|  |  | ▪ Number of entities benefiting from grant programme | 0 | 0 | 75 |  |  |  |  |
| Expected Results | Result 1. Develop better decision-making tools for climate resilient sustainable development | ▪ Number of sectors with planning and investment decisions take climate change adaptation into consideration | 0 | 0 | 11 | ▪ Review report of existing studies ▪ Expert report on climate change threats, opportunities, risks and uncertainties ▪ Expert report on climate vulnerabilities for five priority sectors ▪ Expert report on climate financing ▪ Updated NASAP ▪ Monitoring and Evaluation system for the updated NASAP |  | ▪Institutional coordination at national and local level to effectively implement key policies and regulations on climate change adaptation is sufficient ▪Factors outside the control area of the project have manageable impact on the output-outcome linkage. ▪Data at national and urban level is sufficient enough for detailed analysis; ▪Robust technical approaches are sufficient in the field of climate change adaptation at national and urban context in Türkiye ▪Stakeholder and technical expertise engagement are adequate ▪The project has no negative impacts to critical habitats or environmentally sensitive areas. ▪Climate change does not affect Türkiye’s ecosystems and socio-economic systems in a manner that overwhelms the project efforts. |  |
|  |  | ▪ A strategy document (Updated NASAP) developed | No | No | Yes |  |  |  |  |
|  |  | ▪ A finance tool to support implementation developed | No | No | Yes |  |  |  |  |
|  |  | ▪ Number of stakeholder engagement events organized | 0 | 8 | 35 |  |  |  |  |
|  |  | ▪ Number of participants engaging in consultative meetings, workshops…etc. | 0 | 350 | 1000 |  |  |  |  |
|  |  | ▪ A dissemination campaign for raising public and stakeholder awareness | No | No | Yes |  |  |  |  |
|  |  | ▪ Number of reports (e.g. studies, analyses, assessments) developed | 0 | 2 | 110 |  |  |  |  |
|  |  | ▪ A monitoring and evaluation (M&E) system developed | No | No | Yes |  |  |  |  |
|  |  | ▪ Number of trainings delivered (e.g. M&E, adaptation planning guidelines) | 0 | 0 | 15 |  |  |  |
|  |  | ▪ Number of officials/stakeholders trained | 0 | 0 | 345 |  |  |  |  |
|  |  | ▪ Number of training modules produced | 0 | 0 | 2 |  |  |  |  |
|  | Result 2. Develop adaptation and resilience planning in urban areas | ▪ Number of strategies developed | 0 | 0 | 4 | ▪ Review report of existing studies ▪ Expert report on climate change threats, opportunities, risks and uncertainties ▪ Adaptation planning guidelines for five priority sectors ▪ Adaptation planning guidelines for cities ▪ Urban typology framework for Turkish cities ▪ Expert report on urban vulnerabilities for priority sectors in four selected pilot cities ▪ Expert report on climate financing at city level ▪ Financing strategy for UASAP implementation |  |  |  |
|  |  | ▪ A finance tool to support implementation developed | No | No | Yes |  |  |  |  |
|  |  | ▪ Number of stakeholder engagement events organized | 0 | 10 | 28 |  |  |  |  |
|  |  | ▪ Number of participants engaging in consultative meetings, workshops…etc. | 0 | 440 | 840 |  |  |  |  |
|  |  | ▪ Number of reports (e.g. studies, analyses, assessments) developed | 0 | 2 | 17 |  |  |  |  |
|  |  | ▪ Number of dissemination campaigns for raising public and stakeholder awareness | 0 | 0 | 4 |  |  |  |  |
|  |  | ▪ Number of trainings delivered (e.g. M&E, adaptation planning guidelines) | 0 | 0 | 23 |  |  |  |  |
|  |  | ▪ Number of officials/stakeholders trained | 0 | 0 | 200 |  |  |  |  |
|  |  | ▪ A monitoring and evaluation (M&E) system developed | No | No | Yes |  |  |  |  |
|  |  | ▪ Number of training modules produced | 0 | 0 | 2 |  |  |  |  |
|  | Result 3. Develop capacity for climate change adaptation action Result 4. Improve operational capacity for climate change adaptation action through a climate change adaptation grant programme | ▪ A national platform (National Adaptation Platform) developed | Yes | Yes | Yes | ▪ Review report of existing studies ▪ Expert report on climate change threats, opportunities, risks and uncertainties ▪ Expert report on policy and stakeholder capacity and need assessment ▪ Capacity building strategy ▪ Study visit materials, evaluation report and participants list ▪ Training materials, evaluation report and participants list ▪ Dissemination materials for public and stakeholder awareness raising ▪ Annual M&E Reports ▪ Web-based grant programme information system |  |  |  |
|  |  | ▪ A set of guidelines for the grant programme delivered | Yes | Yes | Yes |  |  |  |  |
|  |  | ▪ Number of stakeholder engagement events organized | 0 | 39 | 62 |  |  |  |  |
|  |  | ▪ Number of reports (e.g. studies, analyses, assessments) developed | 0 | 7 | 7 |  |  |  |  |
|  |  | ▪ Number of trainings delivered | 0 | 22 | 43 |  |  |  |  |
|  |  | ▪ Number of training modules produced | 0 | 12 | 12 |  |  |  |  |
|  |  | ▪ Number of officials/stakeholders trained | 0 | 640 | 1751 |  |  |  |  |
|  |  | ▪ Number of officials/stakeholders participating in the study visits | 0 | 100 | 107 |  |  |  |  |
|  |  | ▪ Number of study visits | 0 | 7 | 7 |  |  |  |  |
|  |  | ▪ Number of dissemination materials produced for raising public and stakeholder awareness | 0 | 13 | 15 |  |  |  |  |
|  |  | ▪ Number of participants engaging in consultative meetings, workshops etc. | 0 | 2,909 | 2,738 |  |  |  |  |
|  |  | ▪ Number of tools developed under grant programme | 0 | 2 | 2 |  |  |  |  |
|  |  | ▪ Number of monitoring visits | 0 | 3 (2 monitoring visits and 11 spot check as project budget) | 3 (2 monitoring visits for 29 contracts and 11 spot check as project budget) 69 |  |  |  |  |

## Workplan

The updated workplan was submitted to the ER officially on 31.12.2025 through the submission of Addendum No:2. After minor revisions requested by the ER, Addendum No:2 was submitted to the CA on 07.02.2025 and approved on 07.02.2025. Followingly another revision was requested by the CA and the final version was submitted on 11.02.2025 and approved on 14.02.2025. The official letter submitted to the CA on 18.02.2025. The updated AWP can be found in Annex 04

## Budget

The latest Budget of the Action was considered as conveyed through 4th-5th (combined) PR as Notification No.12, which serves as the budget forecast for the next reporting period (G.C. Article 3.7.i). changes have been made to the Project’s Budget submitted to ER on 31.12.2025 and after the approval on, it is submitted to CA on 17.01.2025 CA approved Notification No:13 on 07.02.2025. Followingly, official letter of Notification No:13 submitted to CA on 11.02.2025.

Afterwards Addendum No:2 has been submitted to CA officially on 18.02.2025. On 09.04.2025, an official letter from CA was sent to UNDP for the approval of Addendum No:2 from EUD. On the same day, all parties signed Addendum No:2 including UNDP and 2 copies submitted to CA. Please see  Addendum No:2 in Annex 05. Following the Addendum process, the minor notifications which were agreed via e-mail or Operation Coordination Unit Meetings are hereby reflected in Annex 20.

## List of Contracts

The latest Individual Contract and National Personnel Service Agreement modalities were conveyed through AR6 and PR3. Contracts have been delivered as of March 2023. Travel and event management services were acquired through UNDP’s corporate Long-Term Agreement with SERENAS and AST companies in the framework of the existing contract conditions (under 60.000 EUR).

| Contract Reference | Contractor | Procedure Followed | USD Contract Amount | Scope of the Contract |
| --- | --- | --- | --- | --- |
| Consultant on Monitoring and Evaluation and Water Resources in the Context of CCA | Adnan Deniz ÖZDEMİR | UNDP’s Rules and Regulations on Procurement | USD 19,000.00 | The main scope of the assignment is to provide a set climate change adaptation indicators, monitoring and evaluation systems, as well as technical inputs to conduct vulnerability assessments, prepare climate change adaptation strategies and action plans at national and local level to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Consultant on CCA and Industry Sector | Ayşe Özge KEPENEK BOZKIROGLU | UNDP’s Rules and Regulations on Procurement | USD 21,600.00 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Key Expert-1 - Consultancy on Climate Impacts and Modelling | Ceren BALLI GÖZEN | UNDP’s Rules and Regulations on Procurement | USD 9,680.00 | The main scope of the assignment is to provide technical inputs, develop implementation strategies, guide other consultants, conduct analyses / assessments and prepare technical reports and other project related documents. |
| Key Expert-3 - Consultancy on Urban Adaptation to Climate Change | Doğan DURSUN | UNDP’s Rules and Regulations on Procurement | USD 36.060.00 | The main scope of the assignment is to provide technical inputs, develop implementation strategies, guide other consultants, conduct analyses / assessments and prepare technical reports and other project related documents from urban adaptation viewpoint. |
| Consultant on Climate Change Adaptation and Ecosystem Services | Doğanay TOLUNAY | UNDP’s Rules and Regulations on Procurement | USD 16,200.00 | The main scope of the assignment is to provide technical inputs, to conduct vulnerability assessments, prepare of climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Consultant on Climate Change Adaptation and Management Information System | Emre Ege SMEKAL | UNDP’s Rules and Regulations on Procurement | USD 17,400.00 | The objective of the assignment is the provision of technical expertise on the launch and implementation of the Grant Programme (CCAGP). The IC as senior short- term expert on Management Information System will provide technical and administrative assistance and develop a web-based grant Management Information System (MIS) and monitoring and evaluation (M&E) system during grant application design, implementation, monitoring and review process. |
| Consultancy Services on Sectoral Adaptation to Climate Change | Ela BABALIK | UNDP’s Rules and Regulations on Procurement | USD 57,600.00 | The main scope of the assignment is to provide technical inputs, develop implementation strategies, guide other consultants, conduct analyses/assessments and prepare technical reports and other project related documents from sectoral adaptation viewpoint. |
| CCA and Health Sector | Emine Didem EVCİ KİRAZ | UNDP’s Rules and Regulations on Procurement | USD 11,340.00 | The main scope of the assignment is to provide technical inputs, to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level to develop climate change adaptation indicators and to prepare sectoral implementation guidelines |
| Consultant on Climate Change Adaptation and Agriculture Sector | İlkay DELLAL | UNDP’s Rules and Regulations on Procurement | USD 21,150.00 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Consultancy on Climate Change Adaptation and Energy Sector | Levent AYDIN | UNDP’s Rules and Regulations on Procurement | USD 21,600.00 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Key Expert-4- Software Development and Database Management Expert | Yahya AKDAĞ | UNDP’s Rules and Regulations on Procurement | USD 94,500.00 | The main scope of the assignment is to provide software development and update support, technical inputs, develop implementation strategies, cooperate with other consultants, conduct analyses/assessments and prepare technical reports and other project related documents. |
| Key Expert-5- Consultancy on Climate Finance | Özgür PEHLİVAN | UNDP’s Rules and Regulations on Procurement | USD 50,400.00 | The main scope of the assignment is to provide technical inputs on climate financing, develop strategies, conduct analyses/assessments and prepare technical reports and other project related documents. |
| Consultancy on Climate Change Adaptation and Tourism Sector | Süleyman TOY | UNDP’s Rules and Regulations on Procurement | USD 6,180.00 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Grant Programme Expert | Haydar Uğur Dağ | UNDP’s Rules and Regulations on Procurement | USD 9,909.91 | The objective of the assignment is the provision of technical expertise on the implementation of the Climate Change Adaptation Grant Programme during the project lifetime. As senior short-term expert on Climate Change Adaptation Grant Programme, The Grant Programme Expert will provide technical and administrative assistance during implementation, monitoring and review process for grant projects, develop training modules-training sessions, prepare project related documents. |
| Grant Programme Expert | Barış UYSAL | UNDP’s Rules and Regulations on Procurement | USD 4,865.00 | The objective of the assignment is to provide technical expertise on the implementation of the Climate Change Adaptation Grant Programme under the Enhancing Adaptation Action in Turkey Project. The expert is tasked with giving technical and administrative assistance during implementation, monitoring and review process for grant projects, developing training modules-training sessions, the implementation and monitoring of various modules of the MIS program, and preparing project related documents. |
| Consultancy on Climate Change Adaptation and Disaster Risk Management | Mikdat Kadıoğlu | UNDP’s Rules and Regulations on Procurement | USD 14,700.00 | The main scope of the assignment is to provide technical inputs to prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Consultancy on Climate Change Adaptation and Social Development | Zeynep Eren | UNDP’s Rules and Regulations on Procurement | USD 500.00 | The main scope of the assignment is to provide technical inputs to conduct vulnerability assessments, prepare of climate change adaptation strategies and action plans at national and local level, to develop climate change adaptation indicators and to prepare sectoral implementation guidelines. |
| Deliverable-Based Consultancy Services on Grant Programme Expert | Zeynep Aylin Güneygil | UNDP’s Rules and Regulations on Procurement | 9.000,00 USD | The objective of the assignment is to provide technical expertise on the implementation of the Climate Change Adaptation Grant Programme under the Enhancing Adaptation Action in Turkey Project. The experts is tasked with giving technical and administrative assistance during implementation, monitoring and review process for grant projects, developing training modules-training sessions, the implementation and monitoring of various modules of the MIS program, and preparing project related documents. |
| Retainer NPSA HOLDER - Project Implementation Support Analyst – Junior Consultant | Sebahat Düzleyen | UNDP’s Rules and Regulations on Human Resources | 8,874.82 USD | Support the project team, specifically the Project Manager, in the administration and implementation of the daily project activities, |
| Junior Consultant on the Standardized Translation Documents Junior Consultant | Ahmet Şerif Saman | UNDP’s Rules and Regulations on Human Resources | 50,000.00 USD | To ensure compliance between the complementary technical documents and support the project especially during the last intensive months to ensure English translation of the documents |

# PARTNERS AND COOPERATION

## Relation with the End Recipient

UNDP’s relationship with the End Beneficiary, namely the Ministry of Environment, Urbanisation and Climate Change, Directorate of Climate Change    had been fruitful until October 2023 where suspension had been received to the project. Following the rejection on Addendum No1, project implementation has been frozen. Later on, following the approval of re-submission of the Addendum received in February 2024, the project implementation has been re-initiated. Project management unit has been established to better track the remaining activities. Since then, the relations with the End Beneficiary have been re-established. No problem has been experienced in establishing smooth communication, sharing of information, and good practices since the project team was established.

# LINK WITH SUSTAINABLE DEVELOPMENT GOALS AND GENDER EQUALITY

Adopted by all United Nations Member States in 2015, the 2030 Agenda for Sustainable Development provides a shared blueprint for peace and prosperity for people and the planet. The 17 Sustainable Development Goals (SDGs) are at the center of the 2030 Agenda, which is an urgent call for action by all countries – developed and developing – in a global partnership. SDGs recognize that ending poverty and other deprivations must go hand-in-hand with strategies that improve health and education, reduce inequality, and spur economic growth – all while tackling climate change and working to preserve our oceans and forests. Strategies for sustainable development and climate change adaptation have many common elements. Thus, they are vital to insert to adaption actions and strategies.

Within this framework, project actively promotes localizing SDGs by central and local authorities and the public at large through the following interventions:

- Involvement of specific sessions on SDGs in the capacity development programs addressing the municipalities, MoEUCC and other ministries, Union of Municipalities of Türkiye and other associations, as well as social service units such as Women Centers, Child Development Centers at the local level,

- Integration of the policies on effective climate change adaptation with reference to specific SDGs,

- Mainstreaming the SDGs in basic standards and principles of service delivery and performance management tools to be developed under the Project.

Project makes direct contribution to SDG 11: Sustainable Cities and Communities and SDG 13: Climate Action in line with the below mentioned targets and indicators.

SDG-11: Sustainable Cities and Communities

| SDG Target 11.5 | By 2030, significantly reduce the number of deaths and the number of people affected and substantially decrease the direct economic losses relative to global gross domestic product caused by disasters, including water-related disasters, with a focus on protecting the poor and people in vulnerable situations |
| --- | --- |
| Indicators | 11.5.2 Direct disaster economic loss in relation to global GDP, damage to critical infrastructure and number of disruptions to basic services, attributed to disasters [Tier I] |
| SDG Target 11.b | By 2020, substantially increase the number of cities and human settlements adopting and implementing integrated policies and plans towards inclusion, resource efficiency, mitigation and adaptation to climate change, resilience to disasters, and develop and implement, in line with the Sendai Framework for Disaster Risk Reduction 2015-2030, holistic disaster risk management at all levels. |
| Indicators | 11.b.2 Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategies [Tier II] Note: this can be implemented but with a selective scope, covering only climatic hazards. |

SDG-13: Climate Action

| SDG Target 13.1 | Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries |
| --- | --- |
| Indicators | 13.1.2 Number of countries with national and local disaster risk reduction strategies 13.1.3 Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategies |
| SDG Target 13.2 | Integrate climate change measures into national policies, strategies and planning |
| Indicators | 13.2.1 Number of countries that have communicated the establishment or operationalization of an integrated policy/strategy/plan which increases their ability to adapt to the adverse impacts of climate change, and foster climate resilience and low greenhouse gas emissions development in a manner that does not threaten food production (including a national adaptation plan, nationally determined contribution, national communication, biennial update report or other) |
| SDG Target 13.3 | Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning |
| Indicators | 13.3.2 Number of countries that have communicated the strengthening of institutional, systemic and individual capacity-building to implement adaptation, mitigation and technology transfer, and development actions |

Project also makes indirect contribution to several SDGs such as SDG-5: Gender equality, SDG-6: Clean water and sanitation (specifically on water use efficiency), SDG-7: Affordable and clean energy, SDG-9: Industry, innovation and infrastructure, SDG-10: Reduced Inequalities, SDG-12: Responsible consumption and production, SDG-15: Sustainably manage forests, combat desertification, halt and reverse land degradation, halt biodiversity loss, and SDG-17: Partnerships for goals.

SDG-5: Gender Equality

UNDP’s development mandate is centered on gender equality and women’s empowerment.  Attaining human development requires multifaceted approaches that will encompass not only economic prosperity but also improve people’s well-being by ensuring an equitable, sustainable and stable planet which aims to greater wellbeing for all. As a globally recognized norm for UNDP, gender equality and women’s empowerment are integral to every aspect of its work to support countries to eradicate poverty and reduce inequalities and exclusion.

Although it has greater adverse effects on the section whose life relies on natural resources and who is unable to respond to natural disasters, women are facing higher risks and greater burdens from the impacts of climate change in situations of poverty. The inequality is often accelerated by the unequal participation of women in decision-making processes and labor markets, and results in the exclusion of women from climate-related policy-making practices.

Women’s involvement in the response to climate change is crucial due to their local knowledge and capacity in leadership at sustainable practices and brings about a higher level of readiness for the impacts of climate change. Hence, gender equality is one of the core values with which climate change adaptation policies and projects should be incorporated. In terms of project results, the project targets that all results are inclusive and gender responsive through:

- Integration of GESI (Gender Equality and Social Inclusion) to policy framework (systematic uttering and inclusion of the perspective)

- Identification of the relevant entry points in local and sectoral fields and dissemination of such knowledge via reports, workshops, and NAP

- Generation of the tools and procedures of inclusiveness and gender mainstreaming in climate adaptation action and exemplification of their use

At the work-plan level, gender equality and social inclusion dimension is mainstreamed via GESI expertise, gender-disaggregated data, women participation, reference to GESI best practices, GESI sessions in the meetings, GESI-focused participatory assessments, trainings or GESI modules in the trainings and GESI chapters in the reports.

## Project Contribution to SDGs

SDG 11 - Cities have a significant role in the planning process, by formulating and implementing adaptation actions that use limited resources to produce maximum common benefits, while avoiding the adverse consequences of climate change. This project specifically aims to develop adaptation and resilience planning in urban areas through urban adaptation planning on broad scale, involving disaster risk reduction, sustainable development, and poverty reduction, while also integrating existing planning processes and objectives with adaptation actions.

Through Component 2, activities were organized to discuss the impacts of climate change and highly vulnerable sectors and areas, and assess vulnerabilities, risk, data needs and availability, adaptation capacity, and the needs of each selected pilot city. Outcomes employed to develop urban strategy and adaptation action plans for climate change at the local level.

SDG 13 - Climate action includes mitigating climate change and adapting to the impact of climate change by building resilience to phenomena such as flooding, droughts and other extreme weather events, while including focus on strengthening resilience and integrating climate change measures into national policies and planning.

The project promotes Climate Action across all project components. In the reporting period, consultative meetings were organized to develop vulnerability and risk analysis methodology within the framework of climate hazards, exposure, sensitivity, adaptation capacity factors to be integrated into national adaptation policies.

SDG 5 - The project implementation process follows the umbrella scope of the UNDP’s approach towards gender equality and social inclusion. Therefore, the gender equality aspect of UNDP is extended in all project activities, including but limited to the composition of TAT and UNDP Direct Project Costed Staff, selection of short-term experts, women’s participation in meetings/trainings/events to be organized under each component.

The GESI aspect of the project was also reflected in Social Development section of the currently drafted reports as part of the sectoral vulnerability and risk assessments conducted for local climate change adaptation strategy and action plans for pilot cities and the national adaptation strategy and action plan to be updated.

The project also follows UNDP’s Gender Mainstreaming Tools for Programme Management. In line with the UNDP Türkiye Gender Screening Tool for Project Development and Implementation, the gender screening of the project including the gender analysis during the project stages was prepared and presented as an annex to the 2nd PR.

# VISIBILITY

All necessary measures are taken to ensure the visibility of the European Union and the Republic of Türkiye. All visibility actions are carried out following the General Conditions (Annex 12 - General Conditions to the Contribution Agreements, Article 8). The actions on the visibility of the Project follows the Joint Action Plan on Visibility of EU-UN external action programs (2006) and the 'Visibility Guidelines for EC-UN Actions in the Field (2014)''.

A social media presence and active interaction with the follower’s networks is an important channel to disseminate information about the project goals, activities and events. Using social networks allows the project to reach a larger group of people nearly instantly while supporting awareness about the Project among its followers.  Twitter and Instagram accounts offer the most dynamic way of communicating project news and cross-posting relevant news items.

Twitter: https://twitter.com/iklimeuyum

Instagram: https://www.instagram.com/iklimeuyum/?hl=tr

Twitter and Instagram accounts are used to publish project news and coverage of events in which the project is involved. The total number of Instagram followers is 554. During the reporting period, the number of likes for these posts is 90.  The total number of Twitter followers is 838. During the reporting period, 28 tweets were sent from the Twitter account. The total tweet impression is 19,3K.

The project website https://iklimeuyum.org  is one of the main channels for dissemination of project information. The main purpose of the website is to be the public image of the project as well as the main online access point for the different target groups.  It serves as a place to provide access to announcements, surveys, news, and newsletters.

The project website statistics have been analyzed since 26 November 2020 via Google Analyst, and data is collected on a regular basis. During the period (7 September 2023 – 22 September 2025) the project website was visited 30,903 times by 10,619 unique users.

| Month | User | Page view |
| --- | --- | --- |
| 7 April 2023- 7 May 2023 | 392 | 351 |
| 7 May 2023- 7 June 2023 | 824 | 771 |
| 7 June 2023- 7 July 2023 | 1,1K | 1K |
| 7 July 2023- 7 August 2023 | 487 | 413 |
| 7 August 2023- 7 September 2023 | 374 | 330 |
| 7 September 2023 – 7 October 2024 | 1.335 | 2.933 |
| 7 October 2024-08 April 2025 | 3085 | 8375 |
| 08 April 2025- 22 October 2025 | 1979 | 6580 |

Please find the posts shared on the project social media accounts in the reporting period in Annex 03.

Visibility rules were applied at the meetings. Flags, notebooks, books & pencils, media banner, swallow flags, roll up and spider stands were used in the meeting hall. Visibility materials were distributed at the meeting. The distributed set includes a notebook, pen, file, brochure, and bag.

Visibility materials related to the project are submitted in Annex 03.

The estimated completion time for the activities will be updated according to up-to-date AWP based on the finalization of Addendum No:2 process.