## Sheet1
The donor report of the project #00104475 "Strengthening National Capacity for Seismic Risk Assessment, Prevention and Response to Potential Earthquakes" for the period 2023
Achieved results | Description of expenses | Actual costs for 2023 (in US dollars)
|  | Works performed by the Government of Turkmenistan | Works performed by UNDP | Total
Output 1 - Conducting a comprehensive assessment of seismic risks in Ashgabat. a) Work was conducted on a survey of representative buildings in Ashgabt - Based on the results of the instrumental seismic measurements, the frequencies and modes of natural vibration of more than 30 representative residential structures in Ashgabat have been determined. As a result, of the 30 structures, 14 have a natural period of oscillation that exceeds the established standard values, and seismic reinforcement measures are required for these buildings. | Payment to the National Consultant on Earthquake Resistance of Buildings and Structures (the final report was completed at the end of 2022 and the expert provided the report in December. Payment for this work was made in January 2023) | 0 | 3428.57 | 3428.57
| Administrative expenses (7%) | 0 | 239.9999 | 239.9999
Total for Output 1 |  | 0 | 3668.5699 | 3668.5699
Output 2 - Comprehensive development of the Institute of Seismology and Atmospheric Physics at the Academy of Sciences in Turkmenistan, aiming to update and modernize methodological, scientific, technical, and human resources, through. a) More than 30 professionals from government agencies involved in post-disaster assessment and sustainable recovery, with the aim of coordinating or guiding future disaster management efforts, have successfully completed advanced training programs. | A two-day National Training on Post-Disaster Recovery Planning and Needs Assessment was conducted, organized by the UNDP Regional Office in Istanbul | 0 | 2742.86 | 2742.86
| Administrative expenses (7%) | 0 | 192.0002 | 192.0002
Total for Output 2 |  | 0 | 2934.8602 | 2934.8602
Output 3 - Increased preparedness to respond and eliminate the consequences of disasters caused by earthquakes: In 2023, no work was carried out on this result. |  | 0 | 0 | 0
Total for Output 3 |  | 0 | 0 | 0
Output 4 - Project management a)The project team completed all the required work to achieve the objectives of the project as outlined in the prodoc. | Individual Service Contracts | 0 | 7503.88 | 7503.88
| Communication expenses (including Internet) | 0 | 1756.28 | 1756.28
| Затраты на переводы | 0 | 0 | 0
| Operating expenses | 0 | 186.58 | 186.58
| Administrative expenses (7%) | 0 | 661.2718 | 661.2718
Total for Output 4 |  | 0 | 10108.0118 | 10108.0118
Co-financing by the Government of Turkmenistan, excluding interest on general management |  | 0 | 15618.17 | 15618.17
Co-financing by the government of Turkmenistan, taking into account the percentage for general management. |  | 0 | 16711.4419 | 16711.4419
7% Interest for general management |  | 0 | 1093.2719 | 1093.2719
Contributions from UNDP and other donors |  | 0 | 0 | 0
Total costs for 2023: |  |  |  | 16711.4419
Notes:
1) In accordance with the Project Document, the Ministry of Finance of Turkmenistan transfers financial resources for the implementation of project activities in manats at the exchange rate effective on the date of deposit of funds .
2) As an international organization, UNDP keeps records of financial resources in US dollars based on the exchange rate between the manat and the dollar.
3) The balance of funds as of October 31, 2022 was $199,718.97. In April 2023, an extension of the project was signed until June 30, 2024. On December 8, 2023 funds in the amount of $296,800.00 were transferred from Institute of Seismology's own savings to implement the third phase and ensure the successful completion of the project.
Prepared by: Azat Yagshymyradov, Project Analyst UNDP
Approved by: Farhat Orunov, Program Analyst – Resilience Environment and Energy UNDP