2021

Project Implementation Report (PIR)

BD safeguards and conservation  in Palau

Basic Data

Overall Ratings

Development Objective Progress

Implementation Progress

Project Governance

Ratings and Overall Assessments

Gender

Risk Management

Knowledge Management & Communications

Stakeholder Engagement

Annex - Ratings Definitions

# Basic Data

| Project Information |  |
| --- | --- |
| UNDP PIMS ID | 5645 |
| GEF ID | 9208 |
| Title | Integrating biodiversity safeguards and conservation into planning and development in Palau |
| Country(ies) | Palau, Palau |
| UNDP-NCE Technical Team | Ecosystems and Biodiversity |
| Management Arrangements | CO Support to NIM |
| Project Implementing Partner | Government |
| Joint Agencies | (not set or not applicable) |
| Project Type | Full Size |
| Implementation Status | 2nd PIR |
| GEF Fiscal Year | FY21 |
| Trust Fund | GEF Trust Fund |

Project Description

This project aims to address the negative impacts of unsustainable sector-led development practices on biodiversity-rich landscapes of Palau, including its productive coastal and marine ecosystems, while taking into account climate change adaptation needs and inclusive and equitable social and economic development for dependent communities, as well as safeguarding against threats to biodiversity and the introduction and spread of Invasive Alien Species through the tourism and related sectors. The objective of the project is to mainstream biodiversity conservation into integrated land and seascape governance, planning and management in Palau. The project recognizes the fact that these land and seascapes underpin the lives and livelihoods of a large number of local communities and that implementation of a coherent strategy to promote sustainable, biodiversity-friendly livelihood options is an integral part of the solution. The project objective is to be achieved through the implementation of four inter-related and mutually complementary Components (Project Outcomes) that are focussed on addressing existing barriers. The four Outcomes of the project are: Outcome 1: Enhanced national institutional framework for integrated planning and management of land and seascapes; Outcome 2: Integrated multi-sector land and seascape planning and management operational in Babeldaob states to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies; Outcome 3: Integrated multi-sector planning and management operational in 264,686 ha of seascapes and coastal areas in the Southern Lagoon to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies; and Outcome 4: Knowledge management, monitoring and evaluation support, equitable gender benefits and biodiversity conservation in Palau.

| Project Contacts |  |
| --- | --- |
| UNDP-NCE Technical Adviser | Ms. Penny Stock (penny.stock@undp.org) |
| UNDP-NCE Programme Associate | Ms. Somaya Bunchorntavakul (somaya.bunchorntavakul@undp.org) |
| Project Manager/Coordinator | Ms. Dolmii Remeliik (dolmiir@gmail.com) Ms. Anuradha Gupta (anu.bintorio@gmail.com) |
| UNDP Country Office Programme Officer | Mr. Floyd ROBINSON (Floyd.robinson@undp.org) |
| UNDP Country Office Deputy Resident Representative | Kevin Joseph PETRINI (kevin.petrini@undp.org) Levan BOUADZE (levan.bouadze@undp.org) |
| UNDP Regional Bureau Desk Officer | Sharad neupane (sharad.neupane@undp.org) Katri Kivioja (katri.kivioja@undp.org) |
| GEF Operational Focal Point | (not set or not applicable) |
| Project Implementing Partner | (not set or not applicable) |
| Other Partners | (not set or not applicable) |

# Overall Ratings

| Overall DO Rating | Moderately Satisfactory |
| --- | --- |
| Overall IP Rating | Moderately Satisfactory |
| Overall Risk Rating | moderate |

# Development Objective Progress

It is mandatory for all reported progress to be substantiated by evidence. Please upload evidence files for each objective/outcome via the DO PROGRESS section in the online PIR platform.  If there is no evidence to upload, the Project Manager is required to provide an explanation.

| Description |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Project Objective: To mainstream biodiversity conservation into integrated land and seascape governance, planning and management in Palau. |  |  |  |  |  |  |
| Description of Indicator | Baseline Level | Midterm target level | End of project target level | Level at 30 June 2020 | Cumulative progress since project start |
| Mandatory Indicator 1.3.1 Area of sustainable management solutions at sub-national level for conservation of biodiversity and ecosystem services that benefit from integrated landscape and seascape planning and management approaches | Approximately 115,000 hectares (managed effectively) | At least 130,000 hectares of seascapes and landscapes effectively managed through participatory approaches | At least a total of 240,000 hectares of seascapes and landscapes effectively managed through participatory approaches | As of 30 June 2020, 144,788 hectares. Palau recommends changing the baseline and the mid-term target prior to the 2021 PIR, so as to secure Project Board agreement. The baseline may be updated to 144,785 hectares. A reasonable mid-term target would be 175,000 hectares; however this number would need to be vetted and approved by our Board. An adjustment to baseline due to improved data collection at PALARIS put the total area to 144,785. The majority of the growth came from expansion of the Managed Marine Area in Ngarchelong. Approximately 3,000 hectares does not represent an addition, but is an adjustment. This was reported in the 2019 SOE and is not directly related to this project. An additional 2.8 hectares added due to the addition of a 50-year private lands conservation easement with PCS in Peleliu "MVP Forest of Hope". Growth in the total area of land and water under sustainable management has increased due to coordinated efforts by the environment sector to increase support for conservation and sustainable use of resources. While expansion from the baseline is not directly tied to the project, it has contributed to an overall increase in support for effective management. The integrated planning process is progressing on Babeldaob and the Southern Lagoon, with all prerequisites in place to progress integrated landscape planning: multiple participatory committees at multiple jurisdictional levels (national and state), methods of operating, technical support, a clear schedule and outputs, and strong political support at National and State levels. Each State involved in the project has a development Vision that lays the foundation for integrated planning. Conserving, protecting, health, or sustainable use of the environment is explicitly included in 9 of 11 Vision Statements. Capacity for integrated management is rapidly increasing through State Planning Teams who are planning for immediate action on the ground. The project is on track to exceed the EOP target now that all 10 states in Babeldaob are participating in integrated land/seascape planning (up from the proposed 7). | This indicator is on track. 146,248 confirmed, 157,896 (TOTAL) potential. Evidence: Indicator 1.3.1-2.pdf AS OF 2021: Legislated and regulated includes 144,788 hectares of land and sea in Protected Areas plus 1,460 hectares of land in Riparian Buffer Zones (regulated previously but in 2020-2021 were communicated and enforced). AN ADDITIONAL 11,648 hectares on land has been identified for sustainable management solutions. Evidence: Indicator 1.3.1 (excel) This mid-term value of 144,788 hectares of confirmed sustainable management solutions represents protected areas on land and sea and riparian buffer zones on land. EQPB regulations were also updated for marine areas but protected Class AA and A waters (pristine waters) have not yet been mapped. Work on this indicator is progressing steadily through the land use planning efforts of the Babeldaob Joint Coordination Body (JCB). MAFE EPCU acts as the Secretariat for the JCB. The JCB has mapped and agreed to advocate for protection of an additional 11,648 hectares of land to be sustainable managed. As the JCB has no authority (only State Governments have that authority), this means that JCB members have agreed to use the land use designations as the starting point for negotiations in their home state, as those home states undertake Master Planning and Land Use Planning. This number of 11,648 hectares is the result of a year of integrated planning on Babeldaob with 9 of the 10 States. Additional hectares from Airai State (the 10th State) are expected when a new administration there is elected (Airai has been in political flux for months). The 11,648 hectares represents new agreements on land only, as Project Partners have not had a chance to map or zone for offshore marine areas yet. Significant progress was made in mapping and zoning of Koror’s lagoon waters, but as these are already counted within the Protected Areas value of 144,785 hectares (the revised baseline), thus they are not counted here again. The entire Koror Southern Lagoon is a managed area. However, new zones will improve fisheries management in the lagoon. Eventually, each State on Babeldaob plus Peleliu will have a state-wide Master Plan and Land Use Plan that will zone for the entire State. In the next year, work on Babeldaob and Peleliu will also focus on fisheries and aquaculture areas (both nearshore and offshore) and thus Project Partners are confident they will reach the target of 240,000 hectares of sustainable management solutions by the end of the Project. Palau has also zoned 80% of its EEZ as a no-take Marine Protected Area (the Palau National Marine Sanctuary – PNMS – 500,000 square kilometers) which is not counted here because they are counted under a different GEF7-funded project. However, many GEF6 Project Partners are highly involved in the PNMS and implementing types of sustainable management solutions that have been identified in this GEF6 project (such as outreach, enforcement, and zoning). |
| Mandatory Indicator 1.3.2 Number of households benefiting from strengthened livelihoods through solutions for improved management of natural resources and provision of ecosystem services | Number of households currently participating in sustainable resource management and best practice approaches – 39% of HHs (in 7 Babeldaob states and Peleliu) in 2016 (300 HHs ) . (baseline to be validated in Year 1) | At least 45% of HHs in Babeldaob states and Peleliu (at least 340HHs) directly benefit through sustainable resource management approaches and incomes (At least 50% of the beneficiaries would be women inclusive HHs) | At least 55% of HHs in Babeldaob states and Peleliu (at least 425HHs) directly benefit through sustainable resource management approaches and incomes (At least 50% of the beneficiaries would be women inclusive HHs) | Same as baseline. The project has yet to implement action on the ground and thus it is too early to see livelihood benefits. MNRET has prioritized contracting of local indigenous suppliers in villages during this Covid-19 crisis, such as paying for local meals and transportation. So far, because most services secured have been food, women have largely benefitted. Some men have benefitted through transportation services. In the second half of 2020, the Project will distribute $43,000 in direct funding to States and villages for the implementation of natural resource management. Based on the safeguards in place (including community benefit requirements) many families will receive direct financial benefits for their participation. According to Action Plans, 10-20 households in 4-5 States will participate. In reviewing these Action Plans, GEF6 has advocated for inclusion of women, youth, and different social groups. The baseline has not been verified yet but a KAP survey is being conducted and will validate or improve upon the baseline (expected September 2020). Unlike any other environmental project ever in Palau, this project is strongly advocating for gender balance and social inclusion. While not yet at 100%, issues of gender balance have been discussed in a majority of meetings and diverse audiences (e.g. with national and state political leaders, resource managers, and community groups). Thus awareness and involvement of women-inclusive Households has already increased compared to other projects. | This indicator is on track. The progress is verified through different types of data collection as Iit is difficult to track beneficiaries by number of households. Sign-in sheet data shows that 874 people participated in the project in some way. Using women as a proxy for households, participation in the State projects - implementation of best practices in the key sectors to strengthen management and thus livelihoods - was at 322. In total 588 women have participated. 65-70% of participants are women. However, (although information is still being collected), it appears that of those people who received stipends, men were 73% and women were 27%. If this is the case, corrective action will be taken to ensure that women receive financial benefits from the project at the same rate as men and are not expected to work for free. Evidence: Indicator 1.3.2 – Participant Database.xlsx Information on who exactly had received stipends (a direct livelihood benefit) was still being collected, but in the past year $20,897 was paid directly to community members for their participation in livelihood activities (e.g. planting, cleanups, planning). Given that the average stipend is $35, this means that nearly 600 stipends were paid. Participants received stipends for: • Planting trees in Ngarchelong, Ngeremlengui, and Ngchesar • Pulling out invasive weeds in Lake Ngardok (co-financed with state funds) • Cleaning out taro patch waterways in Ngiwal (beneficiaries were mostly women) • Cleaning stream debris and trash in Ngardmau • Removing invasive vines in Peleliu • Aimeliik and Ngaraard did not pay its tree planting volunteers a stipend but provided them with meals. • Ngaraard women did receive stipends for cleaning out taro waterways (co-financed with other GEF funds; beneficiaries were 100% women). An additional 60 households have participated in planning; some planning teams offer a stipend while others rely on volunteers. Evidence: Indicator 1.3.2 – GEF6 States Stipend Log.xlsx 2020 funds of $43,000 were used by States for these activities and some portion of their 2021 funds. Every state provided at least food to its participants. Because of the delay in receiving 2021 funds, State activities in 2021 were delayed. It is proving to be difficult to confirm the baseline and a new baseline may be necessary. Surveys have reached individuals, not households. For instance, the KAP survey found that 69% of individuals had participated in community-wide or state-wide activities to deal with threats to biodiversity. (58% women, 42% men). For instance, the 2020 Gender and Natural Resources report confirmed that sustainable resource management and best practice approaches are important to nearly 70% of Palauans. Fishing, Agriculture, Invertebrate gleaning, collecting medicine, and collection of medicinal plants are primary uses of natural resources. 748 individuals were surveyed. Evidence: Resource Use Gender Report – Palau 2021 – DADG-Ebill-GEF6_Maps.pdf |
| Mandatory indicator 2.5.1 Extent to which Institutional frameworks are in place for integration of conservation, sustainable natural resource use, control and management of IAS, biodiversity and ecosystems and improved livelihoods into integrated land/ seascape planning and management | No states have comprehensive landscape and seascape planning and management approaches; 4 of 16 states have partial plans or zones (Koror, Airai, Melekeok, Ngardmau) | Integrated Landscape/seascape management “strategy” for Babeldaob Island and ILSMPs developed for at least 3 states | Multiple use and sustainable landscape and seascape approaches institutionalized by national legislative, policy, and institutional arrangements and planning and practice effected in 9 states | Same as baseline. There is a near-finished DRAFT of a Babeldaob-Koror Urban Development Strategic Action Plan (KBUDSAP). The plan considers many linkages but is not fully landscape-seascape. No change in the number of States with ILSMPs. Integrated planning process is progressing on Babeldaob and the Southern Lagoon, so institutional frameworks to support eventual ILSMPs are not yet in place. Each partner State has a Development Vision that is the foundation for its integrated, participatory plans. A framework of safeguards, pulled from National Policies, laws, plans, and Best Management Practices, has been drafted and is being tested and communicated. Use of these safeguards has already influenced project designs in two states (one that might have resulted in unfair benefits and one that was originally planning to use an aggressive species). Efforts to review laws and enforcement procedures within the GEF6 categories have just started, with an emphasis in 2020 on aquaculture and fisheries. Partners have developed a clear plan of action for assessing some cross-sector legal and enforcement needs. GEF6 has been a partner throughout the KBUDSAP. Its urban development goals include language about “sustainable” development. | Although this indicator is behind relative to the mid-term target, it is on track to meet or exceed the end of project target. 1) Babeldaob-Koror Regional Urban Development Strategic Plan (KBRUDSAP) was adopted by Ministry of Finance. (Partner activity funded by ADB; GEF6 partners were important stakeholders and heavily involved in its development). 2) Babeldaob-wide Land Use Guide developed and adopted by Babeldaob JCB with guidance on protected areas, housing, agriculture, and tourism sites. Evidence: Indicator 2.5.1- Babeldaob Land Use Guide -Maps-Small.pdf) 3) 9 States actively progressing through Master Planning Evidence: Indicator 2.5.1 – Master Plan.xlsx) MAFE’s Legal Counsel made progress on several pieces of biodiversity-related legislation, although none have been adopted yet. These include • Access and Benefit Sharing regulations • Endangered and Threatened Species regulations • Amendment to the Marine Protection Act and associated regulations for the protection of marine species • Amendments to the PNMS law • Draft of the Biosecurity Regulations • Reef-safe Sunscreen laws and regulations • Sustainable Tourism Regulations Evidence: Palau MAFE Legal Counsel report Project Partners are still working to complete a full Babeldaob-wide strategy but several key aspects have been concluded and agreed, including an island-wide Vision and island-wide Land Use Designation Guidance maps (see #2 above). Agreed elements in the Babeldaob-wide land use designation maps include: • Low impact uses in the watershed catchments above water sources (all 10 states) • Low impact uses in and around tourism sites (including a 300-foot buffer) on land • Identification and agreement of housing subdivision areas based on agreed criteria that fully incorporated best practices (e.g. appropriate safe soils for septic tanks, protection of cultural resources and agricultural land, avoidance of upland forests and high biodiversity areas, etc.). Criteria included environmental sensitivity and economic/social feasibility in addition to environmental laws and regulations. • Identification and agreement of future large-scale agricultural areas based on best practices for soil fertility and integrated livestock/farming principles. In the past year, Ngardmau State officially adopted its 2015 Master Plan and immediately began a review and update. Ngiwal and Ngaraard found and reviewed old Master Plans that were developed in the late 1990s. Thus, 5 States have existing or resurrected Master Plans (Airai, Ngardmau, Melekeok, Ngaraard, and Ngiwal). All 10 States on Babeldaob plus Peleliu signed MOUs with MAFE agreeing to undertake Master Planning following MAFE’s templates and tools (which incorporate biodiversity, social, and climate safeguards). Work has started in 9 of those 11 states. In terms of Institutional Frameworks, the project created Planning Commission legislation and a Master Plan template that are aligned with national law and which will create a state legal basis for master planning. Ngarchelong and Ngaraard have introduced the legislation and it had gone through multiple readings by the end of June 2021. Other states had identifying Planning Commission members while the legislative process takes its time. Significant progress was made in Koror to review its fisheries zones and identify a comprehensive zoning system for its southern lagoon. (This work was co-financed elsewhere but included GEF6-funded GIS work and meeting facilitation and heavy involvement of Project Partners and staff). The KBRUDSAP was finished and adopted. Project Partners took the lead in bringing the new administration up to speed on the KBRUDSAP so that it could would fully align with the GEF6 project. The housing and tourism parts of the KBRUDSAP were reviewed, updated, and localized through by the Babeldaob JCB, with negotiation to localize the housing criteria that had been proposed by KBRUDSAP. |
| The progress of the objective/outcome can be described as: | On track |  |  |  |  |
| Evidence uploaded: | YES |  |  |  |  |
| Outcome 1 Outcome 1 Enhanced national institutional framework for integrated planning and management of land and seascapes |  |  |  |  |  |  |
| Description of Indicator | Baseline Level | Midterm target level | End of project target level | Level at 30 June 2020 | Cumulative progress since project start |
| Indicator 5: Level of institutional capacities for planning, implementation and monitoring integrated land/seascape management plans as measured by UNDP land/seascape management scorecard | Limited institutional capacities for planning, implementation and monitoring of multiple use landscape and seascapes as measured by UNDP Land/ Seascape Capacity Development Scorecard baseline: (i) National level landscape/seascape capacity score 16/63 (ii) State level average score landscape/seascape capacity 15/60 (iii) National Environmental Management score 22/45 (iv) National biosecurity capacity score 15/45 | Increase of institutional capacity as measured by a 10% increase in UNDP Landscape and Seascape Capacity Development Scorecard (national and state levels), National Environmental Management Capacity Scorecard and National Biosecurity Capacity Scorecard | Average Increase of institutional capacity as measured by a 25 % increase in UNDP Landscape and Seascape Capacity Development Scorecard (national and state levels), National Environmental Management Capacity Scorecard and National Biosecurity Capacity Scorecard (Original: Increase of institutional capacity by 50% - changes was agreed during inception) | This indicator is on track. The scorecard levels increased for all four capacities: (i) National level landscape/seascape capacity score 19/63 (ii) State level average score landscape/seascape capacity 22/60 (iii) National Environmental Management score 26/45 (iv) National biosecurity capacity score 23/45 Building capacity to conduct integrated planning is progressing. Establishment of 9 State Planning Teams and 2 Joint Coordination Bodies has increased the involvement of individuals by 70 people. Involvement of 10 Babeldaob States from the proposed 7 has also expanded the scope and utility of plans, increasing the capacity for improved impacts. Specific trainings have been held to build capacity of States and communities to write reports and Action Plans, as well as much one-on-one mentoring. A capacity building plan with formal and informal trainings has been included in the JCB’s plan of work. Concurrent processes that are connected to this project, like the KBUDSAP process, have increased the capacity of National government to undertake integrated planning. This process has also produced resources – such as maps and assessments – that improve capacity scores. The project reached out to elected officials to provide advice on draft National legislation that will mandate and support integrated planning. A strong effort to collect, catalog, and make accessible Best Management Practices (BMPs) has also increased national institutional capacity, especially at MNRET, to advise for improved implementation on the ground. A new system to improve Knowledge Management (via a project website and increased communications to share resources) has increased information availability and access. | This indicator is on track. Scores increased by at least 10% for all four capacities. The scorecard levels increased for all four capacities: (i) National level landscape/seascape capacity score 33/63. (ii) State level average score landscape/seascape capacity 27/60. (iii) National Environmental Management score 32/45. (iv) National biosecurity capacity score 27/45. Capacities increased the most within the National Government sphere, partially as a result of the Ministry’s creation and improved coordination of an Environmental Planning and Coordination Unit (EPCU). The EPCU works closely with the National Environmental Protection Council (NEPC) to coordinate environmental actions such as Best Practice workshops, assessments of national indicators (like SDGs), development of new proposals, etc. Project Partners have collected and collated environmental information, particularly on Best Practices, which are increasingly online and communicated weekly. (i) National level landscape scores - Through this GEF6 project, partners are now following an improved process for integrating biodiversity into national policies. This includes consulting updated spatial maps and spatial data housed at PALARIS; and cross-referencing against national environmental policies, which are now online and which have been shared widely. Some Stakeholder meetings are held under the auspices of the NEPC and with the assistance of the NEPC Secretariat. The Babeldaob JCB was created through the project and has been actively engaged in Landscape/Seascape Planning for the island, and are guided by a common vision: Babeldaob Vision & Core Values. Similarly, a stakeholder group of National, State, and civil society developed the KBRUDSAP, which also has a common vision. The KBRUDSAP fed into the Babeldaob vision and the Babeldaob land use guidance maps. EA/EIS regulations were updated to include specific requirements to measure and avoid harm to biodiversity, with special emphasis on endangered species. Total information and data available has increased, and most is available online on a centralized GEF6 website. Weekly emails appear to have increased knowledge about national biodiversity policies that are being mainstreamed. (ii) State level average scores – Although the project invested heavily in building state capacity, because this indicator is averaged across 11 States, all of which are in different places in terms of planning, growth in the indicator is slow. Through MOUs, the EPCU has secured the commitment of all 11 States (10 on Babeldaob plus Peleliu) to participate in Master Planning using EPCU templates and following the agreed process, which includes safeguards and requirements for protecting biodiversity. Since the project started, States have established planning teams, started working on legislation to create participatory and authorized Planning Commissions, collected spatial data, and progressed on developing State Master and Land use plans. Every State has a Vision. (iii) National Environmental management scores – At the national government and national NGO level, participation is steady and stakeholders regularly participate in decisionmaking processes through forums such as the Conservation Consortium and NEPC, and by consulting centralized spatial data held at PALARIS. Amendments to Title 31 passed the House of Representatives and were introduced in the Senate of the National Congress, and included a framework for national planning that included specific reference to environmental management. With improvements to the housing and use of spatial data at PALARIS, and updates of baseline maps, the ability to monitor and evaluate environmental information is improved and standardized. For instance, planning outside of the Project by tourism partners and climate change partners are now using these environmental tools. (iv) National Biosecurity – Formal MOUs were established with the Bureau of Agriculture and the Bureau of Customs to manage the Biosecurity Division. The National Invasive Species Council (NISC) was reconstituted and has jointly developed positions and identified responses to species issues. The NISC Office also initiated research on fruit flies and CRBs in specific response to needs from agriculture. A draft of the updated Biosecurity Regulation were finally produced, reviewed, and sent back to the Legal Counsel for continued work. Finally, after many funding-related delays, construction on the Biosecurity Quarantine facility commenced. |
| Indicator 6a: Percentage increase in new earthmoving projects requiring environmental assessment (EA) | 6a: 7.5% of new earthmoving projects require EA (2016) | 6a. At least 10% of new earthmoving projects require EA | 6a. At least 15% of new earthmoving projects require EA | This indicator is on track. Although in 2019, 5% of projects required an EA. This is an undesirable trend and the tighter regulations would trigger more EAs. However, many projects were small and thus had less impact. During this reporting period, new and more stringent water quality regulations have been adopted and are already triggering new types of review (e.g. of impacts to buffer zones). Earthmoving regulations and permits are under review and are being updated. This indicator is highly variable due to national and global economic situations and the scheduling of local construction. For instance, even though the number of EAs required decreased (due to the smaller nature of applied permits), the number of safeguards in place increased. For instance, improved water quality regulations classifies and protects water bodies based on water quality and establishes an “Anti-degradation Policy,” improved microbiological and chemical standards, added an Ammonia (NH3) toxicity standard, and uses better science to set a new Dissolved Oxygen standard. Updated Wastewater Treatment and Disposal Regulations also went into force on 19 October 2019. It set more stringent standards for acceptable standards of fecal coliform, suspended solids, and biological oxygen demand. | At a modified level looking only at larger Commercial and Government/NGO permits, this indicator is on track. As of March 2021 (FY 2021): • 4% of ALL projects required an EA. This is still an undesirable trend, as tighter regulations would trigger more EAs. • However, the majority of the permits in 2020 were for residential development (including renovations to existing structures) which are smaller projects and thus exempt from EA requirements. • In 2019, 53% of the permits were for residential permits and in 2020 69% were for residential permits. • Only the commercial and government/NGO projects are likely to trigger EA requirements, if large enough. o Looking only at Commercial and Government/NGO permits, in 2019, EQPB required 11% of applicants to produce an EA; and in 2020 EQPB required 18% of applicants to produce an EA. This is the expected, desirable trend. See spreadsheet: https://docs.google.com/spreadsheets/d/1zo7x2ZN3QCy0nDeoQNIYRS7YaSGMDK3EPL7-0prYoGM/edit?usp=sharing Indeed, in 2021 EQPB was called in front of the Palau Senate to respond to claims about making the EA/EIS Regulations too stringent. This was after EQPB added biodiversity criteria and cumulative impacts criteria. The new and more stringent water quality regulations were communicated widely in the last year. Riparian zones were fully integrated into housing subdivision criteria and into the Babeldaob land use guide. EQPB also updated its EA/EIS regulations to include specific criteria about biodiversity and endangered species, as well as cumulative effects. The addition of the language about biodiversity was as a direct results of GEF6 Project Partners. EQPB EA/EIS Regulations (2020). This indicator may not be accurately capturing progress towards this outcome and may need to be REVISED. Regulations have become more stringent, but an increase in small projects makes it appear as if the indicator is trending in the wrong direction. When subsets of data are analyzed, it appears that the intent of the indicator is being achieved. |
| Indicator 6b: Percentage compliance with environmental safeguards for all permitted earthmoving projects that are exempt from EAs | 6b: 85% of all permitted earthmoving projects that are exempt from EAs comply with prescribed environmental safeguards (2016) | 6b: At least 90% of all permitted earthmoving projects that are exempt from EAs comply with prescribed environmental safeguards | 6b: Full compliance of all permitted earthmoving projects that are exempt from EAs comply with prescribed environmental safeguards | This indicator is on track. From March 2019 to March 2020, the Compliance rate was 95% (violation rate was 5%). However, this is quite variable and does not represent an improving trend yet. For instance, in the prior year (ending March 2019) the Compliance rate was only 84% (violation rate of 16%). Recent compliance appears to be very high, but this is again a factor influenced by economic situations. When many projects are small (e.g. increased proportion of homebuilding due to increasing household incomes, housing loan programs, or falling tourist numbers), compliance will be higher. That said, enforcement agencies have made improvements and increased understanding of environmental regulations and impacts has likely contributed to improved compliance. EQPB is systematically updating its regulations, and these are being communicated and mainstreamed into State development plans as they become available, so increasing compliance is expected to continue. A KAP survey is ongoing to assess level of awareness and compliance with land and zoning requirements. Survey results are expected to be ready by September 2020 so that they inform 2021 Annual Work Planning. | This indicator is steady (and on track). As of March 2021 (FY 2021): • 5% violation rate, or 95% compliance rate. This is holding steady. o The 2020 number was 15 violations:313 earthmoving permits; o The 2021 number is 21 violations:382 permits. • The number of permit applications increased by 22% between the two years, while staffing at EQPB declined from 17 to 16 (including having no Executive Director for part of 2021). Evidence: Indicator 6 – EQPB.xlsx Since the project started EQPB has updated its water quality and EA/EIS regulations and held workshops and trainings with developers, contractors, State governments, and other stakeholders to communicate the revisions. EQPB also produced a guidance document: Palau Marine and Freshwater Water Quality Regulations - Implementation Guidance Manual and training materials: Overview presentation on revised EA/EIS Regulations (2020). See photos from a workshop: https://www.flickr.com/photos/189071815@N08/albums/72157717212052307. The KAP survey confirmed that knowledge of zoning is limited and thus education and outreach will be necessary if permit applications are to conform with land use plans that incorporate zones that are being developed with biodiversity safeguards in place. The KAP survey found: • Around 75% of respondents said that zoning is important and should be followed. • Majority of the population disagrees that private lands should follow zoning rules, but disagrees differently by age that public lands should only be applied zoning rules. • 66.7% of the elderly subgroup, followed by 53.48% of adults and 48.84% of youth view the need for stringent zoning rules be applied to public lands. • Only 20% of people had ever checked to map to see if certain types of development are allowed. Evidence: Palau 2020 KAP - Baseline for IAS and LUP _ Data.pdf_ Project partners are also increasing awareness of regulations and biodiversity safeguards through master, action, and land use planning processes. For instance, state planning teams reviewed safeguards and restrictions before identifying 2021 Action Projects, and had to design projects that incorporated safeguards. See: • https://sites.google.com/view/gef6palau/governance/safeguards, plus • https://sites.google.com/view/gef6palau/governance/endangered-species. • This document that was reviewed in person with all planning teams prior to setting their 2021 AWPs: Funding Guidance and Requirements for 2021 State Funds |
| Indicator 7: Comprehensiveness of national level IAS management framework and ability to prevent IAS of high risk to biodiversity from entering Palau, as measured by IAS Tracking Tool | IAS Tracking Tool Score of 9 (out of total of 27) due to lack of national coordinating mechanism; no national IAS strategy; detection surveys non-existent; priority pathways not actively managed, etc. | Improved policies and legislation for prevention of high risk IAS from entering Palau as measured by 20% increased score in the GEF IAS Tracking Tool (from baseline 9 to 11) | Improved surveillance and controls for prevention of high risk IAS from entering Palau as measured by 50% increased score in the GEF IAS Tracking Tool (from baseline 9 to 15) | This indicator is on track. Slight increase in the Tracking Tool. (This indicator is comprehensive; note there was significant improvement in biosecurity capacity – Indicator 5). IAS Tracking Tool Score of 10 (out of total of 27) due to improvement in management and monitoring of priority pathways (e.g. cargo at the airport and seaport). The project has made significant progress in strengthening the nationwide IAS framework, although there have been some delays. Investment in personnel – particularly an IAS Project Coordinator and a NISC Coordinator have catalyzed action and improved national coordination. They actively coordinate IAS and Biosecurity actions within MNRET and with key partners as they implement the NISSAP. Capacity to secure the border has increased with the hiring and training of Biosecurity Officers and with improved detection techniques. X-ray equipment has been purchased but awaits installation and training. Delays due to Covid-19, particularly the border closure, are responsible for this delay. Biosecurity Officers, however, continue to screen every incoming vessel at considerable risk to themselves. A key sign of progress is the respect paid to the Biosecurity Officers. During this Covid-19 crisis, Biosecurity Officers have been recognized and feted as Frontline Responders by the public and businesses (winning prizes and being recognized on posters). Recognition of their role in protecting the country is relatively new, given that many of these positions were only created under this project. Mainstreaming of policies has improved, with the establishment of Biodiversity and Biosecurity safeguards and with the development of a Native and Non-Native Plant Policy. These policies are specific to GEF6 funding for the time being, but have wide applicability. Through this mainstreaming efforts, advice provided to communities has already improved (e.g. consistent advice on species and methods). A Black and White list is currently under construction. All prohibited and watch-list plants have been identified. Efforts are now on identifying animals and other pathogens for inclusion on the list. Construction plans for a Biosecurity Office are ready and it is progressing through the Government bidding and procurement process before construction begins. The project is behind in establishing an EDRR system; delays from the start of the project are now being compounded by delays due to Covid-19. | This indicator is on track. Continued Slight increase in the Tracking Tool. (This indicator is comprehensive; note there was significant improvement in biosecurity capacity – Indicator 5). IAS Tracking Tool Score of 12 (out of total of 27) due to improvement in management and monitoring of priority pathways (e.g. cargo at the airport and seaport). The nationwide IAS framework continues to improve. Key achievements included production of a draft of the Biosecurity Regulations, which were reviewed in depth and sent back for revision. During the review process, a draft of aquatic species regulations were also reviewed by technical experts and recommended for adoption and inclusion into the final Biosecurity Regulations. Despite the delays, the project finally began construction on a Biosecurity Quarantine Facility in Ngchesar. The NISC was reconstituted, held its first meeting in more than 18 months, and even drafted a response to a national biosecurity action. The Biosecurity Division was moved from the Bureau of Agriculture to the Bureau of Customs and Immigration. NISC organized a response to the proposal when it was first proposed: https://drive.google.com/file/d/1b6bgiXEO3lkKZ3Fs8P1niLEko9ahdkdl/view?usp=sharing. Although the move did ultimately go through, NISC’s concerns were brought up during negotiations for ensuring that Biosecurity’s functions would continue even while under Customs and Immigration. The Biosecurity Division continued to inspect all incoming vessels regularly at the airport and seaport, and the occasional incoming yacht. Several of their forms and procedures (such as Risk Assessment) are under review. Partners also did training of PAN Rangers to improve their ability to monitor and delimit invasive vines and crown-of-thorn starfish. A centralized database was also established and tested and is being refined: https://sites.google.com/view/gef6palau/data-portal. A baseline was established with spatial data showing hotspots and monitoring spots for fruit flies and CRBs in Koror and Babeldaob:  Koror CRB and Fruit Fly  Babeldaob CRB and Fruit Fly Project Partners produced sets of Black and White lists: Official Black & White List: Species to Avoid (BOA, 2020) consisting of: • Draft Black & White List - Invasive Plants and Trees • Draft Black & White List - Marine and Aquatic Invasive Species • Draft Black & White List - Invasive Animals+Diseases Finally, a wealth of information on invasive species, including guidance and best practices, were compiled, organized, put online, and communicated: https://sites.google.com/view/gef6palau/gef6-key-sectors/invasive-species The EDRR and Inter-island Biosecurity outputs are still behind, but partnerships to develop the systems have been established. |
| The progress of the objective/outcome can be described as: | On track |  |  |  |  |
| Evidence uploaded: | YES |  |  |  |  |
| Outcome 2 Outcome 2 Integrated multi-sector land and seascape “Ridge-to-Reef” planning and management operational in Babeldaob states to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies |  |  |  |  |  |  |
| Description of Indicator | Baseline Level | Midterm target level | End of project target level | Level at 30 June 2020 | Cumulative progress since project start |
| Indicator 8: Number of hectares of high conservation value ecosystems, including forests, mangroves and marine areas zoned/allocated for non-exhaustive use | High Conservation Value Forests (dispersal corridors, biodiversity rich areas and buffer areas) outside protected area network lack appropriate management regimes | High Conservation forests including mangroves and marine areas for non-exhaustive use mapped and at least 2,500 ha, allocated for non-exhaustive use | High conservation value forests, (including mangroves and marine areas) allocated for non-exhaustive use of at least 15,500 ha, resulting in total avoided 435,492 tCO2 over 20 years | This work on this indicator is behind but will be accomplished through mapping as part of the JCB planning process. The schedule includes specific outputs to prioritize and address the needs of high conservation value areas. 1,460 hectares of riparian forest that is zoned for non-exhaustive used based on updated EQPB water quality regulations that mandate a 60-foot buffer on either side of streams and rivers. (This is in addition to riparian areas inside protected areas.) Outside of GEF6 but related to its overall mission of sustainable management, EQPB adopted regulations that mandate protection of a riparian buffer. The GEF6 spatial planning process is mainstreaming these regulations into state planning. | This indicator is on track. CUMULATIVE: 2,944 hectares of upland forest on Babeldaob currently regulated or identified and potentially set aside for non-exhaustive use on Babeldaob. Values from: • 1,460 hectares of riparian forest regulated by EQPB regulations. • ADDED IN 2021: 1,484 hectares (OUTSIDE OF PROTECTED AREAS) potentially zoned for non-exhaustive use for water source protection; agreement from Babeldaob JCB but needs State agreement. See map: https://drive.google.com/file/d/1qOZdUUTMvSonWb7t0q4MGr20gFtNr1oq/view?usp=sharing See SPREADSHEET: https://docs.google.com/spreadsheets/d/1oBPGd6-ISDPL3YrLfqyYIwodIVNl1-t2uJ_ToryKip0/edit?usp=sharing The Babeldaob Joint Coordination Body meets regularly and in the past year agreed to a Babeldaob-wide land use designation guide that incorporated biodiversity safeguards. This included agreeing to tentative housing subdivision areas as recommended by the SMCE (Spatial Multi-Criteria Evaluation) tool first developed by the KBRUDSAP and then localized for Babeldaob by the JCB. The SMCE criteria include avoiding important forest areas (identified in Palau’s Statewide Assessment of Forest Resources, SWARs) plus making high-value areas the lowest possible suitability (mangroves and upland forests). See: • Final Housing Subdivision Criteria • Babeldaob Map with proposed Housing Subdivision Restrictions The Babeldaob JCB also agreed that water sources should be protected and agreed to the drawing of tentative borders around entire watersheds draining into public water systems. JCB Members agreed that these areas would be proposed for non-exhaustive use in the State Master Plans. One State, Ngatpang, is considering turning its watershed above a public water source into a Terrestrial Protected Area and thus contributing to the Palau PAN. Work is also underway to identify marine areas for non-exhaustive use. In Koror’s waters, the entire Southern Lagoon has been mapped with proposed fisheries management areas, which include new protected areas. Similar efforts are underway on the west and east coasts of Babeldaob. All 10 States on Babeldaob participate in the Babeldaob JCB and have agreed to comprehensive land use planning and master planning. In this way, entire States will be zoned in a ridge-to-reef systematic manner. |
| Indicator 9: Number of hectares of degraded forests and grasslands and coastal and marine areas outside PAN network rehabilitated | Over 12,500 hectares of forests, grasslands and coastal and marine ecosystems under continued degradation through overuse | At least 100 ha of degraded forests, grasslands and marine ecosystems under restoration through community actions | At least 1,000 ha of degraded forests, grasslands and marine ecosystems restored through community actions resulting in total sequestration of 562,133 tCO2 over 20 year period | The indicator is on track. Community action plans in 4 States that were ready by June 2020 covered 0.9 hectares (9000 square meters). Work to complete actual rehabilitation had not started by the end of June. On the ground restoration work commenced in July 2020 in 2 States. This work is progressing, with 7 partner States on Babeldaob (plus Peleliu in the Southern Lagoon) planning action on the ground to reforest or rehabilitate degraded lands in 2020. To facilitate these community actions, Planning teams are in place and functional, and each Planning Team has a draft or final Restoration Action Plan. The project has provided tools and training to facilitate selection of sites, writing of Action Plans, and use of Best Practices. In addition, the project has compiled existing Best Practices, as well as identifying many new Best Practices that protect biodiversity and provide social safeguards. These BMPs are accessible to the public via a website, have been highlighted in communications to partners, and have been discussed in person via technical support. The project has guided the State Planning Teams to identify the needed support or to select the most appropriate BMPs, while at the same time enabling community input. When States first began drafting Action Plans they sought technical advice from a variety of government, NGO, online, and community sources, and some plans included introduced plants. After identifying sources of information, the project worked to improve input into State plans so that restoration plans mainstream national policies and Best Practices. Now the project and its partners – MNRET, BOA, BD – cite the same Native and Non-Native Plant policy when recommending which plants to use or which methods to use when rehabilitating land. The EPU actively guided States towards using native plants. | This indicator is off-track. In the 2020 PIR, this indicator was deemed on-track because Action Plans were developed for enough land to meet the target. However, when plans were actually implemented it was quickly realized that the plans were over-ambitious and that the labor was much more intensive than planned. Palau's soils are so poor and hard that they need much more effort to replant than was originally planned. There is no way this Indicator can be achieved. Work is labor-intensive and soils are very poor. Suggestions include: 1) reduce the target, 2) tracking a different indicator such as number of trees requested, 3) change the indicator so that we are measuring hectares of land converted from degraded land to some better use (e.g. agriculture). As of June 2021, 26.68 hectares had been restored. See online Table: https://drive.google.com/file/d/1SiCOHXnHqtuac_x4OmbMjPDeptC2Z1g2/view?usp=sharing See map: https://drive.google.com/file/d/1qOZdUUTMvSonWb7t0q4MGr20gFtNr1oq/view?usp=sharing Prior to accessing funds, Project Partners had to write Action Plans that incorporated biodiversity and social safeguards and using Best Practices, including using native species or otherwise following a GEF6 Native and Non-native Plant Policy. Restoration activities included tree planting to control erosion, removal of eroded sediments from streams to allow for natural water flow, and removal of invasive vines along roads. The GEF6 directly financed efforts in 7 States on Babeldaob plus Peleliu, and there were additional partner-led efforts by BOA, EQPB, and Ebiil Society. This indicator is off-track and may need to be REVISED. Restoration of degraded forests and grasslands is very labor intensive and progress is incremental. The Project may need to identify technical assistance to identify a more realistic target. |
| Indicator 10: Change in status of populations of Micronesian Imperial Pigeon and Palauan Fruit Dove | Declining populations of Micronesian Imperial Pigeon and Palaaun Fruit Dove with baseline of 3,000 and 1,600 individuals respectively (2014) | Maintained populations of Micronesian Imperial Pigeon and Palauan Fruit Dove from current baselines | Maintained or improved populations of Micronesian Imperial Pigeon and Palaaun Fruit Dove from current baselines | This indicator measures an end output of the project and thus it is too early in the project to see any changes. Evidence of stable or increasing populations for both species. 2020 (data through 2019 from SOE): --Pigeons: Possible evidence of a slight population recovery within the Ngeremeskang Bird Sanctuary (draft 2019 State of the Birds report). --Doves: Highest recorded mean number of Doves at Long Island in Koror - also evidence of stable or increasing populations (2018 State of the Birds Report). Monitoring programs are in place and data on the indicator is being collected regularly. The project encouraged analysis and presentation of the data in such a way that it could be compared over time. The very process of analyzing these indicators has identified sources of data and provided a more streamlined process for feeding science into policymaking. State restoration plans require both process and outcome indicators. By learning to use these templates, State Planning Teams are becoming better versed in Results-Based Management and the utility of indicators. | This indicator appears to be on track, although data is not clear. Although data is collected regularly (monthly), it was not analyzed in time to update the PIR. Activities to achieve this indicator are underway. However, a new report analyzed bird data from 2005 in preparation for new surveys in 2021. The Project has mainstreamed protection of terrestrial biodiversity into its outputs, including protection or avoidance of upland forests in the Babeldaob land use guidance maps and improved IAS frameworks, including monitoring for brown tree snakes at the border. Awareness of biodiversity has increased, and project partners have reviewed the laws protecting native birds and at least one NGO (PCS) has included in its Strategy the goal of updating the Protected Land Life act to better protect birds. Partnerships with the PAN are in place to improve monitoring of IAS in protected areas and thus avoid new threats to birds. Enforcement partners also started a species review. Out of the ongoing Enforcement Partners assessment and review, DFWP identified the need for and then began working with the Attorney General’s office to be able to issue citations. (Currently DFWP has to elevate every enforcement action to a criminal case, which is difficult and thus many infractions are not pursued.). Beyond birds, the Enforcement Partnership led to improved enforcement of a Hawksbill Sea Turtle law, thereby better protected an endangered species that uses land and sea. Project partners mapped terrestrial tourism locations, most of which included some forest. The JCB agreed to zone tourism are for non-exhaustive use, further protecting the habitats of birds. |
| Indicator 11: Extent of community-based land, forest, coastal and marine management regimes applied, including resultant changes in community incomes from current levels | Current extent of area under community land, forest, coastal and marine management regimes in target project states (to be determined in Year 1) | Areas for community-based management totaling at least 500 ha identified and agreed through a consensus building process, as part of the community-based planning process. | Community-based land, forest, coastal and marine management regimes applied in at least 500 ha of additional areas, resulting in sequestration of 460,681 tCO2eq over 20-year period and in 25% increase in community incomes from current levels, of which at least 50% of beneficiaries are women. | The baseline will be set during the JCB Spatial mapping process, with a baseline set by October 2020. States have identified small areas to begin community management. Action on the ground has not yet started, and thus it is too early to judge changes to income or carbon. | This indicator is on track. Project partners have identified 1,437 hectares across 160 sites and achieved initial agreement (either within the JCB or within State Governments) to manage these areas for low-impact uses, especially with income opportunities. These include access to and improvements to taro patches or farming in Ngarchelong and Ngiwal, access and best practices for aquaculture in Ngeremlengui, and State, village, or community-run tourism in Ngaraard, Ngardmau, Ngchesar, Aimeliik, and Peleliu. 1) 28.38 hectares in 2021 Action Projects 2) 1,004 hectares from tourism sites (agreed by JCB for non-exhaustive use; sites were identified by State representatives). 3) 405 hectares from tourism buffers (a 300-foot buffer around tourism sites). See map of action sites: https://drive.google.com/file/d/1qOZdUUTMvSonWb7t0q4MGr20gFtNr1oq/view?usp=sharing See map of Tourist sites (scroll to page 5): https://drive.google.com/file/d/1YIk75wJTkQ1d4zlHgZ51FvnoYcKuqgbI/edit See Spreadsheet Table: https://docs.google.com/spreadsheets/d/1TEu5P5TnTZ1iFzk_crK2mnnJxXpOYS60jZAlUE3cV9Y/edit?usp=sharing |
| The progress of the objective/outcome can be described as: | On track |  |  |  |  |
| Evidence uploaded: | YES |  |  |  |  |
| Outcome 3 Outcome 3 Integrated multi-sector planning and management operational in 264,686 ha of seascapes and coastal areas in the Southern Lagoon to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies |  |  |  |  |  |  |
| Description of Indicator | Baseline Level | Midterm target level | End of project target level | Level at 30 June 2020 | Cumulative progress since project start |
| Indicator 12: Change in status of fish stocks in designated reef and sea grass areas based on biomass indices | Protected exposed reefs (outer reefs and channels) of 714kg/ha (with unprotected exposed reefs having 63% of this figure compared with MPAs) and 258kg/ha in protected inner reefs (black reefs and patch reefs/reef flats) with unprotected reefs having 57% of this figure compared with MPAs | Maintained fish stocks in designated zones from existing baselines in unprotected exposed outer and inner reefs | Maintained or improved fish stocks in designated zones from existing baselines in unprotected exposed outer and inner reefs | Action on this indicator is progressing slowly, with assessments and planning for the Southern Lagoon. Awareness of reduced fish stocks has increased and there is growing support for additional management of coastal fisheries. Much of that effort is being directed at the PNMS – shifting fishing pressure to offshore fisheries. MPAs remain a focus within PAN, but are receiving less attention than before. Messaging must be carefully balanced – with “food security” being a more successful message than “biodiversity conservation” – particularly now during the Covid-19 economic downturn. A Koror State Planning Team has been formed and has begun a collaborative review of a new Rock Island Management Plan. Given the complicated political and Covid-influenced economic situation in Koror State, having a functioning State Planning Team is an achievement. Koror State is facing a significant budget shortfall due to the border closure and crash of tourism due to Covid-19. Engagement with Koror State must be done carefully and with sensitivity to livelihoods, and thus is progressing very slowly. So far the planning team has approved goals that include better management of fisheries and reefs. There is a risk that loss of income due to Covid-19 will drive unsustainable fishing in Koror waters. The loss of tourism income is negatively impacting the ability of the Department of Conservation and Law Enforcement – particularly the Rangers – to monitor and enforce Progress in establishing a Southern Lagoon JCB has also been similarly slow. Bylaws and SOPs have been created and approved, but the membership has not been approved by the Koror Governor. Thus, coordinated efforts by Koror and Peleliu to plan for fish stocks in the Southern Lagoon has not begun. Given the ongoing shifts in focus, as well as delays and changing needs due to Covid-19, it may become necessary to adapt the project activities under this Outcome. | This indicator appears to be on track, although data is not clear. Project partners have updated their monitoring protocol to be more scientifically and thus the Project can no longer measure progress with these measurements. However, Project Activities are underway to achieve this work (especially zoning in Koror for fisheries). PICRC has completely changed the way it monitors fish stocks, so as to implement a monitoring program that focuses on fish that are harvested - the previously used indicator monitored fish as an indicator of coral reef health and this information could not be used accurately to determine fish stock status. PICRC established a new baseline in 2020 based on data collected in 2017. This program does not monitor fish stocks in seagrass. PICRC will monitor fish every two years. NEW BASELINE: • Mean biomass across all sites = 17.06 + 2.51 g/square meter. • Mean biomass on Fore Reef West = 30.38 +/- 5.55 g/square meter. • Mean biomass on Fore Reef West = ~19 g/square meter. • Mean biomass on Channel = ~15 g/square meter. • Mean biomass on Fringing Inner Reef = ~6 g/square meter. • Mean biomass on Patch Reef = 4.76 +/- 0.69 g/square meter. See 2020 PICRC Report on 2017 Fish Survey: https://drive.google.com/file/d/19lhIgu6UyH0iGobnBgczbPwezaEPT-cf/view?usp=sharing The report does not assess change over time but sets a new baseline. Prior to Covid, all anecdotal reports suggested a repeated decline in nearshore fisheries stocks. Since the borders closed due to Covid, reports are mixed, with some reports of increased fish stocks and some of decreased fish stocks. There will be no data to compare over time until PICRC repeats its fishery survey. Partners validate – anecdotal reports vary. Regardless of the data, significant progress on fisheries was made in Koror and the Southern Lagoon. Koror State completed revisions of its Rock Island Southern Lagoon Protected Area Management Plan and sent it to leaders for the final approval. It included actions to improve fisheries protections. Immediately after, Koror began a comprehensive mapping and zoning project. The project is co-financed and led by PCS, but other GEF6 Project Partners have been heavily involved and GEF6 funding enabled spatial mapping and zoning of the entire lagoon. Through this project Koror is planning for the sustainable use of 60 species of fish. See: • Zoning that has been proposed for the entire Southern Lagoon, based on fisheries management zones • Meeting agenda showing partnership of PALARIS and MAFE EPCU (GEF6) • Species of Fish that are being planned for • Presentation on update of RISL Management Plan • Photos of mapping in Koror Because it is not possible to compare this indicator over time using prior data, this indicator may need to be REVISED. |
| Indicator 13: Change in status of coral cover at designated sites | 27% of reefs have “medium” coral cover (25-50% cover), while 13% of reefs have “low” coral cover (<10% cover) | Maintained percentage coral cover at designated sites from existing baseline | Maintained or increased percentage coral cover at designated sites from existing baseline | Action on this indicator is progressing slowly. Similar to Indicator 12, shifts in needs and attention may require adaption by the project. Identification of High Value sites – including reef sites – is included in the work plan for the Babeldaob JCB and mapping of High Value sites will occur through both the Babeldaob and Southern Lagoon JCB processes. JCB Bylaws and SOPs, as well as the plans, including identifying and designating conservation zones. Again, messaging must proceed carefully, with less discussion of “biodiversity” and more discussion of “sustainable use” given the worsening economic situation. The Covid-19 situation may actually enable a rebound in coral health in tourist sites, although it is too early to know for sure. | This indicator is off-track, although data is not clear. Work on this indicator is behind, although through fisheries zoning in Koror, significant progress has been made to identify high value coral reef sites and protect them (as fisheries habitat or valuable reefs (see Shark City bathymetry)). Planning for multiple sectors in Koror (beyond fisheries) was included in the RISL Management Plan update but still needs spatial planning. Work with Peleliu is slow. The Joint Planning process with Koror and Peleliu has been paused indefinitely due to political difficulties. Project partners have updated their monitoring protocol to be more scientifically and thus the Project can no longer measure progress with these measurements. PICRC has stopped measuring "Areas of High Coral Cover" and instead monitors live coral cover. A revised baseline is possible. In addition, this indicator does not measure project progress as climate change has an overwhelming influence. In PICRC’s most recent report the following baselines can be established: • Outer Reef West live coral cover at 3 and 10 m: 23 and 44%; • Outer Reef East at 3 and 0 m: 10 and 12.8%; • Patch reefs at 3 and 10 m: 30 and 17%; • Inner Reefs at 3 and 10 m: 45 and 39%. Compared to the previous monitoring period (2016): • Live Coral Cover increased at both 3 meters and 10 meters depth on the Outer Reef West and Outer Reef East; • Decreased at both 3 meters and 10 meters depth on Patch Reefs; and • Decreased at 3 meters and increased at 10 meters on Inner Bay Reefs. Compared to a revised baseline, live coral cover decreased in one location due to tropical storm impacts, increased in one location as recovery from a previous storm, was stable in one location, and had mixed increases/decreases in another location. 2020 PICRC Report on 2018 Coral Reef Status: https://drive.google.com/file/d/1i_ccqDUdUoGKqEPlysAkBlEQXjaQYPbk/view?usp=sharing They conclude that "coral reefs in Palau are in relatively good state apart from the eastern outer reefs that are still recovering, four to five years after typhoon disturbances" Climate change has more of an impact on this indicator than management. Reefs are in good health, except where storm impacts have reduced coral cover. Live Coral Cover does not appear to be impacted by the project. In terms of action, this Project has so far focused attention on land and terrestrial planning and mainstreaming and has not yet changed its focus to marine areas, especially on Babeldaob. However, zoning in the Koror Southern Lagoon is further protecting critical fish habitats, including coral reefs. Many of these areas already have high coral cover. Work in Peleliu this year is behind schedule, thus the indicator is deemed off-track. Because it is not possible to compare this indicator over time using prior data and the indicator may need to be REVISED. |
| Indicator 14: Change in nesting success rates (number of nests, number of eggs, hatchlings and survival rates) for Micronesian megapodes in selected sites previously occupied by rats | Current status of Micronesian megapodes nesting success in selected islands established in Year 1 | Maintained population of Micronesian megapodes from selected sites previously occupied by rats from current baseline values | Increased nesting success rates of Micronesian megapodes from selected sites previously occupied by rats from current baseline values | The baseline for this indicator has been set at 15 total nests: 9 active and 6 inactive (December 2018). Action on this indicator is progressing slowly. Biosecurity in general has been included in a revised management plan for Koror’s Rock Islands; the Project is facilitating a review of this draft and will ensure that biosecurity measures include this site. | There is no new data on this indicator and activities, and thus it appears to be off-track. Koror State has continued with enforcement and Biosecurity, but during this Covid-era, the risk of re-introduction from tourist activity has been low. The project is behind in terms of Early Detection and Response and Inter-island Biosecurity at the nationwide level, and thus has not been able to implement actions in Koror or Peleliu. Work in Peleliu this year has focused on trail development in a sustainable manner, so that runoff is minimized and birds and biodiversity are protected and promoted. This includes avoidance of any megapode nests in the area. The trail passes through a private sanctuary set aside for birds, so it will utilize best practices. This work is proceeding very slowly and is behind schedule, thus the indicator is deemed off-track. |
| The progress of the objective/outcome can be described as: | Off track |  |  |  |  |
| Evidence uploaded: | YES |  |  |  |  |
| Outcome 4 Outcome 4 Knowledge management, monitoring and evaluation support, equitable gender benefits and biodiversity conservation in Palau |  |  |  |  |  |  |
| Description of Indicator | Baseline Level | Midterm target level | End of project target level | Level at 30 June 2020 | Cumulative progress since project start |
| Indicator 15: Increase in percentage of sampled community members, tour operators and sector agency staff aware of potential conservation threats and adverse impacts of IAS | Coordinated outreach on conservation threats and biosecurity lacking. Limited awareness of impact IAS among general public. Baseline survey established in Year 1 | At least 5% of sampled community members and 20% of, tour operators and sector agency staff aware of potential conservation threats and adverse impacts of IAS | At least 25% of sampled community members and 75% of tour operators and sector agency staff aware of potential conservation threats and adverse impacts of IAS with equitable knowledge among genders and social groups of which at least 50% are women. | The baseline for this indicator has not yet been finalized, but is expected by September 2020. A KAP Survey was designed, tested, and is ongoing, but enough data has not yet been collected to establish a baseline. This KAP Survey process is behind, but is making progress. Other than establish a baseline, action on this indicator is not scheduled until later in the project. Awareness of IAS and Biosecurity is increasing within specific target audiences – State Planning Teams – as they have become familiar with IAS and Restoration Best Practices, including best practices for native and non-native plants. Because of delays with the National IAS Framework (Outcome 1, Indicator 7) progress on this indicator will likely be delayed as well. However, the project has already adapted yearly work plans to accommodate this delay. Gender mainstreaming in the establishment of Planning Teams has increased the number of women participating in activities, thus ensuring growth in women’s awareness and capacity. | In terms of activities, this indicator is ON TRACK. The KAP report was finally completed. See the report, data, and presentations. The newly established Baseline shows that 46-65% of tour operators are aware of potential conservation threats and impacts of IAS. (Green Fins had already been implemented by the time survey was conducted). Baseline also indicates that 63-84% of community members are aware of conservation threats and impacts of IAS. Given the existing high numbers of awareness about adverse impacts, this indicator does not seem to be relevant. In terms of activities, this indicator is ON TRACK. Suggested changes that use the existing KAP data include: 1) % of survey respondents who report "knowing how to minimize the impact of IAS" a. Baseline would be 34% YES, 37% NO, 29% NO ANSWER. 2) Average number of Invasive Alien Species (IAS) listed by respondents. a. Baseline would be 1.5. 3) % of respondents incorrectly identifying native species as Invasive Alien Species. a. Baseline would be 65%. See spreadsheet: https://drive.google.com/file/d/15u-jP9hQi1-UoiiEtZdddfcQwWuDU1Ej/view?usp=sharing New Indicators would need stakeholder input and Board approval, but the EPCU suggests the following Targets: 1) % of survey respondents who answer YES to knowing how to minimizing impact by EOP increases to 75%. 2) Average number of IAS listed by respondents increases to 5 out of 20 priority IAS plants and 20 priority IAS animals. 3) % incorrectly identifying native species as IAS declines to less than 25%. In terms of action, the Project has collated information on invasive species and begun communicating it to the public and to partners. Project partners (PCS) are also improving IAS awareness and technical skills among PAN Rangers. In terms of Sustainable Tourism, a framework for a Sustainable Tourism Certification program was developed, but it has not yet been reviewed. See: https://docs.google.com/document/d/1GqAwyhpYPBPad1XofxnftZnXyFFfinURGOOm5PsNG2Q/edit This indicator may need to be REVISED to reflect the actual awareness needs, since knowledge of conservation impacts of IAS is already high. Also, this survey will not be repeated until EOP. |
| Indicator 16: Percentage of fifth-grade students received updated “ridge to reef” curriculum, including IAS | Fifth-grade curriculum lacks emphasis on integrated landscape and seascape planning and threats of IAS | Curriculum updated to include biosecurity and IAS | At least 90% of fifth-grade students received updated “ridge to reef” curriculum, including IAS of which 50% are females | Same as baseline. Action on this indicator is scheduled for later years. | This indicator is on track. Educational activities with the Ministry of Education have not begun in earnest and the curriculum has not been updated yet. However, there have been an increase in the number of invasive species outreach programs offered by PMU and by Project Partners, both to students, resource managers, and the public. See the PowerPoint for example of public outreach. Partners conducted organized outreach programs on Invasive Alien Species that reached almost every student last year. See agenda and photos. Public outreach on native species and invasive species has increased through weekly emails, public presentations, and community events. The KAP survey will help refine the curriculum so that it meets specific needs. |
| Indicator 17: Number of best practices of sustainable land, coastal and marine resource use up-scaled by communities/households | Best practice and lessons from GEF 5 available, but currently resources do not exists for their implementation | At least 1 Best Practice per sector being implemented (total of 5: agriculture, aquaculture, fisheries, forestry, sustainable tourism) | At least 18 best practices of sustainable land, coastal and marine resource use up-scaled by 9 communities and used by both genders and multiple social groups. | This indicator is on track. 2 Best Practices (species and mulching) were consistently applied to State Action Plans addressing reforestation (of those that were drafted by June 2020). The project has compiled over 50 Best Practice documents, vetted and catalogued them, and posted them on the GEF6 website. The website and the BMPs have been promoted heavily through weekly emails and social media. The Digital Library and the Best Practices pages of the GEF6 website are the most frequently accessed pages (after the home page). The project has established an evolving set of General, Environmental, Biodiversity, Biosecurity, Climate, and Financial Safeguards that incorporate BMPs, national policies, laws, and best available science. Some BMPs were newly established based on pressing needs – e.g. which species to plant and streambed cuttings. Safeguards and relevant BMPs have been communicated and explained personally to State Planning Teams. Given the variety of BMPs and the breadth of State Planning Team needs, this has been a slow process. The EPU facilitated discussions with BOA, NISC, and BD to settle on Biosecurity Safeguards and establish a Native and Non-native Plant Policy that incorporates science and Best Practices. The Best Practices in use by State Planning Teams indicate uptake and learning from others – for instance, previous planting projects have failed without mulching. | This indicator is on track. 18 Best Practices developed or advocated by the Project or GEF6 Partners, all being implemented in at least one location in each sector. Those being scaled up (to multiple locations): • 1 in Agriculture, • 3 in Forestry, and • 3 in Sustainable Tourism = 7. See spreadsheet: https://docs.google.com/spreadsheets/d/1aXiKJWpLeSyZUNQwAYlYcZ2LprgfC3pxk__5dexzFWc/edit?usp=sharing The 2020 Natural Resource Study, which was completed to enable gender mainstreaming in this indicator, examined which best practices are used by different gender and social groups. |
| The progress of the objective/outcome can be described as: | On track |  |  |  |  |
| Evidence uploaded: | YES |  |  |  |  |

## Action plan

| Off-track objective/outcome | Action(s) to be taken | Responsible party/ies | Due Date |
| --- | --- | --- | --- |
| Outcome 3 | PMU continues to work with Koror and Peleliu individually to achieve objectives, and it requires dedicated time and effort. For instance, PMU reached out to Peleliu and will be traveling there to work with them individually to implement actions. Corrective action has already been taken with BOT with assigning of GEF6 tasks to a new project manager who is overseeing implementation of tourism activities. Progress on the national Early Detection and Rapid Response plan is progressing slowly because of financial issues, but when this is completed then it can be implemented with these states. All activities are already in place but the tenders need to be financed and issued. | PMU remains the responsible party for the majority of work, working with Koror and Peleliu. BOA is responsible for EDRR work. BOT is responsible for tourism work, but PMU is partnering very closely with BOT and Palau Visitor's Authority to ensure activities are carried out. | Oct 1, 2021 |

# Implementation Progress

| Cumulative GL delivery against total approved amount (in prodoc): | 22.31% |
| --- | --- |
| Cumulative GL delivery against expected delivery as of this year: | 26.62% |
| Cumulative disbursement as of 30 June: | 944,599 |

| Key Financing Amounts |  |
| --- | --- |
| PPG Amount | 150,000 |
| GEF Grant Amount | 4,233,562 |
| Co-financing | 22,671,306 |

| Key Project Dates |  |
| --- | --- |
| PIF Approval Date | Apr 19, 2016 |
| CEO Endorsement Date | May 25, 2018 |
| Project Document Signature Date (project start date): | Jul 16, 2018 |
| Date of Inception Workshop | Nov 6, 2018 |
| First Disbursement Date | Sep 21, 2018 |
| Expected Date of Mid-term Review | Jul 16, 2021 |
| Actual Date of Mid-term Review | (not set or not applicable) |
| Expected Date of Terminal Evaluation | Apr 16, 2024 |
| Original Planned Closing Date | Jul 16, 2024 |
| Revised Planned Closing Date | (not set or not applicable) |

Dates of Project Steering Committee/Board Meetings during reporting period (30 June 2020 to 1 July 2021)

2021-06-17

2021-04-08

2020-12-22

2020-09-10

Project Manager: Please provide comments on delays this reporting period in achieving any of the following key project milestones outlined in the above 'Key Project Dates' table. Include comments on COVID-19 related challenges, delays and impact. If there are no delays, please indicated 'not applicable'.

The Mid-Term Review due date was delayed by a month due to difficulty retaining a National Consultant. Because borders were closed due to Covid-19 the International Consultant could not travel to Palau and thus having an on-island National Consultant was critical. Many of the stakeholder meetings were held by Zoom, which were at times difficult to schedule. Key project personnel were able to meet by Zoom, but some rural stakeholders may have been missed. Tourism-related outputs continue to be delayed because of the Covid-19 border closure. Best practices and Certification programs are prepared but have been able to be tested due to few tourists. Additionally, tourism activities have refocused on Pandemic Safety as an enabling condition. With the borders being closed it has not been possible to hire off-island experts and consultants, resulting in low financial delivery and delayed outputs (such as installation of X-ray machines, creation of an Early Detection and Rapid Response system, etc.). While the Project has attempted to work around the border closure with local expertise and Zoom, this creates additional difficulties in that the local labor pool is very small and it is difficult to source and utilized expertise via Zoom.

CO Programme Officer: Please include specific measures to manage the project's implementation performance

The expected date for completion Mid Term Review is delayed by a month. Originally this was planned for 16 July (2021) but is expected to be completed by August 30. The project experienced slippage when the first recommended candidate for national consultant (mid term) review took up senior position within Government and the second best candidate was approached. After consultations with UNDP, team of consultants and Project Implementation Unit , a decision was made to extend this review until August. This is to ensure thorough consultations with more than state governments, national governments department, non governmental organizations and communities. The approach was also taken given that Team Leader (international consultant ) could not travel to Palau due to Corvid 19 restrictions.This decision is in the best interests of all parties as it would support a thorough assessment and allow for well informed recommendations.

NCE RTA: Please include specific measures to manage the project's implementation performance.

The MTR has been completed. The process has been managed virtually, with a consultant based in South America. The TE is currently scheduled for April 2024 and no change is expected. COVID restrictions continue to hamper implementation where it is not possible to bring international expertise and consultants into the country, which has resulted in low financial delivery and delayed outputs. Efforts will be made to catch up as COVID restrictions ease. The project is very fortunate to have a skilled and committed project team who continue to work hard to deliver project results.

# Project Governance

Dates of Project Steering Committee/Board Meetings during reporting period (1 July 2020 to 30 June 2021). Please also upload all meeting minutes using the FILE LIBRARY button.

2021-06-17

2021-04-08

2020-12-22

2020-09-10

# Ratings and Overall Assessments

| Role | 2021 Development Objective Progress Rating | 2021 Implementation Progress Rating |
| --- | --- | --- |
| UNDP-NCE Technical Adviser | Moderately Satisfactory | Moderately Satisfactory |
| UNDP Country Office Programme Officer | Satisfactory | Satisfactory |

| Role | 2021 Overall Assessment |
| --- | --- |
| UNDP-NCE Technical Adviser | This is the second PIR for the full-sized GEF project, 'Integrating biodiversity safeguards and conservation into planning and development in Palau', which was launched in 2018 and is scheduled to close in 2024. The project has just undertaken its MTR. The project aims to address the negative impacts of unsustainable sector-led development practices on biodiversity-rich landscapes of Palau, including its productive coastal and marine ecosystems, while taking into account climate change adaptation needs and inclusive and equitable social and economic development for dependent communities, as well as safeguarding against threats to biodiversity and the introduction and spread of Invasive Alien Species through the tourism and related sectors. The objective of the project is to mainstream biodiversity conservation into integrated land and seascape governance, planning and management in Palau. The project recognizes the fact that these land and seascapes underpin the lives and livelihoods of a large number of local communities and that implementation of a coherent strategy to promote sustainable, biodiversity-friendly livelihood options is an integral part of the solution. The project objective is to be achieved through the implementation of four inter-related and mutually complementary Components (Project Outcomes) that are focussed on addressing existing barriers. The four Outcomes of the project are: Outcome 1: Enhanced national institutional framework for integrated planning and management of land and seascapes; Outcome 2: Integrated multi-sector land and seascape planning and management operational in Babeldaob states to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies; Outcome 3: Integrated multi-sector planning and management operational in 264,686 ha of seascapes and coastal areas in the Southern Lagoon to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies; and Outcome 4: Knowledge management, monitoring and evaluation support, equitable gender benefits and biodiversity conservation in Palau. Unfortunately, the project had a slow start with delays related to recruitments, meeting project management and reporting guidelines and COVID. The Project Management Team was reduced in the past year, and now consists of a Project Manager, Technical Advisor, Financial Support, and a Project Specialist (with links to GEF5). This increases risks in this complex project, where a small team is required to manage 20+ partners. However, the project has a solid support network in place, including support from high level governance, and is managed by a professional and dedicated PMU. In addition, the recent MTR has judged the project to be far too ambitious; the complexity of the project design and the number of targets is challenging for a small PMU to achieve in a micro-SIDS. The final MTR report, which was completed in this reporting cycle, gave the project an overall rating of Moderately Satisfactory. The project is behind schedule relative to the mid-term targets but with a revised implementation strategy, the project could still achieve end of project targets. This assessment concurs with the findings of the MTR. The project’s Development Objective (DO) and Implementation Progress (IP) can both be assessed as Moderately Satisfactory during this reporting period. Progress is on track at the Objective level as a whole, which seeks to to mainstream biodiversity conservation into integrated land and seascape governance, planning and management in Palau. Some outputs have been achieved, although several other outputs, expected processes and outcomes that make up and articulate the objective have not yet been met at mid-term. Delays in delivery have had an impact on the achievement of the objective thus far. Delays are due to delayed project inception, the impact of the pandemic and implementation issues (weak reporting, management, etc.). Progress can be considered on track for Outcome 1, which aims to enhance the national institutional framework for integrated planning and management of land and seascapes. There are some notable shortcomings in the achievement of results due to COVID. But important groundwork has been laid to support institutional framework analysis, review policy frameworks, upgrade policy tools, and generate plans for biodiversity management and land use planning. Capacity has been enhanced at different levels in key institutions as the evidence demonstrates. Progress can be considered on track for Outcome 2, which aims to ensure integrated multi-sector land and seascape planning and management in Babeldaob states to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies. The development of planning tools is underway, including mapping. Policies and plans have been upgraded and national and state level enforcement to reduce threats has been strengthened. Some expected outputs not on track due to context changes and over-ambitious design that does not fully appreciate the Palau context. Concrete demonstration pilots are being implemented per the provided evidence. Progress can be considered off track for Outcome 3, which aims to ensure Integrated multi-sector planning and management operational in 264,686 ha of seascapes and coastal areas in the Southern Lagoon to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies. Issues with baseline have hindered the possibility of properly accounting for the achievement of products and/or results. Per the available evidence, technical groundwork for several planning tools has been put in place. Contextual tools have been developed and evidence/data have been gathered for informed decision-making and planning (using GIS). Progress can be considered on track for Outcome 4, which aims to assure knowledge management, monitoring and evaluation support, equitable gender benefits and biodiversity conservation in Palau. This Outcome deals with a series of products and processes that have been achieved to a good degree as the evidence demonstrates. Communication processes are constant and active, particularly for the last 18 months. Knowledge products have not been produced as targeted however, but stakeholders are keen to combine with other technical outputs to accelerate delivery. Through this outcome, the project is promoting equitable gender benefits, yet it is hindered by resistance to gender mainstreaming. The project’s implementation can be considered Moderately Satisfactory. The overall financial delivery against total amount approved is 20.3%, which is low. This has been due to delays in disbursements due to procedural and reporting complications. Specifically, the national reporting system differs from the required financial reporting by UNDP, necessitating procedural reconciliation around budget lines, entries, budget codes, etc. While efforts were taken to remedy the situation, this further delayed delayed disbursements and hindered procurement. There were also misunderstandings about how to report expenses. Since some activities and therefore budget lines are in the Project Document but not in the log frame per se, this necessitated time-consuming revisions. These revisions not only have affected financial accounting but also work planning for the current year (2021). Financial reporting tools also proved to be burdensome for the PMU, and this has also been a reason for delivery delays. Nevertheless, the project demonstrates due diligence in the management of funds as the project team spend funds according to approved work plans. The project is subject to audit once spending reaches and exceeds the value of US$450,000 in a year as per UNDP CO’s audit threshold and requirements. There have no audits as yet since the spending threshold has not been met. The recent MTR set out the following 15 recommendations to reorient project implementation: 1. The project needs to be reviewed in order to –among other aims-- correct its course, in particular concerning some design features. 2. A broad scoped analysis on the indicators has to take place to further refine and aid the reformulation. 3, Strengthen the project implementation architecture by hiring additional personnel that can provide backstopping for operational processes and for technical support. 4. The project implementation unit and management structure should not only be strengthened but it should also have clearly defined roles and should follow these roles definitions. 5. In tandem with the above, Project should intensify and increase the technical work needed to implement pilots, and to generate / implement tools for integrated planning, as well as to generate knowledge management products. 6. The Project should continue training, information dissemination, and other such activities based on its gender analysis and strategy as well as based on the Gender and Natural Resources 2020 National Report that the Project commissioned. Gender mainstreaming should not be a pillar or only associated to a particular outcome. This is a cross-cutting issue to be imbedded in all pilots, demonstrations, plans and activities. 7. The Project should begin the elaboration of a sustainability plan / exit strategy, in particular in order to cement capacity within Palau and to secure institutional and financial sustainability, bearing in mind that this is the general expectation for the very first outcome anticipated to be obtained by this project. 8. Regarding governance, the Project needs to begin engendering analysis and internal discussions as to what the structure for this institutionalisation should be. 9. Regarding financing, there should be a clear link between continuation and sustainability of plans and activities with their financing once external support ends. 10. UNDP needs to work with and assist the Project in order to aid them in applying processes that support projects’ technical and implementation capabilities (specially support project implementation and efficient decision – making capacities) and in applying procurement systems to increase capacity to efficiently implement projects aiding in the fulfilment of a project’s objective. 11. The Project and all the partners and stakeholders should recognize that the COVID-19 pandemic will have effects upon implementation and cope with the understanding that COVID-19’s impact and the pandemic will be persistent in the near future, and that there is an urgent need to move along using digital means. 12. Although the implementation of the communication strategy as well as the outreach through this has been positive, there is ample room to improve, to make it more suitable, and to upscale its focus. The MTR does not anticipate that the project will require an extension. Due to COVID, the NCE RTA has not been able to travel on mission. It is proposed that the RTA and PMU commence regular monthly calls to review project strategy and progress. In addition, it is agreed that the RTA, CO and PMU will meet following finalisation of the MTR to discuss programmatic and operational adjustments and solutions required to support smoother implementation going forward. |
| UNDP Country Office Programme Officer | This is the second PIR of the Integrating Biodiversity Safeguards and Conservation into development in Palau. The objective of this project is to mainstream biodiversity conservation into integrated land and seascape governance, planning and management in Palau. An overall rating of satisfactory is assigned to the project. As of June 30, overall progress towards mid term targets is advancing well. Few indicators are slightly behind schedule but looking at the bigger picture, the project is on target to meet end of project targets. Key achievements at the objective level: (i)44,788 hectares of land and sea in protected areas plus 1,460 hectares of land in Riparian Buffer zones legislated and regulated (ii) 11648 hectares on land was identified for sustainable management solutions. Members of the Joint Coordination Body (JCB), including 9 of 10 states have commenced negotiations which aim to facilitate operationalization of this commitment. The Project Coordination Unit which serves as secretariat of the JCB, had proactively supported and advocated for integrated planning (iii) Babeldoab-Koror Regional Urban Development Strategic Plan (KRUDSAP) finalized and adopted by the Ministry of Finance. As part of review process, tourism and housing parts were updated. Component 1: enhanced national framework for integrated planning and management of landscapes and seascapes:  The creation of a land planning commission and a state master plan template, which is also aligned to national law. This is an innovative effort of the project coordination unit and commitment to the mainstreaming objectives of this project  In terms of Biosecurity -a National Invasive Species Council (NISC) was constituted. Research on fruit flies and rhinoceros beetles was initiated. Biosecurity regulations are produced and reviewed. This is with the legal counsel as part of vetting process.  Project Coordination Unit continues to improve coordination with National Environmental Protection Council (NEPC),state governments, national governments, non-governmental organizations and communities Component 2: Integrated Multi Sector land and seascape “Ridge to Reef Panning and management operational in Babeldaob states to reduce biodiversity and improve ecosystem services to benefit …..  Progress with community-based efforts resulting in a commitment to improving management of 160 sites in an area of 1,437 hecatres. Examples include tourism, best practices for aquaculture and improvement to taro farming.  Partnership amongst law enforcement partners improving enforcement agencies of Hawsbill Sea Turtle  Project partners have reviewed laws protecting native birds. A local Non-Governmental Organization, Palau Conservation Society, has committed to updates its Land Life Strategic Plans Outcome 3: Integrated multi-sector planning and management operational in 264,686 ha of seascapes and coastal areas in the Southern Lagoon to reduce threats to biodiversity and improve ecosystem services to benefit communities and state economies  Completion of revision to Rock Island Southern Lagoon protected area management plan. This is inclusive of fishery protections (commitment to sustainable use of 60 species)  Palau International Coral Reef Center is establishing baselines and will monitor fish every second year Outcome 4: Knowledge management, monitoring and evaluation support, equitable gender benefits and biodiversity conservation in Palau  Baselines for indicator 15 is established  In terms of awareness on potential conservation threats and impacts of invasive alien species: - 46% – 65% of tour operators are aware - 63% - 84% of community members are aware Implementation Progress: As of June 2021, the project recorded a delivery of USD 968,288 out of a total grant of USD 4,233,562. This represents a delivery of 22.87%. On one hand this may appear as a concern from a purely financial perspective. On the other hand, from a technical perspective, the Project Coordination Unit has laid a solid platform through the establishment of networks, signing of agreements with partners, mobilization of community engagement and advancing the mainstreaming of biodiversity safeguards. Based on this, the project is expected demonstrate improved financial delivery in coming years. The Project Coordination Unit and UNDP have had regular discussions. These discussions aim to touch base on progress (both financial and technically), proactively anticipating issues and jointly proposing solutions. As result of the first wave of Corvid 19 (2020) and second wave (2021), UNDP missions in country have stopped due to travel restrictions. Discussions with the Project Coordination Unit were organized virtually i.e. zoom. Within this reporting period, three board meetings were held. The level of participation and proactiveness of project board in terms of decision making is encouraging. This is indicative of their commitment to ensuring successful realization of project objectives. The former Minister for Ministry of Natural Resources, Environment and Tourism (MNRET) resigned from the board and was replaced by acting Minister, President Whipps, Jr. During this reporting period, there was a new national government which brought about changes/realignments. The new executing agency for Palau BD project is the Ministry of Agriculture, Fisheries, and Environment (MAFE). Corvid 19: a second wave of the Global Pandemic (Corvid 19) struck most Pacific islands around the first quarter of 2021. Initially, this had negative impacts on implementation as there was a period of few months in which implementation had stalled due national focus on vaccination of population, strict management of its borders and restrictions to gatherings. Government staff were also restricted from travelling abroad. In one way, this was advantageous as the Project Coordination Unit was able to meet with and consultant with important stakeholders who have travelled abroad more often, in normal circumstances. Fortunately, the Government of Palau was timely in responses to the Corvid 19 situation through the prioritization of vaccination of its population and strict monitoring of borders. Whilst the Corvid 19 situation is unfolding and unpredictable, the Project Coordination Unit continues to monitor the situation closely. Recommendations: the following is recommended to improve delivery in remaining project life:  convening of a planning workshop once the Mid Term Review report if finalized. Purpose to ensure stakeholder participate/contribute to development of revised multiyear workplan and strategy  project develop an exit strategy and commence implementation following completion of planning workshop  continuation of regular communication between Project Coordination Unit and UNDP  improving communication and visibility of project at regional and international level. Project has achieved some good results but there is much potential to raise the profile of the project globally  continuation of collaboration and partnership with other initiatives including other UNDP-GEF supported projects e.g. Palau National Marine Sanctuary Project  |
| Project Manager/Coordinator | Given the significant progress the Project has made in the last year, we are assigning it a rating of satisfactory. This is despite difficulty in accessing and spending financing – despite lower financial delivery the project has advanced the global and national outcomes. Activities and partnerships are in place and functioning well for most partners, and the project has expanded partnerships beyond the original design because of high interest in the project’s benefits and outcomes. One outcome (Southern Lagoon) is still behind, but in general the project is on track to meet the overall objective of mainstreaming biodiversity into governance, planning, and management. In terms of governance, the project has impacted national government processes as well as State (municipal) governance. The Objective and Outcomes will be achieved, although with some shifts in outputs and activities. For instance, a joint Koror-Peleliu lagoon-wide plan is not politically feasible, but instead the project will facilitate two plans instead for each state. The Project Management Team actually shrank in the past year, and now consists of a Project Manager, Technical Advisor, Financial Support, and a Project Specialist (with links to GEF5). This does increase some risk as managing the 20+ partners is time-intensive. However, by this point in the project many of the Partners are self-managing and the Project has a solid support network in place, including support from high level governance. This is an area to be flagged, however. Progress towards the overall objective is steady and improvements continue. The result of mapping, planning, and outreach (including political outreach) has resulted in land use and lagoon-use guides for much of the island of Babeldaob and the entire Koror lagoon. These land use maps, which are being advocated for adoption in State Master Plans, fully incorporate protection of high value biodiversity areas and best practices in land management. With finances flowing a bit more steadily, and with improved financial management practices by Project Partners (including State Governments), more tangible benefits are being shared. By now hundreds of people have been involved with the project in some way, and have experienced the benefits of biodiversity management directly or indirectly. The project will exceed its targets for integrated planning. Given the high level of interest in the project, and the flexibility of the tools and spatial data collection system, the project will achieve Master Plans in every State on Babeldaob (10 rather than 7). All 10 States have planning teams that are active and several of which are already empowered through legislation (the project has made this a requirement), who have increased capacity to think ecosystem-wide, and who are better prepared to use complex spatial data to make sustainable land use decisions. The project continues to advocate for gender and social mainstreaming in these planning teams and the gender balance has improved as a direct result of project input and requirements. For Outcome 1 the Babeldaob Joint Coordination Body is coherent and functioning, and successfully mapped, identified, negotiated, and agreed to a Babeldoab Land Use Guide that incorporates best practices for agriculture, forestry, tourism, housing, and biodiversity. The project did experience a setback when the Southern Lagoon JCB dissolved due to political difficulties in Koror, and much of the momentum that was achieved there has been lost. Work in Koror continued, with a spatial extent limited to just state waters. Koror has made significant progress with planning by zoning its entire lagoon for fisheries and by adopting a comprehensive vision. Several new marine protected areas have been identified and Leadership approval – with an aligned piece of State legislation – is currently being sought. However, activities in Peleliu have stalled. Difficulties accessing financing exacerbated the situation with Peleliu – due its distance the Project implementing team could not visit frequently and thus were not able to regularly advocate for continued progress. Peleliu remains a partner. Tools for planning and templates for planning commission legislations have been developed and are in use by all teams. National Biosecurity Capacity has increased, with the start of construction of the Quarantine facility, reinvigoration of the NISC, training in Invasive Alien Species, development of Black and White lists, a draft of the Biosecurity Regulations, continued research and mapping of Fruit Flies and CRB, and continued Biosecurity at the borders, which was realigned to a new Ministry. Enforcement partners continued working together. The Palau EQPB has been facing strong political opposition to its environmental regulations, and the Project facilitated strong support for continued environmental protections. EQPB successfully updated its regulations to include Biodiversity protections. Enforcement of an endangered Hawksbill Sea Turtle also was stepped up as a result of this project. For Outcome 2, activities are progressing well. All 10 States signed MOUs with MAFE GEF6 to undertake Master Planning and all 10 are progressing in some way. Many States have sought broader political and legislative support, which has been strong. Project partners completed their action projects this year, restoring lands and streams through community events that involve very labor-intensive work. Financing delays have slowed the next round of community activities, but plans are being implemented now that funds are on island: In some States activities have already begun – for instance erosion control and trail restoration in the Ngerderar protected area, mapping of aquaculture leasing areas based on scientific best practices, and designing of an accessible and low erosion trail for older women farmers. Invasive species activities continue to be behind but progress has begun with training of site managers from partner states. Outcome 3 continues to be a risk and pose difficulties. The Southern Lagoon JCB was dissolved at the request of Koror state due to internal State politics. This affected momentum and made the achievement of a joint lagoon-wide vision and plan impossible. However, work in Koror did continue with extensive fisheries mapping and planning, which has extensive scientific input and good political support so far. Koror completed revisions to the RISL Management Plan and adopted a Development Vision. Work in Peleliu is very slow and delayed, partially because of funding issues and partially because of logistical issues (very small population with multiple competing needs). Tourism outputs fall under this outcome and the project struggle to advance tourism activities and outputs. However, with a new administration in office since January, there has been restructuring of the Bureau of Tourism and much more attention paid to the project and its deliverables. Slow progress is being made to align and expand certification programs and BOT is partnering better to develop new sustainable tourism sites. Almost every state on Babeldaob plus Peleliu mapped tourism sites. |
| GEF Operational Focal point | (not set or not applicable) |
| Project Implementing Partner | (not set or not applicable) |
| Other Partners | (not set or not applicable) |

# Gender

## Progress in Advancing Gender Equality and Women's Empowerment

1) Please review the project's Gender Analysis and Action Plan. If the document is not attached or an updated Gender Analysis and/or Gender Action Plan is available please upload the document below or send to the Regional Programme Associate to upload in PIMS+. Please note that all projects approved since 1 July 2014 are required to carry out a gender analysis and all projects approved since 1 July 2018 are required to have a gender analysis and action plan.

GEF6 Gender Workshop - Final Program - July 2021.pdf Gender and Social Inclusion in the GEF6 Project - MAFE - July 2021.pdf Palau Gender Mainstreaming Policy - MOS - Tkakl Mekreos - July 2021.pdf Resource Use Gender Report - Palau 2021 - BADG-Ebiil-GEF6 _ Maps.pdf

Atlas Gender Marker Rating

GEN2: gender equality as significant objective

2) Please indicate in which results areas the project is contributing to gender equality (you may select more than one results area, or select not applicable):

Contributing to closing gender gaps in access to and control over resources: No

Improving the participation and decision-making of women in natural resource governance: Yes

Targeting socio-economic benefits and services for women: No

Not applicable: No

3) Please specify results achieved this reporting period that focus on increasing gender equality and the empowerment of women. Please explain how the results reported addressed the different needs of men or women, changed norms, values, and power structures, and/or contributed to transforming or challenging gender inequalities and discrimination.

The project is one of the strongest advocates for gender mainstreaming in Palau. The project has conducted outreach on the Palau National Gender Mainstreaming Policy and raised its profile somewhat. The Implementation Unit has an official MOU with the Gender Division and checked in with them on major project deliverables (e.g. such as the Subdivision Housing Criteria). The Project also assisted with a National Gender Mainstreaming Dialogue convened by the Ministry of State. Gender considerations were included in Safeguards and guidance given to States, including Requirements for their 2021 Action Plans and in the template for State Master Plans as well as in the template for State Planning Commission Legislation. These were distributed in multiple formats (digital, paper, and reviewed in person with every planning team). Project Partners have put extra energy into recruiting families and women for field activities in order to ensure a gender balance in participants. One State project is specifically focused on empowering elderly women – development of an accessible trail (with low slope, rest areas, and shade) that is also low erosion and which maintains biodiversity along its path – so that women can access their traditional taro patches. Mapping of this trail pulled in many non-traditional partners (such as Engineering firms) who then became better aware of the project’s gender mainstreaming targets. Planning teams include a good balance of men and women (approximately 60:40%), as advocated by the project. This is a key achievement in improving the participation of women in resource governance. A key achievement was the completion of the Gender and Natural Resource Study, which mapped how agriculture, fishery, forestry, and tourism resources are used by different genders. This is a key resource that will feed into Land use plans and Master plans. A workshop to review results was continually delayed due to financing issues but will be held July 27. The KAP Survey was also finally completed and gender-specific information can now be determined based on the questions. For instance, we can pull out information on which gender understands better the number of invasive species, etc., and thus where and how to target outreach. The project regularly collects disaggregated data, and analysis has identified areas where additional gender mainstreaming is needed.

4) Please describe how work to advance gender equality and women's empowerment enhanced the project's environmental and/or resilience outcomes.

For example, the project held a Taro Workshop that identified environmental best practices that are culturally appropriate and which will maintain or improve biodiversity. One of the findings was that commercial considerations have led to fewer varieties being cultivated. However for both cultural purposes and resilience purposes the women reaffirmed that they would like to cultivate a variety of taro. Out of this came a subsequent project carried out by an NGO to write a booklet about multiple varieties of taro – and the booklet is in Palauan. The project has been heavily involved with Palau’s National Food Dialogues in advance of the UN Global Food Summit, and the project advocated for gender mainstreaming in the agenda and discussion topics. Thus, much of the perspective of the Food Dialogue was on ways to sustainably scale up production while also addressing the livelihood and nutritional needs of families and the poor. Unlike many other countries, young men are a vulnerable group in Palau, and many of the hands-on labor-intensive projects that State partners carried out gave young men an opportunity to participate in a respected community activity and earn financial benefits. These young men increased their understanding of invasive species and their management, which will help them better manage their family’s farms.

# Risk Management

## A) Review of Risks outlined in Risk Register and PIMS+ risk tab

NCE RTA: Please provide an assessment of project risk management (including risks reported in Risk Register and risks included in the project’s risk tab in PIMS+ ) undertaken in the reporting period and summarize the key risk management measures to be taken in the coming year. This text will be pulled into the risk management action plan in this project’s risk tab in PIMS+.

The overall risk rating for this project is Moderate due to late delivery of the MTR and low delivery against the project's work plan, which is due in large part to the COVID19 pandemic. MTR: The MTR process is currently wrapping up (August 2021) and will be completed by 31 August 2021. Delivery: Slow delivery and bottlenecks represent risks to successful implementation, especially since the project has to make up for delays in activities to achieve end of project targets and respond fully to the recommendations and findings of the MTR. Delays in any procurement processes will have cascading and cumulative effects. It is recommended that the project develops a Delivery Acceleration Plan in close coordination with the RTA and UNDP Country Office to support the next phase of project implementation. This should be approved by the PSC and include at least the following: (i) Carry out joint budgeting and procurement planning in a workshop situation with all project partners, to ensure effective coordination and realize efficiencies wherever possible, and ensure that any adjustments are communicated to all parties; (ii) As far as possible, develop all TORS and activity concept notes under each AWP as a block in advance at the start of each quarter, and secure approval and sign-off from relevant authorities and the project’s PSC in one step (instead of developing TORs on a one by one basis); (iii) Front load the budget with purchase of equipment and other larger-value items, or those that might take a longer time to procure; (iv) Consolidate tenders or consultancies where possible and sensible, to reduce the administrative burden and time required for multiple individual procurements; (v) Build the time required for procurement into the workplan and make sure that procurement processes are triggered well enough in advance of when the service/product is required, and in the right sequence, to enable work to be carried out according to schedule; (vi) Convene meetings with each of cofinancier, or with them as a group or in small groups by category (e.g . Govt, NGO, private sector) to assess their current financial circumstances and recovery plans and future capacity to deliver the co-finance commitments that were made at CEO endorsement stage, and explore solutions to any obstacles. vii) Alert the RTA early to any challenges, bottlenecks or delays in requesting / receiving project funds and disbursements from UNDP MCO. We can aim to hold a monthly call to tackle issues as they arise.. COVID-19 : As reflected in this PIR, COVID19 has had significant direct, indirect and induced impacts on the implementation of the project, where it has substantially hindered project implementation especially in remote sites. While it is difficult to predict the future impacts of the pandemic, it is recommended that immediately post-PIR and MTR, the project, with support of UNDP CO and CTA, should develop a project-specific COVID19 Mitigation Plan which should include at least: (i) a simple risk dashboard that can be used to track incidence of COVID19 in the project domain, and among project partners and staff involved in implementation; partner capacity (human resources, capacity to meet co-finance commitments); evidence of direct, indirect and induced impacts (that influence implementation); and, (ii) a set of protocols for stakeholder engagement processes to avoid disease transmission, in line with national directives and international best practice (i.e. thresholds on numbers of participants, social distancing measures; etc). The risk dashboard should be updated monthly and used to inform adaptive management.

## B) Social and Environmental Standards (Safeguards) Risks

1) Have any new social and/or environmental risks been identified during the reporting period?

No

If any new social and/or environmental risks have been identified during the reporting period please describe the new risk(s) and the response to it.

N/A

2) Have any existing social and/or environmental risks become more severe and/or has the project's SESP categorization changed during the reporting period? For example, when a low risk increased to moderate, or a moderate risk increased to high.

No

If any existing social and/or environmental risks have become more severe and/or if the project's SESP categorization has changed during implementation please describe the change(s) and the response to it.

The project conducted a rapid assessment of risks in early June and found that most risks were stable or decreasing. It remains difficult to recruit and involve the most vulnerable of the population, and vulnerable foreigners (such as farmers) remain a challenge to reach. The PMU held a workshop on Gender and Social Inclusion Mainstreaming specifically to reduce this risk even further.

3) Have any social and environmental assessments and/or management plans been prepared or updated, and/or has the SESP been updated in the reporting period, as required? For example, an updated Stakeholder Engagement Plan, Environmental and Social Impact Assessment (ESIA) or Indigenous Peoples Plan.

No

If yes, please upload the document(s) above using the FILE LIBRARY button. If no, please explain when the required documents will be prepared.

n/a

4) Has the project received complaints related to social and/or environmental impacts (actual or potential ) during the reporting period?

No

If yes, please describe the complaint(s) or grievance(s) in detail including the status, significance, who was involved and what action was taken.

The project advocated for the inclusion of biodiversity and cumulative impact criteria in EQPB’s EA/EIS Regulations, and these were successfully included and adopted. However, there was political pushback from Congress, who viewed this as making development more difficult. In truth the regulations do not apply to residential and small development projects, and thus did not actually make access of a building permit more difficult for families and smallholders; this was an incorrect perception.

5) Is the preparation and./or implementation of the project's safeguards management plan(s) on track, including monitoring?

Not Applicable

If no, please explain:

N/A

# Knowledge Management & Communications

The Project Manager must complete the three questions below.

1) Please provide progress on the implementation of the project's Knowledge Management approach approved at CEO Endorsement/Approval. If there is no KM approach/strategy, please comment on how the project is capturing and disseminating best practices and lessons learned.

The website remains a central location and repository to store and access information, not only for the project but also national documents for many sectors. Use of the website is steady every month. A weekly email drives people to the website so they are aware of it as a knowledge management portal. The website was reorganized by Key Sector to make it easier to use. The Project also assists partners by helping them make their documents available online. For instance materials from Palau’s SGP Program were added to the Project website: https://sites.google.com/view/gef6palau/partners-and-subprojects/sgp-small-grants-programme. The project started creating individual State webpages so that Partners can access their own materials in a central location: https://sites.google.com/view/gef6palau/partners-and-subprojects/ngardmau The project assisted other partners to set up websites, for instance with Fisheries documents: https://sites.google.com/view/palau-fisheries As planned, new documents have been prepared, such as the KAP Survey, Gender Natural Resource Document, and updated maps which capture new information. Both the Project Implementation Unit and several partners are now sharing their photos via the Project’s Flickr website. Albums are being labeled to ensure that photos can be found.

2) Please provide URLs specific to this project in the relevant field below. Please categorize the URLs appropriately (for example: project websites, social media sites, media coverage, etc.)

The Project is implementing the Communications Strategy in the Project Document and awareness of the project and its content is very high. The project is quite “popular” and is even referenced at high level events. Several activities that were behind have been implemented in the past year (such as reorganization of the website) and much more extensive communications to the private sector by avenues such as the #MainstreamingMondays newsletter and through forums such as the Taro Workshop and National Food Dialogues.. Individual meetings continue to play a key role in communications, and the Project Implementing Team meets regularly (monthly or more) with project partners to conduct work in person. The Team is very accessible and partners have no issues reaching out. Meetings also include presentations on topics such as invasive species or biodiversity. The Project successfully held meeting with the Governor’s Association, the new President, and the new Minister of Finance on Master Planning. The Project participates in most public awareness activities carried out by partners, including field activities (planting), Earth Day events, and meetings. Project Website: https://sites.google.com/view/gef6palau UNDP: https://www.pacific.undp.org/content/pacific/en/home/countryinfo/palau.html UNDP: https://open.undp.org/profile/PW/recipientprofile Social Media: Facebook (@GEF-6-PALAU) Instagram (@gef6palau) Twitter (@GEF6_Palau) LinkedIn (gef6-mnret-palau) Photos: Flickr: https://www.flickr.com/photos/189071815@N08/ Media Coverage: https://sites.google.com/view/gef6palau/mainstreamingmondays/gef6-press Articles: • Airai State signs MOA with MNRET; all ten States on Babeldaob undertake State Master Planning (Island Times, March 19, 2021) • Agroforestry project aims to “improve the livelihood” in Ngaraard (Island Times, November 10). See Response from GEF6 about Corrections. • Ten States adopt a single “Vision” (Island Times, October 16) • Ten States adopt a single &quot;Vision&quot; (Printed version - Island Times, October 16) • Babeldaob JCB adopts island-wide vision and core values for development (Tia Belau, October 15) • Customs Officers seize 61 cases of Chinese beer (Tia Belau, October 8) (Biosecurity at work) • (Renamed) Oreor-Beliliou SEA JCB begins marine spatial planning and coordination process (Tia Belau, September 10) • 4,994 pounds of trash collected during coastal clean up (Island Times, September 8

3) In the PIR platform, please upload any supporting files, including the project's Communications Strategy, photos, videos, stories and other communication/knowledge materials.

(not set or not applicable)

# Stakeholder Engagement

(A) Provide an update on progress, challenges and outcomes related to stakeholder engagement based on the description in the Stakeholder Engagement Plan or equivalent documentation submitted at CEO Endorsement/Approval. (B) Upload all available documentation of the project's stakeholder engagement, including surveys, FPIC reports and others using the FILE LIBRARY button in the upper right corner of the PIR. (C) If the project's Stakeholder Engagement Plan has been updated during the reporting period, please upload that file using the FILE LIBRARY button above.

The Project is very active with Stakeholders and partners closely with NGOs, National Government, and State Government partners, and even the UN Office and bilateral partners (e.g. Taiwan’s Agricultural Extension, Australia’s embassy on biosecurity). Thus, the project engages with even more stakeholders than originally planned. As planned, stakeholders are involved with multiple aspects of the project – invasive species through the NISC, Master planning through the JCB and Technical Groups, and Best Practices through technical The one area of weakness is with the private sector although this is slowly improving especially now that tourism activities are being better implemented. It is hard to reach the private sector as they cannot attend meetings and generally are very busy; however it is also a matter of perspective. For instance, despite efforts to reach the private sector for the Food Dialogues – especially to discuss matters of affordability, education, nutrition, and access – the private sector viewed it as another environmental initiative.

# Annex - Ratings Definitions

Development Objective Progress Ratings Definitions

(HS) Highly Satisfactory: Project is on track to exceed its end-of-project targets, and is likely to achieve transformational change by project closure. The project can be presented as 'outstanding practice'.

(S) Satisfactory: Project is on track to fully achieve its end-of-project targets by project closure. The project can be presented as 'good practice'.

(MS) Moderately Satisfactory: Project is on track to achieve its end-of-project targets by project closure with minor shortcomings only.

(MU) Moderately Unsatisfactory: Project is off track and is expected to partially achieve its end-of-project targets by project closure with significant shortcomings. Project results might be fully achieved by project closure if adaptive management is undertaken immediately.

(U) Unsatisfactory: Project is off track and is not expected to achieve its end-of-project targets by project closure. Project results might be partially achieved by project closure if major adaptive management is undertaken immediately.

(HU) Highly Unsatisfactory: Project is off track and is not expected to achieve its end-of-project targets without major restructuring.

Implementation Progress Ratings Definitions

(HS) Highly Satisfactory: Implementation is exceeding expectations. Cumulative financial delivery, timing of key implementation milestones, and risk management are fully on track. The project is managed extremely efficiently and effectively. The implementation of the project can be presented as 'outstanding practice'.

(S) Satisfactory: Implementation is proceeding as planned. Cumulative financial delivery, timing of key implementation milestones, and risk management are on track. The project is managed efficiently and effectively. The implementation of the project can be presented as 'good practice'.

(MS) Moderately Satisfactory: Implementation is proceeding as planned with minor deviations. Cumulative financial delivery and management of risks are mostly on track, with minor delays. The project is managed well.

(MU) Moderately Unsatisfactory: Implementation is not proceeding as planned and faces significant implementation issues. Implementation progress could be improved if adaptive management is undertaken immediately. Cumulative financial delivery, timing of key implementation milestones, and/or management of critical risks are significantly off track. The project is not fully or well supported.

(U) Unsatisfactory: Implementation is not proceeding as planned and faces major implementation issues and restructuring may be necessary. Cumulative financial delivery, timing of key implementation milestones, and/or management of critical risks are off track with major issues and/or concerns. The project is not fully or well supported.

(HU) Highly Unsatisfactory: Implementation is seriously under performing and major restructuring is required. Cumulative financial delivery, timing of key implementation milestones (e.g. start of activities), and management of critical risks are severely off track with severe issues and/or concerns.  The project is not effectively or efficiently supported.