Ministry of Finance

< Support to Public Finance Management

and Institutional Development>

Semi- 	Annual Report

| Implementing Agency: | United Nations Development Programme |
| --- | --- |
| Country/Region or Area: | Egypt |
| Project Title and ID: | 00106279 Support to Public Finance Management and Institutional Development |
| Project Duration: | From 1 April 2018 to 31 December 2022 |
| Project Budget for (2023) (AWP): Overall Project Budget: | USD 628,221.99 USD 4,900,000 |
| Reporting Period: | From 1 January 2023 to June 2023 |
| Contact Person/s: | Dina Gamal Dina.gamal@mof .gov.eg Yasmin El Abiad Yasmin.Alabiad@mof.gov.eg |

<INSERT LOGOS OR FLAGS OF ALL DONORS TO PROJECT / PROGRAMME>

Table of Contents

Acronyms

I.	Introduction	4

II.	Progress Review <January 2023 to June 2023>	5

III.	Monitoring and Evaluation	31

3.2	EVALUATIONS	31

IV.	Key Challenges, Lessons Learned and Recommendations	31

V.	Update on risks and mitigation measures	31

VI.	Partnerships and Sustainability	32

VII.	Financial Summary	33

Annex I: Progress Review: detailed matrix of activities and results	35

Annex II: Updated Risk and Issues  Logs	43

Annex III: Annual Work Plan (for next year)	45

Annex IV: Assets inventory	46

Annex V: Markers	47

Annex VI: innovative tools and methodologies	48

(Note: Please use table of contents maker to ensure automatic updating of pages and content).

Use font Corbel and font size 10 for all text on narrative sections.

Acronyms

| EA GFMIS GoE IA IDF IFI IMF M&E MOF MOFA OUDA PEFA PFM RFP PPP PPPCU SDS SOE UNDP WB | Economic Authorities Government Financial Management Information System Government of Egypt Internal Audit Institutional Development Framework International Financial Institution International Monetary Fund Monitoring and Evaluation Ministry of Finance Ministry of Foreign Affairs Operational Unit for Development Assistance Public Expenditure and Financial Accountability Public Fiscal Management Request for Proposal Private Public Partnership PPP Central Unit State Owned Enterprises Sustainable Development Strategy Egypt 2030 United Nations Development Programme World Bank |
| --- | --- |

- Introduction

In 2016, the Government of Egypt (GoE) has declared the Sustainable Development Strategy Egypt 2030 (SDS) as the base for setting the development objective for all Egyptians. Egypt is also committed to the achievement of the SDGs and has already submitted its first voluntary report to the High Level Political Forum (HLPF).  Two key cornerstones in mainstreaming Egypt’s 2030 goals in the public sector practices under the economic dimension are a) the administrative reform programme and b) the economic reform programme, which was agreed upon with IMF.As such, there is a growing need for the Ministry of Finance (MOF) to focus on a) its human resources: their capabilities, the work culture and the effectiveness of their productivity within the scope of the MOF’s institutional development framework; as well as, b) its public financial management core functions. Consequently, the overall objective of this program is to improve the effectiveness of MOF’s performance by instigating a strong inclusiveness organizational culture and a result-focus capacity development of the staff while spearheading the institutionalization of strategic management and supporting the implementation of Egypt’s roadmap for the enhancement of public finance management.

The program is based on the groundwork of preceding assistance projects received mainly from IMF, WB, UNDP and British Embassy and will focus on the following four areas:

- MOF Institutional development

- MOF PFM reform initiatives

- The effectiveness of MOF assistance programs

- Provision of professional assistance to ministerial policy, technical and executive support teams

- Progress Review <January 2023 to June 2023>

Section 1:  Overall progress against Project Dcoument outputs

Project outcomes  :

1-Support to Institutional Development.

2- Support to Public Finance Management.

Project outputs & indicator/s:

1-Institutional Development Strengthened

2-At least 2 PFM Reform initiatives launched

3-Enhancing Effectiveness of MOF Assistance Programs

4-Professional assistance provided to ministerial support teams

| Project Output 1: Institutional Development Strengthened |  |  |  |  |
| --- | --- | --- | --- | --- |
| Output indicators | Baselines | Targets | Progress against targets | Source/Means of Verification |
| Indicators: 1.1Establish strategic management 1.2Capacity development | 1.1.1 Execution of Strategy M&E cycle. 1.2.1 Designing focused capacity development programs.( New Vision for Green Economy & sustainability) 1.2.2 Implementing specialized capacity development programs for selected MOF staff. ( 3 Workshops introducing Unified Public Finance Law for MOF around 150 employees) | Finalizing 4th cycle. Conducting Programs to enhance professional skills. Conducting Programs to enhance professional skills. | 4 cycles (3 baselines + 1 in process during the current reporting period). Designing a focused capacity development program for specialized economic unites in progress ( 3 Workshops introducing Unified Public Finance Law for MOF around 150 employees) | 1.1.1.1M&E semi annual report on the Ministry level have been finalized. Designing a MOF Accelerator program to be implemented by end of the year. Designing an upskilling program for MOF staff in progress. Designing an upskilling program for MOF staff in progress. |

| Project Output2: At least 2 PFM Reform initiatives launched |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output indicators |  | Baselines | Targets | Progress against targets | Source/Means of Verification |
| Indicators: 2.1. Establish an Internal Audit (IA) function Enhancement of Governmental Accounting 2.2FiscalRisk Management Instigation in MOF 2.3 .1PPP Central Unit. 2.3.2. Egypt Project Preparation “ EPPF” | 2.2.1 Reviewing requests for sovereign guarantees (including facility and guarantee agreements), attending relevant meetings and negotiations, recommending loans’ financial terms, and performing analysis for the applicants to analyze the inherent risk in the issuance of guarantees and assess the risk of the guaranteed 2.2.2 Implement the Initial Public Offering (IPO) program. 2.2.3 Work on a number of settlements for on-going disputes. 2.2.4 Work on the restructuring of government entities and industries. 2.2.5 Work on a number of Ad-hoc economic issues 2.2.6.Work on a number of programs to incentivize trade and industrial sectors. 2.3.1 Support the development of Green, Resilient PPP infrastructure programs including processes and pipeline: 2.3.2 Designing FCCL framework. 2.3.3 PPP training and capacity building. 2.3.4 The development of processes, procedures, and a framework to support the integration of climate considerations into PPP project screening and prioritization. 2.3.2.1.Negotiation with stakeholders and Ministry of International Cooperation – MOIC 2.3.2.2. Finalizing draft agreements 2.3.2.3.Procurement and disbursement guidelines 2.3.2.4.EPPF Activation |  | Participate in the review for the Mandate Letter, Term Sheet and Financial Terms and analysis to ensure best financial terms . Implementation of the program. Settlement of Disputes and providing feedback on relevant cases. Implementation of a framework on the restructuring of a public entities. Professional assistance provided to Minister Professional assistance provided to Minister Developing Green Resilient Infrastructure program Implementation of a framework Conducting Programs to enhance professional skills. Developing Framework | Finalizing and signing of the Facilities and Guarantee Agreements related to a public entities affiliated with the public Sectors after required approvals and procedures are finalized. -Evaluating New companies to be included in IPO program . -Preparing reports and /or presentations to be presented to The President ,Cabinet , IPO Committee and Economic Group. Attending and participating in the work of the arbitration committee and conflict resolution committee and providing feedback on the relevant cases. Work is continued on the implementation of a framework on the restructuring of a large public entities. Preparing reports, economic studies , analysis and /or presentations to be presented to The President ,Cabinet and Economic group. Preparing reports, economic studies , analysis and /or presentations to be presented to The President ,Cabinet and Economic group. Preparing Consultant TORs and Providing technical Assistance Providing technical Assistance Attending workshops Providing technical Assistance Providing technical Assistance Providing technical Assistance | The Unit was Established and the activity was accomplished. It is embedded in the new organizational structure. 2.2.1.1 Work is on-going in relation to the reviewing and negotiating the terms of the Guarantee and Facility Agreements for several Loans related to public entities affiliated with the Transportation Sector. 2.2.1.2 Work is done with regards to reviewing and negotiating the terms of the Guarantee and Facility Agreements for a facility agreement in the Textiles sector and working on the amendment of another in the Textile sector, work includes negotiating and reviewing the drafts. 2.2.1.3Analyzed the financial position of entities affiliated with the Transportation Sector and Housing Sector prior to issuing a new guarantee for them. 2.2.1.4Prepared several updates to the minister and cabinet on updated issued guarantees figures. 2.2.1.5Worked is continued for fulfilling CPs in relation to BOO Guarantees. Drafted a template and sent it out to electricity sector to be shared with companies and signed the required documents for 2 companies working with the electricity sector. 2.2.1.6- Preparing a Presentation to the Guarantee Committee on updated guarantees issued position and financial analysis of several SOEs. 2.2.1.7Attended a couple of workshops on fiscal risk management and discussed ways to enhance contingent liabilities’ management. 2.2.1.8 Signed 1 amendment agreement for a previously issued guarantee in the Petroleum sector 2.2.1.9 Work is done with regards to reviewing and negotiating the terms of the Guarantee for 2 issued guarantees one in the Transportation sector and one in the electricity sector including making sure all required documents are supplied by the entities, reviewing the Facility agreement, when applicable, preparing memos and preparing the final presentations to the cabinet. 2.2.2.1 Work is ongoing for the companies identified in the program. 2.2.2.2A member of a valuation committee for one of the companies in the program and acting as the laison between all parties. 2.2.2.3Finalized the listing of an additional 10% stake in Telecom Egypt on the EGX, in a successful 3.11x oversubscribed transaction. MoF was the selling shareholder and hence we worked of obtaining all the required approvals, providing regular updates and coordinated with all involved parties to assure a swift implementation of the transaction. 2.2.2.4Assessing the sale of the stake of MOF in one of its investments , work involved holding calls with potential buyers and investment banks, preparing and sending an RFP to Investment banks and preparing periodic updates on the subject. 2.2.2.5Assessing the sale of some state-owned entities with electricity sector. 2.2.3 Non disclosure given due to activity confidentiality 2.2.4 Non disclosure given due to activity confidentiality 2.2.5.1 -Running the operational aspects of MoF’s first Green Loan and Islamic Financing Facility concluded in November 2021 for USD 3Bn to fulfill the budget requirements for 2021/2022. 2.2.5.2-Working on the required reports under the Green Loan in coordination with concerned parties. 2.2.5.3-Working on the sale of MoF’s stake in certain asset. 2.2.5.4-Work is continued in relation to the proposed structure and mechanics for the offering of certain public assets to the private sector. 2.2.5.5-Work is continued on several outstanding issues between MoF and CBE. 2.2.5.6-Attending weekly meetings pertaining to the process of launching the Sustainable Debt Coalition announced during COP27 by MoF. 2.2.5.7-Working on a return and cost analysis for companies operating in the free zone system. 2.2.5.8-Working on an analysis of the mechanism for maximizing the impact of export subsidies through the export burden reimbursement program. 2.2.5.9-Participating in OECD workshops on the Green Growth Policy Review in Egypt (GGPR). 2.2.5.10Ongoing discussions with lenders and multilateral organizations on potential loans that can be granted to support the budget deficit. Work includes attending meetings, providing updates, liaising with other government bodies etc. 2.2.5.11Finalized the Impact and Allocation report for Egypt’s first sovereign green loan. 2.2.5.12Work is continued on transitioning amending a current MoF loan agreement to accommodate for the LIBOR Transition process. 2.2.5.13Worked on several memos and updates requiring MoF’s opinion on Libor transition for some multilateral loans. 2.2.5.14Completing the process of obtaining new financing for MoF from international banks, with a guarantee from a multilateral institution for the purpose of financing and refinancing social projects in the budget. The work done included getting necessary approvals, providing regular updates, negotiating with banks, hiring legal counsels, reviewing the relevant agreements, etc. 2.2.6.1-Preparing a study to estimate the expected total amount of the export subsidy required by the Ministry of Finance within four years. 2.2.6.2-preparing a cost-benefit analysis for the automotive electro-fitting initiative to assess the feasibility of establishing this initiative and its reward. 2.2.6.3-preparing a cost-benefit analysis for the property export initiative to assess the feasibility of establishing this initiative and its reward. 2.2.6.4-Provide the OECD with the MOF's contribution to the Green Growth Policy Review in Egypt (GGPR) on the assessment of Egypt's progress in meeting its domestic and international environmental policy commitments. 2.2.6.5-Working on a cost-benefit analysis for companies operating in the free zone system. 2.2.6.6-Study the financial statements of number of companies to assess their rights to receive export subsidies. 2.3.1.1The World bank mission started in June 4th - 8th, 2023 for technical assistance to PPP Central Unit through the Public – Private Infrastructure Advisory Facility (PPIAF), The mission consists of the following consultants: World Bank - CPCS Transcom - ARUP International Projects - Shahid Law Firm - Sets -Mobilization and Kick-off meeting took place on 4th of June 2023 at the Ministry of Finance premises. -The mission’s objective was to consult and have technical discussions with the PPP Central Unit, the Ministries of Finance, Planning and Economic Development, Environment and relevant line ministries on the two components of the TA namely: (i) operationalization of the fiscal commitments and contingent liabilities (FCCL) framework; and (ii) development of processes, procedures, and a framework to support the integration of climate considerations into PPP project screening and prioritization. -Meetings have been held with the mission, PPP central Unit and line ministries at both advanced and basic level of PPP expertise to have a technical discussion on FCCL framework operationalization. -Line Ministries are (Ministry of Transport, Ministry of Housing utilities & Urban Communities, Ministry of Environment, Ministry of Planning & Economic Development and Ministry of Electricity). 2.3.2.1The ultimate objective is to develop a robust Fiscal commitments and contingent liabilities (FCCL) framework and support its implementation by key stakeholders for strengthening Egypt’s overall debt management framework for PPPs, and build capacity of the Central PPP Unit and key line agencies to develop and deliver a robust PPP program. -Expected to receive the draft FCCL Framework Report manual in Q3 2023. Expected Consultative Workshop in Q3 2023. Capacity Building Workshops in Q4 2023. Submission of the first draft of the guidelines in Sep., 2023. 2.32.1The initial agreement has been drafted and negotiations between the Ministry of International Cooperation and the EBRD is undergoing. 2.3.2.2The Prime Minister has approved on establishing the facility of EUR 10 million. The Ministry of International Cooperation is in negotiations with the EBRD. |

| Project Output3: Enhancing Effectiveness of MOF Assistance Programs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output indicators | Baselines |  | Targets | Progress against targets | Source/Means of Verification |
| 3.1. Design reforms for financial distortions in agricultural and commodity sector. |  |  |  |  | After the approval of Prime Minister’s Office and in coordination with Ministry of Agriculture and Land Reclamation this activity will be fulfilled through Ministry of Agriculture Since 2020. |

| Project Output 4: Professional assistance provided to ministerial support teams |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Output indicators |  | Baselines | Targets |  | Progress against targets | Source/Means of Verification |
| Indicators: 4.1 Support to Macro-Fiscal Policy Unit. 4.2 .Support to Technical and Legal Consultancy Pool. | 4.1.1 Groundwork for preparation of yearly budget and MTB projection scenarios. 4.1.2 Developing reports for Cabinet and Presidency on budget operations and fiscal performance 4.1.3 Meeting up with rating agencies for assessment of GoE’s credit rating profile 4.1.4 Representations in bilateral and multilateral donors’ negotiations and with IFIs on the macroeconomic and fiscal policies. 4.1.5 Prepare occasional presentations on various economic topics to be delivered to investors, Cabinet of Ministers, Minister of Finance and Presidency. 4.1.6 Representation in IMF negotiations on a semi-annual basis in Article IV missions and Post-Program Monitoring. 4.1.7 Develop, prepare and update reports on PMI performance for Minister and Cabinet . 4.1.8 Support various units within MoF including DMU, International Affairs and others by providing economic data and analysis 4.1.9 Update Medium-Term Debt Strategy (MTDS) and Medium-Term Revenue Strategy (MTRS) as needed 4.1.10 Represent MFPU in Ministerial meetings on several issues including but not limited to debt, energy, hedging and COP27 matters. 4.1.11 Set-up, prepare and negotiate with investment banks on potential opportunities to enhance fiscal operations such as hedging mechanism and investor opportunities 4.1.12Attend medium and high-level committees in preparation of various initiatives where MoF. 4.1.13 Provide analytical, data and research support when needed on matters related to green economy in general and COP27 follow-ups in particular leading up to COP28. Took the necessary action for hiring New Staff and Consultant required for project Activities |  |  | Finalizing the Yearly Budget and to be approved from Parliament. Professional assistance provided to Minister Professional assistance provided to Minister Professional assistance provided to Minister Professional assistance provided to Minister. Professional assistance provided to Minister. Professional assistance provided to Minister Professional assistance provided to Minister Professional assistance provided to Minister Professional assistance provided to Ministry ‘s activities. Professional assistance provided to Ministry ‘s activities. Professional assistance provided to Ministry ‘s activities. Professional assistance provided to Ministry ‘s activities. Professional assistance provided to Minister. | 4.1.1.1 Continued to update budget analytical tables to reflect revisions in estimates over the medium-term 2023/2024 and 2024/2025. 4.1.1.2 Continued working on budget circular for FY 2023/2024, with the budget department ahead of budget preparations. 4.1.1.3Updated estimates for FY 2022/2023 and worked on budget estimates 2023/2024 with relevant departments. 4.1.1.4Laid out the groundwork for the Budget Statement for FY 2023/2024. 4.1.1.5Worked on the Budget Statement for FY 2023/2024. 4.1.2.1Prepared monthly actual performance tables for fiscal operations covering the analysis of expenditure and revenues performance. 4.1.2.2Prepared the fiscal operations presentations to be presented to Cabinet . 4.1.2.3Prepared the memo to be presented to Presidency on fiscal performance for the period July-April. 4.1.2.4Prepared the expected fiscal operations for preliminary budget 2023/2024 to be presented by Minister to Cabinet and Presidency 4.1.2.5Updated debt profiles from October 2022 till January 2023 in preparation for debt projections within budget FY2023/2024. 4.1.3.1Prepared monthly actual performance tables for fiscal operations for the period July- April covering the analysis of expenditure and revenues performance. 4.1.3.2Prepared the memo to be presented to Presidency on fiscal performance for the period July-April. 4.1.3.3Continued to lead regular communication with the rating agencies (Fitch, S&P and Moody’s) over Q1 &Q2 by providing them with necessary data to update their reports and rating assessment, review and comment on draft rating reports on Egypt, as well as arrange annual rating visits. 4.1.3.4 Prepared and compiled data in response to S&P’s Borrowing Survey with focus on Egypt data. 4.1.3.5Prepared the data necessary to lead in sovereign credit rating reviews by Moody’s (on an exceptional basis) and Fitch. 4.1.3.6Coordinated meetings between Fitch ahead of their reviews with CBE, MoF and private sector entities. 4.1.3.7 Assisted CBE team in discussions with Moody’s on an exceptional basis ahead of Moody’s exceptional committee on Egypt. 4.1.3.8 Prepared necessary data for Fitch and Moody’s ahead of their reviews of Egypt’s credit rating. 4.1.3.9Addressed and conducted a meeting with the JCRA (Japanese Credit Rating Agency) to talk about the current macroeconomic situation in Egypt. 4.1.4.1Attended and presented Egypt’s recent macroeconomic developments to investors and participated in the discussion. 4.1.4.2Answered questionnaires sent by the Arab Monetary Fund on Egypt’s current reforms and estimates. 4.1.4.3Attended meetings with OECD within the context of the Country Programme currently in place. 4.1.4.4Attended and participated in a mission by the World Bank regarding tax expenditure and tax administration as part of the Country Economic Memorandum (CEM)”; the new World Bank study on Egypt’s long-term opportunities and challenges for development. 4.1.4.5Attended and participated in a mission by the OECD regarding the preparations for the first PFM Technical Advisory Group meeting which will serve as an inter-ministerial group providing technical advice on project implementation and key PFM reforms. 4.1.4.6Led on several investor calls over two days regarding Egypt’s maiden Sukuk Issuance. 4.1.4.7 Led discussions with the Arab Monetary Fund on latest developments on Egypt’s macroeconomic front. 4.1.4.8Acted as focal points between MoF and OECD regarding their country economic survey by compiling and reviewing the answers provided from several departments. 4.1.4.9Represented the Ministry of Finance on an OECD panel on carbon pricing where we delivered a presentation on Egypt’s experience on energy subsidy reform. 4.1.4.10 Handled the World Bank’s DPF Data Requirements. Participated as an MFPU representative in the OECD’s workshop on medium-term expenditure framework, as part of the OECD Country Programme. 4.1.4.11Attended a workshop hosted by the IMF METAC on fiscal costs and risks from PPPs. 4.1.4.12Attended the Revenue Statistics Workshop organized by the OECD in Addis Ababa as part of the Egyptian Delegation to discuss trends in the domestic revenue mobilization in Africa and prepared a memo for the Minister with the outcomes and potential suggestions. 4.1.4.13Delivered MoF’s comments on the country note and projections for the Egyptian economy for incorporation in the OECD economic outlook to MPED/OECD team. 4.1.4.14 Prepared a memo for the Vice Minister concerning the World Food Programme Country Strategic Plan (2023-2028). 4.1.4.15Representing the Ministry of Finance at the Joint US-Egypt first economic commission. 4.1.4.16 Representing the Ministry of Finance at the IDSC experts’ discussions on fiscal and debt sustainability. 4.1.4.17Representing the Ministry of Finance at the IDSC experts’ discussions on Economic Diplomacy. 4.1.5.1Prepared a presentation on latest developments on customs, in light of external trade report for the period July-December 2021/2022, full year 2021/2022 and first two months in 2023. 4.1.5.2Prepared analytical tables on foreign trade data extracted from the Customs Authority to support Vice Minister’s discussions. 4.1.5.3Prepared a presentation to be used by Vice Minister on inflation developments and peer-to-peer comparison. 4.1.5.4Prepared several memos and presentations on hedging mechanism for oil in light of recent prices to be presented to Minister. 4.1.5.5Prepared and reported the recent developments on Egypt’s sovereign credit rating to Minister, Prime Minister and Presidency detailing strategies and measures to ensure improvement on the ratings’ front. 4.1.5.6Prepared a presentation on debt developments and projections for Minister interventions. 4.1.5.7Prepared a presentation on debt and interest payments developments to support Vice Minister’s presentation in an IDSC forum. 4.1.5.8Prepared a presentation for Minister to support his interventions on the developments of Egypt’s economy and its economic reform programs. Prepared presentations on foreign trade data extracted from CAPMAS. 4.1.5.9Prepared report on FDIs performance in Africa and the Middle East from the investment monitor report published in May 2023. 4.1.5.10Prepared a report on the details of Basil III and how the Fx market in the banking sector is indulged in the process of linking the parallel market of the foreign exchange. 4.1.6.1Represented the Ministry of Finance in several follow-up and preparatory meetings in the context of the economic reform program and ahead of the first review. 4.1.6.2 Represented the Ministry of Finance in IMF meetings with Ministries of Environment, International Cooperation, CBE and FRA in the context of Egypt’s access to the RST Fund. 4.1.6.3Presented a detailed memo to Presidency on IMF Board of Directors’ Meeting in December 2022, explaining each constituency’s position regarding Egypt’s exceptional access to an EFF. 4.1.6.4Attended the IMF/WB Spring Meetings in Washington DC as part of the Egyptian Delegation to continue discussions within the context of the IMF program. 4.1.6.5Presented a detailed memo to Presidency on key results and discussions points raised with IMF during the Spring Meetings ahead of the first review. Prepared the monthly report on PMI developments in Egypt for December 2022, January and April 2023. 4.1.8.1Worked on the bond prospectus for latest Sukuk and Panda bond issuances with DMU. 4.1.8.2Worked on supporting International Affairs Unit with talking points to Minister, attending roundtables with international development partners and other events. 4.1.8.3Attended a training with the DMU on how to best utilize the Bloomberg portal to have access to necessary data related but not limited to commodity prices and debt capital market developments. 4.1.8.4Contributed in the debt publications, related to the World Bank’s DPF data requirements. 4.1.8.5Supported the Transparency and Citizen Engagement Unit with their publications especially by providing data on fiscal and debt Organized, attended and presented several meetings with international investment banks such as Citi, Goldman Sachs and JP Morgan on hedging in Egypt on commodities Attended technical and logistical meetings related to MoF’s “Sustainable Debt Coalition” to be hosted by Egypt in September 2023. 4.1.13.1Working with USAID on climate risk financing 4.1.13.2Working with the World Bank, FRA, IDSC and the Egyptian Federation for Insurance on Disaster and Climate Risk Financing Strategy 4.1.13.3Supported the World Bank in pinpointing terms of reference for a climate advisor within the Ministry of Finance. 4.1.13.4Represented the Ministry of Finance in the coalition of Finance Ministers for climate action (SHERPA) meetings. 4.1.13.5Attended the Net Zero Delivery Summit in collaboration with City of London that is in association with COP27 and included Minister of Finance speech. 4.1.13.6Attended workshop on climate macroeconomics by IMF in collaboration with the coalition of Finance Ministers for climate action (SHERPA) meetings. Took necessary action for preparing TORs and contracting with employees and consultants as follows; hiring 9 new staff member for the project's activities; 3 Economist Economic Researcher Senior Finance Expert Finance Analyst Head of Official Editing Unit Advisor for Financing Affairs Technical Assistant for Head of Customs Authority | 4.1.The Buget is finalized and is beening presented to the Parliament ( waiting for approval). 4.1.2Prepared , Revised and Updated all the Policies Reports , Studies and Talk points which were required by H.E Minister of Finance and Vice Minister to be presented to President, Prime Minister , Parliament (confidential). 4.1.3 Annual Rating Reports submitted to agencies. 4.1.4 Attended Meetings, Prepared , Revised and Updated all the Policies Reports , Studies and Talk points which were required by H.E Minister of Finance and Vice Minister to be presented to delegations agencies and donors (confidential). 4.1.5Collacted Data, Reported to the Cabinet required informations , Participated in committees and Updated Policies as required by H.E Minister of Finance and Vice Minister (confidential). 4.1.6 Non disclosure given due to activity confidentiality 4.1.7Prepared , Revised and Updated all the Reports and Studies which were required by H.E Minister of Finance and Cabinet (confidential). 4.1.8 Attended meetings and Provided Economic data and analysis 4.1.9 Provided Economic data and analysis as required 4.1.10 Collacted Data, Reported to the Cabinet required informations , Participated in committees and Updated Policies as required by H.E Minister of Finance and Vice Minister 4.1.11Continued to lead the communication with IMF , rating agencies , Representatives of Investment banks to provide updated data on the Egyptian economy, review and comment on draft reports on Egypt, as well as arrange annual visits. 4.1.12Attended meetings and Provided Economic data and analysis 4.1.13Attended meetings and Provided Economic data and analysis Issued Contracts and Subcontracts. The new staff / consultants / Service Providors have provided Support to Project Activities. |

Section 2: Progress against each output

| Project document Outputs | Annual outputs | Activities Status |  | WP Outputs Results | Prodoc.output Results |
| --- | --- | --- | --- | --- | --- |
| Prodoc.output 1 Institutional Development Strengthened |  |  |  |  | Institulization of Strategy Mangement for Ministry of Finance |
|  | AWP Output 1 Institutional Development Strengthened 1.1Establish strategic management 1.2 Capacity development Budget: 206,115.00 Expenditure: 35,815.20 |  |  | - Delivered Semi Annual M&E report for cycle 4. - Designing focused capacity development programs.( New Vision for Green Economy & sustainability) |  |
|  | Indicator: 1.1.1 Execution of Strategy M&E 4th cycle. Baseline: 3 cycles of stratrgy M&E Target : Achieving Cycle 4 Indicator :1.1.2. Designing focused capacity development programs.( New Vision for Green Economy & sustainability) Baseline: Target : Conducting Programs to enhance professional skills. Indicator : 1.2.2 Implementing specialized capacity development programs for selected MOF staff. (Workshops introducing Unified Public Finance Law for MOF around 150 employees) Baseline: Target : Conducting Programs to enhance professional skills for around 150 employees |  |  | 1.1.1M&E data gathered for semi annual report on the Ministry level have been finalized. 1.1.2 Designing a MOF Accelerator program to be implemented by end of the year. 1.2.2 Designing an upskilling program for MOF staff in progress. |  |
|  |  |  | Activity 1.1.1 Finalized Cycle 4 Strategy M& E |  |  |
|  |  |  | Activity 1.1.2. Designing focused capacity development programs.( New Vision for Green Economy & sustainability) |  |  |
|  |  |  | Activity 1.2.2 Implementing specialized capacity development programs for selected MOF staff. (Workshops introducing Unified Public Finance Law for MOF around 150 employees) |  |  |
| Prodoc.output 2 At least 2 PFM Reform initiatives launched |  |  |  |  |  |
|  | AWP Output 2 At least 2 PFM Reform initiatives launched - Establish an Internal Audit (IA) function Enhancement of Governmental Accounting. - Fiscal Risk Management Instigation - PPP Central Unit Budget: 85,050.00 Expenditure: 51,957.98 - Indicator: 2.1 Establish an Internal Audit (IA) function Enhancement of Governmental Accounting. Baseline: Target : Indicator: 2.2.1. Reviewing requests for sovereign guarantees (including facility and guarantee agreements), attending relevant meetings and negotiations, recommending loans’ financial terms, and performing analysis for the applicants to analyze the inherent risk in the issuance of guarantees and assess the risk of the guaranteed entities. Baseline: Target : Indicator: 2.2.2 Implement the Initial Public Offering (IPO) program. Baseline: No unit Target : a Unit is handling all the required analysis and studies Indicator: 2.2.3. Work on a number of settlements for on-going disputes. Baseline: Target : Indicator: 2.2.4. Work on the restructuring of government entities and industries. Baseline: Target : Indicator: 2.2.5 Work on a number of Ad-hoc economic issues. Baseline: Target : Indicator: 2.2.6 Work on a number of programs to incentivize trade and industrial sectors. Baseline: Target : Indicator: 2.3.1 Support the development of Green, Resilient PPP infrastructure programs including processes and pipeline: Baseline: Target : Indicator: 2.3.2 Designing FCCL framework Baseline: Target : Indicator: 2.3.3 PPP training and capacity building Baseline: Target : Indicator:2.3.4 The development of processes, procedures, and a framework to support the integration of climate considerations into PPP project screening and prioritization. Baseline: Target : Indicator: 2.3.2.1.Negotiation with stakeholders and Ministry of International Cooperation – MOIC Baseline: Target : Indicator: 2.3.2.2. Finalizing draft agreements Baseline: Target : Indicator: 2.3.2.3.Procurement and disbursement guidelines Baseline: Target : Indicator: 2.3.2. 4.EPPF Activation Baseline: Target : |  |  | -Finalized and approved Internal Audit Reports for Central Departments and /or specialized Units Finalizing and signing of the Facilities and Guarantee Agreements related to a public entities affiliated with the public Sectors after required approvals and procedures are finalized. Evaluating New companies to be included in IPO program . -Preparing reports and /or presentations to be presented to The President ,Cabinet , IPO Committee and Economic Group. Handeling all the procedures related to PPP Programs The Internal Audit Unit was Established and the activity was accomplished. It is embedded in MOF new organization structure. 2.2.1.1 Work is on-going in relation to the reviewing and negotiating the terms of the Guarantee and Facility Agreements for several Loans related to public entities affiliated with the Transportation Sector. 2.2.1.2 Work is done with regards to reviewing and negotiating the terms of the Guarantee and Facility Agreements for a facility agreement in the Textiles sector and working on the amendment of another in the Textile sector, work includes negotiating and reviewing the drafts. 2.2.1.3Analyzed the financial position of entities affiliated with the Transportation Sector and Housing Sector prior to issuing a new guarantee for them. 2.2.1.4Prepared several updates to the minister and cabinet on updated issued guarantees figures. 2.2.1.5Worked is continued for fulfilling CPs in relation to BOO Guarantees. Drafted a template and sent it out to electricity sector to be shared with companies and signed the required documents for 2 companies working with the electricity sector. 2.2.1.6- Preparing a Presentation to the Guarantee Committee on updated guarantees issued position and financial analysis of several SOEs. 2.2.1.7Attended a couple of workshops on fiscal risk management and discussed ways to enhance contingent liabilities’ management. 2.2.1.8 Signed 1 amendment agreement for a previously issued guarantee in the Petroleum sector 2.2.1.9 Work is done with regards to reviewing and negotiating the terms of the Guarantee for 2 issued guarantees one in the Transportation sector and one in the electricity sector including making sure all required documents are supplied by the entities, reviewing the Facility agreement, when applicable, preparing memos and preparing the final presentations to the cabinet. 2.2.2.1 Work is ongoing for the companies identified in the program. 2.2.2.2A member of a valuation committee for one of the companies in the program and acting as the laison between all parties. 2.2.2.3Finalized the listing of an additional 10% stake in Telecom Egypt on the EGX, in a successful 3.11x oversubscribed transaction. MoF was the selling shareholder and hence we worked of obtaining all the required approvals, providing regular updates and coordinated with all involved parties to assure a swift implementation of the transaction. 2.2.2.4Assessing the sale of the stake of MOF in one of its investments , work involved holding calls with potential buyers and investment banks, preparing and sending an RFP to Investment banks and preparing periodic updates on the subject. 2.2.2.5Assessing the sale of some state-owned entities with electricity sector. 2.2.3 Non disclosure given due to activity confidentiality 2.2.4 Non disclosure given due to activity confidentiality 2.2.5.1 Running the operational aspects of MoF’s first Green Loan and Islamic Financing Facility concluded in November 2021 for USD 3Bn to fulfill the budget requirements for 2021/2022. 2.2.5.2-Working on the required reports under the Green Loan in coordination with concerned parties. 2.2.5.3-Working on the sale of MoF’s stake in certain asset. 2.2.5.4-Work is continued in relation to the proposed structure and mechanics for the offering of certain public assets to the private sector. 2.2.5.5-Work is continued on several outstanding issues between MoF and CBE. 2.2.5.6-Attending weekly meetings pertaining to the process of launching the Sustainable Debt Coalition announced during COP27 by MoF. 2.2.5.7-Working on a return and cost analysis for companies operating in the free zone system. 2.2.5.8-Working on an analysis of the mechanism for maximizing the impact of export subsidies through the export burden reimbursement program. 2.2.5.9-Participating in OECD workshops on the Green Growth Policy Review in Egypt (GGPR). 2.2.5.10Ongoing discussions with lenders and multilateral organizations on potential loans that can be granted to support the budget deficit. Work includes attending meetings, providing updates, liaising with other government bodies etc. 2.2.5.11Finalized the Impact and Allocation report for Egypt’s first sovereign green loan. 2.2.5.12Work is continued on transitioning amending a current MoF loan agreement to accommodate for the LIBOR Transition process. 2.2.5.13Worked on several memos and updates requiring MoF’s opinion on Libor transition for some multilateral loans. 2.2.5.14Completing the process of obtaining new financing for MoF from international banks, with a guarantee from a multilateral institution for the purpose of financing and refinancing social projects in the budget. The work done included getting necessary approvals, providing regular updates, negotiating with banks, hiring legal counsels, reviewing the relevant agreements, etc. 2.2.6.1-Preparing a study to estimate the expected total amount of the export subsidy required by the Ministry of Finance within four years. 2.2.6.2-preparing a cost-benefit analysis for the automotive electro-fitting initiative to assess the feasibility of establishing this initiative and its reward. 2.2.6.3-preparing a cost-benefit analysis for the property export initiative to assess the feasibility of establishing this initiative and its reward. 2.2.6.4-Provide the OECD with the MOF's contribution to the Green Growth Policy Review in Egypt (GGPR) on the assessment of Egypt's progress in meeting its domestic and international environmental policy commitments. 2.2.6.5-Working on a cost-benefit analysis for companies operating in the free zone system. 2.2.6.6-Study the financial statements of number of companies to assess their rights to receive export subsidies. 2.3.1.1The World bank mission started in June 4th - 8th, 2023 for technical assistance to PPP Central Unit through the Public – Private Infrastructure Advisory Facility (PPIAF), The mission consists of the following consultants: World Bank - CPCS Transcom - ARUP International Projects - Shahid Law Firm - Sets -Mobilization and Kick-off meeting took place on 4th of June 2023 at the Ministry of Finance premises. -The mission’s objective was to consult and have technical discussions with the PPP Central Unit, the Ministries of Finance, Planning and Economic Development, Environment and relevant line ministries on the two components of the TA namely: (i) operationalization of the fiscal commitments and contingent liabilities (FCCL) framework; and (ii) development of processes, procedures, and a framework to support the integration of climate considerations into PPP project screening and prioritization. -Meetings have been held with the mission, PPP central Unit and line ministries at both advanced and basic level of PPP expertise to have a technical discussion on FCCL framework operationalization. -Line Ministries are (Ministry of Transport, Ministry of Housing utilities & Urban Communities, Ministry of Environment, Ministry of Planning & Economic Development and Ministry of Electricity). 2.3.2.1The ultimate objective is to develop a robust Fiscal commitments and contingent liabilities (FCCL) framework and support its implementation by key stakeholders for strengthening Egypt’s overall debt management framework for PPPs, and build capacity of the Central PPP Unit and key line agencies to develop and deliver a robust PPP program. -Expected to receive the draft FCCL Framework Report manual in Q3 2023. Expected Consultative Workshop in Q3 2023. Capacity Building Workshops in Q4 2023. Submission of the first draft of the guidelines in Sep., 2023. 2.32.1The initial agreement has been drafted and negotiations between the Ministry of International Cooperation and the EBRD is undergoing. 2.3.2.2The Prime Minister has approved on establishing the facility of EUR 10 million. The Ministry of International Cooperation is in negotiations with the EBRD. | The Internal Audit Unit was Established and the activity was accomplished. It is embedded in MOF new organization structure. Fiscal Risk Management providing Confidental Economic studies and analysis to the Minister Support the development of Green, Resilient PPP infrastructure programs including processes and pipeline |
|  |  | Activity 2.2.1Reviewing requests for sovereign guarantees (including facility and guarantee agreements), attending relevant meetings and negotiations, recommending loans’ financial terms, and performing analysis for the applicants to analyze the inherent risk in the issuance of guarantees and assess the risk of the guaranteed entities |  |  |  |
|  |  | Activity 2.2.2 Implement the Initial Public Offering (IPO) program. |  |  |  |
|  |  | Activity 2.2.3 Work on a number of settlements for on-going disputes. |  |  |  |
|  |  | Activity 2.2.4 Work on the restructuring of government entities and industries. |  |  |  |
|  |  | Activity 2.2.5 Work on a number of Ad-hoc economic issues. |  |  |  |
|  |  | Activity 2.2.6 Work on a number of programs to incentivize trade and industrial |  |  |  |
|  |  | Activity 2.3 .1.1 Support the development of Green, Resilient PPP infrastructure programs including processes and pipeline: |  |  |  |
|  |  | Activity 2.3.1.2 Designing FCCL framework |  |  |  |
|  |  | Activity 2.3.1.3 PPP training and capacity building |  |  |  |
|  |  | Activity 2.3.1.4 The development of processes, procedures, and a framework to support the integration of climate considerations into PPP project screening and prioritization. |  |  |  |
|  |  | Activity 2.3.2.1.Negotiation with stakeholders and Ministry of International Cooperation – MOIC |  |  |  |
|  |  | Activity 2.3.2.2. Finalizing draft agreements |  |  |  |
|  |  | Activity 2.3.2.3.Procurement and disbursement guidelines |  |  |  |
|  |  | Activity 2.3.2.4.EPPF Activation |  |  |  |
| Prodoc.output3 Enhancing Effectiveness of MOF Assistance Programs |  |  |  |  | After the approval of Prime Minister’s Office and in coordination with Ministry of Agriculture and Land Reclamation this activity will be fulfilled through Ministry of Agriculture Since 2020 |
|  | AWP Output 3 3.1. Design reforms for financial distortions in agricultural and commodity sector. 3.2MOF Investment Opportunities studied 3.3 Egypt’s Export and Local Subsidy System Reviewed Budget: 0 Expenditure:0 |  |  |  |  |
|  | Indicator: Baseline: Target : |  |  |  |  |
|  |  | Activity 3.1 |  |  |  |
|  |  | Activity 3.2 |  |  |  |
|  |  | Activity 3.3 |  |  |  |
|  |  | Activity 3.4 |  |  |  |
| Prodoc.output4 Professional assistance provided to ministerial support teams |  |  |  |  |  |
|  | AWP Output 4 Professional assistance provided to ministerial support teams 4.1. Support to Macro-Fiscal Policy Unit 4.2Support to Technical and Legal Consultancy Pool: Budget: 280,350.00 Expenditure: 134,680.64 Indicator: 4.1.1 Groundwork for preparation of yearly budget and MTB projection scenarios Baseline: Target : Indicator: 4.1.2 Developing reports for Cabinet of Ministers and Presidency on budget operations and Baseline: Target : Indicator:4.1.3 Meeting up with rating agencies for assessment of GoE’s credit rating profile. Baseline: Target : Indicator:4.1.4 Representations in bilateral and multilateral donors’ negotiations and with IFIs on the macroeconomic and fiscal policies. Baseline: Target : Indicator:4.1.5 Prepare occasional presentations on various economic topics to be delivered to investors, Cabinet of Ministers, Minister of Finance and Presidency Baseline: Target : Indicator:4.1.6 Representation in IMF negotiations on a semi-annual basis in Article IV missions and Post-Program Monitoring Baseline: Target : Indicator:4.1.7 Develop, prepare and update reports on PMI performance for Minister and Cabinet of Ministers Baseline: Target : Indicator :4.1.8 Support various units within MoF including DMU, International Affairs and others by providing economic data and analysis Baseline: Target : Indicator :4.1.9 Update Medium-Term Debt Strategy (MTDS) and Medium-Term Revenue Strategy (MTRS) as needed Baseline: Target : Indicator 4.1.10 Represent MFPU in Ministerial meetings on several issues including but not limited to debt, energy, hedging and COP27 matters. Baseline: Target : Indicator : 4.1.11 Set-up, prepare and negotiate with investment banks on potential opportunities to enhance fiscal operations such as hedging mechanism and investor opportunities Baseline: Target : Indicator:4.1.12 Attend medium and high-level committees in preparation of various initiatives where MoF. Baseline: Target : Indicator:4.1.13 Provide analytical, data and research support when needed on matters related to green economy in general and COP27 follow-ups in particular leading up to COP28. Baseline: Target : Indicator: 4.2Prepare TOR and hire according to needs. Baseline: Target : |  |  |  | providing Confidental Professional Assistance to MOF by preparing Economic , Fiscal Policies, Reports studies and analysis to the Minister and Talk points which were required by H.E Minister of Finance and Vice Minister to be presented to President, Prime Minister and Parliament |
|  |  |  |  | 4.1.1. Continued to update budget analytical tables to reflect revisions in estimates over the medium-term 2023/2024 and 2024/2025. 4.1.1.2 Continued working on budget circular for FY 2023/2024, with the budget department ahead of budget preparations. 4.1.1.3Updated estimates for FY 2022/2023 and worked on budget estimates 2023/2024 with relevant departments. 4.1.1.4Laid out the groundwork for the Budget Statement for FY 2023/2024. 4.1.1.5Worked on the Budget Statement for FY 2023/2024. 4.1.2.1Prepared monthly actual performance tables for fiscal operations covering the analysis of expenditure and revenues performance. 4.1.2.2Prepared the fiscal operations presentations to be presented to Cabinet . 4.1.2.3Prepared the memo to be presented to Presidency on fiscal performance for the period July-April. 4.1.2.4Prepared the expected fiscal operations for preliminary budget 2023/2024 to be presented by Minister to Cabinet and Presidency 4.1.2.5Updated debt profiles from October 2022 till January 2023 in preparation for debt projections within budget FY2023/2024. 4.1.3.1Prepared monthly actual performance tables for fiscal operations for the period July- April covering the analysis of expenditure and revenues performance. 4.1.3.2Prepared the memo to be presented to Presidency on fiscal performance for the period July-April. 4.1.3.3Continued to lead regular communication with the rating agencies (Fitch, S&P and Moody’s) over Q1 &Q2 by providing them with necessary data to update their reports and rating assessment, review and comment on draft rating reports on Egypt, as well as arrange annual rating visits. 4.1.3.4 Prepared and compiled data in response to S&P’s Borrowing Survey with focus on Egypt data. 4.1.3.5Prepared the data necessary to lead in sovereign credit rating reviews by Moody’s (on an exceptional basis) and Fitch. 4.1.3.6Coordinated meetings between Fitch ahead of their reviews with CBE, MoF and private sector entities. 4.1.3.7 Assisted CBE team in discussions with Moody’s on an exceptional basis ahead of Moody’s exceptional committee on Egypt. 4.1.3.8 Prepared necessary data for Fitch and Moody’s ahead of their reviews of Egypt’s credit rating. 4.1.3.9Addressed and conducted a meeting with the JCRA (Japanese Credit Rating Agency) to talk about the current macroeconomic situation in Egypt. 4.1.4.1Attended and presented Egypt’s recent macroeconomic developments to investors and participated in the discussion. 4.1.4.2Answered questionnaires sent by the Arab Monetary Fund on Egypt’s current reforms and estimates. 4.1.4.3Attended meetings with OECD within the context of the Country Programme currently in place. 4.1.4.4Attended and participated in a mission by the World Bank regarding tax expenditure and tax administration as part of the Country Economic Memorandum (CEM)”; the new World Bank study on Egypt’s long-term opportunities and challenges for development. 4.1.4.5Attended and participated in a mission by the OECD regarding the preparations for the first PFM Technical Advisory Group meeting which will serve as an inter-ministerial group providing technical advice on project implementation and key PFM reforms. 4.1.4.6Led on several investor calls over two days regarding Egypt’s maiden Sukuk Issuance. 4.1.4.7 Led discussions with the Arab Monetary Fund on latest developments on Egypt’s macroeconomic front. 4.1.4.8Acted as focal points between MoF and OECD regarding their country economic survey by compiling and reviewing the answers provided from several departments. 4.1.4.9Represented the Ministry of Finance on an OECD panel on carbon pricing where we delivered a presentation on Egypt’s experience on energy subsidy reform. 4.1.4.10 Handled the World Bank’s DPF Data Requirements. Participated as an MFPU representative in the OECD’s workshop on medium-term expenditure framework, as part of the OECD Country Programme. 4.1.4.11Attended a workshop hosted by the IMF METAC on fiscal costs and risks from PPPs. 4.1.4.12Attended the Revenue Statistics Workshop organized by the OECD in Addis Ababa as part of the Egyptian Delegation to discuss trends in the domestic revenue mobilization in Africa and prepared a memo for the Minister with the outcomes and potential suggestions. 4.1.4.13Delivered MoF’s comments on the country note and projections for the Egyptian economy for incorporation in the OECD economic outlook to MPED/OECD team. 4.1.4.14 Prepared a memo for the Vice Minister concerning the World Food Programme Country Strategic Plan (2023-2028). 4.1.4.15Representing the Ministry of Finance at the Joint US-Egypt first economic commission. 4.1.4.16 Representing the Ministry of Finance at the IDSC experts’ discussions on fiscal and debt sustainability. 4.1.4.17Representing the Ministry of Finance at the IDSC experts’ discussions on Economic Diplomacy. 4.1.5.1Prepared a presentation on latest developments on customs, in light of external trade report for the period July-December 2021/2022, full year 2021/2022 and first two months in 2023. 4.1.5.2Prepared analytical tables on foreign trade data extracted from the Customs Authority to support Vice Minister’s discussions. 4.1.5.3Prepared a presentation to be used by Vice Minister on inflation developments and peer-to-peer comparison. 4.1.5.4Prepared several memos and presentations on hedging mechanism for oil in light of recent prices to be presented to Minister. 4.1.5.5Prepared and reported the recent developments on Egypt’s sovereign credit rating to Minister, Prime Minister and Presidency detailing strategies and measures to ensure improvement on the ratings’ front. 4.1.5.6Prepared a presentation on debt developments and projections for Minister interventions. 4.1.5.7Prepared a presentation on debt and interest payments developments to support Vice Minister’s presentation in an IDSC forum. 4.1.5.8Prepared a presentation for Minister to support his interventions on the developments of Egypt’s economy and its economic reform programs. Prepared presentations on foreign trade data extracted from CAPMAS. 4.1.5.9Prepared report on FDIs performance in Africa and the Middle East from the investment monitor report published in May 2023. 4.1.5.10Prepared a report on the details of Basil III and how the Fx market in the banking sector is indulged in the process of linking the parallel market of the foreign exchange. 4.1.6.1Represented the Ministry of Finance in several follow-up and preparatory meetings in the context of the economic reform program and ahead of the first review. 4.1.6.2 Represented the Ministry of Finance in IMF meetings with Ministries of Environment, International Cooperation, CBE and FRA in the context of Egypt’s access to the RST Fund. 4.1.6.3Presented a detailed memo to Presidency on IMF Board of Directors’ Meeting in December 2022, explaining each constituency’s position regarding Egypt’s exceptional access to an EFF. 4.1.6.4Attended the IMF/WB Spring Meetings in Washington DC as part of the Egyptian Delegation to continue discussions within the context of the IMF program. 4.1.6.5Presented a detailed memo to Presidency on key results and discussions points raised with IMF during the Spring Meetings ahead of the first review. Prepared the monthly report on PMI developments in Egypt for December 2022, January and April 2023. 4.1.8.1Worked on the bond prospectus for latest Sukuk and Panda bond issuances with DMU. 4.1.8.2Worked on supporting International Affairs Unit with talking points to Minister, attending roundtables with international development partners and other events. 4.1.8.3Attended a training with the DMU on how to best utilize the Bloomberg portal to have access to necessary data related but not limited to commodity prices and debt capital market developments. 4.1.8.4Contributed in the debt publications, related to the World Bank’s DPF data requirements. 4.1.8.5Supported the Transparency and Citizen Engagement Unit with their publications especially by providing data on fiscal and debt Organized, attended and presented several meetings with international investment banks such as Citi, Goldman Sachs and JP Morgan on hedging in Egypt on commodities Attended technical and logistical meetings related to MoF’s “Sustainable Debt Coalition” to be hosted by Egypt in September 2023. 4.1.13.1Working with USAID on climate risk financing 4.1.13.2Working with the World Bank, FRA, IDSC and the Egyptian Federation for Insurance on Disaster and Climate Risk Financing Strategy 4.1.13.3Supported the World Bank in pinpointing terms of reference for a climate advisor within the Ministry of Finance. 4.1.13.4Represented the Ministry of Finance in the coalition of Finance Ministers for climate action (SHERPA) meetings. 4.1.13.5Attended the Net Zero Delivery Summit in collaboration with City of London that is in association with COP27 and included Minister of Finance speech. 4.1.13.6Attended workshop on climate macroeconomics by IMF in collaboration with the coalition of Finance Ministers for climate action (SHERPA) meetings. Took necessary action for preparing TORs and contracting with employees and consultants as follows; hiring 9 new staff member for the project's activities; 3 Economist Economic Researcher Senior Finance Expert Finance Analyst Head of Official Editing Unit Advisor for Financing Affairs Technical Assistant for Head of Customs Authority |  |
|  |  | Activity 4.1.1 Groundwork for preparation of yearly budget and MTB projection scenarios |  |  |  |
|  |  | Activity 4.1.2 Developing reports for Cabinet of Ministers and Presidency on budget operations and fiscal performance |  |  |  |
|  |  | Activity 4.1.3 Meeting up with rating agencies for assessment of GoE’s credit rating profile. |  |  |  |
|  |  | Activity 4.1.4 Representations in bilateral and multilateral donors’ negotiations and with IFIs on the macroeconomic and fiscal policies. |  |  |  |
|  |  | Activity 4.1.5 Prepare occasional presentations on various economic topics to be delivered to investors, Cabinet of Ministers, Minister of Finance and Presidency |  |  |  |
|  |  | Activity 4.1.6 Representation in IMF negotiations on a semi-annual basis in Article IV missions and Post-Program Monitoring |  |  |  |
|  |  | Activity 4.1.7 Develop, prepare and update reports on PMI performance for Minister and Cabinet of Ministers |  |  |  |
|  |  | Activity 4.1.8 Support various units within MoF including DMU, International Affairs and others by providing economic data and analysis |  |  |  |
|  |  | Activity 4.1.9 Update Medium-Term Debt Strategy (MTDS) and Medium-Term Revenue Strategy (MTRS) as needed |  |  |  |
|  |  | Activity 4.1.10 Represent MFPU in Ministerial meetings on several issues including but not limited to debt, energy, hedging and COP27 matters. |  |  |  |
|  |  | Activity 4.1.11 Set-up, prepare and negotiate with investment banks on potential opportunities to enhance fiscal operations such as hedging mechanism and investor opportunities |  |  |  |
|  |  | Activity 4.1.12Attend medium and high-level committees in preparation of various initiatives where MoF. |  |  |  |
|  |  | Activity 4.1.13 Provide analytical, data and research support when needed on matters related to green economy in general and COP27 follow-ups in particular leading up to COP28. |  |  |  |
|  |  | Activity 4.2 Prepare TOR and hire according to needs. |  |  |  |

  - Progress towards Outputs (achieved/Not achieved): ( Need more clarification whether to put it on output level or activity level)

Based on the project AWP:

2.1.1. Describe the key results achieved for output level results (stated above) that were delivered as planned, and

2.1.2 Describe the results that should have been achieved for output level results that were not delivered as planned.

Tips:

- Make a direct reference to output indicator data from table above in the narrative text

- Focus on reporting at the output level, rather than lising acivities conducted

- Annual reporting: describe and analyze activities but now linking them more solidly to outputs by also including references and evidencing how the total number of activities helped to reach the achievements for the year.

- For each key result, please specify the achievement in the reporting period and the cumulative result as of the reporting date. For multi-year projects, first discuss what is exactly achieved in the reporting period. For example: “.from Jan-June 2013 registration of 1000 police was achieved + 2,000 (total from January 2011 to December 2012). Therefore, 3,000 have now been registered (January 2010-June 2013).”

- Outputs are often complex with many moving parts, so those that did not achieve results as planned may still have delivered some results, which you can describe, along with key challenges that impeded delivery and contributed to hindering performance.

- Also note that there are probably many outputs that were “achieved as planned” that still have important lessons to share on challenges that impeded delivery and strategies taken to overcome.

2.2 Please provide additional comments on targeting of beneficiaries, sustainability of results, strengthening national capacities.

| Targeting | Supporting Public Finance Management and Institutional Development. |
| --- | --- |
| Sustainability | Working in Progress to create a functional Internal Audit Unit inside MOF and finalizing Modern Strategic Document for 3 Years. |
| National capacities | -Focus capacity Development for governmental staff in Strategic Management -Designing specialized capacity development programs for selected MOF staff |
| Innovation | Debt Mangement Unit: - After the Success of the First sovereign Green-Bond in the MENA Region, demonstrating Egypt leadership and commitment to the UN Sustainable Development goals. The DMU succeed to develop the Green Framework to the Sustainable Framework and announce this milestone step during COP27. - Issuing a milestone transaction of Sukuk by USD 1.5 bn for the first time with coupon 10.875% which has been awarded with the “Sovereign Sukuk Deal of Year 2023” by GFC media group. -Working on finalizing the issuing documentation needed for our 1st Panda bonds in Chinese markets - Fiscal Transperency Unit 1- Publishing all the reports prepared by the Unit for more information and including all reports about the budget preparation cycle on the interactive website www.budget.gov.eg and receives public opinions through the feature (your opinion matters) to enable the citizens to share their opinion on the activities and reports of the ministry to be used in updating the published content to comply with their opinions. 2-The unit in cooperation with the Ministry of Education and Technical Education contributed in creating a proposal to help include some concepts of financial culture, transparency, and community participation in the school curriculum this content is on Electronic Website www.budget.gov.eg for the youth from the age of 15 – 18 years through “The Online Camp”and was introduced to university students through “Active Citizenship Club” in many universities. 3-The unit has launched several digital Campaigns to promote two episodes of the Financial Literacy awareness campaign on its Social Media Platforms on Facebook, Instagram, and YouTube. Facebook: https://www.facebook.com/FTCEUnit/ Instagram: transparency_unit YouTube: https://www.youtube.com/channel/UC7Z6feIZ1N8nPsAa7cBlHjg 4- The unit worked towards addressing gender-responsive programs through its Participatory Budgeting Egyptian model by working to support several graduation projects for youth and especially women in different municipalities. |
| South-South Cooperation | The Macro Fiscal Unit - Attended the Revenue Statistics Workshop organised by the OECD in Addis Ababa as part of the Egyptian Delegation to discuss trends in the domestic revenue mobilization in Africa and prepared a memo for the Minister with the outcomes and potential suggestions. Fiscal Transperency Unit FTCE Unit & UNICEF Field Visit to Fayoum to open new channels of cooperation for social Accountability Program The visit started with a meeting with the best participatory budgeting leaders and with a team of experts in the Middle East and North Africa from UNICEF in order to coordinate the implementation of the second phase, which includes the application of the community accountability model, This is to ensure societal oversight to improve public spending on the ground. |
| Knowledge Products | -M&E strategy reports -Pre-Budget FY 2023\2024 Report main objectives are involving citizens in the vision of the Egyptian government on the latest directions of the state’s fiscal policy to be implemented in the next fiscal year’s budget. Link to the Pre-Budget for FY 23/24: https://assets.mof.gov.eg/files/2023-05/41f20cf0-fada-11ed-a205-735d6b5ac56e.pdf -Published the financial bulletin on monthly basis. - Online Camp - Establishing an online camp for the ambassadors of the Ministry of Finance. -Gamification (An interactive game for youth and children for the age group 15-18). -Series of Episodes for Raising Fiscal Awareness through different social media platforms on the new Budget . |

2.3 Gender reporting: please provide additional details on Gender Development Results

Project Gender Marker (as per Atlas)

    - For GEN2 and GEN3 projects, please describe the progress made towards achieving gender equality results

- We have about 47% of project staff employees and /or experts’ females.

Fiscal Transparency & Citizen Engagement Unit

- Head of the FTCE Unit has been chosen amongest 60 women leaders worldwide in the field of economics and participatory Budgeting to attend the First Symposium of the European-African Agenda of the Nations of Women Foundation and the economic summit that has been held from 3rd to 6th of April 2023 in Amsterdam, the Netherlands.

- FTCE Unit and Participatory Budgeting Projects (Women Economic Empowerment):

FTCE unit worked towards addressing gender-responsive programs through its Participatory Budgeting Egyptian model by working to support several graduation projects for youth and especially women in different municipalities. Besides, Promoting transparency and accountability of government institutions is critical for effectively implementing gender equality commitments, with growing demands for fiscal transparency and open governments.

- Monitoring and Evaluation

| MONITORING SCHEDULE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Monitoring Action (Description ) | Due by | Completion date | Comments | Responsibility |
| Board Meeting | 2023 |  |  |  |
| Aduit | 1st Quarter | March 2023 | - | - |
| Progress Reports | Quarterly basis | March 2023 June 2023 |  |  |
| Semi annual Report | June | July 2023 |  |  |
| Financial Reports FR/ICE | Monthly | Submitted Beginning of Each Month. | - | Finance Officer |
| CDRs | Quarterly basis |  | - | Finance Officer |
| Annual Report | December |  |  |  |

  - EVALUATIONS

- MOF has announced the Mid Term evaluation  vacancy for 2 times ( February 2021 and September 2021) with no applicant for the vacancy  and after negotiations  the  Board Meeting Committee agreed to Postpone the Evaluation  of the Project to be a final Project evaluation  on year 2022 .

- MOF has announced the vacancy of project evaluator 3rd time for final Evaluation report on May 2022 still no  applicant for the vacancy.

- MOF has announced the vacancy of project evaluator 4th  time for final Evaluation report on April 2023  still no  applicant for the vacancy.

- Key Challenges, Lessons Learned and Recommendations

- Macro Fiscal Unit Created shock scenarios taking consideration of the Ukrain – Russian Conflict effect on the economy and on the state budget.

- Update on risks and mitigation measures

| Risks | Mitigation Measures |
| --- | --- |
| 1-Moving the Ministry to the new Capital which is considered an Organizational Risk 2-Cabinet Change | -The Ukrain – Russian conflict and its effect on economy has cause delays in moving to the new Capital and we still don’t have a fixed date; this affected some decisions and hindered some of the project activities. -The mitigation plan will be placed once the plan for movement has been declared. We are currently buffering for expected delays - New Minister may have different vision and priorities that may affect and delay some of the project activities (especially Institutional Development Section). -The project is divided into 2 main sections ; - “Support to Public Finance Management” which is fixed as it is consisted of Policies, Reforms and Economic Studies. - “Institutional Development” this part is flexible and can meet with different vision and/ or priorities of new Minister and the plan will be declared accordingly. |

- Partnerships and Sustainability

Fiscal Transperancy Unit

- Ministry of Finance’s partnership with UNICEF has been key over the past four years in the support for fiscal transparency and citizen engagement in the country. UNICEF aims to continue its support to  MoF for the next 2 years in its priorities for increasing transparency and creating platform for dialogue, where all citizens, with a focus on youth and children, would understand more about their public budget and find a safe space to form and voice their opinions.

- FTCE Unit’s Visit to Fayoum to follow up on the process of the Participatory Budgeting in the governorate :

The FTCE unit held a visit to Fayoum Governorate following up on what has been implemented in the Participatory Budgeting  process in Fayoum during the training (TOT)  that was held with the fruitful cooperation with USAID and the implementation of the graduation projects’ evaluation process for Fayoum youth and discussing implementation progresses regarding the Gender-responsive social accountability

- Participation of Transparency Unit in the preparation for the framework of joint cooperation between the Egyptian government and the UN ;the Unit has actively participated as the focal point of the MOF in the signing of a protocol on the framework of joint cooperation between the Egyptian government and the United Nations in the field of sustainable development for the next five years (2023-2027).

- Kemit Organization Tentative Cooperation;  Head of the Unit had a meeting with the representative of Kemit Organization to discuss the areas of potential cooperation between the Unit and Kemit in the sake of applying the National Model of Participatory Budgeting in the governorates and in supporting the citizens in municipalities have their own the SMEs.

- The FTCE participated in a fruitful roundtable in cooperation with the UN in the presence of UNICEF and World Food Program WFP around: Key Policy responses to strengthen food & Nutrition security, protect vulnerable populations and measure the impact of different inflation scenarios.

Debt Management Unit

- After the Success of entering the Asian Markets in 2022 through our First Samurai Bonds in Japanese Market, which was awarded “Yen Bond of Year 2022” by IFR, DMU is Working on finalizing the issuing documentation needed for our 1st Panda bonds in Chinese markets.

- The DMU succeed to develop the Green Framework to the Sustainable Framework and announce this milestone step during COP27 demonstrating Egypt commitment to the UN Sustainable Development goals.

- DMU has involved in the discussion of the three-year IMF program that was being negotiated. The areas of focus of this program are structural reforms, increasing FDIs and expanding the role of the private sector in the Egyptian economy.

PPP Central Unit

- Support the development  of “Public private infrastructure advisory facility” PPIAF( Green, Resilient PPP infrastructure programs including processes and pipeline) in cooperation with WB.

Internal Audit Unit

- IAU succeed to arrange for a technical training courses with OECD regarding specific audit technical topics, several meetings have been held to discuss and agree on the required topics, currently we have agreed on the topics and the course will take place on April 2023, we have agreed also on further course during second half of 2023.

- Financial Summary

Table 1: Overview of available resources for the reporting period: (Kindly note that this table is recommended to remain at your side to be filled by UNDP, for ensuring both accuracy & validity. As  PMU has no access the computerized platform in order to generate accurate information as required.)

(Total funds received from different donors)

| Donor | Opening Balance | Allocations/ funds received in 2021 | Total |
| --- | --- | --- | --- |
| Ministry of Finance |  |  |  |
| UNDP |  |  |  |
| Total |  |  |  |

Table 2: Overview of budget and expenditure per output

(For multi-donor projects, show the cumulative total)

| Output | Budget |  |  | Expenditures |  |  | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | MOF | UNDP | Total | MOF | UNDP | Total |  |
| Institutional Development | 206,115.00 | 0 | 206,115.00 | 35,815.20 | 0 | 35,815.20 | 170,299.80 |
| PFM Reform Initiatives | 85,050.00 | 0 | 85,050.00 | 51,957.98 | 0 | 51,957.98 | 33,092.02 |
| MOF Assistance Programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Ministerial Support Teams | 280,350.00 | 0 | 280,350.00 | 134,680.64 | 0 | 134,680.64 | 145,669.36 |
| Project Management Unit | 56,706.99 | 0 | 56,706.99 | 26,577.14 | 0 | 26,577.14 | 30,129.85 |
| Total | 628,221.99 | 0 | 628,221.99 | 249,030.96 | 0 | 249,030.96 | 379,191.03 |

Table 3: Overview of expenditures per category

| Category | Amount (USD) |
| --- | --- |
| 71635 - Travel – Other |  |
| 71810 - Contractual Services-individual: Implementing Partner | 240,036.41 |
| 72130 - Service Contract-Transportation Services |  |
| 72145 - Service Contract-Training and Education Services |  |
| 72505 - Stationery & other Office Supply |  |
| 73405 - Rental & Maintenance-Other Office Equipment |  |
| 74105 - Management and Reporting Services | 4,861.87 |
| 74110 - Audit Fees |  |
| 74505 - Insurance | 4,034.00 |
| 74510 - Bank Charges |  |
| 74515 - Claims and Adjustments |  |
| 74525 - Sundry | 98.68 |
| 75705 - Learning costs |  |
| 75712 – Training Workshop & Conference - Honorariums |  |
| 75105 - Facilities & Administration - Implement |  |
| 64397 - Services to projects -CO staff 74596 - Services to projects -GOE |  |
| 76120 - Unrealized Loss |  |
| 76130 - Unrealized Gain |  |
| Total | 249,030.96 |

For multi donor projects and if reporting on the the cumulative is requeird the below table should be added:

Table 4: Donor Cumulative Financial Report  ( NA on MOF project )

|  | Year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2016 & Prior | 2017 | 2018 | 2019 | Cumulative to 2014 |
| Income/Revenue |  |  |  |  |  |
| Contributions |  |  |  |  |  |
| Transfer to or from other funds |  |  |  |  |  |
| Refunds to donors |  |  |  |  |  |
| sub-total |  |  |  |  |  |
| IPSAS adjustment for revenue |  |  |  |  |  |
| Other revenue |  |  |  |  |  |
| Total |  |  |  |  |  |
| Expenditure/Expenses |  |  |  |  |  |
| Project expenses (incl support cost) |  |  |  |  |  |
| IPSAS adjustments |  |  |  |  |  |
| Total |  |  |  |  |  |
| Prior year adjustments |  |  |  |  |  |
| Balance |  |  |  |  |  |
| Future Expense |  |  |  |  |  |
| Un-depreciated assets & inventory |  |  |  |  |  |
| Commitments |  |  |  |  |  |
| Total future expenses |  |  |  |  |  |
| Available Resources |  |  |  |  |  |

Data contained in this report is an extract from UNDP financial records. All financial information provided above is provisional. Certified financial statements will be provided on <indicate date>.

## Annex I: Progress Review: detailed matrix of activities and results

| Output 1 | Indicators |  | Baseline | Annual target | Progress / target |
| --- | --- | --- | --- | --- | --- |
| Institutional Development Strengthened Budget: $206,115.00 Expenditure:$35,815.20 | - Execution of Strategy M&E cycle 4 after amendment. |  | 3 Cycles | 1 cycle | - M&E data gathered for semi annual report on the Ministry level has been finalized. |
|  | - Designing focused capacity development programs.( New Vision for Green Economy & sustainability) |  | 0 | 1 | Designing a MOF Accelerator program to be implemented by end of the year. |
|  | - Implementing specialized capacity development programs for selected MOF staff. |  | 0 | 3 Workshops | Designing an upskilling program for MOF staff in progress. |
| Planned activities |  | Results |  |  |  |
| Activity 1: Establish strategic management 1.1 Execution of Strategy M&E cycle |  | M&E semi annual report on the Ministry level have been finalized. |  |  |  |
| Activity 2: Capacity development 2.1 Designing focused capacity development programs.( New Vision for Green Economy & sustainability) 2.2 Implementing specialized capacity development programs for selected MOF staff. ( 3 Workshops introducing Unified Public Finance Law for MOF around 150 employees) |  | Designing a MOF Accelerator program to be implemented by end of the year. Designing an upskilling program for MOF staff in progress. |  |  |  |

| Output 2 | Indicators |  | Baseline | Annual target | Progress / target |
| --- | --- | --- | --- | --- | --- |
| At least 2 PFM Reform initiatives launched Budget:$ 85,050.00 Expenditure:$ 51,957.98 | - 2.1.Establish an Internal Audit (IA) function Enhancement of Governmental Accounting |  |  |  | The Unit was Established and the activity was accomplished. It is planned to be embedded in the new organization structure. |
|  | - 2.2.1 Reviewing requests for sovereign guarantees (including facility and guarantee agreements), attending relevant meetings and negotiations, recommending loans’ financial terms, and performing analysis for the applicants to analyze the inherent risk in the issuance of guarantees and assess the risk of the guaranteed entities.- |  |  |  |  |
|  | - 2.2.2Implement the Initial Public Offering (IPO) program. |  |  |  |  |
|  | - 2.2.3Work on a number of settlements for on-going disputes. |  |  |  |  |
|  | - 2.2.4Work on the restructuring of government entities and industries. |  |  |  |  |
|  | - 2.2.5 Work on a number of Ad-hoc economic issues. |  |  |  |  |
|  | - 2.2.6.Work on a number of programs to incentivize trade and industrial sectors. |  |  |  |  |
|  | - 2.3.1Support the development of Green, Resilient PPP infrastructure programs including processes and pipeline: |  |  |  |  |
|  | - 2.3.2 Designing FCCL framework |  |  |  |  |
|  | - 2.3.3PPP training and capacity building |  |  |  |  |
|  | - 2.3.4 The development of processes, procedures, and a framework to support the integration of climate considerations into PPP project screening and prioritization. |  |  |  |  |
|  | - 2.3.2.1.Negotiation with stakeholders and Ministry of International Cooperation – MOIC |  |  |  |  |
|  | - 2.3.2.2. Finalizing draft agreements |  |  |  |  |
|  | - 2.3.2.3.Procurement and disbursement guidelines |  |  |  |  |
|  | - 2.3.2.4.EPPF Activation |  |  |  |  |
| Planned activities |  | Results |  |  |  |
| Activity 1: Establish an Internal Audit (IA) function Enhancement of Governmental Accounting |  | 1. The Unit was Established and the activity was accomplished. It is planned to be embedded in the new organization structure. |  |  |  |
| Activity 2: Fiscal Risk Management Instigation in MOF 2.1Reviewing requests for sovereign guarantees (including facility and guarantee agreements), attending relevant meetings and negotiations, recommending loans’ financial terms, and performing analysis for the applicants to analyze the inherent risk in the issuance of guarantees and assess the risk of the guaranteed entities. 2.2 Implement the Initial Public Offering (IPO) program. 2.3Work on a number of settlements for on-going disputes. 2.4Work on the restructuring of government entities and industries. 2.5 Work on a number of Ad-hoc economic issues. 2.6.Work on a number of programs to incentivize trade and industrial sectors. Activity 3: PPP Central Unit 2.3.1 .1Support the development of Green, Resilient PPP infrastructure programs including processes and pipeline 2.3.1.2 Designing FCCL framework. 2.3.1.3 PPP training and capacity building. 2.3.2.1 Negotiation with stakeholders and Ministry of International Cooperation – MOIC 2.3.2.2. Finalizing draft agreements 2.3.2.3.Procurement and disbursement guidelines 2.3.2.4.EPPF Activation |  | 2.1.1 Work is on-going in relation to the reviewing and negotiating the terms of the Guarantee and Facility Agreements for several Loans related to public entities affiliated with the Transportation Sector. 2.1.2 Work is done with regards to reviewing and negotiating the terms of the Guarantee and Facility Agreements for a facility agreement in the Textiles sector and working on the amendment of another in the Textile sector, work includes negotiating and reviewing the drafts. 2.1.3Analyzed the financial position of entities affiliated with the Transportation Sector and Housing Sector prior to issuing a new guarantee for them. 2.1.4Prepared several updates to the minister and cabinet on updated issued guarantees figures. 2.1.5Worked is continued for fulfilling CPs in relation to BOO Guarantees. Drafted a template and sent it out to electricity sector to be shared with companies and signed the required documents for 2 companies working with the electricity sector. 2.1.6- Preparing a Presentation to the Guarantee Committee on updated guarantees issued position and financial analysis of several SOEs. 2.1.7Attended a couple of workshops on fiscal risk management and discussed ways to enhance contingent liabilities’ management. 2.2.1.8 Signed 1 amendment agreement for a previously issued guarantee in the Petroleum sector 2.1.9 Work is done with regards to reviewing and negotiating the terms of the Guarantee for 2 issued guarantees one in the Transportation sector and one in the electricity sector including making sure all required documents are supplied by the entities, reviewing the Facility agreement, when applicable, preparing memos and preparing the final presentations to the cabinet. 2.2.1 Work is ongoing for the companies identified in the program. 2.2.2A member of a valuation committee for one of the companies in the program and acting as the laison between all parties. 2.2.3Finalized the listing of an additional 10% stake in Telecom Egypt on the EGX, in a successful 3.11x oversubscribed transaction. MoF was the selling shareholder and hence we worked of obtaining all the required approvals, providing regular updates and coordinated with all involved parties to assure a swift implementation of the transaction. 2.2.4Assessing the sale of the stake of MOF in one of its investments , work involved holding calls with potential buyers and investment banks, preparing and sending an RFP to Investment banks and preparing periodic updates on the subject. 2.2.5Assessing the sale of some state-owned entities with electricity sector. 2.2.3 Non disclosure given due to activity confidentiality 2.2.4 Non disclosure given due to activity confidentiality 2.2.5.1 -Running the operational aspects of MoF’s first Green Loan and Islamic Financing Facility concluded in November 2021 for USD 3Bn to fulfill the budget requirements for 2021/2022. 2.2.5.2-Working on the required reports under the Green Loan in coordination with concerned parties. 2.2.5.3-Working on the sale of MoF’s stake in certain asset. 2.2.5.4-Work is continued in relation to the proposed structure and mechanics for the offering of certain public assets to the private sector. 2.2.5.5-Work is continued on several outstanding issues between MoF and CBE. 2.2.5.6-Attending weekly meetings pertaining to the process of launching the Sustainable Debt Coalition announced during COP27 by MoF. 2.2.5.7-Working on a return and cost analysis for companies operating in the free zone system. 2.2.5.8-Working on an analysis of the mechanism for maximizing the impact of export subsidies through the export burden reimbursement program. 2.2.5.9-Participating in OECD workshops on the Green Growth Policy Review in Egypt (GGPR). 2.2.5.10Ongoing discussions with lenders and multilateral organizations on potential loans that can be granted to support the budget deficit. Work includes attending meetings, providing updates, liaising with other government bodies etc. 2.2.5.11Finalized the Impact and Allocation report for Egypt’s first sovereign green loan. 2.2.5.12Work is continued on transitioning amending a current MoF loan agreement to accommodate for the LIBOR Transition process. 2.2.5.13Worked on several memos and updates requiring MoF’s opinion on Libor transition for some multilateral loans. 2.2.5.14Completing the process of obtaining new financing for MoF from international banks, with a guarantee from a multilateral institution for the purpose of financing and refinancing social projects in the budget. The work done included getting necessary approvals, providing regular updates, negotiating with banks, hiring legal counsels, reviewing the relevant agreements, etc. 2.2.6.1-Preparing a study to estimate the expected total amount of the export subsidy required by the Ministry of Finance within four years. 2.2.6.2-preparing a cost-benefit analysis for the automotive electro-fitting initiative to assess the feasibility of establishing this initiative and its reward. 2.2.6.3-preparing a cost-benefit analysis for the property export initiative to assess the feasibility of establishing this initiative and its reward. 2.2.6.4-Provide the OECD with the MOF's contribution to the Green Growth Policy Review in Egypt (GGPR) on the assessment of Egypt's progress in meeting its domestic and international environmental policy commitments. 2.2.6.5-Working on a cost-benefit analysis for companies operating in the free zone system. 2.2.6.6-Study the financial statements of number of companies to assess their rights to receive export subsidies. 2.3.1.1The World bank mission started in June 4th - 8th, 2023 for technical assistance to PPP Central Unit through the Public – Private Infrastructure Advisory Facility (PPIAF), The mission consists of the following consultants: World Bank - CPCS Transcom - ARUP International Projects - Shahid Law Firm - Sets -Mobilization and Kick-off meeting took place on 4th of June 2023 at the Ministry of Finance premises. -The mission’s objective was to consult and have technical discussions with the PPP Central Unit, the Ministries of Finance, Planning and Economic Development, Environment and relevant line ministries on the two components of the TA namely: (i) operationalization of the fiscal commitments and contingent liabilities (FCCL) framework; and (ii) development of processes, procedures, and a framework to support the integration of climate considerations into PPP project screening and prioritization. -Meetings have been held with the mission, PPP central Unit and line ministries at both advanced and basic level of PPP expertise to have a technical discussion on FCCL framework operationalization. -Line Ministries are (Ministry of Transport, Ministry of Housing utilities & Urban Communities, Ministry of Environment, Ministry of Planning & Economic Development and Ministry of Electricity). 2.3.2.1The ultimate objective is to develop a robust Fiscal commitments and contingent liabilities (FCCL) framework and support its implementation by key stakeholders for strengthening Egypt’s overall debt management framework for PPPs, and build capacity of the Central PPP Unit and key line agencies to develop and deliver a robust PPP program. -Expected to receive the draft FCCL Framework Report manual in Q3 2023. Expected Consultative Workshop in Q3 2023. Capacity Building Workshops in Q4 2023. Submission of the first draft of the guidelines in Sep., 2023. 2.32.1The initial agreement has been drafted and negotiations between the Ministry of International Cooperation and the EBRD is undergoing. 2.3.2.2The Prime Minister has approved on establishing the facility of EUR 10 million. 2.3.2.3The Ministry of International Cooperation is in negotiations with the EBRD. |  |  |  |

| Output 3 | Indicators |  | Baseline | Annual target | Progress / target |
| --- | --- | --- | --- | --- | --- |
| Enhancing Effectiveness of MOF Assistance Programs Budget: $0 Expenditure to date: $0 | - Priority Sector identification |  |  |  |  |
|  | - Value chain analysis of the sector |  |  |  |  |
|  | - Gap identification for the sector |  |  |  |  |
| Planned activities |  | Results |  |  |  |
| Activity 1: Design reforms for financial distortions in agricultural and commodity sector |  | After the approval of Prime Minister’s Office and in coordination with Ministry of Agriculture and Land Reclamation this activity will be fulfilled through Ministry of Agriculture. |  |  |  |

| Output 4 | Indicators |  | Baseline | Annual target | Progress / target |
| --- | --- | --- | --- | --- | --- |
| Professional assistance provided to ministerial support teams Budget:$ 280,350.00 Expenditure:$ 134,680.64 | - Groundwork for preparation of yearly budget and MTB projection scenarios |  | 5 Budget | 1 FY 2023/2024Budget | The Buget is finalized and approved from Parliament and after approval it is published on MOF website . |
|  | - Developing reports for Cabinet of Ministers and Presidency on budget operations and fiscal performance |  |  |  |  |
|  | - Meeting up with rating agencies for assessment of GoE’s credit rating profile. |  |  |  |  |
|  | - Representations in bilateral and multilateral donors’ negotiations and with IFIs on the macroeconomic and fiscal policies. |  |  |  |  |
|  | - Prepare occasional presentations on various economic topics to be delivered to investors, Cabinet of Ministers, Minister of Finance and Presidency |  |  |  |  |
|  | - Representation in IMF negotiations on a semi-annual basis in Article IV missions and Post-Program Monitoring |  |  |  |  |
|  | - Develop, prepare and update reports on PMI performance for Minister and Cabinet of Ministers |  |  |  |  |
|  | - Support various units within MoF including DMU, International Affairs and others by providing economic data and analysis |  |  |  |  |
|  | - Update Medium-Term Debt Strategy (MTDS) and Medium-Term Revenue Strategy (MTRS) as needed |  |  |  |  |
|  | - Represent MFPU in Ministerial meetings on several issues including but not limited to debt, energy, hedging and COP27 matters |  |  |  |  |
|  | - Set-up, prepare and negotiate with investment banks on potential opportunities to enhance fiscal operations such as hedging mechanism and investor opportunities |  |  |  |  |
|  | - Capacity development to executive support team |  | 29 Employee and Consultant | 9 Employee and Consultant | 3 Economist Economic Researcher Senior Finance Expert Finance Analyst Head of Official Editing Unit Advisor for Financing Affairs Technical Assistant for Head of Customs Authority |
| Planned activities |  | Results |  |  |  |
| - Activity 1: Support to Macro-Fiscal Policy Unit - Groundwork for preparation of yearly budget and MTB projection scenarios - Developing reports for Cabinet of Ministers and Presidency on budget operations and fiscal performance - Meeting up with rating agencies for assessment of GoE’s credit rating profile. - Representations in bilateral and multilateral donors’ negotiations and with IFIs on the macroeconomic and fiscal policies. - Prepare occasional presentations on various economic topics to be delivered to investors, Cabinet of Ministers, Minister of Finance and Presidency - Representation in IMF negotiations on a semi-annual basis in Article IV missions and Post-Program Monitoring - Develop, prepare and update reports on PMI performance for Minister and Cabinet of Ministers - Support various units within MoF including DMU, International Affairs and others by providing economic data and analysis - Update Medium-Term Debt Strategy (MTDS) and Medium-Term Revenue Strategy (MTRS) as needed - Represent MFPU in Ministerial meetings on several issues including but not limited to debt, energy, hedging and COP27 matters - Set-up, prepare and negotiate with investment banks on potential opportunities to enhance fiscal operations such as hedging mechanism and investor opportunities - Attend medium and high-level committees in preparation of various initiatives where MoF. - Provide analytical, data and research support when needed on matters related to green economy in general and COP27 follow-ups in particular leading up to COP28. |  | 4.1.1. Continued to update budget analytical tables to reflect revisions in estimates over the medium-term 2023/2024 and 2024/2025. 4.1.1.2 Continued working on budget circular for FY 2023/2024, with the budget department ahead of budget preparations. 4.1.1.3Updated estimates for FY 2022/2023 and worked on budget estimates 2023/2024 with relevant departments. 4.1.1.4Laid out the groundwork for the Budget Statement for FY 2023/2024. 4.1.1.5Worked on the Budget Statement for FY 2023/2024. 4.1.2.1Prepared monthly actual performance tables for fiscal operations covering the analysis of expenditure and revenues performance. 4.1.2.2Prepared the fiscal operations presentations to be presented to Cabinet . 4.1.2.3Prepared the memo to be presented to Presidency on fiscal performance for the period July-April. 4.1.2.4Prepared the expected fiscal operations for preliminary budget 2023/2024 to be presented by Minister to Cabinet and Presidency 4.1.2.5Updated debt profiles from October 2022 till January 2023 in preparation for debt projections within budget FY2023/2024. 4.1.3.1Prepared monthly actual performance tables for fiscal operations for the period July- April covering the analysis of expenditure and revenues performance. 4.1.3.2Prepared the memo to be presented to Presidency on fiscal performance for the period July-April. 4.1.3.3Continued to lead regular communication with the rating agencies (Fitch, S&P and Moody’s) over Q1 &Q2 by providing them with necessary data to update their reports and rating assessment, review and comment on draft rating reports on Egypt, as well as arrange annual rating visits. 4.1.3.4 Prepared and compiled data in response to S&P’s Borrowing Survey with focus on Egypt data. 4.1.3.5Prepared the data necessary to lead in sovereign credit rating reviews by Moody’s (on an exceptional basis) and Fitch. 4.1.3.6Coordinated meetings between Fitch ahead of their reviews with CBE, MoF and private sector entities. 4.1.3.7 Assisted CBE team in discussions with Moody’s on an exceptional basis ahead of Moody’s exceptional committee on Egypt. 4.1.3.8 Prepared necessary data for Fitch and Moody’s ahead of their reviews of Egypt’s credit rating. 4.1.3.9Addressed and conducted a meeting with the JCRA (Japanese Credit Rating Agency) to talk about the current macroeconomic situation in Egypt. 4.1.4.1Attended and presented Egypt’s recent macroeconomic developments to investors and participated in the discussion. 4.1.4.2Answered questionnaires sent by the Arab Monetary Fund on Egypt’s current reforms and estimates. 4.1.4.3Attended meetings with OECD within the context of the Country Programme currently in place. 4.1.4.4Attended and participated in a mission by the World Bank regarding tax expenditure and tax administration as part of the Country Economic Memorandum (CEM)”; the new World Bank study on Egypt’s long-term opportunities and challenges for development. 4.1.4.5Attended and participated in a mission by the OECD regarding the preparations for the first PFM Technical Advisory Group meeting which will serve as an inter-ministerial group providing technical advice on project implementation and key PFM reforms. 4.1.4.6Led on several investor calls over two days regarding Egypt’s maiden Sukuk Issuance. 4.1.4.7 Led discussions with the Arab Monetary Fund on latest developments on Egypt’s macroeconomic front. 4.1.4.8Acted as focal points between MoF and OECD regarding their country economic survey by compiling and reviewing the answers provided from several departments. 4.1.4.9Represented the Ministry of Finance on an OECD panel on carbon pricing where we delivered a presentation on Egypt’s experience on energy subsidy reform. 4.1.4.10 Handled the World Bank’s DPF Data Requirements. Participated as an MFPU representative in the OECD’s workshop on medium-term expenditure framework, as part of the OECD Country Programme. 4.1.4.11Attended a workshop hosted by the IMF METAC on fiscal costs and risks from PPPs. 4.1.4.12Attended the Revenue Statistics Workshop organized by the OECD in Addis Ababa as part of the Egyptian Delegation to discuss trends in the domestic revenue mobilization in Africa and prepared a memo for the Minister with the outcomes and potential suggestions. 4.1.4.13Delivered MoF’s comments on the country note and projections for the Egyptian economy for incorporation in the OECD economic outlook to MPED/OECD team. 4.1.4.14 Prepared a memo for the Vice Minister concerning the World Food Programme Country Strategic Plan (2023-2028). 4.1.4.15Representing the Ministry of Finance at the Joint US-Egypt first economic commission. 4.1.4.16 Representing the Ministry of Finance at the IDSC experts’ discussions on fiscal and debt sustainability. 4.1.4.17Representing the Ministry of Finance at the IDSC experts’ discussions on Economic Diplomacy. 4.1.5.1Prepared a presentation on latest developments on customs, in light of external trade report for the period July-December 2021/2022, full year 2021/2022 and first two months in 2023. 4.1.5.2Prepared analytical tables on foreign trade data extracted from the Customs Authority to support Vice Minister’s discussions. 4.1.5.3Prepared a presentation to be used by Vice Minister on inflation developments and peer-to-peer comparison. 4.1.5.4Prepared several memos and presentations on hedging mechanism for oil in light of recent prices to be presented to Minister. 4.1.5.5Prepared and reported the recent developments on Egypt’s sovereign credit rating to Minister, Prime Minister and Presidency detailing strategies and measures to ensure improvement on the ratings’ front. 4.1.5.6Prepared a presentation on debt developments and projections for Minister interventions. 4.1.5.7Prepared a presentation on debt and interest payments developments to support Vice Minister’s presentation in an IDSC forum. 4.1.5.8Prepared a presentation for Minister to support his interventions on the developments of Egypt’s economy and its economic reform programs. Prepared presentations on foreign trade data extracted from CAPMAS. 4.1.5.9Prepared report on FDIs performance in Africa and the Middle East from the investment monitor report published in May 2023. 4.1.5.10Prepared a report on the details of Basil III and how the Fx market in the banking sector is indulged in the process of linking the parallel market of the foreign exchange. 4.1.6.1Represented the Ministry of Finance in several follow-up and preparatory meetings in the context of the economic reform program and ahead of the first review. 4.1.6.2 Represented the Ministry of Finance in IMF meetings with Ministries of Environment, International Cooperation, CBE and FRA in the context of Egypt’s access to the RST Fund. 4.1.6.3Presented a detailed memo to Presidency on IMF Board of Directors’ Meeting in December 2022, explaining each constituency’s position regarding Egypt’s exceptional access to an EFF. 4.1.6.4Attended the IMF/WB Spring Meetings in Washington DC as part of the Egyptian Delegation to continue discussions within the context of the IMF program. 4.1.6.5Presented a detailed memo to Presidency on key results and discussions points raised with IMF during the Spring Meetings ahead of the first review. Prepared the monthly report on PMI developments in Egypt for December 2022, January and April 2023. 4.1.8.1Worked on the bond prospectus for latest Sukuk and Panda bond issuances with DMU. 4.1.8.2Worked on supporting International Affairs Unit with talking points to Minister, attending roundtables with international development partners and other events. 4.1.8.3Attended a training with the DMU on how to best utilize the Bloomberg portal to have access to necessary data related but not limited to commodity prices and debt capital market developments. 4.1.8.4Contributed in the debt publications, related to the World Bank’s DPF data requirements. 4.1.8.5Supported the Transparency and Citizen Engagement Unit with their publications especially by providing data on fiscal and debt Organized, attended and presented several meetings with international investment banks such as Citi, Goldman Sachs and JP Morgan on hedging in Egypt on commodities Attended technical and logistical meetings related to MoF’s “Sustainable Debt Coalition” to be hosted by Egypt in September 2023. 4.1.13.1Working with USAID on climate risk financing 4.1.13.2Working with the World Bank, FRA, IDSC and the Egyptian Federation for Insurance on Disaster and Climate Risk Financing Strategy 4.1.13.3Supported the World Bank in pinpointing terms of reference for a climate advisor within the Ministry of Finance. 4.1.13.4Represented the Ministry of Finance in the coalition of Finance Ministers for climate action (SHERPA) meetings. 4.1.13.5Attended the Net Zero Delivery Summit in collaboration with City of London that is in association with COP27 and included Minister of Finance speech. 4.1.13.6Attended workshop on climate macroeconomics by IMF in collaboration with the coalition of Finance Ministers for climate action (SHERPA) meetings. |  |  |  |
| Activity 2: Support to Technical and Legal Consultancy Pool Prepare TOR and hire according to needs. |  | Took necessary action for preparing TORs and contracting with employees and consultants as follows; hiring 9 new staff member for the project's activities; 3 Economist Economic Researcher Senior Finance Expert Finance Analyst Head of Official Editing Unit Advisor for Financing Affairs Technical Assistant for Head of Customs Authority |  |  |  |

## Annex II: Updated Risk and Issues  Logs

| PROJECT RISKS AND ISSUES UPDATED PROJECT RISKS: (as in the project document) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Description | Date Identified | Type | Impact & Probability | Countermeasures/ Mngt Response | Owner | Last update | Status |
| 1 | Enter a brief description of the risk | when was the risk first identified | Choose one of the following: Environmental Financial Operational Organizational Political Regulatory Strategic Other | Describe the potential effect on the project if this risk were occur Enter probability on a scale from 1 (low) to 5 (high) P = estimate of the likelihood of the risk occurring Enter impact on a scale from 1 (low) to 5 (high) I = effect on the project if the risk were to occur How Critical (H: High M: Medium, L: Low) | What actions have been taken/will be taken to counter this risk | who has been appointed to keep an eye on this risk | when was the status of the risk last checked | e.g. dead, reducing, increasing, no change |
| 2 |  |  | Environmental Financial Operational Organizational Political Regulatory Strategic Other | Text P = I = C= |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |

| PROJECT RISKS AND ISSUES UPDATED PROJECT ISSUES: (Issues arising during implementation of the project) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # | Description | Date Identified | Type | Countermeasures/ Mngt Response | Last update | Status |
| 1 | Enter a brief description of the issue | when was the issue identified | (i.e. as per choices in Atlas: Change, Problem, Other) | what actions have been taken/will be taken to address this issue | when was the status of the issue last checked | e.g. pending, solved |
| 2 |  |  | Request for Change problem other |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |

## Annex III: Annual Work Plan (for next year)

## Annex IV: Assets inventory

| SECTION 7: ASSETS LIST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Asset ID | Description |  |  |  | Type | Serial No. |  |  | Tag No. |  | Model |  | Location |  | Acquisition Date | Currency | Cost |
| 1 | HP Office Jet 7612 printer |  |  |  | Equipment | G1X85A |  |  |  |  | G1X85A |  | PMU |  | 30/10/2018 | LE | 3500 |
| 2 | Camera flash part |  |  |  | Equipment |  |  |  |  |  |  |  | Minister's Office |  | 23/9/2018 | LE | 650 |
| 3 | Camera Battery & Charger |  |  |  | Equipment |  |  |  |  |  |  |  | Minister's Office |  | 23/9/2018 | LE | 80 |
| 4 | Fingerprint Devices (ZK-K15) |  |  |  | Equipment | ZK-K15 |  |  |  |  | ZK-K15 |  | Consultant Tower |  | 11/6/2018 | LE | 3300 |
| Certified by: |  |  | Project Manager's signature |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Asset ID |  |  |  | Starts at 1 and increases |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description: |  |  |  | Short description of the asset eg: Dell Optiplex 660X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type: |  |  |  | Electrical, Furniture, Vehicle |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Serial No. : |  |  |  | For vehicle it is the chassis, for electrical equipment it is the serial number from the manufacturer |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tag No. : |  |  |  | Furniture need a tag number to stick on the item (chose the numbering) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location: |  |  |  | The room the asset is in |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Acquisition Date: |  |  |  | When it was bought |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex V: Markers

| [Resources] Analyze how the level of resources and composition of resources (core, government cost sharing, bilateral/multilateral resources, vertical funds, private sector funding, IFI funding, etc.) contributed to the achievement of planned results – what worked well and why. | [Resources] Analyze how the level of resources and composition of resources (core, government cost sharing, bilateral/multilateral resource, vertical funds, private sector funding, IFI funding, etc.) hindered the achievement of planned results – what did not work well and the way to correct the course of action. |
| --- | --- |
| [Hows] Analyze what types of UNDP’s interventions worked well and why. | [Hows] Analyze what types of UNDP’s interventions did not work, why and the way to correct the course of action. |
| [Whos] Describe positive impact on target beneficiaries. Analyze what worked well and how it helped leave anyone behind | [Whos] Describe no or negative impact on target beneficiaries. Analyze what did not work, why and the way to correct the course of action not to leave anyone behind. |
| [Partnerships] Analyze what partnerships worked well and why. | [Partnerships] Analyze what partnerships did not work, why and the way to correct the course of action. |
| [Joint Programming] Analyze positive impact of joint programming, including for the implementation of the common chapter. Analyze what worked well and why. | [Joint Programming] Analyze no or negative impact of joint programming, including for the implementation of the common chapter. Analyze what did not work well, why and the way to correct the course of action. |
| [SSC/TrC] Describe positive impact of south-south and/or triangular cooperation on the CPD output. Analyze what worked well and why. | [SSC/TrC] Describe no or negative impact of south-south and/or triangular cooperation on the CPD output. Analyze what did not work, why and the way to correct the course of action. |
| [Humanitarian] Describe UNDP’s contribution to integrate long-term aid and humanitarian assistance (development and humanitarian nexus). Analyze what worked well and why. | [Humanitarian] Describe key challenges in integrating long-term aid and humanitarian assistance (development and humanitarian nexus). Analyze what did not work, why and the way to correct the course of action. |

## Annex VI: innovative tools and methodologies

| Output ID | Output Name | Testing in progress | successfully piloted | successfully scaled | Select applicable innovative tools and methodologies |
| --- | --- | --- | --- | --- | --- |
| XXXX |  | ☐ | ☐ | ☐ | Alternative Finance (including Social Impact Bonds and Investment / Pay for Success) |
| XXXX |  | ☐ | ☐ | ☐ | Artificial Intelligence |
| XXXX |  | ☐ | ☐ | ☐ | Behavioural Insights |
| XXXX |  | ☐ | ☐ | ☐ | Blockchain |
| XXXX |  | ☐ | ☐ | ☐ | Challenge Prizes |
| XXXX |  | ☐ | ☐ | ☐ | Crowdfunding |
| XXXX |  | ☐ | ☐ | ☐ | Foresight |
| XXXX |  | ☐ | ☐ | ☐ | Games for Social Good |
| XXXX |  | ☐ | ☐ | ☐ | Human-Centered Design |
| XXXX |  | ☐ | ☐ | ☐ | Innovation Lab |
| XXXX |  | ☐ | ☐ | ☐ | Micronarratives |
| XXXX |  | ☐ | ☐ | ☐ | Mobile-Based Feedback Mechanism |
| XXXX |  | ☐ | ☐ | ☐ | Positive Deviance |
| XXXX |  | ☐ | ☐ | ☐ | Big Data (including New and Emerging Data) |
| XXXX |  | ☐ | ☐ | ☐ | Randomized Controlled-Trial / Parallel Testing |
| XXXX |  | ☐ | ☐ | ☐ | Real-Time Monitoring |
| XXXX |  | ☐ | ☐ | ☐ | Remote Sensing/ Unmanned Aerial Vehicles (UAVs, drones) |
| XXXX |  | ☐ | ☐ | ☐ | Not Applicable |
| XXXX |  | ☐ | ☐ | ☐ | Alternative Finance (including Social Impact Bonds and Investment / Pay for Success) |
| XXXX |  | ☐ | ☐ | ☐ | Artificial Intelligence |
| XXXX |  | ☐ | ☐ | ☐ | Behavioural Insights |
| XXXX |  | ☐ | ☐ | ☐ | Blockchain |