PAC Meeting Minutes

Being LGBTI in the Caribbean: Reducing Inequality & Exclusion Experienced by LGBTI

11 December 2018

Present: Regional Hub Panama: Richard Barathe, Maribel Landau, Karin Santi, Juana Cooke.  
Dominican Republic Country Office: Luciana Mermet, Ana Cabarcos:  Barbados Country Office: Cherise Adjodha; Haiti Country Office; Leanne Baumung; Jamaica Country Office: Alicia Bowen-McCulskie and Elsie Laurence-Chounoune; USAID: Luis Durán; REDLACTRANS – Caribbean: Alexus D’Marco; CARIFLAGS: Dane Lewis

Apologies: Chisa Mikami

Introduction
Richard Barathe, Director of the Regional Hub welcomed the participants to the PAC and asked everyone to introduce themselves. He then explained the purpose of the PAC and highlighted the importance of UNDP’s work on supporting countries to uphold the human rights of its citizens. Noting that UNDP at the regional level has very good experiences partnering with USAID responding to diverse development challenges, he thanked Luis Durán for his close cooperation with UNDP in the conceptualization of the project.

Presentation of the Project
The project was presented by Karin Santi, providing an overview of the development challenge the project will aim to address.  Being LGBTI in the Caribbean (BLIC) builds on a global partnership between USAID and the UNDP HIV, Health and Development (HHD) team. The first project was implemented in Asia and the Pacific and since then similar projects are being implemented in Africa and Europe.

The BLIC project, with a budget of just under one million dollars, will be implemented in four countries: Barbados, Dominican Republic, Haiti and Jamaica.  Challenges to be addressed include inequality and exclusion of LGBTI persons; legal, policy and regulatory frameworks that continue to undermine LGBTI inclusive development and finally, capacity of LGBTI organisations to engage and impact public policies.   The project will have both national and regional components.  At the national level, the project will focus on producing evidence on the impact of inequality and exclusion of LGBTI persons and strengthening national partnerships among LGBTI civil society organisations and national governments.  Activities will include drafting of national LGBTI reports, hosting of Roundtables and capacity development initiatives.  At the regional level, the focus will be on multi-country studies, such as the Intersex research study as well as on cross-country learning through a regional dialogue.

The BLIC project will be managed by a project board, to ensure coordination and planning of activities across national and regional stakeholders.  The Board will have overall authority over the project and is responsible for its initiation, direction, review and eventual closure.  The Project Board will consist of a panel with the project responsible parties, including CARIFLAGS and REDLACTRANS as regional LGBTI organisations, Country Office representatives and the Donor.

Since the agreement has been signed UNDP has submitted an Annual workplan to USAID and this workplan will be shared with Country Offices to use as a basis to develop their own-country specific plans.  UNDP will work with, the USAID contractor Panagora to develop a comprehensive monitoring and evaluation plan.

UNDP and USAID have also discussed the marketing and branding strategy for this project.  UNDP will be able to brand the project with its logo while USAID will on a case-by-case basis decide whether their logo should be included.

Questions and Discussion

During the discussions colleagues noted that this a very important project for UNDP and that they have started to discuss the project with civil society organisations in the respective countries.  Dominican Republic noted that they have collaborated well with USAID working LGBTI issues and look forward to start recruiting for the Community Coordinator position soon.

In the ensuing discussion UNDP Barbados said that It is important to bear in mind the CARICOM and OECS context in how the project is framed.   It was also noted that the desired change as outlined in the project document is not measurable, that it will difficult to show how the project has reduced inequality. The Office also stressed that it may be strategic to include stakeholders such as faith based organisations and universities to move on issues such as legislation.

Elsie Laurence-Chounoune, UNDP Jamaica explained that UNDP is accountable for results at the output level and not at the outcome level.  She also stressed that we need to be cognizant that with this project the issues to be addressed will be context specific. The desired change or the outcome of the project does not mean that the project will be responsible to achieve that result but rather that the project contributes to the result.

USAID agree with Elsie that we need to contextualize the project, looking for the best scenarios for each specific context. The draft annual workplan will be circulated to all the offices and the national offices will review and revise the workplan, including their country-specific activities.

The meeting also considered the concern raised by the Jamaica Office that it will not be able to get the Government of Jamaica to endorse the project.  Both Barbados and Haiti Country Offices expressed similar concerns.  DIM projects are required to have government endorsements.

The meeting recognized that given the subject getting such endorsement will not be easy and several approaches were discussed including using HIV or health as entry points.  The Dominican Republic informed the meeting that endorsement will come from the National AIDS Council, since the Council is generally more open to working with vulnerable groups.

The meeting took note of civil society partners concern that it is important to look more broadly at the impact of exclusion, stigma and inequality experienced by LGBTI persons.  That is for example, in the education sector, access to social services or in the workplace.

To allow for additional entry points there was a request to include a broader focus on HIV and health in the project document.  It was proposed that the language on human rights is changed to include health approach or a broader focus on inequality approach.

The Haiti Office noted that the Gender Equality Marker attributed is GEN 3, meaning that in the project document we would need to, for example, see a gender analysis, strategies for enhancing gender equality, sex disaggregated indicators and results. Recognising that while the project addresses gender equality though a focus on issues of gender identity, UNDP´s Gender Equality Strategy does not specifically address sexual orientation and gender identity.

The meeting concluded with Richard Barathe thanking the participants for the useful feedback and offering support to Country Offices in moving forward with this important initiative.

Decisions

- The Panama team together with country office focal points to adjust the language in the project document to allow for new entry points to engage governments.

- Country Offices will continue to seek government endorsement.

- Country Offices will document efforts towards securing government endorsement.

Appendix 1: Confirmation of Minutes

| Organization | Name |
| --- | --- |
| UNDP Barbados and OECS | Cherise Adjodha, HIV Focal Point |
| UNDP Haiti | Leanne Baumung, HIV Focal Point |
| UNDP Jamaica | Elsie Laurence-Chounoune, DRR |
| UNDP Dominican Republic | Luciana Mermet, DRR Ana Cabarcos, HIV Focal Point |
| USAID | Luis Durán, Inclusive Development Specialist |
| REDLACTRANS | Alexus D’Marco |
| CARIFLAGS | Dane Lewis |