BEING LGBTI IN THE CARIBBEAN (BLIC) Bi-Annual Report Submission Date: October 30, 2024 [Contract/Agreement] Number: AID-517-IO-17-00001 Activity Start Date and End Date: September 22, 2018, to February 28, 2025 [COR/AOR] Name: Luis Duran Submitted by Jean Sano Santana, Chief of Party United Nations Development Programme City of Knowledge, Building 128, Panama City, Panama Tel: +507 302 4610 Email: jean.sano.santana@undp.org This document was produced for review by the United States Agency for International Development in the Dominican Republic (USAID/DR). -04-2024 to 30-09-2024

# Program Overview/Summary

| Program Name: | Being LGBTI in the Caribbean (BLIC) |
| --- | --- |
| Activity Start Date and End Date: | September 22, 2017, to February 28, 2025 |
| Name of Prime Implementing Partner: | United Nations Development Programme |
| [Contract/Agreement] Number: | AID-517-IO-17-00001 |
| Name of Subcontractors/Sub-awardees: | Barbados and Eastern Caribbean Equals Barbados Dominican Republic: ProActividad Comunidad de Trans, Travestis y Trabajadoras Sexuales Dominicanas (COTRAVETD) Trans Este Podemos Avanzar (TEPA) Trans Unidas Dominicanas (TUD) Movimiento LGBTIQ Jamaica TransWave Equality for All Foundation Guyana Guyana Trans United Proud To Be Trans Regional: Eastern Caribbean Alliance for Diversity and Equality – ECADE Cari-Flags |
| Major Counterpart Organizations: | Not Applicable |
| Geographic Coverage (cities and or countries): | Barbados, Dominican Republic, Guyana, and Jamaica |
| Reporting Period: | April 1, 2024, to September 30, 2024 |

Contents

1.	Program Overview/Summary	0

1.1	Program Description/Introduction	2

2.	ACTIVITY IMPLEMENTATION PROGRESS	4

2.1	Progress Narrative	4

2.2	Implementation Status	7

2.3	Implementation Challenges	10

2.4	Gender Equality and Female Empowerment	11

2.5	Science, Technology, and Innovation (STIP) Impacts	11

2.6	Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts	12

2.7 LGBTI Inclusion	12

LGBTI inclusion is the focus of the project.	12

2.8 Inclusion of Persons with Disabilities (PwD)	12

3.	Environmental Compliance	12

4.	STAKEHOLDER PARTICIPATION AND INVOLVEMENT	13

5.	MANAGEMENT AND ADMINISTRATIVE ISSUES	14

6.	Budget	15

7.	LESSONS LEARNED	15

8.	PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS	15

9.	How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report	16

## Program Description/Introduction

Being LGBTI in the Caribbean (BLIC) is a regional programme that aims to enhance knowledge, partnerships, and capacities of LGBTI communities, civil society, and States to reduce human rights violations and negative attitudes towards LGBTI people in the Caribbean, with country level focus in Barbados, Dominican Republic, Guyana, and Jamaica, as well as regional activities.

Research and data collected by the project have highlighted that the transgender community, especially transgender women, as the most marginalized segment of the LGBTI groups. In the Dominican Republic, for example, 75% of trans women who participated in the National LGBTI survey reported experiencing an act of violence or discrimination in the last year, compared to 42% of the LGBI population. Stigma is relatively higher towards transgender women in other implementing countries. In Jamaica, for instance, all trans women respondents (100%) reported earnings below the average household monthly income, compared to 39% of the LGBI population. In Barbados, 62.2% of transgender women respondents noted that they had attempted to end their life, which is three times more than the (21.4%) of cisgender respondents who reported attempting suicide.

As a result, building on the work and milestones achieved under first and second phases of the project (2017-2023), the ongoing third phase focuses on the socio-economic empowerment of transgender women and gender diverse persons through inclusive public policies and model interventions. This new phase of the project will be implemented in collaboration with governments, civil society, regional institutions, and other stakeholders to advance the social-economic inclusion of transgender women.

The objectives and activities of the project are as follows:

| Objective (s) | Project Activities |
| --- | --- |
| 1. To support the governments of Barbados, Dominican Republic, Guyana, and Jamaica in the revision of policies for the social, economic, and labor inclusion of transgender women and gender diverse persons. | 1.1 Research on the access of transgender women and gender diverse persons to social protection services. 1.2 Research on the access of transgender women and gender diverse persons to the job market. 1.3 Mapping of the status of gender recognition. |
| 2. To strengthen the capacities of civil society groups and community organizations of transgender persons to advocate for the revision of policies for the economic and labor inclusion of transgender and gender diverse persons. | 2.1 High impact funding to civil society organizations (CSOs) to conduct advocacy efforts. 2.2 High impact funding to CSOs to conduct awareness activities (pride, transgender day of remembrance, etc.) 2.3 Hands on capacity development through the transfer of knowledge and tools. |
| 3. To promote the individual economic and labor inclusion of transgender women and gender diverse persons in Barbados, Dominican Republic, Guyana, and Jamaica through direct services. (see image 1 below as refence) | 3.1 High impact funding to CSOs to provide direct services to transgender women and gender diverse persons. 3.2 Support CSOs in the establishment of a psychosocial support system through the hiring of a social worker and a psychologist 3.3 Enrollment of program participants in vocational training/academic programs. |

This report covers six months of project implementation (April 1, 2024, to September 30, 2024) providing an overview of status of planned activities and upcoming initiatives.

# ACTIVITY IMPLEMENTATION PROGRESS

## Progress Narrative

From April 1, 2024 to September 30, 2024, the project has enrolled 184 transgender and gender diverse participants. All participants have undergone psychological and socio-economic assessments, allowing the program to address both mental health and economic needs. This approach ensures that barriers to job access are tackled from multiple angles, recognizing the unique challenges faced by transgender and gender-diverse individuals. Through these assessments, the participants developed their life plans, setting short and long-term goals for their personal development and care plans to help them coordinate how they will achieve these goals. These assessments and plans guide the tailored support that each participant is receiving under the project.  Participants are enrolled in diverse vocational and academic courses such as cosmetology, photography, cake making and decorating, numeracy, literacy, bookkeeping, office management and computer studies. In some instances, program participants are being supported for their higher education schooling. To date 75 participants have been enrolled into their training programs while the remaining participant are in the process of enrollment. Participants who currently own a business or those with businesses ideas are being supported through the Innovation Lab Offices of UNDP in Barbados and the Dominican Republic.

Overall, we are working with nine (9) organizations across the region:

- Barbados (1): Equals, a LGBT+ led and ran organization.

- Dominican Republic (5): ProActividad, a LGBT+ organization, is serving as institutional umbrella (fiscal sponsor) for four trans organizations: Comunidad de Trans, Travestis y Trabajadoras Sexuales Dominicanas (COTRAVETD), Trans Este Podemos Avanzar (TEPA), Trans Unidas Dominicanas (TUD) and Movimiento LGBTIQ.

- Guyana (2): Guyana Trans United (GTU) and Proud To Be Trans (PTBT), both trans led and ran organizations.

- Jamaica (1): Transwave, a trans led and ran organizations.

The agreements between the BLIC project and these organizations aim to:

- Grant high impact funding to CSOs to provide direct services to 170 transgender women and gender diverse persons (program participants) across the implementing countries.

- Support CSOs in the establishment of psychosocial support systems for 170 program participants through the hiring of social workers and a psychologists.

- Enrollment of 170 program participants in vocational training/academic programs.

Over the past months, the BLIC project and the organizations have been implementing the following program steps:

- Implementing partner CSO. Recruited potential program participants from their community networks. Builds relationships with academic/vocational institutions and secure program participants’ enrollment. Trains an intern or mentee, who is a transgender woman or gender diverse person, to become effective project managers. There are six mentees total: Barbados (1), Dominican Republic (2), Guyana (1), and Jamaica (2).

- Potential Participants. Interested transgender women and gender diverse person provided consent (or do not) to be evaluated by the project social workers and psychologists as well as for their information being captured for project monitoring, evaluation and communication purposes.

- Project Psychologists. Conducted a mental health evaluation. The project hired an LGBTIQ+ sensitive psychologist for each implementing country for a total of four mental health providers regionally.

Project Social Workers. Conducted a social needs assessment and program readiness test. The project hired an LGBTIQ+ sensitive social worker for each implementing country for a total of four social services navigators regionally.

- Project Participants. Selected participants worked with the project social workers and psychologists, building on the initial evaluations, and completed a life plan that includes mental health care referrals (if needed), social services referrals (if needed) and a vocational or business venture path. Participants are financially supported to access all these services.

- Academic/Vocational Training. Based on each participant’s academic/vocational training aspiration, the implementing partners and the project social workers have facilitated the enrollment of program participants to their desired courses.

Seed funding. Participants who currently own a business or those with businesses ideas are being supported through the Innovation Lab Offices of UNDP in the implementing country offices. Completing a mentoring or business literacy program is required prior to receiving funding.

BLIC national project managers work closely with the CSO partners and the social workers and psychologists to ensure progress. In three out of the four countries, the number of program participants has been reached or surpassed, participants have completed their life plans and are currently taking classes or in the process of enrollment (see next session for more details on indicators).

To support the governments of Barbados, Dominican Republic, Guyana, and Jamaica in the revision of policies for the social, economic, and labor inclusion of transgender women and gender diverse persons, the project has been conducting research.  Knowledge products has been produced for two of the intended research lines in all countries and a consultant has been hired to start working on the third and final investigation line (see next session for more details on indicators).

In this reporting period, the project has continued to enhance the capacities of CSO partners to implement the ongoing joint-program, advocate for LGBTIQ+ people rights, and raise awareness about transgender and gender diverse persons issues. Project coordinators in all countries have conducted inception meetings to ensure understanding of technical, programmatic, and financial procedures. The team has also co-developed monitoring and evaluation, reporting, and financial tools with the CSO partners leadership.  Since the last report, advocacy and awareness raising actions were financially and technically supported in all four countries and beyond:

During International Day Against Homophobia, Biphobia and Transphobia (IDAHOBIT):

In Barbados, with BLIC’s support, EQUALS hosted an IDAHOBIT event consisted of a intergenerational panel discussion followed by a workshop. The panel highlighted the stories of LGBTQ+ community members of various age ranges (Gen Z, Millennial, Gen X and Boomer) to allow for cross generational conversations. After the panel discussion, there was a workshop where the audience was split into four groups and discussed how stigma and discrimination within different contexts impacts LGBTQ+ people of different generations and conceptualized 22 initiatives to tackle them and how the different generations can support each other.

In Jamaica, the project supported Equality For All Foundation in the organization of the Larry Chang Symposium to discuss the findings of the Community Needs Assessment Survey conducted by the organization about LGBTQ+ Jamaicans.

In St. Lucia, the project support ECADE in the organization of TRANSCENDENCE 2024, a three-day regional convening dedicated to addressing the rights, justice, and dignity of transgender and gender-diverse individuals in the Caribbean and Latin America. The conference aimed to identify and advocate for comprehensive legal protections, foster an inclusive society, and empower gender-diverse communities through education, advocacy, and capacity-building initiatives.

During PRIDE:

In Barbados, an Art Festival was scheduled forcibly postponed to November 2nd due to the passing of Hurricane Beryl.

In the Dominican Republic, the project supported REVASA with the political advocacy event that marks the beginning of the Santo Domingo Pride parade.

In Guyana, GTU organized a Drag Fest in Region 6- East Berbice-Corentyne. The event was opportunity for members of the community to display their creative skills, build their confidence and self-esteem in the form of a fashion show. The event also served as a chance to conduct public awareness and promote visibility of the trans-community in that region. The project also contributed to PTBT activities. The organization hosted a movie night. The firm shown encompassed family acceptance of LGBT persons, the misinterpretation of religious scriptures and its adverse consequences. PTPT organized a PRIDE closing meeting to discuss on the success and shortcomings of their advocacy programs as well as planning for future initiatives.

In Jamaica, with BLIC’s support, Equality For All Foundation hosted a Power Breakfast with the objective of gathering local actors from the various agencies who have been supportive of the LGBTQ movement and discuss and plan what the next 10 years of the movement can look like in the country. Additionally, the project supported a Community Care Day to provide the LGBTQ community with a comprehensive hub for psycho-social and physical health services. These services were facilitated by queer and allied practitioners.  The project also contributed to the Pride Opening Ceremony and Brunch.

Other activities aimed at raising awareness and advocating for LGBTI+ rights included:

In Barbados, the project supported CARIFLAG, who in partnership with ILGA/NAC, coordinated the four-day Regional Strategy Conference “Stronger Together” intended to delve into the current landscape of LGBTQI+ issues, highlighting the remarkable progress made and the ongoing efforts to secure and expand rights.

In the Dominican Republic, CSO partners hosted an Enrollment session to the Sistema Unico de Beneficiarios (SIUBEN). This joint activity supported by BLIC and UNDP’s Social Protection program allowed 69 individuals to be registered in SIUBEN databases as potential recipients of government social programs. SIUBEN has the institutional and functional ties with the Social Policy Coordination Cabinet and maintains institutional relationships with sectoral entities in the social sector, which request information from its databases to meet the needs of families in poverty situations.

In the Dominican Republic, the “Communication Workshop with a Human Rights Approach: Misinformation, Hate Speech, and Mental Health” was organized by the UN's Interagency Communication Group (GICOM) as part of the 'Free and Equal' campaign and the 'Being LGBTI in the Caribbean' project. Activists from LGBTIQ+ civil society organizations discussed the challenge of making the positive aspects of the LGBTIQ+ community visible in an environment often marked by discrimination was discussed.

In the Dominican Republic, the project led a Consultation on Digital Inclusion for LGBTIQ+ Groups in the Dominican Republic to discuss strategies and measures to promote the digital inclusion of LGBTIQ+ groups. The conversation centered around identifying challenges and opportunities to improve access.

In the Dominican Republic, the project supported the Second Family Law Institute meeting in Latin America. The meeting helped participants develop and share strategies for protecting LGBT individuals and families across the region.

## Implementation Status

See disaggregated data on the indicators here.

Output 1: Knowledge, strategic information, and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated.

Indicator: Number of research papers on LGBTI produced:

During the reporting period, two (2) research products were completed:

- Inclusive Social Protection and Poverty Alleviation Programs in Barbados, Guyana, Jamaica

- Access Barriers to Social Protection and the Labor Market for Transgender and Gender Diverse People in the Dominican Republic.

All these four research efforts, currently in final stage for publication, focused on transgender and gender diverse individuals’ access to social protection and poverty alleviation programs in the implementing countries. This research paper considered secondary data taken from desk review documents from sources including local civil society and LGBTQ organizations and survey and focus group discussions with community members. The documents will be socialized with relevant stakeholders after publication.

A second line of research focused on identifying barriers and opportunities to access the workforce for transgender and gender-diverse persons in Barbados, the Dominican Republic, Guyana and Jamaica is on the initial stage of evaluation and proofreading. The third and final research effort of the project, on the status of gender identity recognition in all implementing countries, will start later this year. The consultant is already hired.

Deviation Narrative:

The target set (4) was designed to measure the project-wide impact across all four participating countries. However, we are reporting one knowledge product for the Dominican Republic and a combined one for the remaining three implementing countries. To streamline processes and strategically allocate funds, the three knowledge products covering the English-speaking countries were consolidated into a single publication.

Output 2: Policies and tools that enable conditions for equitable access to decent jobs for transgender women and gender diverse persons.

Indicator: Number of vulnerable persons benefitting from USG-supported social services

A total of 184 transgender women and gender diverse person across all four implementing countries are benefitting from USG-supported social services. Services include:

- Psychosocial assessment of participants: all 184 participants have undergone psychological and socio-economic assessments, allowing the program to address both mental health and economic needs. This approach ensures that barriers to job access are tackled from multiple angles, recognizing the unique challenges faced by transgender and gender-diverse individuals. Through these assessments, the participants developed their life plan setting short and long-term goals for their personal development and care plans to help them coordinate how they will achieve these goals. These assessments and plans guide the tailored support that each participant is receiving under the project.  In Barbados, 26 people have been enrolled in the program and 9 of them are taking classes. In Dominican Republic, 114 people have been enrolled in the program and 45 of them are taking classes. In Guyana, 30 people have been enrolled in the program and 7 of them are taking classes. In Jamaica, 14 people have been enrolled in the program and all 14 of them are taking classes.

- Psychological Assessment: from these assessments, over half of the participants have been referred to psychological counseling for support with forms of depression and anxiety. These participants have all been connected with professionals linked to the Ministry of Public Health, ally nonprofits, or private practices in case-by-case basis depending the resources available in each country.

- Socio-Economic Assessment: care plans have been developed for all XXX program participants. Based on the needs of the participants, the social workers have been linking them to various social services through the established referral networks.

- Tailored Psycho-Social Support:  the program is offering continuous psychosocial support to participants which includes mental health counselling and group sessions focused on trauma and grief. Our social workers and psychologists maintain regular check-ins with participants to foster a supportive environment and encourage participants to stay engaged with their therapy and training thus enhancing their overall well-being and employability. To accomplish this, the psychologists and social workers* have been doing the following:

- Weekly check-ins with participants to ensure that they are keeping up with their counselling appointments and managing well with their daily life plans.

- The psychologists have developed a psychoeducation document to sensitize participants on the importance of following through with their counselling sessions for their long-term mental wellbeing management,

- In specific cases, like in Guyana, the social worker has also been providing support to participants in matter outside the scope of the program such as the case of a participant who is engaged in a court process to secure a restraining order against a former partner.

*In the Dominican Republic, due to the large number of participants, the psychologist and social worker are supported by a network of 12 transgender women who have been trained by the program to monitor and follow up with program participants.

- Inclusive Training Opportunities:  Participants are enrolled in diverse vocational and academic courses such as cosmetology, photography, cake making and decorating, numeracy, literacy, bookkeeping, office management and computer studies. In some instances, program participants are being supported for their higher education schooling. To date 75 participants have been enrolled into their training programs while the remaining participant are in the process of enrollment.

- Focus on Self-Employment and Entrepreneurship: Participants who currently own a business or those with businesses ideas are being supported through the Innovation Lab Offices of UNDP in the implementing country offices.

Deviation Narrative

The project was set at 85 individuals, but we achieved an impressive 184 participants, exceeding the target by a substantial margin. This outcome was part of a strategic approach to not only catch up on prior program gaps but also to account for potential drop-offs and attrition over time. By initially training more participants, we ensured that the project could maintain its long-term impact even if some individuals transitioned out or disengaged from the program. This proactive approach has strengthened our capacity-building efforts, maximizing the reach and sustainability of our gender equality and empowerment initiatives in the Caribbean.

Output 3: Capacity of transgender community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge and concrete actions to address stigma and discrimination.

Indicator: Number of persons trained to advance outcomes consistent with gender equality or female empowerment through their roles in public or private sector institutions or organizations

A total of 258 persons were trained through the program joint efforts with CSO partners and other relevant stakeholders.

| Event/Conference/Meeting (See descriptions in section 2.1) | Territorial Focus | People Trained | Sex Disaggregation |
| --- | --- | --- | --- |
| IDAHOBIT event by EQUALS | Barbados | 68 | 41 (F), 27 (M) |
| PRIDE Power Breakfast by Equality for All Foundation | Jamaica | 19 | 8 (F), 11 (M) |
| Second LGBTI Family Law Institute Meeting | Dominican Republic | 30 | No data |
| Strategy Conference “Stronger Together” by CariFLAGS | Regional | 77 | 43 (F), 34 (M) |
| TRANCENDENCE by ECADE | Regional | 64 | 31 (F), 33 (M) |

Deviation Narrative:

The target set (60) was designed to measure project-wide impact across all four participating countries. Regionally, we reached 258 persons. By leveraging broader convenings, we significantly amplified the program’s overall impact and reach. The regional approach proved highly effective in fostering cross-country collaboration and knowledge sharing among a larger and more diverse group, which we believe aligns strongly with the project’s overarching goals of advancing gender equality and empowerment of LGBTIQ+ people.

Indicator: Number of human rights organizations trained and supported

A total of 16 organizations have been supported by the project for the current reporting period. Of these, 100% are LGBTI organizations and four (4) also work on issues related to the human rights of women.  The organizations include:

| Country | Organizations |
| --- | --- |
| Barbados (3) | Equals Barbados Barbados LGBTQ+ Coalition CEED |
| Dominican Republic (7) | ProActividad Comunidad de Trans, Travestis y Trabajadoras Sexuales Dominicanas (COTRAVETD) Trans Este Podemos Avanzar (TEPA) Trans Unidas Dominicanas (TUD) Movimiento LGBTIQ REVASA Family Law Institute |
| Guyana (2) | Guyana Trans United Proud To Be Trans |
| Jamaica (2) | TransWave Equality for All Foundation |
| Regional (2) | Eastern Caribbean Alliance for Diversity and Equality – ECADE Cari-Flags |

Deviation Narrative:

Our target was set at 4, but we successfully trained and supported 16 organizations. This increase reflects our responsive approach to meet high demand and strengthen local capacity beyond initial projections. By engaging additional organizations, we were able to foster a wider network of human rights advocates, enhancing both reach and impact across communities.

## Implementation Challenges

The implementation has faced several challenges across different areas, such as internal processes, relationships with CSOs partners, external factors, and interactions with program participants. These challenges are being actively addressed by the project team, but they have impacted the timeline and overall progress.

Internal Processes: One challenge has been the delayed start of project implementation, primarily due to the lengthy recruitment process needed to recruit the essential project staff. This delay had a ripple effect, influencing several critical aspects of the project:

- Psychosocial Assessments and Program Enrollment: These processes were delayed causing some participants to miss the opportunity to meet registration deadlines for skills training courses.

- Skills and Academic Training: Since the enrollment process was delayed, participants missed out on key registration periods.

- Condensed Timeline for Coordinating Other Trainings: With the project timeline now compressed into four months, coordinating various training sessions has become more challenging. The project must now account for participants' class schedules, psychosocial support sessions, and employment obligations, which makes it difficult to accommodate all necessary training.

Relationship with CSO partners: The relationship with the CSO implementing the project has presented its own set of challenges:

- Workload Concerns: The CSOs has expressed the time they need to devote to the project is greater than initially expected. This may affect staff motivation and capacity to effectively implement the program.

- Reporting Requirements: The CSOs has also raised concerns about the reporting requirements, indicating that they are more extensive than initially expected. BLIC staff has spent significant time working with partners to facilitate the proper reporting.

External Factors and Participant Challenges: The project faces further challenges related to external factors and participants’ circumstances:

- Coordination with Training Institutions: External partners, particularly public institutions providing skills training, have rigid schedules that don’t always align with the project’s timelines. This has created a disconnect between the project’s planning and the availability of training opportunities for participants.

- Participant Schedules: Many participants are juggling multiple responsibilities, including employment, classes, and psychosocial support sessions. Coordinating training that fits into their complex schedules has been a considerable challenge, particularly within the compressed project timeline.

## Gender Equality and Female Empowerment

The project addresses gender equality in the broader sense, challenging the culturally-defined set of economic, social, and political roles, responsibilities, rights, entitlements obligations, associated with being female and male, and the sigma and discrimination that is directed at an individual based on biological sex, intersex status, gender identity (e.g., transgender), or behaviours that are not in line with social expectations of what it means to be a man or woman, boy or girl (e.g., gay men).

## Science, Technology, and Innovation (STIP) Impacts

The project´s social media accounts, blog and the UNDP website are important outlet to communicate project activities and results. This includes:

●      X: https://twitter.com/LGBTICaribbean

  - 1,361 followers (21 more than the previous six-month period).

●      Instagram: https://www.instagram.com/lgbticaribbean/

  - 35 posts in the last 6 months and 1,860 followers (130 new followers in this period)

  - 45.6% of our followers are from the three beneficiary countries of the project, these being Dominican Republic (29.1%), Jamaica (6.6%) Barbados (6.3%), and Guyana (3.6%). 60% of our followers are between 18 and 34 years old; the next age ranges being 35-44 (26.9%) and 45-54 (2.5%)

●      Facebook: https://www.facebook.com/LGBTICaribbean

  - 1385 followers (39 more than in previous 6-month period)

  - 22 posts in the last 6 months

  - BLIC’s Facebook page followers are distributed as follows: Haiti (21.05%), Dominican Republic (13.16%), USA (11.14%), Venezuela (7.54%), Guyana (7.11%), Jamaica (3.43%), Canada (2.89%) and others (33.66%) in that order.

## Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts

Not Applicable

## 2.7 LGBTI Inclusion

## LGBTI inclusion is the focus of the project.

## 2.8 Inclusion of Persons with Disabilities (PwD)

A total of 23 persons with disabilities are enrolled in the program: Barbados (16), Dominican Republic (1), and Guyana (6). No data on this indicator for Jamaica.

# Environmental Compliance

The Project is in compliance with USAID Environmental regulations.

# STAKEHOLDER PARTICIPATION AND INVOLVEMENT

Barbados. The BLIC team engaged with:

- Barbados Workers Union. The team delivered a presentation on Employment (Prevention of Discrimination) Act to members. The Union seems open to receive SOGIE training.

- Open For Business. The team partnered to execute Private Sector Engagement Conference  in November 26th and 27th, 2024.

- Ministry of Labour. An official gave a key informant interview to BLIC researcher conducting the paper on transgender women and gender-diverse people labour access.

- University of the West Indies (UWI) Cavehill Campus. The team partnered with the university to deliver series of sensitization workshops to students in November 2024.

- Barbados Community College. The team partnered with the college to help the institution review internal policies and sensitize students and staff.

- Barbados Institute of Management and Productivity. The team partnered with the Institute to help the institution review internal policies and sensitize students and staff.

- Scotiabank. The bank agreed to deliver financial literacy training to program participants.

- PwC. The team was invited to participate in panel discussion on diversity and human rights.

Dominican Republic. The BLIC team engaged with:

- Ombudsman Office. The team established the integration of partner organizations into the LGBTI thematic working group the Office is planning to launch next year.

- US State Department. The team also supported the coordination of a meeting between partner CSOs and Suzanne Goldberg, Senior Advisor to the Under Secretary for Civil Security, Democracy, and Human Rights. The conversation centered around the police and other armed forces treatment towards LGBTIQ+ people.

- USAID. The team supported the coordination of an LGBTIQ+ access to Labor and Human Rights Roundtable between partner CSOs and USAID Deputy Assistant Administrator Bama Athreya and Special Representative for International Labor Affairs Kelly Fay Rodriguez. The team also presented the LGBTI “Amor, Lucha e Inclusión” Mural located at the Museo de la Resistencia to USAID Administrator, Samantha Power.

- Spanish Agency for International Development Cooperation (AECID). The team presented the project to the Spanish Ambassador and representatives from Spanish Cooperation.

Guyana. The BLIC team engaged with:

- Carnegie School of Home Economics. Guyana’s only culinary school. The team, along with GTU, was able to establish a relationship with the school’s vice principle and the institution is willing to enroll program participants.

- Guyana Women’s Leadership Institute. A request for a meeting was made to discuss with the institute opportunities for program participants to enroll in upcoming and future skills training. The team has not received a reply yet.

- SASOD. The team attended the Book Launch “Defiant Bodies: Making Queer Community in the Anglophone Caribbean”. In attending this activity, the project was able to network with Parliamentarians, shared details of the BLIC Project. These Parliamentarians will be engaged as we disseminate the findings from the Project’s research studies.

- Global Environment Facility Small Grants Programme (GEF-SGP). The team connected GTU to this grant funding opportunity for the organization’s agri-processing ventures.

Jamaica. The BLIC team engaged with:

- HEART/ NSTA Trust. The institute agreed to enroll program participants. To that end, the team is supporting TransWave in completing the draft Partnership Agreement (P.A).

# MANAGEMENT AND ADMINISTRATIVE ISSUES

Staff contract modality. In the case of Guyana, our country coordinator is an independent contractor. This type of contract, under UNDP regulation, limits her access to internal platforms which forces her to rely on the country office for administrative support, occasionally causing delays.

Procurement team limited bandwidth. Procurement teams at country offices are under immense pressure causing internal procedure timing delays. During the reporting period, the BLIC Team has relied on the Regional Hub team for procurement and payments.

# Budget

# LESSONS LEARNED

- It is crucial to expedite personnel contracting. Conduct pre-bid meetings for any future consultancies, particularly for areas where consultancies are not common like Social Work to ensure interested consultants are clear on how to submit applications that properly respond to the Terms of Reference to avoid having to re-advertise.

- Participant preparation is essential. Implementing an orientation at the start of the program would foster a better understanding of the program and its expectations among participants, enhancing their commitment and experience.

- Geographical considerations are important in planning services. Decentralizing staff would reduce travel burdens for rural participants and create more equitable access to services.

# PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS

REGIONAL

- The BLIC Team Annual Coordination meeting is scheduled to be held in Barbados from 25-26 November 2024.

- The Open for Business-UNDP Private Sector Engagement Conference is scheduled to be held in Barbados from 27-28 November 2024.

BARBADOS

- A Queer Arts Festival funded by UNDP BLIC and executed by Equals is scheduled for 2 November 2024.

- A Transgender Wellness Fair and Candlelight Vigil funded by UNDP BLIC and executed by Equals is scheduled for 24 November 2024.

- The sensitization of the three educational institutions identified in Barbados (UWI, BIMAP and BCC) and review of their internal policies is scheduled for next quarter.

- The preparation for the workforce, financial literacy and entrepreneurship workshops for participants are scheduled to be held in the next quarter.

- Conclude the enrollment of participants in training and academic institutions

- Transfer seed funding fund to selected participants

DOMINICAN REPUBLIC

- Completion of campaign around the inclusion of transgender and gender diverse persons and allyship.

- Conclude the enrollment of participants in training and academic institutions

- Transfer seed funding fund to selected participants

- Support the transgender day of remembrance activities.

GUYANA

- Provide workforce Development Training

- Provide SOGIE Sensitivity Training

- Conclude the enrollment of participants in training and academic institutions

- Transfer seed funding fund to participants selected

- Support the transgender day of remembrance activities.

JAMAICA

- Completion of social media campaign around the inclusion of transgender and gender diverse persons in the workforce.

- Conclude the enrollment of participants in training and academic institutions

- Transfer seed funding fund to selected participants

- Research conducted and document developed on the history of the trans movement in Jamaica.

- Support the transgender day of remembrance activities.

# How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report

Not Applicable