BEING LGBTI IN THE CARIBBEAN (BLIC) Annual Report 15 -10 -2021 to 15-04-2022 Submission Date: 24 June 2022. [Contract/Agreement] Number: AID-517-IO-17-00001 Activity Start Date and End Date: September 22, 2018, to February 28, 2023 [COR/AOR] Name: Luis Duran Submitted by Karin Santi, Chief of Party United Nations Development Programme City of Knowledge, Building 128, Panama City, Panama Tel: +507 302 4610 Email: karin.santi@undp.org This document was produced for review by the United States Agency for International Development in the Dominican Republic (USAID/DR).

# Program Overview/Summary

| Program Name: | Being LGBTI in the Caribbean (BLIC) |
| --- | --- |
| Activity Start Date and End Date: | September 22, 2017, to February 28, 2023 |
| Name of Prime Implementing Partner: | United Nations Development Programme |
| [Contract/Agreement] Number: | AID-517-IO-17-00001 |
| Name of Subcontractors/Sub-awardees: | Barbados and Eastern Caribbean Butterfly Barbados and Equals. Dominican Republic: Centro de Estudios Biopsicosociales LGBT (CEB-LGBT); Comunidad de Lesbianas Inclusivas Dominicanas (COLESDOM); Comunidad de Trans-Trasvesti Trabajadoras sexuales Dominicanas (COTRAVETD); Diversidad Dominicana; Red de Voluntarios Amigos Siempre Amigos (REVASA); Trans Amigas Siempre Amigas (TRANSSA); and Trans Este Podemos Avanzar (TEPA) Universidad Autónoma de Santo Domingo (UASD). Haiti: Association Nationale de Protection des Femmes en Enfants Haïtiens (ANAPFEH); Association Pour la Réduction de La Vulnérabilité en Haïti (AREV-Haïti); Ayibopost Collectif Haïtien d'Aide et Appui à l'Émancipation Sociale (CHAAPES); Héritage pour la Protection des Droits Humains; Kouraj Pou Pwoteje Dwa Moun; Organisation des Citoyens pour une Nouvelle Haïti (OCNH); and Institut Panos ci-devant Institut Panos Caraïbes. Jamaica Jamaica AIDS Support for Life (JASL), J-FLAG; TransWave, and WeChange Regional Caribbean Forum for Liberation and Acceptance of Genders and Sexualities (CariFLAGS) |
| Major Counterpart Organizations: | Not Applicable |
| Geographic Coverage (cities and or countries): | Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica and St Lucia |
| Reporting Period: | 1 April 2021 – 15th October 2021 |

Contents

1.	Program Overview/Summary	0

1.1	Program Description/Introduction	1

2.	ACTIVITY IMPLEMENTATION PROGRESS	2

2.1	Progress Narrative	2

2.2	Implementation Status	3

2.3	Implementation Challenges	6

3.	INTEGRATION OF CROSSCUTTING ISSUES and USAID FORWARD PRIORITIES	6

3.1	Gender Equality and Female Empowerment	6

3.2	Science, Technology, and Innovation (STIP) Impacts	6

3.3	Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts	7

3.4	LGBTI Inclusion	7

3.5	Inclusion of Persons with Disabilities (PwD)	7

4.	Environmental Compliance	7

5.	STAKEHOLDER PARTICIPATION AND INVOLVEMENT	7

6.	MANAGEMENT AND ADMINISTRATIVE ISSUES	7

7.	Budget	8

8.	LESSONS LEARNED	8

9.	PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS	8

10.	How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report	10

## Program Description/Introduction

Being LGBTI in the Caribbean (BLIC) is a regional programme that aims to enhance knowledge, partnerships, and capacities of LGBTI communities, civil society and States to reduce human rights violations and negative attitudes towards LGBTI people in the Caribbean, with country level focus in Barbados, Dominican Republic, Haiti and Jamaica, as well as regional activities.  To achieve its goals, it is crucial that the project responds to the experiences and needs of the LGBTI community in the Caribbean.

While numerous reviews of the situation LGBTI people vis-à-vis laws, policies and practices have been carried out in the Caribbean, currently very little systemic data reflects the issues and circumstances of LGBTI people in the region. Governments often lack data and evidence needed to shape policies and programs for LGBTI inclusion. Many civil society organisations still need to develop solid coordination mechanisms among themselves, in order to increase their impact, to be recognised as full partners at national level and to develop joint strategies for advocacy and lobbying. Up to date data would enable analysis on the level of LGBTI rights and inclusion. Such analysis would enable the development of laws, policies, as well as advocacy programmes that are more effective in instigating social, legal and political changes, partnerships and opportunities.

The proposed project has the following mutually reinforcing objectives:

1.	To strengthen data/evidence base on the rights of LGBTI people and enhance the capacity of governments, civil society and LGBTI groups to address and reduce inequality, exclusion, violence and discrimination experienced by LGBTI persons in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica and St Lucia.

2.	To increase awareness of homophobic and transphobic violence and discrimination and strengthen the capacity of civil society organizations to challenge negative attitudes towards LGBTI people including through engaging government officials, parliamentarians, political parties, trade unions, religious leaders, civil society, media, and the general population in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, St Lucia and regionally.

The programme is a collaboration between governments, civil society, regional institutions, and other stakeholders to advance the social inclusion of lesbian, gay, bisexual, transgender, and intersex people. The programme is supported by the U.S. Agency for International Development (USAID).

This report covers the six months of project implementation (October 2020 - March 2021) providing an overview of activities conducted and provide an overview of upcoming initiatives.

# ACTIVITY IMPLEMENTATION PROGRESS

## Progress Narrative

Capacity building of human rights defenders remains an important priority for the BLIC project.  During this reporting period, about 105 human rights defenders have benefitted from the capacity building sessions implemented through the BLIC project.   In the Dominican Republic between November 2021 and March 2022 training  sessions engaged young people at two universities, Universidad Iberoamericana and the Pontificia Universidad Católica Madre y Maestra.   The training session focused on regional human rights systems, LGBTI inclusion and the importance of protection based on sexual orientation and gender identity.   Engaging university students, although not a traditional partner of the project, are critical since young people know what is happening on their campuses and in their communities and are uniquely positioned to incorporate rights based approaches and can be instrumental in addressing intersectional approaches to violence and discrimination.

Ensuring safe spaces to help vulnerable groups such as trans people is essential within Haiti's development context. With the support of the BLIC project and in partnership with the Joint United Nations Programme on HIV/AIDS (UNAIDS), the organization Community Action for the Integration of Vulnerable Haitians (ACIFVH) was able to establish Kay Trans Ayiti (the Creole name for Trans House Haiti). Kay Trans Ayiti is a space where transgender people can come to seek assistance and where shelter, food and psychological support is offered.   Post the 2021 earthquake support was also provided to Partnership for Vulnerability Reduction in Haiti (AREV-Haiti0 and ACIFVH to assist beneficiaries in the Southern Region, the most affected region of the country.   Through the Hotline for Suicide and HIV Prevention project, staff discovered that several trans people had been denied medical treatment in hospitals in the city of Les Cayes because of their gender identity.  To date, the two associations have accompanied more than 700 people and raised awareness on HIV prevention, more than 400 people have been able to find financial support and the leadership of trans women has been strengthened through the creation of temporary jobs.

Across the Caribbean,  LGBTI persons reported that the COVID-19 pandemic negatively impacted their mental health.  In Jamaica, the BLIC project supported J-FLAG to partner with the Department of Psychology and Social Work at the University of the West Indies (UWI) Mona to integrate LGBTI sensitive material into select undergraduate and graduate courses (BSc. Psychology, MSc. Applied Psychology and MSc. Clinical Psychology degrees). The objective is for the next generation of mental health practitioners to be equipped to deliver adequate care to LGBTI persons. Course material will be developed including a course description, rationale, course aims, course learning outcomes, course content/syllabus, quizzes, test material, and suggested readings/learning resources. The materials developed will be submitted to UWI for approval before the start of the school year in September 2022.

The project continues to have a strong social media presence.  To date, the project has an important outlet through its Twitter, Instagram and Facebook accounts that help share information related to project activities but also increase the impact of actions implemented by local partner CSOs.  Further information on the project´s social media presence is detailed below.

## Implementation Status

Output 1: Knowledge, strategic information and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated	
Indicator: Number of research papers on LGBTI produced.

- For the reporting period, no knowledge products have been produced.  However, the Being LGBTI reports are undergoing the recently implemented Quality Assurance Protocol implemented within UNDP.

Output 2: Support Meaningful engagement through national and regional policy dialogues 
Indicator: Number of public forums in which national governments and LGBTI civil society interact.

  - Dominican Republic:   Provision of services is a key component in the implementation of public policies.  Taking this into consideration, the project implemented initiatives targeted at key government institutions that provide services to LGBTI persons. These five (5) forums were co-convened and organized with the Ministry of Women (2 forums), SUPERATE, the Office of the Social Subsidies Administrator, and the Ministry of Industry, Commerce and MSMEs.  All the forums included the participation of local LGBTI CSOs.  LGBTI persons were able to speak of their needs and expectations and engaged in productive dialogue.  Project staff also delivered training on basic concepts on human rights of LGBTI persons and the State´s obligations to ensure the enjoyment of all human rights by all persons. It is expected that through this initiative, the provision of services within priority public policies will improve for LGBTI beneficiaries.

  - In the case of SUPERATE, an intersectional approach was taken, and training included issues on human rights and HIV and inclusion of persons with disabilities.  A total of thirty (30) staff members from the organization received a certificate on human rights and inclusion as part of the Training Program on Inclusion and Human Rights in Public Administration.

Output 3: Capacity of LGBTI Community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge and concrete actions to address stigma and discrimination.

Indicator: Number of human rights defenders trained and supported

A total of 105 human rights defenders were trained and supported by the BLIC project.  Of these defenders 72% were young persons (29 years old or less), and 84% were female.

·         Training of human rights defenders for the reporting period was focalized in the Dominican Republic, through a conscientious effort to reach young university students, for the details provided in previous sections.

·         In this regard, a total of 35 students of the Universidad Iberoamericana were educated about LGBTI inclusion and human rights; 25 students of the Pontificia Universidad Católica Madre y Maestra were educated about LGBTI inclusion and human rights.

·         Likewise, 45 clinical psychology professionals were trained as part of the first university course on Human rights, Gender and Affirmative Therapies for LGBT+ people. This activity was carried out in coordination with the Office of Gender Equity and Development and the Mental Health Directorate of the Ministry of Public Health, and the Pan-American Health Organization (PAHO).

The Director of ASA highlighted how initiatives like this go beyond the intended outcomes, turning participants into advocates for change:

“I think that the greatest achievement is being able to have all that amount of knowledge that increases the questioning to continue investigating, but that we can apply it, not only in the consultation (…) but also in daily life.”

Indicator: Number of human rights organizations trained and supported.

- In the Dominican Republic, two (2) human rights organizations were trained and supported.

The Being LGBTI project technically supported Diversidad Dominicana in the elaboration of a proposal to establish an LGBTI committee in the Office of the Ombudsman to follow-up on complaints of human rights violations and public policies.   This initiative originates in the fact that, based on previous negative engagements with government institutions, LGBTI persons may be reluctant to present formal complaints, resulting in impunity and lack of truthful statistical records of human rights violations against LGBTI persons.  The initiative intends for the Committee to present the cases, on behalf of the complainants, and provide close follow-up.

Similarly, Amigos siempre Amigos (ASA) was a partner on the first university course on Human rights, Gender and Affirmative Therapies for LGBTI people.  This activity was carried out in coordination with the Office of Gender Equity and Development and the Mental Health Directorate of the Ministry of Public Health, the LGBTI CSO Amigos Siempre Amigos and the Pan-American Health Organization (PAHO).

In the Dominican Republic, the discrimination and violence experienced by LGBTI people seriously affects their mental health.  According to the results of the 2020 National LGBTI Survey, 57.9% said they had been depressed, while another 32.7% considered suicide and 17.8% of actually tried to take their own lives.  Similarly, the 2020 report of the Independent Expert on protection against violence and discrimination based on sexual orientation or gender identity, which recommends that States establish and facilitate health and other services related to exploration, the free development or affirmation of sexual orientation and gender identity.  The initiative also speaks to one of the recommendations sue identified during the first National LGBTI Dialogue carried out by the project in 2019: “Train and raise awareness about LGBTI issues among health professionals, with the purpose of combating discrimination and prejudice”.

As WHO´s Regional Senior Advisor on Mental Health and the use of substance for the America´s indicated during the closing ceremony, “… raising awareness at all levels, academic institutions, the media, professional associations, the population in general is a large part of this awareness work (...) the fact that it is not a subject that is talk is a big part of the problem”.

Tackling this issue, the initiative resulted in 40 psychology professionals receiving tools and resources to provide gender reaffirming mental health services, with a gender perspective.  With this initiative, the project aimed to further promote the well-being and health of LGBTI persons in the country, while also developing local capacities.

The Director of ASA highlighted how initiatives like this go beyond the intended outcomes, turning participants into advocates for change:

“I think that the greatest achievement is being able to have all that amount of knowledge that increases the questioning to continue investigating, but that we can apply it, not only in the consultation (…) but also in daily life.”

Indicator: Number of Civil Society Organizations (CSOs) receiving USG assistance engaged in advocacy interventions

- Dominican Republic – two (2 )Dominican Human Rights organizations were supported for advocacy activities that focus on visibility.

  - The project supported the BOCANADA Magazine published by REVASA. Bocanada is a comprehensive physical and virtual space that provides front-line information to the GLBTIQ community, including articles on the main issues that affect the community. The first edition of Bocanada magazine included an infographic with the results of the 2020 National LGBTI Survey, making the results of the study known to the wider LGBTI public.

  - REVASA and ASA were supported in the organization of the LGBTI Outfest Film Festival. This cultural and educational activity associates the seventh art with the promotion of Human Rights. The Outfest, was celebrated from December 9 to 12, 2021. A total of forty-one thousand five hundred and fifteen (41,515) people participated and were reached in the broadcast gala.

## Implementation Challenges

The continued imitations of in=person activities due to COVID-19 pandemic may impact on the learning objectives of the participants in educational activities that are being implemented online. People with limit connection to internet have less opportunities to engage in the project activities that are held online.

## Gender Equality and Female Empowerment

The project addresses gender equality in the broader sense, challenging the culturally-defined set of economic, social, and political roles, responsibilities, rights, entitlements obligations, associated with being female and male, and the sigma and discrimination that is directed at an individual based on biological sex, intersex status, gender identity (e.g., transgender), or behaviours that are not in line with social expectations of what it means to be a man or woman, boy or girl (e.g., gay men).

## Science, Technology, and Innovation (STIP) Impacts

The projects social media accounts, blog and the UNDP website has regularly been updated to share project results. This includes:

During the reporting period the Communications Consultant has been updating BLIC social media accounts, blog and the UNDP website to share project results. This includes:

- Twitter: https://twitter.com/LGBTICaribbean

  - 2,134 tweets published (183 tweets were published in the last 6 months) and 1,138 followers in total.

  - In the last 6 months, our tweets earned 70,269 (70K) impressions (that are the number of times users saw the tweet on twitter).

    - Our top tweet was our condolence message for Brandy Rodriguez, a leading voice for the trans community and the advancement of LGBTI rights in Trinidad and Tobago, on October 28th. This message reached more than 4.500 people. In December, another one of our top tweets earned 3,5K impressions and a total of 118 engagements. This tweet shared news on the trans affirmation fight of Jamaican activists.

  - In this period our profile received 16,245 visits (2 thousand more visits than the total number of visits received during the past six months), being November the month with more visits (up to 3K), coinciding with the Intersex Report launch event;

  - 124 new mentions in the last six months;

  - and 75 new followers in this same period.

- Instagram: https://www.instagram.com/lgbticaribbean/

  - In the last 6 months numbers have increased to 333 posts and 1,416 followers. This means 48 new posts and 86 new followers in this period.

  - During this period, a total number of 3,094 accounts have been reached, among which 460 accounts engaged.

  - 160 new stories were featured.

  - 4 new videos were uploaded - with a total of 292 views.

  - 47% of our followers are from 4 beneficiary countries of the project, these being Dominican Republic (31%), Jamaica (7%), Barbados (5%) and Haiti (4%).

  - 50% of our followers are among 25-34 years old; the next age ranges being 35-44 (22%) and 18-24 (19%)

- Facebook: https://www.facebook.com/LGBTICaribbean

  - Numbers have raised to  1,304 followers and  1,148 likes

  - During the past six months, 135 new posts have been posted on BLIC’s Facebook page, reaching 3,209 (3K) people, 82 engagements (reactions, likes, comments or shares) and 61 post clicks.

  - 4 new videos have been uploaded on our facebook site: https://www.facebook.com/LGBTICaribbean/videos.

  - The post with highest performance in the past six months has been the “Save the date” for the Intersex Report launching event (November): 262 people reached, 15 enaggements and 10 reactions, comments and shares, to date.

  - The majority of our Facebook page followers’ are from Haiti, Dominican Republic, USA, Guyana, Venezuela and Jamaica, in that order.

- Medium blog: https://medium.com/being-lgbti-in-the-caribbean

  - 6 new articles were published in the last 6 months.

  - 793 new views in the last 6 months; which is the highest number of visits our Medium blog has had since its creation. In the previous six months period (April-September 2021) the blog articles received a total number of 43 visits.

- In particular, our top article (the article with more visits) has been the announcement of the LGBTI Gender, Rights and Affirmative Therapy Training Course that took place in the Dominican Republic between February and March 2021.

- Another popular article has been the Call for the Small Grants proposals, shared on the blog on March 18th, which has had a total number of 85 views and growing.

- YouTube channel (https://www.youtube.com/channel/UCNKnXbskgTJwDd1ntQP6Jww)

- The channel now features a total of 68 subscribers, 64 videos, with 3.880 views (only on Youtube, most of our videos are promoted on Facebook though).

- A specific campaign was prepared for the Intersex Report Launch Event during the month of November 2021.

- In Twitter, the campaign consisted of 10 posts, including infographic cards sharing information and testimonies of the Intersex Report. These posts reached a total of 10,390 (10K) impressions and 300 engagement (total number of times a user has interacted with the tweet).

November’s top tweet, which earned 2,297 impressions, included an infographic card sharing one of the testimonies of the Intersex Report. The tweet had a total of 62 engagements. The Top Media Tweet was the “Save the date” of the Intersex Report launching event, which earned 1,661 impressions and 63 engagements.

The event was also broadcast via live-tweeting through @lgbticaribbean Twitter profile on November 23rd, in both English and Spanish.

- In Facebook, the campaign consisted of 9 posts in 3 languages (English, Spanish and French), a “Save the date” and infographic cards, which reached 452 people, 15 engagement and 6 post clicks. The pPost with highest performance in the past six months has been the “Save the date” for the Intersex Report launching event.

- In Instagram, 7 posts were uploaded in 3 languages (English, Spanish and French), including the “Save the date” and 5 infographic cards. These posts had 81 likes. Also, 12 Instagram stories were uploaded to promote the event and share testimonies.

- The #LGBTINews and #LGBTIStories series have been featured in both Twitter and Facebook, sharing LGBTI related news and inspiring stories from the region or globally.

- A specific publication in “Diario Libre” from the Dominican Republic addressed the results of the National LGBTI Survey.

## Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts

## No Activities during this reporting period.

## 2.7 LGBTI Inclusion

## LGBTI inclusion is the focus of the project.

## 2.8 Inclusion of Persons with Disabilities (PwD)

Where possible the project includes sign language interpretation or subtitles.

# Environmental Compliance

The Project is in compliance with USAID Environmental regulations.

# STAKEHOLDER PARTICIPATION AND INVOLVEMENT

The BLIC project works with a range of partners.  Government partners include Ombudsperson Offices, Ministries of Health, Education, Gender and Labour. Civil society partners include both national and regional organizations.  In addition, UN Agencies have also partnered with the project on distinct activities.

# MANAGEMENT AND ADMINISTRATIVE ISSUES

The project has seen a shift in staffing, staff are currently being recruited for both the Barbados and Haiti Country Offices.

# Budget

# LESSONS LEARNED

- In the Dominican Republic due to the good relationships and the visibility of the project, more state institutions and private sector companies are asking to receive training and develop policies for the inclusion of LGBTI people.

- While Haiti has known political unrest and natural catastrophes, the impact of the August 2021 earthquake in the Southern part of Haiti deserves special consideration on Psychosocial support; socioeconomic support services; human rights and protection advocacy. This emergency is compounding existing deep vulnerabilities for LGBTQI Haitian, given the ongoing COVID-19 pandemic, volatile security/political situation including gang violence which has led to displacement, and a history of recurring disasters from which many communities have not fully recovered

# PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS

Barbados

- Support the Launch of the National LGBTI survey

- Support the implementation of the LGBTI Social Innovation Lab

- Provide technical support to Butterfly Barbados and Equals on implementation of small grants

Dominican Republic

The activities to be implemented by the Dominican Republic in the next quarter are:

- Training on LGBTI human rights for public servants of the social protection program Superate, the Ministry of Women and other institutions that could ask for support.

- Support and activity from the CSO RD es de Todes for the commemoration of the International Day Against Homophobia, Biphobia and Transphobia.

- Delivery to the judiciary of the of instructional brochures for justice personnel and users of the justice system on access to justice for LGBTI people, migrants and people with disabilities. With the support of the International Organization for Migration.

- Dissemination of an infographic with the main findings and recommendations of the National LGBTI Survey 2020.

- Support the activities implemented by LGBTI CSOs for the commemoration of the pride month.

- Launch of the Being LGBTI in the Dominican Republic Report.

- Implementation of the LGBTI+ Social Innovation Lab.

Haiti

- Finalise recruitment  of the BLIC Coordination position

- Follow up with Heritage and AREV-Haiti on implementation of small grants.

- Launch LGBTI National Survey

- Two-day workshop for managers of public institutions (Ministries) on non-discrimination, Human Rights and their link with sexual orientation and gender identity (SOGI) (West - South / Cayes - Grand Anse / Departments Jérémie and Center)

Jamaica

- Support the launch of the LGBTI National SUrvey

- Completion of Sexual & Reproductive Health sessions with LBQ Women

- Support Identification of good practices in LGBTI Inclusion in the private sector

- Support for LGBTI CSOs to engage in advocacy around the National Anti-Discrimination Advocacy

COMMUNICATIONS:

- Communication activities during the quarter will include the regular update of all social media platforms (including giving specific visibility to national and regional BLIC activities)

- Most of our communications efforts will now focus on providing specific support to two future virtual events: the Private sector LGBTI inclusion best practices Regional Forum (June 2022, tentative date) and in the lead-up to the Second national LGBTI Dialogue in Dominican Republic. Coordination meetings will be held with the technical support group prior to the events, as well as with different CSOs from the region.

- Support to the events will include providing audiovisual material, producing a social media kit, a set of key messages and other communications materials in advance, as well as live tweeting during the event. Later on, a special newsletter and a blog article will be produced on both events, as well as other social media content, to summarize the main conclusions and recommendations reached. Prior connections with the media will be made.

- A specific blog will be created for IDAHOT 2022 (May 17th), according to this year’s theme “Our bodies, our lives, our rights”

- The communications consultant will also provide assistance to the CSOs awarded the Small Grants through different meetings and/or communications training.

- Communications support will be given to national LGBTI surveys in Barbados, Haiti and Jamaica, replicating the support given to the National LGBTI Survey in Dominican Republic.

# How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report

Not Applicable

Information retrieved on September the 23rd, 2021.

Information retrieved until March 31st 2022.

Accounts reached: number of accounts that have seen our content at least once.

Accounts engaged: number of accounts that have interacted with our content.

Likes are public while followers are not, which may explain the difference between numbers in our case.