BEING LGBTI IN THE CARIBBEAN (BLIC) Bi-Annual Report Submission Date: November 14th, 2022 [Contract/Agreement] Number: AID-517-IO-17-00001 Activity Start Date and End Date: September 22, 2018, to February 28, 2023 [COR/AOR] Name: Luis Duran Submitted by Karin Santi, Chief of Party United Nations Development Programme City of Knowledge, Building 128, Panama City, Panama Tel: +507 302 4610 Email: karin.santi@undp.org This document was produced for review by the United States Agency for International Development in the Dominican Republic (USAID/DR). -04 -2021 to 30-09-2022

# Program Overview/Summary

| Program Name: | Being LGBTI in the Caribbean (BLIC) |
| --- | --- |
| Activity Start Date and End Date: | September 22, 2017, to February 28, 2023 |
| Name of Prime Implementing Partner: | United Nations Development Programme |
| [Contract/Agreement] Number: | AID-517-IO-17-00001 |
| Name of Subcontractors/Sub-awardees: | Barbados and Eastern Caribbean Butterfly Barbados Equals. Dominican Republic: Cámara de Comercio LGBTI Trans Este Podemos Avanzar (TEPA) RD es de Todes Jamaica Equality for All Jamaica AIDS for Life Regional UNIBAM |
| Major Counterpart Organizations: | Not Applicable |
| Geographic Coverage (cities and or countries): | Barbados, Dominican Republic, Haiti, and Jamaica |
| Reporting Period: | April 1st, to September 30th, 2022. |

Contents

1.	Program Overview/Summary	0

1.1	Program Description/Introduction	2

2.	ACTIVITY IMPLEMENTATION PROGRESS	2

2.1	Progress Narrative	2

2.2	Implementation Status	4

2.3	Implementation Challenges	7

2.4	Gender Equality and Female Empowerment	7

2.5	Science, Technology, and Innovation (STIP) Impacts	7

2.6	Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts	10

2.7 LGBTI Inclusion	10

LGBTI inclusion is the focus of the project.	10

2.8 Inclusion of Persons with Disabilities (PwD)	10

3.	Environmental Compliance	10

4.	STAKEHOLDER PARTICIPATION AND INVOLVEMENT	11

5.	MANAGEMENT AND ADMINISTRATIVE ISSUES	11

6.	Budget	11

7.	LESSONS LEARNED	12

8.	PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS	12

9.	How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report	13

## Program Description/Introduction

Being LGBTI in the Caribbean (BLIC) is a regional programme that aims to enhance knowledge, partnerships, and capacities of LGBTI communities, civil society, and States to reduce human rights violations and negative attitudes towards LGBTI people in the Caribbean, with country level focus in Barbados, Dominican Republic, Haiti, and Jamaica, as well as regional activities.  To achieve its goals, it is crucial that the project responds to the experiences and needs of the LGBTI community in the Caribbean.

While numerous reviews of the situation LGBTI people vis-à-vis laws, policies and practices have been carried out in the Caribbean, currently very little systemic data reflects the issues and circumstances of LGBTI people in the region. Governments often lack data and evidence needed to shape policies and programs for LGBTI inclusion. Many civil society organisations still need to develop solid coordination mechanisms among themselves, to increase their impact, to be recognised as full partners at national level and to develop joint strategies for advocacy and lobbying. Up to date data would enable analysis on the level of LGBTI rights and inclusion. Such analysis would enable the development of laws, policies, as well as advocacy programmes that are more effective in instigating social, legal, and political changes, partnerships, and opportunities.

The proposed project has the following mutually reinforcing objectives:

1.	To strengthen data/evidence base on the rights of LGBTI people and enhance the capacity of governments, civil society and LGBTI groups to address and reduce inequality, exclusion, violence, and discrimination experienced by LGBTI persons in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, and St Lucia.

2.	To increase awareness of homophobic and transphobic violence and discrimination and strengthen the capacity of civil society organizations to challenge negative attitudes towards LGBTI people including through engaging government officials, parliamentarians, political parties, trade unions, religious leaders, civil society, media, and the general population in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, St Lucia and regionally.

The programme is a collaboration between governments, civil society, regional institutions, and other stakeholders to advance the social inclusion of lesbian, gay, bisexual, transgender, and intersex people. The programme is supported by the U.S. Agency for International Development (USAID).

This report covers the six months of project implementation (April 2022 to October 2022) providing an overview of activities conducted and provide an overview of upcoming initiatives.

# ACTIVITY IMPLEMENTATION PROGRESS

## Progress Narrative

For the reporting period, a total of eighteen (18) human rights organizations have been trained and supported under the Being LGBTI in the Caribbean project. 15 of these organizations are based in the Dominican Republic and 3 in Barbados and the Eastern Caribbean. All are LGBTI organizations and more than 60% are engaged in women´s issues.  Five (5) organizations received support to engage in advocacy interventions through the small grants programme,

Eighty-five (85) human rights defenders benefitted from capacity building sessions with a focus on media sensitization, history of the LGBTI movement, how to register organizations, amongst others.   Of the 85 human rights defenders trained, 87% are women, and 63% self-identified as LGBTI persons and at least 34% are young people.

One of the main activities currently being implemented under the BLIC initiative is the roll-out of the LGBTI surveys for Barbados and Jamaica.

In this regard, in Barbados, the University of the West Indies (UWI), SALISES Department (Sir Arthur Lewis Institute of Social and Economic Studies) Cave Hill, Barbados was recruited to conduct the National LGBTI Survey with advisory support from the LGBTI Advisory Committee. The participation of representatives of the LGBTI community in all stages of the project are guaranteed through this committee.

The survey instrument was finalised by the advisory committee and is in the process of approval from the UWI Ethics Committee to ensure adherence to safety and ethical protocols. Given that the survey asks questions that may cause discomfort, for example questions on experiences of violence, a list of resources to access psycho-social support has been included in the survey. Likewise, in Jamaica, the survey instrument was presented to the Advisory Committee.  At writing, the survey has been launched and is progressing in accordance to established workplan.

At the regional level with support from the BLIC project the Caribbean Regional Dialogue on LGBTQI+ D.A.T.A convened in Barbados, brought together over 100 delegates from regional and international civil society organisations, government, private sector, and donors.   Driven by a surge of LGBTQI research throughout the Caribbean, the Dialogue was organized into a series of roundtables covering 12 themes (e.g., labour, poverty, education, de-colonialisation, migration and brain drain, and more). The Dialogue provided an opportunity for participants to discuss viable solutions for LGBTQI+ inclusion, safety, health, and – especially trying to articulate economic inclusion and livelihoods in the Caribbean and developed policy options for 4 sectors (public sector, private sector, economic development, and legal sector).

Other activities implemented during the reporting period include a training on LGBTI human rights for students of the Instituto Tecnológico de Santo Domingo (INTEC), with the participation of fourteen (14) persons. The participants learned about the basic concepts related to sexual orientation and gender identity, the human rights situation of LGBTI persons, and how they can work to promote and protect the human rights of LGBTI people.  In addition, a training workshop on Masculinities and LGBTI human rights, was organised with the APEC University with the participation of ten (10) persons. The training was conducted within the framework of a masculinities diploma course implemented by the Ministry of Women, the APEC University, Friedrich Ebert Foundation, and UNDP.

## Implementation Status

Output 1: Knowledge, strategic information, and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated

Indicator: Number of research papers on LGBTI produced.

In the Dominican Republic, the Being LGBTI in the Caribbean: Dominican Republic report was published, providing evidence on the human rights situation as well as on socio-economic inclusion of LGBTI people in the Dominican Republic.

The report has a qualitative approach based on interviews with more than 100 LGBTI people, state officials, and specialists.  The report shows that LGBTI people in the Dominican Republic continue to face enormous vulnerability in the face of violence and discrimination; continue to be excluded from the exercise of basic rights and lack recognition and legal protection of their identities.  Recognition and legal protection of their families is also non-existent.

The research shows that as of early 2000, in the Dominican Republic there is a gradual increase in the number of actions and clauses within government institutions to promote inclusion and confront discrimination. This positive change at normative and institutional levels respond to political, economic, cultural, and sociodemographic changes in Dominican society. At the same time, organized LGBTI civil society has grown exponentially in recent years and is currently comprised of very diverse organizations with a presence in different provinces.

In addition, the report shows the experiences of LGBTI people through stories that describe the violence to which they are exposed in both private and public spaces; the difficulties they face in accessing housing, and discrimination, harassment and bullying in the educational environment.

The report launch event took place at the Dominican Resistance Memorial Museum, with the participation of representatives from USAID, UNDP, the Dominican State, civil society, embassies, and international cooperation agencies.

Output 2: Support Meaningful engagement through national and regional policy dialogues

Indicator: Number of public forums in which national governments and LGBTI civil society interact.

A total of 6 forums were convened and organized to promote public policies in dialogues between state institutions and LGBTI CSO’s in the Dominican Republic.

Provision of services is a key component in the implementation of public policies.  Taking this into consideration, the project implemented initiatives targeted at key government institutions that provide services to LGBTI persons. Four (4) forums were co-convened and organized with the Ministry of Women, INDOTEL, SUPERATE, and School of Public Prosecutions.  All the forums included the participation of local LGBTI CSOs (RD es de Todes, COLESDOM, TRANSSA and Voluntariado GLBT).  LGBTI persons were able to speak of their needs and expectations and engaged in productive dialogue.  Project staff also delivered training on basic concepts pertinent to human rights of LGBTI persons and the State´s obligations to ensure the enjoyment of all rights by all persons. It is expected that this initiative will improve the provision of services within priority public institutions for LGBTI beneficiaries.

In the case of INDOTEL (press note) and SUPERATE (video/press note) an intersectional approach was taken, and training included issues on human rights and HIV and inclusion of persons with disabilities.  RD es de Todes participated in these forums.

In addition, two (2) public forums were held to launch knowledge products. 1) TRANSSA launched a manual and a booklet on security and justice for LGBTI people with the participation of 10 people, and two representatives of the justice sector: (the Attorney General Office and the National Defence Office). 2)The launch of the report "Being LGBTI in the Caribbean Dominican Republic" with the participation of the Minister of Economy, Planification and, Development, and the Vice-minister of Innovation, as well as CSO representatives attended. Press notes

Output 3: Capacity of LGBTI Community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge, and concrete actions to address stigma and discrimination.

Indicator: Number of CSOs trained and supported

In Barbados, the Media Workshop: Reporting and Communicating on LGBTI Issues was supported with the intent to strengthen the inclusion and social acceptance of LGBTI persons, to enable news reporters to correctly represent LGBTI people in their reporting and to educate and sensitize news reporters on covering stories of LGBTI people without prejudice, misrepresentation and contempt for gender identity and sexual orientation.

The agenda included 5 sessions subdivided in 12 activities: including on, reporting on, and working with the LGBTI community, example, and experience of media activity, using appropriate LGBTI terminology and concepts, and identifying and combatting anti-LGBTI Stereotypes and prejudices in media content.

A total of 10 organisations engaged in this activity including. Barbados Community College, University of the West Indies Cave Hill Campus, Equals, Butterfly Barbados, We Talking Bois, of these civil society organizations, three (3) are human rights organizations---Equals, Butterfly Barbados, and We talking Bois.

In the case of the Dominican Republic, 15 human rights organizations were trained and supported through the following activities:

- Trans Este Podemos Avanzar (TEPA), Camara de Comercio LGBT and RD es de Todes were supported to implement three projects that focus on education to promote labour inclusion, human rights education, visibility, health, advocacy, reduction of violence, stigma, and discrimination of LGBTI people.

- In July the project supported the Feria de Activismos Queer 2022 by RD es de Todes, where fourteen (14) civil society organizations participated with stands providing information about their activities to interested people and receiving workshops on strategic communication, history of the LGBTI movement in the Dominican Republic, formalization of the non-profit associations and fundraising. Photos

Indicator: Number of human rights defenders trained and supported

For this reporting period, a total of 85 human rights defenders were trained and supported.  As previously mentioned, more than 86% of are women and 63% self-identified as being an LGBTI persons.

In Barbados, the Media Training workshop, resulted in 22 human rights defenders trained and supported.  Of these, 12 were women.   In the Dominican Republic, of the 63 human rights defenders trained and supported 35 were women and 54 self-identified as an LGBTI person.

In the Dominican Republic, TEPA with the support of the project organized trainings on art activism, mental health, and safety measures in social media for 63 human rights defenders.  10 human rights defenders attended the Artivism workshop; 17 human rights defenders attended the Healing Justice workshop; 7 human rights defenders attended the Safety in Social Media workshop; 16 human rights defenders were part of the workshop on Transtheoric Method for behavioural change; and 13 human rights defenders attended the workshop on self-esteem and management of emotions.

Indicator: Number of Civil Society Organizations (CSOs) receiving USG assistance engaged in advocacy interventions

A total of five (5) civil society organizations have received assistant to engage in advocacy interventions: in the Dominican Republic, REVASA, ASA and TRANSA; in Barbados, Equals and Butterfly Barbados

- Dominican Republic – Three (3) Dominican Human Rights organizations were supported for advocacy activities that focus on visibility and access to justice.

  - REVASA and ASA were supported in the organization of the Caravana del Orgullo LGBTIQ Dominicano. This activity consisted of the mobilization of LGBTI people, to celebrate diversity and make the population visible. The caravan was celebrated on July 10, 2022. A total of four thousand (4,000) people participated directly in the Santo Domingo Caravan, making a tour through the city, concluding with a closing concert where there was an estimated attendance of eight thousand (8,000) people. Photos/ Video

  - TRANSSA was supported for the launch of the manual and a booklet on security and justice for LGBTI people. 10 people participated in the event. Two representatives from the Attorney General’s Office and the National Defense Office participated in the launch. Photos/ Video

Meanwhile, in Barbados two (2) organizations received technical-support through the small-grants programme to engage in advocacy interventions.

In the Case of Butterfly Barbados, their initiative:  Visibility Counts: Transgender & Gender Diverse Community in Barbados, creates an opportunity for dialogue to facilitate awareness of challenges the Transgender & Gender Diverse community encounters. The overall goal of the project is to sensitize the Barbados Family Planning Association (BFPA) Clinic on best practices and interactive skills to competently comprehensive services to the community through the clinic and to utilize community needs assessment/ focus groups. The data derived will be presented to various stakeholders inclusive of the government.

After the intended retreat roundtable discussion, a report will be drafted for the various stakeholders inclusive of the government for inclusive laws as it relates to the LGBTI community with support from the BFPA as collaborators.

On the other hand, Equals is implementing a project is to increase knowledge and awareness among mental healthcare professionals on LGBTQ+ issues to facilitate increased access to mental health services for the LGBTQ+ community through empowerment and sensitization. Equals goal is to train mental healthcare professionals in the public and private sector on methods to address implicit biases as it relates to the LGBTQ+ community. The main beneficiaries of this project are members of the LGBTQ+ community who are seeking mental health services from mental health professionals.

The training will allow the said professionals to deliver care to the LGBTQ+ community that is free from stigmatization and discrimination. For example, trained guidance counsellors will now be able to provide LBGTQ+ students with a safe and affirming environment.

## Implementation Challenges

Given the complexity of the crisis in Haiti, especially concerns for the security of LGBTI person and project personnel all project activities were suspended.

## Gender Equality and Female Empowerment

The project addresses gender equality in the broader sense, challenging the culturally-defined set of economic, social, and political roles, responsibilities, rights, entitlements obligations, associated with being female and male, and the sigma and discrimination that is directed at an individual based on biological sex, intersex status, gender identity (e.g., transgender), or behaviours that are not in line with social expectations of what it means to be a man or woman, boy or girl (e.g., gay men).

## Science, Technology, and Innovation (STIP) Impacts

The project´s social media accounts, blog and the UNDP website are important outlet to communicate project activities and results. This includes:

- Twitter: https://twitter.com/LGBTICaribbean

  - 2,396 tweets published (254 tweets in the last 6 months) and 1,236 followers in total (98 more followers than during the previous six-month period).

  - In the last 6 months, tweets earned 70,827 (70K) impressions (that are the number of times users saw the tweet on twitter). There has been an increase on the impressions earned compared to the previous period (70,269)

    - The top tweet was linked to the #InspiringCards collage, on May 9, featuring quotes of LGBTI activists from the region for the #ProudlyCaribbean campaign. This message reached more than 4.800 people. In June, another one of our top tweets earned more than 2K impressions and a total of 126 engagements. This tweet shared the UN Free & Equal campaign on LGBTI families.

  - In this period the account received 32,268 visits, doubling the previous period number of visits (16,245 visits from October 2021 to March 2022), September was the month with more visits (up to 9K), coinciding with the DATA LGBTQI+ Regional Event, the launch of BLIC Media Training Workshop in Barbados and the launch of the “Being LGBTI in the Caribbean: Dominican Republic 2022” report.

  - 166 new mentions in the last six months.

  - and 114 new followers in this same period.

- Instagram: https://www.instagram.com/lgbticaribbean/

  - In the last 6 months numbers have increased to 396 posts and 1,538 followers. This means 63 new posts and 122 new followers in this period, exceeding the previous six-month period’s figures.

  - During this period, a total number of 5,920 accounts have been reached (almost doubling the 3,094 accounts reached during the previous period), among which 798 accounts engaged. There is a progressive increase during the past months of the accounts that engage with BLIC’s Instagram content, September being the month with highest rates.

  - 198 new stories were featured.

  - 8 new videos were uploaded - with a total of 575 views.

  - 45% of our followers are from 4 beneficiary countries of the project, these being Dominican Republic (30%), Jamaica (8%), Barbados (5%) and Haiti (2%).

  - 50% of our followers are among 25-34 years old; the next age ranges being 35-44 (22%) and 18-24 (19%)

- Facebook: https://www.facebook.com/LGBTICaribbean

  - Numbers have raised to 1,316 followers and 1,152 likes

  - During the past six months, 170 new posts have been posted on BLIC’s Facebook page, reaching 3,064 (3K) people, 122 engagements (reactions, likes, comments or shares) and 34 post clicks.

  - 15 new videos have been uploaded or shared on our Facebook site: https://www.facebook.com/LGBTICaribbean/videos.

  - The majority of BLIC’s Facebook page followers are from Haiti, Dominican Republic, USA, Venezuela, Guyana, and Jamaica, in that order.

- Medium blog: https://medium.com/being-lgbti-in-the-caribbean

  - 5 new articles were published in the last 6 months.

- “Salud mental afirmativa para las personas LGBTIQ+”

- “Convocatoria voluntariado Segundo Diálogo Nacional LGBTI+”

- “Health and Rights for LGBTI People in the Dominican Republic”

- “Orgullo LGBTI Dominicano 2022”

- “Hallazgos y resultados principales de la Encuesta Nacional LGBTI”

  - 218 new views in the 5 published articles during the last 6 months.

- In particular, our top article (the article with more visits) has been the “Convocatoria voluntariado Segundo Diálogo Nacional LGBTI+”, announcing the call for volunteers for the Second National LGBTI+ Dialogue in the Dominican Republic, that will take place in October 2022.

- YouTube channel (https://www.youtube.com/channel/UCNKnXbskgTJwDd1ntQP6Jww)

- The channel now features a total of 84 subscribers, 67 videos, with 3.942 views (only on YouTube, most of our videos are promoted on Facebook though).

- In the last 6 months 3 new videos were uploaded:

- “Saadiq Stoute for Proudly Caribbean Campaign” Testimony video

- “Caravana del Orgullo LGBTI Dominicano 2022” Video of the June Pride parade in Dominican Republic

- “Seguridad para todos desde el enfoque de la diversidad” Video of the launch of 2 toolkits with TRANSSA

- Newsletters (subscription link)

- BLIC newsletter audience has 929 contacts, from which 895 are subscribers

- 7 new newsletters have been shared with BLIC audience in the past 6 months with a total of 833 opens, and an average of 41% opening rate

- Articles featuring the project in national/regional media or UNDP sites:

- IDAHOBIT article published in UNDP global site, in English and Spanish, May 17

- IDAHOBIT article published in PNUD LAC site, in English and Spanish, May 17

- UNDP’s Administrator Declaration published in UNDP global site in English, Spanish and French, highlighting achievements of the BLIC project, May 13

- Article on Small Grants call for proposals published in Funds for NGOs in English, April 6

- Article on Small Grants call for proposals published in Concoursn.com in English, April 6

BLIC campaigns during the reporting period featured in social media accounts, blog and the UNDP website include:

- A specific campaign was prepared for Pride Month, during June 2022

- 5 #PrideMonth cards were shared through social media

- The hashtags #PrideMonth and #MesDelOrgullo were used in all related publications during June

- Support was given through social media to Pride related activities in the region

- Video and photo album of Dominican Republic Pride Parade

- Newsletter and Blog article on Pride activities and results

- Social media kits with materials and suggested posts were shared with UNDP and USAID offices

- A specific campaign was prepared for the launch of the Report “Being LGBTI in the Caribbean: Dominican Republic 2022” during September 2022

- Graphic materials designed and shared through all social media

- Press release to be shared

- 5 infographic cards sharing the results of the report to be shared during October

- New Campaign for International Days designed and promoted through social media, consisting of 9 cards and messages

- IDAHOBIT 2022, May 17

- Pride Day, June 28

- International Day of Friendship, July 30

- Bivisibility Day, September 23

- International Lesbian Day, October 8

- Spirit Day, 20 October

- Intersex Awareness Day, 26 October

- Trans Remembrance Day, 20 November

- AIDS Day, 1 December

- The #LGBTINews and #LGBTIStories series have been featured in both Twitter and Facebook, sharing LGBTI related news and inspiring stories from the region or globally in Spanish, English and French.

## Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts

- In the Dominican Republic the project is supporting the Dominican LGBT Chamber of Commerce to promote the labour inclusion of LGBTI people in the private sector.

- In addition, the project is compiling a compendium of good practices on private sector inclusion that is undergoing internal quality assurance process for publications.

- Finally, UNDP, facilitated a consultation between USAID and private sector entities in the Dominican Republic, in the general context of the Second National Dialogue.

## 2.7 LGBTI Inclusion

## LGBTI inclusion is the focus of the project.

## 2.8 Inclusion of Persons with Disabilities (PwD)

Where possible the project includes sign language interpretation or subtitles.

# Environmental Compliance

The Project is in compliance with USAID Environmental regulations.

# STAKEHOLDER PARTICIPATION AND INVOLVEMENT

The BLIC project works with a range of partners.  Government partners include Ombudsperson Offices, Ministries of Health, Education, Gender, and Labour. Civil society partners include both national and regional organizations.  In addition, UN Agencies have also partnered with the project on distinct activities.

# MANAGEMENT AND ADMINISTRATIVE ISSUES

The project continues to experience a high turnover of staff.  This can be attributed to the fact that project staff are mainly young professionals who are availed of opportunities to either advance their studies or career with new opportunities.

# Budget

# LESSONS LEARNED

# PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS

DOMINICAN REPUBLIC

- Second LGBTI National Dialogue 2022.

- Dissemination of the main recommendations of the National Dialogue LGBTI 2022.

- Small Grants technical support to RD es de Todes, TEPA and the LGBTI Chamber of Commerce

- OutFest Support

- Training to government and other partners as requested

- Dissemination of Results of Being LGBTI in Dominican Report.

- Present result of National Survey – e.g., results on mental health to be presented at regional psychiatric congress

- Support events on gender-based violence and during human rights week.

BARBADOS

- Human Rights Defenders Capacity-Building Series (virtual) to promote a culture of respect for human rights with specific reference to the LGBTI Community

- Communication Skills (October 13, 2022)

Learning to communicate effectively about LGBTI issues and social media tools & best practices

- Leaving No-One Behind (October 19, 2022)

Learning what explicit actions can be taken to end extreme poverty, curb inequalities, confront discrimination and fast-track progress for the furthest behind.

- Monitoring and Evaluation (October 26, 2022)

Learning the tools and processes to measure if a program has been implemented according to the plan (Monitoring) and is having the desired result (Evaluation)

- Support the Launch of the National LGBTI survey

- Disseminate and share survey results

- Provide technical support to Butterfly Barbados and Equals on implementation of small grants

- Support CSO with Capacity Development Initiatives

JAMAICA

- National LGBTI Survey

- Small grants for LGBTI community groups (Equality for All)

- Trans Day of Remembrance (together with TransWave)

- World AIDS Day Breakfast Forum

- Host 3 virtual/face-to-face Capacity building workshops for LGBTQI groups to improve the capacity in:

  - Financial Literacy/ socio-economic inclusion

  - Media and communication

  - Positive health dignity and prevention (PHDP) Capacity Building session

COMMUNICATIONS:

●	Regular updating of all social media platforms (including giving specific visibility to national and regional BLIC activities)

●	Providing technical support to the event “Second LGBTI+ National Dialogue, Dominican Republic 2022”, to be held in October 2022.

●	A social media practical workshop will be delivered in Barbados for CSOs beneficiaries.

●	Two new communication campaigns for social media will be prepared, these being “On their shoulders” and “What Matters”, with the support of UNDP Country Offices in the project’s beneficiary countries.

●	Provide assistance to the CSOs awarded the Small Grants through different meetings and/or communications training.

●	Communication’s support will be given to national LGBTI surveys in Barbados, Haiti, and Jamaica, replicating the support given to the National LGBTI Survey in Dominican Republic.

# How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report

Not Applicable

Information retrieved until September 30th, 2022.

Accounts reached: number of accounts that have seen the content at least once.

Accounts engaged: number of accounts that have interacted with the content.

Likes are public while followers are not, which may explain the difference between numbers in our case.