BEING LGBTI IN THE CARIBBEAN (BLIC) Bi-Annual Report Submission Date: April 17, 2023 [Contract/Agreement] Number: AID-517-IO-17-00001 Activity Start Date and End Date: September 22, 2018, to February 28, 2025 [COR/AOR] Name: Luis Duran Submitted by Karin Santi, Chief of Party United Nations Development Programme City of Knowledge, Building 128, Panama City, Panama Tel: +507 302 4610 Email: karin.santi@undp.org This document was produced for review by the United States Agency for International Development in the Dominican Republic (USAID/DR). -10 -2022 to 31-03-2023

# Program Overview/Summary

| Program Name: | Being LGBTI in the Caribbean (BLIC) |
| --- | --- |
| Activity Start Date and End Date: | September 22, 2017, to February 28, 2025 |
| Name of Prime Implementing Partner: | United Nations Development Programme |
| [Contract/Agreement] Number: | AID-517-IO-17-00001 |
| Name of Subcontractors/Sub-awardees: | Barbados and Eastern Caribbean Butterfly Barbados Equals. Dominican Republic: Cámara de Comercio LGBTI Trans Este Podemos Avanzar (TEPA) RD es de Todes Jamaica Equality for All Jamaica AIDS for Life Regional UNIBAM |
| Major Counterpart Organizations: | Not Applicable |
| Geographic Coverage (cities and or countries): | Barbados, Dominican Republic, and Jamaica |
| Reporting Period: | October 1, 2022, to March 31, 2023 |

Contents

1.	Program Overview/Summary	0

1.1	Program Description/Introduction	2

2.	ACTIVITY IMPLEMENTATION PROGRESS	2

2.1	Progress Narrative	2

2.2	Implementation Status	3

2.3	Implementation Challenges	7

2.4	Gender Equality and Female Empowerment	7

2.5	Science, Technology, and Innovation (STIP) Impacts	7

2.6	Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts	8

2.7 LGBTI Inclusion	8

LGBTI inclusion is the focus of the project.	8

2.8 Inclusion of Persons with Disabilities (PwD)	8

3.	Environmental Compliance	9

4.	STAKEHOLDER PARTICIPATION AND INVOLVEMENT	9

5.	MANAGEMENT AND ADMINISTRATIVE ISSUES	9

6.	Budget	9

7.	LESSONS LEARNED	9

8.	PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS	10

9.	How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report	11

## Program Description/Introduction

Being LGBTI in the Caribbean (BLIC) is a regional programme that aims to enhance knowledge, partnerships, and capacities of LGBTI communities, civil society, and States to reduce human rights violations and negative attitudes towards LGBTI people in the Caribbean, with country level focus in Barbados, Dominican Republic, Haiti, and Jamaica, as well as regional activities. To achieve its goals, it is crucial that the project responds to the experiences and needs of the LGBTI community in the Caribbean.

While numerous reviews of the situation LGBTI people vis-à-vis laws, policies and practices have been carried out in the Caribbean, currently very little systemic data reflects the issues and circumstances of LGBTI people in the region. Governments often lack data and evidence needed to shape policies and programs for LGBTI inclusion. Many civil society organisations still need to develop solid coordination mechanisms among themselves, to increase their impact, to be recognised as full partners at national level and to develop joint strategies for advocacy and lobbying. Up to date data would enable analysis on the level of LGBTI rights and inclusion. Such analysis would enable the development of laws, policies, as well as advocacy programmes that are more effective in instigating social, legal, and political changes, partnerships, and opportunities.

The proposed project has the following mutually reinforcing objectives:

1.	To strengthen data/evidence base on the rights of LGBTI people and enhance the capacity of governments, civil society and LGBTI groups to address and reduce inequality, exclusion, violence, and discrimination experienced by LGBTI persons in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, and St Lucia.

2.	To increase awareness of homophobic and transphobic violence and discrimination and strengthen the capacity of civil society organizations to challenge negative attitudes towards LGBTI people including through engaging government officials, parliamentarians, political parties, trade unions, religious leaders, civil society, media, and the general population in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, St Lucia and regionally.

The programme is a collaboration between governments, civil society, regional institutions, and other stakeholders to advance the social inclusion of lesbian, gay, bisexual, transgender, and intersex people. The programme is supported by the U.S. Agency for International Development (USAID).

This report covers the six months of project implementation (October 2022 to March 2023) providing an overview of activities conducted and provide an overview of upcoming initiatives.

# ACTIVITY IMPLEMENTATION PROGRESS

## Progress Narrative

During this reporting period, a total of eighteen (18) human rights organizations have been trained and supported under the Being LGBTI in the Caribbean project. Fourteen (14) of these organizations were supported in Barbados and two (2) each in Jamaica and the Dominican Republic. In Barbados, LGBTI CSOs and ally organisations were supported to engage in the national constitutional reform hearings. The support allowed CSOs to obtain specific information on participation in the political process, strategize as a community and meet with other coalition members to create an action plan for the Constitutional Reform Commission Consultations and written submission, LGBTQ+ Protections and Their Importance to The New Constitution was presented to the Commission.

Public Forums bringing together government and non-state actors were held in the Dominican Republic. Among the 4 forums realised, the Second National LGBTI Dialogue. This two-day meeting promoted the formulation and implementation of intersectoral and inclusive policies on security, justice, health, and health equity for lesbian, gay, bisexual, trans, queer and intersex (LGBTQI+) people. The search and promotion of these policies will be achieved through a consensus between the State, civil society, the private sector, and other important actors in Dominican society.

LGBTI persons report an increased need for mental health support. The BLIC project supported Equality for All in Jamaica to improve the pre-service training of medical and psychology students at the University of West Indies, Mona by equipping their lecturers and instructors with the tools and knowledge to integrate greater attention to the healthcare needs of LGBT persons within their existing curriculum. While in Barbados, Equals was supported to provide training to the Barbados Psychological Association, the Barbados Psychiatric Association, and staff at Queen Elizabeth Hospital to increase knowledge and awareness among mental healthcare professionals on LGBTI mental health needs and to facilitate increased access to mental health services.

## Implementation Status

Output 1: Knowledge, strategic information, and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated

Indicator: Number of research papers on LGBTI produced.

The national LGBTI survey reports for Jamaica and Barbados are in the final stages of completion and will be published in the next quarter.

Output 2: Support Meaningful engagement through national and regional policy dialogues

Indicator: Number of public forums in which national governments and LGBTI civil society interact.

During this reporting period four (4) public forums have been held. In the Dominican Republic, two (2) forums were co-convened and organized with the Ministry of Women. Both forums included the participation of local LGBTI CSO RD es de Todes. A CSO member delivered a presentation on the basic concepts pertinent to human rights of LGBTI persons and BLIC project staff presented on the State´s obligations to ensure the enjoyment of all rights by all persons. It is expected that this initiative will improve the provision of services within priority public institutions for LGBTI beneficiaries.

In addition, two (2) public forums were held, including the Second National Dialogue LGBTI+ Preforum with 30 representatives from key sectors and institutions of the justice and health systems, to agree on the minimum commitments to be assumed by the government sector in alliance with the rest of the convened sectors (including LGBTI civil society organizations), as well as the definition of the responsible institution and the design of the draft roadmap on inclusive public policies. Preforo del Segundo Diálogo Nacional LGBTI+ | Flickr.

The Second National Dialogue LGBTI+ was held as a space for debate, analysis and reflection aimed at promoting practices, interventions and intersectoral public policies in security, justice and health, inclusive of LGBTI+ people, with the participation of civil society, business sector, academia, influencers, media, activists and human rights defenders and other relevant actors of the Dominican society inside and outside the country, with 18 public institutions. The event was supported by The Ministry of Public Health, the United Nations High Commissioner for Refugees (UNHCR), the Canadian Embassy, the Embassy of the United Kingdom, the Embassy of the Netherlands and the Free and Equal Campaign of the United Nations System. 2do Diálogo Nacional LGBTI | Flickr Realizan el Segundo Diálogo Nacional de Inclusión de personas LGBTQI+ | Programa De Las Naciones Unidas Para El Desarrollo (undp.org)

Output 3: Capacity of LGBTI Community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge, and concrete actions to address stigma and discrimination.

Indicator: Number of CSOs trained and supported

Over the past six months the project supported 18 CSOs, 2 in Jamaica, 2 in Dominican Republic and 14 in Barbados.  Fourteen (14) of these organisations directly work on LGBTI issues while the remaining four (4) are women’s rights organisations.

In the Dominican Republic, Trans Este Podemos Avanzar (TEPA) was supported to implement three projects that focus on education to promote health, advocacy, reduction of violence, stigma, and discrimination against LGBTI people. Amigos Siempre Amigos was supported with the participation in the workshop on Psychosocial support from a non-harmful approach to children, adolescents, LGBTIQ+ youth and their families.

In Barbados, a total of 14 CSO’s were trained, 10 were LGBTI CSOs: CAISO, Equals, SASOD, WE Change, , Equality for All Foundation Jamaica, Renacer, United and Strong, Grenchap, Kambrada/FOKO, Action Citoyenne pour l’Égalité Sociale en Haïti while 3 Women Organisations participated in the training, including Raise Your Voice, Caribbean Women in Leadership (CIWiL) , Women's Resource and Outreach Centre The training took the form of a three-part Human Rights Defenders Capacity-Building Series which was conducted to promote a culture of respect for human rights with specific reference to the LGBTI people. The workshops were designed as an open call to human rights defenders. These sessions were requested from the local CSOs, and it should be noted that while the focus was initially on LGBTI CSOs, the sessions were open to other organisations where people wanted to gain knowledge/specific skills to incorporate initiatives within their organisations to address stigma and discrimination.

The Series involved: 
Communication Skills Workshop:

Learning to communicate effectively about LGBTI issues and social media tools & best practices. The workshop included sessions on the following: an overview of the BLIC Project, a social media overview (Instagram, Facebook, Newsletter, Twitter, Instagram, Medium Blog, YouTube), creating specific campaigns, communicating effectively about LGBTI related issues, using appropriate LGBTI terminology and concepts, best practices, and examples, the BLIC media experience, working with the LGBTI community.

Leaving No One Behind:

This training session focused on the actions that can be taken to end extreme poverty, curb inequalities, confront discrimination and fast-track progress for the furthest behind. The workshop included sessions on the following: Agenda 2030 and Sustainable Development Goals, what is inclusion? (dimensions of exclusion, barriers for inclusion), how the concept of leave no one behind can be integrated in the work of organisations.

Monitoring and Evaluation Essentials:  
The training session focused on the tools and processes to measure if a program has been implemented according to the plan (Monitoring) and whether it is having the desired result (Evaluation). Generally, the workshop included sessions on introduction to monitoring, indicator development, target setting, designing a results framework and an introduction to evaluation.

Indicator: Number of human rights defenders trained and supported

In total 231 human rights defenders were trained and supported, of whom 46 self-identified as members of the LGBTI community.  Of the total participants 131 identified as female while a 54 identified as male.

In the Dominican Republic, TEPA with the support of the project organized trainings on art activism, mental health, and safety measures in social media for 46 human rights defenders.  13 human rights defenders attended the Artivism workshop; 17 human rights defenders attended the Healing Justice workshop; 4 human rights defenders attended the Safety in Social Media workshop; and 12 human rights defenders were part of the workshop on Transtheoric Method for behavioural change.

In Barbados, a total of 185 human rights defenders were trained (131 female, 54 male). The Human Rights Defenders Capacity-Building Series  resulted in 91 human rights defenders trained (63 female, 28 male) and the collaboration with Equals resulted in 83 trained human rights defenders trained (52 female, 31 male).  The BLIC Project partnered with Equals, one of the recipients of the Small Grants Programme. The grant focused on, Breaking Down Barriers of Access to Mental Healthcare by LGBTQ+ People and was based on increasing knowledge and awareness among mental healthcare professionals on LGBTQ+ concerns to facilitate increased access to mental health services for the LGBTQ+ community through empowerment and sensitization. The goal was to train mental healthcare professionals in the public and private sector on methods to address implicit biases as it relates to the LGBTQ+ community. The main beneficiaries of this project were members of the LGBTQ+ community who are seeking mental health services from mental health professionals. With the support of the project, the following sensitivity trainings were conducted:

- Breaking Down Barriers of Access to Mental Healthcare by LGBTQ+ People.

A total of 83 human rights defenders were trained/supported.

- Social Workers Training

Participants indicated the sessions were informative and interactive and their understanding of Gender Identity and the surrounding continuum was clarified.

- Psychological Training

Organisations trained include the Barbados Psychological Association, the Barbados Psychiatric Association, and Queen Elizabeth Hospital staff (QEH) Participants indicated the sessions were positive as the small group allowed for in-depth discussions, questions, and collaborations.

- Queen Elizabeth Hospital Training

The following departments were involved in the training: Accident and Emergency, Psychiatry, Internal Medicine, Patient Advocacy, Paediatrics, Administration. Participants indicated the training clarified their understanding and furthered their knowledge on Sexual Orientation and Gender Identity. Equals agreed to share the educational materials utilised to conduct the training to the Queen Elizabeth Hospital as well as specific recommendations that can be used to create a policy.

Indicator: Number of Civil Society Organizations (CSOs) receiving USG assistance engaged in advocacy interventions

During this reporting period two (2) CSOs receiving assistance were engaged in advocacy interventions. Both organisations are based in Barbados.

Constitutional Reform Process

Barbados has been undertaking a Constitutional Review Process which has included community or constituency consultations. LGBTI organisations came together in Community Town Hall Sessions where people were able to obtain specific information on participation in the political process, strategize as a community and meet with other coalition members to create an action plan for the Constitutional Reform Commission consultations and written submissions to the Commission. The Constitutional Reform Commission was appointed to oversee the development and enactment of a new Constitution of Barbados in so doing, BLIC supported the following activities:

Community Town Hall Strategic Training/Session

The session created a space for the discussion of community needs which was crucial for collective decisions on CSOs/activists’ political path in Barbados. Comprehensive discussions focused on discrimination of elders, the need for greater engagement with younger queer people, increased education on transgender and non-binary topics within the community and schools, distinguishing factors between the striking down of buggery and serious indecency: Sections 9 and 12, Barbados Sexual Offences Act Chapter 154 and the Constitutional Reform Commission Consultation Process, and discrimination in accessing public services.

Pre-Constitutional Reform Commission -Strategic Training/Session

The strategic session enabled discussions surrounding frequently asked questions to submit to the Constitutional Reform Commission, submissions, strategy for the consultation. The following plan was devised to present to the Commission: sharing of personal stories of injustice within health and police departments, presentation of the submissions and FAQs.

The Community Town Hall Strategic Session and Pre-Constitutional Reform Commission -Strategic Planning Session resulted in the submission of the Report, “LGBTQ+ Protections and Their Importance to The New Constitution” by the LGBTQ+ Coalition of Barbados. The Submission included sections on the following: the LGBTQ+ Community: dispelling some myths, why protections for the LGBTQ+ community should be explicitly included in the Constitution, definitions of common terms, the right to freedom from discrimination, the rights of the child, immigration, and citizenship, right to work, religious freedom, right to private and family rights, right to life and savings clause.

Post-Constitutional Reform Commission -Strategic Training/Session

The strategy session enabled the community to debrief from the Constitutional Consultation. This consisted of discussions surrounding the inclusion of sexual orientation and gender identity within the Constitution, the need for further community engagement, allyship engagement, and public engagement. After the intended retreat roundtable discussion, a report will be drafted for the various stakeholders inclusive of the government for inclusive laws as it relates to the LGBTI community with support from the Barbados Family Planning Association as collaborators.

## Implementation Challenges

Given the complexity of the crisis in Haiti, especially concerns for the security of LGBTI person and project personnel all project activities were suspended.

## Gender Equality and Female Empowerment

The project addresses gender equality in the broader sense, challenging the culturally-defined set of economic, social, and political roles, responsibilities, rights, entitlements obligations, associated with being female and male, and the sigma and discrimination that is directed at an individual based on biological sex, intersex status, gender identity (e.g., transgender), or behaviours that are not in line with social expectations of what it means to be a man or woman, boy or girl (e.g., gay men).

## Science, Technology, and Innovation (STIP) Impacts

The project´s social media accounts, blog and the UNDP website are important outlet to communicate project activities and results. This includes:

●      Twitter: https://twitter.com/LGBTICaribbean

  - 1,310 followers (74 more than the previous six-month period).

  - 43,107 impressions (number of times users saw the tweet on twitter).

●      Instagram: https://www.instagram.com/lgbticaribbean/

  - 39 posts in the last 6 months and 1,694 followers (39 new posts and 281 new followers in this period)

  - 12,747 accounts reached

  - 43.8% of our followers are from 4 beneficiary countries of the project, these being Dominican Republic (31.9%), Jamaica (7.4%), Barbados (4.5%). 48% of our followers are among 25-34 years old; the next age ranges being 35-44 (24.1%) and 18-24 (16.5%)

●      Facebook: https://www.facebook.com/LGBTICaribbean

  - 1310 followers (6 less than in previous 6-month period)

  - 5 posts in the last 3 months, reaching 113 people, 5 engagements (reactions, likes, comments or shares)

  - The majority of BLIC’s Facebook page followers are from Haiti, Dominican Republic, USA, Venezuela, Guyana, and Jamaica, in that order.

●      Medium blog: https://medium.com/being-lgbti-in-the-caribbean

  - 345 views in the last 6 months.

●      YouTube channel (https://www.youtube.com/channel/UCNKnXbskgTJwDd1ntQP6Jww)

  - The channel now features a total of 98 subscribers (14 more than last period), 73 videos, with 13,890 views

  - In the last 6 months 6 new videos were uploaded:

➔   Monólogos Libres e Iguales - "Mi circo, mi vida", Jeandi R Bello

➔  Monólogos Libres e Iguales - "Emociones a la carta", Victor Sossa

➔  Monólogos Libres e Iguales - "Jugando a danzar", Isra Guerrero
➔ Monólogos Libres e Iguales - "Mi viaje", Yeifri Ramirez
➔ Monólogos Libres e Iguales - "Transitando una pérdida", César Peralta
➔ Informe "Ser LGBTI en el Caribe: República Dominicana 2022": Evento de lanzamiento, video of the launch of BLIC in the Dominican Republic.

●      Newsletters (subscription link)

  - BLIC newsletter audience has 923 contacts, from which 878 are subscribers

  - 8 new newsletters have been shared with BLIC audience in the past 6 months with a total of 1405 opens, and an average of 34.7% opening rate

## Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts

- UNDP facilitated a consultation between USAID and private sector entities in the Dominican Republic, in the general context of the Second National Dialogue.

## 2.7 LGBTI Inclusion

## LGBTI inclusion is the focus of the project.

## 2.8 Inclusion of Persons with Disabilities (PwD)

Where possible the project includes sign language interpretation or subtitles.

# Environmental Compliance

The Project is in compliance with USAID Environmental regulations.

# STAKEHOLDER PARTICIPATION AND INVOLVEMENT

The BLIC project works with a range of partners. Government partners include Ombudsperson Offices, Ministries of Health, Education, Gender, and Labour. Civil society partners include both national and regional organizations. In addition, UN Agencies have also partnered with the project on distinct activities.

# MANAGEMENT AND ADMINISTRATIVE ISSUES

The recruitment of a Chief of Party will be conducted during the quarter as well as National Officers that will provide support to project implementation

# Budget

# LESSONS LEARNED

Due to the good experience the project had collaborating with the Sir Arthur Lewis Institute of Social and Economic Studies (SALISES) on the finalisation of the Barbados national LGBTI survey, they will be included in UNDP’s expert roster and be considered for future research initiatives. SALISES is one of the premier institutes of development studies.

# PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS

BARBADOS

- Support the Launch of the National LGBTI survey

- Disseminate and share survey results

- Hold meetings with national stakeholders (including civil society organizations and government institutions) to present the BLIC phase III project

- Select a transgender women's organization to implement the socioeconomic of transgender and gender diverse persons inclusion program.

- Recruit the National Programme Focal Point: CSO

GUYANA

- Hold meetings with national stakeholders (including civil society organizations and government institutions) to present the BLIC phase III project

- Elect a transgender women's organization to implement the socioeconomic of transgender and gender diverse persons inclusion program.

- Recruit the National Programme Focal Point: CSO

DOMINICAN REPUBLIC

- Publish the roadmap on recommendations of the National Dialogue

- Hold meetings with national stakeholders (including civil society organizations and government institutions) to present the BLIC phase III project

- Select a transgender women's organization to implement the socioeconomic inclusion programme of transgender and gender diverse persons

- Recruit the National Programme Focal Point: CSO

JAMAICA

- Support the Launch of the National LGBTI survey

- Disseminate and share survey results

- Hold meetings with national stakeholders (including civil society organizations and government institutions) to present the BLIC phase III project

- Select a transgender women's organization to implement the socioeconomic of transgender and gender diverse persons inclusion program.

- Recruit the National Programme Focal Point: CSO

COMMUNICATIONS:

- Regular updating of all social media platforms (including giving specific visibility to national and regional BLIC activities)

- Provide technical support to the launch events for the National Surveys in Barbados and Jamaica

- Develop design products to mark LGBTI commemorative dates

- Develop Communication Strategy for BLIC phase III

# How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report

Not Applicable

Information retrieved until April 12, 2023.

Accounts reached: number of accounts that have seen the content at least once.

Given the low number of followers lost, it could be due to deleted accounts.

Accounts engaged: number of accounts that have interacted with the content.