BEING LGBTI IN THE CARIBBEAN (BLIC) Bi-Annual Report Submission Date: November 6th, 2023 [Contract/Agreement] Number: AID-517-IO-17-00001 Activity Start Date and End Date: September 22, 2018, to February 28, 2025 [COR/AOR] Name: Luis Duran Submitted by Karin Santi, Chief of Party United Nations Development Programme Barbados Email: karin.santi@undp.org This document was produced for review by the United States Agency for International Development in the Dominican Republic (USAID/DR). -04 -2022 to 30-09-2023

# Program Overview/Summary

| Program Name: | Being LGBTI in the Caribbean (BLIC) |
| --- | --- |
| Activity Start Date and End Date: | September 22, 2017, to February 28, 2025 |
| Name of Prime Implementing Partner: | United Nations Development Programme |
| [Contract/Agreement] Number: | AID-517-IO-17-00001 |
| Name of Subcontractors/Sub-awardees: | Barbados and Eastern Caribbean Butterfly Barbados Equals. Dominican Republic: Cámara de Comercio LGBTI Trans Este Podemos Avanzar (TEPA) RD es de Todes Jamaica Equality for All Jamaica AIDS for Life Regional UNIBAM |
| Major Counterpart Organizations: | Not Applicable |
| Geographic Coverage (Cities and or countries): | Barbados, Dominican Republic, Guyana and Jamaica |
| Reporting Period: | April 1st, 2023, to September 31st, 2023 |

Contents

1.	Program Overview/Summary	0

1.1	Program Description/Introduction	2

2.	ACTIVITY IMPLEMENTATION PROGRESS	2

2.1	Progress Narrative	2

2.2	Implementation Status	3

2.3	Implementation Challenges	7

2.4	Gender Equality and Female Empowerment	7

2.5	Science, Technology, and Innovation (STIP) Impacts	7

2.6	Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts	8

2.7 LGBTI Inclusion	8

LGBTI inclusion is the focus of the project.	8

2.8 Inclusion of Persons with Disabilities (PwD)	8

3.	Environmental Compliance	9

4.	STAKEHOLDER PARTICIPATION AND INVOLVEMENT	9

5.	MANAGEMENT AND ADMINISTRATIVE ISSUES	9

6.	Budget	9

7.	LESSONS LEARNED	9

8.	PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS	10

9.	How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report	11

## Program Description/Introduction

Being LGBTI in the Caribbean (BLIC) is a regional programme that aims to enhance knowledge, partnerships, and capacities of LGBTI communities, civil society, and States to reduce human rights violations and negative attitudes towards LGBTI people in the Caribbean, with country level focus in Barbados, Dominican Republic, Haiti, and Jamaica, as well as regional activities. To achieve its goals, it is crucial that the project responds to the experiences and needs of the LGBTI community in the Caribbean.

While numerous reviews of the situation LGBTI people vis-à-vis laws, policies and practices have been carried out in the Caribbean, currently very little systemic data reflects the issues and circumstances of LGBTI people in the region. Governments often lack data and evidence needed to shape policies and programs for LGBTI inclusion. Many civil society organisations still need to develop solid coordination mechanisms among themselves, to increase their impact, to be recognised as full partners at national level and to develop joint strategies for advocacy and lobbying. Up to date data would enable analysis on the level of LGBTI rights and inclusion. Such analysis would enable the development of laws, policies, as well as advocacy programmes that are more effective in instigating social, legal, and political changes, partnerships, and opportunities.

The proposed project has the following mutually reinforcing objectives:

1.	To strengthen data/evidence base on the rights of LGBTI people and enhance the capacity of governments, civil society and LGBTI groups to address and reduce inequality, exclusion, violence, and discrimination experienced by LGBTI persons in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, and St Lucia.

2.	To increase awareness of homophobic and transphobic violence and discrimination and strengthen the capacity of civil society organizations to challenge negative attitudes towards LGBTI people including through engaging government officials, parliamentarians, political parties, trade unions, religious leaders, civil society, media, and the general population in seven countries – Barbados, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, St Lucia and regionally.

The programme is a collaboration between governments, civil society, regional institutions, and other stakeholders to advance the social inclusion of lesbian, gay, bisexual, transgender, and intersex people. The programme is supported by the U.S. Agency for International Development (USAID).

This report covers the six months of project implementation (April 2023 to September 2023) providing an overview of activities conducted and provide an overview of upcoming initiatives.

# ACTIVITY IMPLEMENTATION PROGRESS

## Progress Narrative

During this reporting period, a total of sixteen (16) human rights organizations were trained and supported.  Of these, five (5) organizations are based in Guyana, and the remaining eleven (11) in the Dominican Republic.  The totality of human rights organizations supported during this reporting period identify as LGBTI civil society organizations.

The culmination of two (2) National LGBTI surveys-in Jamaica and Barbados allowed for important discussions to occur at national level, engaging diverse actors, including government counterparts, academia, and international cooperation agencies.  During the preparation of both reports, national LGBTI civil society organizations had a leadership role, both in the design of the research, its implementation, and the interpretation and dissemination of results.   Both knowledge products resulted in good media coverage.

Two project countries, Barbados and Jamaica are undergoing Constitutional Reviews and the project has been supporting CSOs to ensure they can effectively engage in the community consultation and advocate for inclusion of sexual orientation and gender identity in key considerations to be addressed.

As the project embarks in a new implementation stage, efforts have also been placed in ensuring a smooth transition to phase III, finalizing the hiring of the new staff and reaching out to government and civil society organizations to reengage in project implementation.

## Implementation Status

Output 1: Knowledge, strategic information, and evidence on the impact of inequality and exclusion of LGBTI people developed and disseminated

Indicator: Number of research papers on LGBTI produced.

Two (2) National LGBTI Survey Reports for Jamaica and Barbados were finalized and launched.

During the reporting period, Jamaica completed and launched the National LGBT Survey which highlighted the various socio-economic challenges faced by LGBTI persons. Additionally, through the analysis of these challenges, recommendations to inform the development and advancement of inclusive public policies were identified.  Through a hybrid mechanism, the launch of the LGBT Survey allowed for the highlighting and discussion of the report findings and recommendations identified from the data collected and analysed. Additionally, it allowed for the highlighting of next steps and practical activities that could assist bridging the social, economic, and legal gaps experienced by the LGBT community in Jamaica.  The launch consisted of remarks from UNDP and UNAIDS, followed by a presentation on the findings and recommendations of the report. A panel discussion, comprising of members from CSOs was held to discuss the alignment of the findings and to discuss active ways in which the recommendations of the report could be included in strategic plans within Jamaica.

After the launch, the Report has been disseminated amongst the respective local networks to include CSOs, UN agencies, Academia, and the Government.

Similarly, the United Nations Development Programme (UNDP), in collaboration with the University of the West Indies Cave Hill campus (UWI,) and Equals launched the Barbados National LGBTI Survey Report on July 13, 2023.

The National LGBTI Survey Report for Barbados is the culmination of extensive research conducted by UNDP in partnership with local organizations, activists, and community stakeholders. The report provides essential insights into the lived experiences, and challenges of the LGBTI community in Barbados. It explores various dimensions of their well-being, including citizen security, health, education, employment, housing, violence, access to justice, and political participation.

The launch event brought together key stakeholders, civil society representatives, academics, international organisations, and members of the LGBTI community. The event served as a platform for open dialogue and reflection on the survey findings, fostering an inclusive environment for discussing the way forward in addressing the specific lived realities and needs of the LGBTI community.

The survey results show that LGBTQ+ persons experience stigma and discrimination in various areas, including the workplace and educational institutions. The report stated that respondents often grapple with heightened vigilance by constantly monitoring the reactions of the general population to avoid discrimination and harassment. Nearly 17 percent of LGBTQ+ people were on the receiving end of a violent act in the 12 months preceding the survey, and most of these incidents go unreported. Such experiences have a negative impact on the mental health of LGBTQ individuals: nearly 70 percent of all survey respondents experienced suicidal ideation, and 24.7 percent said they attempted to take their life at some point.

Output 2: Support Meaningful engagement through national and regional policy dialogues.

Indicator: Number of public forums in which national governments and LGBTI civil society interact.

A total of one (1) forum in which CSOs and governments interact was held during the reporting period.  This event took place in the Dominican Republic, where Phase II of the BLIC project was launched.  The event was attended by high-level representatives of the Dominican State, civil society organisations, and international cooperation agencies, with the purpose of presenting the interventions and exploring possible lines of inter-institutional cooperation.

Output 3: Capacity of LGBTI Community groups developed through enhanced coordination, increased access to existing tools, transfer of knowledge, and concrete actions to address stigma and discrimination.

Indicator: Number of CSOs trained and supported

A total of sixteen (16) civil society organizations were trained and supported during the reporting period.  Five (5) organizations are based in Guyana and the remaining eleven in the Dominican Republic.

In the case of the Dominican Republic, During the period from 2022 to 2023 the project developed the National Roadmap for The Promotion and Protection of the Right to Health of Lgbti+ People, and The National Roadmap for the Protection of the Rights to Security and Justice Of Lgbti+ People, both with the purpose of identifying common objectives of people of sexual diversity with national development plans and other actions. This draft document was finalized in October 2022 and then went through a validation process for approval where civil society organizations participated: Revasa, ASA, DIVERDOM, COLESDOM, COLETH, CCLGBTRD, TEPA, RD ES DE TODES, LA CEIBA, UNIDI, to ensure national ownership.  The Final Draft has been published and shared with all national partners.

In the case of Guyana, support was provided to a PRIDE Panel discussion focussing on The Nexus Between LGBTQ+ Rights and Development that was attended by the Minister of Parliamentary Affairs and Governance, CSOs, development partners and members of the private sector.  The event was co-convened with the LGBTI organisation, EQUAL.

Indicator: Number of human rights defenders trained and supported

A total of twenty (20) human rights defenders were trained. Of these, fourteen (14) identify as male, six (6) as female and 100% self-identify as members of the LGBTI community.

Several Caribbean countries (Barbados, Belize, and Jamaica) are undergoing Constitutional Review Processes.  During the reporting period UNDP organised a Caribbean Constitutional Change Conference held in Barbados which aimed to share knowledge, experience, perspectives, and lessons learned in relation to constitutional change in the Commonwealth Caribbean. The BLIC project held a follow up workshop with CSOs in Jamaica on the Constitutional Reform Process in Jamaica. This discussion identified the various steps being taken by the Government and expounded on the various stages in the process. Ultimately the aim of the discussion was to highlight to role of CSOs in this process to ensure that ensuring that their voices are heard. For this discussion, there was representation from five (5) CSOs which 20 participants: 14 male and 6 female.

Indicator: Number of Civil Society Organizations (CSOs) receiving USG assistance engaged in advocacy interventions

Five (5) CSOs participated in a workshop on Constitutional Reform Process in Jamaica.  While in Barbados two (2) CSOs have been supported.  Equals has been engaged in the Constitutional Reform process and facilitated a community townhall to engage other LGBTI CSOs and ally organisation while the Pride Barbados Committee to host the launch Barbados PRIDE at the UN House. This year the Master of Ceremonies was Barbados PRIDE Committee Member, Ro-Ann Mohammed, and opening remarks were made UNDP Deputy Resident Representative, and the UN Resident Coordinator.

## Implementation Challenges

This period of implementation saw the project completing activities under Phase II of the project, such as the launch of the National Survey Report, while also reorganising to start implementing Phase III.  This has led to some delays given that staff recruitment and engaging of CSO on Phase II had to be prioritised.

## Gender Equality and Female Empowerment

The project addresses gender equality in the broader sense, challenging the culturally-defined set of economic, social, and political roles, responsibilities, rights, entitlements obligations, associated with being female and male, and the sigma and discrimination that is directed at an individual based on biological sex, intersex status, gender identity (e.g., transgender), or behaviours that are not in line with social expectations of what it means to be a man or woman, boy or girl (e.g., gay men).

## Science, Technology, and Innovation (STIP) Impacts

The project´s social media accounts, blog and the UNDP website are important outlets to communicate project activities and results. This includes:

- Twitter: https://twitter.com/LGBTICaribbean

  - 2,612 tweets published (216 tweets in the last 6 months)

  - 1,337 followers in total (101 more than in the previous period).

  - In the last 6 months, our tweets earned 10,384 impressions (number of times users saw our tweets on twitter).

    - The top tweet from this period (2,671 impressions) was one in which we welcomed the written judgement of the December 2022 ruling by Barbados High Court, which repeals colonial-age laws that criminalized same-sex acts.

- Instagram: https://www.instagram.com/lgbticaribbean/

  - In the last 6 months numbers have increased to 444 posts and 1,726 followers (49 new posts and 187 new followers in this period).

  - A total of 4,739 accounts have been reached, among which 458 accounts engaged.

  - 2 new videos were uploaded, with a total of 1,421 views.

  - 45% of our followers are from 4 beneficiary countries of the project, these being Dominican Republic (30%), Jamaica (8%), Barbados (5%) and Haiti (2%).

  - 50% of our followers are among 25-34 years old; the next age ranges being 35-44 (22%) and 18-24 (19%)

- Facebook: https://www.facebook.com/LGBTICaribbean

  - Numbers have raised to 1,342 followers.

  - During the past six months, our posts have reached 3,146 accounts and received 226 engagements (reactions, likes, comments, clicks or shares).

  - The reach of our posts has increased to an average of 385 accounts per post.

  - The majority of BLIC’s Facebook page followers are from Haiti, Dominican Republic, USA, Guyana, Venezuela and Jamaica, in that order.

BLIC campaigns during the reporting period featured:

- National LGBTI Survey Barbados (July 2023)

- Graphic materials designed and shared through all social media (flyers and infographics)

- 8 infographics with the main findings

- National LGBTI Survey Jamaica (October 2023)

- Graphic materials designed and shared through all social media (flyers, infographics, event programme)

- 9 infographics with the main findings

- Campaigns for International Days designed and promoted through social media.

- IDAHOBIT 2023, May 17 (video)

- Bi Visibility Day, Sept. 23 (SM post)

## Public Private Partnerships (PPP) and Global Development Alliance (GDA) Impacts

- UNDP facilitated a consultation between USAID and private sector entities in the Dominican Republic, in the general context of the Second National Dialogue.

## 2.7 LGBTI Inclusion

## LGBTI inclusion is the focus of the project.

## 2.8 Inclusion of Persons with Disabilities (PwD)

Where possible the project includes sign language interpretation or subtitles.

# Environmental Compliance

The Project is in compliance with USAID Environmental regulations.

# STAKEHOLDER PARTICIPATION AND INVOLVEMENT

The BLIC project works with a range of partners. Government partners include Ombudsperson Offices, Ministries of Health, Education, Gender, and Labour. Civil society partners include both national and regional organizations. In addition, UN Agencies have also partnered with the project on distinct activities.

# MANAGEMENT AND ADMINISTRATIVE ISSUES

The recruitment of a Chief of Party will be conducted during the quarter as well as National Officers that will provide support to project implementation

# Budget

# LESSONS LEARNED

Given that the project is transitioning to phase to a more focussed approach on the socio-economic inclusion of transgender and gender diverse persons, time should have been allocated for an inception phase to allow for staff recruitment and contracting CSOs.

# PLANNED ACTIVITIES FOR NEXT QUARTER INCLUDING UPCOMING EVENTS

Barbados

- Finalise recruitment and onboarding of National Project Coordinator.

- Finalise Implementing Partner Agreement with local CSO.

- Support regional study (Barbados, Guyana, and Jamaica) on transwomen accessing social protection programmes.

Dominican Republic

- Finalise recruitment and onboarding of Chief of Party and National Project Coordinator.

- Finalise Implementing Partner Agreement with local CSO.

- Support national study on transwomen accessing labour markets and social protection programmes.

Guyana

- Finalise recruitment and onboarding of National Project Coordinator.

- Finalise Implementing Partner Agreement with local CSO.

- Support regional study (Barbados, Guyana, and Jamaica) on transwomen accessing social protection programmes.

Jamaica

- Finalise recruitment and onboarding of National Project Assistant.

- Finalise Implementing Partner Agreement with local CSO.

- Support regional study (Barbados, Guyana, and Jamaica) on transwomen accessing social protection programmes.

# How IMPLEMENTING PARTNER has addressed A/COR comments from the last quarterly OR Semi-annual report

Not Applicable

Information retrieved until September 30th, 2023.

Accounts reached: number of accounts that have seen the content at least once.

Accounts engaged: number of accounts that have interacted with the content.