






Project Progress Report (2023 version)


Name of Project: Enabling China to Prepare Its Fourth National Communication, and Biennial Update Reports on Climate Change

Date of report: 11/30/2023



A. PROJECT PROFILES

	Quantum Project ID
	110698

	Project overall duration
	48 months

	Location(s)
	China

	Implementing partner
	Foreign Environment Cooperation Center (FECO), Ministry of Ecology and Environment (MEE)

	Responsible party (if any)
	Ministry of Ecology and Environment (MEE)

	UNDP Programme Officer
	Liu Shijun



	Gender Marker (GEN 1/2/3)
	GEN 2

	Relevant CPD 2021-2025 output
	Output 2.4: Capacity of target government bodies enhanced to reduce environmental footprint at targeted areas.
	Relevant SP output
	Output 2.1.1  Low emission and climate resilient objectives addressed in national, sub-national and sectoral development plans and policies to promote economic diversification and green growth 


Guidance. Please ensure data below are in line with the UNDP Quantum system.

	Annual budget
	USD 1,414,152

	Expenditure (to date)
	USD 1,250,000

	Delivery rate (to date)
	88%
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B. RESULTS

B.1 Results Towards the Annual Work Plan

Guidance.
· On the “Project outcome/output statement”, please stick to those project outcomes and outputs stated in the AWP. The reporting should be based on the first level of the structure.
· On the “Result, backed up by evidence and segregated data” columns, please focus on the results of the project (instead of the “process”) with credible evidence and segregated data. The report should also focus more on gender equality and women empowerment, digitalization, innovation and partnerships, as applicable.
· On the “Indicator” section, please stick to the the indicators, baselines, and final targets from the AWP, and provide the actual level.
	Project outcome/output statement
	Results, backed up by evidence and segregated data
	Indicator
	Baseline Level
	Level as of end-2023
	Annual Target Level

	Outcome 1.1 Clearer understanding of the magnitude and sources of the GHG emissions and removals from the different sectors. 
	e.g. In August and September 2023 the project has organized two thematic training & sharing sessions in AAA city of BBB province, respectively focusing on Youth Entrepreneurships, and Capacity Building On E-Commerce. Altogether 1400 local participants (47.8% female) joined these sessions. The presenters were from ZZZ University and YYY private sector, etc.

Based on the pre and post training sessions, it is observed 83% attendees found the Capacity Building on E-Commerce more useful. Against the pre-training baseline survey, the capacities of entrepreneurships, and E-Commerce were improved by 34%. For more details of the survey result see the Annex 1.
	No. of completed GHG inventories that are used in the preparation of the NC and BURs.

No. of updated yearly data sets uploaded to the National GHG Emissions Database and used in the preparation of the NC and BURs.

No. of governmental entities that are capable of producing acceptable and useful time series of sectoral GHG emissions applying 2006 IPCC guidelines.

No. of trained GOC agencies that regularly collect, update, analyze and report required data and analytical information used for conducting and preparing GHG inventories.
	5





5
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	Output 1.1.1 National GHG Inventories 2017 and 2018 for the 4NC and 3BUR with recalculation of historic GHG inventories applying IPCC 1996 guidelines.
	
	
	
	
	

	Output 1.1.2 National GHG Inventory 2020 for the 4BUR with recalculation of historic GHG inventories applying 2006 IPCC guidelines.
	
	
	
	
	

	Output 1.1.3. Improved national GHG inventory database system and updated inventory database.
	
	
	
	
	

	Output 1.1.4. Improved national system and mechanism for a sustainable GHG data collection, preparation and archiving process with extensive stakeholder engagement, smooth and timely data collection and coordinated and effective organization.
	
	
	
	
	

	Output 1.1.5 Completed capacity building of relevant government departments in collecting required data and information for conducting and preparing GHG inventories.
	
	
	
	
	

	Outcome 2.1 Better understanding of China’s vulnerability to the threats of climate change and improved accuracy of prediction of impacts in the vulnerable sectors of the country.
	Activities for delivering this output were started in June 2023, and finished mid-term report of "Updated analysis report on China's climate change characteristics and future trends". The historical climate change and spatiotemporal distribution in the past century, and future climate change under different scenarios, changes in extreme climate events were included in the report.
Activities for delivering this output were started in June 2023, and finished mid-term report of "The impact of climate change, vulnerability assessment report”. The observed and projected impacts of climate change on agriculture, water resources, terrestrial ecosystems, coastal zone and human health were included in the report.
Activities for delivering this output were started in June 2023, the analysis results of frequency and intensity of extreme climate events and climate change related disasters were included in the “Updated analysis report on China's climate change characteristics and future trends”. The impacts of extreme climate events were include in “The impact of climate change, vulnerability assessment report”.
Compared the main contents of Adaptation Strategy 2020 and Adaptation Strategy 2035, collected and sorted out the adaptation strategies and goals in various fields since the 13th Five Year Plan, analyzed the policies and actions to adapt to climate change since the 13th Five Year Plan, and formed the first draft of the Analysis and Research Report on the Effectiveness of Implemented Adaptation Actions.
	No. of governmental entities that are capable of producing improved climate change vulnerability and adaptation assessments and improved formulations of climate change adaptation measures and plans.
	1
	2
	2

	Output 2.1.1 Results of the updated analyses of climate change characteristics and future trends in China.
	
	
	
	
	

	Output 2.1.2 Report on the climate change impact and vulnerability assessments in agriculture, water resources, coastal zones, terrestrial ecosystems, human health.
	
	
	
	
	

	Output 2.1.3 Report on the impacts of the frequency and intensity of extreme climate events and climate change related disasters.
	
	
	
	
	

	Output 2.1.4 Report on the effectiveness analysis on implemented adaptation actions.
	
	
	
	
	

	Output 2.1.5 Completed capacity building for relevant government departments on collecting climate data/information and assessment of climate change impact and vulnerability.
	
	
	
	
	

	Outcome 3.1 Enhanced understanding of the appropriate policies to enable the proper planning and implementation of prioritized applicable and feasible climate change mitigation (CCM) actions for China.
	The first draft of Report on "Compilation of a Review of National Climate Change Mitigation Policies and Measures" for the Global Environment Facility's Capacity Building Project on China's Preparation for the Fourth National Communication and Biennial Update Report on Climate Change is completed. In the draft, documents on implemented national climate change mitigation policies and actions from multiple departments and fields in Chin are collected, organized, and analyzed from the perspective of climate change. According to the requirements of the implementation of the United Nations Framework Convention on Climate Change, systematically prepare information on policies and actions to mitigate climate change in the required reports, in order to enhance the understanding of stakeholders on these policies and actions, promote the identification of opportunities for mitigating climate change, and deploy strategic guidelines for green investment.
	No. of formulated and recommended new or improved national CCM policies and feasible CCM actions plans.
	0
	1
	1

	Output 3.1.1 Summary of national CCM policies and measures.
	
	
	
	
	

	Outcome 3.2 Improved accounting of the results and impacts of implemented CCM actions through an improved national MRV system.
	Activities for delivering this output were started in January 2023 and the mid-term evaluation of progress was accomplished in November 2023. The mid-term deliverable was officially reviewed and accepted in November 2023, with the detailed information as follows:
· The final report named “Research on the refined methodology and related assumptions for assessing the impact and estimated emission reduction of CCM actions” in Chinese was developed and delivered. 
· This report includes a thorough review of the methodologies adopted for assessing the mitigation actions and their effects in previous China’s BURs, key lessons learned from the Annex I and Non-Annex I Parties regarding the progress assessment methodologies, and the development of refined methodology and related assumptions based on China’s CCM actions.
· An expert review meeting was arranged and results of the study was approved. 
The first draft of Report on the Optimization of China's Monitoring, Reporting, and Verification (MRV) System for the Preparation of China's Fourth National Communication on Climate Change and Biennial Update Report Capacity Building Project by the Global Environment Facility is completed. In the draft, the current status of China's existing greenhouse gas monitoring, reporting and verification system are collected, organized, and analyzed from the perspective of climate change. The information on the monitoring, reporting, and verification system is systematically updated in accordance with the requirements of the United Nations Framework Convention on Climate Change. The progress of national independent contribution is estimated to improve China's transparency in addressing climate change. 
Activities for delivering this output were started in January 2023 and the mid-term evaluation of progress was accomplished in November 2023. The mid-term deliverable was officially reviewed and accepted in November 2023, with the detailed information as follows:
· The first draft of the report named “Research on impact assessment and emission reduction estimation of implemented CCM actions” in Chinese was developed and delivered. 
· This report includes China’s low-carbon development status analysis, a review of China's CCM actions, and impact assessment and emission reduction estimation of implemented CCM actions of China using the refined methodology and related assumptions.
· An expert review meeting was arranged and results of the study was approved.
	No. of governmental entities that can capably report evidence-based GHG emission reduction data using the country’s official MRV system.
	7
	32
	32

	Output 3.2.1 Refined methodology and related assumptions for assessing the impact and estimated emission reduction of CCM actions.
	
	
	
	
	

	Output 3.2.2. Report on the completed improvements in, and the operational performance of, the country’s measurement, reporting and verification (MRV) system.
	
	
	
	
	

	Output 3.2.3. Completed capacity building for relevant government departments on assessment of the effectiveness of implemented CCM policies.
	
	
	
	
	

	Output 3.2.4. Completed impact assessment and emission reduction estimation of implemented CCM actions.
	
	
	
	
	

	Outcome 4.1 Enhanced capacity to determine, analyze, refer to, and articulate key national circumstances information in the national communication (NC) reports and biennial update reports (BUR).
	Activities for delivering these outputs were started in Jun. 2023. During the past 6 months, communication with governmental entities, literature research, data collection and selection, etc. was carried out, to draft Overview Of National Circumstances and Institutional Arrangements in China, which got approval from the MEE.
	No. of governmental entities that are substantially involved and/or contributing to the performance of analyses of the various in-country factors that affects and impacts on the climate and climate change situation in the country as articulated in the NC Reports and BURs
	2
	30
	30

	Output 4.1.1 Completed sets of vetted data/information on each pertinent indicator (e.g., natural resources, energy, environment, social and economic) that collectively characterize the country’s national circumstances
	
	
	
	
	

	Outcome 4.2 Enhanced understanding and capacity to determine applicable, feasible and cost-effective CCM and climate change adaptation (CCA) technologies, techniques and measures, and the most suitable financial resources and financing options that can be applied to implement action that address CCM and CCA issues.
	
	No. of governmental government entities that are capable of:
•Identifying, assessing, planning, designing, implementing: 
•Identifying and sourcing financing for the implementation of:
•Gathering, processing, storing, managing:
Feasible and applicable CCM & CCA technologies, techniques, and measures.
	3
	
	

	Output 4.2.1. Report on capacity-building needs for the identification and determining applicable, feasible and cost-effective CCM&CCA technologies, techniques, and measures.
	
	
	
	
	

	Output 4.2.2. Report on capacity needs for determining financial resources and financial options for the implementation of appropriate CCM&CCA technologies, techniques, and measures.
	
	
	
	
	

	Outcome 4.3 Further enhanced public awareness of climate change issues.
	The observation and monitoring status of climate system in China was investigated and documented, including components of atmosphere, ocean, biology, water resources, and cryosphere. Observations and monitoring on GHG concentration are also described in the report, as part of atmospheric observations.
	No. of people that have improved understanding of the climate change issues of the country. climate and weather forecasts for China.
	0
	
	

	Output 4.3.1. Completed document on the results, conclusions, and recommendations of the implemented activities for enhancing public awareness about climate change issues.
	
	
	
	
	

	Output 4.3.2. Completed report on GHG concentration, climate observation and monitoring in China.
	
	
	
	
	

	Output 4.3.3. Completed capacity building for relevant government departments on collecting information and in assessing technologies, and financing of technology applications.
	
	
	
	
	

	Outcome 5.1 Better understanding of GHG emissions and sinks in the Hong Kong and Macao SARs, and improved capacities for NC, and BUR.
	[bookmark: OLE_LINK1]By the end of 2023, Hong Kong and Macao SARs have prepared and submitted relevant parts of 4NC and 3BUR to central government, which include GHG inventories 2017 and 2018, vulnerability and adaptation assessments and improved formulations of CCM and CCA measures and plans.
	No. of SAR agencies that are capable of producing improved GHG inventories, vulnerability and adaptation assessments and improved formulations of CCM and CCA measures and plans.

Progress towards completion, SAR government-approval, and submission of reports to P.R. China, % completion.
• 4NC
• 3BUR
• 4BUR

	0












0
0
0
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100%
100%
0
	2












100%
100%
0

	Output 5.1.1. Completed workshops on coverage and implementation of Hong Kong and Macao SARs' GHG inventories for the year 2017, 2018 using the IPCC 1996 guidelines, and 2020 utilizing the IPCC 2006 guidelines.
	
	
	
	
	

	Output 5.1.2. Completed workshops on assessment methodologies for Hong Kong and Macao SARs’ mitigation actions.
	
	
	
	
	

	Output 5.1.3. Completed chapters of Hong Kong and Macao SARs’ NC and BUR in the 4NC Report, 3BUR, 4BUR.
	
	
	
	
	

	Output 5.1.4. Updated GHG inventories in the Hong Kong and Macao SARs for years 2017, 2018, and 2020.
	
	
	
	
	

	Output 5.1.5. Updated supplementary information on climate change in the Hong Kong and Macao SAR's.
	
	
	
	
	

	Outcome 6.1 China’s compliance to the reporting obligations to the UNFCCC.
	4NC and 3BUR have been complied and submitted to the State Council for approval
	No. required reports prepared, translated and submitted to UNFCCC.
	5
	5
	5

	Output 6.1.1. Improved working mechanisms for the preparation of the required reports UNFCCC (4NC, 3BUR, 4BUR) reporting.
	
	
	
	
	

	Output 6.1.2. Completed capacity building of relevant departments participating in the report preparation.
	
	
	
	
	

	Output 6.1.3. Finalized and submitted 4NC, 3BUR, 4BUR (Chinese & English) to the UNFCCC.
	
	
	
	
	






B.2 Project Impact

Guidance: It is crucial to maintain a broader perspective that connects the dots between overall project activities, outputs, outcomes, and impact. In Section B.2, please go beyond discussing immediate activities and focus on the long-term impact of the project. Use 1-2 paras (more are welcome) to discuss (a) how this project have contributed to broader societal, economic, or environmental goals, and/or (b) how the project informs policy-making process in China and/or (c) how it contributes to national and local priorities, etc.


According to the latest IPCC Assessment report,  science has made great strides recently in determining which potential causes are actually responsible for the climate change that occurred during the twentieth century, providing strong evidence that greenhouse gas (GHGs) released to the atmosphere by human activities are the main cause of contemporary global warming.
The least developed provinces and regions in China are often the most affected by climate change. In these areas both the government and the people need to increase the capacities to cope with the potential climate disasters. It is reasonably foreseeable to improve the ability of local people to adaptation, so to minimize the adverse effects of climate change.

To achieve the objective of the Convention and fulfill the obligation of the Parties, China needs to collect and report reliable, transparent and comprehensive information on GHG emissions, climate actions and support (Article 12). By communicating information on GHG emissions and actions to reduce them, as well as on adaptation and means of implementation such as finance, technology transfer and capacity-building, the transparency and reporting system allows to understand ambition and progress on climate actions and support by Parties and informs the COP deliberation and guidance on these matters. The reporting requires China to submit timely national reports , in accordance with the principle of common but differentiated responsibilities and respective capabilities.

The project will enhance China’s capability to prepare and deliver time-series consistent national GHG inventories every two years, applying 2006 IPCC guidelines with higher transparency, increased completeness and accuracy and stronger comparability. A normalization mechanism for GHG inventories and reporting will be established. It will enable China to strengthen and update the impacts and vulnerability assessments of climate change and combine with emissions scenario analysis of policies and actions for climate change mitigation. It will enable China to have a reliable NAMAs and NDCs tracking systems to fulfill the obligations of NCs and BURs. It will enhance the stakeholders’ understanding of the appropriate policies to enable the proper planning and implementation of prioritized applicable and feasible climate change mitigation actions for China low GHG development.


C. RISK

Guidance.
· Please populate the offline matrix with those risks as identified on the pro doc, and update the status. Please bring in or strike out a risk, if it’s recently found or addressed. Be sure to distinguish “cause”, ‘’event”, “impact”. i.e. Because of [cause], [event] may occur, which would lead to [impact].
· Following the finalization and submission of this report, UNDP Programme Officer shall update the risks in Quantum.

	#
	Category

	Cause
	Event
	Impact
	Risk Valid
 Period
	Risk Level - Impact &
Likelihood
	Treatment(s)
	Risk Owner

	
	Primary Category: 
Social and Environmental Financial, Operational Organizational, Political Regulatory Strategic, Other

	A brief description of what could cause the potential event.

	A brief description of the potential future event. The occurrence or change of a particular set of circumstances. 

	A brief description of the potential impact of the event. The totality of all effects of an event affecting objectives.

	When does this risk valid from and when does it valid to?

	Indicate the level of impact and likelihood of the risk 

Enter Impact (I) and Likelihood (L) on a scale from 1 (low) to 5 (high)  e.g. I = 1; L = 3
	What actions have been taken/will be taken to counter this risk? What is the current status of this treatment (Not Started, On Going, Completed)? When is the anticipated completion date?

	Who has been appointed to keep an eye on this risk?



	Ongoing
	Social and Environmental

	Project activities might not be implemented in a gender- sensitive manner  
	Women are not able to increase their participation in decision-making on project activities and have equal access to work.

	Exacerbate gender inequality and lead to women's unemployment. 
	from 01/01/2023 to 31/12/2023
	I =3
L =1
	· { On Going , Dec 31 2023}  The project could potentially offer a wide range of opportunities, for individuals and groups get trained in capacity development program activities, to be hired as a consultant or contractor for the project implementation. If care is not taken, any existing discrimination in the country towards woman could continue to come to play through the project.
· { On Going , Dec 31 2023} Special measures to ensure that any potential discrimination against women in the implementation of the project is countered have been identified and included in the project design. The results of such measures will be observed during project implementation, and if any corrective action is necessary, this will be addressed. Beyond that, the PMO will make special efforts to explore and facilitate the inclusion of interventions to enhance the role of women. Special activities have been designed to involve women, e.g., in the productive use of RE activities, to have strong representation of women in training courses and seminar-workshops, and to ensure a significant proportion of project consultants are women.
· { On Going , Dec 31 2023} Regarding the gender-equitable hiring process, the project proponent and implementing partner will carry out adequate and conscientious planning and implementation of project-related procurement activities. This involves the preparation and implementation of appropriate procurement plans for the employment of all qualified and capable people, while ensuring that proper government procurement and labor laws/regulations will be applied and complied with.
	MEE

	2
	Strategic

	Inadequate and possibly constrained coordination during the implementation of the project.
	Cooperation and coordination between departments and teams were not close enough, resulting in slow progress or even delays in projects.

	Inability to complete and submit compliance reports in accordance with the project implementation plan
	from 01/01/2023 to 31/12/2023
	I = 4
L = 3

	· { On Going , Dec 31 2023} MEE and the project management unit shall maintain close working relations with relevant departments of the State Council and make necessary adjustments to the work in a timely manner according to the adjustment of national policies, which can ensure the implementation of the project and achieve optimal results. In case this happens, MEE will facilitate discussions with project stakeholders and relevant government authorities through the project steering committee (PSC) to come up with decisions on the coordinated implementation of the agreed barrier removal activities.
	MEE

	[3]
	Operational 

	Incomplete activity level data for the preparation of national GHG requisitions
	Lack of access to activity level data for national inventory preparation and use of the IPCC 2006 version of the methodology to account for GHG emissions
	Difficult to submit the reports in a timely manner.
	from 01/01/2023 to 31/12/2023

	I = 4
L =2

	· { On Going , Dec 31 2023} China intends to submit the GHG inventory of the year 2017, 2018 and 2020. According to the requirements of UNFCCC, the chosen reporting year in NCs shall not be 4 years earlier than the submission year. Therefore, the preparation is under time pressure and involves heavy work. 
	MEE

	[4]
	Social and Environmental

	The project implementation would be affected in case the epidemic breaks out
	Inability to carry out normal project activities, such as seminars and face-to-face exchanges
	Failure to promote the project affected by the epidemic
	from 01/01/2023 to 31/12/2023

	I = 3
L = 3

	· { On Going , Dec 31 2023} The project will always pay attention to the impact of the epidemic on the implementation of the project. When necessary, the project will carry out the socio-economic impact assessment of the impact of the epidemic on the progress of the project, and promote the implementation of the project according to the plan through various means, such as online meeting, telephone, etc.
	MEE



Guidance. please provide details on incorporation of gender perspectives in various aspects of project management. Please provide quantitative data, qualitative case studies and success stories whenever necessary to illustrate the most significant contributions to gender equality.

Please choose the Gender marker rating of this project: ☐GEN-3; ☒GEN-2; ☐GEN-1

	Outputs 

	1
	Please describe all activities undertaken within this project during the reporting year that directly or indirectly contributed to the advancement of women’s empowerment and gender equality. This may include initiatives promoting women's economic empowerment, enhancing women's decision-making capacities, and changing the harmful gender bias and stereotypes, etc.
	Female participants are especially encouraged in workshops, seminars, training activities.
In  each training session it’s required to arrange at least one section to address women specific topic or demand in the training agenda.

	Outcomes

	Please elaborate on the contributions and impacts this project has made to ONE or MULTIPLE relevant Gender Equality Strategy 2022-2025 priority areas of work[footnoteRef:2] during the reporting year. Please provide relevant evidence to support the claims. [2:  Please refer to UNDP Gender Equality Strategy 2022-2025 for more details: https://genderequalitystrategy.undp.org/#] 


	2
	Promote women’s economic empowerment, employment, and access to resources, and diminishing the structural barriers in economies that keep women behind.
	Promote women’s economic empowerment, employment, and access to resources, and diminishing the structural barriers in economies that keep women behind.

	3
	Support the incorporation of gender considerations into local economic and social development plans, accelerate women’s equal representation in local governance, especially in rural areas.
	Support the incorporation of gender considerations into local economic and social development plans, accelerate women’s equal representation in local governance, especially in rural areas.

	4
	Support building gender-responsive resilience to a wide range of shocks and crises, including conflict, climate change, disasters, environmental degradation and epidemics.
	Support building gender-responsive resilience to a wide range of shocks and crises, including conflict, climate change, disasters, environmental degradation and epidemics.

	5
	Support women’s improved access, use, and control of resources, and enhance women’s participation and leadership role in climate action.
	n/a

	6
	Promote gender equality in green energy systems, policies, decision-making and ownership, as well as at the technical and service provision levels.
	When reviewing and assessing project outcomes including developed reports, policies and achievement of demonstration projects, female consultants are prioritized to be invited to form the expert panel.  

	7
	Raise awareness on gender equality and challenge the gender stereotype and biased social norms that limit women’s equal rights and opportunities
	

	Resources Allocation

	8
	How much of the annual project budget/resources has been allocated to address the identified needs of women and men? If no investment has been made, does the project plan to increase project investment to support women’s empowerment and gender equality?
	No concrete budget is allocated, but gender equality & empowerment is always the concern when organizing project activities, and we are endeavored to promote the participation and decision making involvement of female stakeholders.

	Challenges & Lessons Learned

	9
	What are some key challenges/potential risks faced by the project in (further) promoting women's empowerment and gender equality? What are the possible mitigation measures the project will adopt to tackle those challenges?
	N/A

	Knowledge Management

	10
	Have success story(ies) of female beneficiaries have been featured and shared as examples of the project’s key achievement in promoting women’s empowerment and gender equality? Are both women and men represented and visible in the communication products?
	N/A



E. COMMUNICATION AND VISIBILITY

Guidance. Please provide URLs specific to this project (for example, project websites, social media sites, media coverage, etc.) as far as this is applicable. Note that some of these links would be the evidence and data sources for Section B above.

	#
	Details of communications activities
	Date
	External link (if applicable)

	1
	Inception workshop 
	11/18/2022	http://www.fecomee.org.cn/dtxx/xwdt/202211/t20221124_1006037.html

	2
	
	Click or tap to enter a date.	

	[+]
	
	Click or tap to enter a date.	



F. LESSONS LEARNED AND WAY FORWARD

F.1 Lessons Learned

Guidance. Describe any lessons that will be applied to address challenges or improve the implementation pace. Outline any good practices, as applicable.


F.2 Way Forward

Guidance. List key issues which need to be followed up and addressed for the next reporting period.

	#
	Issue/observation
	Action to be taken
	Responsible
	Timeline

	1
	Ensured that the work under each subcontract be completed in timely manner
	Regular communication and coordination of supervision and management
	FECO and Subcontractor
	Completion in accordance with the contract execution period

	2
	Hold various seminars as appropriate to promote the smooth implementation of project
	Report regularly to MEE on the progress of the project.
	FECO
	Carry out work according to MEE's work requirements.

	[+]
	
	
	
	



G. ANNEXES

Guidance. Include any detailed project information here, e.g. meeting minutes, detailed action plan, agreement signed, etc. Chinese version is also acceptable. 
image1.png
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Resilient nations.




