United Nations Development Programme

| Project title: Climate Change Adaptation in the Lowland Ecosystems of Ethiopia |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country: Ethiopia | Implementing Partner: Environment, Forest and Climate Change Commission |  |  |  |  | Management Arrangements : National Implementation Modality (NIM) |
| UNDAF/Country Programme Outcome 3: By 2025, all people in Ethiopia live in a society resilient to environmental risks and adapted to climate change. |  |  |  |  |  |  |
| UNDP Strategic Plan Output: Output 1.4: Scaled up action on climate change adaptation and mitigation across sectors which is funded and implemented |  |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Project ID (formerly Award ID): 00116829 |  |  |  | Atlas Output ID (formerly Project ID): 00113814 |  |  |
| UNDP-GEF PIMS ID number: 5630 |  |  |  | GEF ID number: 9303 |  |  |
| Planned start date: January 2021 |  |  |  | Planned end date: January 2027 |  |  |
| PAC meeting date: 26 October 2020 |  |  |  |  |  |  |
| Expected date of Mid-Term Review: November 2023 |  |  | Expected date of Terminal evaluation: November 2026 |  |  |  |
| Brief project description: Ethiopia is among the most vulnerable countries on the African continent. Small-holder farmers, agro-pastoralists and pastoralists; in the Ethiopian lowland ecosystem are particularly and increasingly vulnerable to climate change. They view climate change as a threat that has resulted in food insecurity and dependence on food aid, but at the same time have limited awareness of the long-term risks that climate change poses and are not familiar with climate smart solutions to build their resilience and adaptive capacity. Due to lack of weather information for the short, medium and long-term and limited knowledge of adaptation measures, land users follow unsustainable, climate sensitive livelihood practices. As it currently stands, generating, interpreting, packaging and disseminating credible and timely weather and climate forecasts is challenging and faced with capacity limitations. Lack of access to timely and credible weather and climate forecasts has left land users with no option except to rely on traditional methods of weather prediction, which has proved ineffective in the context of a changing climate. The land users in the lowland ecosystems are resource-poor and their low income means they are unable to make investments and take on risks. In particular, the pastoralists in the lowland ecosystem areas of Somali and Afar regions have their daily livelihood challenges being manifested by the constant need to cope with climate change impacts like food, livestock grazing and water shortages, in addition to migration from internal displacement among others. Moreover, because the main resources in the lowland ecosystem of Ethiopia are controlled by men; women rarely participate in decision-making and their contributions in building resilience and adaptive capacity are seldom recognized. The decrease in food in times of drought has affected human health especially children under five years, pregnant women and the elderly, and reduced immunity and productivity. Under the baseline situation, the land users are taking actions to cope with climate change and related hazards. However, not all the current coping strategies are effective in serving the long-term adaptation needs. These coping strategies are based on short-term considerations, survival needs, and lack of information or imperfect foresight; leading to mal-adaptation. There is limited support tailored to the needs of land users to maintain and diversify their livelihoods while adjusting to climate change, moderating or coping with the impacts, and taking advantage of the opportunities that may come along with climate change. Consequently, the pathways and solutions to design and implement a range of interventions for the attainment of poverty reduction and food security goals while reducing the cost of climate change are still scant and scattered. Land users across the Ethiopian lowland ecosystems therefore are still at risk to climate-change threats and have faced several barriers to effectively reduce and manage the adverse impacts of climate change. This proposed LDCF project intends to strengthen the ability of land users to adapt to the discernible impacts of climate change through i) disseminating credible weather information and advisory services using locally suitable communication channels to inform the preparation and implementation of actions meant for building resilience and adaptive capacity at a watershed level; ii) reaching a wider audience of land users and government stakeholders across the lowland ecosystem of Ethiopia through a Training-of-Trainers (TOT) approach, iii) conducting a “learning by doing” training to promote clarity and commitment of land users and iv) providing needs responsive support to diversify livelihood options in a way that leads to tangible and replicable changes. The full and effective implementation of this project will deliver the following benefits to vulnerable communities in twelve Woredas across the six regions: i) increased understanding of key adaptation issues, including community-based adaptation techniques as a basis for incorporating climate smart technologies and good practices through a practical learning-by-doing approach; ii) enhanced capability to respond to ongoing and emerging threats through the development of climate adaptive action plans by utilizing early warning, downscaled weather information and climate change knowledge products and iii) enhanced capacity of land users to create, improve and sustain diversified livelihood options at the same time as rehabilitating degraded watersheds. |  |  |  |  |  |  |
| Financing Plan (cash transferred to UNDP and budgeted under this LDCF project) |  |  |  |  |  |  |
| LDCF |  |  |  | USD 5,836,073 |  |  |
| UNDP TRAC resources |  |  |  | USD 200,000 |  |  |
| Cash co-financing to be administered by UNDP |  |  |  | - |  |  |
| - Total Budget administered by UNDP |  |  |  | USD 6,036,073 |  |  |
| Parallel co-financing (all other co-financing that is not cash co-financing administered by UNDP) |  |  |  |  |  |  |
| Government |  |  |  | USD 10,250,000 |  |  |
| - Total co-financing |  |  |  | USD 10,250,000 |  |  |
| - Total Project Financing (1) + (2) |  |  |  | USD 16,286,073 |  |  |
| Signatures |  |  |  |  |  |  |
| Signature: print name below |  | Agreed by Government |  |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by Implementing Partner |  |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by UNDP |  |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	4

II.	Development Challenge	7

III.	Strategy	11

IV.	Results and Partnerships:	18

V.	Project Management	31

VI.	Project Results Framework	33

VII.	Monitoring and Evaluation (M&E) Plan	35

VIII.	Governance and Management Arrangements	39

IX.	Financial Planning and Management	44

X.	Total Budget and Work Plan	46

XI.	Legal Context	56

XII.	Risk Management	57

Annex A:  Multi Year Work Plan	60

Annex B:  GEF Tracking Tool at baseline	65

Annex C:  Overview of Technical Consultancies	68

Annex D: Terms of Reference	70

Annex E:  UNDP Social and Environmental Screening Procedure and plans as needed	76

Annex F:  Stakeholder Engagement Plan	85

Annex G: Gender Analysis and Action Plan	88

Annex H:  UNDP Risk Log	92

Annex I:  Results of the capacity assessment of the project implementing partner and HACT micro assessment	96

Annex J: Theory of Change	97

Annex K: List of Stakeholders Consulted during the PPG Phase	99

Annex L: Tentative Lists of Activities proposed for project outputs	104

Annex M: Co-finance letters	106

List of Acronyms and Abbreviations:

| AWS | Automatic Weather Stations |
| --- | --- |
| CBE | Community Based Enterprise |
| CBO | Community-based Organisation |
| CCA | Climate change adaptation |
| CIRDA | Climate Information for Resilient Development in Africa |
| CO | Country Office |
| COA | Country Operations Assistant |
| CRGE | Climate Resilient Green Economy |
| CSA | Climate-smart agriculture |
| DCD | Deputy Country Director |
| DFID | Department for International Development |
| DRR | Deputy Resident Representative |
| EFCCC | Environment, Forest and Climate Change Commission |
| EIA | Environmental Impact Assessment |
| EIAR | Ethiopian Institute of Agricultural Research |
| EPACC | Ethiopia’s Programme of Adaptation to Climate Change |
| ERC | Evaluation Resource Centre |
| ESIA | Environmental and Social Impact Assessment |
| ESMP | Environmental and Social Management Plan |
| ESSP | Ethiopia Strategy Support Program |
| EWS | Early Warning System |
| EWSP | Ethiopian Water Sector Policy |
| FAO | Food and Agriculture Organisation |
| FNC | First National Communication |
| FSP | Full Sized Project |
| GCF | Green Climate Fund |
| GDP | Gross Domestic Product |
| GEF | Global Environment Facility |
| GIS | Geographic Information Systems |
| GEFSEC | Global Environment Facility Secretariat |
| GoE | Government of Ethiopia |
| GM | Global Mechanism |
| GTP | Growth and Transformation Plan |
| HABP | Household Asset Building Programme |
| HACT | Harmonized Approach to Cash Transfer |
| IEO | Independent Evaluation Office |
| IFPRI | International Food Policy Research Institute |
| INDC | Intended Nationally Determined Contribution |
| IP | Implementing Partner |
| KM | Knowledge Management |
| LDC | Least Developed Country |
| LDCF | Least Developed Country Fund |
| LOA | Standard Letter of Agreement |
| M&E | Monitoring and Evaluation |
| MDG | Millennium Development Goal |
| MEA | Multi-lateral Environmental Agreement |
| MoANR | Ministry of Agriculture and Natural Resources |
| MoEF | Ministry of Environment and Forest |
| MoFEC MoH | Ministry of Finance and Economic Cooperation Ministry of Health |
| MoWIE | Ministry of Water, Irrigation and Electricity |
| MSP | Medium Sized Project |
| MTR | Mid-Term Review |
| NAP | National Action Programme |
| NAPA | National Adaptation Programme of Action |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NGO | Non-Governmental Organisation |
| NIM | National Implementation Modality |
| NMA | National Meteorology Agency |
| NPSDRM | National Policy and Strategy on Disaster Risk Management |
| NPSC | National Project Steering Committee |
| OFP | Operational Focal Point |
| ORDA | Organisation for the Rehabilitation and Development of Amhara |
| PAC | Project Appraisal Committee |
| PFAA | Project Finance and Administrative Associate |
| PIF | Project Identification Form |
| PIMs | Project Implementation Manuals |
| PIR PM | Project Implementation Report Project Manager |
| PMC PMU | Project Management Cost Project Management Unit |
| POPP | Programme and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| PRODOC | Project Document |
| QA | Quality Assurance |
| RA | Regional Administration |
| ROAR | Results Orientated Annual Report |
| RR | Resident Representative |
| RTA | Regional Technical Adviser |
| SBAA | Standard Basic Assistance Agreement |
| SDGs | Sustainable Development Goals |
| SDPRP | Ethiopia’s Sustainable Development and Poverty Reduction Programme |
| SESA | Strategic Environmental and Social Assessment |
| SESP | Social and Environmental Screening Procedure |
| SLM | Sustainable Land Management |
| SLMP | Sustainable Land Management Programme |
| SNC | Second National Communication |
| SNNPR | Southern Nations, Nationalities and Peoples’ Region |
| SSTrC | South-South and Triangular Cooperation |
| STAP | GEF Scientific Technical Advisory Panel |
| SWC | Soil and Water Conservation |
| TBWP | Total Budget and Workplan |
| TE | Terminal Evaluation |
| TM | Task Manager |
| ToC | Theory of Change |
| TOR | Terms of Reference |
| TRAC | Thematic Resources Assigned from the Core |
| UN | United Nations |
| UNCCD | United Nations Convention to Combat Desertification |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |
| UNDP-GEF | UNDP Global Environmental Finance |
| UNFCCC | United Nations Framework Convention on Climate Change |
| UNOPS | United Nations Office for Project Services |
| USAID | United States Agency for International Development |
| WFP | World Food Programme |
| WPO | Woreda Project Officer |
| WSC | Woreda Steering Committee |

# Development Challenge

Ethiopia has the second largest population of 102 million (2016) in Africa, making it the second most populous nation in the continent, after Nigeria. Ethiopia’s economy has grown rapidly primarily as a result of increased agricultural production. The agricultural sector in Ethiopia – which accounts for more than 80% of total employment and 45% of the country’s GDP is dominated by smallholder farmers, agro-pastoralists and pastoralists, (here referred to as “Land users”) that rely on rainfall and traditional farming practices. Current practices of cultivating crops and overgrazing of livestock contribute towards large-scale land degradation. Deforestation is taking place at a rate of about 140,000 hectares per year in Ethiopia.

At the national level, temperatures have increased by an average of around 1°C since the 1960s. Rainfall is subject to high variability between years, seasons and regions. Yearly variation around mean rainfall level is 25% and can increase to 50% in some regions. Extreme climate events are also common, particularly droughts and floods. Floods and droughts have resulted in severe losses of crops and livestock, leading to food insecurity. The economic impact depends on the extent of the variability and extreme events but droughts alone can reduce total GDP by 1% to 4%.

The rain in the lowland ecosystem of Ethiopia has often started later than expected over the last decade and has been mostly inadequate and unreliable. In many places water scarcity has increased. The unavailability of water imposes higher demands on women’s and girls’ time which would have otherwise been spent on other productive and human development activities. According to the views of land users, in 2018 alone, women and girls walked an average of 6kms a day to collect water. This is significant considering that the twelve woredas being targeted by this project consist of an estimated population of 600,000 people (or 120,000 households) and, according to the records of the concerned woreda administration offices, women represent about 49% of this population.

The land users rely on rain-fed agriculture and their crop production system has been buffeted by acute shocks related to climate. This has made it more difficult for them to grow crops or raise animals in the same way they have been doing. They stated that rain has been erratic, and when it comes it is too much and destroys their crops. They are now questioning the suitability of agriculture as an occupation in view of changing climatic conditions. The lowland ecosystem of Ethiopia is also home to significant livestock population which is characterized by low productivity, poor nutrition, low veterinary care and uncontrolled overgrazing. The grazing land has lower quality of pasture due to intensive grazing. The quality of the grazing land is progressively declining due to shorter rainy seasons, frequent droughts and overgrazing, causing cattle to graze before grasses have produced seeds, creating more shortages in subsequent seasons.

Changes in temperature coupled with frequency of extreme weather events have been damaging crops and reducing yields. Heat stress has entailed disease outbreaks, reduced milk production and resulted in extra expenditure or loss of income. In particular, prolonged dry seasons and droughts have become more frequent and severe. These risks are made worse by an upsurge in pests and diseases, especially the increasing threat of Fall Armyworm. Changes in pest and disease patterns have also threatened crop production and animal husbandry. The ranges and distribution of pests and diseases are likely to increase; causing new problems for crops and animals previously unexposed to these pests and diseases. These challenges are further aggravated by climate change and the absence of resilient alternative sustainable income generating activities.

Land users in the Ethiopian lowland ecosystems view climate change as a threat that has resulted in food insecurity and dependence on food aid. However, they also express having limited awareness of the long-term risks that climate change poses, and do not know how to respond to these risks and / or of the options available to adapt to them. Indeed, due to lack of reliable information as well as limited knowledge of, and access to a wide range of adaptation options they are forced to follow unsustainable livelihood systems as they use short term coping mechanisms. Generating, interpreting, packaging and disseminating credible and timely weather and climate forecasts is a challenge in Ethiopia. Lack of access to timely and credible weather and climate forecasts has left land users with no option except to rely on traditional methods of weather forecasting, which has proved ineffective given the context of a changing climate. Discussion with land users and government stakeholders revealed that the challenge of meeting poverty reduction and food security goals has been mainly associated with incapability to plan better so as to minimize climate related losses and damages.

The land users in the target project areas are resource-poor and their low income means they are unable to make investment and take on risk. In particular, the pastoralists in the Somali and Afar regions have seen their daily livelihood challenges being the constant need to cope with challenges like livestock feed, food, water shortages and migration from internal displacement among others. Moreover, because the main resources in the lowland ecosystem of Ethiopia are controlled by men, women rarely participate in decision-making and their contributions in building resilience and adaptive capacity are seldom recognized. In addition, the decrease in food in times of drought has affected human health especially among children under five years, pregnant women and old people, and reduced human disease resistance and productivity.

The focus group discussion (FGD) held during the PPG phase on impacts of and vulnerability to climate change with lowland farmers, agro-pastoralists and pastoralists revealed that land users are taking actions to cope with climate change and related hazards. However, their current coping strategies such as charcoal and firewood selling are not effective in serving their long-term adaptation needs. These coping strategies are based on short-term considerations, and survival needs, leading to mal-adaptation.

Due to the  limited support tailored to the needs of land users to maintain their livelihoods while adjusting to climate change,  land users across the Ethiopian lowland ecosystems are at risk due to climate-change threats. They face several barriers to effectively managing these risks.

THE BARRIERS IN BUILDING RESILIENCE AND ADAPTIVE CAPACITY

The following three sets of overarching barriers stand in the way of advancing towards the project objective of building sustainable and climate-resilient economic growth among vulnerable communities, targeting lowland areas in Ethiopia. The full and effective implementation of this project will deliver the following benefits to vulnerable communities in twelve Woredas across the six regions: i) increased understanding of key adaptation issues, including community-based adaptation techniques as a basis for incorporating climate smart technologies and good practices through a practical learning-by-doing approach; ii) enhanced capability to respond to ongoing and emerging threats through the development of climate adaptive action plans by utilizing early warning, downscaled weather information and climate change knowledge products and iii) enhanced capacity of land users to create, improve and sustain diversified livelihood options at the same time as rehabilitating degraded watersheds.

Barrier #1:

Lowland communities lack knowledge on risks of climate change; and the benefits of climate smart solutions and adaptation practices.

The causes and implications of current and future climate change are not well understood within lowland communities. Therefore, the land users in these communities are not ready to adopt climate resilient farming and animal husbandry practices because their knowledge of the risk of climate change as well as how to minimize risks and take advantage of these opportunities are limited. The current coping strategies of land users are not also effective in serving their long-term adaptation needs. On the other hand, there are a number of interventions that can make farming and animal husbandry practices in the lowland ecosystems of Ethiopia climate resilient and more productive. Yet, designing actions based on appropriate and participatory interventions that can steer course away from climate sensitive activities remain a challenge.

Although climate change is recognised as a matter of national importance within Ethiopia’s CRGE strategy, the Agriculture Sector Climate Resilient Strategy and the NAPA, the technical and scientific understanding of climate change and adaptation and its practical application is not well developed within government institutions. Gaps in the technical capacity can be attributed to insufficient training of staff employed in relevant departments within the Ministry of Agriculture, Environment, Forest and Climate Change Commission as well as development agents and extension officers at Woreda-level. As a result, they lack the capacity to offer needed advisories and effective extension support to the land users that would enable them to adopt more resilient and productive practices.  Consequently, the land users have limited awareness of the risks that climate change poses and are not familiar with climate smart solutions to build their resilience and adaptive capacity.

At present, there are few initiatives – either through the GoE or elsewhere – to conduct training activities supporting the implementation of the Climate Resilient Green Economy Strategy (CRGE). In particular, there are few training programmes on land management practices for climate change adaptation that are appropriate for Ethiopia’s lowland ecosystems. In addition, there are limited opportunities available for training on how to mainstream activities that are congruent with the CRGE strategy into decision-making and agricultural planning either at the federal or at the regional and woreda levels.

Government stakeholders and land users in the lowland communities require better understanding of community-based adaptation processes as a basis for incorporating climate smart solutions through a practical learning-by-doing approach in order to overcome the barrier.  The proposed project activities under outcome 1: Technical capacity for implementing diversified climate change adaptation practices strengthened will address this barrier.

Barrier #2: Limited access to climate forecasts, decision-making tools and climate advisory services for Lowland communities

Effective adaptation requires farmers to have access to up-to-date, downscaled climate information, and the appropriate tools and advisory services at their disposal. Ethiopia’s Lowland communities do not have access to these, and are not connected to the climate information, products and advisory services. Technological and capability constraints have hindered the provision of weather and climate forecasts, including guidance and value-added advisory services to land users. In addition, information on how to adopt alternative and innovative farming, pastoral and agro-pastoral practices based on these climate forecasts is not available. This is a result of insufficient availability of climate forecast information, particularly at the local level and inadequate capacity of agricultural extension officers to guide farmers and other land users based on climate forecasts. Consequently, lowland farmers, pastoralists and agro-pastoralists can only undertake limited proactive measures in response to climate change.

At the level of overarching policies, plans and strategies, Ethiopia has made some progress in mainstreaming climate change considerations into national and regional frameworks. This has provided a good basis for the implementation of national adaptation priorities through existing LDCF projects. There is need to find more operational ways of influencing policies and actions on the ground. This requires expanding the capability to gather climate data and to share downscaled weather information and climate change information products with practical applications that combine climate predictions with advisory support services for vulnerable land users. However, the capacity at the national level to generate downscaled climate data and use it at local level is not yet well developed. Often, climate data is provided in complex scientific formats and at high resolutions. The generation of the data is also not informed by the needs of users on the ground.

Moreover, having the tools and undertaking climate information analyses is not in itself enough without the ability to use it to inform decisions at the farm level. Currently, there exists no climate advisory services tailored to the needs of Lowland communities. Practical application requires concerned government stakeholders and land users to have the capacity to use these information and analysis to respond to ongoing and emerging threats in the project area.

Overall, there is no alignment among the components of the climate information products and services value chain, from the collection, analysis and packaging of such information to meet the needs of communities, to the application of this information at local level to support adaptation decisions and actions. Along the chain, there are huge capacity constraints and disconnects in government institutions to provide the information, tools and advisory services synergistically.

The proposed project activities under outcome 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools will address this barrier.

Barrier #3: Inability of land users to invest in climate smart technologies and solutions required to diversify and sustain their livelihoods in the face of climate change.

The land users in the project area are resource-poor and unable to invest in the available climate smart technologies, opportunities and solutions for the diversification of their livelihood system. In the project area, there is potential for constructing reservoirs, ponds and boreholes that help address the prevailing water scarcity. Indeed, the land users in the project area have underutilized this potential and few of them rely on flowing streams/rivers and shallow wells with limited capacity to supply domestic water needed during the drought period. There are also opportunities for local communities to diversify their livelihood options thereby building their adaptive base and assets, but are not able to do so due to a number of reasons. They lack technical knowhow to tap into these opportunities, while the advisory services available to them from support institutions is largely lacking in these areas. These services also focus on traditional agro-based livelihoods which themselves are climate-sensitive. Opportunities in activities such as bee keeping, fish farming, processing and marketing of natural products are not fully tapped by lowland land users to diversify their livelihoods and incomes while building adaptive assets.

These opportunities also remain untapped as they are out of reach for the land users who are not able to access funding and technical knowhow. They are therefore not able to construct, own and operate integrated water storage facilities and reservoirs, including accompanying irrigation and solar pump support structures to enable the creation, improvement and sustenance of diversified livelihood options. Some of the investments especially in the construction of water storage facilities and reservoirs, including accompanying irrigation and solar pump support structures require a high up-front capital investment.

This has also become more difficult in the absence of appropriate financial capital especially for poor land users with limited access to the financial services (Ethiopia is one of the most under-banked countries in sub-Saharan level, with a bank branch to population ratio of 1:43912 in 2013/14). Small land users are also perceived as risky borrowers by the formal financial services sector, which is compounded by their lack of collateral, while the costs of finance from the informal financial services sector makes this source unaffordable to them.

The proposed project activities under outcome 3: Climate change adaptation practices adopted in communities in lowland ecosystems will address this barrier.

Although no single initiative can address all the barriers mentioned above, the LDCF-financed project will deliver complimentary outcomes to contribute towards overcoming these barriers. The theory of change (ToC) (Annex K below) underpinning the design of this LDCF-financed project includes the barriers discussed above and activities that contribute to the preferred solution discussed in section III through the delivery of the outcomes 1, 2 and 3.

# Strategy

As described in section II above, land users across the Ethiopian lowland ecosystems face several barriers to effectively reduce and manage the impacts of climate change. The objective of the proposed LDCF project is to promote climate change adaptation and sustainable economic growth among communities in Ethiopia’s lowland ecosystems; which are selected using predefined criteria set by EFCCC through a bottom-up process. In so doing, the project will target close to 60,000 (52% women and 48% men) beneficiaries in twelve Woredas across six regions (please see the below Table 1).

Table 1: List of Regions and Woredas

|  | Regions | Woredas |
| --- | --- | --- |
| 1. | Afar | Dewe and Awash-Fentale |
| 2. | Amhara | East Belesa and Sahleseyemt |
| 3. | Oromia | Zeway dugda and Babile |
| 4. | Somali | Degahabur and Harawo |
| 5. | SNNPR | Halaba and Alle |
| 6. | Tigray | Sahrti Samre and Were Leke |

The proposed project will develop and implement a capacity building support programme to strengthen the ability of land users through i) reaching a wider audience of land users and government stakeholders across the lowland ecosystems of Ethiopia using a TOT approach; ii) disseminating credible weather information and advisory services using a locally suitable communication channels to inform the preparation and implementation of actions designed for building resilience and adaptive capacity at a watershed level, iii) conducting a “learning by doing” training to promote clarity and commitment of land users and iv) providing needs responsive support to diversify livelihood options in a way that leads to tangible and replicable changes.

Accordingly, at the local-level, this project will deliver the following benefits to vulnerable communities in twelve Woredas across the six regions: i) increased understanding of key adaptation issues, including community-based adaptation techniques as a basis for prioritizing and incorporating climate smart technologies and good practices through a practical learning-by-doing approach; ii) enhanced capability to respond to ongoing and emerging threats through the development of climate adaptive action plans by utilizing early warning, downscaled weather information and climate change knowledge products and iii) enhanced capacity to create, improve and sustain diversified livelihood options at the same time as rehabilitating degraded watersheds in the project regions.

This LDCF project will also support the GoE in reaching its development targets such as those specified under the GTP II, the CRGE Strategy and the SDGs. The project will contribute to Ethiopia’s National Adaptation Programme of Action (NAPA) through inter alia: i) Key Adaptation Need 24 – Promotion of on-farm and homestead forestry and agro-forestry practices in arid, semi-arid and dry sub-humid parts of Ethiopia; ii) Key Adaptation Need 29 –  Strengthening/enhancing drought and flood early warning systems in Ethiopia; and iii) Key Adaptation Need 32 – Enhancing the use of water for agricultural purposes on small farms in arid and semi-arid parts of Ethiopia.

In addition, the project will contribute to several Sustainable Development Goals (SDGs), including: i) SDG 8 – Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all; ii) SDG 12 – Achieve food security and improved nutrition and promote sustainable agriculture; iii) SDG 13 –Take urgent action to combat climate change and its impacts; and iv) SDG 15 – Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss.

RELEVANT NATIONAL AND INTERNATIONAL REGIONAL RELATED INITIATIVES

Ethiopia has undertaken several efforts to strengthen technical, financial and institutional capacities for enabling climate change adaptation. There are already a number of existing national policy initiatives, sectoral policies, programs and strategies that may directly or indirectly address climate change adaptation. The most relevant public documents that have relevance for climate change adaptation include Ethiopia’s National Economic Development Plan (The Growth and Transformation Plan (GTP II), Ethiopia’s Programme of Adaptation to Climate Change (EPACC), the Green Economy Strategy (GE), the Nationally Determined Contribution (NDC) of Ethiopia, the recently prepared National Adaptation Plan (NAP), the Environmental Policy of Ethiopia, the Agriculture and Rural Development Policy and Strategy, the Water resources Management Policy, the Health Sector Development Policy and Program, the National Policy on Disaster Prevention and Preparedness, the National Policy on Biodiversity Conservation and Research, the Science and Technology Policy, the Population Policy and National Agricultural Research Policy and Strategy. In Ethiopia, various international initiatives continue to strive for sustainable development.

In spite of these efforts, there is disparity between objectives and what has been implemented due to the technical capacity limitations of government stakeholders and land users to translate these public documents into on-the-ground action to the fullest.

In view of the recent development with adaptation project implementation in Ethiopia, the project will coordinate with the following relevant projects including; The Green Climate Fund (GCF) financed project-‘’Responding to the increasing risk of drought’’; the Adaptation Fund (AF) financed project- ‘’Building gender responsive resilience of the most vulnerable communities’’ and the USAID Financed FAO Project on Fall Army Worm with the Ministry of Agriculture.

The baseline and associated baseline projects

In order to reverse land degradation and to improve rural livelihoods, the government is currently implementing several programmes. However, these programmes are not multi-sectoral and usually focus on issues such as land production or soil and water conservation across watersheds. They do not take and have not taken the predicted effects of future climate change on land users into account in their approaches. In addition, current land use planning fails to adequately integrate climate change considerations into short-, medium- and long-term development planning. Long-term investments in developing agricultural land are subsequently being implemented without the benefit of appropriate climate-related information being considered.

The baseline projects are described in the table below. The right-hand column describes how the proposed LDCF project will build on or align with the activities of each project.

Table 2a: Baseline and aligned projects details

| Title | Budget (US$) | Time frame | Objective | Focal activities/ outputs | Funding source | Implementing partner | How the proposed LDCF project will align |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Baseline Projects |  |  |  |  |  |  |  |
| Establishing an emergency community–based Fall Armyworm monitoring, forecasting, early warning and management system (CBFAMFEW) in eastern Africa | 944,000 | 2017- 2020 | To put in place a Community-Based Fall Armyworm Monitoring, Forecasting and Early Warning as a tool for limiting the potential damage caused by this pest to crops and pastures, and thereby improve food security and livelihoods of rural communities in targeted villages and communities in the eastern Africa sub-region (Burundi, Ethiopia, Kenya, Rwanda, Somalia, Tanzania and Uganda) | Output 1: Surveillance of FAW in the sub-region improved Output 2: Capacity of member states in FAW EWS built Output 3: Communication networks and linkages strengthened. | OFDA contribution 944,000 USD | MoANR in collaboration with Centre for Agriculture and Bioscience International (CABI) and International Centre for Insect Physiology and Ecology (ICIPE). | Through outputs 1.1, 1.2 and 1.3, the project will align with the Fall Army work project through the implementation of Fall (Africa) Armyworm community-based monitoring, forecasting and early warning initiative of the MoANR and FAO in the project area |
| Agricultural Growth Programme (AGP) | 254,500 | 2017–2021 | To contribute towards Poverty reduction, Climate change Mitigation and Adaptation through climate smart agriculture initiatives. | Introducing climate-smart technology to smallholder farmers. Decreasing poverty at a household level. | World Bank | MoANR | Through Outputs 3.2; 3.3; and 3.4, the proposed LDCF project will align with the activities of the AGP by further reducing poverty through the introduction of additional income-generating activities, and by implementing climate-smart agricultural and SWC measures that increase local communities’ resilience to climate change. |
| Productive Safety Net Programme –4 (PSNP4) | 763,082 | 2005– 2020 | To reduce food insecurity in chronically food-insecure households. | Engage households in community asset‐ building efforts to earn income. Increase resilience of local communities to adverse impacts of climate change. Provide “food for work” in watershed restoration initiatives. | DFID; World Bank | MoANR | The proposed LDCF project will build upon the existing biophysical and physical SWC structures developed by in the PSNP4 Programme. This will take place through Outputs 3.1 and 3.3. Capacity development under Outputs 1.2; 1.3; 2.3; and 3.4 will further the capacity development undertaken by the PSNP4. |
| Household Asset Building Programme (HABP) | 194,900 | 2011–2020 | To diversify income sources and build household assets. | Extending credit to food insecure households Creating linkages between MFIs, credit associations and local communities. | World Bank | MoANR | The proposed LDCF project will align with the HABP by assisting local communities to leverage finance through MFIs. This leveraged finance would ultimately be used to upscale watershed restoration and create additional sources of income for local communities. |
| Aligned Projects |  |  |  |  |  |  |  |
| Responding to the increasing threat of drought: building the resilience of the most vulnerable communities through climate-smart and landscape- based investments. | 90,7 million | 2018-2023 | To implement technologies and infrastructure, along with innovative methods, that contribute to climate-smart, landscape- based systems to be rolled out as a key element of the national CRGE strategy. | Implementing climate-smart SWC measures and biological conservation measures. Promoting livelihood diversification Strengthening linkages in value chains of agricultural and livestock products. Developing capacity of national and sub-national government departments to integrate climate considerations into planning, implementation and monitoring of development programmes. | GCF | EFCCC | The proposed LDCF project will align with the GCF project by ensuring that duplication of activities does not occur. The GCF project is implementing similar activities, however in different Woredas. The lessons learned will be integrated into the implementation of the LDCF project, particularly those relating to linking with MFIs for the upscaling of project activities. |
| Great Green Wall Initiative of the Sahara and the Sahel (GGWSSI) | 66,780,000 | 2002- ongoing | To improve the resilience of human and natural systems in the Sahel- Saharan zone against climate change through sound ecosystem management and the sustainable development of land resources, the protection of material and immaterial rural heritage and the improvement of the living conditions and livelihoods of populations living in these areas. | Short to medium term: conserving, restoring and enhancing biodiversity and soils; diversifying agricultural production systems; promoting income- generating activities to increase household income; and improving basic social infrastructure. Long term: improving carbon sequestration in vegetation cover and soils; restoring degraded landscapes; and improving the living conditions of Local communities. | Multi-donor funding including World Bank, FAO | EFCCC | Watershed restoration and sustainable landscape management are common objectives between the GGWSSI and the proposed LDCF project. Thus, the implementation of the LDCF project will contribute towards achieving a greater objective in the Sahara and Sahel. Additionally, the proposed LDCF project will take the lessons learned from the GGWSSI and ensure that they are integrated into the implementation of the project activities. |

Co-financing: The main source of co-financing for the project are the government and land users with UNDP providing direct co-financing. The realization of these co-financing sources will be monitored during the mid-term review and terminal evaluation processes and will be reported to the GEF accordingly. The planned co-financing sources are described as follows:

Table 2b: Co-financing Investments Overview

| Co-financing source | Co-financing type | Co-financing amount in USD | Planned Activities/Outputs | Duration | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | Direct | 200,000 | Project Management | 6 years | … | … |
| Government | Leveraged Grant | 10,250,000 | Components 1 and 2 | 6 years | … | … |
| Total contributions co-financing projects |  | 10,450,000 |  |  |  |  |

PROJECT RATIONALE AND POLICY CONFORMITY

LDCF CONFORMITY

          - This project is fully consistent with the goals of LDCF Strategic Objectives in several ways including increased knowledge and understanding of climate variability and change-induced risks at country level and in targeted vulnerable areas, strengthened adaptive capacity to reduce risks to climate-induced economic losses, successful demonstration, deployment, and transfer of relevant adaptation technology in targeted areas and enhanced enabling environment to support adaptation related technology transfer. It specifically responds to the Focal Area Objective CCA2 (Increasing Adaptive Capacity: Increase adaptive capacity to respond to the impacts of climate change, including variability, at local, national, regional and global level), CCA2-Outcome 2.1 (Increased knowledge and understanding of climate variability and change-induced risks at country level and in targeted vulnerable areas). This is aligned with project Components 1 and 2, as it focuses on expanding the knowledge and understanding among relevant groups of stakeholders on specific climate risks affecting the lowland ecosystem project sites as well as for strengthening climate change adaptation practices. The project also responds to the Focal Area Objective CCA1 (Reducing Vulnerability: Reduce vulnerability to the adverse impacts of climate change, including variability, at local, national, regional and global level), specifically CCA1-Outcome.2 (Climate-risk management adopted by smallholder farmers through accessible climate information and decision-making tools), and CCA1-Outcome 3 (Climate change adaptation practices adopted in communities in lowland ecosystems). Finally, the project is aligned with Focal Area Objective CCA3 (Promote transfer and adoption of adaptation technology).

GEF CONFORMITY

          - The project has been formulated to meet the overall GEF requirements in terms of implementation and design. Specifically, the following requirements have been addressed:

          - National ownership: As mentioned above, Ethiopia approved and submitted its NAPA in June 2007. This proposal addresses five of the priorities identified under the NAPA (Page 60). The NAPA was prepared through a participatory process, with the full involvement of relevant stakeholders. Accordingly, this project is country-driven and the project’s concept is consistent with, and supportive of, national development strategies.

          - Ethiopia has signed and ratified the UNFCCC in 1994 and is currently categorized as a Least Developed Country (LDC). Ethiopia is implementing the priorities identified in its National Adaptation Programme of Action (NAPA) and National Adaptation Plan (NAP). Noting that other priorities have been addressed through previous LDCF projects, this project will address the following priorities identified by the Government and stakeholders in the NAPA and NAP. The list below highlighted the corresponding priorities to be addressed by the project:

- Priority 2: Strengthening/enhancing drought and flood early warning systems in Ethiopia

- Priority 3: Development of small-scale irrigation and water harvesting schemes in arid, semi-arid, and dry sub-humid areas of Ethiopia

- Priority 4: Improving/enhancing rangeland resource management practices in the pastoral areas of Ethiopia

- Priority 6: Capacity building program for climate change adaptation in Ethiopia

- Priority 11: Promotion of on farm and homestead forestry and agro-forestry practices in arid, semi-arid and dry-sub humid parts of Ethiopia

          - Financing: Cost-effectiveness criteria were applied in the choice of adaptation measures and modalities during the NAPA process. During the PPG process, alternative approaches and appropriate technologies have been considered and the most cost-effective approach determined. During implementation, coordination with related activities will ensure synergies and cost-efficiencies. Finally, the level of co-financing ensures financial cost-effectiveness.

Institutional synergies and support: The project is to be linked with other concurring projects, programs and initiatives, including one ongoing project financed by LDCF and the ongoing soil and water conservation activities at the local level. It complements rather than duplicate these other related efforts. The project will be implemented by the Environment, Forest and Climate Change Commission (EFCCC), with support from UNDP, which will play a pivotal role in project support and in ensuring the coordination and synergies with other projects, programs and initiatives, and it will provide necessary institutional support. Specifically, the project will ensure strong and effective collaborations at policy and implementation level with the Green Climate Fund (GCF) financed project-‘’Responding to the increasing risk of drought’’; the Adaptation Fund (AF) financed project- ‘’Building gender responsive resilience of the most vulnerable communities’’ and the USAID Financed FAO Project on Fall Army Worm with the Ministry of Agriculture, as indicated in the project outputs and activities section of the PRODOC. The synergies will be achieved by inviting the projects to the project steering committee meetings in order to promote joint planning and reporting.

          - Monitoring and evaluation: The project will follow the GEF monitoring and evaluation procedures in addition to UNDP guidance on M&E for adaptation projects. Adaptive management will be a key component on the management approach. Details regarding monitoring and evaluation is included under Section 6 herein below. In order to better address gender issues, indicators will be gender disaggregated and these will be further developed during the inception phase of the project.

          - Stakeholder involvement: The project design was formulated as a result of extensive stakeholder consultations (see Table 3 herein below). A plan is also included to ensure the wider involvement of stakeholders during project implementation and monitoring.

COUNTRY OWNERSHIP: DRIVENNESS AND ELIGIBILITY

          - Ethiopia is a Least Developed Country (LDC), Party to the UNFCCC, and it has completed its NAPA in 2007. The proposed project covers five priority areas identified in the Ethiopian NAPA. The project - building on the NAPA, was developed through an extensive participatory process. Both the project’ concept (i.e. the PIF) and this PRODOC were prepared through a highly participatory process, in line with UNDP’s and GEF’s requirements. During the project preparation stage, numerous meetings were held with stakeholders to assess their interests and define their roles and responsibilities. The project design has benefited from field visits and consultations carried out during the preparation phase, including from national stakeholder meetings, consultations and validation workshops. Direct consultations were also carried out by a team of consultants, who were tasked with identifying and considering other relevant local, national or regional studies and projects.

          - Furthermore, the project directly addresses priorities identified under the National Communication for Ethiopia to the UNFCCC. The project will build local community adaptation capacities as well as strengthens commune-level and decentralized government services to be able and address adaptation in a well informed and knowledgeable way. The systemic capacity to address adaptation in Ethiopia will be further strengthened through targeted interventions at the policy, planning and budgeting levels.

          - COUNTRY ELIGIBILITY

          - The Government of Ethiopia (GoE) is a party to several international Conventions, including: (i) The Convention on Biological Diversity (CBD); (ii) The United Nations Convention to Combat Desertification (UNCCD); (v) The United Nations Framework Convention on Climate Change (UNFCCC) and (vi) The Basel Convention on the Control of Transboundary Movements of Hazardous Wastes and their Disposal. The United Nations Framework Convention on Climate Change (UNFCCC) has classified Ethiopia among the non-Annex I parties. Ethiopia developed and submitted its National Adaptation Program of Action (NAPA) in 2007 and is entitled to benefit from the LDCF for the implementation of NAPA priority measures. In implementing priority interventions identified in the NAPAs, the project satisfies the criteria outlined in the UNFCCC Decision 7/CP.7 and GEF/C.28/18. It also responds to Decision 1/CP.16, which invites Parties to enhance action on adaptation by “building resilience of socio-ecological systems, including through economic diversification and sustainable management of natural resources”. The project has been endorsed by both the national UNFCCC and GEF focal points. The project responds to urgent and immediate adaptation priorities and actions identified under the Ethiopia’s NAPA.

          - DESIGN PRINCIPLES AND STRATEGIC CONSIDERATIONS

The adopted approach to project design combines the use of natural solutions (biodiversity and ecosystem services) and appropriate technology to help adapt to climate change by strengthening, safeguarding and building both ‘natural’ and ‘social’ assets, including the interplay between them. Following this line, the project design builds from the body of knowledge and lessons drawn from local experiences. Accordingly, the basic project design adds value to several projects developed through the NAPA by bringing them together where lessons, processes, etc. can be shared. Implementation of activities like the water reservoirs and storage ponds under this project will be based on careful selection and preparation of feasibility studies. The design of this Project is informed by the NAPA of Ethiopia, particularly on the selection of cost-effective measures. The Ethiopia’s NAPA has identified key climate hazards affecting populations and assets, identified most vulnerable sectors, and presented a list of  measures to respond to these climate risks. In the development of the NAPA, multi-criteria analyses were used for filtering long lists of adaptation measures and to prioritize actions according to their potential for positive effects on economic development, social capital and environmental management. As such, the actions prioritized by the NAPA are not only the most urgent and most pressing but have also been assessed to be cost-effective. The proposed LDCF project aligns with the priorities of the NAPA to implement necessary actions that have already been identified as cost-effective.

To this effect, and based on the proposed flow analysis and assessment to be conducted, a feasibility studies will be undertaken following the selection of the appropriate location for water storage intervention, including for livestock watering points, in each woreda in collaboration with communities’ representatives

A focus on capacity building will ensure that measures are replicable and can be implemented by local communities without dependence on outside support for the core measures designed to improve and maintain provisioning of ecosystem services. The key design principles that underpin this LDCF project are:

- Promoting multi-sectoral approaches.

- Operating at multiple geographical scales.

- Integrating flexible management structures to enable adaptive management.

- Minimizing trade-offs and maximizing synergies with development and conservation goals to avoid unintended negative social and environmental impacts.

- Incorporating best available science and local knowledge.

- Fostering knowledge generation and diffusion.

- Promoting resilient ecosystems and nature- based solutions to provide benefits to people, especially to the most vulnerable.

- Being participatory, transparent, accountable, and culturally appropriate, while actively embracing equity and gender issues.

          - The project design is in line with the PIF, but refined through the recent studies and direct consultations undertaken during the PPG phase as follows:

- review of sectoral studies on climate change, natural resource management, water, agro-pastoral practices

- stakeholder analysis for component 1 and 2

- field mission to the project zone including consultations and interviews with local communities and relevant authorities on the ground

- interviews with partners and stakeholders on national and regional levels

- validation of field mission findings and proposed activities with key stakeholders at the national level

# Results and Partnerships:

Expected results:

PROJECT GOALS, OUTCOMES, OUTPUTS AND ACTIVITIES

This project seeks to remove the barriers that have hindered land users and government stakeholders from building their resilience and adaptive capacity, particularly those vulnerable communities represented by women and youths in the targeted lowland ecosystem of Ethiopia. To this effect, a range of capacity development interventions tailored to the needs of the targeted land users and government stakeholders will be implemented as outlined in the following project outcomes, outputs and activities below. As designed in the PIF, Component 1 and 2 of the project will deliver the following three outcomes:

| Components | Outcomes |
| --- | --- |
| - Capacity development for climate risk information and adaptation | - Technical capacity for planning diversified climate change adaptation practices strengthened - Climate adaptive management adopted by local communities through accessible climate information and decision-making tools |
| - Adaptation practices adopted at scale in lowland ecosystem | - Climate change adaptation practices implemented by communities in lowland ecosystems. |

Component 1: Capacity development for climate risk information and adaptation

Outcome 1: Technical capacity for planning diversified climate change adaptation practices strengthened (Co-financing for Component 1, Outcome 1: $2,099,702; LDCF grant requested for Outcome 1: $450,000)

This outcome will deliver strengthened capacity of farmers, agro-pastoralists and pastoralists on planning, monitoring and evaluating diverse climate change adaptation approaches. To this effect, the project would develop targeted training modules to be eventually made available online by appropriate partner institution. The modules would be put online for wider use across the country. These modules would be based on agreed areas of interventions that help strengthen adaptive capacity of the pastoralist, farmer and agro-pastoralist communities. Key considerations would be given to community-based adaptation training that leads to the development of climate resilient action plans across the watershed. The training modules would also include community forecasting, monitoring and early detection of such risks as the Fall Armyworm infestation. Using the developed training modules (as listed below), sets of capacity building seminars and training workshops would be delivered to government officials and woreda development agents respectively.

Subsequently, specific learning by doing community adaptation and participatory trainings would be devolved to the local communities to help strengthen their adaptive capabilities.: More specifically, the training modules will include issues identified for training needs as detailed below. These trained communities from the twelve woredas will in turn develop their own respective water security focused climate adaptive action plans through incorporating climate smart technologies and good practices, as well as early response measures including community-based monitoring, forecasting and early warning initiatives using the guidelines developed by FAO and being implemented by the MoANR. In addition to the Fall Armyworm response plan, targeted community based adaptive response will be developed to include the flash flood risks adaptive response and grievance and response mechanism to address Farmers Pastoralist Conflicts at the community level. The early warning and response measure will depend on the need of each of the twelve project sites.

Furthermore, the results of project interventions implemented under outcomes 2 and 3 will be monitored and the results thereof would be used as an input for the development of best practice guidelines to promote the up-scaling of climate-resilient farming, agro-pastoralism and pastoralism in Ethiopia’s lowland ecosystems. Best practices from the training and demonstrations would be documented across the twelve woredas. These experiences would be shared across the regions through effective television and radio documentaries, local language-based posters and other awareness materials.

During the PPG phase, the following training needs were identified to address specific needs of institutions and communities at regional and woreda/community-levels:

- Training on climate smart technology and good practices for community adaptation (Regional Institution level training: support Output 1.1)

- Training on developing climate adaptive community-based action plan (Regional Institution level training; support Output 1.2)

- Responding to climate emergency at community level: early detection and monitoring training on Fall Armyworm, Pastoralist/farmers conflict and Emergency flood (Woreda and Community level training; support Output 1.3)

- Training session on adaptive soil and water conservation techniques, including rehabilitation, improvement and maintenance of a productive and healthy watershed (Woreda and Community level training; support Output 1.2, 3.3)

- Training on climate and weather information for planning and agricultural advisory support for the agro-metrology task force established and hosted by the MoANR (Regional Institution Level training; support Output 2.1)

- Training on climate smart technologies for adaptive capacities and diversified livelihoods, including provision of enhances the knowledge base and capability of land users, including women and youths, on the establishment of community-based enterprises like water storage and rainwater harvesting techniques, livestock fattening and agroforestry, poultry production, etc. (Woreda/Community Level training; support Output 3.2)

The outputs under Outcome 1 include:

  - Training modules and platform for enhancing the knowledge and capability of government officials, DAs and local-communities in twelve woredas on the formulation and implementation of adaptation measures are established and sustained.

  - Strengthened capacity of development agents (DAs) and government officials to support the implementation of climate change adaptation practices at the woreda and regional levels.

  - Community action plans for adaptive crop production and animal husbandry developed using a participatory approach in twelve Woredas.

  - Project benefits and climate change adaptation practices are documented and disseminated to local community members in twelve woredas through learning, using innovative and locally adapted means.

The strengthened technical capacity for planning climate change adaptation practices through the provision of targeted training under outcome 1 informs and contributes to Outcome 2 by enhancing the understanding of farmers, agro-pastoralists and pastoralists as well as other stakeholders to generate the inputs required for the formulation and adoption of climate adaptive management plan. The capabilities built under outcome 1 for the provision of inputs to Outcome 2 will be achieved including through enhancing capacity of stakeholders on how to i) define the geographical boundaries of the project area; 2) identify and document climate-related challenges faced by stakeholders; 3) gather credible climate related data; 4) identify climate risks and prioritize climate-related challenges that are likely to affect the social, environmental and/or economic status of local communities and their watershed by considering drivers of future trends and how these issues are currently being addressed as well as 5) on how to plan, monitor and evaluate diverse climate change adaptation approaches.

Outcome 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools. (Co-financing for Component 1, Outcome 2: $2,193,632; LDCF grant requested for Outcome 2: $681,782)

This outcome will deliver the adoption of climate adaptive management practices by local communities using climate information and appropriate decision-making tools. To this effect, functional Automatic weather stations (AWS) – that will complement and be connected to the on-going effort to extend Ethiopia’s climate observatory network will be installed. Protocols will be developed for climate data collection and analysis as well as on the provision of support regarding climate data storage and management for future reference and decision making in collaboration with the National Meteorology Agency (NMA). Climate monitoring technologies such as rain gauges and handheld climate forecast devices will be distributed to the woredas in the intervention sites. In addition, training on the use of these climate monitoring technologies will be provided to woreda-level officers and DAs. The data collected from the AWS and the household monitoring devices will be used to compile short-term and seasonal climate forecasts meant for land users.

In order to down-scale the data, the project will work with the Agro-meteorology Task Force established and hosted by the MoANR. This task force currently meets every other week to manually compile agro-meteorology data. Partnership with the MoANR Agro-meteorology Task Force will be formed with the aim of enhancing efficiency and clarity on the implications of weather information and on the practical application of climate science and traditional weather forecast practices. This multi-stakeholders Task force team will ensure that weather and climate forecast services are made easily accessible. The project will also provide capacity building support to the Task Force. The project will facilitate the linkage of activities under this outcome with the Agro-meteorology Task Force Initiative and support the updating of the Task force decision tools to digitized tools. These tools will allow the effective use of climate forecasts provided by the AWS and the downscale of the weather and advisory information to farmers, pastoralist and agro-pastoralist in the project area. Once implemented, the decision-making tools will be tested for a two-year period. The results of this testing period will be combined with lessons learned from the project “CCA Growth: Implementing Climate Resilient and Green Economy plans in highland areas in Ethiopia” to inform national up-scaling of decision-making tools for agro-pastoralists, pastoralists and farmers.

Local weather forecasts will be made available to the land users through mobile phones in each woreda. This would complement the Task Force on Agro-meteorology on-going collaboration with Wageningen University, Netherlands and the Agricultural Transformation Agency (ATA) of Ethiopia. By providing end-users with information in a tailored, useable format, this outcome is building on the GEF financed LDCF project that is being implemented in the highland ecosystem of Ethiopia. This outcome will also build on the lessons learned through the LDCF-funded project “Strengthening climate information and early warning systems in Africa for climate resilient development and adaptation to climate change – Ethiopia” and solicit international expertise to develop climate forecast and decision-making tools.

The Woreda level climate adaptive management plans will be screened against the environmental and social criteria to ensure compliance with the SESP and that all risks identified therein are taken into account. High risk activities will not be supported by the project. Community adaptation plans will also include identification of vulnerable groups within the areas covered by the plans, and outline requirements for FPIC. Additional plans, including an Indigenous People’s Plan or equivalent, may be prepared, whose level of detail will be proportional to the complexity of the nature and scale of the proposed activities and their potential impacts on indigenous peoples and their lands, resources and territories.

The outputs under Outcome 2 include:

  - Nine Automatic Weather Stations (AWS) installed and linked to the national meteorological network and protocols for use and maintenance established in each woreda.

  - Appropriate weather and climate monitoring and forecast technologies acquired by representatives of the beneficiary communities and maintained through a functional and durable partnership.

  - Climate-risk assessment and decision-making tools developed and used in collaboration with local communities in twelve woredas.

  - Climate-risk assessment and decision-making tools are pilot tested and periodically improved using the results thereof in each of the twelve woredas.

  - Proactive climate adaptive management plan prepared anchored on functional water storage infrastructure to enhance the resilience and adaptive capacity of local communities in the twelve Woredas. Management plans will be careened against the SESP during plan preparation processes to exclude high risk activities.

The formulation and adoption of climate adaptive management plan using an up-to-date, downscaled climate information, and the necessary tools and advisory services under Outcome 2 explicitly links the information gathered under outcome 1 for the formulation and adoption of proactive climate adaptive management that would also describe who will be doing what and when to deal with the prioritized climate challenge risks under Outcome 1. Outcome 2 in turn provides inputs that will be implemented by local communities in lowland ecosystem through investment in climate smart technologies, opportunities and solutions as specified under Outcome 3.

Woreda level plans, climate risk assessments and data from AWS integrated with the Met department will inform the interventions under component 3 and the proposed special innovation direct investment.The uptake and use of data and information by local communities gives the AWS infrastructure its ultimate value, and is the purpose for having this infrastructure under the project. This has value both within the project areas as well as within the broader national network. In this regard, the project will facilitate the uptake and use of information and data by local communities through the Agro-Met Task Force Mobile Data provision to farmers and communities at large. It will also strategically support the relevant government institutions, including National Meteorological Agency and Ministry of Agriculture to facilitate community access and use of this information in decision making. This will not only be supported through this project, but through other projects as well thereby ensuring that the installed AWS serve the needs of farmers.

Component 2: Adaptation practices adopted at scale in lowland ecosystem

Outcome 3: Climate change adaptation practices implemented by communities in lowland ecosystems. (Co-financing for Component 2, Outcome 3: $5,956,666 ; LDCF grant requested Component 2, Outcome3: $4,426,383)

This outcome will strengthen land users capacity for the implementation of climate change adaptation practices  for building resilience and diversification of their livelihoods options. This component of the project will thus support land users to create, improve and sustain diversified livelihood options through rehabilitating degraded watersheds in a way that would lead to tangible and replicable changes. This will be achieved through the provision of needs-based technical support for soil and water conservation activities (soil bund, afforestation, check dam, hill-side terracing, etc.) and construction, operation and utilization of water storage structures for the diversification of livelihood options. As a result of this, land users will be able to do supplementary irrigation and engage in creating alternative climate resilient income generating opportunities. Water storage locations would be identified through the development of climate adaptive community-based action plans from Outputs 1.3. The climate adaptive plan will be developed for each woreda in the 6 regions through a participatory consultation process with the aim of securing, in advance, the commitment of the local community to contribute labor during construction, operation and maintenance; as well as to conserve the entire catchment area for long time durability and functionality of the water storage structure.

Local communities in the woredas targeted under this component will benefit from the implementation of a number of on-the-ground activities including; increased adaptive capacity through implementation of adaptive farming, agro-pastoral and pastoral practices; improvement of land productivity through such agro-ecological interventions as the bunds, alley cropping and terracing techniques and enhanced availability of fodder crops for livestock feed through planting of drought-resistant and high yield and early maturing varieties. Furthermore, to enhance access to resources in order to scale innovation for climate adaptation in the lowland ecosystem, the project would assist land users to organize into groups to learn from each other and replicate resilient practices.

A range of livelihood improvement activities will be implemented based on the community action plans developed under Component 2, and will vary from community to community. Examples of activities that will be considered include growing, processing and marketing of fruits and vegetables, installation of technologies for water and energy provision such as solar powered water pumps  and biogas to reduce deforestation for community groups, planting fast growing trees for firewood and construction, energy-efficient fuel-wood stoves for clean cooking solutions, growing area closure (fencing) plants using fruits trees, growing  animal forage plants, poultry and animal fattening. The project will train beneficiaries, and especially empower women to engage in value chain business opportunities such as processing and marketing of milk and milk products. Location-specific alternative livelihood support activities such as tree nurseries, bee keeping, fish farming at natural and artificial lakes, edible mushroom cultivation, compost preparation or sustainable use of incense and gum to reduce deforestation and forest degradation would be supported in the intervention sites. To support the offtake and sustainability of these options, the project will support beneficiaries to initiate business enterprises, and will link them to financing schemes.

Following the initial assessments done during the PPG phase, the project will conduct in-depth, focused capacity needs assessments with the aim of strengthening the capacity of beneficiaries for the delivery of sustainable and scalable businesses. The in-depth assessments, based on the selected livelihood activities for each community, will strengthen community buy-in and increase the levels of uptake and sustainability of the adaptive practices and technologies. As well as providing entry points for the establishment of community-based enterprises and involvement of the private sector in running the business enterprises. The assessments will include: i) analysis of market opportunities; ii) identification and implementation of selected income-generating activities; and iii) appropriate support to local communities on value-addition activities, including agro-processing and marketing skills; iv) sustainable financing options. In addition, the development of community business enterprises (CBEs) will be supported to: i) increase local communities’ access to markets; ii) increase market efficiencies; and iii) promote the development of local private sector agents such as agricultural service providers.

The project will also support training of extension agents to follow-up on the implementation of the adaptation and livelihoods activities and review progress in each Woreda with the aim to i)  review successes and failures from the LDCF and to suggest up scaling activities; and ii) develop training material and provide training workshops on developing bankable business plans  It will also develop a long-term M&E strategy for each Woreda that will be followed up by the extension agents and other development facilitators at Woreda level.

To ensure compliance with the Social and Environmental Screening Procedure carried out under this project, all community action plans and activities under Output 3.1, 3.2 and 3.3 will be screened against the identified and any additional risks, and mitigation measures applied. Additional plans, including an Indigenous People’s Plan or equivalent, may be prepared, whose level of detail will be proportional to the complexity of the nature and scale of the proposed activities and their potential impacts on vulnerable groups and their lands, resources and territories. Higher risk activities will not be covered by the project.

The outputs under Outcome 3 include:

  - Sites identified, through community planning processes, as critically degraded are rehabilitated in the twelve woredas anchored on functional water storage infrastructure designed, constructed and utilized to enhance the resilience and adaptive capacity of local communities in the twelve Woredas. The screening process will be carried out during the site selection and design of infrastructure before any construction takes place, with the possible need for free prior informed consent (FPIC). If indicated, an Indigenous Peoples Plan will be developed and implemented

  - Alternative livelihood opportunities created, expanded and made more responsive to climate change through the implementation of community-led climate adaptive initiatives in the twelve woredas. Livelihood options will be screened using the SESP to assess risks. High risk options will not be supported by the project.

  - Farm/pastureland rehabilitated through physical and biological soil and water conservation measures in degraded areas in each woreda for and by the vulnerable lowland farmer, pastoralist and agro-pastoralist communities.  SESP screening will be undertaken during the design of rehabilitation measures to identify risks and mitigation measures, excluding high risk measures. The screening will indicate the possible need for free prior informed consent (FPIC). If indicated, an Indigenous Peoples Plan will be developed and implemented

  - Community-based enterprises established and operationalized in each woreda to develop and strengthen climate resilient local business.

  - Woreda-level M&E and follow-up strategy developed and adopted by woreda development facilitators and extension agents.

The implementation of adaptation plans outlined under Outcome 2 by local communities in lowland ecosystem ensures that land users in the project area enhance their investment in climate smart technologies, opportunities and solutions in order to diversify their livelihood system while mitigating risks and driving actual improvements in performance (Outcome 3). Project performance will be tracked periodically in order to learn from the outcomes and inform future climate change adaptation plans and actions within and outside the geographical boundaries of the Project area. Undertaking frequent evaluation in this way helps to generate and document knowledge and obtain good practice results that would be disseminated to strengthen capacity for the implementation of diversified climate change adaptation practices.

Outcomes 1 and 2 are intended to provide the basis for implementing climate adaptive solutions and practices (Outcome 3) through climate-informed planning at the local level as well as the use of climate information. For each community, the strategies and practices selected under Outcome 3 will be based on the skills and information from planning processes (Outcome 1) that take into account climate change considerations, as well as the capacity to generate provide and use climate information (Outcome 2) to come up with solutions that address climate risks and vulnerabilities. This will generate knowledge that will be applied in the long term. The implementation of Outcome 3 will follow a participatory process that involves communities as well as local level planning and development institutions in the application of climate-informed planning tools and locally relevant climate data. This structure and approach of the project is a deliberate strategy to ensure that planning capacity and the use of climate information are the basis for climate change interventions, and that there is capacity in the local planning structures to facilitate this process. A provision has been made for special innovation direct investment in community infrastructure and alternative livelihoods creation for Woredas with capacity to include additional site making maximum of 3 sites per woreda.

ADDITIONAL COST REASONING

The GEF-LDCF intervention through this project will make a significant incremental contribution towards the Government of Ethiopia (GoE)’s efforts to promote the implementation of climate change adaptation and sustainable economic growth measures among communities in the lowland regions of Afar, Amhara, Oromia, Somali, SSNPR and Tigray, as described herein below:

1. Enhanced capacity for climate change adaptation planning: Without this intervention, capacity in DAs/government officers and local communities will remain inadequate for planning and implementation of interventions on climate change adaptation. Furthermore, progress made through training under the Managing Environmental Resources to Enable Transition (MERET) programme may be lost. Existing capacity limitations that hinder planning and implementation of adaptation interventions will leave lowland communities vulnerable to the current and future effects of climate change. This intervention is expected to extend and build on the progress made by the MERET programme by targeting priority adaptation needs. New partnership between stakeholders will be built and existing relationships will be strengthened for the provision of training in collaboration with MoANR. This training and relationship-building will increase the capacity of government officers, DAs and local communities to undertake urgent and early response to emerging threats through coordinated planning, especially participatory and climate adaptive community actions that would help land users set priority for climate change adaptation actions across multiple sectors and geographic areas, thereby supporting local communities to decrease their vulnerability to the current and future effects of climate change. In addition, the successful approaches identified by the project will be used to inform future up scaling of similar adaptive farming, agro-pastoral and pastoral interventions across Ethiopia.

2. Climate risk-management practices for smallholder farmers, agro-pastoralists and pastoralists: Without this intervention, the land users in the project area will not have access to accurate and downscaled climate forecasts. This situation is likely to put these land users with no options except to rely on traditional methods, which has been proved ineffective given the context of a changing climate. As a result, land users will be unable to be proactive in taking advantage of the opportunities and avoiding the risks presented by climate change.

The collaboration with NMA will provide new AWS to the existing NMA system and thereby assure improved collection of weather and climate information across the project area. Instead of developing new decision support systems in the project area, this intervention will partner and help strengthen the MoANR hosted Agro-meteorology Task Force, which currently represents a practical, scalable and replicable decision support and early warning system that fits into the project objective. This will ensure improved analysis and delivery of reliable and timely climate forecasts for smallholder farmers, agro-pastoralists and pastoralists in an innovative way using mobile technology. Upgrading of decision-making tools hosted by the Task Force will allow land users in the project area, for example, to make informed choices based on climate forecasts.

In addition, this component will help scale the implementation of Fall (Africa) Armyworm community-based monitoring, forecasting and early warning initiative of the MoANR and FAO in the project area. For example, expanding the implementation of the Fall (Africa) Armyworm community forecaster initiative across the project area will reduce the damage that would result from the African armyworm on crops and pastures and thereby help improve food security and livelihoods of rural communities in high risk regions and woredas in the project area.

3. Adoption of climate change adaptation practices: Without this intervention, the land users will continue to apply business-as-usual farming, agro-pastoral and pastoral techniques that do not take into consideration the current and future effects of climate change adequately. In addition, the widespread reliance of land users on marginal livelihoods imposed on them as a result of limited or lack of access to water, and their limited capacity to maximise market efficiencies will limit socio-economic development. Traditional agricultural practices – combined with limited livelihood options and inefficient access to climate smart agricultural techniques- will make land users vulnerable to the current and future effects of climate change. This vulnerability will exacerbate food insecurity in Ethiopia’s lowlands. This intervention is expected to: i) increase the area of cultivable farmland as a result of increased access to water through connected solar pumped irrigation; ii) increase agricultural productivity per unit area through the inclusion of improved varieties of climate-resilient seeds into local farming techniques; iii) increase availability of feed for livestock through the expanded fodder cultivation and access to irrigation water; iv) diversify livelihoods including through the promotion of solar technologies, tree nurseries, honey bee rearing, edible mushroom cultivation and gardening; and v) pilot an expanded community agroforestry. In addition, a more conducive economic environment for land users will be promoted through providing support and training to access markets. Therefore, this incremental contribution will increase the socio-economic prospects of farmers, pastoralists and agro-pastoralists in the face of climate change.

Global environmental and/or adaptation benefits: Specific adaptation benefits emanate from the project will have local and global benefits. Initially, these benefits will accrue at a local level and be achieved through: i) reclamation of degraded land through the implementation of appropriate agro-ecological measures; ii) planting of climate-resilient fodder crops to increase rangeland productivity under climate change conditions; iii) climate-resilient staple/cash crops planted to maintain agricultural productivity under future climate scenarios; iv) climate monitoring technology transferred to farmer/agro-pastoralist households, youths and women groups; v) climate change adaptation techniques – such as agroforestry – adopted in lowland farmer and agro-pastoral communities; vi) location-specific alternative livelihoods supported and diversified in lowland communities; and vii) community-based enterprises established and strengthened in each woreda to promote business development and strengthen local value chains for greater adaptive capacity. By increasing the uptake of adaptive farming, agro-pastoralist and pastoral practices in Ethiopia’s lowlands, food security and local livelihoods will be strengthened. Furthermore, the development of community-based enterprises will promote the sustainability of alternative livelihoods and improve the local economy in lowland communities. Therefore, the adaptive capacity of Ethiopia’s lowland communities will be strengthened under the conditions of climate change.

The project’s activities will target local communities in twelve woredas. However, the results of these local adaptation interventions will inform Ethiopia’s CRGE strategy and promote the up-scaling of successful interventions. Furthermore, the cost-effectiveness of the project’s interventions will provide an evidence base for the implementation of future initiatives that promote adaptation to climate change in similar ecosystem within and beyond Ethiopia.

Partnerships:

During the implementation of the Lowland Ecosystems climate adaptation project, the project management team will facilitate coordination with other bilateral donors active in the sector and targeted woredas. They will also facilitate data sharing and information exchange with appropriate research institutes and organisations at the regional level. Key research and regional institutions have been incorporated to the project steering committee in order to ensure more effective collaborations at project decision making level.

Partnerships with regional donors including projects sponsored by the FAO/USAID and the Adaptation Fund will be nurtured and indeed have been integrated into project outputs delivery. This would be realized through appropriate MoUs. The project will also benefit from UNDP’s framework for cooperation with donors for project financing. This LDCF initiative will complement other relevant GEF-financed initiatives in Ethiopia, namely the project on CCA Growth: Implementing climate resilient and green economy plans in highland areas in Ethiopia implemented by UNDP. The proposed project will equally align with the following baseline projects to maximize benefits to the recipient local communities: i) FAO-USAID funded Africa/Fall Armyworm Project; ii) Adaptation Fund Project on Climate Smart Integrated Rural Development among others.

Each of these projects has a similar overall objective to that of the LDCF project. To align with the baseline projects, climate change risks and opportunities will be integrated into the existing capacity development programmes at a national and sub-national level. Technical capacity building is currently being undertaken by the projects LDCF project “CCA Growth: Implementing climate resilient and green economy plans in highland areas in Ethiopia.” Through Components 1 and 2, the Lowland Ecosystems LDCF project will further the ongoing technical capacity development programmes by incorporating lessons learnt into the training modules to be developed.

Risks and Assumptions:

The lists of project risks have been expanded since the original PIF to make them more specific and comprehensive. These risks are summarized in Annex H herein below. The project Manager will follow the UNDP standards in administering the project risk. The Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log. Risks will be reported as critical when the impact and probability are high (i.e. when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher). Management responses to critical risks will also be reported to the GEF in the annual PIR.

Stakeholder engagement plan:

Participation and engagement are the cornerstones for the effective implementation of the project, including its sustainability. There are two levels at which participation/engagement will occur in this regard (i) within the implementing group; and (ii) the broader constituent group. The implementing group incorporates organizations responsible and accountable for the project and those responsible for activities that influence the project, for example, institutions that have a role in the management of lowland ecosystems.

Details of the stakeholder participation during the PPG phase are provided in the table below.

Table 3: List of Stakeholders Consulted

| Type of stakeholders | Roles and Responsibilities |
| --- | --- |
| Government at the federal level: | Supporting, facilitating, coordinating and ensuring: - vertical and horizontal coordination during planning, implementation, reporting, monitoring and evaluation - collaboration and cooperation among stakeholders at all governance levels - implementation and review of project activities - full participation of women in the project activities. - compliance with reporting procedures |
| - Environment, Forest and Climate Change Commission (EFCCC) |  |
| - Ministry of Agriculture and Natural Resources (MoANR) |  |
| - National Meteorology Agency (NMA) |  |
| - Ministry of Water and Energy (MoWE) |  |
| - Ministry of Finance and Economic Cooperation (MoFEC( |  |
| Government at the sub-national level: | - Promote understanding of the project’s outcomes and ownership of the project; - Manage relationships with PMU and steering committee of the Project - Provide technical assistance to land users. - Supervise and provide all technical and logistics support |
| - EFCCC like regional bureaus |  |
| - Regional ANRs |  |
| - Regional water, irrigation and Energy Bureaus |  |
| - Woreda Administrations |  |
| - Woreda EFCCC like bureaus |  |
| Vulnerable groups: | - Work towards the achievement the project’s outcomes; - Engage in planning, implementing and monitoring as well as in the evaluation of the interventions; - Maximize synergies with other on-going projects. |
| - Farmers, agro-pastoralists and pastoralists |  |
| - Women and girls |  |
| - Youth |  |

The stakeholders identified during project preparation will continue to be consulted in project implementation. Furthermore, i) stakeholders of high influence and high importance will be identified and closely involved throughout the implementation of the project to ensure their support for the project (such as water user groups, women associations and youth associations); ii) stakeholders of high influence but low importance will be identified and kept informed and their views on the project will be acknowledged and taken into account in order to avoid disruption or hindrance of the project’s implementation; iii) stakeholders of low influence and high importance will be identified and special efforts will be undertaken to ensure that their needs are met and that their participation is meaningful; iv) stakeholders of low influence and low importance are unlikely to be closely involved in the project and require no special participation strategies (beyond information-sharing).

An updated stakeholder involvement plan that would provide a framework to guide interaction between implementing partners and the key stakeholders will be developed and presented during the project inception workshop. This would guide the stakeholders throughout the project implementation phase. Stakeholders will be consulted throughout the project implementation phase to: i) promote understanding of the project’s outcomes; ii) promote local community ownership of the project through engaging in planning, implementing and monitoring as well as in the evaluation of the interventions; iii) communicate to the public in a consistent, supportive and effective manner and iv) maximise synergies with other on-going projects.

The project’s design incorporates activities and mechanisms to ensure on-going and effective stakeholder participation for different institutions, groups and forum during project implementation, including:

- Project inception phase and workshop will enable stakeholder awareness of the start of project implementation: The project will be launched by a multi-stakeholder workshop. This workshop will provide an opportunity to provide all stakeholders with the most updated information on the project and the project work plan. It will also establish a basis for further consultations as the project’s implementation commences.

- Project Steering Committee ensures representation of stakeholder interests in the project: A Project Steering Committee (PSC) will be constituted to ensure broad representation of all key interests throughout the project’s implementation. PSC is further described in Section VII (Management Arrangements) of the Project Document.

- Regional/project technical platform supports project implementation from the six project regions and relevant sub-regional entities. Representation of women is a priority.

- Project communications facilitate on-going awareness: The project will develop, implement and maintain a communication strategy to ensure that all stakeholders are informed on an on-going basis about the project’s objectives and activities; overall project progress; and the opportunities for involvement in various aspects during project’s implementation.

- Capacity building: Project activities are focused on building the capacity needed– at the systemic, institutional and individual levels – by stakeholders to ensure the sustainability of initial project investments.

Gender equality and empowering women:

Women in the lowland ecosystem of Ethiopia will suffer the most from the effects of climate change. In communities that are highly dependent on local natural resources such as in Ethiopia, women are disproportionately vulnerable to the effects of climate change. Climate change will impact the sectors for which women bear primary responsibility, such as agriculture, nutrition, water and energy supplies. Moreover, because of gender differences in property rights, access to information and cultural, social and economic roles, the effects of climate change will affect men and women differently. This could limit women’s overall influence in decision-making that is relevant for activities on the ground under Components 1 and 2. Furthermore, women’s general stand in society is constrained by their limited access to schooling and training, which contributes to limited access to leadership positions. As stakeholders’ decision taking level, this could constrain their ability to have a say in a number of activities under Component 2.

Although a small contribution to overall empowerment and emancipation at society’s level, these gender considerations and empowerment in this project will help Ethiopia implement its commitments under the Convention on the Elimination of all Forms of Discrimination Against Women (CEDAW), as an example. Doing so is furthermore in line with domestic policies, strategies and action plans.

In terms of getting women actively engaged in lowland climate change adaptation and natural resource management programmes, special programming intervention efforts are focused on designing activities in which rural women will be engaged. The project has deliberately provided for the representation of women in technical committees and platforms in addition to specific activities that support their involvement in the various interventions. Annex G present the gender action plan with which the project will incorporate gender considerations in the implementation procedures for the project. The annex also consists of detail description of proposed gender mainstreaming activities for different outputs that will directly contribute to increasing of women’s adaptive capacity.

All components of the project will be implemented and monitored with gender considerations in the cultural and regional context. Various indicators will also be monitored according to gender. In the composition of project teams, equal opportunities will be offered so as to promote the full and effective participation of women in decision-making and project leadership.

The Box below summarizes some of the important gender considerations that have informed this project.

Box. Example of gender focused project design and implementation

The project will make a defined contribution to women’s empowerment at the local level, defined as the “sum total of changes needed for a woman to realize her full human rights – the combined effect of changes in her own aspirations and capabilities, the environment that surrounds and conditions her choices, and the power relations through which she negotiates her path.”[*] This will be achieved in a manner with which women can feel comfortable, given their own social, cultural and religious context. In other words, through agency, relations and structures - the project will make a contribution to all three dimensions

Relations: Power relations through which she negotiates her path Examples: -Being involved in local decision-making processes -Getting recognized (by external groups) as an important stakeholder in natural resource management and adaptation -Having their issues and ideas heard through a local adaptation process (using good practice in participation)

Agency: Changes in her own aspirations and capabilities Examples: -Knowledge of climate trends -Access to appropriate measures (incl. technologies) for adaptation -Access to income-generating employment via the HIMO approach**; and, when women are able to earn an income, their families are more likely to benefit

Structures: Environment that surrounds and conditions her choices Examples: Gender equitable adaptation planning at local level (and support from national and regional level to implement these plans)

Notes: Borrowing from Care International’s definition of gender empowerment. See e.g. http://www.care-international.org/what-we-do/our-focus-on-women-and-girls.aspx - HIMO refers to "Haute Intensité en Main d'Œuvre" or labour intensive works.

South-South and Triangular Cooperation (SSTrC):

This project is country specific and does not focus on collaboration with other countries for the implementation of project activities. However, it draws on global principles of climate change adaptation and sustainable natural resource management and the lessons learnt from the project will be disseminated regionally. It is also planned that the project will share its experiences and lessons at regional and global climate change adaptation fora, including the annual Community Based Adaptation Conferences.

Sustainability, Innovativeness and Scaling Up:

Sustainability:

The project will introduce several new interventions that include practices and technologies that will need to continue beyond its lifetime. Specifically, the use of climate forecasts and decision-making tools will be novel to most lowland communities. The sustainability of the project lies in its strong ownership within the community. Sustainability considerations are embedded in several activities proposed under the project. Measures have been taken to ensure that project activities continue beyond the duration of project implementation, with long-term benefits to all stakeholders, including the GoE and local communities.

Stakeholders at various levels, including: i) national-level; ii) regional level, iii) woreda-level; iv) community-level; and v) individual-level have been consulted throughout the PPG phase. During these consultations, stakeholders were asked to identify the major impacts of climate change, and the activities they viewed as necessary to overcome these climate-induced problems. The needs and recommendations of stakeholders have consequently been integrated into the project design, thereby ensuring that these needs are met and the participation and ownership of land users and government stakeholders is assured. It is worth noting that there is a strong commitment to the successful implementation of the project by government stakeholders who will be contributing most of the human resources, technical expertise and support throughout.

Activities such as ToT build productive relationships and contribute to sustainable knowledge transfer. The results of improved training programmes through a TOT approach and collaboration with MoANR and other members of the Agro-Met Task Force will equip extension and development agents to provide local communities with downscaled agro-meteorological information that offers guidance and advice on response strategies to the expected extreme weather events. The provision of such capacity development support to the targeted woredas will allow local communities to prepare for climate change threats long after the project has ended. Furthermore, long-term initiatives of the program such as the delivery of weather forecast services will continue into the future beyond the duration of the project.

In addition, stakeholders’ consultation/participation has shown to encourage ownership and improve sustainability of past projects in Ethiopia. In other countries, capacity development has been proven to enhance government officials’ knowledge of climate change concepts thereby improving their ability to integrate climate change into government budgetary processes and to leverage private sector investment into watershed management. In light of this, the proposed LDCF project will focus on building capacity, increasing awareness and improving understanding of climate change risks and opportunities amongst government staff and local communities at both national and sub-national levels. As key development agents, trained local stakeholders and decision-makers consisting of both women and young people will in turn have the best chance of becoming multipliers and securing benefits beyond the direct investment.

For livestock management, it is proposed that the project should build on the results and models promoted by the highly successful related projects that have promoted the distribution of naturally resilient and locally breed species. The present project will show how it also applies in the propagation of improved fodders species to support the pastoralists fodder storage.

Implementation of livelihoods-focused programmes will bring socioeconomic benefits to local communities targeted by the project. Medium to long-term socioeconomic benefits catalyzed by the project will include increased land productivity and yields for food crops, and availability of water resources among others. These will enable local communities to generate additional income, further increasing their resilience to future climate change beyond the scope of the project.

In order to ensure sustainability of project supported and procured equipment especially the solar water pump, youths at the community level would be trained and empowered to support solar water pump maintenance as part of local entrepreneurship and job creation. A time-based agreement with the implementing entity or MoU for post project operations and maintenance of equipment in partnership with the communities and the woreda administrators will also be made with trained youths. Local communities will make contributions towards the costs of maintaining the equipment, while the monitoring of these will be embedded in the programmes of the relevant government programmes, local institutions and NGOs working the respective woredas.

Innovation:

Innovative approaches to adaptive farming, pastoralism and agro-pastoralism – based on international best practices – will be introduced to local communities. In addition, the development of alternative livelihoods that will promote the resilience of local communities will be undertaken in parallel with the establishment of CBEs to facilitate improved smallholder access to markets. This will increase the sustainability of these livelihoods by improving the economic viability of approaches introduced through this project. The nature-based solutions would be promoted for flood and erosion control, including river bank and land stabilization in catchment areas. With current research on new materials, ‘nature-based solutions’, as with the use of indigenous grass are rather innovative. They are equally more sustainable and likely more cost effective, than infrastructural solutions alone. The planting of climate-resilient species will have additional benefits including: i) stabilizing soil to prevent soil erosion; ii) increasing infiltration, thereby raising groundwater levels; iii) mitigating the intensity of water runoff and flood impacts; and iv) sequestering carbon in the soil. Special provision has also been made and budgeted for to promote specific and but direct investment in community infrastructure and alternative livelihoods creation for Woredas with capacity to include additional site making maximum of 3 sites per woreda

The project implementation is also innovative in the context of Ethiopia’s lowlands and would be delivered in the following ways: i). training modules would be hosted online to provide training for other institutions in future; ii) mobile phones will be provided to communities to access climate information and agro-advisory services; and iii). Solar water pumps provided to aid water delivery from reservoirs to irrigated farmlands, while youths at the local communities would be trained to provide maintenance support on solar solutions.

Finally, the outcomes of the project interventions, the experience-sharing workshops and the best practice project reports will be used to build an evidence base for climate-resilient farming, agro-pastoralism and pastoralism in Ethiopia and these cases made available online for future references.

Scaling up

Two pathways will be followed for scaling up the project, underpinned by the knowledge management component of the project. The first pathway is the autonomous uptake of the practices and technologies introduced by the project. This will take the form of providing information within and outside the project areas that will enable non-participants to see the benefits arising from the project and accruing to those participating in it. The awareness functions will be tailored such that it demonstrates the practical application of practices and technologies without the aid of project funds. The process will also involve private sector players to be part of the awareness programmes, with them providing information on how the technologies and other inputs used in for instance climate smart agriculture can be accessed by individual households and groups.

The second pathway is to embed project practices in government and NGO programmes so that they are promoted in other regions. To promote the up-scaling of effective project activities across Ethiopia’s arid and semi-arid areas, decision-makers in the GoE responsible for national budget allocations will be provided with the project’s evidence base in a concise, accessible format. This will enable them to allocate resources towards the promotion of effective practices in other regions.

# Project Management

Cost efficiency and effectiveness:

The SLMP in Ethiopia demonstrated the importance of a holistic soil and water conservation approach to promote sustainable productivity and livelihoods for communities in Ethiopia. To this effect, lessons learned from the two decades of SLMP experience are used to inform the design of the proposed LDCF project for cost-efficiency and effectiveness. The design of the Project is also corroborated by information presented in the NAPA of Ethiopia, particularly with regards to the selection of cost-effective measures. In the development of the NAPA, multi-criteria analyses were undertaken in order to prioritize actions according to their potential for positive effects on economic development, social capital and environmental management. As such, the actions proposed by the NAPA are not only the most urgent and most pressing, but have also been assessed to be cost-effective. The proposed LDCF project is thus designed to align with the priorities articulated under the NAPA; for example, with key Adaptation Need 24; ii) 29 and iii) 32), in order to implement necessary actions that have already been identified as cost-effective.

Accordingly, the following strategies identified in the final design of the project enables the project to be more cost-effective and efficient compared to their alternatives that could have otherwise been used:

(i) Reaching a wider audience of land users and government stakeholders across the lowland ecosystem of Ethiopia through a TOT approach. This is more cost efficient than reaching out to every farmer individually. It also builds up the economies of scale by enabling trained farmers to reach out to more farmers even beyond the lifetime of the project.

(ii) Adopting an implementation modality of the project using existing government structures avoids costs that would otherwise occur if new structures were put in place.

(iii)Disseminating credible information and advisory services through a locally suitable communication channels. The alternative would have to set up new channels that are dedicated to the project, which would be more costly, time consuming and not suitable for local needs. New channels would need to be piloted, but the locally available ones are tried and tested, ready to be used.

(iv) Conducting a “learning by doing” training to promote clarity and commitment of beneficiaries. This strategy provides an opportunity for beneficiaries to be part of shaping interventions and understand the way they work. It enables them to make incremental investment into the adoption of practices and technologies that they understand through a learning by doing approach. It enables beneficiaries to grow with the project, which minimizes the need for costly follow-up activities after the project.

(v) Providing needs-responsive support to promote ownership and contribute to project success and efficient use of resources. This is opposed to the strategy to providing a blanket of support measures that are not aligned to the needs of the beneficiaries, which runs the risk of some of them not being fully adopted and sustained in the long term.

Several other considerations have been taken into account in the design of the project to ensure cost-efficiency and effectiveness. The interventions under the project have been determined through consultations undertaken at all governance levels so as to ensure that products are well targeted to needs, explore low cost options and reaffirm the need to align with NAPA priorities (see Section II – Development Challenge) that have already been identified as cost-effective. In order to avoid duplication of efforts and double counting, the proposed LDCF project will pursue active partnerships with other on-going initiatives, including the FAO project on Fall Army Worm as well as with the Agro-met initiative of the MoANR, the Green Climate Fund (GCF) financed project-‘’Responding to the increasing risk of drought’’ and the Adaptation Fund (AF) financed project- ‘’Building gender responsive resilience of the most vulnerable communities’’.

Although some proposed interventions under the project would have immediate adaptation benefits such as improved yields as a result of planting drought-resistant crop varieties and increased income as a result of animal fattening or bee keeping activities, other economic and ecological benefits emanating from the implementation of climate smart technologies and practices under this are likely to become visible following restoration of degraded land at a watershed level. Therefore, the proposed LDCF project will deliver even greater long-term benefits relative to the baseline situation by restoring degraded land at a watershed level.

In addition, under Component 1, Outcome 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools would be achieved through working very closely with government partners and extension services, trying to strengthen the mechanisms that are already in place. The measures under Component 1, Outcome 2 are designed to strengthen government/ministry coordination and more generally coordination amongst actors at a regional and woreda scale. Component 2 which seeks to promote climate change adaptation practices strengthens the resilience of vulnerable communities to climate change in the selected sites by enabling the incorporation of nature-based solutions and using locally available materials.

Furthermore, the project is built on strategic design considerations such as cost effectiveness of demonstration interventions and up-scaling potential within the regions by being situated in six neighboring lowland regions. The template and design would basically have similar approach that would only require replication in different woredas. The project has selected only two woredas from each region to encourage learning and scale of project management support. This would help in minimizing logistics and other costs of engagement. In most cases, the two chosen woredas are quite large and can have a wide strategic impact (especially regarding water accessibility); while at the same time as helping in developing outputs that can be adapted elsewhere.

Project management:

The project will be implemented over a period of six years (72 months) through the National Implementation Modality (NIM) and procedures. The Standard Basic Assistance Agreement between UNDP and the GoE, and the Country Programme will be applied as the basis of the agreement. The project will be executed by the Environment, Forests and climate Change Commission (EFCCC); which is the Implementing Partner of this project. The Implementing Partner will be responsible for coordinating action on the ground and for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources. The Implementing Partner will also engage partners and service providers, including those that will be directly tasked with implementation, while also closely monitoring the project and reporting according to procedures. Due to the geographical distance between the capital and the project regions, project activities will be implemented under the single national Project Management Unit (PMU), which will be situated in Addis Ababa in the capital with Regional Centers serving as services support bases for the interventions at woreda level.

Details of the Management and project governance structure is available on Section VIII

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): SDG 8 – Promote sustained inclusive and sustainable economic growth, full and productive employment and decent work for all; SDG 12 – Achieve food security and improved nutrition and promote sustainable agriculture; SDG 13 – Take urgent action to combat climate change and its impacts; SDG 15 – Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forest, combat desertification, and halt and reverse land degradation and halt biodiversity loss. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: UNDAF Outcome: By 2020, key government institutions at national level and in all regions and cities are able to plan, implement and monitor priority climate change mitigation and adaptation actions and sustainable natural resource management. |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan: Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemical and waste. |  |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks/Assumptions |
| Project Objective: To promote climate change adaptation and sustainable economic growth among communities in Ethiopia’s lowland ecosystems | Mandatory indicator: Number of direct project beneficiaries - dis-aggregated by gender. | 0 | 60,000 in the project zone, of which at least 52% are female | 120,000 in the project zone, with at least 52% female | Project’s periodic reports, validated by independent evaluations and reviews. Risks: Uncertainty in climate-related data and projections at regional and local (woreda) level provides insufficient parameters for planning adaptation measures Assumptions: High level of vulnerability is currently due to climate data, poverty, and resource dependence. All households in the project area are committed to participating in the project activities and adopting climate adaptation technologies and practices and work collaboratively to develop and implement additional income-generating activities in each of the 12 target Woredas. |
| Component 1/Outcome1 Technical Capacity for planning diversified climate change adaptation practices strengthened | Number of participants trained on key adaptation issues, including community-based adaptation techniques | 0 | At least 600 beneficiaries educated in topics related to climate change adaptation. At least 50% of the beneficiaries are female. | At least 1200 beneficiaries educated in topics related to climate change adaptation At least 50% of the beneficiaries are female. | Project’s periodic reports, validated by independent evaluations and reviews. |
|  |  |  |  |  | Risks: Staff turnover Assumptions: Experts trained are active in providing training in the topics related to climate change adaptation. |
|  | Number of Climate adaptive action plans developed taking into consideration climate smart approaches and future scenario. | 0 action plans | 6 relevant climate smart action plans at identified sites in each woreda. | 12 relevant climate smart action plans at identified sites in each woreda. | Project’s periodic reports validated by independent evaluation and reviews. Risks: Process of preparing participatory and Climate adaptive action plan can be slow for various reasons outside the project control Assumptions: Current action plans do not mainstream climate smart approach and consideration for future climate adequately |
| Component 1/ Outcome 2 Climate adaptive management adopted by local communities through accessible climate information and decision-making tools | Number of AWS operational in each of the 9 uncovered Woredas | 3 AWS are currently installed at some targeted woredas. | 7 operational AWS in the 12 woredas | 12 operational AWS (one in each of the 12 woredas) | Project’s periodic reports, validated by independent evaluations and reviews. Assumptions: The NMA is committed to promoting, installing AWS in each woreda. The NMA staff is responsible for long –term upkeep and maintenance of installed equipment |
|  | Number of people with access to weather forecasts and advisory services at project sites – disaggregated by gender | 0 | 600 beneficiaries of which at least 52% are female | 1,200 of which at least 52% are female | Project’s periodic reports validated by independent evaluation and reviews. Risks: Mobile phones diverted and does not reach land users Assumptions: Woreda Offices staff, extension agents and communities willing to adopt and utilize technology for sharing climate and weather information. |
| Component 2/ Outcome 3 Climate change adaptation practices implemented by communities in lowland ecosystems. | Ha of degraded land rehabilitated, forested or restored | 0 ha | Approx. 50ha per each woreda of degraded land rehabilitated | Approx. 100ha per each woreda of degraded land rehabilitated, i.e. min. of 1,200ha in total by project end, as a result of various activities under outputs 3.1, 2.2, 3.2, 3.3 | Project’s periodic reports validated by independent evaluation and reviews. |
|  |  |  |  |  | Risks: Assumptions: Extension agents and local communities are willing to adopt a participatory approach and work collaboratively to develop and implement action plans in each of the 12 target woredas |
|  | Population benefiting from the adoption of diversified, climate-resilient livelihood options: Number of people % of female % of the target population | - 0 - 0 - 0 | 60,000 people with 52% female | - 120,000 people - 52% female - 10% of the target population | Project’s periodic reports validated by independent evaluation and reviews. Risks: Lack of finance Assumptions: Extension agents and local communities are willing to adopt a participatory approach and work collaboratively to develop and implement action plans in each of the 12 target woredas |
| Component/ Outcome 4 Knowledge Management and M&E | % increase in number of beneficiaries aware of climate risks and knowledge of response measures (established based on surveys) | 0 level of awareness for beneficiaries | 50% beneficiaries awareness level reaches, with 52% female | a) 100% beneficiaries awareness reached b) 52% female | Project’s survey reports validated by independent evaluation and reviews. Risks: Assumptions: Stories/testimonies from representatives of project intervention sites, target groups or beneficiaries are sufficiently interesting to be portrayed as climate adaptive strategies and awareness. |

# Monitoring and Evaluation (M&E) Plan

The project results, corresponding indicators and mid-term and end-of-project targets in the project results framework will be monitored annually and evaluated periodically during project implementation. If baseline data for some of the results indicators is not yet available, it will be collected during the first year of project implementation. The Monitoring Plan included in Annex details the roles, responsibilities, and frequency of monitoring project results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office is responsible for ensuring full compliance with all UNDP project monitoring, quality assurance, risk management, and evaluation requirements.

Additional mandatory GEF-specific M&E requirements will be undertaken in accordance with the GEF Monitoring Policy and the GEF Evaluation Policy and other relevant GEF policies. The costed M&E plan included below, and the Monitoring plan in Annex, will guide the GEF-specific M&E activities to be undertaken by this project.

In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report.

Additional GEF monitoring and reporting requirements:

Inception Workshop and Report:  A project inception workshop will be held within 60 days of project CEO endorsement, with the aim to:

- Familiarize key stakeholders with the detailed project strategy and discuss any changes that may have taken place in the overall context since the project idea was initially conceptualized that may influence its strategy and implementation.

- Discuss the roles and responsibilities of the project team, including reporting lines, stakeholder engagement strategies and conflict resolution mechanisms.

- Review the results framework and monitoring plan.

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP and other stakeholders in project-level M&E.

- Update and review responsibilities for monitoring project strategies, including the risk log; SESP report, Social and Environmental Management Framework and other safeguard requirements; project grievance mechanisms; gender strategy; knowledge management strategy, and other relevant management strategies.

- Review financial reporting procedures and budget monitoring and other mandatory requirements and agree on the arrangements for the annual audit.

- Plan and schedule Project Board meetings and finalize the first-year annual work plan.

- Formally launch the Project.

GEF Project Implementation Report (PIR):

The annual GEF PIR covering the reporting period July (previous year) to June (current year) will be completed for each year of project implementation. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR. The PIR submitted to the GEF will be shared with the Project Board. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

GEF and/or LDCF/SCCF Core Indicators:

The GEF and/or LDCF/SCCF Core indicators included as Annex will be used to monitor global environmental benefits and will be updated for reporting to the GEF prior to MTR and TE. Note that the project team is responsible for updating the indicator status. The updated monitoring data should be shared with MTR/TE consultants prior to required evaluation missions, so these can be used for subsequent ground truthing. The methodologies to be used in data collection have been defined by the GEF and are available on the GEF website. If relevant to the project: The required Protected Area Management Effectiveness Tracking Tool (METTs) have been prepared and the scores included in the GEF Core Indicators.

Independent Mid-term Review (MTR):

The terms of reference, the review process and the final MTR report will follow the standard templates and guidance for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC).

The evaluation will be ‘independent, impartial and rigorous’. The evaluators that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project under review.

The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the evaluation process. Additional quality assurance support is available from the BPPS/GEF Directorate.

The final MTR report and MTR TOR will be publicly available in English and will be posted on the UNDP ERC by November 2023. A management response to MTR recommendations will be posted in the ERC within six weeks of the MTR report’s completion.

Terminal Evaluation (TE):

An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance for GEF-financed projects available on the UNDP Evaluation Resource Center.

The evaluation will be ‘independent, impartial and rigorous’. The evaluators that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project being evaluated.

The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the BPPS/GEF Directorate.

The final TE report and TE TOR will be publicly available in English and posted on the UNDP ERC by November 2026.  A management response to the TE recommendations will be posted to the ERC within six weeks of the TE report’s completion.

Final Report:

The project’s terminal GEF PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

Table 4: Mandatory GEF M&E Requirements and M&E Budget

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop | UNDP Country Office | $11,000 | None | Within two months of project document signature |
| Inception Report | Project Manager | None | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Quarterly, annually |
| Risk management | Project Manager Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework and environmental and social risks | Project Manager M&E Specialist Woreda Project Officers | Per year: $4,000 LDCF = $10,000 Total (LDCF+TRAC = $24,000) | 14,000 | Annually before PIR |
| GEF Project Implementation Report (PIR) | Project Manager and UNDP Country Office and UNDP-GEF team | None | None | Annually |
| Lessons learned and knowledge generation | Project Manager | Per year: $2,000 ($12,000) | None | Annually |
| Monitoring Implementation of Stakeholder Engagement Plan | Project Manager UNDP Country Office | $2,500 | None | On-going |
| Monitoring Implementation of Gender Action Plan | Project Manager UNDP Country Office UNDP GEF team | $2,500 | None | On-going |
| Addressing environmental and social grievances | Project Manager UNDP Country Office | $3,000 | None | On-going |
| Project Board meetings | Project Board UNDP Country Office Project Manager | Per year: $3,000 ($18,000) | None | At minimum annually |
| Supervision missions | UNDP Country Office | None |  | Annually |
| Oversight missions | UNDP-GEF team | None | None | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Manager and UNDP-GEF team | None | None | To be determined. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 50,000 | None | Between 2nd and 3rd PIR. |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 50,000 | None | At least three months before operational closure |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | $159,000 | 14,000 |  |

# Governance and Management Arrangements

Roles and responsibilities of the project’s governance mechanism: The project will be implemented following UNDP’s national implementation modality, according to the Standard Basic Assistance Agreement between UNDP and the Government of Ethiopia, and the Country Programme.

The Implementing Partner for this project is Environment Forest and Climate Change Commission (EFCCC).

The Implementing Partner is responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources.

The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Risk management as outlined in this Project Document;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets;

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

The project organisation structure is as follows:

Implementing Partner:

Environment, Forest and Climate Change Commission

Project Board/National Project Steering Committee

Development Partners

UNDP RR

Project Executive

Environment, Forest and Climate Change Commission

Beneficiary Representatives

MoANR, MoLF, NMA, Regional and Zonal EFCCC, DRMC, EBI, EEFRI, EAI, APADB, OPDC

Project Assurance

UNDP

Country Office Programme Specialist

Regional Technical Advisor

Principal Technical Advisor

Project Management Unit:

National Project Manager, Project Technical Specialist, Woreda Project Assistant, Finance Assistants

Project Organisation Structure

Responsible Party – Service Provider to be determined and contracted as necessary

Responsible Party – Service Provider to be determined and contracted as necessary

Responsible Party – Service Provider to be determined and contracted as necessary

PROJECT BOARD/ NATIONAL PROJECT STEERING COMMITTEE:  Project implementation will be overseen by the Project Board herein refer to as the National Steering Committee (NPSC) as described below is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

Specific responsibilities of the Project Board include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the project manager;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on project manager’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

- Ensure highest levels of transparency and take all measures to avoid any real or perceived conflicts of interest.

The NPSC will be comprised of individuals representing the following institutions: EFCCC (Co-chair); UNDP (Co-chair); MoANR; Ministry of Finance and Economic Cooperation (MoFEC); National Meteorological Agency (NMA); Ministry of Water, Irrigation and Energy (MoWIE); Regional Representatives (Six regional representatives - one from each region) of EFCCC replica, Disaster Risk Management Commission (DRMC), Ethiopian Biodiversity Institute (EBI), Ethiopian Wildlife Conservation Authority (EWCA), Ethiopian Environment and Forestry Research Institute (EEFRI), Ethiopian Agricultural Institute (EAI), Afar Pastoral and Agriculture Development Bureau (APADB) and Oromiya Pastoral Development Commission (OPDC).

Meetings of the NPSC will be held on a bi-annual basis. Additional meetings can be scheduled as needed. The terms of reference for the PSC are contained in Annex D.

In order to ensure UNDP’s ultimate accountability for the project results, NPSC decisions will be made in accordance to standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

In case consensus cannot be reached within the Board, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

Potential members of the NPSC are reviewed and recommended for approval during the PAC meeting. Representatives of other stakeholders can be included in the NPSC as appropriate.

The NPSC contains three distinct roles, including:

(1) An Executive: the individual representing the project ownership to chair the group, which will be the EFCCC.

The Executive’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The executive has to ensure that the project gives value for money, ensuring cost-conscious approach to the project, balancing the demands of beneficiary and suppler.

Specific Responsibilities: (as part of the above responsibilities for the Project Board)

- Ensure that there is a coherent project organisation structure and logical set of plans;

- Set tolerances in the AWP and other plans as required for the Project Manager;

- Monitor and control the progress of the project at a strategic level;

- Ensure that risks are being tracked and mitigated as effectively as possible;

- Brief relevant stakeholders about project progress;

- Organise and chair Project Board meetings.

(2) The Senior Supplier: individual or group representing the interests of the parties concerned which provide funding for specific cost sharing projects and/or technical expertise to the project. The Senior Supplier’s primary function within the NPSC is to provide guidance regarding the technical feasibility of the project. In the case of this project this will be UNDP.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Make sure that progress towards the outputs remains consistent from the supplier perspective;

- Promote and maintain focus on the expected project output(s) from the point of view of supplier management;

- Ensure that the supplier resources required for the project are made available;

- Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts.

(3) The Senior Beneficiary: individual or group of individuals representing the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the NPSC is to ensure the realization of project results from the perspective of project beneficiaries. This is the EFCCC, on behalf of the Government of Ethiopia.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Prioritize and contribute beneficiaries’ opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Specification of the Beneficiary’s needs is accurate, complete and unambiguous;

- Implementation of activities at all stages is monitored to ensure that they will meet the beneficiary’s needs and are progressing towards that target;

- Impact of potential changes is evaluated from the beneficiary point of view;

- Risks to the beneficiaries are frequently monitored.

The Project Assurance role supports the NPSC by carrying out objective and independent project oversight and monitoring functions. The Project Manager and Project Assurance roles should never be held by the same individual for the same project. UNDP fulfills the Project Assurance role.

Woreda Steering Committee (WSC): The project will use a similar approach to that of the MERET programme by establishing a WSC in each Woreda. The WSCs will regularly consult with relevant CBOs, farmer, pastoralist, women and youth groups, as well as landless women and youth to ensure that project interventions are benefiting all stakeholders.

Each of the twelve Woredas will have a WSC comprising: i) the Woreda Administrator (Chair of the WSC); ii) an EFCCC representative (Secretary to WSC); iii) a Woreda Project Officer (WPO); iv) a local university representative; v) local CBO representatives (including women and youth groups); vi) a CBO representative; vii) a representative for MFIs; and a sectoral representative from both from the Woreda and Kebele levels from the following government departments: Ministry of Environment, Forest, Climate Change; Land Use Administration; Crop Production; Animal Production; and Cooperative offices.

The WSCs will meet at least three times a year. Tasks of the WSC include the following:

- creating an environment conducive for farmers, women, unemployed youth and other vulnerable groups to set and achieve targets;

- ensuring effectiveness of project activities in converting the project sites into a climate resilient landscape;

- providing needs-driven capacity development support for women, unemployed youth and other vulnerable groups in reaching development targets;

- assisting in the formulation of bankable climate resilient investment plans by farmers, women and unemployed youth for the up scaling of project interventions;

- executing specific strategic actions such as organising competitions regarding CCA Lowland Ecosystems Project activities among high school or undergraduate students; awarding farmers for outstanding performance; or awarding politicians for their pro-CCA Lowland Ecosystems Project political work; and

- Facilitating the sharing of achievements, lessons and experiences amongst stakeholders.

The Project Management Unit (PMU) will be responsible for running the project on a day-to-day basis on behalf of the Implementing Partner and within the constraints laid down by the NSC. The PMU will be hosted within the EFCCC. The additional members of the PMU will provide project administration, management and technical support to the PM as required by the needs of the individual project or PC. The PM’s function will end when the final project terminal evaluation report and corresponding management response, and other documentation required by the GEF and UNDP, have been completed and submitted to UNDP (including operational closure of the project). The PMU will work closely with the NPSC as well as the WSCs throughout the implementation of the project. Specific tasks of the PMU will include the following:

- ensure CCA Lowland Ecosystems Project activities are implemented according to the set objectives;

- facilitate communication and meetings of the NSC in order to review activities achieved, and discuss activities planned for approval and implementation;

- ensure WSCs report periodically and on schedule regarding progress/performance/budget execution against the M&E framework and budget of the project;

- support Woreda Project Officers (WPOs) to collaborate with active like-minded organisations to improve and upscale project activities among farmers, women, unemployed youth and other vulnerable groups in their respective Woredas;

- hold regular meetings and other ad hoc meetings with the WPOs in order to discuss plans and progress, and to

- follow‐up any concerns the WPOs or the beneficiary groups may have; and

- Coordinate and liaise with other donor and government project managers to ensure that synergies are built and that there is no overlap of tasks.

The Project Manager (PM) will run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the NPSC. The PM function will end when the final project terminal evaluation report, and other documentation required by the GEF and UNDP, has been completed and submitted to UNDP (including operational closure of the project).

The Implementing Partner appoints the Project Manager, who should be different from the Implementing Partner’s representative in the Project Board.

Specific responsibilities include:

- Provide direction and guidance to project team(s)/ responsible party (ies);

- Liaise with the Project Board to assure the overall direction and integrity of the project;

- Identify and obtain any support and advice required for the management, planning and control of the project;

- Responsible for project administration;

- Plan the activities of the project and monitor progress against the project results framework and the approved annual workplan;

- Mobilize personnel, goods and services, training and micro-capital grants to initiative activities, including drafting terms of reference and work specifications, and overseeing all contractors’ work;

- Monitor events as determined in the project monitoring schedule plan/timetable, and update the plan as required;

- Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments or reimbursement using the fund authorization and certificate of expenditures;

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports;

- Be responsible for preparing and submitting financial reports to UNDP on a quarterly basis;

- Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Capture lessons learned during project implementation;

- Prepare the annual workplan for the following year; and update the Atlas Project Management module if external access is made available.

- Prepare the GEF PIR and submit the final report to the Project Board;

- Based on the GEF PIR and the Project Board review, prepare the AWP for the following year.

- Ensure the mid-term review process is undertaken as per the UNDP guidance, and submit the final MTR report to the Project Board.

- Identify follow-on actions and submit them for consideration to the Project Board;

- Ensure the terminal evaluation process is undertaken as per the UNDP guidance, and submit the final TE report to the Project Board;

The Project Technical Specialist/Deputy Project Manager (DPM) will assist the PM to discharge the duties listed above. Details of TORs of the members of the PMU are included in Annex D.

A Woreda Project Assistant/Officer (WPO) will be selected for each Woreda. The WPOs will be responsible for the annual management, accountability and general oversight on the planning, implementing, monitoring and reporting of the five-year project. Additionally, the WPOs will be responsible for developing a database of lessons learned corresponding to each component of the project. The database will provide useful information from which implementing groups and other stakeholders can benefit. WPOs will also manage annual plans and budgets as well as develop corresponding reports on progress that will be submitted to the NSC for review and feedback. The woreda based Finance Assistants will also assist the woreda officers to administer and account for the project activities funding directed to the woredas and the communities.

The Project Assurance of UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes oversight of project execution to ensure that the project is being carried out in accordance with agreed standards and provisions. UNDP is responsible for delivering GEF project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation. UNDP is also responsible for the Project Assurance role of the Project Board/Steering Committee.

Project extensions: The UNDP Resident Representative and the UNDP-GEF Executive Coordinator must approve all project extension requests. Note that all extensions incur costs and the GEF project budget cannot be increased. A single extension may be granted on an exceptional basis and only if the following conditions are met: one extension only for a project for a maximum of six months; the project management costs during the extension period must remain within the originally approved amount, and any increase in PMC costs will be covered by non-GEF resources; the UNDP Country Office oversight costs in excess of the CO’s Agency fee specified in the DOA during the extension period must be covered by non-GEF resources.

# Financial Planning and Management

The total cost of the project is $16,286,073. This is financed through a LDCF grant of $5,836,073, $200,000 in cash co-financing to be administered by UNDP and $10,250,000 in parallel co-financing.  UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP bank account only.

Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

| Co-financing source | Co-financing type | Co-financing amount | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| UNDP | Grant | 200,000 | All of the Components | More pressing challenges emerge for UNDP to support government on other development issues and fund for environmental interventions get redirected. | At the beginning of the planning year, co-financing for GEf-funded projects would be set aside and allocated to the project as appropriate. |
| EFCCC | In Kind | 10,250,000 | All the Components. Staff, Office space, Capacity building. | Weak commitment and engagement | The project coordinator will work with the respective project partners to look for mutual solutions to mitigate the impact on project results. |

Budget Revision and Tolerance: As per UNDP requirements outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board.

Should the following deviations occur, the Project Manager/CTA and UNDP Country Office will seek the approval of the BPPS/GEF team to ensure accurate reporting to the GEF:

a) Budget re-allocations among components in the project budget with amounts involving 10% of the total project grant or more;

b) Introduction of new budget items that exceed 5% of original GEF allocation.

Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies. Audit cycle and process must be discussed during the Inception workshop. If the Implementing Partner is an UN Agency, the project will be audited according to that Agencies applicable audit policies.

Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. All costs incurred to close the project must be included in the project closure budget and reported as final project commitments presented to the Project Board during the final project review. The only costs a project may incur following the final project review are those included in the project closure budget.

Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. Operational closure must happen with 3 months of posting the TE report to the UNDP ERC. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

Transfer or disposal of assets: In consultation with the Implementing Partner and other parties of the project, UNDP is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file. The transfer should be done before Project Management Unit complete their assignments.

Financial completion (closure):  The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

The project will be financially completed within 6 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the BPPS/GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the BPPS/GEF Directorate in New York. No action is required by the UNDP Country Office on the actual refund from UNDP project to the GEF Trustee.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Proposal or Award ID: | 00116829 | Atlas Primary Output Project ID: | 00113814 |
| Atlas Proposal or Award Title: | Climate change adaptation in the lowland ecosystems |  |  |
| Atlas Business Unit | ETH 10 |  |  |
| Atlas Primary Output Project Title | Climate Change Adaptation in the Lowland Ecosystems of Ethiopia |  |  |
| UNDP-GEF PIMS No. | 5630 |  |  |
| Implementing Partner | Environment, Forest and Climate Change Commission |  |  |

| GEF Component/ Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (US$) | Amount Year 2 (US$) | Amount Year 3 (US$) | Amount Year 4 (US$) | Amount Year 5 (US$) | Amount Year 6 (US$) | Total (US$) | See Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Technical capacity for implementing diversified climate change adaptation practices strengthened | EFCCC | 62160 | LDCF | 71300 | Local Consultants | 100,000 | 50,000 | 6,600 | 0 | 0 | 0 | 156,600 | 1 |
|  |  |  |  | 71600 | Travel | 41,000 | 5,000 | 5,050 | 0 | 0 | 0 | 51,050 | 2 |
|  |  |  |  | 71800 | Contractual Services-Imp Partn | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 72,000 | 3 |
|  |  |  |  | 72300 | Materials & goods | 22,000 | 0 | 0 | 0 | 0 | 0 | 22,000 | 4 |
|  |  |  |  | 74200 | Audio visual & print production costs | 6,000 | 2,000 | 2,000 | 1,450 | 500 | 500 | 12,450 | 5 |
|  |  |  |  | 75700 | Training, Workshop and Conferences | 50,000 | 50,000 | 10,000 | 5,000 | 5,000 | 3,900 | 123,900 | 6 |
|  |  |  |  | 72200 | Equipment & Furniture | 4,500 | 0 | 0 | 0 | 0 | 0 | 4,500 | 7 |
|  |  |  |  | 73400 | Rental & Maint. of Other Equip | 0 | 1,500 | 1,500 | 1,500 | 1,500 | 1,500 | 7,500 | 8 |
|  |  |  |  |  | Total Outcome 1 | 235,500 | 120,500 | 37,150 | 19,950 | 19,000 | 17,900 | 450,000 |  |
| OUTCOME 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools | EFCCC | 62160 | LDCF | 71600 | Travel | 27,000 | 5,000 | 10,000 | 1,000 | 1,500 | 1,500 | 46,000 | 9 |
|  |  |  |  | 72100 | Contractual services - Companies | 56,000 | 144,000 | 2,600 | 0 | 0 | 0 | 202,600 | 10 |
|  |  |  |  | 72300 | Materials & goods | 270,000 | 6000 | 4,000 | 5,000 | 5,000 | 5,000 | 295,000 | 11 |
|  |  |  |  | 74200 | Audio visual & print production costs | 12,000 | 10,000 | 6,982 | 0 | 0 | 0 | 28,982 | 12 |
|  |  |  |  | 75700 | Training, Workshop and Conferences | 76,000 | 20,000 | 1,200 | 0 | 0 | 0 | 97,200 | 13 |
|  |  |  |  | 72200 | Equipment & Furniture | 4,500 | 0 | 0 | 0 | 0 | 0 | 4,500 | 14 |
|  |  |  |  | 73400 | Rental & Maintenance of Other Equip | 0 | 1,500 | 1,500 | 1,500 | 1,500 | 1,500 | 7,500 | 15 |
|  |  |  |  |  | Total Outcome 2 | 445,500 | 186,500 | 26,282 | 7,500 | 8,000 | 8,000 | 681,782 |  |
| OUTCOME 3: Climate change adaptation practices adopted in communities in lowland ecosystems EFCCC | EFCCC | 62160 | LDCF | 71300 | Local Consultants | 461,200 | 421,083 | 0 | 0 | 0 | 0 | 882,283 | 16 |
|  |  |  |  | 71800 | Contractual Services-Imp Partn | 72,000 | 72,000 | 72,000 | 72,000 | 72,000 | 72,000 | 432,000 | 17 |
|  |  |  |  | 71600 | Travel | 10,000 | 15,000 | 15,000 | 15,000 | 10,000 | 10,000 | 75,000 | 18 |
|  |  |  |  | 72300 | Materials & goods | 11,200 | 1,476,900 | 666,000 | 620,000 | 36,900 | 2,200 | 2,813,200 | 19 |
|  |  |  |  | 74200 | Audio visual & print production costs | 33,000 | 9,200 | 2,200 | 0 | 8,000 | 5,000 | 57,400 | 20 |
|  |  |  |  | 75700 | Training, Workshop and Conferences | 48,000 | 24,000 | 20,000 | 20000 | 16,000 | 10,000 | 138,000 | 21 |
|  |  |  |  | 72200 | Equipment & Furniture | 21,000 | 0 | 0 | 0 | 0 | 0 | 21,000 | 22 |
|  |  |  |  | 73400 | Rental & Maintenance of Other Equip | 0 | 1,500 | 1,500 | 1,500 | 1,500 | 1,500 | 7,500 | 23 |
|  |  |  |  |  | Total Outcome 3 | 656,400 | 2,019,683 | 776,700 | 728,500 | 144,400 | 100,700 | 4,426,383 |  |
| PROJECT MANAGEMENT COST | EFCCC | 62160 | LDCF | 71400 | Contractual services - Individual | 25,000 | 14,000 | 14,000 | 14,000 | 14,000 | 15,908 | 96,908 | 24 |
|  |  |  |  | 71600 | Travel | 1,000 | 1,000 | 2,000 | 2,000 | 2,000 | 2,000 | 10,000 | 25 |
|  |  |  |  | 71200 | International Consultants | 0 | 0 | 50,000 | 0 | 0 | 50,000 | 100,000 | 26 |
|  |  |  |  | 74100 | Professional services | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 | 18,000 | 27 |
|  |  |  |  | 74500 | Miscellaneous Expenses | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 | 12,000 | 28 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 16,000 | 5,000 | 5,000 | 5000 | 5,000 | 5,000 | 41,000 | 29 |
|  |  |  |  |  | PMC Sub-total LDCF | 47,000 | 25,000 | 76,000 | 26,000 | 26,000 | 77,908 | 277,908 |  |
|  |  | 4000 | TRAC | 71300 | Local Consultants | 3,000 | 0 | 0 | 0 | 0 | 0 | 3,000 | 30 |
|  |  |  |  | 71400 | Contractual services - Individual | 18,000 | 18,000 | 18,000 | 18,000 | 18,000 | 18,000 | 108,000 | 31 |
|  |  |  |  | 71800 | Contractual Services-Imp Partn | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 72,000 | 32 |
|  |  |  |  | 71600 | Travel | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 6,000 | 33 |
|  |  |  |  | 72500 | Office supplies | 2,500 | 1,700 | 1,700 | 1,700 | 1,700 | 1,700 | 11,000 | 34 |
|  |  |  |  |  | PMC Sub-total UNDP TRAC | 36,500 | 32,700 | 32,700 | 32,700 | 32,700 | 32,700 | 200,000 |  |
|  |  |  |  |  | Total PMC (LDCF+TRAC) | 83,500 | 57,700 | 108,700 | 58,700 | 58,700 | 108,608 | 477,908 |  |
|  |  |  |  |  | Total LDCF | 1,384,400 | 2,351,683 | 916,132 | 781,950 | 197,400 | 204,508 | 5,836,073 |  |
|  |  |  |  |  | Total UNDP TRAC | 36,500 | 32,700 | 32,700 | 32,700 | 32,700 | 32,700 | 200,000 |  |
|  |  |  |  |  | Grand Total (LDCF+TRAC) | 1,420,900 | 2,384,383 | 948,832 | 814,650 | 230,100 | 237,208 | 6,036,073 |  |

Budget notes:

| 1 | - Consultancy firm/s to develop six sets training modules for climate adaptation capacity building at 30 Day each = 30 X $500 X 6 =$90,000 - Consultant to train 60 TOTs at Regional level @ $250 per day for 30 Days at 6 regions = 30 X $250 X 6 = $45,000 - Trained Experts to conduct training @ woreda and community level @ $50 per day for 36 days at 12 woredas = $50 X 36 X 12 = $21,600 Training Modules to be developed: - Training on Climate smart technology and good practices for community adaptation (Output 1.1 @ Regional level) - Training on developing climate adaptive community-based action plan development (Output 1.2 @ Regional level) - Training on climate and weather information for planning and agricultural advisory support for the agro-metrology task force established and hosted by the MoANR (Output 2.1 @ Regional Level) - Responding to climate emergency at community level: early discovery and monitoring training on Fall Armyworm and Emergency flood (Output 1.3 @ Woreda level) - Training session on adaptive soil and water conservation techniques, including rehabilitation, improvement and maintenance of a productive and healthy watershed (Output 1.2, 3.3 @ Woreda level) - Training climate smart technologies for adaptive capacities and diversified livelihoods, including provision of enhances the knowledge base and capability of land users, including women and youths, on the establishment of community-based enterprises like water storage and rainwater harvesting techniques, livestock fattening and to engage in agroforestry, poultry production, etc. (Output 3.2@Woreda Level) Total=$156,600 |
| --- | --- |
| 2 | - International Consultants’ local travel costs for regional trainings US$150 car hire per day for 30 days (including car hire and driver): US$150X30=$4,500 - One international return flight at US$2,000 for international consultant. - Travel costs per 2 days regional workshop estimated at US$50 dollars per person. 10 officials will attend from each region: $50X10 participants per regions X 6 regions X 3workshops = $9,000 - Travel costs per 2 days woredas workshop estimated at US$30 dollars per person. 20 officials will attend from each woreda (two Woredas in each region): $30X10 participants per woredas X 12woredas X 3workshops= $10,800 - Travel cost for national consultants to conduct regional trainings: 25-day; car hire at US$150 per day = US$150 X 25= $3,750 - Travel costs by PMU staff for Management Administrative Support, Field Activities Implementation and Technical Monitoring for Outcome 1: Car hire @ $150 per day for 140 Days = $21,000 Total= $51,050 |
| 3 | Project Technical Specialist salary = US$1,000 per month for 72 months = $72,000 |
| 4 | Materials and goods – Laptop computers and software (US$1,000 each) including one per each of the Twelve Woredas, one at regional level for each one of the six regions and four at national level – therefore, total number of laptops = 22; (22X$1,000=$22,000) Total: $22,000 |
| 5 | - Audio visuals including projectors for woredas @$500 = ($500X12= $6,000) - Printing and dissemination of updated pamphlets, leaflets and other knowledge products at US$537.50 per Woreda for each of the twelve Woredas ($537.50 X 12= $6,450) Total $12,450 |
| 6 | - Trainings to be conducted: - Training on Climate smart technology and good practices for community adaptation (Output 1.1 @ Regional level) - Training on developing climate adaptive community-based action plan development (Output 1.2 @ Regional level) - Responding to climate emergency at community level: early discovery and monitoring training on Fall Armyworm and Emergency flood (Output 1.3 @ Woreda level) - Training session on adaptive soil and water conservation techniques, including rehabilitation, improvement and maintenance of a productive and healthy watershed (Output 1.2, 3.3 @ Woreda level) - Training on climate and weather information for planning and agricultural advisory support for the agro-metrology task force established and hosted by the MoANR (Output 2.1 @ Regional Level) - Training climate smart technologies for adaptive capacities and diversified livelihoods, including provision of enhances the knowledge base and capability of land users, including women and youths, on the establishment of community-based enterprises like water storage and rainwater harvesting techniques, livestock fattening and to engage in agroforestry, poultry production, etc. (Output 3.2@Woreda Level) Training Seminar/workshop organisation: To include food, Audio Visual-material, printing costs, hiring of marquee/venue etc: - One national Seminar/conference will be held for national government staff: Two days at US$3,000 per day workshop = US$3,000 X 2 = $6,000 - 18 regional training workshops (3 regional training workshop each for 6 regions) at US$2,000 per workshop ($2,000 per day). = 18X2,000= $36,000 - 36 Woreda level workshops (3 workshops for each of 12 woredas) US$1,000 per workshop 36 X $1,000 = $36,000 Participation: - 30 Participants at National training workshops for two days: 2 X 30 X $75 = $4,500 - 18 regional workshops will be held per region, with 5 participants per region (30 persons) @DSA of $50: 30 X 50 X 18 = $27,000 - 36 workshops for Woreda and community representatives: for 20 participants per woreda at DSA of $20: 20 X 20 X 36 = $14,400 Woreda-level workshops will be attended by the relevant steering committee, CBOs, farmers groups, women groups, youth groups and extension officers. The workshops will be one day. It is estimated that the workshops will be attended by about 100 attendees per workshop. Total: $123,900 |
| 7 | - 15% share of twelve motorbikes to be purchased (one per Woreda). Cost = $2,500 per motorbike x 12 x 15% = $4,500 Total: $ 4,500 |
| 8 | - Fuel reimbursables for Hired Vehicles and motorbikes for component 1 @$1,000 per year (Year2-6) = $5,000; - Motorbikes maintenance and fuel cost for component 1 @$1500 per year for years 2-6 = $2,500; Total $7,500 |
| 9 | - Travel costs for international consultant for training: Car hire at US$150 per day for 60 days (including car hire and driver) =$9,000. $2,000 @yr3 for a return flight, if required. - Travel costs for local consultants for regional workshop at US$150 per day for 80 days (including car hire and driver) = $12,000. $2,000 @yr3 for international flight, if required. - Travel costs by PMU staff for Management Administrative Support, Field Activities Implementation and Technical Monitoring for Outcome 2: Car hire @ $150 per day for 140 Days = $21,000 9,000+2,000+12,000+2000+21,000= Total = $46,000 |
| 10 | - Consultant Meteorology– fees: 30 days at US$500 per day ($15,000)– to consult with each of the twelve Woredas and to analyse the accuracy of climate information being generated for each of the Twelve Woredas. This specialist will: i) undertake an equipment needs assessment of the existing weather stations in at Nine uncovered locations; ii) propose the list of equipment to be purchased; iii) identify potential suppliers; and iv) develop a long-term maintenance plan for the existing and new equipment. - AgroMet Task Force collaboration to provide support for AgroMet advisory: at $5,000 for 2 years (total $10,000) for years 1 and 3 for 20 days each. Partnership will deliver plans and AgroMet advisory. - EWS Capacity development plans and digitized tools to downscale AgroMet weather information at $100,000 and advisory support at $20,000. - MoANR as service provider to conduct capacity development for Fall (Africa) Armyworm early warning and monitory at US$200 per day for 24 days @ 12 woredas ($200*24*12=$57,600) - $(15,00010,000+100,000+20,000+57,600= Total $202,600 |
| 11 | - Service provider sub-contract for purchase and installation of: i) Nine AWS at US$30,000 each (including costs related to shipment); ii) equipment for upgrading existing weather stations; and iii) plastic rain gauges for each Woreda. - AWS equipment supports and maintenance at $25,000 from yr3. - 9*$30,000+$25,000 = Total $295,000 |
| 12 | - Printing and dissemination of reports on findings of assessment and other educational and informative material at $4,982 - Development and dissemination of training material and maintenance manuals at US$2,000 per Woreda for each of the twelve Woredas @$2,000 X 12 = ($24,000) 4,982+24,000= Total $28,982 |
| 13 | - Workshop organisation at $2,000 each for 12 Woredas: (12*2,000=$24,000) - One ToT workshop organisation at $2,000 for regional extension and development agents (6 regions) as resource persons: (2000*6=$12,000) - One workshop to train regional extension officers and development agents on responding to climate challenges in the face of climate challenges. ~24 people to attend workshop. $50*24*6=$7,200 - Workshop in each Woreda to train extension officers and development agents on the effective dissemination of climate information, advice and warnings: $30*50*12=$18,000 - Workshop by extension officers to train local community groups (women, youth and farmer groups) on understanding climate information and responding to early warnings. US$30 per person with ~100 expected to attend in each of the 12 Woredas. ($30*100*12=$36,000) Total $97,200 |
| 14 | - 15% share of twelve motorbikes to be purchased (one per Woreda). Cost = $2,500 per motorbike x 15% = $4,500 Total= $4,500 |
| 15 | - Fuel reimbursables for Hired Vehicles and motorbikes @$1,000 per year (Year2-6)= $5,000; - Motorbikes maintenance cost @$500 per year for years 2-6 = $2,500; - Total $7,500 |
| 16 | - 2 Water Storage infrastructure at each of 12 woreda: design and construction (including social and environmental screening and mitigation measures) per reservoir including material, transport and installation labour @ $15,000 each = 2*12*15,000 = $360,000 - Cost of PV-pumps US$3,600 each. Two to be installed in each Woreda ($3,600X2X12= $86,400 - Cost of Solar panels at US$500 each = ($500X24=12,000) - Cost of drilling for 24 wells for PV-pump sites at US$700 per metre. Depths to be determined during assessments under Output 3.1. at a lump sum amount of $229,083 allocated towards drilling wells (including social and environmental screening and mitigation measures). - Batteries to store power generated by PV-panels at US$600 X 24= $14,400 - Maintenance of PV-pumps 24 days per year for five years at US5 per day for 24 sites: 24X5X5X24 = $14,400 - Local consultant to: i) conduct analysis on market opportunities; ii) provide technical support for the identification and implementation of selected income-generating activities; and iii) provide training of local communities on value-addition activities, including agro-processing and marketing skills. Fees: 90 days at US$200 per day ($200X90=$18,000). During Year 2 and year 3, the consultant will undertake follow-up training of extension agents and review the progress in each Woreda. Fees: 50 days at US$200 per day: $200X50=$10,000 - Local consultant to: i) develop a long-term M&E strategy for each Woreda; ii) review successes and failures from the LDCF and other projects to suggest up scaling activities; iii) develop training material and provide training workshops on developing bankable business plans. and iv) develop strategy for post project operation and maintenance of project equipment. Travel to each of the twelve Woredas to gather information to be undertaken during Years 1, 3 and 5. Fee for consultant: US$300 per day for 60 days: $300X60=$18,000 - Flow and Ground water assessment consultant to assess water potential at 12 project sites, design and support implementation of water storage and enrichment (borehole drilling, irrigation facility) based on climate adaptive community action plan. Fees: US$ 400 per day for 120 days ($48,000). - A civil engineer and a soil & water conservation/rehabilitation consultant will be hired to work with the groundwater assessment specialist in all woredas to develop CCA intervention plans. These plans will outline the exact dimensions and positioning of soil and water conservation measures; position of well sites; and specific plant species to be used in strengthening physical structures. To include social and environmental screening and mitigation measures. Civil Eng. Fees: US$ 400 per day for 120 days ($48,000); Soil % Water Conservation fees: US$400 per day for 60days ($24,000) = $(360,000+86,400+12,000+229,083,000+14,400+14,400+18,000+10,000+18,000+48,000+48,000+24,000) = Total $882,283 |
| 17 | - 12 x Woreda Project Facilitator (WPF) payments @ US$300 per WPF per month for 72 months (300*12*72) =$259,200 - 12 Woreda Finance Assistant (WFA) payments @ US$200 per WFA per month for 72 months (200*12*72) = $172,800 = (259,200+172,800) = Total $432,000 |
| 18 | - Travel costs by PMU staff for Management Administrative Support, Field Activities Implementation and Technical Monitoring for Outcome 3: Car hire @ $150 per day for 500 days (100 days per year in years 2 to 4, 80 days each for years 1 and 5, and 40 days for year 6) making total of $75,000 - Total 75,000 |
| 19 | - Establish 60ha of nursery site, i.e. 5ha each per woreda, including: - Cost of above planting material at US$1,000 per hectare for 24 ha (total $60,000). - Labour cost for planting trees = US$5 per person day. 1000 person days per Woreda = 5X1,000X20days=$100,000 - Watershed rehabilitation work, including physical and biological soil and water conservation measures allocated to each Woreda for additional SWC structures identified during implementation and for tools required such as spades, pickaxes and shears = $1,290,000 - Allocation of $50,000 per project site making X2 per woreda for climate resilient livelihood activities 50,000*2*12=$1,200,000 - Direct investment of $13,600 per woreda on special innovation in community infrastructure for alternative livelihoods creation in each woreda with capacity to include additional sites (maximum of 3 sites per woreda): $13,600 x 12 = $163,200. Total = $2,813,200 Note: The above subject to social and environmental screening. High risk activities not to be implemented without approval of Project Board (Steering Committee) |
| 20 | - Training material development for stakeholder workshop at US$1,000 per workshop (1,000*12 = $12,000). - Printing of training modules for workshops@$1,000 per year and $1,400 year6=$6,400 - Training material, AV equipment and stationery @ $3,000X6=$18,000 - 6 Desktop computer and printer for training support and access for each project region @ $3,500X6=$21,000 Total = $57,400 |
| 21 | - Twelve woreda level capacity development workshops to be held annually for the first three years to inform Sub-national government staff and extension agents on climate smart technologies, farming, agro-pastoral and pastoral practices at US$2,000 per workshop 2,000*12= $24,000 - Experience sharing visit for land users per Woreda at US$2,000 for year 3 and 5 at $48,000 - Capacity development workshops on developing business plans will include Woreda government staff, extension agents and local community groups in each of the twelve Woredas for 60 people to attend in each Woreda. One day at US$2,000 per workshop (US$24,000 in Year 2 and 3) = $48,000 - Consultant develop Guidance note for community level climate smart technologies, farming, agro-pastoral and pastoral practices: 30dayX$150=$4500 - Development of Guidance Note on Community level climate smart technologies, farming, agro-pastoral and pastoral practice=$13,500 Total= $138,000 |
| 22 | - 70% share of twelve motorbikes to be purchased (one per Woreda). Cost = US$2,500 per motorbike x 70% = $21,000 Total= $21,000 |
| 23 | - Fuel Reimbursables for Hired Vehicles and motorbikes @$1,000 per year for 5 years (Years 2-6) = $5,000; - Motorbikes maintenance cost @$500 per year for 5 years (Years 2-6) = $2,500; Total $7,500 |
| 24 | - Monitoring implementation of Stakeholder Engagement Plan, monitoring implementation plan of Gender Plan, development, updating and monitoring of livelihood interventions for Yr1 (25,000), and 14,000/year for year 2 until year 5 and 15,908 for year 6. Details to be determined at inception period.; 25,000+14,000+14,000+14,000+14,000+15,908= Total $96,908 |
| 25 | - Travel for monitoring of indicators in project results framework and environmental and social risks @ $10,000 |
| 26 | - MTR Specialist Consultant = $50,000 - TE Specialist Consultant = $50,000 Total = $100,000 |
| 27 | - Annual audit = US$3,000 per year = $3,000*6 = Total $18,000 |
| 28 | - Miscellaneous costs for any unforeseen expenses associated with project management 2,000/year for 6 years @ 2,000*6 = $12,000 |
| 29 | - Inception workshop = $11,000 - Annual NPSC meeting @$3,000*6 = $18,000 - Lessons learned and knowledge generation @2,000*6=12,000 Total = $41,000 |
| 30 | - Local consultant to develop a mechanism for addressing environmental and social grievances @ $3,000 |
| 31 | - Project Manager salary = US$1,500 per month for 72 months = $108,000 |
| 32 | - Finance and Administrative Officer (with strong Procurement competence) salary = US$1,000 per month for 72 months =$72,000 |
| 33 | - Travel for monitoring of indicators in project results framework environmental and social risks @ $6,000 |
| 34 | - Office supplies = $2,500 for year 1 and $1,700 for year 2 to year 6 respectively = Total $11,000 |

|  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Amount Year 5 | Amount Year 6 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF | 1,384,400 | 2,351,683 | 916,132 | 781,950 | 197,400 | 204,508 | 5,836,073 |
| UNDP | 36,500 | 32,700 | 32,700 | 32,700 | 32,700 | 32,700 | 200,000 |
| TOTAL | 1,420,900 | 2,384,383 | 948,832 | 814,650 | 230,100 | 237,208 | 6,036,073 |

Summary of Funds

# Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Ethiopia and UNDP, signed on 6 February, 1981. All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by the Environment, Forest and Climate Change Commission (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

The designations employed and the presentation of material on this map do not imply the expression of any opinion whatsoever on the part of the Secretariat of the United Nations or UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

Implementing Partner - Government Entity (NIM)

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

- The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

## Annex A:  Multi Year Work Plan

| Output | Indicator | Responsible Party | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Component 1/Outcome1 : Technical Capacity for planning diversified climate change adaptation practices strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outputs: 1.1. Training modules and platform for enhancing the knowledge and capability of government officials, DAs and local-communities in twelve woredas on the formulation and implementation of adaptation measures are established and sustained. | AS INDICATED IN THE PRF | PMU; EFCCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2Strengthened capacity of development agents (DAs) and government officials to support the implementation of climate change adaptation practices at the woreda and regional levels. |  | PMU; EFCCC, NMA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 Community action plans for adaptive crop production and animal husbandry developed using a participatory approach in twelve Woredas |  | PMU; EFCCC, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4. Project benefits and climate change adaptation practices are documented and disseminated to local community members in twelve woredas through learning, using innovative and locally adapted means. |  | PMU; EFCCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1/ Outcome 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. Nine Automatic Weather Stations (AWS) installed and linked to the national meteorological network and protocols for use and maintenance established in each woreda. |  | PMU; EFCCC, NMA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Appropriate weather and climate monitoring and forecast technologies acquired by representatives of the participating beneficiary communities and maintained through a functional and durable partnership. |  | PMU; EFCCC, NMA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 Climate-risk assessment and decision-making tools developed and used in collaboration with local communities in twelve woredas. |  | PMU; EFCCC, NMA, MoANR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 Climate-risk assessment and decision-making tools are prepared, pilot tested, put in use and periodically improved using the results thereof in each of the twelve woredas. |  | PMU; EFCCC, NMA, MoANR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2/ Outcome 3: Climate change adaptation practices implemented by communities in lowland ecosystems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Critically degraded sites identified and rehabilitated in the twelve woredas through project activities anchored on functional water storage infrastructure designed, constructed and put in use to enhance the resilience and adaptive capacity of local communities in the twelve Woredas |  | PMU; EFCCC, WA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 Alternative livelihood opportunities created, expanded and made more responsive to climate change through the implementation of community-led climate adaptive initiatives in the twelve woredas. |  | PMU; EFCCC, WA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Farm/ pasture land rehabilitated through physical and biological soil and water conservation measures in degraded areas in each woreda for and by the vulnerable lowland farming, pastoralist and agro-pastoralist communities. |  | PMU; EFCCC, WA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 Community-based enterprises established and operationalized in each woreda to develop and strengthen climate resilient local business |  | PMU; EFCCC, WA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Evaluation (M&E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mid Term |  | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Terminal Evaluation |  | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex B:  GEF Tracking Tool at baseline

| Project identification |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project title: | Climate change adaptation in the lowland ecosystems of Ethiopia. |  |  |  |  |  |
| Country(ies): | Ethiopia |  |  | GEF project ID: 9303 |  |  |
| GEF Agency(ies): | UNDP |  |  | Agency project ID: 5630 |  |  |
| Executing Partner(s): | Environment, Forest and Climate Change Commission (EFCCC) |  |  | Council/ CEO Approval date: |  | PIF Approval, Mar 28, 2018 |
| Project status at submission: |  |  |  | Tool submission date: |  |  |
| Project baselines, targets and outcomes |  |  |  |  |  |  |
| Indicator | Unit of measurement | Baseline at CEO Endorsement | Target at CEO Endorsement | Actual at mid-term | Actual at completion | Comments (e.g. specify unit of measurement) |
| Objective 1: promote climate change adaptation and sustainable economic growth among communities in Ethiopia’s lowland ecosystems |  |  |  |  |  |  |
| Indicator 1: Number of direct beneficiaries | number of people | 0 | 120,000 |  |  |  |
|  | % female | 0 | 52 |  |  |  |
|  | vulnerability assessment (No) |  |  |  |  |  |
| Outcome1: Technical Capacity for planning diversified climate change adaptation practices strengthened |  |  |  |  |  |  |
| Indicator 2: Number of training and participants on key adaptation issues, including community-based adaptation techniques | Number of trained people | 0 | 1,200 |  |  | The trainees comprise regional and woreda government officials and local community representatives. |
|  | % female | 0 | At least 52% |  |  |  |
| Indicator 3: Climate adaptive action plans developed by taking into account CSA and the future climate scenario | Number of action plans | 0 | 12 |  |  | The action plans identify, prioritize and integrate adaptation measure at identified sites in each woreda. |
| Outcome 2. Climate adaptive management adopted by local communities through accessible climate information and decision-making tools |  |  |  |  |  |  |
| Indicator 4: AWS are operational in each of the 9 targeted woredas | Number of functional AWS | 3 | 12 operational AWS (one in each of the 12 woredas) |  |  |  |
|  | number of people | 0 | 120,000 |  |  |  |
|  | % female | 0 | 50 |  |  |  |
| Indicator 5 Number of people with access to improved and innovative climate information and services at the site woreda level – disaggregated by gender | number of people | 0 | 1,200 |  |  |  |
|  | % female | 0 | at least 52% |  |  |  |
| Outcome 3 Climate change adaptation practices implemented by communities in lowland ecosystems |  |  |  |  |  |  |
| Indicator 6: Ha of degraded land rehabilitated, are forested or recuperated to resemble more natural habitats | ha of land | 0 | 1200 hectares |  |  | Degrade land is rehabilitated as a result of various activities under outputs 3.1, 2.2, 3.2 Hectares under watershed restoration and CSA management measures |
| Indicator 7: Numbers of Population benefiting from the adoption of diversified, climate-resilient livelihood options: | number of people |  | 120,000 people |  |  |  |
|  | % female |  | 52 |  |  |  |
|  | % of targeted population |  | 10% |  |  |  |
| Indicator 8: % increase in awareness of climate risks and knowledge of response measures (established based on surveys) | number of people that are aware of risk and knowledge | 0 | 300,000 |  |  | There are Twelve project Woredas, which will all receive access to improved climate information. |
|  | % female |  | 52% |  |  |  |
|  | % of targeted population |  | 50% |  |  |  |
| Reporting on GEF gender indicators |  |  |  |  |  |  |
| Q1: Has a gender analysis been conducted during project preparation? |  |  | YES | NA | NA |  |
| Q2: Does the project results framework include gender-responsive indicators, and sex-disaggregated data? |  |  | YES |  |  |  |
| Q3: Of the policies, plans frameworks and processes supported (see indicators 12 and 13 above), how many incorporate gender dimensions (number)? |  |  | ALL |  |  |  |
| Q4: At mid-term/ completion, does the mid-term review/ terminal evaluation assess progress and results in terms of gender equality and women's empowerment? |  |  | YES |  |  |  |

## Annex C:  Overview of Technical Consultancies

Details of local consultants to be executed are indicated below with the cost and the numbers of days for each consulting assignments. This would be reviewed by the project management units at the project inception phase.

| Consultant | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| For Project Management / Monitoring & Evaluation |  |  |
| Local / National contracting |  |  |
| Local MTR Specialist | US$10,000 | To assist with updating MTR Tracking Tool |
| Local TE Specialist | US$10,000 | To assist with updating TE Tracking Tool |
| International / Regional and global contracting |  |  |
| Mid-Term Review Specialist | US$40,000 | Mid-Term Evaluation |
| Terminal Evaluation Specialist | US$40,000. | Terminal Evaluation |
| For Technical Assistance |  |  |
| Outcome 1 |  |  |
| Local / National contracting: |  |  |
| Consultancy firm/s | 20 Day each = 20 X $1,000 X 6 =$60,000 | To develop six sets training modules for climate adaptation capacity building |
| Consultant | $350 per day for 60 Days at 6 regions = 30 X $350 X 6 = $63,000 | To train 60 TOTs at Regional level |
| Consultant Meteorology | fees: 30 days at US$200 per day ($6,000) | Consult with each of the twelve Woredas and to analyse the accuracy of climate information being generated for each of the Twelve Woredas. This specialist will: i) undertake an equipment needs assessment of the existing weather stations in at Nine uncovered locations; ii) propose the list of equipment to be purchased; iii) identify potential suppliers; and iv) develop a long-term maintenance plan for the existing and new equipment. |
| Local consultant | 50 days at US$200 per day. | i) Conduct analysis on market opportunities; ii) provide technical support for the identification and implementation of selected income-generating activities; and iii) provide training of local communities on value-addition activities, including agro-processing and marketing skills. Fees: 90 days at US$200 per day. During Year 2 and year 3, the consultant will undertake follow-up training of extension agents and review the progress in each Woreda. Fees: |
| Local consultant | US$300 per day for 60 days | i) Develop a long-term M&E strategy for each Woreda; ii) review successes and failures from the LDCF and other projects to suggest up scaling activities; iii) develop training material and provide training workshops on developing bankable business plans. and iv) develop strategy for post project operation and maintenance of project equipment. Travel to each of the twelve Woredas to gather information to be undertaken during Years 1, 3 and 5. Fee for consultant: |
| Flow and Ground water assessment specialist | Fees: US$ 450 per day for 150 days ($67,500). | To assess water potential at 12 project sites, design and support implementation of water storage and enrichment (borehole drilling, irrigation facility) based on climate adaptive community action plan. |
| Civil engineer and landscape rehabilitation specialist | Fees: US$ 450 per day for 150 days ($67,500). | To work with the groundwater assessment specialist to develop CCA intervention plans. These plans will outline the exact dimensions and positioning of soil and water conservation measures; position of well sites; and specific plant species to be used in strengthening physical structures. |
| International / Regional and global contracting |  |  |

## Annex D: Terms of Reference

Terms of Reference for National Steering Committee (NPSC)

Background

The NPSC will be responsible for undertaking management-related and technical decisions for the project in accordance with this ToR and providing guidance and direction for the project when required.

Tasks of the NPSC will include inter alia approval of project plans, Annual Work Plans (AWPs) and revisions by UNDP and the EFCCC. The committee will ensure a continued cohesion between the project and the mandate of the EFCCC. It will also provide additional linkages and interactions with high-level policy components within the Government. The NPSC will approve the responsibilities of the PMU and intervene when conflicts within the project and between project members arise.

The NPSC will comprise the following members:

  - EFCCC (Co-chair); UNDP (Co-chair);

  - MoANR; Ministry of Finance and Economic Cooperation (MoFEC);

  - National Meteorological Agency (NMA);

  - Ministry of Water, Irrigation and Energy (MoWIE);

  - Regional Representatives (Six regional representatives - one from each region) of EFCCC replica,

  - Disaster Risk Management Commission (DRMC),

  - Ethiopian Biodiversity Institute (EBI),

  - Ethiopian Wildlife Conservation Authority (EWCA),

  - Ethiopian Environment and Forestry Research Institute (EEFRI),

  - Ethiopian Agricultural Institute (EAI), Afar Pastoral and

  - Agriculture Development Bureau (APADB) and

  - Oromiya Pastoral Development Commission (OPDC).

Scope of Work

Specific responsibilities of the NPSC are as follows:

  - Setting a strategic direction, reinforcing government leadership of the programme and coordinating all interventions.

  - Providing guidance and agreeing on possible countermeasures/management actions to address specific risks.

  - Approving the work plans prepared by the PM (prior to approval by UNDP).

  - Conducting regular meetings to review the progress of LDCF resources and providing direction and recommendations to ensure that the agreed deliverables are produced to a satisfactory standard.

  - Reviewing and approving all activities that are supported by the project based on the project objectives, work plan and availability of funding.

  - Providing technical advice to create synergy and uniformity between supported activities, policies and alignment projects.

  - Monitoring and evaluation of programme activities through periodic meetings and occasional site visits.

  - Receiving reports on all activities supported by the programme to serve as an additional basis for monitoring and assessing LDCF resources’ performance and delivery.

The NPSC will meet at least twice a year but could meet more frequently at the start of the project. With the assistance of the PMU, the chairperson of the PB will convene Steering Committee meetings. The committee may invite other collaborating institutions as the need arises. The National Project Manager (PM) will participate in the NPSC and provide the Secretariat to the Committee, with other PMU staff joining on demand and invitation.

Terms of Reference for Project Staff /Consultants

Terms of Reference (ToRs) for suggested project key staff/consultants are included in this annex. The TORs may be reviewed and adjusted during the inception phase for the followings:

- National Project Manager

- Project Technical Specialist/Deputy National Project Manager

- Woreda Finance Assistant x12

- Woreda Facilitators x 12

- Finance Officers x12

National Project Manager (PM)

Terms of Reference for Project Manager (PM) and Deputy National Project Manager

Scope of Work

The Project Manager will be recruited by EFCCC on a full-time basis to coordinate the implementation of LDCF resources. He/she will be accountable for inter alia: i) the quality, timeliness and effectiveness of the interventions carried out; and ii) the use of project funds.The PM will report to the NSC.

Particular responsibilities of the PM include:

- Head the PMU.

- Report to the NSC regarding project progress.

- Oversee and manage project implementation, monitor work progress, and ensure timely delivery of outputs in accordance with GEF and UNDP guidelines.

- Ensure timely preparation of detailed AWPs and budgets for approval by NSC.

- Organise the NSC meetings.

- Deliver quarterly progress reports to the UNDP Task Manager and UNDP.

- Provide on-the-ground information for UNDP progress reports.

- Provide technical support to the project, including measures to address challenges to project implementation.

- Supervise, coordinate and facilitate the work of the Project Finance and Administrative Associate (PFAA) and the Project Technical Assistant to the Coordinator (PTA), field officers and the technical committee (including national and international experts).

- Participate in training activities, report writing and facilitation of expert activities that are relevant to the PM’s area of expertise.

- Establish linkages and networks with the on-going activities of other government and non-government agencies.

- Liaise and coordinate with UNDP TM on a regular basis.

Qualifications

- Master’s degree in environment, natural resources management, ecological restoration or a closely related field.

- A minimum of 10 years relevant work experience including at least 6 years’ experience as a lead project manager in relevant sectors.

- Demonstrated solid knowledge of adaptation to climate change, ecological restoration and sustainable exploitation of natural resources.

- Experience in the public participation development process associated with environment and sustainable development is an asset.

- Experience in working and collaborating within governments is an asset as well as experience in GEF projects.

- Fluent in Amharic and English including writing and communication skills.

Reporting

The PM will work closely with the PSC and the UNDP TM to ensure the availability of information on progress and performance regarding the implementation of the project. The PM will deliver progress reports on a monthly basis to the TM and the UNDP CO. These reports will include: i) status of activities; and ii) challenges encountered on the ground during project execution.

Project Technical Specialist

Act as deputy National Project Manager to assist and support the project Manager to carry out all the responsibilities of the Project Manager positions, as assigned by the Project Manager. The Project Technical Specialist

will hold a minimum of 5 years of working experiences and report to the National Project Manager.

National Administrative and Finance Officer

Long term national consultant: Strong Procurement & Accounting responsibility, up to 6 years

Background (to be complemented with project information before publishing)

The Finance Officer provides support to the Project Manager for delivery in line with good accounting practices. The position is based at the National Office with 12 additional Finance Officers based at each Woreda level.

Duties and Responsibilities

  - If applicable and needed, serve as the budget holder for GEF and UNDP funds

  - Collect, register and maintain all information on project activities, with focus on finance

  - Prepare and check all the necessary documentation for procurement, in close collaboration with the Project Manager, and in consultation with the UNDP Country Office where needed (e.g. international procurement, where UNDP’s service can be advantageous), and seeking external expertise (e.g. legal or in engineering) when needed.

  - Contribute to the preparation and implementation of annual work plans and progress reports

  - Monitor project activities, budgets and financial expenditures

  - Advise all project counterparts on applicable administrative procedures and ensures their proper implementation

  - Maintain project correspondence and communication

  - Support the preparations of project work-plans and operational and financial planning processes

  - Assist in procurement and recruitment processes

  - Assist in the preparation of payments requests for operational expenses, salaries, insurance, etc. against project budgets and work plans

  - Follow-up on timely disbursements by UNDP CO

  - Receive, screen and distribute correspondence and attach necessary background information

  - Prepare routine correspondence and memoranda for Project Manager’s signature

  - Assist in logistical organization of meetings, training and workshops

  - Prepare agendas and arrange field visits, appointments and meetings both internal and external related to the project activities and write minutes from the meetings

  - Maintain project filing system and any necessary records for e.g. project equipment inventory

  - Perform any other duty relevant to the assignment

Competencies:

- Bookkeeping skills

- Administration skills

- Good organizational skills

Required Skills and Experience

Education:

- A degree and/or professional qualification in accountancy

- PRINCE2 certificate an advantage

Experience:

- At least 5 years of administrative and/or financial management experience;

- Demonstrable ability to administer project budgets, and track financial expenditure;

- Demonstrable ability to maintain effective communication with different stakeholders, and arrange stakeholder meetings and/or workshops;

- Excellent computer skills, in particular mastery of all applications of the MS Office package, in particular excel; mastery of other finance applications is a plus;

- Prior UNDP/GEF project experience and knowledge of UNDP and GEF procedures and guidelines is an advantage.

Language:

Fluency in written and spoken English and Amharic.

Woreda Facilitators and Finance Assistants

Long-term local contract: Woreda Facilitator x 12 – one in each project interventions site, up to 6 years

The Woreda Officers have responsibility to for delivering the field aspects of the project at the 12 project sites.

The Woreda Officers will be located at the woreda administrative offices.

Duties and Responsibilities

- Supervise and coordinate the delivery of project outputs in the field, and especially at the woreda level, as per the project document, working closely with the Project Manager

- Mobilize all project inputs and support in accordance with UNDP procedures for nationally executed projects

- Supervise and coordinate the work of all regional project staff, consultants and sub-contractors

- Input to and/or prepare and revise project work and financial plans, as required by UNDP, in close cooperation with the National Project Manager

- Liaise with partners at the regional level for effective coordination of all project activities

- Contribute to the production and timely submission of the Inception Report, Combined Project Implementation Review/Annual Project Report (PIR/APR), Technical reports, quarterly financial reports, and other reports as may be required by UNDP, GEF, and other oversight agencies

- Perform any other duty relevant to the assignment

Competencies

- Experienced field project manager

- Financial management and control capabilities

- Advanced leadership, negotiation and communication skills

- Sensitive to context of the project and considerable understanding of the regions

Required Skills and Experience

Education:

- Minimum MA or MSc in Social or Environmental Sciences, Development, Environmental Management and related

- Demonstrable background in Ecosystem Based Adaptation and related Climate Change and Natural Resource Management issues as asset

- PRINCE2 certificate an advantage

Experience:

- Minimum 7 years’ experience in project management, of which 5 years is in a sub-national context, ideally in the project location

- Prior UNDP/GEF project experience.

Language:

Fluency in written and spoken English and Amharic.

## Annex E:  UNDP Social and Environmental Screening Procedure and plans as needed

The UNDP environmental and social safeguards requirements have been followed in the development of this LDCF project. In accordance with the UNDP Social and Environmental Screening Procedure (SESP), the project is categorized as moderate risk and, as outlined below, the potential negative environmental or social impacts will be managed through standard best practice and the application of tools identified in the risk assessment below.

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Climate change adaptation in the lowland ecosystems of Ethiopia |
| - Project Number | 00113814 |
| - Location (Global/Region/Country) | Africa/Ethiopia |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

This project enhances transparent, detailed and all-inclusive discussions and decision making among land users, government and other stakeholders. It promotes the participation of government stakeholders who are responsible for reflecting the needs of those who are most affected by climate change, particularly the vulnerable and marginalized communities. It also promotes the participation of the ultimate land users or local communities to bring about the climate resilient development envisaged by them. In order to help these actors and stakeholders take informed decision in mainstreaming human-rights based approach, the project strengthens the ability of land users, government and other stakeholders. The project will also implement a Stakeholder Engagement Plan to ensure meaningful stakeholder engagement throughout. A project Grievance Redress Mechanism will also be established to ensure affected people have access to mechanisms to submit concerns. Stakeholders will be informed of UNDP’s Accountability Mechanism (www.undp.org/secu-srm).

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

One of the key design principles that underpin this project is ‘’ Being participatory, transparent, accountable, and culturally appropriate, while actively embracing equity and gender issues’’. Therefore, in order to implement gender mainstreaming, the project has included gender analysis and tentative gender action plan that focuses on the involvement and integration of women in delivery of the project outputs and promotion of active women participation in the project management, monitoring and evaluation. To improve gender equality and women’s empowerment, the project pursues the following approaches: a) encourages the representation of members in the project governance and management arrangements that are capable of articulating the needs and challenges of women; b) training sessions and workshops will be delivered with gender sensitivity to ensure that a) both male and female participants are empowered to participate meaningfully in the trainings; b) all participants are made aware of their responsibility to respect the views of all of their colleagues during training sessions; c) trainers will be required to have skills and experience necessary to plan and facilitate gender sensitive training and d) knowledge generated by the project will be gender-sensitive, ensure inclusion and sensitivity towards differences among target audiences and e) the project will use appropriate access and communication channels to reach men and women equally when disseminating information, knowledge and training materials. (For more information, please see Annex G: Gender Analysis and Action Plan).

Briefly describe in the space below how the Project mainstreams environmental sustainability

The objective of the project is to promote climate change adaptation and sustainable economic growth among communities in Ethiopia’s lowland ecosystems. The project intends to mainstream environmental sustainability through running a TOT approach designed to reach a larger audience; disseminating weather information and climate advisory services; conducting a “learning by doing” training meant for land users and providing needs responsive support in a way that leads to tangible and replicable changes. The implementation of the project increases climate resilience and diversify livelihood options of land users in the lowland ecosystem of Ethiopia by minimizing risks or avoiding risks as well as enhancing the capacity of stakeholders and ecosystems to adapt to climate change. Therefore, this project is meant for integrating actions that bring about long-term sustainability of environment in the face of climate change that is set to continue changing.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). If no risks have been identified in Attachment 1 then note “No Risks Identified” and skip to Question 4 and Select “Low Risk”. Questions 5 and 6 not required for Low Risk Projects. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |  |
| --- | --- | --- | --- | --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |  |
| Risk 1: Duty-bearers do not have the capacity to meet their obligations in the Project | I = 3 P = 2 | Moderate | The proposed project is essentially a country-driven initiative. Therefore, Ethiopian stakeholders will be the ultimate duty-bearers. |  | The roles and responsibilities of each participating duty-bearer have been identified and clarified. The project will seek to fill the capacity gaps and resource needs – already identified at PPG stage – through ongoing capacity development programmes. Throughout project implementation, duty-bearers will be in regular communication with the PMU to ensure that tasks are understood and conducted effectively. Further capacity gaps will be identified and addressed through adaptive management by proposing cost effective strategies and approaches to addressing these needs during project implementation. The project will apply a human-rights based approach, including through meaningful stakeholder engagement throughout. |  |
| Risk 2: Rights-holders do not have the capacity to claim their rights. | I = 4 P = 2 | Moderate | The project sites include areas in which poverty and employment are high and literacy rates are low. Therefore, the ability of individuals and groups to influence decision making is reduced. |  | The project will establish new and support existing community-based Groups and associations that will receive training on participatory approaches to land use planning, as well as on climate change adaptation techniques. These activities will empower local communities to claim their rights to land and natural resources. The project will be characterized by direct and meaningful participation of different stakeholders at community, local, regional and national government levels. Beneficiaries and other potentially affected people will also have access to information about the project and a project grievance mechanism. |  |
| Risk 3. Women’s engagement in leading change and in land-use practices, which is encouraged by the project, may be constrained by organisational types of behaviour that are generally not considered acceptable, appropriate or desired for women in a deeply conservative societies found across the project areas. | I = 3 P = 3 | Moderate | Observations during the PPG phase has shown that women in the project areas are not expected to take the front-line and hence their specific concern may not be accommodated while their desires to take active role in project interventions may be denied. |  | The project aims to specifically engage women in its implementation and as beneficiaries as a means of fostering gender equality in the share of development and adaptation benefits. The community-based interventions are planned to be carried out through in a way to directly benefit the women in design and approaches. It is clear that a special design is needed to ensure that such an approach will be culturally acceptable. The stakeholder engagement plan for the project will ensure meaningful and effective engagement of women throughout. A gender action plan is also developed for the project. |  |
| Risk 4: Proposed project will involve plantation development, or reforestation which could affect local habitat and ecosystems | I = 1 P = 5 | Low | Conservation agriculture and agroforestry techniques will be implemented during the project. Focus will be placed on utilising indigenous species as far as possible, however in certain instances – such as woodlots – exotic species may be used. The proposed project will promote the regeneration of degraded land through reforestation and the use of SWC measures. |  | Indigenous, multi-use plant/tree species will be selected. Exotic species will only be used when absolutely necessary (when no indigenous alternative is available) around homesteads for wood production and agricultural practices. In such cases prior assessment of the possibility of accidental or unintended introduction of invasive alien species will be undertaken. Under no circumstances will alien species known to be invasive be introduced. Training of local communities will include education on the benefits of using indigenous, multi-use plant species rather than exotics in watershed restoration programmes. Reforestation or plantation activities will be sited on lands where natural habitats have already been converted to other land uses. However, the project will seek to avoid siting activities on lands that were converted in anticipation of the Project. The Community Climate Adaptation Action Plans will include an assessment of potential social and environmental impacts to inform selection of plantation and reforestation activities and sites to avoid potential adverse impacts where possible, and minimize and mitigate any residual impacts. Site specific management plans will be put in place prior to implementation of any activities that may have adverse impacts. Activities assessed to be High Risk will not be supported by the project. |  |
| Risk 5: The proposed project involves small-scale extraction, diversion and containment of surface and ground water. | I = 3 P = 4 | Moderate | The project will construct small-scale water holding structures like dykes or other mechanisms to slow water flow and to increase groundwater recharge. Additionally, the project will construct up to 12 small reservoirs to store rainwater or extracted using solar PV-pumps. This water would be used to run small-scale irrigation. |  | Geo-hydrological assessments and an EIA will be carried out for each Community Climate Adaptation Action Plan involving water holding structures and irrigation to determine the ideal location for mini storage, reservoirs and PV-pumps and measures to ensure social and environmental sustainability. The project will not support activities that significantly alter flow regimes in ways that prevent water resources from fulfilling their functions for upstream and downstream ecosystems and their services to local communities. Social and environmental assessments will address, among other issues, potential effects and impacts related to climate variability, water pollution, sedimentation, water-related disasters, drinking water supply, energy production, agriculture, and fisheries. In addition, communities will be consulted in the broader site selection process. Site specific management plans will be in place prior to implementation of any activities that may have adverse impacts. Activities assessed to be High Risk will not be supported by the project. |  |
| Risk 6: Outcomes of the proposed project will be sensitive or vulnerable to potential impacts of climate change (e.g. from unanticipated extreme weather events and climate hazards and increasing dryness leading to water scarcity) | I = 3 P = 4 | Moderate | The project is targeting degraded watersheds and agri-productive lands to increase local communities’ resilience to climate change. |  | Current and future climatic variability will be taken into account in the assessments done to inform the Community Climate Adaptation Action Plans and related restoration processes. Furthermore, resilient species – particularly in the seedling stages – will be selected for agro-forestry and CSA techniques. This will promote maximum survival of species and greater vegetative coverage of soil surfaces compared with the use of climate-sensitive species. “No-regret” physical SWC measures will be implemented that enable communities to thrive during harsh climatic periods as well as during optimal years. Updated and improved site-specific climate information, forecasting and projections will be developed. Institutional capacity development and training programmes will take place focusing on changing behaviour and increasing preparedness to climate change amongst Woreda government staff, including extension agents. Down-scaled and site-specific agro-meteorological information and advice will be provided to local communities and farmers to prepare appropriately for extreme weather events. Furthermore, the project will adopt an ongoing learning-by-doing approach that will allow for iterative and adaptive management to prepare for dealing with extreme weather events. Climate-smart SWC and CSA techniques will be implemented to reduce risks of extreme weather to livelihoods and ecosystems. Lessons learned will be captured and disseminated elsewhere in Ethiopia through knowledge-sharing forums. A number of project activities –including climate-smart watershed restoration and rehabilitation, CSA, and SWC measures – have been identified to address these challenges and aimed to ensure more water retention along the channels and designed to decrease the erosive power of water runoff and increase rainwater infiltration. This will recharge and maintain groundwater levels. The implementation of these project activities will therefore mitigate against this risk and reduce the probability of conflict over water resources. |  |
| Risk 7: Potential community and occupational health and safety risks during construction and operation of small-scale infrastructure and water retention components of project. | I = 2 P = 1 | Low Risk |  |  | Community Climate Adaptation Plans will be informed by an assessment of potential social and environmental risks, including health and safety issues, to inform design and siting of interventions. Risks and potential impacts on the safety of affected communities during the design, construction, operation, and decommissioning of activities will be assessed and preventive measures and plans in place to address them. These measures will favour the prevention or avoidance of risks and impacts over their minimization and reduction. Consideration will be given to potential exposure to both accidental and natural hazards, especially where the structural elements of the project are accessible to members of the affected community or where their failure could result in injury to the community. Project will ensure activities consider how women’s and children, persons with disabilities, and marginalized groups’s. health and safety could be particularly at risk. For structural elements or components whose failure or malfunction may threaten the safety of communities: (i) plans for Project supervision, operation, and maintenance will be developed and monitored; (ii) independent expertise on the verification of design, construction, and operational procedures will be used; and (iii) periodic safety inspections will be carried out. |  |
| Risk 8: Proposed project could affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources potentially leading to economic displacement or land rights issues | I = 3 P =3 | Moderate | Existing land exclosure sites will be targeted for watershed restoration during project implementation. |  | The project will ensure that local communities – including women and landless youths – are involved in the assessments, negotiations and dialogue regarding land classification, use and planning. Vulnerable groups will be empowered to influence allocation decisions and will receive benefits from the restoration and provision of income-generating activities on communal lands. |  |
| Risk 9: There is a possibility of marginalized groups, in line with SES 6, being present in the project area. Ethiopia is ethnically diverse and made up of over 80 different ethnic groups. While the Ethiopian constitution guarantees the rights of all these groups, there is the potential that in some areas some groups, particularly smaller ethnic minorities, may be marginalized. | I = 3 P = 3 | Moderate | The project specifically targets the marginalised and socioeconomically disadvantaged sections of society, including small minority groups and other groups such as Internally Displaced Peoples (IDPs), landless, people living with disabilities, people with HIV/AIDS and youth. UNDP SES 6 has been triggered to safeguard the interests of groups that may be disadvantaged or marginalized. |  | The project activities will be guided by the Stakeholder Engagement Plan and GAAP to ensure representation of marginalised groups and women during designing, planning, managing, implementing and monitoring of activities. Activities under Outcomes 2 & 3 will ensure the assessment of marginalized groups, as well as ensuring project staff are sensitised and trained to identify and engage with such groups and to ensure they are consulted with and are meaningfully represented in user groups and committees formed during the project. Consultation and training activities will take into account the need of marginalized communities, including when selecting timing, location and format, taking into account needs of these groups as well as prevailing cultural norms. |  |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  |  |  | Comments |
|  | Low Risk |  |  |  |  |  |
|  | Moderate Risk |  |  | X |  | The highest order of risk is “moderate” which, according to the SESP guidance, include activities with potential adverse environmental and social risks and impacts. However, the risks are limited in scale due to the nature of the project activities and are easily identifiable and manageable through the use of standard tools during implementation. Stakeholder engagement in all activities is key to managing most of the risks while environmental and social assessments will be applied to inform the Community Climate Adaptation Plans and site-specific management plans in place prior to the implementation of any activities with potential for adverse impacts. |
|  | High Risk |  |  |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |  |
|  | Check all that apply |  |  |  |  | Comments |
|  | Principle 1: Human Rights |  |  | X |  | As a development organization, UNDP’s project design and implementation prioritises human approaches to ensure project intervention does not contribute to the worsening of the conditions of certain groups and individuals, but rather promotes equal participation, equitable representation and fair access to benefits. |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  | X |  | The project design includes gender considerations in all aspects to ensure that women and youth empowerment are integrated into project implementation, monitoring and reporting of results. |
|  | 1. Biodiversity Conservation and Natural Resource Management |  |  | X |  | Biodiversity conservation and natural resource management are at the centre of the project’s approach to promoting climate change adaptation. Restoring degraded watersheds and introducing climate-smart agriculture are viewed as cost effective approaches to increase the resilience of local communities to climate change. |
|  | 2. Climate Change Mitigation and Adaptation |  |  | X |  | This is a climate change adaptation project, designed specifically to mainstream climate risk considerations into food production and water management systems. |
|  | 3. Community Health, Safety and Working Conditions |  |  | X |  | Water harvesting and soil conservation structures in proximity to settlements and along frequented routes may pose a risk of drowning or injury to people, especially children, and to livestock. An ESIA will be conducted to assess and mitigate risks that have been identified and that may be identified during the inception phase, before any implementation is carried out. |
|  | 4. Cultural Heritage |  |  | ☐ |  |  |
|  | 5. Displacement and Resettlement |  |  | ☐ |  |  |
|  | 6. Indigenous Peoples |  |  | X |  | The project will involve socioeconomically marginalised and disadvantaged groups and its activities will be conducted on communal lands and properties of communities who may qualify as indigenous peoples in the broad sense of the term. The ESIA will further assess and determine whether an Ethnic Minority Plan is required and whether there is need for FPIC. This, together with the Stakeholder Engagement Plan and the Gender Action Plan will minimize the risk to these communities. |
|  | 7. Pollution Prevention and Resource Efficiency |  |  | ☐ |  |  |

Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases, PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | No |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | No |
| 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | Yes |
| 6. Is there a risk that rights-holders do not have the capacity to claim their rights? | Yes |
| 7. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 8. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | Yes |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | Yes |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | Yes |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | Yes |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | Yes |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | Yes |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | Yes |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | Yes |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | Yes |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect, and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | Yes |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources? | Yes |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | Yes |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the Project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to the screening question 6.3 is “yes” the potential risk impacts are considered potentially severe and/or critical and the Project would be categorized as either Moderate or High Risk. | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.7 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.8 Would the Project potentially affect the physical and cultural survival of indigenous peoples? | No |
| 6.9 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | Yes |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | Yes |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

## Annex F:  Stakeholder Engagement Plan

A tentative Stakeholder Engagement Plan is included below. This will be updated during the project inception phase by the Project Manager to take into consideration any new changes that would have occurred between its preparation and start of implementation.

| Outcome | Output | Stakeholder | Key responsibilities |
| --- | --- | --- | --- |
| Outcome 1: Technical capacity for planning diversified climate change adaptation practices strengthened | Output 1.1: Training modules and platform for enhancing the knowledge and capability of government officials, DAs and local-communities in twelve woredas on the formulation and implementation of adaptation measures are established and sustained. | EFCCC, MoANR, NMA | - Coordinating the preparation of training modules and establishment of platforms - Engaging partners and service providers - Overseeing the process designed for the selection of TOT trainers and trainees - Overseeing the preparation of training modules; establishment of platforms and the delivery of TOT training. - Facilitating partnerships across national, regional and Woreda-levels. |
|  | Output 1.2: Strengthened capacity of development agents (DAs) and government officials to support the implementation of climate change adaptation practices at the woreda and regional levels. | EFCCC, MoANR, NMA | - Overseeing implementation of TOT training and seminars - Facilitating organisation of regional and Woreda-level training workshops and seminars - engaging partners and service providers - Supporting and encouraging TOT trainers and trainees. |
|  | Output 1.3: Community action plans for adaptive crop production and animal husbandry developed and implemented using a participatory approach in twelve Woredas. | DAs & Government officials, EFCCC, MoANR, NMA | - Coordinating the preparation of community action plans - Overseeing and supporting the preparation of community action plans. - Facilitating the implementation of community action plans |
|  | Output 1.4: Project benefits and climate change adaptation practice guidelines are documented and disseminated to local community members in twelve woredas through learning and using innovative and locally adapted means. | EFCCC, MoANR, NMA, local communities, TOT trainees | - Establishment of knowledge-sharing forum. - Facilitation of linkages between project coordinators for the preparation of knowledge products. - Overseeing the preparation of documentaries, leaflets and posters. - Documenting and disseminating good practices - Sharing experiences through visits |
| Outcome 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools | Output 2.1: Nine Automatic Weather Stations (AWS) installed and linked to the national meteorological network and protocols for use and maintenance established in each woreda. | NMA, EFCCC, MoANR, MoWIE, extension agents, CBOs, local communities. | - Overseeing the installation and functionality of AWS. - Coordinating the procurement of equipment. - Collaborating in development of protocols for data collection, monitoring and transmission. - Provision of support regarding climate data storage and management for future reference and decision making. - Facilitating linkage with the Agro-meteorology Task Force and updating of decision tools to digitized tools |
|  | Output 2.2: Appropriate weather and climate monitoring and forecast technologies acquired by representatives of the participating beneficiary communities and maintained through a functional and durable partnership. | NMA, EFCCC, MoANR, MoWIE, extension agents, CBOs. | - Coordinating the distribution, use and maintenance of equipment to beneficiaries - Coordinating the process for the selection of beneficiaries entitled to acquire equipment - Overseeing the delivery of the right equipment to the right beneficiary; - Facilitating cooperation among beneficiaries at the Woreda-level. |
|  | Output 2.3: Climate-risk assessment and decision-making tools developed and used in collaboration with local communities in twelve woredas. | NMA, EFCCC, MoANR, MoWIE, extension agents, CBOs. | - Facilitating establishment of monitoring and management committees. - Facilitating development of risks and hazards communication strategies. - Engaging in establishing early warning systems and advice on methods of disseminating information. |
|  | Climate-risk assessment and decision-making tools are pilot tested and periodically improved using the results thereof in each of the twelve woredas. | NMA, EFCCC, MoANR, MoWIE, extension agents, CBOs. | - Overseeing the preparation and implementation and improvement of pilot testing plan - Coordinating capacity development workshops. - Facilitating dissemination of feedback from pilot testing |
| Outcome 3: Climate change adaptation practices implemented by communities in lowland ecosystems. | Critically degraded sites identified and rehabilitated in the twelve woredas anchored on functional water storage infrastructure designed, constructed and utilized to enhance the resilience and adaptive capacity of local communities in the twelve woredas. | EFCCC, MoANR, MoWIE, NMA, extension agents, CBOs, local communities. | - Overseeing the process for the identification and rehabilitation of degraded land - Facilitating preparation of integrated watershed management and landscape management plans with specialist consultants. - engaging partners and service providers - Overseeing the construction, utilization and maintenance of water storage structure - Facilitating ownership by and coordination among end users |
|  | Alternative livelihood opportunities created, expanded and made more responsive to climate change through the implementation of community-led climate adaptive initiatives in the twelve woredas. | NMA, EFCCC, MoANR, MoWIE, extension agents, CBOs. | - Overseeing the identification of appropriate location for water storage structure, establishment of nursery facilities, and plantation of appropriate tree species engaging partners and service providers - Coordinating measures for building erosion control and rehabilitation of degraded land - Developing and implementing a range of additional income-generating activities. |
|  | Farm/pasture land rehabilitated through physical and biological soil and water conservation measures in degraded areas in each woreda for and by the vulnerable lowland farming, pastoralist and agro-pastoralist communities. | NMA, EFCCC, MoANR, MoWIE, extension agents, CBOs. | - Coordinating the preparation and implementation of plans on a range of climate-smart technologies and good practices. - engaging partners and service providers - Facilitating demonstration plots at each of the project intervention sites. - Establishing land user groups. |
|  | Community-based enterprises established and operationalized in each woreda to develop and strengthen climate resilient local business. | NMA, EFCCC, MoANR, MoWIE, extension agents, CBOs. | - Overseeing actions designed to empower local communities for the diversification of their livelihoods. - Participating in training on business plan development. - Facilitate the penetration of renewable energy and energy efficient technologies - Engaging in the development of up-scaling and M&E strategies. |

## Annex G: Gender Analysis and Action Plan

To implement gender mainstreaming, the project will update the tentative Gender Action Plan below during the project inception period. The plan will guide the PMU on involvement and integration of women in delivery of the project outputs and promotion of active women participation in the project management, monitoring and evaluation. The key guidelines for the strategy are outlined below:

- Gender balance and gender rank will be ensured as much as possible regarding women participation in the NPSC and in the PMU. Project interventions will seek a greater and more even gender representation with the potential for gender mainstreaming-related activities. Furthermore, relevant gender representation on various levels of project governance will be pursued. All project staff recruitment shall be specifically undertaken inviting and encouraging women applicants. The TORs for key project staff all incorporate gender mainstreaming related responsibilities.

- In response to the relatively low participation of women in the project development, the project will incorporate gender considerations in the implementation procedures in a number of different ways:

- Empower women by involving them in planning processes, capacity building activities under Components 1 and 2;

- Strong focus on gender within Component 2 with an emphasis on providing grants to female led households, and/or to households that participate in activities that have an emphasis on female-led activities (e.g. fuel-efficient woodstove); active involvement of women in restoration activities;

- All awareness raising activities will specifically target women and encourage them to take responsibilities including for engagement with the authorities;

- Women’s organisations will be involved in project implementation and capacity development at national and woreda levels.

- The project will adopt the following principles in the day to day management: (i) gender stereotypes will not be perpetuated; (ii) women and other vulnerable groups will be actively and demonstrably included in project activities and management whenever possible, and (iii) derogatory language or behaviour will not be tolerated.

- The project will promote gender mainstreaming and capacity building within its project staff to improve understanding of gender issues and will appoint a designated focal point for gender issues to support development, implementation, monitoring and strategy on gender mainstreaming internally and externally. This will include facilitating gender equality in capacity development and women’s empowerment and participation in the project activities. The project will also work with UNDP experts in gender issues to utilize their expertise in developing and implementing GEF projects. These requirements will be monitored by the UNDP Gender Focal Point during project implementation.

- The project will use gender disaggregated indicators in the PRF for regular monitoring and evaluation of the project progress and reporting and will facilitate involvement of women in the M&E implementation.

The description of proposed gender mainstreaming activities is given in the Table below:

| Project Outputs | Responsible organizations | Gender Mainstreaming Actions |
| --- | --- | --- |
| Component 1/Outcome1: Technical Capacity for planning diversified climate change adaptation practices strengthened |  |  |
| 1.1 Established institutional platform for enhancing the knowledge and capability of local-communities in twelve woredas on the formulation and implementation of climate change response measures through partnership and the provision of needs-responsive training. 1.2 Strengthened capacity of development agents (DAs) and government officials to support the implementation of climate change adaptation practices at the woreda and regional levels. 1.3 Community action Plans for adaptive crop production and animal husbandry as well as community-based natural resource management developed and implemented using a participatory approach in twelve woredas 1.4 Project benefits and best climate change adaptation practice guidelines are documented and disseminated to local community members in twelve woredas through learning, using innovative and locally adapted means. | PMU, EFCCC, NMA, RAs, WAs | Target 52/48 training recruitment policy to all types of trainings for trainees Target 52/48 participation of female staff Ensure women groups are effectively consulted and involved in land use options decision Promote participation of women in development and implementation of participatory Land Use Plans for target woredas Awareness campaigns to target men and women differently; integrate awareness project within women’s organisations Promote fair distribution of benefits with significant share to women Involve women and women organizations in generating gender lessons |
| Component 1/ Outcome 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools |  |  |
| 2.1 Automatic Weather Stations (AWS) installed or rehabilitated, linked to the national meteorological network and protocols for use and maintenance established in each woreda. 2.2 Appropriate weather and climate monitoring and forecast technologies acquired by representatives of the participating beneficiary communities and maintained through a functional and durable partnership. 2.3 Climate-risk assessment and decision-making tools developed and used in collaboration with local communities in twelve woredas. 2.4 Climate-risk assessment and decision-making tools are prepared, pilot tested, put in use and periodically improved using the results thereof in each of the twelve woredas. | PMU, EFCCC, NMA, RAs, Was | Ensure women are involved as weather data monitors at woreda level 50% of women in targeted areas have access to early warning tools and capacities Adopt measures that ensure gender sensitive planning and implementation |
| Component 2/ Outcome 3: Climate change adaptation practices implemented by communities in lowland ecosystems. |  |  |
| 3.1 Critically degraded sites identified and rehabilitated in the twelve woredas through project activities anchored on functional water storage infrastructure designed, constructed and put in use to enhance the resilience and adaptive capacity of local communities in the twelve woredas 3.2 Alternative livelihood opportunities created, expanded and made more responsive to climate change through the implementation of community-led climate adaptive initiatives in the twelve woredas. 3.3 Farm/pasture land rehabilitated through physical and biological soil and water conservation measures in degraded areas in each woreda for and by the vulnerable lowland farming, pastoralist and agro-pastoralist communities. 3.4 Community-based enterprises established and operationalized in each woreda to develop and strengthen climate resilient local business and value chains. | PMU, EFCCC, RAs, WAs | Ensure women are Involved in the decision-making process for choosing sites Active involvement of women and women groups in planning and implementation of restoration projects Increase the number of women in plan implementation committees Target active involvement of women in design and implementation of livelihood projects. Target 52/48 women participation in capacity building trainings for the plan implementation Active involvement of women and women groups in planning and implementation of restoration projects Promote fair distribution of benefits with significant share to women Increase the focus of interventions on female-headed households as beneficiaries of projects. |
| Knowledge Management and M&E | PMU | Apply gender specific analysis in the project M&E Active involvement of women in the project M&E processes Incorporate gender issues in the process of lessons learning Track gender disaggregated data for M&E Consider gender related reporting |
| Project Management | PMU | Ensure that both men and women are visible in the project documents Collect gender-disaggregated data (age, ethnicity, income, education) for reporting and planning Apply gender clause to human resource recruitment, encouraging the applications from women candidates and their hiring At inception: gender screening of the project design and workplan TORs of all staff to include specific responsibilities that support mainstreaming of gender throughout project implementation |

## Annex H:  UNDP Risk Log

|  |  |  | Project risks |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | Date Identified | Type | Impact & Probability | Countermeasures/management response | Owner | Status |
| Unanticipated extreme weather events and climate hazards e.g. pest outbreaks, severe drought, flooding disrupting project work. | At PIF Stage | Environmental | Projected increases in temperatures and frequency of droughts may negatively impact agricultural productivity and natural resource availability. Intense and erratic rainfall in certain areas will cause localized flooding and damage to infrastructure. Pest outbreak in addition will result in an increase in food insecurity. P=4 I=3 | Updated and improved site-specific climate information, forecasting and projections will be developed. Institutional capacity development and training programmes will take place focusing on changing behaviour and increasing preparedness to climate change amongst Woreda government staff, including extension agents. Down-scaled and site-specific agro-meteorological information and advice will be provided to local communities and farmers to prepare appropriately for extreme weather events. Furthermore, the project will adopt an ongoing learning-by-doing approach that will allow for iterative and adaptive management to prepare for dealing with extreme weather events. Climate-smart SWC and CSA techniques will be implemented to reduce risks of extreme weather to livelihoods and ecosystems. Lessons learned will be captured and disseminated elsewhere in Ethiopia through knowledge-sharing forums. | EFCCC | Increasing |
| Increasing dryness leading to decline of river flows and continued decline of groundwater levels, causing extreme scarcity and competition. | At PPG Stage | Environmental | The decrease in Water availability may negatively impact domestic, agricultural and livestock sectors and rendered interventions unworkable. Underground water recharges may dry-off. Consequently, agricultural productivity may decline, livelihoods could be negatively impacted, and food security may decrease. This could lead to possible conflicts. P=4 I=3 | A number of project activities –including climate-smart watershed restoration and rehabilitation, CSA, and SWC measures – have been identified to address these challenges and aimed to ensure more water retention along the channels and designed to decrease the erosive power of water runoff and increase rainwater infiltration. This will recharge and maintain groundwater levels. The implementation of these project activities will therefore mitigate against this risk and reduce the probability of conflict over water resources. | EFCCC | Increasing |
| Women’s engagement in leading change and in land-use practices, which is encouraged by the project, may be constrained by organisational types of behaviour that are generally not considered acceptable, appropriate or desired for women in a deeply conservative societies found across the project areas. | At PPG Stage | Organisational | Observations during the PPG phase has shown that women in the project areas are not expected to take the front-line and hence their specific concern may not be accommodated while their desires to take active role in project interventions may be denied. I= 3 P= 3 | The project aims to specifically engage women in its implementation and as beneficiaries as a means of fostering gender equality in the share of development and adaptation benefits. The community-based interventions are planned to be carried out through in a way to directly benefit the women in design and approaches. It is clear that a special design is needed to ensure that such an approach will be culturally acceptable. | EFCCC |  |
| Institutional capacity and relationships between government departments are not sufficient to provide effective solutions to climate problems that are complex and multi- sectoral. | At PPG Stage | Organisational | Planned project interventions may not be implemented effectively. Climate change may not be mainstreamed into sectoral policies, planning, and budgeting processes. P=2 I=3 | Capacity needs assessments will be undertaken to determine i) the existing linkages between government departments; and ii) the involvement of project stakeholders in decision making. The results will inform capacity development programmes. Institutional and technical capacity will be developed to support inter- departmental coordination, planning and implementation of CCA projects in Ethiopia. | EFCCC | No change |
| Limited ownership of project activities by regional and woreda-level officials. | At PIF Stage | Operational | Low commitments of targeted vulnerable group may discourage ownership and needed motivation from regional and woreda level officials I=2 P= 2 | Participatory approach including sites visit, interviews and consultations with local officials and communities to identify needs and assess priorities will be applied in various project activities in order to ensure commitment and ownership. All targeted regional and woreda-level offices will incorporate the project activities into their annual work programmes. | EFCCC | N/A |
| Delays in procurement at federal and woreda levels, causing project implementation delays, particularly in the development of hard infrastructure. | At PIF Phase | Operational | Delays in project implementation may result in project activities not being properly implemented. P=2 I=3 | Centralised procurement will be undertaken and a Finance Officer with procurement experience hired by the UNDP to regularly address delays in implementation. A system for the expedited transfer of funds will be established. Any delays in implementation will be identified on a monthly basis. The root causes of delays will be addressed through consultative meetings between the relevant participating stakeholders, WSC and Project Manager. Contentious issues will be resolved, lessons learned documented and disseminated to other Woredas so as to avoid occurrence of similar problems. | UNDP and EFCCC | N/A |
| Political unrest at regional and woreda administrative offices | At PPG Stage | Political | Increasing political unrest at targeted regional and woreda administrative center may prevent project activities implementation and delay. I= High P= Likely | This risk is beyond project and all UN Security advice would be respected. Recent interventions are pointing towards de-escalation of unrest and adoption of peace. | UNDP/EFCCC | Decreasing |
| Poor co-ordination in project implementation. | At PIF stage | Operational | Poor sequencing of activities leading to sub-optimal project performance. P=2 I=2 | The project will ensure competent project management teams are employed to manage the project and also strengthen the capacity of implementing partners in project monitoring and with the needed equipment. UNDP would also ensure that the Project Monitoring system is operational. | UNDP/EFCCC | N/A |
| COVID-19 pandemic and response measures at national and local levels may slow down implementation of work plans | PPG stage | Operational and environmental (Health and safety) | COVID-19 pandemic in project sites may result in lockdowns which limit access of staff and materials to the sites and constrain the timely implementation of the project Annual Work plan activities P=2 I=3 | Safety and awareness measures: The project and its personnel will abide by all rules and regulation mandated by the Government of Ethiopia in response to COVID-19. Project staff will take additional precautions to ensure that stakeholders and beneficiaries are not exposed to and that project activities do not in any way, allow spreading of the virus to rural areas. Awareness among project staff and stakeholders, including communities will be embedded in all interactions. Adaptive measures: Project annual work plans will be developed with provision for likely delays due to COVID-19. Project will adopt alternative methods for facilitating activities such as meetings and training sessions. Where activities cannot be carried out or postponed, they will be adapted while ensuring the project still achieves its adaptation objectives. Field based project facilitators will be trained to be able to manage project activities with remote supervision by the PMU. | PMU, EFCCC, Site Officers | Uncertain |
| The COVID-19 pandemic may affect income diversification activities, Value chains and markets | PPG Stage | Operational | Disruptions in value chains may limit beneficiaries’ access to markets thereby affecting climate resilient diversification components of the project. This may hamper the expected impact of the project. P=2 I=2 | The project will facilitate the purchase and sell of project produces to local markets, localize value chains and linkages to the nearby private sector agencies. Support farmers and pastoral groups to establish and strengthen local linkages. Alternative value chains and livelihood activities that are viable and contribute to recovery efforts will be pursued as adaptive measures, while ensuring the climate change adaptation objective remains central to the project, and for the benefit of the most vulnerable communities. | PMU, Site Officers | Uncertain |

Potential risks and likely countermeasures are outlined in the table below. The risks identified here – as well as new/emergent risks – have been re-assessed during the PPG phase.

## Annex I:  Results of the capacity assessment of the project implementing partner and HACT micro assessment

The report of the Micro-assessment of the government implementing partner is hereby attached below:

## Annex J: Theory of Change

Objective: to promote climate change adaptation and sustainable economic growth among communities in Ethiopia’s lowland ecosystems

Outcome 3: Climate change adaptation practices implemented by communities in lowland ecosystems.

Outcome 2: Climate adaptive management adopted by local communities through accessible climate information and decision-making tools.

Outcome 1: Technical capacity for planning diversified climate change adaptation practices strengthened

Output 1.3.

Community action plans meant for adaptive crop production and animal husbandry developed using a participatory approach in twelve Woredas.

Output 1,1

Training modules and platform needed for enhancing the knowledge and capability of government officials, DAs and local-communities in twelve woredas on the formulation and implementation of climate change response measures are established and sustained.

Output 2.1. Nine Automatic Weather Stations (AWS) installed and linked to the national meteorological network and protocols for use and maintenance established in each woreda.

Output 2.2.

Appropriate weather and climate monitoring and forecast technologies acquired by representatives of the beneficiary communities and maintained through a functional and durable partnership.

Output 3.1.

Critically degraded sites identified and rehabilitated in the twelve woredas anchored on functional water storage infrastructure designed, constructed and utilized to enhance the resilience and adaptive capacity of local communities in the twelve Woredas.

Output 3.2.

Alternative livelihood opportunities created, expanded and made more responsive to climate change through the implementation of community-led climate adaptive initiatives in the twelve woredas.

Outpour 3.3

Farm/pasture land rehabilitated through physical and biological soil and water conservation measures in degraded areas in each woreda for and by the vulnerable lowland farmer, pastoralist and agro-pastoralist communities.

Output 3.4.

Community-based enterprises established and operationalized in each woreda to develop and strengthen climate resilient local business.

Output 1.2. Strengthened capacity of development agents (DAs) and government officials to support the implementation of climate change adaptation practices at the woreda and regional levels.

Output 1.4. Project benefits and climate change adaptation practices are documented and disseminated to local community members in twelve woredas through learning, and using innovative and locally adapted means.

Output 2.3.

Climate-risk assessment and decision-making tools developed and used in collaboration with local communities in twelve woredas.

Outpour 2.4.

Climate-risk assessment and decision-making tools are pilot tested and periodically improved using the results thereof in each of the twelve woredas.

Barrier #3: Inability of land users to invest in climate smart technologies and solutions required to diversify and sustain their livelihoods in the face of climate change

Barrier #2: Limited access to climate forecasts, decision-making tools and climate advisory services for Lowland communities

Barrier #1: Lowland communities lack knowledge on risks of climate change; and the benefits of climate smart solutions and adaptation practices..

## Annex K: List of Stakeholders Consulted during the PPG Phase

Federal level

| Mohamed Kedir | SNNPR | Environment and Forest | 0912686923 |
| --- | --- | --- | --- |
| Gutu Beker | Afar | Environment and Forest | 0924512361 |
| Kuse Tanase | SNPPR | Environment bureau | 0910355617 |
| Tamiru Assefa | AA | MoA | 0956388144 |
| Tsige Geberegiorgis | Tigray | Environment Bureau | 0912687152 |
| Haileab Girmay | Tigray | Environment bureau | 0914042511 |
| Awoke Ytoy | Amhara | EPWPOA | 0918020079 |
| Mulu Slute | amhara | EPWPOA | 0918739374 |
| Yared Tsegaye | amhara | Environment Bureau | 0979262299 |
| Abebe Belete | amhara | Environment bureau | 0914603015 |
| Mebrat Mekonen | amhara | Environment bureau | 0925876922 |
| Workneh Gshre | Federal | MoWIE | 0911103197 |
| Dadofo Majii | Oromia | Environment office | 0911956886 |
| Kasim Geda | Oromia | Oromia land administration | 0913327722 |
| Wubua Mekonnen | AA | UNDP | 0911561417 |
| Wordy Hashim | AA | EFCCC | 0913133802 |
| Tesfaye Haile | AA | UNDP | 0911435832 |
| Habtamu Demboba | AA | EFCCC | 0911462653 |
| Sleshi Tsegahun | AA | EFCCC | 0911747423 |
| Shumu Nagasa | Oromia | OEFCCA | 0911756002 |
| Miski Mohamed | Oromiya | OEFCCA |  |
| Abdu Sala | SNNPR | MoGIS | 0911466123 |
| Murad Nuredin | Oromia | EFCCA | 0925211146 |
| Husen Amino | Oromia | EFCCA |  |
| Amanuel G/mada | Oromia | Oromia | 0901321230 |
| Zekarias Maru | AA | NMA | 0926391919 |
| Birhanu Assefa | AA | MoANR | 0916831504 |
| Esayas Lemma | AA | MoANR | 0920722169 |
| Zebdios Salato | AA | MoANR | 0911922499 |

Regional Level

| Awota Tedlla - | 014325518 |
| --- | --- |
| Zenebe Teshome | 0914624326 |
| Tsegaye G/Giorgis | 0914697575 |
| Armaye Girma | 092478255 |
| Desalegne Nguse | 0923493275 |
| Tesegaye G/giorgis | 0912677150 |
| Hadash Siko | 0914107536 |
| Wolday Hagos | 0944413763 |
| Hailay Hinsa | 0914122322 |
| Rahel Atashiza | 0914177386 |
| Ftwi Sahley | 0914177374 |
| Abrha Nigusu | 0914048650 |
| Fekade Segaye | 0919027023 |
| Mawecha Tsadik | 0923050609 |
| Yemane Halefom | 0958126734 |
| G/egziabhere Ababa |  |
| Taklay Mehari | 0914236011 |
| Brhanu Ndehna | 0914413712 |
| Desta Mengistu | 0914404597 |
| Jember Ayalneh | 09180635536 |
| Melkamu Muhabaw | 09181854 |
| Tarko Sintayehu | 0918411363 |
| Baye Abege | 0909149247 |
| Worke Tsegaw | 091842342 |
| Abdulkadir Mohammed | 0913084083 |
| Alli Ibrahim | 021224789 |
| Mohammed Ali | 0930845284 |
| Nur Ibrahim | 0949904979 |
| Ahmed Ibrajim | 0922081014 |
| Abahaba Husen | 0910283216 |
| Ahmed Idin | 0915749446 |
| Abdinkan Ziye | 0915060652 |
| Aanisa Muktar | 0915240546 |
| Hastider Ali | 0915064590 |
| Alemayehu Hulusu | 0915064320 |
| Ibrahim Abdi | 0915969921 |
| Swkha Ahmed | 0930950208 |
| Alimce Maxamed | 0915452582 |
| Mohummed Mahammed | 0984193658 |
| Dodefe Hassi | 0911956886 |
| Hayiquwa Mamo | 0937909837 |
| Alelign Terefe | 0910416526 |
| Abdella Iresso | 0920082927 |
| Kadir Raesn | 0920087688 |
| Asnakech Megerssa | 0913363545 |
| Tarik Degefu | 0915266157 |

LAND USERS

| KASAYE MENGSTU | M |
| --- | --- |
| MULU AYAL | M |
| ASEGDEW KASSE | M |
| KIBRET KASSE | M |
| DESTAW YISMAW | M |
| MEBRATE TEKEBA | F |
| TIRU BIYADG | F |
| FEKADU MENGSTE | M |
| MILASH KASE | M |
| ACHEWACH DEBASH | M |
| KINDU YISMAW | M |
| WORKE FEKADU | F |
| ALE MELKAMU | M |
| ALEMITU ASFAW | F |
| TSEHAY BEKELE | M |
| ZENEBECH ABRHAM | F |
| TEKAE W/MHRET | F |
| SENBETU TAKELE | F |
| ALIAM NEGA | M |
| AREGAWI HAYIS | M |
| LETELIBANOS CHERKOS | F |
| HADASH LWLO | M |
| MULU HAILU | F |
| WUBET BERHE | M |
| ABGEB G/MARIAM | M |
| MARU G/SENBET | M |
| GIRMAY HAGOS | M |
| YOHANES TAREKE | M |
| HAGOS CHEKOLE | M |
| GETU MERDEKIROS | M |
| MANTSEGEBA GERAS | F |
| GIRMAY KALAYU | M |
| MULU WOLDU | F |
| HAREG TESFAY | F |
| CHEKULA AELMU | F |
| ZEWDU GEBRU | M |
| ALEM MOLA | M |
| DERESE LAKEW | M |
| NGUSE MITKU | M |
| GOSAYE DEGENE | M |
| TILAHUN WOLE | M |
| MUSSE GEBRYE | M |
| GOSH GIRMAY | M |
| GETACHEW AZEZE | M |
| MLASH TILAW | M |
| HADEG AMARE | M |
| DINBER TASSEW | M |
| GASHAW YESENBEL | M |
| WAGNEW AMARE | M |
| WERKE WASE | M |
| ENYESH FEKADE | F |
| ENKAYEHUSH SEMBERU | F |
| ALEMITU MALKAMU | F |
| BELAYNEW MARU | M |
| BAYE GETACHEW | M |
| BELETE GUADALEM | M |
| GENET SISAY | M |
| ALEBEL DESTAW | M |
| FEKADU MENGSTE | M |
| WODAJE MUCHE | M |
| MASRESHA FENTA | M |
| MARE GESSESE | M |
| GEDAMU AGDE | M |
| ALEMU YIGZAW | M |
| AMBAW DESE | M |
| ZNGUWACH BELACHEW | M |
| YESHAREG DEMS | M |
| ADUGNA TEKEBA | M |
| BELAYNEH WASE | M |
| ASE MELAKU | M |
| ALEBACHEW MELAKU | M |
| WOREKET NEGA | M |
| ZEYTE ABEBE | M |
| ERKYHUN MESELE | M |
| DEBESH DEMS | M |
| ALENE GETU | M |
| AGARAW TEZERA | M |
| WORKRO GEDAMU | M |
| GZAT WEDAJE | M |
| GIRMAW NESEFE | M |
| MEBRAT AGEAI | M |
| SHEBABAW MLASH | M |
| GASHAW AYENE | M |
| GETU AGDEW | M |
| AWOJE TSEGAYE | M |
| MAMECHE MENGSTE | M |
| SETEGN TAREKE | M |
| MESAFNT GETNET | M |
| WUBANTE THEGNE | M |
| DINKNEW DESTA | M |
| ALELET BEGAR | M |
| TSEGAW MENGSTE | M |
| WUBET MANASEB | F |
| SEFRASH HAILE | F |
| TIGET MARACHEW | F |
| TADELU AZEZE | F |
| BIRCHKO FEREDE | F |
| SHEWAYR EYASU | F |
| TSEHAY ANBESU | F |
| JEMBER AYALNEH | M |
| MELKAMU MUHABAW | M |
| TARKE SINTAYEHU | M |
| WERKE TEGAW | M |
| BAYE ABEJE | M |
| YARED TSEGAYE | M |
| NGUSU WAGAW | M |
| GOSHU BZUAYE | M |

## Annex L: Tentative Lists of Activities proposed for project outputs

The following lists of key activities are proposed to be delivered. These would be updated during the inception phase of the project implementation where necessary:

Outputs 1, the following activities will be undertaken:

- Recruit service providers to develop training modules and deliver trainings to ToTs.

- Establish partnership with appropriate regional institution to host training modules (off and online) and maintain the platform.

- Train 60 ToTs (10 trainee per region) to deliver trainings to regional government officials, DAs, Woreda officials and other stakeholders.

- TOT experts train, interact, and provide follow-up training to 1,200 DAs/government officers and local community representatives in Afar, Amhara, Oromia, Somali, SNNP and Tigray, with a focus on community leaders, women and volunteers that are economically, physically and socially disadvantaged.

- Woreda officials and DAs facilitate the formulation of climate adaptive community-based action plans with focus on Fall Armyworm Response Initiative or flood risk or local grievance and response mechanism to manage conflict and risks for the twelve selected project sites across the six regions.

- Develop TV and Radio documentaries to promote good practices,

- Prepare Information leaflets and posters on community adaption practices being implemented.

- Share experiences through trips and exchange visits to community adaptation initiatives.

- Undertake case studies to capture what the adaptive approaches look like to the communities and these can help contribute to government policies.

To deliver outputs 2, the following activities will be undertaken:

- Install nine (9) automatic weather stations (AWS) in collaboration with the NMA.

- Distribute climate monitoring equipment to woredas in the intervention sites that help generate inputs for seasonal weather and climate forecast services, and better agricultural advisories.

- Establish partnership with the MoANR Agro-meteorological Task Force through signed Memorandum of Understanding (MoU) in order to facilitate weather and climate data collection and analysis.

- Establish linkage with on-going MoANR weather information downscaling initiative through signed MoU.

- Distribute mobile phones to 100 representatives from each project woredas to pilot provision of weather information and advisory services to land users.

- Develop decision-making tools with the participation of land users to allow the effective generation and utilization of weather and climate information.

To deliver outputs 3, the following activities will be undertaken:

- Identify appropriate location in each woreda for water storage intervention in collaboration with communities’ representatives

- Establish or upgrade Tree Nursery facilities that provide inputs for the establishment of agro-forestry systems and rehabilitation of degraded watershed and catchment areas,

- Plant appropriate tree species and build erosion control measures to rehabilitate, reforest and protect at least 100ha of degraded farmland and pasture land for each woreda,

- Design and construct (total of 24 at 2 per woredas) water storage reservoirs, boreholes and rainwater harvesting facilities for improved irrigation that help produce fodder, vegetable and fatten animal.

- Locate livestock watering points near the pastoralist settlements, especially near grazing areas and routes.

- Engage women and youth in particular, to establish community-based enterprises (CBEs) to develop and strengthen climate resilient local business,

- Introduce and scale alternative clean energy options and wood efficient stoves to reduce deforestation and land degradation by empowering local artisans to produce and distribute energy efficient cooking and baking stoves for household use.

4

## Annex M: Co-finance letters

The term “indigenous peoples” is not recognized legally or politically in Ethiopia. There is no national legislation in Ethiopia mentioning or protecting the rights of indigenous peoples. Ethiopia chose not to ratify ILO Convention 169 and was absent during the voting on the UN Declaration on the Rights of Indigenous Peoples (UNDRIP). The project design recognises and has in place necessary safeguards to ensure inclusion of women and vulnerable groups.

The project preparation process involved extensive meetings with communities and their representatives in all of the project woredas and over half of the kebeles where activities are proposed. None of the individuals or groups who were met identified themselves as as indigenous. None of the government officials met during the site visits mentioned the presence of indigenous communities in the project sites. This was confirmed again during validation workshops and separately from woreda administrators of all 22 project woredas.

However, the UNDP definition of indigenous peoples includes highly vulnerable and marginalised groups, who in the project context would include homeless and internally displaced people. Furthermore, the rich cultural diversity of Ethiopia implies that even mainstream communities have distinct cultures, customary beliefs, traditional values, ownership and rights over land. In view of the presence of highly vulnerable and marginalised groups and these unique cultural values, it was decided that the vulnerable communities in the project sites fit into the broad definition of indigenous people and that SES Standard 6 applies to the project. This would ensure the rights and interests of the marginalised and vulnerable groups and culturally distinct communities are safeguarded.

The World Bank. 2016. Data: Ethiopia. Available at: http://data.worldbank.org/country/ethiopia.

Ethiopian Central Statistics Agency & World Food Programme. 2014. Comprehensive Food Security and Vulnerability Analysis, March 2014.

which include inter alia: i) deforestation for wood fuel; ii) cropping in marginal areas such as steep slopes; and iii) overgrazing

The problem has been recognised since the early 1970s by the Government of Ethiopia (GoE) itself, which states the causes to include, “poverty, population pressure, inappropriate (land) use and management, inadequate inputs, unsuitable farming and grazing practices, inappropriate technologies, inefficient markets…and land tenure insecurity” (Government of Ethiopia. 2011. Revised Project Implementation Manual for the Sustainable Land Management Program. Ministry of Agriculture and Rural Development, The Federal Democratic Republic of Ethiopia. January, 2011.)

Food and Agriculture Organisation (FAO). 2010. Global forest resources assessment 2010. FAO forestry paper 163, Rome, 2010.

Ethiopia’s Climate Resilient Green Economy: Climate Resilient Strategy-Agriculture, FDRE, 2013

NDC-Ethiopia available at: https://www4.unfccc.int/sites/ndcstaging/Pages/Home.aspxIbid

For example, enhancing rainwater harvesting techniques to take advantage of increased rainfall.

Gashayie, A. and Singh, M. 2016. Development of Financial Sector in Ethiopia: Literature Review. Journal of Economics and Sustainable Development Vol.7, No.7, 2016. https://iiste.org/Journals/index.php/JEDS/article/viewFile/30063/30885

These criteria comprise the following four elements: i) absence of external support; ii) being located in the lowland ecosystem; iii) vulnerability and capacity to cope with climate change and iv) groundwater potential.

The Second Growth and Transformation Plan (GTP II) (2015/16-2019/20) Available online at:  https://www.africaintelligence.com/c/dc/LOI/1415/GTP-II.pdf. Accessed 15 May 2016.

Details of different component amounts are indicated in the GEF CEO Endorsement Document as required.

Available online at: https://unfccc.int/resource/docs/natc/ethnc2.pdf

Climate change national adaptation programme of action (NAPA) of Ethiopia. 2007. Available online at: http://unfccc.int/resource/docs/napa/eth01.pdf.),

These criteria were: i) climate change risk (loss avoided by poor people); ii) poverty reduction potential (impact on poor people’s income growth); iii) cost effectiveness; iv) complementarities with national and sectoral plans, policies, and strategies and v) synergy with national plans including action plans under multilateral environmental agreements (MEAs)

At Kebele level, “development agents” are responsible for technical advisory services to farmers. At a Woreda-level, “extension officers” oversee the activities of and provide guidance to development agents. The term “extension agents” is used to refer to both levels throughout this document, as their roles often overlap.

The partnership between MoANR and Wageningen University to develop downscaled weather and Agricultural advisory support to farmers and pastoralist would be explored further and supported by the project to achieve the objective set out in this component.

A participatory planning approach is one in which local communities are actively involved in the strategic planning, management and implementation of a project.

The Global Mechanism of the UNCCD. 2007. Practical guide to designing integrated financial strategies for combating desertification. Rome, Italy: Global Mechanism (GM) of the UNCCD.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/policies_guidelines

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

Excluding project team staff time and UNDP staff time and travel expenses.

Refer budget note 25 and 33

Refer budget note 30

Included in the inception period studies, budget note 24

Included in the inception period studies, budget note 24

Local expert to develop ‘’environmental and social grievance response mechanism’’, budget note 31

Refer budget note 30

Refer budget note 26

Refer budget note 26

In the MERET programme, Community Based Participatory Watershed Development Teams (CBPWDTs) were established. CBPWDTs were in permanent contact with development agents, local leaders, community members and Woreda line ministry representatives. Their role was to identify issues and opportunities, mobilise communities, and to plan and implement project activities.

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.

The Executing Agency is also accountable for the use of LDCF project funds.