THE GLOBAL DISABILTY FUND (GDF) END OF PROGRAMME REPORT –

NATIONAL PROGRAMMES

Programme information -Summary

| Programme title: | Accelerating Disability rights in Cambodia |
| --- | --- |
| Countries | Cambodia |
| Overall programme duration: | Inception Phase: 25 February 2021 to 30 September 2021 First phase: 24 months (from 04 March 2022 to 31 March 2024) Second phase: 18 months (26 July 2024 to 31 December 2025) |
| Budget: | Inception Phase: USD 70,000 Phase 1: USD 600,000 Phase 2: USD 500,000 Total: USD 1,170,000 |
| Overall programme focal persons: | Mao Meas, Programme Analyst, UNDP, email: mao.meas@undp.org |
| All PUNOs focal points: | 1. Mr. Sit Song, Programme Coordinator, UNDP, email: sit.song@undp.org 2. Ms. Roanna Tay, Human Rights Officer, OHCHR, email: roanna.tay@un.org 3. Mr. Bunleng Pheap, National Programme Officer, email: b.pheap@unesco.org |
| OPDs and Gov focal points | H.E Sambath UNG, Secretary General of Disability Action Council, email: sambath@dac.gov.kh Mr. Chhor Bonnaroath, Program Manager, Cambodia Disabled People’s Organization (CDPO), email: pm@cdpo.org |
| Reporting period (please include start and end date of the implementation phase): | 04 March 2022 to 31 December 2025 |
| Short description of the programme: | The programme in Cambodia is implementing a triple track approach to advance the rights of persons with disabilities. It focuses on legal reform, and system change, capacity-building of national stakeholders, and increased participation and inclusion of rights-holders in compliance with the CRPD. A final push will consolidate efforts to reform the legislative and policy framework for Cambodia through a new Disability Law and third phase of the National Disability Strategic Plan 2024-2028 (NDSP3). Once these are endorsed, the programme aims to accelerate capacity development and monitor the implementation of these initiatives, especially at subnational levels. It also aims to empower rights holders (Organizations of Persons with Disabilities (OPDs), Women with Disability Forums (WWDFs), and other under-represented groups) by ensuring disability are integrated into the development, implementation, and monitoring phases of the law and NDSP3. This strategy is crucial for a more inclusive society that upholds the rights and dignity of all its members, in all our diversity. |
| Target groups1 | All persons with disabilities |
| Thematic focus2 : | Social protection, Economic empowerment, Employment, Media, Information and Access to Justice |

Acronyms and Abbreviations

ADRC		Accelerating Disability Rights in Cambodia

CDPO		Cambodian Disabled People’s Organization

CIP		Commune Investment Plan

CSO		Civil Society Organization

CTRO		Center for Trauma Care and Research Organization

DAC		Disability Action Council

DAC-SG		Disability Action Council-Secretariat General

DAWG		Disability Action Working Groups

DDP		Deaf Development Programme

GDF		Global Disability Fund

GDSP		General Department of Social Policy

DFAT		Australian Department of Foreign Affairs and Trade

DI		Disability Inclusion

DPs		Development Partners

MEF		Ministry of Economy and Finance

M&E		Monitoring and Evaluation

MoSVY		Ministry of Social Affairs Veterans and Youth Rehabilitation

MoCFA		Ministry of Culture and Fine Arts

MCS		Ministry of Civil Servants

MPTC		Ministry of Post and Telecommunications

NDSP2		National Disability Strategic Plan 2019-2023

NDSP3		National Disability Strategic Plan 2024-2028

NEA		National Employment Agency

OHCHR		Office of the High Commissioner for Human Rights

OPD		Organization of Persons with Disabilities

PDAC		Provincial Disability Action Council

TOR		Terms of Reference

TPO		Transcultural Psychosocial Organization

TVET		Technical and Vocational Education and Training

RGC		Royal Government of Cambodia

UNCRPD		United Nations Convention on the Rights of Persons with Disabilities

UNDAF		United Nations Development Assistance Framework

UNESCO		United Nations Educational, Scientific and Cultural Organization

UNDP		United Nations Development Programme

WWDF		Women with Disability Forum Organization

## 1.Progress towards impact and specific outcomes

Using the table format provided below, please provide information on the contribution towards impact and outcome indicators. Please make sure to capture, in your description, relevant shifts in addressing gaps in preconditions to CRPD implementation, capacity development as well as in the wider disability inclusion agenda and implementation of the SDGs in the country. Where it has not been possible to collect data on indicators, additional narrative information should be provided detailing why that was the case and what plans have been put in place to ensure that the relevant data will be provided.

Expected Impact of the programme/ Impact statement

By 2025, the Joint Programme advanced disability inclusion in Cambodia by strengthening national laws and policies and improving access to public services including information, disability identification, employment, social protection, legal aid, justice and inclusive media. These efforts enabled persons with disabilities, especially women and underrepresented groups, to benefit from stronger support, greater social inclusion, and fuller realization of their rights under the Convention of the Rights of Persons with Disabilities (CRPD).

Please provide narrative description on the contribution towards the stated impact

The Joint Programme’s achievements between 2021 and 2025 are reflected in substantial improvements across the normative framework, service access, disability inclusion, disability identification, employment inclusion, and social protection. A new draft Law on the protection of the rights of persons with disabilities has been developed and is being finalized, with technical support from the programme to ensure meaningful participation of Organizations of Persons with Disabilities (OPDs) and better compliance with the CRPD. The National Disability Strategic Plan 2024-2028 (NDSP3) was launched in December 2024 and disseminated to line ministries, PDACs, OPDs and civil society organizations. The programme also supported the finalization of the long-overdue State party report to the Committee on the Rights of Persons with Disabilities, which was officially submitted to the United Nations (UN) on 21 January 2026. The programme enhanced the capacity of national stakeholders, particularly key duty bearers and rights holders at both national and subnational levels, to contribute effectively to disability-inclusive policies and the implementation of the CRPD and SDGs. The programme has contributed to advancement disability inclusion in Cambodia through thematic policy level interventions (e.g. legislative support, policy briefs, thematic reporting), multi-topic capacity development of the targeted stakeholders (e.g. DACs, OPDs, WWDFs, line ministries, CSOs, media), advocacy, and cross-stakeholder collaboration. A training on access to justice was delivered to judges, prosecutors and court officials from 23 provinces, enabling participants to identify and reduce barriers and strengthen cooperation with OPDs. The programme also built the capacity of OPDs and civil society organizations, focusing on deaf and hard-to-hearing persons and persons with psychosocial disabilities, who are underrepresented in Cambodia. Access to essential services over the programme period, increasing from 4,995 persons with disabilities, including 2,787 women, who received PPE, emergency food assistance, and critical social services in 2021, to 46,487 persons with disabilities, including 15,628 women, accessing a wide range of services across the six Provincial Disability Action Councils (PDACs) by 2025. This tenfold increase demonstrates strengthened provincial coordination, improved governance through PDACs, and enhanced capacity of subnational administrations to deliver inclusive services in healthcare, rehabilitation, education, employment, vocational training, and social protection. Disability inclusion and Media and Information Literacy (DMIL) have been strengthened through evidence-based needs assessments, the promotion of inclusive media, journalist capacity-building, and OPD-led digital awareness initiatives, enhancing access to information for persons with disabilities. In 2023, 139 provincial information officials across all 24 provinces were trained in international standards on access to information, in line with Articles 9 and 21 of the UNCRPD. In addition, nearly 100 journalists, including 54% women and 8% persons with disabilities, were trained to support information officers at both national and subnational levels. This initiative significantly improved the capacity of officials and journalists to respond to the information needs of persons with disabilities, leading to a notable enhancement in the quality and accessibility of public information. Progress in disability identification systems further reinforced inclusive service delivery. CRPD‑aligned disability assessments expanded from 215,358 persons with disabilities assessed in 2021 to 355,280 persons, including 174,013 women, by 2025 nationwide. This growth reflects stronger administrative systems, broader outreach, and closer alignment with national disability policies, enabling more accurate planning and more effective targeting of social assistance and other essential public services. Employment participation among persons with disabilities also improved in absolute terms. In 2021, 8,856 persons with disabilities, including 4,204 women, were employed across Cambodia’s public and private sectors—primarily in garment factories. By 2025, this number increased to 14,407 persons, including 5,562 women, indicating progress in promoting inclusive employment and greater willingness among employers to hire persons with disabilities, despite percentage shifts linked to updated census data. Social protection measures expanded alongside service delivery and employment support. In 2021, 61,400 persons with disabilities received monthly cash transfers under the government’s COVID‑19 response. By 2025, 63,223 persons with disabilities were receiving regular monthly support through the Family Package Social Assistance Programme, demonstrating strengthened systems for identifying eligible households and sustaining long‑term assistance for vulnerable groups. #### Please refer to Annex 1. Impact Indicators of the Joint Programme

State Outcome 1

Capacity of national stakeholders, especially of key duty bearers and rights holders, is enhanced, to ensure more effective contributions towards disability inclusive policies, systems and for the implementation of the CRPD and SDGs.

Please provide narrative description on the progress made to achieve outcome 1

Strengthened Sub‑National Disability Coordination Bodies for Sustainable Inclusion in Cambodia The JP delivered significant institutional strengthening across Cambodia’s disability inclusion system. It enhanced the coordination and operational effectiveness of six Provincial Disability Action Councils (PDACs), enabling them to independently develop and implement their annual work plans. As an outcome of the training, the Kampong Cham PDAC developed a unified four year work plan (2025–2028), and the Siem Reap PDAC developed a five year y-year work plan (2025–2028), and the Siem Reap PDAC developed a five year -year work plan (2025–2029), both of which have been integrated into the respective provincial governing work plans. A major milestone was the successful mobilization of national government budget allocations for disability inclusion: the Kampong Cham and Siem Reap PDACs received US$750 and US$7,500, respectively, to implement their annual action plans. This marks an important step toward sustainable, government led support for disability led support for disability inclusive services at the sub-national level. As a result, these PDACs were able to provide inclusive services to 260,428 persons with disabilities, including 106,765 women and girls, during the four-year period from 2022–2025. Strengthened National M&E System for Sustainable Monitoring of Disability Inclusion in Cambodia The JP significantly strengthened the monitoring and evaluation (M&E) capacity of the DAC‑SG by equipping its M&E team with the skills required to manage and operate the national digital M&E system for the National Disability Strategic Plan 2024–2028 (NDSP3). Through targeted capacity development, the team is now able to coordinate effectively with 24 line‑ministry Disability Action Working Groups and all 25 Provincial DACs to systematically track progress on national disability indicators. A key achievement of the programme is the full handover of the digital NDSP3 M&E system to the DAC‑SG, marking an important milestone toward sustainable, government‑owned monitoring of disability inclusion efforts. The system now enables the DAC‑SG to generate NDSP3 progress reports, support evidence‑based disability inclusion planning, and contribute to future national disability reports, including the CRPD State Report. These strengthened capacities and the institutionalization of M&E processes ensure that disability data management and reporting remain sustainable beyond the programme’s duration. Empowered OPDs and WWDFs to Lead Effective Advocacy for Inclusive Public Services The JP made significant progress in empowering Organizations of Persons with Disabilities (OPDs), Women with Disabilities Forums Organizations (WWDFs), underrepresented groups, and youth with disabilities. Through targeted capacity-building, two OPDs and five WWDFs received training on advocacy workplan development, institutional management, and financial management-building. This support enabled these organizations to independently develop and implement their annual advocacy workplans and effectively engage with local authorities and public service providers. As a direct result of their strengthened capacity, they successfully advocated for improved access to essential public services, benefiting 3,681 persons with disabilities, including 2,111 women and girls, who gained access to social assistance programmes, health and rehabilitation services, vocational training, employment opportunities, and education services. Empowering Deaf and Hard of Hearing Communities with Enhanced Leadership and Communication Skills The JP also expanded leadership and communication capacities among deaf and hard-ofhearing communities in remote provinces. Five groups comprising-hearing communities in remote provinces. Five groups comprising 59 deaf and hard-of hearing-hearing people (including 26 women) from Kampong Cham and Tbong Khmum received foundational sign language and leadership training. Additionally, 365 deaf and hard-of hearing people (including 57 women and 60 youth), among them 40 participants from Kampong Cham and Tbong Khmum, completed the intensive Deaf Leadership Training Programme (DLTP), delivered through 13 structured training courses. This comprehensive programme strengthened participants’ leadership abilities, understanding of Deaf rights, community development skills, and confidence in sign language communication. These emerging leaders are now well positioned-positioned to contribute to and strengthen the future leadership pipeline of the Association of the Deaf People in Cambodia. Enhancing Knowledge and Evidence to Advance Disability Inclusion in Cambodia The programme also generated strong knowledge, sharing outcomes that expanded evidence based practices and improved access to disability inclusive information, communication, and services. A localized manual on the CRPD and facilitator’s guide was developed for DAC, which not only reflects the principles of the Convention but also incorporates the roles and responsibilities of subnational authorities and provides guidance on organizing inclusive training sessions, strengthening DAC officials’ capacity to sustainably continue delivering CRPD-based training. Disability inclusion was advanced through justice sector training, which resulted in the capacity-building of 246 justice actors across Cambodia and connections built with their local OPDs. The programme also provided capacity-building to OPDs and facilitated the inaugural dialogue between OPDs and DAC. The programme strengthened disability inclusion in media by localizing UNESCO’s manual, developing DMIL resources, implementing inclusive campaigns, and fostering collaboration with OPDs and provincial authorities, creating a multistakeholder platform and empowering media to ensure accessible, inclusive, and representative coverage for persons with disabilities. Key achievements included the development of evidence-based information needs assessment, OPD-led digital awareness initiatives, and strengthened disability-inclusive access to information through targeted support to information actors. In 2025, additional communication and rights based resources​ such as a localized CRPD Manual and a Khmer translation of UNESCO’s Practical Manual on Disability Equality in the Media were finalized and disseminated. These efforts supported training for media houses and journalists to better reflect and amplify the voices of persons with disabilities in the media. Furthermore, a situation analysis on the rights of deaf and hard of hearing people, as well as a situation analysis of OPDs, were developed and shared with OPDs, underrepresented organizations, and relevant stakeholders​. These resources contribute to a growing evidence base that strengthens informed decision making and inclusive programming across the disability sector sharing outcomes that expanded evidence-based practices and improved access to disability inclusive information, communication, and services.

State Outcome 2

Gaps in achievement of essential building blocks or preconditions to CRPD implementation in development and humanitarian programmes are addressed.

Please provide narrative description on the progress made to achieve outcome 2

Policy Changed and Strengthened CRPD Implementation The JP made major contributions to advancing disability‑inclusive policy reform and strengthening the enabling environment for CRPD implementation in Cambodia. A key achievement was supporting the Royal Government of Cambodia in the national launch and dissemination of the NDSP3 to approximately 4,500 participants, including 2,500 persons with disabilities at the 27th National and 43rd International Day of Persons with Disabilities on 3 December 2025. The event, presided over by Deputy Prime Minister H.E. Dr. Savoeun Neth, gathered approximately 4,500 participants, including more than 1,000 persons with disabilities. In his remarks, the Deputy Prime Minister urged all sectors, public, private, and civil society, particularly line ministries, provincial and district administrations, and commune councils to integrate disability inclusion into their work and budget plans as outlined in the NDSP3, ensuring improved services for persons with disabilities at all levels. Through close collaboration with the Royal Government of Cambodia (RGC), the JP strengthened national systems for monitoring and implementing the NDSP3. The programme trained 24 Provincial Disability Action Committees (PDACs) and 24 line ministries and national institutions on NDSP3 indicators, enabling each institution to identify and apply the indicators most relevant to their mandates. This capacity strengthening directly contributed to multiple national-level policy reforms advancing Cambodia’s compliance with the Convention on the Rights of Persons with Disabilities (CRPD). As a result of the JP’s support, several ministries introduced landmark policy measures in 2024–2025 that expand disability inclusion across key sectors. The Ministry of Information released a regulation requiring enhanced accessibility on public and private television channels, including sign language interpretation, audio description, and subtitles, ensuring improved access to information for persons with visual and hearing disabilities. The Ministry of Interior and the Ministry of Economy and Finance jointly released a regulation in 2025 to explain a national budget allocation for commune administrations to fund disability inclusive-inclusive social services. The Ministry of Environment incorporated disability inclusion into Cambodia’s Third Nationally Determined Contribution (NDC 3.0), marking an important step in integrating disability considerations into climate policy. Furthermore, the RGC included persons with disabilities as a priority group within the National Policy on Social Protection 2024–2035, ensuring their eligibility for monthly cash transfers under the Family Package of the social assistance scheme. Disability inclusion was also embedded into sectoral strategies, with the Ministry of Women’s Affairs integrating disability considerations into the Neary Rattanak VI Strategic Plan 2024–2028, and the Ministry of Education, Youth and Sport embedding disability inclusion in its Disability Inclusive-Inclusive Action Plan 2024–2028. Furthermore, commitments were secured from the Ministry of Culture and Fine Arts to ratify the Marrakesh Treaty, marking an important step toward accessible information for persons with visual impairments. These policy outcomes collectively demonstrate a strengthened national commitment and institutional capacity to implement the CRPD, directly attributable to the Joint Programme’s coordinated support. Demonstrating strengthened national commitment to its obligations under the Convention on the Rights of Persons with Disabilities (CRPD), the Royal Government of Cambodia formally endorsed its First Initial State Report on the Implementation of the CRPD in late 2025. This milestone reflects significant progress in institutional capacity, coordination, and compliance supported by the Joint Programme. The report has been officially submitted to the UN CRPD Committee as of 21 January 2026, marking a major step toward advancing accountability, visibility, and international recognition of Cambodia’s efforts to promote and protect the rights of persons with disabilities. H.E Sambath UNG, Secretary General of the Disability Action Council-Secretariat General, acknowledged that “The Government of Cambodia expresses deep appreciation for the United Nations’ collaboration and support in completing our Initial State Report on the implementation of CRPD, marking an important milestone in advancing disability rights and strengthening inclusive development nationwide.” Although internal reforms within MoSVY delayed the endorsement of the new disability law, this delay provided opportunities for the technical team to incorporate further inputs, ensuring alignment with the CRPD. The programme provided legal and technical advice on the draft law, including new provisions on legal capacity, the legal recognition of sign language, and the governmental coordination and focal point(s) mechanism for CRPD implementation. The draft law is now under review by DAC and MoSVY leadership and is expected to be submitted to the Council of Ministers by mid-2026. Strengthening Decentralized Disability Governance Through Expansion of District DACs in Cambodia The JP significantly strengthened disability governance structures by supporting the expansion of the Disability Action Council (DAC) mechanism to decentralized levels. A major achievement was the establishment of 10 District Disability Action Councils (District DACs) in Kampong Cham Province in 2023, enabling more coordinated and responsive service delivery for persons with disabilities at the local level. These District DACs brought together commune chiefs, OPDs and self-help-help groups, and all relevant public sector representatives, creating a formal platform where persons with disabilities can raise their rights and needs during quarterly meetings. The successful implementation of this district level model generated strong momentum for replication across provinces. As a direct outcome of the Joint Programmer’s level model generated strong momentum for replication across provinces. As a direct outcome of the JP’s influence, Tbong Khmum Province established seven District DACs, and Oddar Meanchey Province, even without being a target province of the programme, established one District DAC after learning from the model. This expansion reflects growing national ownership and recognition of the value of decentralized disability coordination. Building on this success, the Disability Action Council–Secretariat General (DAC-SG) has initiated revisions to the national sub-decree governing Provincial DACs to formally integrate District DACs as part of the official disability governance structure. The revised -decree governing Provincial DACs to formally integrate District DACs as part of the official disability governance structure. The revised sub-decree is expected to be approved by the Royal Government of Cambodia in April 2026, marking a transformative policy shift that institutionalizes district level disability coordination nationwide and ensures -level disability coordination nationwide and ensures long-term sustainability of the Joint Programme’s-term sustainability of the JP’s results. Strengthened Civil Society Engagement and International Visibility The programme also strengthened the role of civil society and OPDs in national and international human rights processes, contributing to more inclusive governance structures. Through targeted support, the JP enabled OPDs and persons with disabilities to actively participate in Cambodia’s fourth cycle of the Universal Periodic Review (UPR). OPDs made a former Stakeholder Submission, and four representatives from CSOs and OPDs joined the UPR pre‑session in Geneva, where they successfully raised key disability inclusion issues. Their engagement contributed directly to eight disability-related recommendations being reflected in the final UPR outcomes, demonstrating increased visibility and recognition of disability rights at the global level. This enhanced participation reflects a critical step toward fulfilling CRPD obligations, empowering civil society to influence policy dialogue, and ensuring accountability for disability-inclusive development.

State Outcome 3

National development and humanitarian plans, budgets, programmes and monitoring processes are disability inclusive.

Please provide narrative description on the progress made to achieve outcome 3

Advanced Inclusive COVID-19 Recovery by Building OPD Leadership and Participation in Local Governance At the inception phase, the JP developed the COVID-19 Crisis Recovery Plan for Persons with Disabilities 2021-2023, which was complementary to the National Disability Strategic Plan 2019-2023 (NDSP2) for the DAC-SG and OPDs in Cambodia. The advocacy toolkits were also developed for the OPDs and WWDFs to advocate for the rights and needs of persons with disabilities, particularly regarding the social assistance programme during and after the COVID-19 pandemic. The JP then used the advocacy toolkits to train one OPD and 5 WWDFs, enabling them to advocate for disability inclusion within local government mechanisms successfully. As a result of their strengthened capacity, one OPD and 5 WWDFs were formally appointed as members of the CCWC. This institutional recognition created a sustained platform for persons with disabilities to participate in local decision‑making. Their active engagement in CCWC monthly meetings led to measurable improvements in access to essential public services, enabling 1,681 persons with disabilities (including 951 women) in 2022 and 2023 to receive support such as cash transfers, disability identification assessments, IDPoor registration, education services, health care, and rehabilitation. Strengthening National Disability Inclusive-Inclusive Social Protection Systems for an Equitable COVID-19 Recovery The implementation of the NDSP2 and the COVID-19 Crisis Recovery Plan for Persons with Disabilities (2021–2023) generated substantial national-level impact by strengthening disability-inclusive social protection systems across the RGC. As a direct result of these efforts, over 60,000 persons with disabilities were included in the government’s cash transfer programme in 2022, improving their economic security during and after the COVID-19 crisis. In addition, by 2023, 288,000 persons with disabilities, including an estimated 135,000 women and girls, completed disability identification assessments and received 222,148 disability identification cards. These cards serve as an essential gateway to national social benefits and public services including health care, rehabilitation, education, and social assistance, ensuring stronger inclusion and long-term access to government support. These achievements demonstrate significant progress toward building robust national systems for disability inclusion. They also reflect improved coordination and strengthened linkages between community-level OPDs and government social protection mechanisms, contributing to more equitable and sustainable fulfilment of the rights of persons with disabilities.

## 2. Achievement of specific outputs

Please complete by indicating what was achieved on each output and report against the output indicators. In the narrative, please describe any challenges during the output delivery. The narrative could include any qualitative results from the output activities that were completed, contextual specifics e.g. who are the beneficiaries? What are the intervention types? Any unexpected / unplanned results?

Please complete one table per output including all relevant output indicators. Add as many tables as required.

Output 1.1 (phase 1).

Enhanced capacity of multi-stakeholders at national and subnational level in charge of disability mechanisms (Disability Action Council, Provincial Disability Action Council and Disability Action Working Group at line ministries) to support implementation and monitoring of disability inclusive policies (Social protection), laws (Disability Law, Law on Access to information) and plans (National Disability Strategic Plan 2-NDSP2).

Brief narrative description on completion of output

The JP strengthened Cambodia’s disability inclusion system by guiding DAC, OPDs, and key stakeholders toward aligning national disability policies with the CRPD, improving monitoring frameworks, and enhancing OPD participation in policymaking. Through targeted capacity‑building, three PDACs improved their ability to plan, monitor, and deliver disability‑inclusive services, resulting in regular coordination meetings and stronger local mechanisms, such as Kampong Cham’s new district‑level disability action working groups, that empowered persons with disabilities to voice their needs directly to local authorities. The project also advanced national efforts to address information barriers by developing a Research Framework for the Information Needs Assessment, training 139 provincial information officers on UNCRPD-aligned standards, and improving the accessibility of public information services. and creating a comprehensive Digital, Media and Information Literacy Competency Framework in collaboration with government ministries and OPDs, which will guide cross‑ministerial actions to improve digital, media and information literacy for all Cambodians, including persons with disabilities, ensuring that no one is left behind. By equipping individuals with these skills, the programme supports meaningful participation in Cambodia’s digital economy and society, informed decision-making, resilience to online mis- and disinformation, and active engagement in public dialogue through the critical production and consumption of information. The JP has driven significant progress in disability inclusion and Digital, Media, and Information Literacy (DMIL) in Cambodia, ensuring that persons with disabilities can access information, participate fully in public life, and engage confidently in the digital and media landscape. Between 2022 and 2023, the JP strengthened national and sub-national disability inclusion systems across Cambodia by enhancing the capacities of five PDACs to deliver improved public services and social assistance to 161,325 persons with disabilities, including 71,445 women. The JP also equipped justice actors, media houses and information officers with a stronger understanding of disability rights and CRPD principles to reduce barriers in accessing justice and information. At the national level, the DAC SG improved its monitoring and reporting capabilities through a new digital M&E system adaptable for future disability strategies and CRPD reporting, and advanced key policy initiatives, including the National Guideline on Disability Inclusive Social Protection and revisions to the Access to Information Law. The JP also supported a national consultation with 88 participants, including 27 women and 29 persons with disabilities, contributing to Cambodia’s commitment to ratify the Marrakesh Treaty in the future and further expanding access to information for all. (See Annex 2. Output indicator results)

Output 1.1 A (phase 1):

Enhanced capacity of disability movement, including women with disabilities and most vulnerable groups (deaf persons, blind persons and persons with psychosocial disabilities) to effectively engage in development, implementation and monitoring of CRPD and Inclusive SDGs processes by improving their capacity for meaningful engagement and advocacy with the national and subnational stakeholders including government and service providers in areas of inclusive social protection, access to justice, meaningful representation (persons with hearing impairment) and economic empowerment (women with disabilities)

Brief narrative description on completion of output

The JP significantly strengthened disability inclusion and local governance by building the capacity of commune administration leaders, OPDs, and deaf groups to participate meaningfully in decision‑making and community life. Training improved the knowledge of six commune council leaders by 38%, enabling disability‑inclusive activities to be integrated into 2023 Commune Investment Plans. Between 2022 and 2023, six OPDs (including 5 WWDFs) were equipped with advocacy skills, resulting in official OPD representation on CCWCs, where they successfully voiced the rights and needs of persons with disabilities and supported 1,681 persons with disabilities, including 992 women, to access essential services such as social assistance, health care, rehabilitation, and education. By 2023, the JP also established and strengthened seven groups of persons who are deaf or have hearing impairments, providing training on leadership, communication, teamwork, and sign language, and supporting their vision to establish a future Cambodian Deaf Association with backing from provincial and national authorities. By 22023, the JP further enhanced access to justice, psychosocial support, and information rights for persons with disabilities. Through awareness sessions, 134 community members improved their understanding of psychosocial support, contributing to the unchaining and uncaging of persons with psychosocial disabilities, while 127 persons with psychosocial disabilities received inclusive psychosocial services. Collaboration with Legal Aid of Cambodia strengthened case documentation skills among OPDs and expanded legal support, with 17 cases involving persons with disabilities handled in 2023. At the national level, a landmark Information Needs Assessment for Persons with Disabilities developed with CDRI and validated by over 60 stakeholders, provided strong policy recommendations to improve information accessibility. Additionally, a training module on access to information for persons with disabilities was developed with CDPO, equipping information providers with essential knowledge on disability rights, legal frameworks, and inclusive communication. (See Annex 2. Output indicator results)

Output 1.1 A (phase 2):

The capacity of DAC, DAWGs at line ministries, Provincial DACs, District DACs, UNCTs, OPDs and media is enhanced through approaches and strategies designed to accelerate knowledge transfer for the effective delivery of inclusive services to persons with disabilities, including women, girls and underrepresented groups of persons with disabilities at both national and subnational level.

Brief narrative description on completion of output

Scaling Provincial Disability Action Models to Deliver Inclusive Services for Over 99,000 Persons with Disabilities The JP significantly strengthened institutional capacity and coordination mechanisms within Cambodia’s disability inclusion system, particularly across six PDACs. Through improved work planning, systematic monitoring, and stronger cross sectoral collaboration, these PDACs delivered inclusive services to 99,103 persons with disabilities including 35,320 women and girls across health, rehabilitation, education, employment, and social protection services in 2024 and 2025. The Programme also documented and shared a best practice model from Kampong Cham (Khmer version), where the five-year PDAC Work Plan (2024–2028) was developed, supported by a national budget allocation of at least US$750 annually since 2024, and successfully implemented to reach 29,510 persons with disabilities, including 10,228 women and girls, over 2024–2025. This model has informed replication efforts across all 25 provinces. For example, Siem Reap PDAC developed and began implementing its five-year Work Plan (2025–2029) with an annual national budget allocation of US$7,500 to support disability inclusion activities. Enhanced Government and UN System Accountability for Disability Inclusion Through Strengthened Coordination Mechanisms At the national level, the JP significantly strengthened institutional capacity and advanced disability inclusion across government and UN systems. Through targeted capacity building, 43 DAC-SG officials enhanced their competencies in workplan development and monitoring and evaluation, resulting in more systematic and evidence-based coordination of disability related actions. Collaboration between the Disability Action Council (DAC) and the Ministry of Justice further expanded access to justice efforts, with 246 justice actors across Cambodia, trained from 2023 to 2025 to better address the needs and rights of persons with disabilities. These combined actions contributed to stronger national mechanisms for implementing disability related commitments. UN-wide coordination and accountability also improved. Engagement through the UNDIS regional workshop catalyzed the designation of disability focal points across UN entities, creating a more coherent UN system response to disability inclusion. The JP played a central role in improving disability mainstreaming within the UN Country Team (UNCT). It supported the adoption of the UN Disability Inclusion Strategy (UNDIS) Action Plan, leading to strengthened governance structures, including focal points appointed in all UN entities and key coordination bodies such as the Operations Management Team (OMT). In late 2024, the UNCT Human Rights Group, supported by the JP, completed the first UNDIS Action Plan and mapping, establishing the foundations and coordination framework required to institutionalize disability inclusion across the UNCT. Continuous capacity strengthening efforts JP supported training for the Human Resources Group, Communications Group, and all UNDIS Focal Points, along with technical assistance during the completion of the UNDIS Scorecard. In June 2025, a follow-up training delivered jointly with the Resident Coordinator’s Office and Human Rights Group reached 30 UN disability focal points and members of OMT, M&E, and Communications Groups, as well as OPDs. The training improved participants’ understanding of UNDIS implementation and fostered direct dialogue with OPDs on challenges and entry points for inclusive practices. These engagements are translated into concrete outcomes. UN entities committed to mainstreaming disability inclusion across programming and internal operations. Immediate follow up actions included revising procurement, premises, and human resources guidelines to promote inclusive practices; supporting UNDIS scorecard rollouts; and improving access to recruitment opportunities for persons with disabilities through OPD networks. Engagement through the UNDIS regional workshop catalyzed the supported training for the Human Resources Group, Communications Group, and all UNDIS Focal Points, along with technical assistance during the completion of the UNDIS Scorecard. Empowering OPDs, WWDFs, and Underrepresented Persons with Disabilities Following targeted advocacy training and the development of NDSP3-aligned work plans, seven Organizations of Persons with Disabilities (OPDs) and Women with Disabilities Forums (WWDFs) significantly strengthened their capacity to influence local governance, as evidenced by the following results: - All seven OPDs and WWDFs were formally invited to participate in monthly meetings of 14 Commune Committees for Women and Children (CCWCs), securing a sustainable platform for ongoing advocacy on the rights and needs of persons with disabilities. - Between January and December 2025, these partnerships facilitated access to essential services for 2,008 persons with disabilities (including 1,114 women), such as social assistance (IDPoor), disability identification, education, health care, and rehabilitation, through 14 local commune administrations. - All 14 commune councils committed to implementing disability-inclusive actions in 2026, including enhanced participation of persons with disabilities in social assistance and IDPoor assessments, as well as strengthened referral mechanisms for health and rehabilitation services. The JP catalyzed more inclusive local governance structures and demonstrated that empowered OPDs and WWDFs play a direct and critical role in improving service delivery and securing institutional commitments at the community level, in alignment with NDSP3 implementation. Enhanced Deaf Leadership to Drive Advocacy and Lay the Foundation for a Future National Deaf Association The JP collaborated with the Deaf Development Programme (DDP) of Caritas Cambodia in 2024 and 2025 to expand leadership, communication, and organizational development among Deaf and hard-of-hearing persons. Key achievements include: - A comprehensive 2024 situation analysis on the rights of deaf and hard of hearing people informed a three-year roadmap toward establishing a national Deaf Association. - Five Deaf groups formed in 2024 were strengthened through ongoing engagement and leadership training. - The Deaf Leadership Training Programme (DLTP) was expanded, led by eight trained deaf trainers (four women), supported by DDP and international advisor Colin Allen. - A dedicated Deaf leadership management team was created, improving capacities in communication, decision-making, reporting, and programme oversight. - Leadership and sign language skills were expanded to five deaf groups (59 participants, including 26 women) in Kampong Cham and Tbong Khmum in 2024. - A national awareness-campaign was produced and launched in cooperation with both DAC and DDP, bringing greater attention and advocacy to the recognition of Cambodian sign language as a step toward inclusion of deaf and hard-of-hearing persons. - A White Paper on the Legal Recognition of Sign Language was shared with DAC in July 2025, which included draft provisions for consideration for inclusion in the new draft Disability Law. - A total of 365 deaf and hard of hearing persons (57 women and 60 youth), including 40 from remote provinces, completed 13 DLTP training courses, strengthening their rights awareness, community mobilization abilities, and leadership confidence in 2025. - A two-part capacity-building programme on Promoting Human Rights Awareness Among the Deaf Community was organized in collaboration with DLTP, engaging 20 emerging deaf leaders (11 women, 9 men) in discussions on fundamental human rights, the CRPD, and the importance of formal recognition of Cambodian Sign Language. A growing cadre of trained Deaf leaders is now positioned to drive national level advocacy and support the future establishment of a national Deaf Association, addressing a longstanding gap in representation for deaf and hard of hearing persons in Cambodia. Enhanced Knowledge Generation and Evidence Based Resources to Advance CRPD Aligned Disability Rights Based Resources to Advance CRPD Aligned Disability Rights Based Resources to Advance CRPD Aligned Disability Rights The Programme also generated substantial knowledge products and strengthened networks to advance disability rights nationally. A policy brief based on Cambodia’s first Information Needs Assessment advocated for accessible information and contributed to policy recommendations aligned with the CRPD, training 139 provincial information officers, aiming at improving the accessibility of public information services. To support future capacity‑building, the Programme drafted a localized CRPD Manual with an accompanying facilitator’s guide, which OHCHR has already supported DAC to deliver to 113 PDAC officials. The programme also produced a Khmer translation of UNESCO’s Disability Equality in the Media Practical Manual and delivered a disability-inclusive media training curriculum reaching 100 media professionals nationwide. This has led to more accurate, diverse, and empowering representations of persons with disabilities in Cambodian media. The programme also established a sustainable national network of master trainers with disabilities, introduced an updated DMIL curriculum reflecting OPDs’ lived experiences, and provided small grants to support localized training and advocacy, creating a lasting impact on inclusive media and information access in Cambodia. Furthermore, two major studies were conducted: (1) a situation analysis on the rights of deaf and hard‑of‑hearing people, outlining recommendations and a strategic roadmap toward establishing a national Deaf Association; and (2) a situation analysis on the status of OPDs across Cambodia, identifying challenges and strategies to strengthen the disability movement and promote meaningful participation of persons with disabilities in community and national processes. Overall, the Joint Programme contributed to stronger national, UN institutional and OPD systems, enhanced accountability mechanisms, and improved collaboration with OPDs and underrepresented organizations, creating the momentum needed to advance disability inclusion sustainably across government and UN structures. A deaf young lady said: "Before I joined the deaf group, I did not have friends because I could not communicate with other people in the village. After joining, I learned basic Khmer sign language and could communicate with peers and even chat with them via Facebook. My life has completely changed. Now I can talk to the world. OPDs expressed appreciation for the dialogue, noting its significance as a starting point for future engagement. They highlighted key challenges, including registration processes, funding gaps and the need for awareness-raising at the subnational level. They shared their hopes and expectations for collaboration with DAC and future, regular dialogues. (See Annex 2. Output indicator results)

Output 1.1B (phase 2):

The capacity of the M&E team of DAC, DAWGs, provincial DACs, CDPO, OPDs and relevant stakeholders is enhanced to operationalize the digital M&E system of NDSP3.

Brief narrative description on completion of output

The JP strengthened national monitoring and evaluation capacities by supporting the DAC and DAC‑Secretariat General (DAC‑SG) in developing robust indicators aligned with the strategic objectives of the NDSP3. Through technical discussions held during the final validation workshop on 26–27 March 2024, combined with three targeted training sessions for the DAC‑SG M&E team, the JP facilitated the creation of a comprehensive set of NDSP3 indicators, which were formally approved by DAC. This process equipped the DAC‑SG with the skills necessary to coordinate effectively with data collectors and apply standardized M&E tools, laying a strong foundation for improved data quality and evidence‑based decision‑making. To ensure sustained capacity and ownership, JP delivered an additional three training sessions on the new digital M&E system for NDSP3 to the M&E team of DAC-SG in late 2024. These sessions covered indicator interpretation, system navigation, and practical guidance on data entry, analysis, and reporting. As a result, the DAC‑SG M&E team gained the confidence and technical competency required to manage the system independently. By December 2025, the digital NDSP3 Monitoring and Evaluation (M&E) system, led by DAC-SG, was disseminated to all 25 Provincial Disability Action Councils and 24 line ministries, marking a major step toward evidence-based tracking of disability inclusion. Although the digital M&E system was not officially launched for data collection has not yet, preparations are well underway to confirm the final indicators with the relevant line ministries. To strengthen institutional capacity, 184 (44 women) focal persons (2 focal persons per institution) from 29 line ministries and 24 PDACs received training on NDSP3 indicators and data collection processes. This will enable quarterly reporting to DAC-SG and ensure timely, accurate monitoring of progress under the National Disability Strategic Plan 2024–2028. These efforts reflect growing commitment to embedding disability inclusion within planning and accountability systems at both national and subnational levels. In addition, the digital NDSP3 M&E system was handed over to DACSG, ensuring national ownership. DAC-SG now holds full responsibility to manage, maintain, and upgrade the system in line with future needs during the implementation of NDSP3 and subsequent national disability strategies. The JP has strengthened national systems, improved institutional capacity for monitoring disability inclusion, and established the foundation for a sustainable, evidence-driven approach to implementing NDSP3 at both national and subnational levels. (See Annex 2. Output indicator results)

Output 1.2 (phase 1):

Enhanced capacity of UNCT to support government on SDGs inclusive processes and COVID-19 inclusive recovery plan by building inclusive tools, dialogues and effective participation of OPDs

Brief narrative description on completion of output

The JP strengthened the capacity and accountability of Provincial DACs by working closely with DAC to develop and pilot a comprehensive self‑assessment tool covering nine key areas of governance, coordination, and resource mobilization. Through this tool, three PDACs, Kampong Cham, Battambang, and Kampong Speu, systematically evaluated their performance and identified areas for improvement. Between March and October 2022, their average functionality score increased from 3.56 to 3.72 out of 5, demonstrating measurable progress in areas such as role clarity, planning, capacity building, partner collaboration, and meeting effectiveness. This structured assessment approach improved PDACs’ ownership of their roles and strengthened OPD engagement in subnational disability inclusion efforts. At the national level, the JP contributed to the UN Disability Inclusion Strategy (UNDIS) implementation through the annual Disability Scorecard, which showed incremental progress in 2023. While over 35% of the 14 indicators met the required standards and more than 50% were close to meeting them, the results also highlighted areas still needing improvement. In response, the UNCT Human Rights Group agreed on follow‑up measures and began developing targeted actions to strengthen UNCT compliance with UNDIS, supported by coordination from the RCO and the JP team. Overall, the JP generated a stronger evidence base, clearer performance benchmarks, and renewed commitment to improving disability‑inclusive governance at both subnational and national levels. (See Annex 2. Output indicator results)

Output 2.1 (phase 1):

Drafting of new Disability Law and required sub-legislation aligned with CRPD with full participation of OPDs (from the consultation until the submission to Council of Ministers)

Brief narrative description on completion of output

The JP played a central role in advancing the reform of Cambodia’s disability law by strengthening national ownership, technical capacity, and inclusive policymaking. It provided extensive technical assistance to the DAC‑SG, including advising on the formation of a technical working group with OPD representation, reviewing international good practices, and ensuring alignment of the draft law with the UNCRPD and related human rights frameworks. The programme facilitated broad-based consultations with government ministries, OPDs, CSOs, and the private sector, enabling the collection and consolidation of stakeholder inputs and supporting DAC in drafting the statement of rationale for high‑level officials. As part of the government’s evolving review process, the programme continued to advise DAC‑SG and the General Department of Social Policy on legislative refinement, including new requirements to conduct a cost‑effectiveness analysis demonstrating the necessity, expected impact, and budget implications of the disability law. In parallel, the JP strengthened Cambodia’s compliance with international human rights obligations by providing legal and technical analysis to MoSVY and DAC‑SG. This included detailed recommendations to integrate gender equality and the rights of women and girls with disabilities (CRPD Article 6) and to reinforce inclusive provisions across key areas such as employment, reasonable accommodation, health, mobility, political participation, justice services, and protection from violence. Although structural changes following the July 2023 national election delayed formal approval of the law, the coordinated support of UNDP and OHCHR ensured continued progress, with plans to advance the legislation to the Council of Ministers by mid-2026. Overall, the programme’s contributions have strengthened national systems, improved legal coherence with international standards, and laid the groundwork for a more robust and rights‑based disability legislative framework in Cambodia. (See Annex 2. Output indicator results)

Output 2.1.2 (phase 1):

The new Disability Law has clear implementation plan with clear roles and is effectively disseminated to both national and sub national level through communication campaigns throughout the country

Brief narrative description on completion of output

The JP contributed to strengthening national readiness for implementing Cambodia’s forthcoming disability law by supporting the DAC and MoSVY throughout the legislative development process. Although the endorsement of the law has been delayed due to post‑election restructuring within line ministries, the programme ensured that critical groundwork was completed to facilitate smooth implementation once the law is approved. This includes helping DAC identify key regulatory areas such as the employment quota system, social assistance programme, disability identification system and higher education fee reductions for students with disabilities that will require ministerial action immediately after endorsement. The programme also provided advice on the coordination and focal point(s) mechanism required for implementation under the CRPD, for consideration in DAC’s future structure and responsibilities. As a result, the government is better positioned to operationalize the law’s provisions once it receives Royal approval. In response to the evolving context, the programme also provided strategic guidance to prioritize the final validation of the draft law while simultaneously preparing for the next policy cycle. This has resulted in DAC and MoSVY initiating preparatory steps for the new National Disability Strategic Plan 2024–2028, ensuring alignment with the forthcoming legal framework and CRPD. The programme’s support has therefore strengthened institutional preparedness, improved policy coherence, and positioned national stakeholders to effectively implement and enforce the new disability law once endorsed. (See Annex 2. Output indicator results)

Output 2.1.3 (phase 1):

Disability Action Council has a clear mandate and approved plans to monitor National Disability Strategic Plan and the New Disability Law with full participation with OPDs.

Brief narrative description on completion of output

The JP significantly strengthened national monitoring and evaluation systems for disability inclusion by supporting the establishment of the DAC‑SG M&E team in February 2022 and enhancing its capacity to track progress on the National Disability Strategic Plan 20219-2023 (NDSP2). With financial support from DFAT and GDF, the programme provided technical guidance and collaborated with a web development firm to create an online Web Application reporting system containing 98 indicators to monitor NDSP2 implementation. As a result, government focal points from four line ministries and twelve Provincial DACs successfully reported their progress through the digital system, marking the first time Cambodia utilized a centralized, data‑driven platform to monitor disability policy implementation. The JP strengthened the use of evidence to drive disability‑inclusive policy action. Through the dissemination of NDSP2 monitoring results and Web Application data across ministries, the RGC issued two disability‑inclusive regulations in 2022: one on social assistance cash transfers for flood‑affected vulnerable households, and another on inclusive physical accessibility in sub‑national administrative facilities. The Programme, through DAC, also supported the review of NDSP2 implementation and generated key recommendations that directly informed the development of NDSP3. Building on improved national M&E capacity, the JP supported DAC‑SG to convene a national multi‑stakeholder workshop in June 2024 with OPDs, government ministries, and civil society. The workshop contributed directly to the zero draft of the NDSP 2024–2028, ensuring that evidence, lessons learned, and stakeholder inputs from NDSP2 were systematically embedded in the new strategy. Overall, the JP demonstrated measurable impact by institutionalizing data‑driven planning and strengthening disability‑inclusive policy development in Cambodia. (See Annex 2. Output indicator results)

Output 2.1A (phase 2):

Access to disability inclusive services increased in line with NSDP3 for persons with disabilities, including women, girls and underrepresented groups of persons with disabilities, through the effective and efficient operationalization of DAC, DAWG at line ministries, provincial and district DACs, and OPDs.

Brief narrative description on completion of output

Advancing Disability Inclusive Policy Reform and Institutional Capacity in Cambodia Inclusive Policy Reform and Institutional Capacity in Cambodia-Inclusive Policy Reform and Institutional Capacity in Cambodia The JP contributed to significant national progress on disability inclusive policy reform in Cambodia. It supported the official launch of the NDSP3, reaching 4,500 participants including 2,500 persons with disabilities at the National and International Day of Persons with Disabilities on 03 December 2025 and helped strengthen the alignment of key legal and policy frameworks with the Convention on the Rights of Persons with Disabilities (CRPD). In 2025, the JP, in collaboration with the DAC-SG, conducted NDSP3 dissemination and training sessions for individual ministries and PDACs, reaching 3,621 participants including 1,446 women and 257 persons with disabilities from 23 line ministries and 25 PDACs. The training equipped government officials and OPD staff with a solid understanding of the seven strategic objectives and 96 indicators of NDSP3, and strengthened their capacity to identify, select, and integrate the relevant objectives and indicators into their respective institutional plans. Training results demonstrated a strong shift in knowledge and readiness for implementation. Of the 323 participants who completed feedback forms, 261 (81%) reported improved knowledge from moderate to high on NDSP3. Additionally, 174 participants (54.13%) expressed confidence in training others. Regarding institutional uptake, 162 respondents (50.2%) confirmed integrating NDSP3 into their 2025 workplans, with additional commitments for 2026 (140 respondents; 43.3%), 2027 (13 respondents; 4%), and 2028 (8 respondents; 2.5%). Impact of NDSP3 Implementation on Inclusive Service Delivery for Persons with Disabilities The JP provided technical inputs that strengthened the revised disability law and supported the endorsement of Cambodia’s initial CRPD State Report by the Council of Ministers in late 2025. Through sustained UN advocacy, disability inclusive commitments were integrated into major national frameworks, including the National Social Protection Framework Policy 2024–2035, the Neary Rattanak VI Strategic Plan, and the Disability Inclusive Action Plan. The Ministry of Culture and Fine Arts (MoCFA) also committed to ratifying the Marrakesh Treaty following capacity building activities supported and established the technical working group by the programme. Disability inclusive commitments were integrated into major national frameworks, including the National Social Protection Framework Policy 2024–2035, the Neary Rattanak VI Strategic Plan, and the Disability Inclusive Action Plan of Ministry of Education Youth and Sport (MoEYS). The JP generated concrete, measurable outcomes in expanding participation and inclusion for persons with disabilities. Cash transfer inclusion through the National Social Assistance Fund grew from just over 60,000 persons with disabilities in 2021 to 63,223 by December 2025 for the family package social assistance programme. Each recipient now receives US$7 per month (US$84 annually), amounting to a total government investment of US$5,310,732 in 2025. Disability identification also expanded significantly. The number of persons assessed for disability identification cards increased from 215,358 in 2021 to 355,280 in 2025 including 174,013 women and girls—enabling improved access to health, rehabilitation, education, and social protection services. Employment outcomes showed further impact. The number of persons with disabilities employed in the public and private sectors rose from 3,621 (815 women) in 2021 to 7,502 (1,035 women) in 2025, demonstrating notable progress in inclusive workforce participation. Increased Participation and Inclusion of Rights Holders Enhancing the capacity-building support delivered in 2023, two Organizations of Persons with Disabilities (OPDs) and five Women with Disabilities Forums (WWDFs) successfully implemented their advocacy workplans in partnership with 26 local commune administrations. As a direct result of these strengthened advocacy efforts, 2,000 persons with disabilities—including 1,119 women and girls, gained access to essential public services between 2024 and 2025. These services included disability identification cards, IDPoor cards, and social assistance packages, helping to improve social protection coverage and reduce barriers to inclusion. A key outcome of the programme is the institutionalized participation of persons with disabilities in local decision-making. All 26 commune administrations have now formally included persons with disabilities as members of their CCWC. This marks a significant shift toward inclusive governance, ensuring that the voices, priorities, and lived experiences of persons with disabilities are represented in formal planning and policy discussions at the local level. The programme also enhanced civil society engagement in Cambodia’s fourth cycle of the Universal Periodic Review (UPR). Four representatives from CSOs and OPDs participated in the UPR presession in Geneva, elevating the visibility of disability issues. Their contributions helped ensure that eight UPR recommendations explicitly addressed disability inclusion. These recommendations have been supported by the Government for implementation during the fourth cycle. (See Annex 2. Output indicator results)

Output 2.1B (phase 2):

The digital monitoring and evaluation system is operationalized to efficiently monitor and report on the NDSP3 and other disability-related policy, plans, and guidance.

Brief narrative description on completion of output

Enhanced M&E Capacity Within DAC-SG to Drive NDSP3 Implementation In March 2025, DAC-SG strengthened its Monitoring and Evaluation (M&E) function by expanding the team with new members responsible for data collection, monitoring, analysis, and reporting. This strengthened M&E team now manages and coordinates the digital M&E system for NDSP3. They received four rounds of training from the project on digital system management and data monitoring with line ministries and all Provincial Disability Action Councils (PDACs). As a result of these investments, the team delivered digital M&E training to 184 focal persons (24% women, including 8% persons with disabilities) across 29 line ministries/institutions and 25 PDACs in August and October 2025. DAC-SG also plans to expand NDSP3 and digital M&E dissemination to eight additional national institutions between December 2025 and January 2026, strengthening institutional understanding of NDSP3 and supporting the integration of its 96 indicators into workplans. Once dissemination is complete, DAC-SG will officially launch the digital system and require line ministries and PDACs to submit 2025 annual reports and quarterly reports for 2026 starting March 2026. The digital M&E system significantly enhances NDSP3 implementation at national and subnational levels by improving data quality, transparency, and accountability. It strengthens the capacity of line ministries and PDACs to produce evidence-based results, enabling the RGC to report effectively on national and international commitments, including the CRPD initial State Report and the NDSP3 progress report. The system also informs disability inclusive policy development and revision, ensuring that reforms are grounded in reliable data. Development of an Online Disability Inclusion Learning Platform A digital learning platform on disability inclusion has been developed and integrated into the DAC-SG website. The platform features six modules covering: - The CRPD - Barriers and facilitators to participate - Accessibility - Reasonable accommodation - Meaningful participation - NDSP3 information Upon launch, all DAC-SG staff, Disability Action Working Group members from line ministries, and Provincial/District DACs will be required to complete the modules to obtain certification. Annual refresher courses will be mandated to maintain knowledge and ensure the delivery of inclusive, nondiscriminatory, and stigma-free services. (See Annex 2. Output indicator results)

Output 2.2 (phase 1)

Full participation of OPD in the process of revision of the National Disability Strategic Plan to be aligned with the CRPD and new Disability Law ensured once the Law is approved. (NDSP 2 extension or new NDSP 3- whatever option is chosen by the Government)

Brief narrative description on completion of output

The JP strengthened national accountability and enhanced dialogue and planning for disability inclusion by supporting the DAC‑SG to convene a national reflection workshop on NDSP2 implementation in November 2022, with active participation from a wide range of persons with disabilities. Bringing together 220 participants (83 women and 32 persons with disabilities) from line ministries, PDACs, OPDs, CSOs, and the private sector, the workshop enabled stakeholders to review achievements, identify implementation challenges, and set priorities for NDSP3. With technical guidance from the programme, DAC agreed to engage an international consultant to analyze the workshop findings and develop the NDSP2 achievement report, forming the evidence base for the new strategic plan. The programme also ensured inclusive participation in shaping NDSP3 (2024–2028). A national consultation workshop in June 2024 engaged 30 (14 women) persons with disabilities, including representatives from CDPO, 10 OPDs, and under‑represented groups, whose inputs directly informed the zero draft of the new plan. This draft will be further circulated for feedback before finalization with DAC‑SG, ensuring that NDSP3 reflects the lived experiences and priorities of persons with disabilities. Through these efforts, the JP advanced evidence‑based planning and strengthened meaningful participation in national disability policy development. The NDSP3 will be launched for implementation in phase 2 (2024 to 2205). (See Annex 2. Output indicator results)

Output 3.1 (phase 1):

Disability inclusion is strengthened in planning, implementation and monitoring of UN development activities at the country level including in humanitarian settings.

Brief narrative description on completion of output

The JP strengthened the inclusion of persons with disabilities in national development planning by supporting meaningful participation in the formulation of the UN Sustainable Development Cooperation Framework (UNSDCF) 2024–2028. In May 2022, the UN Resident Coordinator convened 19 persons with diverse disabilities, including 10 women, to share their priorities and vision for the disability sector. Their contributions were formally integrated into the draft UNSDCF, ensuring that the perspectives of persons with disabilities shaped the framework’s strategic direction and priorities. As a direct outcome of this engagement, disability‑inclusive data and indicators were incorporated into Priority 1 of the UNSDCF, specifically under Human Outcome 1 on health, gender‑responsive education, and social protection. This integration ensures that persons with disabilities are explicitly recognized in national monitoring efforts and that progress in these sectors will be tracked with a stronger equity and inclusion lens. Through this process, the Joint Programme advanced both representation and accountability, contributing to a more inclusive UN–government cooperation framework for 2024–2028. (See Annex 2. Output indicator results)

Output 3.2 (phase 1):

Effective implementation of COVID-19 inclusive Recovery Plan through national monitoring system is ensured

Brief narrative description on completion of output

The JP strengthened national monitoring of disability‑inclusive COVID‑19 recovery by integrating key recovery indicators such as vaccination numbers and cash‑transfer recipients into the NDSP2 digital Web Application. This avoided the need for a separate M&E tool and enabled OPDs and stakeholders to report consistently using a unified system. As a result, the Royal Government of Cambodia recorded those 64,709 persons with disabilities received COVID‑19 cash transfers between June 2020 and October 2022. The DAC‑SG M&E team used both digital and manual reports from ministries and PDACs to analyze NDSP2 progress and produce the national recovery plan report. At the community level, the programme strengthened local service coordination and disability inclusion. In 2023, 1,367 persons with disabilities, including 878 women, accessed essential services through six commune councils, including cash transfers, disability identification, IDPoor assessment, education, health, and rehabilitation. Importantly, these commune councils incorporated disability‑inclusive actions into their 2024 Commune Investment Plans, such as accessible infrastructure, support for social assistance enrolment, transportation to health centres, and community disability‑awareness activities. These efforts improved local responsiveness and expanded access to services for persons with disabilities during the post‑pandemic recovery period. (See Annex 2. Output indicator results)

Output 3.3 (phase 1):

Full participation of OPDs in processes of implementation and monitoring of inclusive COVID-19 Recovery Plan is ensured

Brief narrative description on completion of output

The JP strengthened OPDs’ and Women with Disabilities Forums’ capacity to engage in COVID‑19 recovery and disability‑inclusive advocacy. With programme support, CDPO trained six persons with disabilities mostly women, on the COVID‑19 recovery plan and toolkit, resulting in a 100% increase in their knowledge and the development of six advocacy plans for 2023. These OPDs also actively contributed to Provincial DAC meetings, where their inputs on NDSP2 implementation were incorporated into the draft NDSP3, ensuring the strategic plan reflects real challenges faced by persons with disabilities. The programme also broadened inclusive policymaking and digital empowerment. More than 10 OPDs and under‑represented groups provided recommendations for national guidelines on disability inclusion, social protection, TVET, employment, and access to information. Through UNESCO, 30 organizations were equipped with digital, media and information literacy skills, and four training courses including a module for 60 participants, enhanced OPDs’ ability to engage in digital platforms and strengthen their advocacy. Participants expressed strong interest in continued training, highlighting the programme's role in filling a critical gap in digital skills for persons with disabilities. (See Annex 2. Output indicator results)

## 3. Equality between men and women

Please describe how the programme ensured equality between men and women by responding to the questions below.

How did the programme consider differences in the barriers faced by men and women with disabilities?

The JP adopted a gender‑ and disability‑responsive approach, recognizing that men and women with disabilities in Cambodia face both shared and distinct barriers shaped by gender norms, discrimination, and unequal access to resources and decision‑making. At the outset, the Programme acknowledged the multiple, intersecting barriers faced by persons with disabilities overall, including poverty, stigma and discrimination, limited access to services (such as education, health, justice, and information), and inaccessible physical infrastructure. These challenges are further compounded by weak disability mainstreaming across national and sub‑national policies, driven by limited capacities among government officials, OPDs, local authorities, service providers, and the private sector. The programme carefully considered gender differences by partnering with implementing partners committed to both gender equality and disability inclusion, ensuring that the specific needs and challenges of men and women with disabilities were understood and considered in implementation. The Programme also recognized group‑specific barriers affecting persons with psychosocial disabilities, Deaf women and men, including stigma, language deprivation, limited access to Cambodian Sign Language, and a critical shortage of interpreters. These barriers disproportionately affect Deaf women, who often face compounded exclusion due to gender norms and reduced access to education and information. The Programme promoted inclusive consultation processes and awareness‑raising to ensure these perspectives were reflected in policy dialogue and planning.

In what way did the programme advance gender equality?

Within this context, the Programme explicitly addressed gender‑specific barriers, particularly those faced by women with disabilities. Consultations and assessments highlighted that women with disabilities experience heightened vulnerability compared to men, including reduced access to economic opportunities, social protection, leadership roles, and skills development. In response, the Programme prioritized targeted support to five WWDFs, strengthening their institutional, advocacy, and leadership capacities to better address women‑specific issues such as economic empowerment, social protection, and participation in local governance and decision‑making processes. To address structural inequalities affecting both men and women with disabilities, the Programme strengthened the capacity and sustainability of OPDs and WWDFs, which had been weakened by reliance on external funding and declining institutional capacity. By supporting organizational development, advocacy skills, and engagement with local authorities, the Programme enhanced the ability of OPDs and WWDFs to represent diverse gender perspectives and contribute substantively to policy and programme interventions (new disability law, NDSP3, first initial state report on CRPD implementation, commune investment plans), particularly at the local level. The Programme also collaborated with a leading organization promoting gender equality and disability inclusion, to further advance these objectives. Awareness-raising campaigns and training programmes specifically addressed gender-specific barriers. Women with disabilities were featured in videos on both disability-related International Days and other campaigns (e.g. Human Rights Day and 16 Days of Activism against gender-based violence), often highlighting the particular barriers that they face. Specific materials on intersecting and multiple discrimination were also included in the training programme on access to justice and the localized manual on the CRPD in Cambodia. Overall, the JP ensured that gender differences in barriers were systematically identified and addressed by combining disability mainstreaming with targeted support for women with disabilities, thereby promoting more inclusive, equitable, and sustainable outcomes within the disability movement and national policy processes.

How have the specific actions undertaken by the programme contributed directly to the empowerment of women and girls with disabilities? Please include here baseline and end line data on how women with disabilities were included and impacted while implementing the project. Kindly note that in the expenditure section below projects are requested to state the overall funding spent on these activities.

The programme contributed directly to the empowerment of women and girls with disabilities by embedding gender equality across its design, implementation, and monitoring processes, while also delivering targeted actions to strengthen women’s participation, leadership, and access to services. To promote inclusive participation, the programme set a minimum target of 25% women participants, including women with disabilities, across all workshops, meetings, and training activities. Gender‑disaggregated data was systematically collected and analysed, ensuring that women’s participation and outcomes were tracked and used to inform adaptive programming. These platforms enabled women with disabilities to actively voice their perspectives and, in several cases, take on coordination and leadership roles, strengthening their confidence, visibility, and influence in policy and community processes. The programme also focused on strengthening the institutional and advocacy capacity of five WWDFs led by women with disabilities, enabling them to address gender‑specific barriers such as limited access to social protection, health services, and economic opportunities. Between 2024 & 2025, as a direct result of advocacy efforts by five WWDFs, 850 women with disabilities, representing 58% of 1,463 persons with disabilities reached successfully accessed essential public services. These included social protection schemes, healthcare, IDPoor benefits, Disability Identification Cards, and rehabilitation services delivered by 14 local commune administrations. This outcome demonstrates the programme’s tangible contribution to improving women’s access to rights‑based services and reducing structural exclusion at the local level. Beyond service access, the programme amplified the voices and leadership of women with disabilities through public advocacy and awareness‑raising. Women with disabilities were featured as advocates delivering key messages in awareness-raising videos and social media campaigns marking the International Day of Persons with Disabilities, Human Rights Day, and the 16 Days of Activism against Gender‑Based Violence. By positioning women with disabilities as rights holders and change agents, rather than beneficiaries, the programme strengthened their public visibility, challenged stigma, and contributed to shifting social norms. Collectively, these actions ensured that women and girls with disabilities were not only included but meaningfully empowered to influence decisions, access services, and lead advocacy efforts at community and national levels. The programme directly empowered women and girls with disabilities by promoting women-led research, strengthening leadership skills, and creating pathways for women with disabilities, particularly Deaf women, to influence decision-making within the disability movement. To advance women’s leadership in knowledge generation, the programme recruited two Deaf women as researchers to conduct a national situation analysis on the rights of Deaf and hard-of-hearing people in 2024. This not only built their technical research and advocacy skills but also ensured that evidence and policy recommendations were informed by the lived experiences and perspectives of Deaf women themselves, strengthening gender responsive and inclusive policy dialogue. Building on this foundation, the programme implemented a comprehensive Deaf Women’s Leadership Training from April to November 2025, reaching 58 Deaf women from Phnom Penh and Kampong Cham Province. Through 13 structured training modules, participants developed leadership, advocacy, and organizational skills, increased their confidence, and strengthened their ability to engage in community and institutional processes. The training also prepared participants to take on future leadership roles in the establishment and governance of Local Deaf Associations and, ultimately, a National Deaf Association potentially led by Deaf women. The JP has developed the gender equality video awareness, which was talked about by a lady with deafness to highlight how deaf women face both gender-based and disability-based discrimination, limiting their access to education, employment, and participation compared to men. It emphasizes the need for equal rights and opportunities so that women and men can fully participate on an equal basis. “It’s important for a deaf woman to attend training courses so she can learn, engage, and participate fully with others. However, some individuals may hold discriminatory beliefs, wrongly assuming that deaf people lack intelligence. But it does not matter; everyone has equal rights regardless of their hearing ability. I want to advocate for other deaf people and help them understand their rights. In the past, women faced many challenges about their gifts because men had more rights, and women faced difficulty accessing education and often needed permission just to attend school. When it comes to work, men and women may have the same job, but women are often paid less. Women are also pressured to stay home and cook, unable to access education, while men have more opportunities to gain knowledge and receive an education. That is why I want to spread awareness among deaf women so they can understand their rights," said Ms. Chheang Long, a lady staff member of the Deaf Development Programme. These targeted actions contributed directly to the empowerment of women and girls with disabilities by increasing their representation in research and leadership, strengthening their agency and voice, and laying the groundwork for sustainable, women-led Deaf organizations. Collectively, the programme moved beyond participation toward structural empowerment, positioning women with disabilities as leaders, researchers, and drivers of change within Cambodia’s disability movement.

How did women with disabilities and women led OPD groups (informal/formal) participate in the implementation?

Women with disabilities and women-led OPD groups played meaningful roles in implementation by assuming leadership at the local level. Through the WWDFs, five trained women with disabilities led meetings, engaged commune authorities, and monitored disability-inclusive work plans, contributing to improved services for 850 women with disabilities. Their leadership helped ensure that advocacy efforts translated into tangible results for local communities. At the national level, women with disabilities and women-led OPDs contributed directly to policy development. They informed the NDSP3 to ensure the needs of women and girls with disabilities were integrated across strategic objectives, and they actively advocated for Article 53 in the new disability law. Their participation strengthened national frameworks by ensuring that the rights, protection, and opportunities of women and girls with disabilities are clearly recognized and prioritized. Overall, the programme enabled women with disabilities and women‑led OPD groups both formal and informal to participate meaningfully in implementation by strengthening their capacities, positioning them as local advocates and monitors, and ensuring their leadership influenced service delivery, local governance, and national policy frameworks.

## 4. Full and effective participation of persons with disabilities

Please describe how the programme ensured the full and effective participation of persons with disabilities and their representative organizations by responding to the questions below.

How did the programme consider the barriers faced by persons with disabilities for effective participation?

The programme was intentionally designed to address the diverse and intersecting barriers that persons with disabilities face in Cambodia, ensuring their meaningful and equitable participation across all stages of implementation. A rights-based approach guided the programme, focusing on removing socio-economic, structural, and attitudinal barriers such as poverty, stigma, discrimination, limited access to services and information, justice, education and physical inaccessibility. Consultation processes were adapted to be accessible, and local authorities and service providers were engaged to strengthen disability-responsive services. Recognizing communication and language-related barriers for Deaf people, the programme incorporated the use of Cambodian Sign Language interpretation where possible, promoted awareness of Deaf rights, and collaborated with specialized organizations to expand communication accessibility. It also supported national-level advocacy by advising on the inclusion of Deaf rights in the new Disability Law and partnering on campaigns promoting the right to sign language. For persons with psychosocial disabilities, the programme addressed deep-rooted stigma, social isolation, and harmful practices by fostering safe, inclusive consultation spaces, supporting their engagement through OPDs, and raising community awareness. This included targeted grants to strengthen advocacy, rights awareness, and the inclusion of persons with mental and psychosocial disabilities. The programme also considered the gender-specific barriers faced by women with disabilities, who often encounter greater exclusion in economic participation, leadership, and access to services. By providing targeted capacity development to women-led OPDs and WWDFs, the programme ensured that women’s priorities and lived experiences shaped programme planning and decision-making. Finally, acknowledging the institutional and operational limitations of OPDs and WWDFs, the programme invested in strengthening their organizational capacities to promote sustainability and increase their influence in policy development, implementation, and monitoring, particularly at the sub-national level. This approach enabled OPDs to participate effectively while building long-term national ownership.

How were persons with disabilities involved in the programme’s governance as well as in the planning, implementation, monitoring and evaluation phases?

The Joint Programme (JP) ensured the meaningful involvement of persons with disabilities, OPDs, WWDFs and underrepresented organizations throughout all phases of governance, planning, implementation, monitoring, and evaluation. Their participation was intentionally built into every stage of the programme cycle. 1. Involvement in Planning Processes At the planning stage, the JP conducted a comprehensive situation analysis in late 2021 with major involvement from OPDs, WWDFs, CSOs working on disability, and relevant government bodies. This process helped identify the rights, needs, and challenges of persons with disabilities. Their recommendations were directly integrated into the JP proposal, ensuring that programme priorities were informed and shaped by persons with disabilities themselves. 2. Involvement in Governance and Policy Development The programme ensured representation of OPDs and WWDFs within national governance and policy-making mechanisms: - The Cambodian Disabled People’s Organization (CDPO) was appointed a member of several national working groups, enabling meaningful participation in the development of major policy and legal frameworks, including: - the new Disability Law - the National Disability Strategic Plan (NDSP3) - the Marrakesh Treaty - the first Initial State Report on CRPD implementation - CDPO was also involved in CRPD and MIDL trainings alongside the JP team. Their engagement as trainers of trainers strengthened the capacity of OPD networks to continue disability rights education beyond the life of the programme.-rights education beyond the life of the programme. - The programme consistently advocated with government, and facilitated, the consultation and active involvement of OPDs, including through organization of the first annual DAC-OPD dialogue in 2025. These governance roles ensured that persons with disabilities influenced national-level decision-making and legal reforms. 3. Involvement in Programme Implementation The JP partnered with national and underrepresented OPDs to deliver services and advocate for inclusive practices: - CDPO implemented a subgrant project with 1 OPD and 5 WWDFs to strengthen service delivery within 12 local commune administrations. - Underrepresented groups were also supported through subgrants: - Deaf Development Programme (DDP) led by Deaf people - Center for Trauma Care and Research Organization (CTRO) - Transcultural Psychosocial Organization (TPO) These organizations worked directly with Deaf and hard-of-hearing persons and persons with psychosocial disabilities to improve their participation, rights awareness, and access to needed services in their communities. At the subnational level, the JP trained 2 OPDs and 5 WWDFs on key legal documents (COVID Recovery Plan 2021–2024, NDSP3), advocacy toolkits, and institutional development so they could advocate effectively with 26 local commune administrations.-national level, the JP trained -Recovery Plan 2021–2024, NDSP3), advocacy toolkits, and institutional development so they could advocate effectively with OPDs were also regularly involved in all capacity-building activities, as both co-trainers and participants. 4. Involvement in Research, Learning, Monitoring, and Dialogue The JP ensured that persons with disabilities played an active role in shaping evidence and monitoring programme progress: - Three studies were conducted with the direct participation of persons with disabilities, Deaf and hard-of-hearing people, including: - Access to information - Rights of Deaf and hard-of-hearing people - Situation analysis of OPDs Their contributions helped identify challenges, needs, and enablers and provided recommendations for future programming. - OPDs, WWDFs, and CDPO monitored the progress of their recommendations through regular workshops and meetings with national working groups, Provincial DACs, and commune administrations. - On 25 December 2025, 27 persons with disabilities (including 13 women) from OPDs, WWDFs, DDP, and the Blind Association participated in the JP sharing workshop. They actively provided feedback on achievements and proposed recommendations for ongoing and future programming. 5. Involvement in Evaluation At the evaluation stage, the JP ensured that persons with disabilities contributed directly to assessing programme performance: - CDPO, 1 OPD, 3 WWDFs, relevant CSOs, and at least 20 persons with disabilities participated in the terminal evaluation. - They provided feedback on the effectiveness and limitations of the JP and offered recommendations for shaping the next phase of programming. This approach ensured that the voices of persons with disabilities influenced both accountability and future programme design. In conclusion, across planning, governance, implementation, monitoring, and evaluation, the JP ensured that persons with disabilities were not merely consulted but actively engaged as leaders, decision-makers, implementers, and evaluators. Their contributions strengthened the programme’s inclusiveness, enhanced service delivery, and improved accountability at both national and sub-national levels.

How have the specific actions undertaken by the programme contributed directly to the full and effective participation of persons with disabilities?

The programme’s specific actions directly strengthened the full and effective participation of persons with disabilities by embedding their leadership, voices, and decision-making roles across planning, governance, implementation, monitoring, evaluation, and advocacy processes. These actions translated into both increased participation and tangible improvements in access to rights and services. 1. Strengthening Participation in National Planning Processes By facilitating the direct engagement of persons with disabilities in national level consultations, the programme ensured they influenced strategic frameworks. In March 2024, 40 persons with disabilities actively contributed to the final consultation for the NDSP3, shaping priorities and ensuring the national framework reflected their needs and rights. Contribution: This action elevated persons with disabilities from consultation subjects to co architects of national disability policy. 2. Expanding Spaces for National Advocacy and Collective Voice Annual participation of more than 2,000 persons with disabilities in the National and International Day of Persons with Disabilities (2022–2025) created inclusive platforms for networking, visibility, and collective advocacy. Likewise, the participation of over 100 Deaf and hard of hearing persons in the national and international day of Deaf people, every year to promote sign language recognition and the rights of deaf and hard of hearing people in Cambodia. These events amplified their voices in public discourse, strengthened solidarity among OPDs and WWDFs, and increased recognition of disability issues by government and society. 3. Enhancing Representation in Governance Structures The appointment of 23 persons with disabilities to District and Provincial Disability Action Councils (DACs) across multiple provinces created direct representation in local governance. Through these roles, they influenced planning, implementation, monitoring, and evaluation of disability related work plans. Their leadership contributed to 99,103 persons with disabilities, including 35,320 women and girls, receiving services across health, education, employment, and social protection in 2024–2025. Embedding persons with disabilities in governance positions ensured systemic participation and strengthened accountability at sub national levels. 4. Building Capacity for Leadership in Programme Implementation Two OPDs and five WWDFs received targeted capacity building and then led advocacy with 26 local administrations, which facilitated improved inclusive service delivery. As a direct result, 3,681 persons with disabilities (including 2,111 women) accessed health, rehabilitation, education, vocational training, ID cards, IDPoor cards, and social assistance. Empowering OPDs and WWDFs shifted them from beneficiaries to drivers of programme implementation, enabling them to influence systems that directly affect their communities. 5. Strengthening Deaf Leadership and Community Mobilization The Deaf led development programme at Caritas Cambodia supported 365 Deaf and hard of hearing persons to complete 13 DLTP training courses in 2025. These trainings enhanced their leadership skills, rights awareness, and ability to mobilize their communities, positioning them as future leaders of a national Deaf Association. These actions built sustainable Deaf led leadership and advanced self-representation. 6. Supporting Participation in Global Human Rights Mechanisms The programme supported four CSO and OPD representatives to engage in the UPR pre session in Geneva in 2024. Their advocacy contributed directly to the inclusion of eight disability related recommendations in the final UPR outcomes. This elevated persons with disabilities into international policy spaces, strengthening Cambodia’s compliance with CRPD obligations and reinforcing accountability for disability inclusive development. In conclusion, through these integrated actions, the programme transformed participation from passive involvement into active leadership. Persons with disabilities became central actors in shaping policies, influencing governance, delivering services, driving advocacy, and monitoring progress. This approach not only strengthened inclusiveness and improved service delivery but also embedded long term accountability at national and sub national levels, ensuring their full and effective participation in all aspects of the programme.

#### Please use the table below to summarize the details of OPDs the programme has engaged with.

| Type of OPD (Umbrella, regional, national, specific disability type) | Contact details (Email address of contact person of the organization and website where available) | Overall OPD leadership (disaggregated according to sex and type of disability) | OPD representatives engaged in the programme (disaggregated according to sex and type of disability) |
| --- | --- | --- | --- |
| Cambodian Disabled People’s Organization (national) | monika.mak@cdpo.org pm@cdpo.org | CDPO is a leading NGO in Cambodia focused on empowering persons with disabilities through the OPD network. Its roles include advocating for rights, implementing disability programs, promoting inclusion policies, and strengthening 75 local OPDs and WWDFs. | Ms. Monika Mak, Executive Director. Woman with a physical disability Mr. Bonnaroath Chhor, Programme Manager, Man with a physical disability Provided subgrant |
| Organization of Persons with Disabilities, Ratanakiri Province | +855-97-4992198 (Tel and Telegram) | Ratanakiri OPD is an OPD that represents persons with disabilities, including indigenous persons with disabilities, in Ratanakiri Province. Its core roles include advocating for their rights, implementing disability‑related activities, and promoting inclusive service provision for persons with disabilities across the province. | Ms. Kers Davy, Executive Director, Woman with a physical disability Provided subgrant through CDPO |
| Organization of Persons with Disabilities, Samrong Torng District | +855-12 435 150 (Tel and Telegram) | Samrong Torng District, Kampong Speu Province, is an OPD that represents persons with disabilities, including indigenous persons with disabilities, in Samrong Torng District, Kampong Speu Province. Its core roles include advocating for their rights, implementing disability‑related activities, and promoting inclusive service provision for persons with disabilities across the Samrong Torng District, Kampong Speu Province. | Mr. Sam Eng Sum, Executive Director, Man with a visual disability Provided subgrant through CDPO |

## 5. Ensuring the inclusion of marginalized and underrepresented groups of persons with disabilities

Please describe how the project ensured inclusion of marginalized and underrepresented groups of persons with disabilities by responding to the questions below.

How did the programme consider and identify marginalized and underrepresented groups of persons with disabilities? for example by considering type of disability, gender, age, location, minority status or other contextually appropriate demographic factors.

The situation analysis reveals that individuals who are Deaf, blind, or who have intellectual or psychosocial disabilities are among the most vulnerable groups and require additional support to access services, obtain information, seek justice, and meaningfully participate in representing their voices and interests. Persons who are Deaf face particularly significant barriers to full inclusion. The analysis identified pervasive gaps in public awareness regarding the rights and needs of Deaf individuals, which contribute to ongoing stigma, discrimination, and social exclusion. A critical challenge is language deprivation, often resulting from inadequate early intervention for Deaf children and their families. This leads to limited exposure to Cambodian Sign Language (CSL) and is compounded by a severe shortage of qualified interpreters across the country. JP research further indicates that persons with severe disabilities, especially women, girls, and indigenous people, encounter substantial barriers in accessing information. These challenges stem from the absence of disability‑specific legislation, limited availability of accessible communication tools such as Braille and sign language outside urban areas, and deeply rooted socio‑cultural stigma. Additional obstacles include a lack of tailored information on health and rights, low digital literacy in rural communities, and physical, communication, and attitudinal barriers that contribute to social isolation.

In what way did the programme advance equity regarding rights and needs of most marginalized groups?

The programme advanced equity by intentionally prioritizing the rights and needs of the most marginalized groups of persons with disabilities and ensuring their full, meaningful, and dignified participation throughout programme implementation. Working in close collaboration with OPDs, CDPO, and DAC-SG, the programme actively reached underrepresented groups including persons with hearing, visual, intellectual and psychosocial disabilities, as well as their families and personal assistants and indigenous people with disabilities who often face the greatest barriers to participation. To remove these barriers, the programme provided a wide range of reasonable accommodation. This included sign language interpretation and live captioning services for Deaf communities, accessible digital documents compatible with screen readers for blind participants, and financial support for personal assistants assisting persons with intellectual and psychosocial disabilities, as well as children with disabilities. These accommodations ensured that individuals who are typically excluded from consultations, training, and meetings were able to participate actively, safely, and confidently. Through these deliberate measures, the programme not only increased participation but also strengthened the representation and influence of most marginalized groups. Their voices, concerns, and priorities were consistently heard and incorporated into programme discussions and decision-making processes. Importantly, their contributions directly shaped key national documents such as the new disability law and the NDSP3, with several of their recommendations reflected in the final versions. By centering those who are most often left behind, the programme advanced equity by ensuring that marginalized groups and underrepresented organizations were not only present, but fully empowered to contribute, influence policy development, and claim their rights on equal footing with others.

How have the specific actions undertaken by the programme contributed directly to the inclusion of marginalized and underrepresented groups of persons with disabilities?

The programme contributed directly to the inclusion of marginalized and underrepresented groups of persons with disabilities by implementing targeted actions that addressed their specific information, accessibility, participation, and representation needs. To begin with, the programme strengthened access to information, one of the most significant barriers for marginalized groups, by issuing a policy brief on the Information Needs Assessment for Persons with Disabilities in Cambodia. This helped identify the distinct challenges faced by underrepresented disability groups in obtaining timely, accessible, and relevant information. In parallel, the programme conducted a comprehensive Situation Analysis on the Rights of Deaf and Hard-of-hearing People in Cambodia, led by a Deaf researcher and two deaf research assistants. This study highlighted systemic gaps in access to services, social participation, and advocacy, while also identifying opportunities to advance equity for the Deaf community. These evidence-driven analyses laid the groundwork for targeted interventions. The programme’s findings emphasized the urgent need to strengthen Cambodian Sign Language (CSL), improve access to education and healthcare, expand employment opportunities, and ensure that justice and public services are accessible. The study also underscored the importance of establishing a National Deaf Association, an essential step towards enabling Deaf Cambodians to exercise their rights and participate meaningfully in national development. The programme also developed specialized training and materials for justice actors to improve their understanding of the unique barriers faced by persons with intellectual and psychosocial disabilities and discussing the issues of legal capacity and supported decision-making in relation to Cambodian law. By raising these issues, these capacity-building activities contributed directly to ensuring greater awareness and more equitable access to justice for these highly marginalized groups.-building activities contributed directly to ensuring more The programme provided subgrant to the Deaf Development Programme of Caritas Cambodia, Transcultural Psychosocial Organization, and the Center for Trauma Care and Research Organization as key partners to empower them supporting targeted interventions for Deaf people and persons with psychosocial disabilities. This partnership approach ensures sustained support and increased participation from groups that are often excluded from mainstream disability initiatives. As a result, 365 deaf and hard of hearing persons (including 57 women and 60 youth) completed 13 training programmes that equip them to become the leaders of the Deaf Association in Cambodia in the future. Support was provided to 133 persons with psychosocial disabilities (including 52 women), and 28 awareness-raising sessions on mental health and stigma reduction were conducted with 134 family members of persons with psychosocial disabilities. In addition, 193 persons with disabilities directly received capacity-building and training on mental health and psychosocial disabilities, a group of 5 persons came together to set up a group for persons with psychosocial disabilities, and talk shows on psychosocial disabilities received 3,100 views on social media. To further promote inclusion, the programme produced public facing advocacy materials featuring the lived experiences of Deaf individuals. A case story titled “Open Up the World for Deaf People in Cambodia” highlighted the transformative impact of access to sign language, strong community networks, and collaboration with local authorities. Additionally, six videos on the rights of women with disabilities and the importance of sign language were developed and broadcast through social media in collaboration with the DAC‑SG and OPDs. Shared particularly during the International Week of Deaf People and the International Day of Sign Languages, these videos amplified the voices of Deaf women and youth and helped raise public awareness on the importance of inclusion. Together, these actions created concrete pathways for underrepresented and marginalized disability groups, particularly persons with hearing, visual, intellectual and psychosocial disabilities, to gain visibility, access their rights, strengthen leadership capacity, and participate more fully in society. Through research, advocacy, partnerships, accessible communication, and capacity building, the programme ensured that their voices shaped both policy and practice, advancing meaningful and sustained inclusion.

How did marginalized and vulnerable persons with disabilities and these groups led by marginalized and vulnerable persons with disabilities (informal/formal) participate in the implementation?

The programme ensured that marginalized and vulnerable persons with disabilities and the groups led by them, played an active and influential role in programme implementation through targeted support, empowerment initiatives, and the creation of direct engagement opportunities in decision-making spaces. 1. Participation and Leadership of Deaf Communities Because Cambodia does not yet have a national Deaf association, the programme strategically provided subgrants to Maryknoll Cambodia and Caritas Cambodia, two organizations with established Deaf development programmes, to engage Deaf and hard-of-hearing persons meaningfully in programme activities. Through this support, the programme helped establish five Deaf groups in Kampong Cham and Tbong Khmum provinces in 2023. Representatives from these groups, including a Deaf woman leader, participated in quarterly meetings of the Kampong Cham Provincial Disability Action Committee (DAC) throughout 2024 and 2025. During these meetings, the Deaf representative advocated specific actions related to Deaf rights and inclusion, ensured that the concerns of Deaf communities were documented, and successfully influenced the DAC’s annual work plan. As a result of 2025, 365 Deaf and hard-of-hearing persons (including 57 women and 60 youth) participated in 13 training programmes that enhanced their leadership, advocacy, and community-engagement capacities. These individuals are now positioned as emerging leaders who can eventually form and lead a future national Deaf Association. 2. Participation of Persons with Visual Disabilities and Advocacy for Accessible Information The programme also facilitated engagement for persons with visual disabilities by ensuring their presence in national dialogues. Representatives from a blind association and at least 20 persons with visual disabilities took part in consultation workshops on the ratification of the Marrakesh Treaty, organized by the Ministry of Culture and Fine Arts (MoCFA) between 2023 and 2025. They raised critical concerns regarding access to printed materials and the broader information needs of blind persons. As a direct result of their advocacy, MoCFA established a technical working group in early 2025 that includes at least two persons with visual disabilities (informal), and the Ministry committed to ratifying the Marrakesh Treaty by 2026. 3. Participation of Indigenous People with Disabilities To promote inclusion among Indigenous communities, the programme supported the Ratanakiri OPD, led by an Executive Director and members who are themselves Indigenous persons with disabilities. Through the programme’s support, this OPD engaged with the Ratanakiri Provincial DAC and two commune administrations to advocate for accessible public services. These efforts led to improved access to education, social protection, vocational training, and employment services for 90 Indigenous persons with disabilities, including 32 women and girls. 4. Participation of Persons with Psychosocial Disabilities To support reintegration and inclusion of persons with psychosocial disabilities, the programme provided subgrants to two NGOs: Transcultural Psychosocial Organization (TPO) and Center for Trauma Care and Research Organization (CTRO) specializing in mental health and psychosocial support. These NGOs conducted interventions providing support to 133 persons with psychosocial disabilities (including 52 women) and raising awareness with 134 family members of persons with psychosocial disabilities. In addition, 193 persons with disabilities directly received capacity-building and training on mental health and psychosocial disabilities, a group of 5 persons came together to set up a group for persons with psychosocial disabilities and talk shows on psychosocial disabilities received 3,100 views on social media. Through these interventions, persons with psychosocial disabilities, often among the most marginalized, were able to participate more fully in programme activities and in their communities. 5. Participation of Persons with Intellectual and Psychosocial Disabilities and Their Families In response to earlier concerns raised by families and informal networks, the programme ensured that persons with intellectual and psychosocial disabilities and their caregivers were invited to all key programme activities. Reasonable accommodation, including caregiver support and accessible facilitation, was provided to ensure they could participate meaningfully. Their feedback, concerns, and lived experiences were consistently incorporated throughout the implementation period, ensuring that the programme remained responsive to their unique needs. In conclusion, through targeted subgrants, empowerment of disability-led groups, facilitation of participation in governance structures, and provision of reasonable accommodations, the programme ensured that marginalized and vulnerable persons with disabilities were not just participants, but active contributors, advocates, and emerging leaders. Their involvement directly shaped programme implementation influenced local and national decision-making processes and strengthened the overall inclusiveness and effectiveness of the programme.

Please use the table below to list the type of marginalized and underrepresented groups of persons with disabilities who were included so far in programme implementation.

| Type of Marginalized or Underrepresented group | Organization contact details (email address of Organization contact where available) |
| --- | --- |
| Women and Children with Disabilities Forum Organization, Kampong Cham | Ms. Vannet Khun, Executive Director Woman with a physical disability Tel/Telegram: Tel: +855-96-6462 257 Bateay District, Kampong Cham Province Received subgrant through CDPO |
| Women with Children Disabilities Forum in Takeo (local province) | Ms. Vivathana Vorn, Executive Director Woman with a physical disability Tel/Telegram: +855-96-2221316 Takeo Town, Takeo Province Received subgrant through CDPO |
| Women with Children Disabilities Forum Organization, Kampot Province | Ms. Chenda Yun, Executive Director Woman with a physical disability Tel/Telegram: +855-12-939803 Received subgrant through CDPO |
| Women with Children Disabilities Forum Organization, Battambang Province | Ms. Sok Chan Sieng, Executive Director Woman with a physical disability Tel/Telegram: +855 17 480 784 Received subgrant through CDPO |
| Women with Children Disabilities Forum Organization, Svay Rieng Province | Ms. Malis Moch, Executive Director Woman with a physical disability Tel/Telegram: +855 88 228 8332 Provided subgrant through CDPO |
| Deaf Development Programme | Mr. Vanna Nem, Staff of Deaf Development Programme, a deaf person, Email: vannanem579@gmail.com, Tel: +855-97-615 9606 Received subgrant through Marryknoll Cambodia and Caritas Cambodia |
| Former board members of the Association of Blind in Cambodia | Mr. Kimleap Mang, Former board members of the Association of Blind, a blind person, Tel/Telegram: +855-76- 888 8880 Active Participation in consultation meetings and workshops of the programme |
| President of the Parent Association for Children Intellectual Disabled (PACHID | Ms. Simon Svay, President of the Parent Association for Children Intellectual Disabled (PACHID), a caregiver of child with intellectual disability, Tel: +855-12-526 322 Active Participation in consultation meetings and workshops of the programme |

## 6. Partnership-Building

Please provide a narrative on how the programme has contributed to greater UN inter-agency collaboration to advance the rights of persons with disabilities in the country.

The joint programme contributed significantly to strengthening UN inter-agency collaboration on advancing the rights of persons with disabilities in Cambodia. Through its engagement with the UN Country Team (UNCT) under Output 1.2, the programme enhanced the UN system’s capacity to support the government in implementing disability-inclusive and SDG-aligned processes. By developing inclusive tools, facilitating dialogue among UN entities, and promoting the participation of OPDs in coordination spaces—particularly during Phase 1, the programme helped embed disability inclusion more firmly within UNCT planning, policy discussions, and joint messaging. A key outcome was the enhanced disability inclusion leadership within the UNCT Human Rights Group. The joint programme supported the development of Cambodia’s first UN Disability Inclusion Strategy (UNDIS) Action Plan and delivered training for 30 disability focal points across agencies. As a result, UN staff demonstrated improved understanding of disability inclusion, and new channels for engagement with OPDs were established, strengthening accountability and visibility of disability issues within the UN’s collective work. These efforts laid the groundwork for a more systematic UN approach to UNDIS implementation and contributed to ongoing UNCT actions to improve performance on the UNDIS Scorecard. The programme also contributed to broader UN system coherence by catalysing disability inclusion across multiple sectoral policies and national frameworks. As a result of improved coordination and technical guidance: - UNAIDS supported the Ministry of Health to integrate disability inclusion into the GEDSI Integrated HIV Response National Action Plan (2025–2028) . - UNDP assisted the Ministry of Environment to incorporate disability inclusion in Cambodia’s Third Nationally Determined Contribution (NDC 3.0) . - UNICEF supported the Ministry of Education, Youth and Sport to integrate disability inclusion into the Inclusive Education Work Plan (2024–2028) . - UNDP and UNICEF worked with the National Social Protection Council to ensure persons with disabilities are included in social assistance measures under the National Social Protection Policy Framework (2024–2035) . - OHCHR provided inputs to the Ministry of Women’s Affairs about the inclusion of persons with disabilities in the fourth national action plan to prevent violence against women (2024-2030). - WHO partnered with the Ministry of Health to develop a comprehensive Health Equity Strategy and action plan for persons with disabilities. These cross-agency contributions demonstrate a clear shift toward a more coherent and unified UN approach to disability inclusion in Cambodia, an outcome directly strengthened by the joint programme’s coordination, technical support, and engagement with government and OPDs. While opportunities remain to deepen coordination, the programme has already helped ensure that disability inclusion is systematically embedded across major national policies and UN sectoral initiatives.

Please describe the different stakeholders (for example Government departments, UN entities, OPDs and Civil Society) involved and how they worked together.

Stakeholder Collaboration and Resulting Impact The JP brought together key stakeholders including government ministries, UN entities, OPDs, and civil society organizations (CSOs), to jointly advance disability inclusion in Cambodia. By creating structured platforms for dialogue and shared decision-making, the JP strengthened cooperation between rights-holders and duty-bearers, resulting in tangible policy and systems-level outcomes. Government Leadership and Interministerial Coordination Through JP-supported consultations, workshops, and policy dialogues, government bodies such as the DAC, MoSVY and MoH, MoCFA, worked alongside UN agencies and OPDs to develop and refine key national policies. These collaborative platforms enabled inclusive contributions to major policy instruments such as the new disability law, NDSP3, the COVID19 Recovery Plan, the Marrakesh Treaty process, and the first CRPD State Report. From 2021 to 2025, DAC in collaboration with the JP convened all stakeholder groups annually to develop unified key messages for national and international disability days. These collective messages were elevated to national leadership and consistently reflected in the Prime Minister’s official statements, demonstrating increased high-level political commitment to disability inclusion. UN Entities’ Technical Support and Policy Alignment UN agencies actively contributed their expertise through the JP’s coordination mechanisms. This resulted in strengthened integration of disability inclusion across government sectoral plans such as HIV response (UNAIDS), environmental policy (UNDP), inclusive education (UNICEF), social protection (UNDP/UNICEF), and health equity (WHO). The JP played a catalytic role in ensuring that disability inclusion became a shared UNCT priority and was consistently reflected in national frameworks. OPD and CSO Engagement Leading to Concrete Service Improvements The JP facilitated regular dialogue between OPDs, CSOs, and government representatives, enabling OPDs to raise practical challenges faced by persons with disabilities at the community level. One key issue raised concerned barriers to accessing the IDPoor system and social assistance programmes. In response, DAC and MoSVY brought these concerns to the National Social Assistance Fund (NSAF), leading to improved disability data inclusion. As a direct outcome of this coordinated advocacy, by 2025 a total of 63,223 persons with disabilities were included in NSAF beneficiary data and gained access to the family social assistance package. Strengthening Representation in Government Coordination Structures The JP also ensured that persons with disabilities gained meaningful representation within formal government coordination bodies. As a result, at least 18 persons with disabilities now serve as members of 18 District Disability Action Councils, and at least 5 OPD/CSO representatives hold positions in the national-level DAC. This has strengthened accountability, enabled direct participation in policy discussions, and improved the responsiveness of government structures to disability issues. The JP has also facilitated the first annual OPD-DAC dialogue and provided advice on the new draft Disability Law that calls for formal mechanisms of OPD consultation and active participation.

## 7. Creation of knowledge products

How has the programme contributed to generating new knowledge on how best to promote the rights of persons with disabilities to support national level policy and system changes?

Throughout its implementation, the Joint Programme (JP) played a critical role in generating new knowledge, evidence, and analytical insights that informed policy development and system strengthening for disability inclusion in Cambodia. By conducting targeted research and producing evidence based recommendations, the JP equipped government institutions, OPDs, and UN entities with the information needed to design more inclusive policies and improve services for persons with disabilities.-based recommendations, the JP equipped government institutions, OPDs, and UN entities with the information needed to design more inclusive policies and improve services for persons with disabilities. Foundational Situation Analysis (2021) At the outset, the JP conducted a comprehensive situation analysis on the rights of persons with disabilities. This study identified urgent gaps, systemic barriers, and priority solutions that directly informed JP’s programme design and implementation. The analysis provided a strong evidence base for determining intervention areas and ensuring that programme activities were grounded in the lived realities of persons with disabilities. Evidence for Disability Inclusive COVID19 Response (2021–2023) In response to the pandemic’s disproportionate impact on persons with disabilities, the JP developed the COVID19 Recovery Plan 2021–2023 to complement the National Disability Strategic Plan II (NDSP2). This plan was evidence based and introduced new knowledge on how to ensure disability inclusive access to vaccination, prevention services, PPE, and social assistance. The findings contributed to improved preparedness and service adaptation during the pandemic, helping government partners understand and act on the unique risks and needs faced by persons with disabilities. Review of NDSP2 to Inform NDSP3 (2023–2024) To support the development of the new NDSP3, the JP conducted an in-depth review of NDSP2 in 2023. The analysis identified success factors, gaps, and actionable recommendations that were used by national authorities in drafting and finalizing NDSP3 (2024–2028). This ensured that the new national strategy is more responsive, evidence-driven, and aligned with CRPD principles. Research on Access to Information for Persons with Disabilities (2024) The JP produced a dedicated study, Access to Information for Persons with Disabilities in Cambodia: Challenges and the Way Forward, which shed light on systemic communication barriers. The findings supported the development of Disability Inclusive Media Literacy (DIML) training materials for both persons with disabilities and government officials, strengthening institutional capacity to provide accessible information and enhancing persons with disabilities’ ability to engage with public communication systems. Practical Manual on Disability Equality in Media The programme also localized UNESCO’s Practical Manual on Disability Equality in Media and developed a training guidebook on digital, media, and information literacy for persons with disabilities. These resources promote inclusive, relevant, and accessible media coverage, support content production, and raise public awareness to advance inclusive service delivery. Situation Analysis on Deaf and Hard-of-Hearing Persons (2024) The JP conducted targeted research on the challenges faced by deaf and hard-of-hearing people in Cambodia. This analysis generated new insights on communication access, service gaps, and institutional barriers. It also provided a roadmap for strengthening deaf associations and networks, enabling them to advocate more effectively for their rights and recognition. OPD Situation Analysis (2024) to Inform Legal and Treaty Processes In 2024, the JP carried out a nationwide situation assessment of OPDs. The findings directly informed the final drafting of the new disability law and provided evidence to support Cambodia’s preparations for accession to the Marrakesh Treaty. The research strengthened understanding of OPD capacities, challenges, and needs, and it ensured that OPD perspectives were embedded in national legal reforms and international commitments. White Paper on the Legal Recognition of Sign Language (2025) The JP produced a White Paper on the Legal Recognition of Sign Language for DAC, providing an overview of practices from different countries and recommending proposed draft articles in the new draft Disability Law. Training manual and facilitator’s guide on the CRPD in Cambodia (2025) The JP developed a localized CRPD manual and a facilitator’s guide for DAC, which provides a useful training tool on the Convention that incorporates the Cambodian context, including relevant examples and the roles and responsibilities of subnational authorities. By serving as a practical reference tailored to the Cambodian context, the manual and the facilitator’s guide strengthen DAC officials’ capacity to sustainably continue delivering CRPD-based training.

Please also describe in this section any unique expertise and products developed by the programme that could be used to support other countries within a south-south cooperation framework

The JP’s research products and technical tools serve as valuable resources that can support disability-inclusive development in other countries through South–South cooperation. Key products include: - Access to Information research and Disability-Inclusive Media Literacy (DIML) materials, which provide a practical model for strengthening accessible communication systems and building the capacity of government officials and persons with disabilities. - Guidance and analytical frameworks used in the NDSP2 Review, which offer replicable methodologies for evaluating national disability strategies in line with CRPD principles. The resulting NDSP3 document also serves as a learning resource that other countries can draw from as an example of evidence-based, inclusive strategy development. - Situation analysis of deaf and hard-of-hearing persons, which presents a roadmap for strengthening deaf associations and can be adapted by other countries seeking to improve inclusive communication and sign language development. - OPD Situation Assessment Tool (2024), which maps OPD capacities, challenges, and needs, providing a transferable methodology for countries aiming to strengthen OPD participation in policy processes. - Cambodia’s Initial State Report on CRPD implementation, which offers lessons learned for new CRPD States Parties—particularly on managing lengthy reporting delays and improving coordination mechanisms. In addition to research, the JP developed inclusive consultation and coordination models that enabled meaningful engagement among OPDs, government ministries, and UN entities. These models used during the drafting of the new disability law, the development of NDSP3, and preparation of the national CRPD report illustrate a practical approach to participatory governance that can be adapted to other country contexts. The JP also strengthened mechanisms for integrating persons with disabilities into government coordination structures, successfully placing 18 persons with disabilities in district-level Disability Action Councils and 5 OPD/CSO representatives in the national DAC. This participatory model demonstrates an effective approach that other countries can replicate to institutionalize disability representation in public decision-making processes.

#### Please list type of knowledge products the programme has developed using the table below .

| Name of product and type of product (report, guidelines, assessments etc) | Purpose Describe what was the purpose of the product | Process Describe who participated in the development of product (OPDs, NGOs, Academia etc.) and the different stages of development | Link /attachment | Accessible formats | Validation Has the product been validated by national actors. If yes by whom? |
| --- | --- | --- | --- | --- | --- |
| Policy Brief: CLOSING THE INFORMATION DIVIDE: Addressing the Information Needs for Persons with Disabilities in Cambodia | To highlight key findings and put forward evidence-based policy recommendations for policy-makers to further enhance access to information for persons with disabilities | The policy brief was developed based on the Information needs assessment for persons with disabilities in Cambodia which had gone through a rigorous data collection process with relevant stakeholders | https://cdri.org.kh/storage/pdf/PB2024E-1%20info%20needs%20for%20Disabilities_1724212504.pdf | No | The validation was conducted with 60 experts and representatives from Organizations of Persons with Disabilities, the Government, Civil Society, Media and Academia: https://www.unesco.org/en/articles/cambodia-breaking-down-barriers-facilitate-access-information-persons-disabilities |
| Research report: Situation analysis on the rights of deaf and hard of hearing people in Cambodia | To assess the challenges and facilitators of deaf and hard of hearing people and provide the roadmap for future deaf association in Cambodia | More than 50 deaf and hard of hearing people and 20 persons with disabilities and participants from OPDs, CSOs, government departments, UN entities, donors participated the study. | https://drive.google.com/file/d/1Uf6Y_jXQQrCwNuEGxw9mG1TobQ3S5CMR/view?usp=drive_link | https://drive.google.com/file/d/1Uf6Y_jXQQrCwNuEGxw9mG1TobQ3S5CMR/view?usp=drive_link | No |
| Research report: Situation analysis on OPDs in Cambodia | To assess the challenges and facilitators of OPDs and provide the roadmap for strengthening its institution | More than 60 persons with disabilities and participants from OPDs, CSOs, government departments, UN entities, donors participated the study. | https://drive.google.com/file/d/1oujMCXvgVBoQ416HAeHtvR2jn_2uqQQ0/view?usp=drive_link | https://drive.google.com/file/d/1oujMCXvgVBoQ416HAeHtvR2jn_2uqQQ0/view?usp=drive_link | No |
| State party report: Initial report submitted by Cambodia under article 35 of the Convention, due in 2015 | To respond to the obligation as the state party on the CRPD (ratified in 2012) | All relevant stakeholders including government departments, UN entities, OPDs, WWDFs, CSOs, private sectors and disability experts, attended the consultation to develop the report. | https://tbinternet.ohchr.org/_layouts/15/treatybodyexternal/Download.aspx?symbolno=CRPD%2FC%2FKHM%2F1&Lang=en | https://tbinternet.ohchr.org/_layouts/15/treatybodyexternal/Download.aspx?symbolno=CRPD%2FC%2FKHM%2F1&Lang=en | Endorsed by the Council of Minister of Cambodian Government in Khmer version in October 2025, submitted by Cambodia to the United Nations on 21 January 2026. |
| Digital M&E System on NDSP3 | To monitor and track the progress of the NDSP3 Implementation | All government coordination bodies including DAWGs, PDACs and OPDs attended consultation meetings and workshops to develop this system. | https://ndsp.gov.kh | No | It has not officially launched yet by the RGC. |
| Online learning platform on Disability Inclusion | This online learning platform enables the DAC‑SG, DAWGs, PDACs, and OPDs to access disability‑inclusion training remotely. It reduces the time and costs associated with organizing in‑person training sessions and provides an easy‑to‑manage system for the DAC‑SG to oversee and deliver ongoing capacity‑building. | All government coordination bodies including DAWGs, PDACs and OPDs attended consultation meetings and workshops to develop this system. | https://fresjob.com/elearning/ | No | It has not officially launched yet by the RGC. |
| Report on National situational analysis and assessment of the impact of the COVID-19 crisis on the rights and wellbeing of persons with disabilities and their access to services and supports | - To provide a high-level analysis of the legislative and policy context regarding disability, budget allocation, use of data and mainstreaming of disability across critical sectoral areas in Cambodia. - To engage relevant stakeholders, including OPDs, to gain a high-level understanding of critical issues, policies, gaps and opportunities and build a base of mutual understanding to bring into future co-design of programs for persons with disabilities, or programs that are inclusive of persons with disabilities. - To understand the impact of the COVID-19 pandemic on the rights and wellbeing of persons with disabilities in Cambodia and their access to services and supports. - To provide an evidence-based disability rights perspective to support COVID-19 recovery planning, both during and after the pandemic. | All relevant stakeholders including government departments, UN entities, OPDs, WWDFs, CSOs, private sectors and disability experts attended the consultation to develop the situation analysis | https://drive.google.com/file/d/1oujMCXvgVBoQ416HAeHtvR2jn_2uqQQ0/view?usp=drive_link | No | No |
| Advocacy toolkit and checklist on COVID-19 Recovery Plan | To be a basic guide to support the advocacy efforts of CDPO and other OPDs to plan its own advocacy, to suit the purpose, context, and needs of persons with disabilities in your target area. | All relevant stakeholders including government departments, UN entities, OPDs, WWDFs, CSOs, private sectors and disability experts attended the consultation to develop the situation analysis | https://drive.google.com/file/d/177Mpk0FbJVf1Qj3iqwXQipLYE5NMM443/view?usp=drive_link | No | No |
| Report of the Programme Evaluation | To evaluate the results of the JP by UNDP, OHCHR and UNESCO, towards the expected outcomes and outputs. | All relevant stakeholders including government departments, UN entities, OPDs, WWDFs, CSOs, donors, private sectors and disability experts attended the consultation to evaluate the JP | Still in draft document | No | No |
| Good practice document on Kampong Cham PDAC | To document the good practice and share with government coordination body and OPDs | Three Provincial DACs, 3 OPDs, 2 WWDFs and 10 members of the Kampong Cham, Kampong Speu and Tbong Khmum attended the consultation meetings to develop this good practice document | https://drive.google.com/file/d/1bu9qk7TILV9RfShaUY0Tg3cz0JarySCC/view?usp=drive_link | No | No |
| UNESCO's Practical Manual on Disability Equality in the Media | To promote inclusive, accessible content and, as of March 2025, is training media professionals on its application | This initiative, part of the UN Joint Project "Accelerating Disability Rights in Cambodia," focuses on ensuring ethical representation, accessibility (captions, audio descriptions), and inclusive hiring. | https://core.unesco.org/en/project/261CMB5000#:~:text=Building%20on%20the%20successful%20completion,from%20the%20UNPRPD%20Disability%20Fund https://unesdoc.unesco.org/ark:/48223/pf0000391032 | No | No |

## 8. Communications materials

Branding: Were there any visual assets developed? (For example, banners, notebooks, social media cards).

The JP produced a total of eight videos promoting the rights of persons with disabilities. Five videos (including one synopsis video) were co-produced with DAC and released in late 2023 to raise awareness of the experiences of four persons with disabilities as members of diverse Cambodian society; they have been featured by DAC on social media and at awareness-raising events for different International Days. Three videos were co-produced with DAC and DDP on the occasion of the International Day of Sign Languages in 2025 and raise awareness about deaf rights and the right to sign language. The JP also regularly published social media posts on various International Days to raise awareness and share advocacy messages related to the rights of persons with disabilities. The programme printed T‑shirts for participants—including persons with disabilities, children, women, men, and older persons—who attended the National and International Day of Persons with Disabilities on 3 December each year from 2022 to 2025. These events were presided over by senior government officials. For example, in 2024, H.E. Vongsey Vissoth, Deputy Prime Minister and Minister of the Council of Ministers, officiated the event and launched the NDSP3. In 2025, H.E. Savoeun Neth presided over the celebration to reinforce the implementation of the NDSP3. Information from these events was widely shared through the Facebook pages of relevant government institutions, OPDs, CSOs, and private sector partners, utilizing one of Cambodia’s most popular platforms for public communication. The JP also produced NDSP3 booklets for the DAC-SG to distribute to participants attending NDSP3 awareness-raising sessions across the 25 PDACs and 24 DAWGs in line ministries in 2025. Although the NDSP3 documents (in both Khmer and English) are available on the DAC-SG website, in the Cambodian context many stakeholders, particularly government officials, still prefer printed materials that they can keep in their offices for regular reading and reference.

Dissemination: What tools work best for communication and dissemination, and what don´t? (For example, dissemination across social media platforms, which platforms have worked best from your experience and why do you think that is the case) Have you collaborated with any ‘influencers’ or organizations in the country for cross-promotion of the project, civil society or partner organizations? If yes, could you share their handles? Is there a dedicated webpage section or Flickr album.

In Cambodia, Facebook remains the most widely used social media platform for accessing and searching for information. Short videos (under three minutes) have proven particularly effective, as they include accessible features such as captions, audio, and sign language interpretation. These accessibility elements make the content easy to understand and useful for diverse audiences in both urban and rural areas. For example, NDSP3 launching ceremony was popularly posted by the UN Entity and the government bodies .

Media: Has there been any media coverage? If yes, what were the main obstacles when liaising with the media? Has there been any media request for interviews?

Various International Days organized by the government (MOSVY and DAC) have received media coverage. In addition, the Khmer Times featured the topic of the rights of persons with disabilities in its “Cross Talk Show” on the occasion of the International Day of Persons with Disabilities in 2025.

#### Please also list the type of communications material using the table below.

| Name of Product | Type of Product (toolkit, Video, Poster, etc.) | Purpose | Dissemination | Links/ Attachments | Language | Accessible formats |
| --- | --- | --- | --- | --- | --- | --- |
| Open Up the World for Deaf People in Cambodia | Case study | Promote the deaf community | UNDP Website | As footnote | English | As footnote below |
| One Woman’s Mission to Change the Lives of Persons with Disabilities in Cambodia | Human Story | Promote the leadership of women with disabilities and share key empowerment lessons learned. | UNDP Website | https://www.undp.org/cambodia/stories/one-womans-mission-change-lives-persons-disabilities-cambodia | English | No |
| NDSP3 Educational Awareness Video | Video | Build knowledge on NDSP3 | DAC-SG Facebook | https://www.facebook.com/share/v/1B7U3fGaYQ/ | Khmer | With sign language interpreter, audio and subtitles. https://www.facebook.com/share/v/1B7U3fGaYQ/ |
| “My Rights, My Life” video campaign | Video | Raise awareness of the rights and experiences of persons with disabilities | OHCHR Cambodia facebook, DAC-SG facebook and events | https://www.youtube.com/@UNCOHCHR/videos https://www.youtube.com/@UNCOHCHR/videos | English and Khmer | With captions and sign language interpretation |
| Two videos featuring deaf women in the “More Women Leaders = Better Future” video campaign | Video | Promote the empowerment of women with disabilities, particularly deaf women | OHCHR Cambodia facebook | https://www.facebook.com/reel/3874370619451818, https://www.facebook.com/reel/2964338283746721 | English and Khmer | With captions and sign language |
| “Advancing the Right to Sign Language in Cambodia” video campaign | Video | Raise awareness about deaf rights and the importance of sign language | OHCHR Cambodia facebook, DAC/MOSVY facebook, DDP facebook | https://www.facebook.com/OHCHRCambodia/reels/ | English and Khmer | With captions and sign language interpretation |
| Khmer Times Cross Talk Show on “Persons with Disabilities” | Video Talk show | Build understanding about the rights of persons with disabilities and the work of the UN | Khmer Times | https://www.youtube.com/watch?v=qWmoPln-t_M | English and Khmer | With captions and sign language interpretation |
| Strengthening Media Reporting Through a Deeper Understanding of Disability Equality | Article | Promote transformative change for disability inclusion within media organizations in Cambodia | UNESCO Website | https://tinyurl.com/b4eebm8a | English |  |
| Information Needs Assessment for Persons with Disabilities in Cambodia | Research Report | Assess the current state of information accessibility for persons with disabilities | CDRI Website | https://cdri.org.kh/publication/information-needs-assessment-for-persons-with-disabilities-in-cambodia | English |  |
| UNESCO releases Cambodia’s first information needs assessment for persons with disabilities | Article | Raise awareness of Cambodia’s first Information Needs Assessment for Persons with Disabilities | UNESCO Website | https://www.unesco.org/en/articles/unesco-releases-cambodias-first-information-needs-assessment-persons-disabilities | English |  |
| Accelerating Disability Rights in Cambodia | Article | Promote a joint UNs initiative supporting the full inclusion of persons with disabilities in Cambodian society by improving their access to information and strengthening disability-inclusive policies and systems. | UNESCO Website | https://www.unesco.org/en/articles/accelerating-disability-rights-cambodia | English |  |
| Cambodia promotes inclusive media to empower persons with disabilities | News Article |  | Khmer Times | https://www.khmertimeskh.com/501770238/cambodia-promotes-inclusive-media-to-empower-persons-with-disabilities/ | English |  |
| Cambodia Pushes for Inclusive Media to Empower Persons with Disabilities | News Article | Advance inclusive media in Cambodia to empower persons with disabilities through improved access to information and participation | Khmer Tims | https://www.khmertimeskh.com/501769224/cambodia-pushes-for-inclusive-media-to-empower-persons-with-disabilities/ | English |  |
| Cambodia Calls for Greater Disability Equality in and through the Media | Press article | Advance disability equality in and through media in Cambodia by strengthening inclusive representation and accessibility. | UNESCO Website | https://www.unesco.org/en/articles/cambodia-calls-greater-disability-equality-and-through-media | English |  |

## 9. Challenges

Please describe any major challenges that arose during the programme implementation and how this affected the programme implementation.

There was a gap funding of GDF to the programme from April to July 2024 due to the transition from phase 1 to phase 2. Since late 2024, the RGC has initiated a structural reform of nine ministries with the aim of streamlining their organizational structures. The MoSVY and the DAC-SG are included in this reform. As of the end of 2025, the reform process is still under discussion among MoSVY, the DAC-SG and the Ministry of Civil Service (MCS), with no agreement yet on the final structure. This ongoing process has delayed progress on the new disability law, as several articles within the draft law depend on the finalization of the relevant public institutional structures that are expected to be revised under the reform.

Please could you share what action you took to address identified challenges?

Given that UN entities have contributed co-funding to the programme alongside the GDF, particularly UNDP, they leveraged these funds during the interim period from April to July 2024 to ensure the programme's smooth implementation with relevant stakeholders. Although the new disability law did not progress to the Council of Ministers or the Parliament for endorsement in 2025, this delay created an opportunity for the JP technical team to provide final inputs. These inputs were based on the project’s situation analysis on the rights of deaf and hard of hearing people, as well as the status OPDs. As a result, important recommendations were incorporated into the draft law. Examples include proposing national budget mechanisms to support OPD participation in commune-level administrative activities, legally recognizing sign language for deaf and hard of hearing people and increasing the number of sign language interpreters in Cambodia. Despite the delay in endorsing the new disability law, other programme work plans were implemented successfully and progressed well toward the expected outputs and outcomes for the 2022–2025 period.

## 10. Project Sustainability

Please provide an overview of initiatives planned by various stakeholders in order to follow up on activities initiated by the programme.

Several initiatives have been identified for continuation and scale-up by national and subnational stakeholders following the completion of the JP. Overall, the programme demonstrates promising dimensions of sustainability through the development of thematic policies, strengthened capacities and monitoring systems and the expansion of disability‑inclusion mechanisms at the sub‑national level. 1. Expansion of Disability Coordination Mechanisms at Subnational Levels During the JP, 18 District DACs were established across three Provincial DACs (Kampong Cham, Tboung Khmum, and Oddar Meanchey). This model has been recognized as a key success by the DAC-SG. - DAC-SG plans to amend the Sub-Decree on the functioning of DAC and PDAC to formally include the establishment of District DACs nationwide. - Once the Royal Government confirms the DAC-SG structure reform, DAC-SG is expected to proceed with scaling up district-level disability coordination bodies across all provinces. 2. Operationalization of the Digital M&E System for NDSP3 The JP developed a digital monitoring and evaluation system to track the implementation of the NDSP3 by line-ministry DAWGs and PDACs. - DAC-SG’s M&E team is expected to finalize all indicators with line ministries by March 2026. - The system will subsequently be launched for use by DAWGs at national and subnational levels to submit quarterly progress reports. - This system will serve as a key tool for the NDSP3 mid-term review planned for late 2026. 3. Launch and Utilization of the Disability Inclusion Online Learning Platform An online learning platform on disability inclusion, developed in Khmer during the JP, will continue to serve as a long-term capacity-building resource. - DAC-SG is expected to officially launch the platform and encourage members of DAC, DAWGs, PDACs, and other stakeholders to complete the training. - This will help strengthen understanding of disability inclusion and NDSP3 and support the development of disability-inclusive plans within institutions. 4. Sustaining OPD Engagement at the Commune Level The JP established partnership platforms linking two OPDs, five WWDFs, and 26 commune administrations. - Representatives from OPDs and WWDFs have already been integrated as members of CCWC. - Their ongoing participation in monthly CCWC meetings is expected to continue beyond the JP, ensuring sustained inclusion of persons with disabilities in local planning processes. 5. Advancement of the New Disability Law By the end of 2025, the draft of the new disability law had consolidated all inputs from government agencies, UN entities, OPDs, and civil society organizations. - DAC-SG holds the finalized draft and is expected to move it forward once the structure reform of DAC-SG is approved in 2026. - This will allow the draft law to progress to the next stages of endorsement. 6. Continuing and expanding capacity-building programmes In 2026, DAC has indicated that it intends to expand the programme on access to justice to the local level by engaging with local authorities and law enforcement, and the PDAC training by widely disseminating the localized CRPD manual and conducting a comprehensive capacity-assessment of PDACs, which will further inform future PDAC training efforts. 7. Environmental sustainability The programme was designed as an environmentally friendly initiative, with a focus on mitigating risks related to environmental protection. It was structured to ensure that no environmental harm would arise from its activities.

Please outline how the medium-to-long term sustainability of the work initiated by the project will be ensured after the end of the Project.

The sustainability of the work initiated by the JP is supported through institutional integration, system development, capacity-building mechanisms, and strengthened coordination structures. Several components of the programme have been embedded within national and subnational systems, ensuring continuity beyond the project period. Institutionalization of Disability Coordination at Subnational Levels The establishment of 18 District DACs during the JP has demonstrated an effective model for strengthening local disability coordination. Based on this lesson learned, DAC-SG intends to revise the Sub-Decree on the functioning of DAC and PDAC to formally include the establishment of District DACs under all PDACs nationwide. Once adopted, this structure will ensure a sustained disability coordination mechanism at the decentralized level, enabling OPDs, self-help groups of persons with disabilities, district officials, and commune authorities to jointly identify and address the rights and needs of persons with disabilities at the community level. Long-Term Use of the Digital M&E System for NDSP3 The digital monitoring and evaluation system developed under the JP provides a long-term mechanism for tracking NDSP3 implementation under the continued ownership of DAC-SG. Since the DAC-SG M&E team has been fully trained on system management, the platform will serve as a core tool for routine monitoring, including the NDSP3 mid-term review in late 2026. Beyond NDSP3, the system can be upgraded and adapted as the monitoring tool for the next National Disability Strategic Plan (2029–2033), ensuring continuity and long-term value of the JP investment. Continued Capacity Building Through the Online Learning Platform The localized training materials and disability inclusion online learning platform developed by the JP provides a sustainable, long‑term training resource under the leadership of DAC‑SG. The DAC-SG team has been capacitated to become trainers and facilitators of the manual, so that they can sustainably continue delivering CRPD-based training. The DAC‑SG M&E team has been trained to manage the online platform, which allows for tracking trainees’ participation and evaluation scores. DAC‑SG can continue using this platform for capacity building on disability inclusion for DAC members, DAWGs, PDACs, and other stakeholders. This ensures continuous online learning resources that contribute to the capacity development of disability inclusion among relevant stakeholders in Cambodia. Sustained OPD Participation in Local Governance The JP strengthened connections between OPDs, WWDFs, and 26 commune administrations, resulting in their formal inclusion as members of the Commune Committees for Women and Children (CCWC). Because OPD and WWDF representatives are now officially integrated into these structures, they will continue participating in monthly CCWC meetings beyond the JP period. This institutionalization ensures that persons with disabilities remain engaged in local planning, service delivery, and monitoring in the long term. Continuation of Legal Reform Efforts on the New Disability Law By the end of 2025, the final draft of the new disability law had incorporated inputs from government agencies, UN entities, OPDs, and civil society organizations. Once adopted, the law will provide a long-term legal foundation for disability rights and inclusive governance, ensuring that the JP’s contributions continue to shape policy implementation and enforcement in the years ahead.

## 11.Risk Reporting

Please describe any risks experienced during the programme’s implementation and how these were managed.

| Type of risk* (Contextual, programmatic, institutional) | Risk | Occurrence (Y/N) | Impact on result | Mitigation strategies | Risk treatment owners |
| --- | --- | --- | --- | --- | --- |
| Contextual | The government partners, including DAC-SG, did not implement key actions a few months before the national elections in July 2023 due to other key priorities from the RGC. | Y | Delayed implementing the project, affecting financial delivery and outcomes | Each UN Agency worked with the government partners to develop a concrete operation plan for implementation before and after the national election. | UNDP, OHCHR & UNESCO |
| Contextual | The endorsement of the new disability law has been delayed due to the national election in late 2023 and subsequent government reforms to MoSVY and DAC‑SG structures in 2024. | Y | The delay in endorsing the new disability law impacts its implementation within the JP period, as the law must reflect government structures that are still being finalized through ongoing reforms. | The JP team has provided all necessary technical inputs, collected from relevant stakeholders including government departments, UN entities, OPDs, and CSOs and has encouraged the MoSVY Minister and the DAC‑SG management to accelerate the government structure reform process with the MCS. During Phase 2, the JP focused only on providing residual support to finalize the remaining steps needed for the disability law to proceed to the Council of Ministers and the Parliament. At the same time, the JP shifted its primary focus toward developing NDSP3 and supporting its operationalization. | UNDP, OHCHR and UNESCO in collaboration with DAC-SG |

* Please specify here the type of risk and refer to the following definitions:

Contextual: risk of state failure, return to conflict, development failure, humanitarian crisis; factors over which external actors have limited control.

Programmatic: risk of failure to achieve the aims and objectives; risk of causing harm through engagements.

Institutional: risk to the donor agency, security, fiduciary failure, reputational loss, domestic political damage etc.

## 12. Detailed expenditure in relation to sections 3, 4 and 5 above

| Category | Activity (please describe) | Budget Allocated | Total Expenditure |
| --- | --- | --- | --- |
| Direct impact on empowerment of women and girls with disabilities | Direct capacity building, coaching, and support for women with disabilities forum organizations to advocate for disability inclusion with local administration offices. | $ 39310.99 | $ 39310.99 |
| Full and effective participation of persons with disabilities/ OPD capacity building |  | $107,762.24 | $107,762.24 |
|  | Participation of OPDs in meetings and consultation workshops | $45,913.87 | $45,913.87 |
|  | Capacity training to OPDs on disability inclusion, inclusive justice and legal aids, information and media | $22,048.37 | $22,048.37 |
|  | Direct grant to OPDs for their disability inclusion activities | $ 39,800 | $ 39,800 |
| Direct reach/inclusion of marginalized and vulnerable groups |  |  | $84,210.32 |
|  | Direct grant and activities with deaf development programme, two organizations working with persons with psychosocial disabilities (TPO and CTRO) | $83,935.32 | $83,935.32 |
|  | Campaign for the promotion of the rights of deaf and hard-of-hearing persons and recognition of sign language (2025) | $275.00 | $275.00 |
| Accessibility costs | Ensure the accessibility of venues (ramps, toilets, parking areas) for persons with disabilities for their barrier-free participation. | $6217.85 | $6217.85 |

# 14. Photos depicting Project related impact and outcomes

Please share photos depicting programme in high resolution image files with appropriate consents of subjects having been taken as well as with the associated credits and along with permission for use in GDF publications and communications materials including website. Please refer to the GDF photography guidelines which have been shared with the country teams already.

| Photo No. | Photo description for use in alternative text for images to enable persons with visual impairments using screen readers to understand and perceive the image. | Consent for Use of Photo obtained (Y/N) | Photo Caption | Photo Credit |
| --- | --- | --- | --- | --- |
| 12 photos | All photos were taken in 2024 | Y | Yes | Mentioned in the caption of each photo as below link |
| 37 photos | Photo of persons with disabilities including men, women, girls and boys and the photos of some meetings and consultation workshops during the JP implementing period. | Y | Yes | Mentioned in the caption of each photo via this link https://drive.google.com/drive/folders/1fcdkAZpQ24VpPFRVrBc-okeybSmEw8yK?usp=drive_link |

Annex 1. Impact Indicators of the Joint Programme

| GDF Impact Indicator (please refer to approved proposal section 5 for relevant indicators selected by the programme) | Country baseline (2021) (Beginning of the project reporting period) | Country Endline (2025) (End of the project reporting period) | Means of Verification |
| --- | --- | --- | --- |
| Number of persons with disabilities who accessed public services including social assistance programmes, employment services, education, vocational training, health services, rehabilitation, disability identification assessments, IDPoor assessments, and related support through the coordination and assistance of the Five Provincial Disability Action Councils (Kampong Cham, Kampong Speu, Tbong Khmoum, Battambang and Siem Reap Provicnes) and local administration offices (commune councils). | 4,995 persons with disabilities including 2,787 women with disabilities accessed PPE materials (hand sanitizers, face masks and alcohol), the emergency supported packages (including instant noodles, rice and canned fish), and other social service supports (health and rehabilitation services, education water supplies and so on) from five PDACs. | 46,487 persons with disabilities including 15,628 women accessed services through the coordination of six PDACs. These services covered critical areas such as healthcare, rehabilitation, vocational training, employment, education, and social protection, contributing to improved quality of life and greater social inclusion. | Final Programme Narrative Report on Programme to Promote Disability Inclusion and Quality Services for Gender-Based Violence (GBV) Victims from 03 February 2022 to 30 November 2021. Data of Six PDACs on persons with disabilities accessed public services from 2022 to 2025. |
| Amount of national budget allocated to the Five Provincial Disability Action Councils (Kampong Cham, Kampong Speu, Tbong Khmoum, Battambang and Siem Reap Provicnes) for the implementation of the Disability Inclusion Annual Work Plan. | No information about the budget allocation | The government has allocated USD 8,250 to the Siem Reap and Kampong Cham PDACs to implement the disability inclusion activities of Kampong Cham and Siem Reap Provinces. | Report of the Kampong Cham and Siem Reap PDAC Quarterly meetings |
| Number of persons with disabilities who have undergone a CRPD aligned disability assessment and are in possession of disability certification compared to statistical estimations of the number persons with disabilities. | 215,358 persons with disabilities were assessed for disability identification cards | 355,280 (174,013 women) persons with disabilities are assessed for disability identification cards | Statement of the Cambodian Prime Minister on the occasion of the National and International Day of Persons with Disabilities, 3 December 2021 and 2025 (Unofficial English Translation). |
| Percentage of persons with disabilities employed as compared to other persons and to overall employment rate, disaggregated by type of employment (public, private, self-employed), age, sex and disability | A total of 8,856 persons with disabilities including 4,204 women were employed in public and private entities, representing 1.28% of the 689,532 persons with disabilities recorded in the 2019 Census. | A total of 14,407 persons with disabilities including 5,562 women were employed across public and private entities, representing 0.88% of the 1,640,259 persons with disabilities recorded in the 2024 Inter‑Census. | Statement of the Cambodian Prime Minister on the occasion of the National and International Day of Persons with Disabilities, 3 December 2021 and 2025 (Unofficial English Translation). |
| Number of persons with disabilities accessed the government social assistant schemes from the government | By 2021, around 61,400 persons with disabilities received the monthly cash transfer support due to the impact of the COVID-19 pandemic from the government. | By December 2025, 63,223 persons with disabilities received the monthly cash support through the family package social assistance programme from the government. | Prime Minister Statement on 03 December 2021 to congratulate the occasion of the 23rd Cambodian Day of Persons with Disabilities and the 39th International Day of Persons with Disabilities. The National Social Assistant Fund provided statistics on the number of households that received government-funded family package social assistance in 2025. |

Annex 2: Output indicator results

| Indicator* | Start level (2021) Baseline (Beginning of the project reporting period)* | Target* | End level (2023) End line (End of the project reporting period)* | Means of Verification |
| --- | --- | --- | --- | --- |
| Output 1.1. (phase 1): Enhanced capacity of multi-stakeholders at national and subnational level in charge of disability mechanisms (Disability Action Council, Provincial Disability Action Council and Disability Action Working Group at line ministries) to support implementation and monitoring of disability inclusive policies (Social protection), laws (Disability Law, Law on Access to information) and plans (National Disability Strategic Plan 2-NDSP2). |  |  |  |  |
| 1.1.1. # of trainings (disaggregation by type of capacity building) developed and delivered in the UNPRPD programme. (Disaggregated by topics) | 1 training with 15 topics. | 8 trainings (disability inclusion, UN Disability Inclusion Strategy, SDGs inclusive processes, Covid 19 inclusive recovery plan, inclusive commune investment plan and M&E tool of new disability law and disability inclusive social protection, access to information and access to justice) Year 1: 5 trainings (i. web and App application, ii. monitoring and evaluation, iii. disability inclusive services, iv. inclusive commune investment plan and v. disability inclusive service) | 9 Training topics for 19 training sessions ( 8 topics: (1) work plan development, (2) NDSP2 monitoring and report, (3) Marrakesh Treaty, (4) CRPD, (5) access to justice to justice actors for persons with disabilities, (6) inclusion of persons with disabilities in employment in Cambodia, (7) inclusion of persons with disabilities in job placement in Cambodia, (8) inclusion of persons with disabilities in technical & vocational education & training in Cambodia, (9) CPRD and access to information for persons with disabilities for information officials. | Training report (partners) Annual Report 2022 and 2023 |
| 1.1.2. # of participants (disaggregated by type of stakeholder) disaggregated by sex, disability, rural/urban participating in capacity building activities funded or provided by UNPRPD programmes | 68 participants (30 women 38 men) | 500 participants (at least 40% women) Year 1 (2022): 374 participants (53 women, 40 persons with disability). | 960 participants (402 (42%) women) | Training report (partners) Annual Report 2022 and 2023 |
| 1.1.3. # and % of participants reporting increased knowledge or capacity to design or revise policies or systems to be more disability inclusive. | 68 participants (30women 38 men) | 500 participants and 70% of participants increased knowledge | 663 participants and 93% of participants increased knowledge | Training report (partners) Annual Report 2022 and 2023 |
| Output 1.1 A (phase 1): Enhanced capacity of disability movement, including women with disabilities and most vulnerable groups (deaf persons, blind persons and persons with psychosocial disabilities) to effectively engage in development, implementation and monitoring of CRPD and Inclusive SDGs processes by improving their capacity for meaningful engagement and advocacy with the national and subnational stakeholders including government and service providers in areas of inclusive social protection, access to justice, meaningful representation (persons with hearing impairment) and economic empowerment (women with disabilities) |  |  |  |  |
| 1.1.2. # of participants (disaggregated by type of stakeholder) disaggregated by sex, disability, rural/urban participating in capacity building activities funded or provided by UNPRPD programmes | N/A | 50 participants (at least 40% women) Year 1 (2022): 27 participants (23 women, 27 persons with disability (5 physical disabilities & 22 deaf persons). | 338 participants (203 women, 285 persons with disabilities, 338 rural) | Annual Report 2022 and 2023 |
| 1.1.3. # and % of participants reporting increased knowledge or capacity to design or revise policies or systems to be more disability inclusive. | 68 participants (30 women 38 men) | 5 women with disabilities Year 1 (2022): 5 women with disabilities and 100% of them increased knowledge on recovery plan and advocacy toolkit | 60 OPDs (35 women) attended DMIL and DL trainings and 85% of them increased knowledge. | Annual Report 2022 and 2023 |
| 1.1.4. # of OPDs (disaggregated by type umbrella- disability specific- women- underrepresented other) that benefitted from capacity building activities (type of activities) funded by UNPRPD programmes to strengthen the capacity of organizations of persons with disabilities. | Four OPDs (all of them are men and physical disabilities) | 6 OPDs (including 5 WWDFs) Year 1 (2022): 6 OPDs (all of them have physical | 15 OPDs (5 OPDs, 6 women and girls with disability forums, 1 Deaf Development Program, 1 Phnom Penh Center for Independent Living (severe disability), 1 Cambodian Blind Association and 1 Youth with Disability Organization). | Annual Report 2022 and 2023 |
| 1.1.5. # of capacity building activities funded by UNPRPD programmes, directed at women and girls with disabilities on their rights and requirements and/or directed at underrepresented groups of persons with disabilities on their rights and requirements. (disaggregated by target group) | N/A | 10 capacity building activities provided to women and girls with disabilities and deaf persons. Year 1: 8 trainings (3 trainings (i. COVID-19 Recover Plan, ii. Toolkit and iii. Advocacy Plan Development) to 5 women with disabilities, 5 trainings (i. the way to communicate using foundation of Cambodian sign language, ii. find out and understand about any problems occurring in social media, iii. hygiene and cleanliness, iv. method to inspect and control the group, v. sharing about income generation and saving.) to 22 deaf persons (17 women) | 16 capacity building activities provided to women and girls with disabilities and deaf persons (1. Digital, Media, and Information Literacy, (2) project reflection and networking with local authority, (3) psychosocial disabilities education, (4) incident reporting and monitoring mechanism, (5) Universal Periodic Review, (6) basic sign language, (7) set up the group, (8) policy of the group, (9) roles of the group, (10) knowledge of deafness, (11) know yourself, (12) friend relationship, (13) team work, (14) inclusion of persons with disabilities in employment in Cambodia, (15) inclusion of persons with disabilities in job placement in Cambodia, (16) inclusion of persons with disabilities in technical & vocational education & training in Cambodia | Annual Report 2022 and 2023 |
| Output 1.1 A (phase 2): The capacity of DAC, DAWGs at line ministries, Provincial DACs, District DACs, UNCTs, OPDs and media is enhanced through approaches and strategies designed to accelerate knowledge transfer for the effective delivery of inclusive services to persons with disabilities, including women, girls and underrepresented groups of persons with disabilities at both national and subnational level. |  |  |  |  |
| 1.2.1. # of knowledge products (disaggregated by type of product/thematic focus) developed, piloted and disseminated to the relevant stakeholders to inform inclusive practices | 4 drafted products (guidelines and manuals, disability inclusive social protection, disability inclusive employment) | 5 knowledge products produced/developed | 7 knowledge products developed. | 2024 Annual Report |
| 1.2.2. # of knowledge products developed that address gaps related to inclusion of women and girls with disabilities and/or underrepresented groups of persons with disabilities (disaggregated by thematic focus) | 4 drafted products (guidelines and manuals, disability inclusive in social protection, disability inclusive employment) | 4 knowledge products (training material on 1) CRPD and access to justice, 2) access to information, 3) disability inclusion, and 4) basic sign language communication) | 9 knowledge products developed. 1) CRPD and access to justice 2) access to information assessment 3) Disability inclusion services 4) Open up the world for deaf people in Cambodia 5) Advocacy tool for NDSP3 6) Draft situation analysis on the Rights of Deaf people, and 7) Draft situation analysis on the current situation of the OPDs and WWDFs in Cambodia. 8) Deaf Leadership Training Programme 9) White Paper on the Legal Recognition of Sign Language. | 2024 Annual Report |
| 1.2.3. # of actors involved in developing and testing of knowledge products (disaggregated by actor (Govt/NGOs/OPDs/Other) | 7 actors (GOV/NGOs/ OPDs/ UNCT/Under-represented organizations/donors /experts) | 7 actors (GOV/ NGOs/OPDs/ UNCT/ Under-represented organizations/ donors/experts) | 7 actors (GOV/ NGOs/OPDs/ UNCT/ Under-represented organizations/ donors/experts) | 2024 Annual Report |
| 1.2.4. # of stakeholders reporting increased or strengthened policies and systems as a result of UNPRPD funded KM tools (disaggregated by stakeholder) | 2 stakeholders: (1) DAC and (2) Government line ministries | 7 stakeholders (GOV/NGOs/OPDs/ UNCT/Under-represented organizations/ donors/experts) | 7 stakeholders 1) DAC-SG on development of the NDSP3 2) Ministry of Women’s Affairs on the inclusion of the persons with disabilities in the Neary Rattanak Strategic Plan (2024-2028) 3) Ministry of Education Youth and Sport on the development of the Disability Inclusive Action Plan 2024-2028 4) National Social Protection Council on the inclusion of persons with disabilities in the National Social Protection Policy Framework 2024-2035 5) Ministry of Public Works and Transport on the draft of the disability inclusion in the public bus 6) Ministry of Interior on development of eight indicators related to persons with disabilities 7) Six Provincial DACs on disability inclusion services and CRPD, and 8) 6 OPDs and WWDFs on the knowledge of NDSP3 9) Ministry of Justice and justice actors (judges, prosecutors, court officials) on access to justice for persons with disabilities | 2024 Annual Report |
| Output 1.1B (phase 2): The capacity of the M&E team of DAC, DAWGs, provincial DACs, CDPO, OPDs and relevant stakeholders is enhanced to operationalize the digital M&E system of NDSP3. |  |  |  |  |
| 1.2.1. # of knowledge products (disaggregated by type of product/thematic focus) developed, piloted and disseminated to the relevant stakeholders to inform inclusive practices | 1 knowledge product (material training on digital NDSP2 M&E) | 2 knowledge products (1) training manual on digital NDSP3 M&E and 2) digital NDSP3 M&E system | 3 knowledge products developed. 1) training manual on digital NDSP3 M&E and 2) Digital NDSP3 M&E system have been upgraded. 3) Digital online learning platform on disability inclusion for DAC-SG, DAWG and PDACs. | 2024 Annual Report |
| 1.2.2. # of knowledge products developed that address gaps related to inclusion of women and girls with disabilities and/or underrepresented groups of persons with disabilities (disaggregated by thematic focus) | No drafted product | 1 knowledge products (1) training manual on digital NDSP3 M&E | 2 knowledge products developed 1) The public information related to the disability report of NDSP3 has been created in the web application. 2) Educational and promotional video on the NDSP3 | 2024 Annual Report https://www.facebook.com/reel/1923541351910032 |
| 1.2.3. # of actors involved in developing and testing of knowledge products (disaggregated by actor (Govt/NGOs/OPDs /Other) | 7 actors (GOV/NGOs/ OPDs/UNCT/ Underrepresented organizations/ donors/experts) | 7 actors (GOV/NGOs/ OPDs/UNCT/ Underrepresented organizations/ donors/experts) | 7 actors (GOV/NGOs/ OPDs/UNCT/ Underrepresented organizations/ donors/experts) | 2024 Annual Report |
| 1.2.4. # of stakeholders reporting increased or strengthened policies and systems as a result of UNPRPD funded KM tools (disaggregated by stakeholder) | 2 stakeholders: (1) DAC and (2) Government line ministries | 1 stakeholder (GOV) | 3 stakeholders - M&E team of DAC-SG - DAWG Provincial DAC | 2025 Annual Report Results of the Post Test on NDSP3 Training |
| Output 1.2 (phase 1): Enhanced capacity of UNCT to support government on SDGs inclusive processes and COVID-19 inclusive recovery plan by building inclusive tools, dialogues and effective participation of OPDs |  |  |  |  |
| 1.2.1.# of knowledge products (disaggregated by type of product /Thematic focus) developed, piloted and disseminated to the relevant stakeholders to inform inclusive practices | Final COVID-19 recovery plan, Advocacy toolkits, NDSP2, Legal Aid Practical Guideline | 3 (Operational plan of COVID-19 recovery plan, Disability Inclusive Social Protection Guideline, National Disability) Year 1: 1) Assessment tool on the function of the Provincial DAC was developed. | 4 drafted products: (1) Guidelines on Disability Inclusive Social Protection, (2) Training Guideline on Inclusion of Persons with Disabilities in Employment in Cambodia, (3) Training Guideline on Inclusion of Persons with Disabilities in Job Placement in Cambodia, (4) Training Guideline on Inclusion of Persons with Disabilities in Technical & Vocational Education & Training 1 Analysis of Disability Scorecard report with recommendations for 2023 | Annual Report 2022 and 2023 |
| 1.2.2. # of knowledge products developed that address gaps related to inclusion of women and girls with disabilities and/or underrepresented groups of persons with disabilities (disaggregated by thematic focus) | 1 (UN Disability Scorecard Report) | 1 Analysis of Scorecard report recommendations Year 1: completed Scorecard report recommendations for 2022. | 1 Analysis of Disability Scorecard report with recommendations for 2023 | Annual Report 2022 & 2023 UNRCO Disability Scorecard report |
| 1.2.3. # of actors involved in developing and testing of knowledge products (Disaggregated by Actors GOV/NGOs/ OPDs/Other) | N/A | 5 (Disability Action Council, MoI, NEA, TVET, MoJ). Year 1: 2 actors (DAC and 5 OPDs) involved in the development of assessment tool on the function of the Provincial DAC. | 7 actors involved: (1) Disability Action Council, (2) Government line ministries, (3) OPDs, NGOs, (4) Underrepresented organizations, (5) UN agencies, (6) donors (DFAT), (7) individual experts | Annual Report 2022 & 2023 |
| 1.2.4. # of stakeholders reporting increased or strengthened policies and systems as a result of UNPRPD funded KM tools (disaggregated by stakeholder) | N/A | 2 stakeholders: (1) DAC and (2) Government line ministries (MoSVY and General Secretariat-l of National Council for Social Protection) strengthened policies and systems | 2 stakeholders: (1) DAC and (2) Government line ministries (MoSVY and General Secretariat-l of National Council for Social Protection) strengthened policies and systems | Annual Report 2023 |
| Output 2.1 (phase 1): Drafting of new Disability Law and required sub-legislation aligned with CRPD with full participation of OPDs (from the consultation until the submission to Council of Ministers) |  |  |  |  |
| 2.1.1.# of national regulatory frameworks and systems changes targeted by the UNPRPD programme disaggregated by 1) legislation/ regulation, 2) policies/plans /strategies, 3) capacity building programmes, 4) operational guidance/standards, 5) direct services/service overhaul/service modelling, 6) audits/reviews/assessments, 7) governmental programmes, 8) administrative procedures, 9) formal monitoring and accountability mechanisms or bodies, 10) regulatory/oversite/monitoring systems, 11) financing and budgeting or 12) other (please explain) | Zero draft of new disability law | 2 (new disability law and M&E unit or mechanism) Year 1: 2 (1 regulatory framework (draft new disability law) and 1 system change (digital M&E system for the NDSP) | 3 national regulatory frameworks: (1) final draft of new disability law and (2) first draft NDSP 2024-2028, (3) National Social Assistance Program for Family Package (Khmer version) | Final draft of new disability law and First draft of the NDSP 2024-2028 National Social Assistance Program for Family Package (Khmer version) |
| 2.1.2. Type of change (development/revision/reform) in legal frameworks and systems | Zero draft of new disability law | Year 1 (2021): 2 (1. new disability law developed and 2. digital M&E system for the NDSP established together with the new working group of the MEL set up). | 3 types of change: Comply with CPRD on the draft of the new disability law (revision) and NDSP3 (reform). Disability inclusion in the social assistance system (reform). | Final draft of new disability law (Khmer version) Endorsed NDSP3 (https://dac.gov.kh/en/download/33/national-disability-strategic-plan-2024-2028.html) Endorsed National Social Protection Policy Framework 2024-2035 ( https://nspc.gov.kh/Images/National%20Social%20Protection%20Policy%20Framework%202024-2035_2025_02_20_15_45_55.pdf) |
| Output 2.1.2 (phase 1): The new Disability Law has clear implementation plan with clear roles and is effectively disseminated to both national and sub national level through communication campaigns throughout the country |  |  |  |  |
| 2.2.1. # of multi-stakeholder coordination mechanisms (disaggregated formal/informal) to support legislative policy and systems changes developed or strengthened | N/A | 3 (OPD network, UNCT and DAC) | 3 (OPD network, UNCT and DAC) | Social media of DAC on the consultation meeting on disability law. https://www.facebook.com/share/p/1DST7seevH/ https://www.facebook.com/share/p/1Cp4BZHiQX/ ​​​​ |
| 2.2.2. # of stakeholders within each mechanism (disaggregated by type of stakeholder Gov/ UN/OPDs/other). | 3 (GOVT, UN & OPD) | 6 (GOV/UN/ OPD/WWDF/NGO/INGO) | 6 (GOV/UN/ OPD-WWDF/NGO-CSO/Expert) | Annual Report |
| 2.2.3. # stakeholders involved in consultation and validation processes (disaggregation by stakeholder (GOV/UN/OPDs/other) | 3 (GOVT, UN & OPD) | 6 (GOV/UN/ OPD-WWDF/NGO-CSO/Expert) | 6 (GOV/UN/ OPD-WWDF/NGO-CSO/Expert) | Annual Report https://www.facebook.com/share/p/1Cp4BZHiQX/ |
| Output 2.1.3 (phase 1): Disability Action Council have clear mandate and approved plans to monitor National Disability Strategic Plan and the New Disability Law with full participation with OPDs. |  |  |  |  |
| 2.1.1. # of national regulatory frameworks and systems changes targeted by the UNPRPD program disaggregated by: 1) legislation/ regulation, 2) policies/ plans/strategies, 3) capacity building programs, 4) operational guidance/standards, 5) direct services/service overhaul/ service modelling, 6) audits/ reviews/assessments, 7) governmental programs, 8) administrative procedures, 9) formal monitoring and accountability mechanisms or bodies, 10) regulatory/ oversite/monitoring systems, 11) financing and budgeting or 12) other (please explain) | N/A | One national regulatory frameworks and systems changes targeted by the UNPRPD program (9) formal monitoring and accountability mechanisms or bodies). Year 1 (2021): One national regulatory frameworks and systems changes targeted by the UNPRPD program (9) formal monitoring and accountability mechanisms or bodies). | 2 drafts of national regulatory frameworks: (1) draft CPRD report for 2013-2020 and (2) draft NDSP3. | Initial State party Report on the Implementation of the CPRD and NDSP3. |
| 2.1.2. # type of change (development/ review/reform) in legal frameworks and systems | N/A | One type of change (development/ revision/reform) in legal frameworks and systems Year 1 (2021): One type of change (establishment of the DAC’s online M&E tool-NDSP2 Web Application Report) | Two types of changes: (1) CPRD report following to the guidelines of CRPD committee (development) and (2) NDSP3 complying with CRPD and indicators. | Initial Report on the Implementation of the CPRD and NDSP3 |
| Output 2.1A (phase 2): Access to disability inclusive services increased in line with NSDP3 for persons with disabilities, including women, girls and underrepresented groups of persons with disabilities, through the effective and efficient operationalization of DAC, DAWG at line ministries, provincial and district DACs, and OPDs. |  |  |  |  |
| 2.1.1.# of national regulatory frameworks and systems changes targeted by the UNPRPD program disaggregated by 1) legislation/ regulation, 2) policies/plans/ strategies, 3) capacity building programs, 4) operational guidance/standards, 5) direct services/service overhaul/service modelling, 6) audits/reviews/ assessments, 7) governmental programs, 8) administrative procedures, 9) formal monitoring and accountability mechanisms or bodies, 10) regulatory/oversite/ monitoring systems, 11) financing and budgeting or 12) other (please explain) | 2 drafts of national regulatory frameworks: disaggregated by (1) final draft of new disability law and (2) first draft of the NDSP 2024-2028, (4) National Social Assistance Program for Family Package (Khmer version) | Designed the pilots on coordination mechanisms of the 8 district DACs of Kampong Cham provincial DAC | 18 regulation letters of district governors to establish the 18 district/Khan DACs of Kampong Cham, Tbong Khmoum, and Oudor Meanchey provincial DACs were officially formed, and the roles and responsibilities were disseminated to the members to provide support and coordination to persons with disabilities within their respective districts. | 2024 Annual Report Regulation Letter of all 18 district governors (Khmer version) https://www.facebook.com/share/p/1BgyVR9oE2/ |
| 2.1.2. # type of change (development/review/reform) in legal frameworks and systems | 3 types of change: Comply with CPRD on the draft of the new disability law (revision) and NDSP3 (reform). Disability inclusion in the social assistance system (reform). | 1 type of change (the integration of disability inclusion in the action plan or strategic plan of DAWG at the line ministry [e.g., inclusive education] is developed) | 5 types of changes on disability inclusion in the DAWGs are as below. 1) Ministry of Women’s Affairs on the inclusion of the persons with disabilities in the Neary Rattanak Strategic Plan (2024-2028) 2) Ministry of Education Youth and Sport on the development of the Disability Inclusive Action Plan 2024-2028 3) National Social Protection Council on the inclusion of persons with disabilities in the National Social Protection Policy Framework 2024-2035 4) Ministry of Interior and Ministry of Economic and Finance on the inclusion of the budget allocation for disability inclusion activities for the national fund to the local commune councils (2025) 5) Ministry of Information on the inclusion of accessibility (sign language interpreter, audio voice, and subtitle) on the media and TV channels (2025). | 2024 Annual Report https://www.khmertimeskh.com/501469701/ministry-launches-neary-rattanak-plan-for-next-five-years/ https://moeys.gov.kh/storage/uploads/documents//67316f9d3a57f.pdf https://nspc.gov.kh/Images/National%20Social%20Protection%20Policy%20Framework%202024-2035_2025_02_20_15_45_55.pdf https://www.facebook.com/share/p/1ExCv8BU8b/ |
| Output 2.1B (phase 2): The digital monitoring and evaluation system is operationalized to efficiently monitor and report on the NDSP3 and other disability-related policy, plans, and guidance. |  |  |  |  |
| 2.1.1.# of national regulatory frameworks and systems changes targeted by the UNPRPD program disaggregated by 1) legislation/ regulation, 2) policies/plans/ strategies, 3) capacity building programs, 4) operational guidance/standards, 5) direct services/service overhaul/service modelling, 6) audits/reviews/ assessments, 7) governmental programs, 8) administrative procedures, 9) formal monitoring and accountability mechanisms or bodies, 10) regulatory/oversite/ monitoring systems, 11) financing and budgeting or 12) other (please explain) | Digital M&E system for NDSP2 | 1 system change of upgrading the digital M&E system of NDSP3 together with the capacity building programme for the DAC-SG M&E team | 1 system change of upgrading the digital M&E system with 96 indicators of the NDSP3 together with the capacity building programme for the DAC-SG M&E team | 2025 Annual Report https://www.facebook.com/share/p/17dN967FA4/ |
| 2.1.2. # type of change (development/review /reform) in legal frameworks and systems | M&E team of DAC-SG | The DAC-SG is reformed to effectively operate the digital M&E system | The M&E team of the DAC-SG was officially reformed in September 2024 with two main groups (1) on data collection, analysis and report and (2) on the digital technology management) to manage the digital M&E system of DAC-SG. They were trained to manage the system independently. | 2024 Annual Report |
| Output 2.2 (phase 1) Full participation of OPD in the process of revision of the National Disability Strategic Plan to be aligned with the CRPD and new Disability Law ensured once the Law is approved. (NDSP 2 extension or new NDSP 3- whatever option is chosen by the Government) |  |  |  |  |
| 2.2.1. ​# of multi-stakeholder coordination mechanisms (disaggregated formal/informal) to support legislative policy and systems changes developed or strengthened | N/A | Three multi-stakeholders (DAC, OPD and UN) Year 1 (2021): Three multi-stakeholders (1) DAC (formal government disability coordination), (2) CDPO (formal organization of persons with disabilities and (3) UN (formal) | Three multi-stakeholders (1) DAC (formal government disability coordination), (2) CDPO (formal network of the organization of persons with disabilities and (3) UNCT (formal) | Final draft of the NDSP3 https://eacnews.asia/home/details/23208 https://www.linkedin.com/posts/undp-cambodia_inclusion-integration-participation-activity-7075024664200167425-Mp4H?utm_source=share&utm_medium=member_desktop&rcm=ACoAAE_PYxcBVYKZWiMXYbQ7bTvRGexJSHPklJg |
| 2.2.2. # of stakeholders within each mechanism (disaggregated by type of stakeholder Gov/ UN/OPDs/other) | N/A | 2 stakeholders within each mechanism Year 1 (2021): 2 stakeholders in DAC: (1) Disability Action Working Group at line ministries and (2) Provincial DAC and 10 OPDs from the members of CDPO | 7 multi-stakeholder coordination mechanisms: Formal mechanisms including (1) DAC, (2) GOV’T, (3) CSO, (4) OPDs and (5) UN Agencies and informal mechanism including (6) Under-representative Organizations (hearing and visual impairments), persons with disabilities/families/carers and (7) individual disability expert | 2022 & 2023 Annual Report https://www.undp.org/cambodia/speeches/reflection-workshop-implementation-national-disability-strategic-plan-2019-2023 |
| 2.2.3. # stakeholders involved in consultation and validation processes (disaggregation by stakeholder (GOV/UN/OPDs/other) | 5 (GOV’T/UN/ OPD/ CSO) involved in consultation of the new disability law | 4 Stakeholders Year 1 (2021): 5 (GOV’T/UN/ OPD/ CSO) involved in consultation of the new disability law | 7 multi-stakeholder coordination mechanisms: (1) DAC, (2) GOV’T, (3) OPDs, (4) CSO, (5) UN Agencies, (6) Under-representative Organizations (hearing and visual impairments) and (7) individual disability expert | 2022 & 2023 Annual Report |
| Output 3.1 (phase 1): Disability inclusion is strengthened in planning, implementation and monitoring of UN development activities at the country level including in humanitarian settings. |  |  |  |  |
| 3.1.2. # UNSDCF where disability inclusion has been mainstreamed and/or targeted. | N/A | 19 (10 women) Persons with Disabilities (physical, hearing, blind, intellectual disabilities) invited to join development process of the UNSDCF 2024-2028. | UNSDCF incorporated persons with disabilities. At least 1 indicator of UNSDCF directly included the data of persons with disabilities. | UNSDCF 2024-2028 |
| Output 3.2 (phase 1): Effective implementation of COVID-19 inclusive Recovery Plan through national monitoring system is ensured |  |  |  |  |
| 3.2.2. # of adopted/ implemented COVID 19 inclusive response and recovery plans and frameworks containing systematic mainstreaming of persons with disabilities including the most marginalised | COVID-19 recovery plan (2021-2023) | 2 (1: COVID-19 recovery plan endorsed by DAC, 1: Disability Inclusive Social Protection guideline) Year 1: (1) COVID-19 recovery plan was finalized by DAC to implement with relevant stakeholders in late 2021, the recovery plan was disseminated with six commune councils to ensure smooth implementation. Meanwhile, the Disability Inclusive Social Protection Guideline was in the process of being recruited for international consultation. | 7 adopted/ implemented COVID-19 activities: (1) Disability inclusion was included in the social assistant family package manual of the government and 6 local administration offices (commune councils) included the disability inclusion activities (such as access to health service, social assistance, ID disability, disability awareness and rehabilitation services) in their commune | 2022 & 2023 Annual Report Family package manual of the government (Khmer version) |
| Output 3.3 (phase 1): Full participation of OPDs in processes of implementation and monitoring of inclusive COVID-19 Recovery Plan is ensured |  |  |  |  |
| 3.3.3. # of identified persons with disabilities including through their representative organizations participating in the State’s formulation/implementation of COVID-19 policy responses | 18 (40% women) persons with disabilities | 20 (10 women) persons with disabilities Year 1 (2021): 28 (22 women) persons with disabilities | 305 (144 women) persons with disabilities | 2022 & 2023 Annual Report |

https://docs.google.com/spreadsheets/d/1geIPE3T5ydHq6XDD8JNg-aLNA8AhReT6/edit?usp=drive_link&ouid=102430105287673132199&rtpof=true&sd=true

https://www.undp.org/cambodia/speeches/report-launching-and-dissemination-impact-evaluation-cash-transfer-programme-poor-and-vulnerable-households-during-covid-19#:~:text=Then%20came%20the%20good%20news,people%20living%20with%20HIV/AIDS.

https://www.undp.org/cambodia/stories/open-world-deaf-people-cambodia

https://www.facebook.com/OHCHRCambodia/posts/pfbid0219arRBHBLQcMMfKeJuw6sqGwRoruiCm2njjq9HD2xzv7QNnJv5df28aV3uJwswREl

Prime Minister’s Statement as the Honorary President of the Disability Action Council, on the occasion of the 23rd Cambodian Day of Persons with Disabilities and the 39th International Day of Persons with Disabilities,

3 December 2021.

Prime Minister’s Statement as the Honorary Chair of the Disability Action Council, on the occasion of the 27th Cambodian Day of Persons with Disabilities and the 43rd International Day of Persons with Disabilities, on 03 December 2025.

https://www.facebook.com/share/v/15o31bPaaE/

https://www.facebook.com/reel/3874370619451818

https://unesdoc.unesco.org/ark:/48223/pf0000391858.locale=en

UNDP 2025. Situation analysis on the rights of deaf and hard of hearing people in Cambodia.

https://tpocambodia.org/wp-content/uploads/2015/09/2012-Leitner-Cambodia-Report-on-mental-health.pdf

UNDP 2025. Situation analysis of the Organizations of Persons with Disabilities in Cambodia.

UNDP 2025. Situation analysis on the rights of persons with disabilities.

https://www.unesco.org/en/articles/cambodia-breaking-down-barriers-facilitate-access-information-persons-disabilities

https://www.undp.org/cambodia/stories/open-world-deaf-people-cambodia

https://youtu.be/nEjRkmZrDgE?si=JiuefSfm3EKCVK-7

https://www.facebook.com/reel/3874370619451818

https://www.facebook.com/reel/2964338283746721

https://www.facebook.com/reel/1120184390290803

https://www.facebook.com/reel/728369880217486

https://www.facebook.com/reel/1310529797228691

https://www.unaids.org/en/resources/presscentre/pressreleaseandstatementarchive/2025/may/20250516_cambodia#:~:text=Cambodia%20has%20embraced%20this%20concept,%2C%20Twitter%2C%20Instagram%20and%20YouTube.

https://www.undp.org/cambodia/press-releases/cambodia-launches-third-nationally-determined-contribution-ndc-30-accelerate-climate-action-and-sustainable-development

https://data.opendevelopmentcambodia.net/en/dataset/ea70175c-5cc0-4472-8206-427cabd96616/resource/6626e6a1-e41a-4434-8068-577f1a012b19/download/moeys_action-plan-on-inclusive-education-2024-2028_en.pdf

https://nspc.gov.kh/Images/National%20Social%20Protection%20Policy%20Framework%202024-2035_2025_02_20_15_45_55.pdf

https://dac.gov.kh/en/download/33/national-disability-strategic-plan-2024-2028.html

https://tbinternet.ohchr.org/_layouts/15/TreatyBodyExternal/countries.aspx?CountryCode=KHM&Lang=EN

https://www.linkedin.com/posts/undp-cambodia_cambodia-disabilityinclusion-activity-7269702811150381057-dIb7?utm_source=share&utm_medium=member_desktop&rcm=ACoAAE_PYxcBVYKZWiMXYbQ7bTvRGexJSHPklJg

https://www.akp.gov.kh/post/detail/354828

https://www.facebook.com/share/p/16sByFryJv/

https://dac.gov.kh/en/download/33/national-disability-strategic-plan-2024-2028.html

https://www.facebook.com/share/p/15RZTXHrej/

https://www.facebook.com/share/p/18YZmF8Df9/

https://www.undp.org/cambodia/stories/open-world-deaf-people-cambodia

https://drive.google.com/drive/folders/1RS0sxXOHAQ29nW099CcZ6rVyziXRrFP-?usp=drive_link

https://drive.google.com/drive/folders/1RS0sxXOHAQ29nW099CcZ6rVyziXRrFP-?usp=drive_link