With financial support from 
the Russian Federation

The Russian Federation-UNDP Trust Fund for Development

Graduation Based Social Protection Project

Cambodia

Mid-Year Progress Report

01 January 2021 – 30 June 2021

The template of Project Annual Narrative and Financial Progress Report approved by the 6th meeting of the TFD Steering Committee in 2017, technical update in 2020

# The Russian Federation-UNDP Trust Fund for Development (TFD)

# Project Semi Annual Narrative and Financial Progress Report

| # Project title: | # Graduation Based Social Protection |
| --- | --- |
| # Atlas Project ID: | # 00118418 |
| # Implementing partner: | # United Nations Development Programme with the following responsible parties: National Social Protection Council, Ministry of Economy and Finance, Ministry of Interior, Ministry of Planning, and Ministry of Social Affairs, Veterans and Youth Rehabilitation |
| # Project budget: | # Total: US$ 2,300,000 # TFD: US$ 1,000,000 |
| # Co-financing attracted since project start: | # Direct contribution to project budget: # Direction contribution: USD 800,000 (UNDP) # In-kind co-financing: |
| # Project start and end date: | # 2019-2023 |
| # Reporting Period: | # 01 January – 30 June 2021 |
| # Date of the last Project Board meeting: | # 23 July 2020 (first Board) |
| # SDGs supported by the project: | # SDG 4, 8 & 9 |

# ACRONYMS (in alphabetical order)

CSES: Cambodia Socio-Economic Survey

MoSVY: Ministry of Social Affairs, Veterans and Youth Rehabilitation

PLIG: Project Local Implementing Group

POM: Project Operation Manual

RCT: Randomized Control Trial

SNAs: Sub-National Administrations

WVI: World Vision International

# 1. EXECUTIVE SUMMARY

The Graduation Based Social Protection (GBSP) project has been designed based on the global experiences and the findings of a major research study - Graduation Based Social Protection for Cambodia’s Extreme Poor, conducted in 2017. Graduation-based approaches have proved the world over, that they can succeed by enabling poor households to boost their own incomes and secure a lasting exit from poverty, therefore  it is expected to make a valuable contribution to Cambodia’s social protection system.

This four-year project aims to test the effectiveness and practicality of graduation-based approaches in the Cambodia context via a pilot experiment. Basing on its proven practicality and viability, graduation-based approaches are adopted as part of the Government’s National Social Protection Policy Framework (NSPPF) and scale up nationwide. The project composes of 4 principal components:  (1) Set-up and roll-out of the pilot, preparation of analytical instruments and institutional arrangements;  (2) Delivery of the pilot to several thousand households at 2 localities (several villages within 2 specified rural/remote districts);  (3) Delivery of a follow-on asset package (to separate group of households) informed by the initial round;  and (4) Review and reporting, including analysis and building a policy case.

# This progress report covering from January to June 2021. During this period, the project completed key major activities such as entering into the Letter of Agreement (LoA) with the Ministry of Social Affairs, Veterans, and Youth Rehabilitation (MoSVY) on 31 March 2021. Through this LoA, MoSVY will use its Covid 19 cash transfer experience to transfer cash for household consumption and one-off lump sum cash for investment to 1,600 households. At the same time, the workplan and budget was reviewed with the project key partner, World Vision International (WVI) to include key activities such as the capacity building of Sub-national Administration (SNAs), local volunteers, and livelihood design to meet the need of poor households and align with opportunities and negative impacts causing from the Covid 19. The 2021-2022 work-plan and budget was also revised and approved by the Board via an email sent on 11 March 2021 to seek the approval of the Project Board. It should note that despite of the lockdown, restriction of movement and gathering and widespread of the Covid 19 in the country, the project could carry out the baseline survey and completed the interview with nearly 3,000 households in two target districts. The data are now being reviewed and cleaned.

# For activities at the ground, since coming onboard WVI’s local team has worked with district and commune administrations. The virtual meeting was held on 11 May 2021 to inform local authorities about the project and sought their supports for data collection works. The local team has collected socioeconomic data which are useful and important to design a poverty graduation course composing of livelihoods, life skills and financial inclusion training. Meanwhile, MoSVY team has developed the cash transfer operation manual and at the same time, is recruiting project staff members to run its project operation unit. A micro HACT assessment has been conducting with MoSVY to assess its capacity to implement the activities.

# During this period, the project has encountered direct challenges, mainly disruption from Covid 19. The incident of 20 February 2021 has caused the large scale widespread of the virus in Phnom Penh and soon after to the project’s target areas. Data collection plan has been revised many times while enumerators should be recruited in local areas since it is risky to move people from place to place. Therefore, the project and its partner has spent much time on training and coaching of those enumerators and set up a remote control and supporting data quality control system. Moreover, two staff members of WVIs were in two weeks quarantine due to their indirect contact with Covid 19 patients. Despite these challenges, by adopting precautionary measures and at the same with the good cooperation with local authorities, the interview process was timely completed.

# 2. RESULTS

# The outbreak of the Covid 19 global pandemic has changed development landscape in Cambodia and at the same time opposed to some extent to the concept of poverty graduation approaches which has been implemented in the inclusive and smooth economic growth context. Based on UNDP and World Bank’s economic analysis, Cambodia economic growth contracted by -3 percent in 2020 and the poverty rate gets double. Having realized downward impacts, the baseline survey has been conducted to measure its impact on households, study the impacts of the government’s cash transfer program, and simultaneously analyze poverty profile which all of these are key criteria to select project participants and design poverty graduation interventions.

# During this period, the project completed key major activities of the output 1 and kick off the activities in the output 2 as the followings:

# Output 1: Institutional and management arrangements, and analytical tools are in place to deliver a graduation based social protection pilot. This output is almost completed.

# 1.1 Design of the RCT & scheme design, & selection of localities

# Randomized Control Trial (RCT) protocol was finalized in March 2021. Even so, it is treated to be a living document which should improve from time to time as fit since the Covid 19 has changed socioeconomic development in the project’s target areas. Its contamination effects will be reviewed, analyzed, and assessed in addition with other contamination sources. This is to ensure the validity of the RCT, especially measuring project treatment effects.  Please refers to attachment in Annex: 10.9.

# In addition to the RCT protocol, project’s result log frame (indicators) and assumption/hypothesis on impacts causing from graduation approach to poverty (income, consumption, and household welfare) was produced. This provides concrete result chains for impact monitoring and evaluation.

  - Design of pilot instruments & operating arrangements

# Project Operation Manual was finalized in February 2021. The same as the RCT Protocol it has been revised from time to time as fit and will update to meet the changing situation and enable the project to flexibly implement its activities. Please refers to attachment in Annex: 10.9.

  - Set-up of management arrangements & institutional structures

# Via an email sent on 11 March 2021, the project sought the approval from the project board on the work-plan and budget 2021 and 2022. As per the project team’s request, the project board, composing of the Co-Chairs and members, endorsed the workplan and budget. Please refers to attachment for the minute (Annex: 10.6).

# Virtual training about GBSP’s poverty graduation approaches (operation manual) and RCT via Zoom was conducted with 30 participants on 11 May 2021. Government officials, project partners and local implementers attended this important training so that they can fully understand key concepts and the project design. As the project is moving, more practical training will be provided so that they will contribute more and more to the project implementation and to replicate in the future.

  - Design of the local area economic survey

The concept note was drafted, and the consultant is formulating an analytical tool and develop a questionnaire.  It will be rolled out in Q4 2021.

  - Design and contracting/ setup of specialized components

- LPIGs was already endorsed and supported by the Provincial Administrations and recently by district/commune administrations. The formal announcement of LPIGs will be done soon after communes/villages are assigned into treatment and control groups. By doing so, the roles of local authorities can be clearly identified and define the level of engagement and support.

- The Letter of Agreement with MoSVY was done on 31 March 2021. Through this partnership, the project can use the ministry’s system to transfer cash to its treatment groups. The ministry will build the capacity of local authorities to check and verify the names of the project beneficiaries, register or onboard them onto the digital cash transfer system, and support them to withdraw cash as per the project’s schedule.  The ministry has developed the cash transfer operation manual for GBSP and are recruiting staff members to carry out project activities.

- WVI has recruiting staff members and already deployed them into the project target areas. Since coming on board, the local team has worked with local authorities to inform about the project and discuss about cooperation. The meeting with district and communication administrations was held via zoom on 20 May 2021. This meeting resulted in the commitments of the local authorities to support and involve in the project implementation. At same time, the local team has been collecting socioeconomic data which are useful to design graduation courses mixing livelihood capacity enhancing, life skill training and financial inclusion.

- Four thermometers and automatic disinfection machines were purchased and distributed to two provincial halls and two district halls. The contribution aims to help protect and prevent the project team and local stakeholders from the infection of the Covid 19. The administrations highly appreciated the donation from the project, especially Russian Trust Fund, as the equipment is provided at the right time.

Output 2: Delivery of a graduation-based pilot social protection programme with 3,000 extreme poor household participants (with 2,400 households receiving assets and/or cash transfers and assigning into control group), with randomized selection. The second output as plan is now starting.

2.1. Analyze data from the baseline survey and select those meeting criteria to be project participants, and conduce random assignment (treatment and control groups)

- Nuppun Research Consulting was commissioned by UNDP to conduct data collection for the project. Since onboarding from April and up to the end of June 2021, Nuppun completed the interview with almost 3,000 households in the two target districts. The data is being reviewed and cleaned by Nuppun’s quality control team and UNDP’s economist/statistician.

# 3. PROJECT RISKS

# The incident of 20 February 2021 has caused the large scale of virus transmission and infection in the country. During this reported period, 500 new positive cases per day have been confirmed in both rural and urban areas.  Covid 19 has been the issue of specific spots/areas, then most communities, and now to individual households. Therefore, the probability of getting virus infection is high for each individual so this causes stress/trauma to some project personnel and disrupt the project implementation.

# Despite most of the works can be virtually done, the quality of works can be minimized to some extent. Without face to face or physical interaction, the relationship between the project team and local stakeholders as well as project beneficiaries are skeptical as they do not know each other much and feel lack of trust.

# Facing such challenges, the project has increased precautionary measures and worked closely with project partners to develop a crisis plan to ensure that the project can roll out in this serious pandemic context and address barriers in order to optimize work quality. One of the priority actions is to encourage all staff personnel to get vaccinated, follow the government’s precautionary measures, comply with the workplace’s safety protocol, and importantly prepare for emergency response at the household level.

# 4. LESSONS LEARNT

- Cambodia has economically suffered from this crisis. The country economy has been directly affected through the contraction of global demands, especially its key export sectors like tourism, entertainment and hospitality, garment/footwear/textile, real estate/construction, and loss of remittance through migration. To return Cambodia economy to the pre-crisis stage, it is not a silo matter but requires the alignment and dependence with/on global economies, international trade, and regional supply chains. As such, Covid-19 is a driving catalyst which reverses the current development trajectory as it adds more vulnerability to the poor and pull back those just above the line to fall back into poverty.

- Considering the vulnerability and multiple impacts causing by Covid-19, the project demonstrates its relevance, technical soundness, and practicality to tackle those issues. Including these aspects into the project strategy and implementation, it can potentially relief the deprivation of households, strengthening livelihood capacity and exponentially boost local economic outputs.

- Implementing poverty graduation activities in the pandemic context is becoming more challenged and complicated. With the virus are present in the project fields, local project team and beneficiaries have the probability of virus infection and can contribute to virus transmission. Moreover, market and value chains have been sluggish due to income decline and the decrease of purchasing power so many businesses and products have not been operated or demanded. Agriculture or food related products, medicines and basic need products have been worked very well since people have stored foods and medicines in accordance to the risk perception or situation. Due to the slowdown of industrial/service sectors in urban areas and neighboring countries, Cambodia laborers have returned to their hometown and worked in agriculture sector. Meanwhile the school has been closed, children has stayed at home and need cares from elders. The dynamic changes have shaped the new livelihood system which the project should explore to come up right strategies which can assist poor households to cope with current vulnerability and plan for the upcoming future business/production/employment opportunities once the country/the world can safely reopen or return to normal. Because of this new development landscape and in accordance with the RCT protocol, an individual survey will be conducted to capture this change and analyze new opportunities to invest the project resource which can return optimum benefits to project beneficiaries and their communities.

- Conducting data collection during the pandemic is a good lesson learned which the project finds useful to share publicly. Knowing that Covid 19 is already present in some villages and will widespread quickly, the project decides to recruit local resource people having some or much experience on interview or survey to be its enumerators. To get these potential groups, the project has worked closely with local authorities and Provincial Departments of Planning to search and identify them. Once they are identified and agreed to be enumerators, the project learning from FAO’s survey experience during the 2nd wave outbreak, has adopted a three-pronged approach: 1). Intensive remote training which requires enumerators to attend two weeks training, 2). On-the job training (three rounds of interview assessment and feedback/improvement is provided soon after each interview) so only well performed and meeting requirements are recruited to interview in the later stages, and 3). Ongoing coaching which enumerators can seek immediate supports from their supervisors. With the balance of recruited enumerators and the scope of work in addition with the strict compliance and follow of health safety measures, the interview of almost 3,000 households is timely completed and with the zero risk of virus infection/transmission.

# 5. FUTURE PLANS

# To contribute to the government and stakeholders to return its economy to the pre-crisis and make it resilient, the project has been accelerating its activities at the ground, mainly output 2.

# For the next half year, the project plans to complete the following activities:

2.1. Analyze data from the baseline survey and select those meeting criteria to be project participants, and conduct random assignment (treatment and control groups)

The data of the household survey will be cleaned and ready for analysis such as power calculation, random sampling, and cluster assignment. 2,400 households will be selected and assigned into treatment and control group by August 2021.

2.2. Conduce a local economic assessment survey

The project is working with the consultant to complete the economic tool and questionnaire, and work with WVI to train enumerators. The economy survey will carry out in Q4 2021.

2.3. Work with asset groups to identify, select and transfer assets (ownerships)

The project team and WVI has gathered secondary data and studies about value chains and livelihoods of the poor. The findings and successful interventions by other projects are used to design the project’s poverty graduation pathway. At the same, this is used to validate asset options defined in the project document and provide more viable and suitable options for the project beneficiaries. The works will be completed by Q3 2021.

2.4. Provide on-going trainings and technical assistance to asset/cash transfer groups

The project team and WVI are working to identify income generating opportunities in the project target areas and procedure to consult with the project beneficiaries. WVI is working with local authorities to define available resources/services which can use to support the project beneficiaries, i.e., extension service, skill training, access to public services. This activity will start from Q4 2021 to Q4 2022.

2.5. Transfer cash to asset and transfer groups monthly

The project team and MoSVY are working together to develop cash transfer procedure and system and identify stakeholders involving in the process. The Cash Operation Manual with all aspects, including complaint handling mechanism is being drafted. Onboarding project beneficiaries into the ministry’s cash transfer system will be done by Q3 2021 and cash transfer will be carried from Q4 2021 to Q3 2022.

2.6. Provide literacy training/financial inclusion to both treatment groups

The project team and WVI, with the support from local authorities, is identifying saving facilities in the local areas. Experiences from WVI’s previous projects are gathered and used to design financial training and promote saving in those facilities or with financial institutions.

The project team will work with MoSVY to explore more options which can transfer cash to project beneficiaries and at the same time, provide them a bank account which they can keep their deposit or saving. This will be a long-term strategy for the project and the ministry to design a friendly financial scheme for the poor.

# 2.7. Provide behavior change communication (BCC) to both treatment groups

# BCC guide was produced by the project consultant and shared to WVI and MoSVY teams. Dring Q3 2021, training will be provided to local staff members and the refreshment will be done based on the need and their performance. As plan, BCC will be applied to change/promote positive behaviors in livelihood/income generation, life skills and financial management. BCC will be done from Q4 2021 to Q4 2022.

# 6. PARTNERSHIPS

# Below are the key partners that have been engaged during the start-up of the project.

| # Key Partners | # Areas of Partnership |
| --- | --- |
| # National Social Protection Council, Minister of Economy and Finance | # The partnership aims to get graduation approaches adopted in the National Social Protection Policy Framework and scale up nationwide. Through this project, it needs to demonstrate practicality of deliverability/implementation arrangement and returns on investment, mainly poverty reduction (number of households graduating from poverty and local GDP/economic outputs). |
| # Ministry of Interior, National Committee for Sub-National Democratic Development | # This partnership aims to set up the project implementation structure at local levels and build capacity of SNAs through direct participation and leadership in the project implementation. Roles and functions between ministries and SNAs will be identified, reviewed and assessed in order to build an integrated system which synchronizes operations and enable smooth cooperation which different multiple supports/interventions can be carried out at the same time or in a well aligned complementary manner. |
| # Ministry of Planning | # This partnership aims to reinforce UNDP’s support for MoP on ID poor program through previous projects and during Covid-19 while make use of this program to identify project beneficiaries. The project expects that it can contribute to improve the system. In addition, it also aims to complement the ministry’s on-going works on Local GDP assessment. The project can contribute to the design and formulation of local economic survey tools and economic models. |
| # Ministry of Social Affairs, Veterans and Youth Rehabilitation | # The partnership aims to make use of the existing cash transfer system, which is already set up by MoSAVY, especially a new arrangement which is established to transfer cash to poor households during Covid-19. This also intends to upgrade and strengthen the ministry’s financial system which result in promoting trust, use of the system, and effective public service delivery. |
| # Ministry of Agriculture, Forestry and Fishery | # The partnership with MAFF is critical as the project targets poor households depending on agriculture to earn their living. The project aims to capitalize technical knowledge, local resource people and extension system to improve the project beneficiaries’ farming productivity and manage on-farm risks. |
| # FAO | # FAO has substantial agriculture development experience, noticeably also asset transfer to rural farmers. Partnership with FAO can provide technical assistance on improving farming productivity vis a vis access to knowhow on asset transfer arrangement. |
| # World Vision International | # Practical experience on graduation projects is needed and vital to factor in the project implementation as it is new to Cambodia. WVI has local offices in the project target areas and capable field operation team which can set up a local ecosystem by mobilizing, engaging, and facilitating all stakeholders. The partnership aims to implement the first round of ICT trial. |
| # Wing | # Wing is a commercial bank having expertise on online money transfer. Wing makes business and transaction so much easier with trust and smoothly. Its fin-tech system provides multiple options to subscribers or users which transaction can be done online, and swift from e-cash to cash through its nationwide branches and local kiosks. Partnership with Wing has two main purposes: 1) to transfer money timely as plan and 2) to set up financial records of project beneficiaries as parts of making them financially inclusive with cost efficiency. |

# 7. PARTNERSHIP WITH THE RUSSIAN FEDERATION

# The Russian Federation has significant roles in this project for both financing and strategic guidance as project donor. Representatives from the Embassy of Russia in Phnom Penh are invited to be project board members to oversight and review/approve the project work-plan and budget.

# The project team has closely worked with them during the project implementation and oversight activities. Progress reports were shared and submitted as per requirement to a focal person.

# 8. COMMUNICATION AND VISIBILITY

# The project communication strategy was formulated to raise the visibility of the project and the Trust Fund, engage focal people and representatives in project activities, as well as create specific events to highlight the achievement of RTF in cooperation with UNDP. https://www.kh.undp.org/content/cambodia/en/home/projects/graduation-based-social-protection.html

# So far, the project webpage was created to inform public about the project and at the same time the active role of RTF in development assistance for Cambodia. National and Sub-National Stakeholders were informed and aware of RTF via the project communication materials and project team. At grassroot level, with the aim to raise RTF visibility, thermometers were purchased and distributed to local authorities which RTF logos were sticked.

# 9. FINANCIAL MANAGEMENT

# Table1: Funding Contribution Overview 2020-2021

| # Allocated Resources | # Committed fund (Prodoc) | # Committed fund (Revise, BRV-G03) | # Actual Fund Receive | # Fund to be Received |
| --- | --- | --- | --- | --- |
| # • TRAC-00012: |  |  |  |  |
| # 2019 (TRAC2) | # 40,389.55 | # 40,389.55 | # 40,389.55 |  |
| # 2020-2021(TRAC1) | # 140,000.00 | # 502,228.20 | # 502,228.20 | # - |
| # 2022-2023 (TRAC1) | # 619,610.45 | # 287,382.25 |  | # 287,382.25 |
| # Total TRAC-00012 | # 800,000.00 | # 830,000.00 | # 542,617.75 | # 287,382.25 |
| # • Russian-TFD-00206: |  |  |  |  |
| # 2020-2021 | # 400,000.00 | # 400,000.00 | # 400,000.00 |  |
| # 2022-2023 | # 600,000.00 | # 600,000.00 |  | # 600,000.00 |
| # Total Russian TFD-00206 | # 1,000,000.00 | # 1,000,000.00 | # 400,000.00 | # 600,000.00 |
| # Funding Gap | # 500,000.00 | # 1,317,101.90 | # - | # 1,317,101.90 |
| # Total Funding Gap | # 500,000.00 | # 1,317,101.90 | # - | # 1,317,101.90 |
| # Total Project Resource | # 2,300,000.00 | # 3,147,101.90 | # 942,617.75 | # 2,204,484.15 |

| # Table 2: Funding balance up-to-date (24 Dec 2019-30 June 2021) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Allocated Resources | Actual Fund Receive | Expenses/Fixed Asset/POs/NEX advance |  |  |  |  |  |  | Balance | Delivery rate (%) |
|  |  | 2019 CDR | 2020 CDR | Expenses Jan-June 2021 | Depreciation Fixed Asset (up-todate) | Undepreciation Fixed Asset | PO Commitment | Total |  |  |
| • TRAC1-04000: 2019-2021 | 502,228.20 | - | 86,228.20 | 117,208.26 |  |  | 19,310.00 | 222,746.46 | 279,481.74 | 44% |
| • TRAC2-04010: 2019-2021 | 40,389.55 | 9,871.55 |  |  | 3,602.82 | 26,915.18 |  | 40,389.55 | - | 100% |
| • Russian-TFD-00206: 2019-2020 | 400,000.00 | - | 35.63 | 33,318.50 | - |  | 57,169.00 | 90,523.13 | 309,476.87 | 23% |
| Total | 942,617.75 | 9,871.55 | 86,263.83 | 150,526.76 | 3,602.82 | 26,915.18 | 76,479.00 | 353,659.14 | 588,958.61 | 38% |

# Table 3: Cumulative Expenses Jan-June 2021

| EXPECTED OUTPUT AND RESULT INDICATORS | Jan-June 2021 |  |  |  |
| --- | --- | --- | --- | --- |
|  | Approved budget (BRV-G03) | Expenses Jan-June 2021 | Total Expenses | Delivery rate (%) |
| Output 1: Institutional and management arrangements, and analytical tools are in place to deliver a graduation-based social protection pilot (which is nationally affordable and capable, of being scaled-up) | 266,889.76 | 84,699.91 | 84,699.91 | 32% |
| Output 2: Delivery of a pilot graduation-based social protection programme with 2,400 extreme poor household participants (with 1,600 households receiving assets and/or cash transfers), with randomized | 813,014.54 | 32,542.62 | 32,542.62 | 4% |
| Output 3: Carry-out a follow-on graduation trial, of similar size and shape (but more efficiently), to ensure future RGC deliverability |  |  | - | 0% |
| Output 4: Review and analysis of experiment and follow on round completed |  |  | - | 0% |
| Project Management and Technical Support (Act5) | 79,700.00 | 30,816.19 | 30,816.19 | 39% |
| A - Total Activities cost | 1,159,604.30 | 148,058.72 | 148,058.72 | 13% |
| B- GMS (8%) | 60,768.35 | 2,468.04 | 2,468.04 | 4% |
| Total Budget (A)+(B) | 1,220,372.65 | 150,526.76 | 150,526.76 | 12% |

# In addition to the budget summary table please attach a Combined Delivery Report as an annex.

# Submitted by Reathmana Leang, Project Management Specialist _______

# Cleared by Mao Meas, Programme Analyst (CO Quality Assurance) _________

# Cleared by Rany Pen, A-RR_________         (CO Official)

# Date_______________

# Recommended length of the report – up to 15 pages (exclusive of the annexes)

# 10. ANNEXES

# 10.1 Project performance data

# Indicator disaggregated by gender when applicable can be organized in a table form following the results framework format:

| Expected outputs | Output indicators | Data source | Baseline |  | Value for the previous year if different from baseline | Target for the reported year | Actual value for the reported year |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year |  |  |  |
| Output 1: Institutional and management arrangements, and analytical tools are in place to deliver a graduation based social protection pilot | Constituting the project board | Minute | 1 meeting | 2020 | 1 meeting | 1 meeting | 1 meeting |
|  | Key project strategic documents | 2 documents | 2 | 2020 | 2 | 2 | 2 |
|  | Partnership with specialized facilities | 3 Partnerships | 3 | 2020 | 2 | 2 | 2 |
|  | Monitoring tool (baseline survey) | 1 Survey | 1 | 2021 | 1 | 1 | 1 |
|  | local economic assessment tool (survey) | 1 Survey | 1 | 2021 | 1 | 1 | 1 |
|  | Selection of project participants | RCT document & field works | Around 3,000 poor households | 2021 | 3,000 | 2,400 | 2,400 |
| Activities |  |  |  |  | Results |  |  |
| - Design of the RCT & scheme design, & selection of localities - Design of pilot instruments & operating arrangements - Set-up of management arrangements & institutional structures - Design of the local area economic survey - Design and contracting/ setup of specialized components - Selection of (2,400) treatment and control group participants, at the specified locations |  |  |  |  | - RCT was completed. - Project operation manual was completed - The project board was constituted. The project board was approved Workplan and Budget 2021-22 in 31 March 2021 - The concept note was drafted and consulted with the consultant. It will be rolled out in Q4 2021 - Three agreements were successfully made with partners/service providers: - CSO Grant Agreement with WVI was made in 2020. The workplan and budget 2021-22 were reviewed and updated to include the changes causing from the Covid 19 and the recommendations of the first project board meeting - Letter of Agreement was signed with MoSVY. MoSVY will use its system to transfer cash to treatment groups in the project’s target areas and build the capacity of the SNAs on this function - ToR of Local Project Implementing Groups were endorsed and supported by Provincial, District and Commune Administrations - Project locations were identified through the poverty analysis. Two districts which the project selected to be its target have the common characteristics of the country poverty profile, mainly Tonle Sap and highland/plateau regions. |  |  |
| Output 2: Delivery of a graduation-based pilot social protection programme with 3,000 extreme poor household participants (with 2,000 households receiving assets and/or cash transfers), with randomized selection | 2.1. Allocation of participants to RCT group | RCT document | 3 groups (asset, cash, Nil) | 2021 | 3 trial groups | 3 trial groups | 3 trial groups |
|  | 2.2. Delivery of the local economy survey | Economic survey | 1 survey | 2021 | 1 survey | 1 survey | 1 survey |
|  | 2.3. Asset selection & distribution to the graduation (treatment) group | Report from a partnered NGO & field works | 800 households | 2021 | 800 households | 800 households | 800 households |
|  | 2.4. Deliver initial & follow-up training to graduation group households, & ongoing TA | Report from a partnered NGO & field works | 1,600 households | 2021-22 | 1,600 households | 1,600 households | 1,600 households |
|  | 2.5. Deliver cash transfer to the treatment (graduation) and first control (cash transfer) group | Reports from MoSVY & field works | 1,600 households | 2021-22 | 1,600 households | 1,600 households | 1,600 households |
|  | 2.6. Ensure financial inclusion of extreme poor participants | Reports from a partnered NGO & field works | 1,600 households | 2021-22 | 1,600 households | 1,600 households | 1,600 households |
|  | 2.7. Provide behavioral change communications (BCC) to graduation group HHs. | Reports from a partnered NGO & field works | 1,600 households | 2021-22 | 1,600 households | 1,600 households | 1,600 households |
| Activities |  |  |  |  | Results |  |  |
| 2.1. Analyze data from the baseline survey and select those meeting criteria to be project participants, and conduce random assignment (treatment and control groups) 2.2. Conduce a local economic assessment survey 2.3. Work with asset groups to identify, select and transfer assets (ownerships) 2.4. Provide on-going trainings and technical assistance to asset/cash transfer groups 2.5. Transfer cash to asset and transfer groups monthly 2.6. Provide literacy training/financial inclusion to both treatment groups 2.7. Provide behavior change communication to both treatment groups |  |  |  |  | 2.1. Nuppun Research Consulting was commissioned to collect data for UNDP. The interview with 3,000 households was completed. 2.2. The local economic survey will be rolled out in Q4 2021 once the graduation activities start. 2.3. WVI is working with local authorities, community volunteers and stakeholders to establish working groups/sub-working groups to discuss and consult with selected households about their livelihood strategies. At the onset, WVI is raising awareness about the project to those local stakeholders, seek their view about cooperation plan, and discuss about their support/contribution. Soon after the households are selected and assigned by the consultants, the working groups above will work with them on asset selection, distribution and use as well as investment plan 2.4. WVI’s local project team is collecting livelihood information/ value chains/stakeholder mapping which can use to develop livelihood capacity improvement plan and formulate training curriculum. 2.5. MoSVY has already drafted the cash operation manual and informed about the cash transfer activities to local authorities. 2.6. To be rolled out in Q4 2021 2.7. To be rolled out in Q4 2021 |  |  |

# 10.2 Updated Risk Log

# Refer to project risk log in the project document and include it here to show any updates and mitigation measures

| # | Description | Date Identified | Type | Impact & Probability | Counter-measures / Mngt response | Owner | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Outbreak of Covid-19 as a global pandemic and large-scale impacts in Cambodia (three incidents) | Third wave happened on 20 February 2021 and last up to now | Economic and health threats | Contract the economic growth (-3% in 2020) and double poverty rate. The third wave has caused lockdown in many areas and curfew. Many places in the country is being infected. There is an average of 500 cases per day. Two project target areas have been affected by the virus. Some villages have been locked down. P = 5 I = 5 | Update the poverty profile Assess its impacts on the project localities Tailor graduation approaches to meet livelihood changes and address vulnerability (adjust graduation support package if the situation is serious while keeping the original concept) Adapt flexible governing and implementing arrangement which most works will be done via virtual meeting, telecommunication, and remote/distance monitoring Develop and implement access to real time information for all project aspects which enable everyone (UNDP team) have comprehensive knowledge and update. This enables task division among the project team to split roles and take turn to conduct field visit and monitor project activities implemented by project partners/contractors | Management Program analyst Project manager Local implementers (partners and service providers) | December 2020 | Infection has widespread to many places, so the pandemic affects economy, health system and possibly society. The death toll keeps rising so may cause household crisis (orphans, loss of productive assets, decrease of income generating capacity etc.) Covid 19 is moving into micro level (households) which is hard to control since there are many distributing spots. Good news is that the effort and commitment of the government to get people vaccinated. Hopefully, the speed of vaccination and the available vaccine stock will enable the government to get herd immunity in a short time. The herd immunity will lower risk for individuals and support the country to reopen with safety, especially to prevent large scale outbreak in the future. |

# 10.3 Combined Delivery Report for the reported year

# Please refers to excel sheet.

# 10.4 Media coverage report with links to main publications

# UNDP’s website informs about the project and its progress:

# https://www.kh.undp.org/content/cambodia/en/home/projects/graduation-based-social-protection.html

# 10.5 Statistical annex on main results since the project start (attached separately in Excel)

# 10.6 Minutes of the online meeting

# 10.7 Annual Work Plan for the coming year (draft, if not approved yet)

| # Project # Outputs | # Project # activities | # 2021 |  |  |  | # Key deliverables |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | # Q1 | # Q2 | # Q3 | # Q4 |  |
| # Output 1: Institutional and management arrangements, and analytical tools are in place to deliver a graduation based social protection pilot | - Design of the RCT & scheme design, & selection of localities | # x |  |  |  | # RCT was completed and endorsed. # Tuek Phos District of Kampong Chnang and Rovieng District of Phrea Vihear were selected to be the project’ target areas. |
|  | - Design of pilot instruments & operating arrangements | # x |  |  |  | # POM was completed. |
|  | - Set-up of management arrangements & institutional structures | # x |  |  |  | # An offline meeting was convened, via email, to review and approve Project Annual Workplan and Budget 2021-22. |
|  | - Design of the local area economic survey | # x |  |  |  | # The concept note and tool are completed and endorsed. |
|  | - Design and contracting/ setup of specialized components | # x |  |  |  | # CSO agreement with WVI was completed # Letter of Agreement with MoSVY was completed # ToR of LPIGs was endorsed by SNAs |
|  | - Selection of (2,400) treatment and control group participants, at the specified |  | # x |  |  | # Data collection, interview with nearly 3,000 ID Poor households, was completed. Data is being cleaned so soon will be analyzed. - Random sampling and random assignment will be done- to select 2,400 out of 3,000 households to be project participants |
| Output 2: # Delivery of a graduation-based pilot social protection programme with 3,000 extreme poor household participants (with 2,000 households receiving assets and/or cash transfers), with randomized selection | 2.1. Conduct random assignment (treatment and control groups) |  |  | # x |  | # Based on village randomization, project participants are assigned into treatment and control groups. |
|  | 2.2. Conduce a local economic assessment survey |  |  |  | # x | # Local economic survey is started. A partnered NGO collects data through the questionnaire provided by an expert. |
|  | 2.3. Work with asset groups to identity, select and transfer assets (ownerships) |  |  | # x |  | # A partnered NGO consults and work with project participants on asset menu, pre-capacity building, and asset transfer with ownership. |
|  | 2.4. Provide on-going trainings and technical assistance to asset/cash transfer groups |  |  |  | # x | # A partnered NGO provide livelihood trainings, especially asset management and accumulation vis a vis investment. As well, technical assistance is provided to them |
|  | 2.5. Transfer cash to asset and transfer groups monthly |  |  |  | # x | # Cash is transferred on a monthly basis as consumption stipend to both treatment group as well as one off lump sum to cash group |
|  | 2.6. Provide literacy training/financial inclusion to both treatment groups |  |  |  | # x | # Financial literacy training is delivered # Saving in households or via other means are promoted. |
|  | 2.7. Provide behaviour change communication to both treatment groups |  |  |  | # x | # Life skill trainings (nutrition, WASH, health, ects) are delivered to both treatment groups # Frequent visit is carried out by field officers and experts based on the needs of individual participants to mentor and coach them. It expects to set up a vision and commitment for poverty graduation |

# 10.8 Evaluation reports if available

# 10.9 - … Any other annexes can be added if deemed necessary by the project team. Examples may include personal stories of project beneficiaries, outline of main projects supported under the area-based programmes, etc.

- Randomized Control Trial Protocol

- Project Operation Manual