## 2021
Actual project cost for 2021 - "Supporting business in banking and digital transformation"
Achieved results for 2021 | Descriptions | Actual charges
|  | Governor amount | UNDP amount | Total in USD
Output 2: As part of the support for the digital transformation of the bank, there were: 1) an international tender was held to select an expert to draw up technical specifications for the implementation of a Mobile and WEB platform for the bank; 2) an international tender was held to select an IT company to develop a Mobile and WEB platform for the bank, during which the need for an additional budget for this event was revealed. | Project charges for hiring process | 1133.64 |  | 1133.64
0
| Operational charges |  |  | 0
| 7% GMS | 79.36 |  | 79.36
Total Output 2 |  | 1213 |  | 1213
Output 3: Project management - Development of technical specifications for hiring experts and companies, reporting, budget management, coordination of signed contracts. | Project management | 24081.31 |  | 24081.31
| Operational charges | 2957.11 |  | 2957.11
| 7% GMS | 1892.68 |  | 1892.68
Total Project Management |  | 28931.1 |  | 28931.1
Co-financing from the Government of Turkmenistan excluding interest for general management |  | 27038.42 |  | 27038.42
Co-financing from the Government of Turkmenistan including interest for general management |  | 30144.1 |  | 30144.1
GMS 7% |  | 1892.68 |  | 1892.68
| Project costs | 30144.1 |  | 30144.1
Prepared: Jennet Annaberdiyeva, Manager of the Project
Approved: Akmyrat Danatarov, Programme specialist

## 2022
Actual project cost for 2022 - "Supporting business in banking and digital transformation"
Achieved results for 2022 | Descriptions | Actual charges
|  | Governor amount | UNDP amount | Total in USD
Output 2: As part of the support for the digital transformation of the bank, the implementation of the NetInfo Mobile and WEB platform for the bank was started. STAGE 1 - PROJECT INITIATION - was completed. A draft time plan to identify Milestones and Major Deliverables, throughout the project was provided, and subject to finalization after the Full Screen design Documents have been agreed. A mockup as a visual design draft presented to client, in order to lock down the look and feel of the design approach. A draft copy of this document was produced after the initial Kick off meeting with the Bank. It provides a clear description of the Business Requirements, that have been discussed. This document was finalised after the Onsite Analysis workshops which had been completed by Netinfo and the Bank. Thus, ensuring all the Banks requirements are captured and listed fully. This acceptance was given strictly in terms of the design; style, colours, layout and positioning of components. The correct labels, fields and business flows will be updated after the final SDD's. (2nd stage). The clear description of the Business Requirements was presented, for all stakeholders involved in the project to have a clear picture of these requirements and to be satisfied that it meets the needs and expectations of the Bank. | Stage 1 of the contract was completed, accepted and paid | 98042 |  | 98042
0
| Operational charges | 3134.63 |  | 3134.63
| 7% GMS | 7082.37 |  | 7082.37
Total Output 2 |  | 108259 |  | 108259
Output 3: Project management - Development of technical specifications for hiring experts and companies, reporting, budget management, coordination of signed contracts. | Project management | 16213.8 |  | 16213.8
| Operational charges | 1248.31 |  | 1248.31
| 7% GMS | 1222.3 |  | 1222.3
Total Project Management |  | 18684.41 |  | 18684.41
Co-financing from the Government of Turkmenistan excluding interest for general management |  | 17462.11 |  | 17462.11
Co-financing from the Government of Turkmenistan including interest for general management |  | 126943.41 |  | 126943.41
GMS 7% |  | 1222.3 |  | 1222.3
| Project costs | 126943.41 |  | 126943.41
Prepared: Jennet Annaberdiyeva, Manager of the Project
Approved: Akmyrat Danatarov, Programme specialist