## IC
PROCUREMENT ACTION PLAN 2021, Year 1 (Burkina Faso AMP Project)
THE PLAN COVERS ALL PROCUREMENT FOR CONSULTANCY, GOODS AND CONTRACTUAL SERVICES THAT TAKE PLACE OR START IN YEAR 1 AND MAY COVER THE ENTIRE PROJECT LIFETIME (e.g. services that start in Year 1 but occur annually)
SINCE PROJECT IS FULL NIM, THE PROCUREMENT PROCEDURES OF THE REA-REF ARE USED
ACTIVITIES THAT DO NOT START IN YEAR 1 ARE NOT CAPTURED HERE. THIS OPROCUREMENT PLAN WILL BE UPDATED BY PMU DURING YEAR 1
| Project Name | Project Number | Type of Supply | Description of goods, services or works |  |  | Estimated Total Price (USD)* | Available Budget (USD)* | Estimated Completion of Activity** (dd/mm/yyyy) | Responsible Staff | Requisition Docs*** Ready |  | Solicitation Process |  |  |  | Issue of TOR and PN |  |  |  |  | Evaluation of Offers | Committee Review/Approval Timeline***** (dd/mm/yyyy)
[5 empty] | Quantity / Duration | Estimated Unit Price |  |  |  |  | Date (dd/mm/yyyy) | By | Local or International | Issue Date (dd/mm/yyyy) | Deadline for Receipt (dd/mm/yyyy) | Duration (Days) | Date (dd/mm/yyyy) | ABER's Web | AMP Regional Project | Local Paper | Int.Paper /Media | (Single Stage, Two Stage or Two Stage with Combined Weights ) | CAP Chairperson Comments Date | ACP Sub. Date | CPO's approval Date***
1 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.1: Two International Consultants will support the establishment of the multi-stakeholders platform providing support services in terms of set-up and management frameworks (by laws, strategies, lobbying, delivery models etc. for the platform) | 14 | 700 | 9800 | 9800 | 2021-12-31 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
2 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.2: 1 International Senior consultant with expertise on minigrids delivery models to draft minigrid strategy | 12 | 700 | 8400 | 8400 | 2022-12-31 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
3 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.3: 1 international expert on capacity-building | 20 | 700 | 0 | 0 | 31/21/2022 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
4 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.4: 1 international expert on quality standards | 20 | 700 | 14000 | 14000 | 2022-12-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
5 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.5: 1 international expert on certification and job-tasks/curriculum development for solar minigrid related jobs | 10 | 700 | 7000 | 7000 | 2022-12-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | No | No | Single Stage | 7 days after evaluation report | N/A | N/A
6 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.1: Local Expert to support operations of the multi-stakeholders platform in the national dialogue an other activities. | 20 | 300 | 6000 | 6000 | 2022-06-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | No | Single Stage | 7 days after evaluation report | N/A | N/A
7 | Burkina Faso AMP Chlid Project | 6510 | Individual Contractor | Output 1.2: 1 local expert will provide support to international consultant for drafting and dissemination of minigrid strategy | 20 | 300 | 6000 | 6000 | 2022-12-31 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | 2021-09-20 | 2022-03-14 | 60 | 2021-09-20 | Yes | No | Yes | No | Single Stage | 7 days after evaluation report | N/A | N/A
8 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.3: Local capacity-building and training expert to provide support to interenational consultant for capacity-building trainings | 20 | 300 | 6000 | 6000 | 31/11/2022 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | No | Single Stage | 7 days after evaluation report | N/A | N/A
9 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.4: 1 local quality standards expert to support interenational expert | 20 | 300 | 6000 | 6000 | 2022-11-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | No | Single Stage | 7 days after evaluation report | N/A | N/A
10 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 1.5: Local consultant with expertise on certification will support international consultant | 10 | 300 | 3000 | 3000 | 2022-11-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | No | Single Stage | 7 days after evaluation report | N/A | N/A
11 | Burkina Faso AMP Chlid Project | 6511 | Individual Contractor | Output 1.3: Contractor to provide material & goods relalted to capacity buidling of r institutional stakeholders | 6 | 1000 | 6000 | 6000 | 2022-12-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
12 | Burkina Faso AMP Chlid Project | 6512 | Individual Contractor | Output 1.4: Contractor for material & goods related to quality standards such as tools and software to conduct test | 4 | 1250 | 5000 | 5000 | 2022-12-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
13 | Burkina Faso AMP Chlid Project | 6513 | Individual Contractor | Output 1.5: Contractor for material & goods such as educational material for certification scheme | 4 | 2000 | 8000 | 8000 | 2022-12-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
14 | Burkina Faso AMP Chlid Project | 6514 | Individual Contractor | Output 1.1: Contractor for supplies for trainings and multi-stakeholder platform meetings | 2 | 750 | 1500 | 1500 | 2022-12-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
15 | Burkina Faso AMP Chlid Project | 6515 | Individual Contractor | Output 1.1: Contractor for trainings on delivery models | 1 | 1500 | 1500 | 1500 | 2021-01-30 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
16 | Burkina Faso AMP Chlid Project | 6516 | Individual Contractor | Output 1.2: Contractor for training on minigrid strategy (venue, etc.) | 2 | 2500 | 5000 | 5000 | 2022-12-31 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
17 | Burkina Faso AMP Chlid Project | 6517 | Individual Contractor | Output 1.3: Contractor for venue and related servies for training of institutional stakeholders around tariffs, procuremenrt/tenders, etc. | 1 | 2500 | 2500 | 2500 | 2022-12-31 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
18 | Burkina Faso AMP Chlid Project | 6518 | Individual Contractor | Output 1.4: Contractor for venue and related servies for training on quality-standards | 1 | 2500 | 2500 | 2500 | 2021-12-31 | Mr. Bah F. M . Saho, ECREEE |  | ECREEE PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
19 | Burkina Faso AMP Chlid Project | 6519 | Individual Contractor | Output 1.5: Contractor for venue and related servies for training on certification scheme | 1 | 2500 | 2500 | 2500 | 2021-11-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
20 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 2.1: International Legal Expert to support prepartion of tenders and contracting on the pilot projects | 12 | 1000 | 12000 | 12000 | 2024-11-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | No | Single Stage | 7 days after evaluation report | N/A | N/A
21 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 2.1: International safeguards expert | 1 | 7020 | 7020 | 7020 | 2022-12-31 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | Yes | No | Single Stage | 7 days after evaluation report | N/A | N/A
22 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 2.2: International Minigrid Business Model and Finance Expert for trainings on winning tender bidders, COOPEL and private sector actors around developing and implementing innovative business models and cost-reduction levers | 14 | 700 | 9800 | 9800 | 2023-11-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | No | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
23 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 2.3: International Consultant to support the growth of the national industry association | 12 | 700 | 8400 | 8400 | 2023-06-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
24 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 2.2: Local consultant with expertise capacity international consultant tasked with building capacity of stakeholders from COOPELs and private sector association on innovative business models, finances anbd cost-reduction levers | 20 | 300 | 6000 | 6000 | 2023-06-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
25 | Burkina Faso AMP Chlid Project | 6510 | Individual Consultant | Output 2.3: Local consultant to support operations of industry association | 24 | 300 | 7200 | 7200 | 2022-06-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
26 |  | 6511 | Individual Contractor | Output 2.3: Contractor for supplies for industry association | 1 | 6000 | 6000 | 6000 | 2021-11-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
27 | Burkina Faso AMP Chlid Project | 6512 | Individual Contractor | Output 2.3: A firm will be hired to develop/design communication collaterals for the association such as website, deck, etc. for the industry association | 1 | 4000 | 4000 | 4000 | 2022-12-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
28 | Burkina Faso AMP Chlid Project | 6513 | Individual Contractor | Output 3.1: Sub-contract to for capacity-building of domestic financial sector on minigrids business and financing model | 3 | 5000 | 15000 | 15000 | 2023-12-30 | Janine Ouattara, UNCDF |  | UNCDF'S ADMIN. UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
29 | Burkina Faso AMP Chlid Project | 6514 | Individual Contractor | Output 3.2: Sub-contract for market assessment exercices | 1 | 30000 | 30000 | 30000 | 2022-12-30 | Janine Ouattara, UNCDF |  | UNCDF'S ADMIN. UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
30 | Burkina Faso AMP Chlid Project | 6516 | Individual Contractor | Output 3.4: Sub-contract for feasibility studies | 1 | 40000 | 40000 | 40000 | 2023-12-30 | Janine Ouattara, UNCDF |  | UNCDF'S ADMIN. UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
31 | Burkina Faso AMP Chlid Project | 6517 | Individual Consultant | Output 4.1: International consultant digital strategy expert | 10 | 700 | 7000 | 7000 | 2021-12-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
32 | Burkina Faso AMP Chlid Project | 6519 | Individual Contractor | Output 4.1: Local consultant with expertise in digital strategy to support international consultant | 10 | 300 | 3000 | 3000 | 2021-12-31 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
33 | Burkina Faso AMP Chlid Project | 6519 | Individual Contractor | Output 4.2: Contractor for Minigrids Digital Platform | 1 | 55000 | 55000 | 55000 | 2023-12-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | International | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
34 | Burkina Faso AMP Chlid Project | 6520 | Individual Contractor | Output 4.3: Local consultant for QAMF | 10 | 300 | 3000 | 3000 | 2021-12-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
35 | Burkina Faso AMP Chlid Project | 6521 | Individual Contractor | Output 4.4: Inception workshop | 1 | 4000 | 4000 | 4000 | 2021-10-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
36 | Burkina Faso AMP Chlid Project | 6521 | Individual Contractor | Output 4.4: Materials and goods for M&E | 1 | 55000 | 55000 | 55000 | 2022-12-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
37 | Burkina Faso AMP Chlid Project | 6522 | Individual Consultant | Output 4.3: International QAM and MRV expert in minigrids | 10 | 700 | 7000 | 7000 | 2024-11-30 | Ismael Nacoulma, ABER | 2021-09-20 | ABER PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | No | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
38 | Burkina Faso AMP Chlid Project | 6523 | Individual Contractor | Output 4.1: Workshop on digita strategy | 1 | 2500 | 2500 | 2500 | 2022-11-30 | Ismael Nacoulma, ABER | 2021-09-20 | ABER PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | No | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
39 | Burkina Faso AMP Chlid Project | 6524 | Individual Contractor | Output 4.6: Contractor for CoP / Knowledge Networks/industry association | 1 | 10000 | 10000 | 10000 | 2025-12-30 | Ismael Nacoulma, ABER |  | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
40 | Burkina Faso AMP Chlid Project | 6526 | Individual Contractor | PMU: Project Manager | 48 | 1710 | 82080 | 82080 | 2025-09-30 | Ismael Nacoulma, ABER | 2021-08-30 | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
41 | Burkina Faso AMP Chlid Project | 6527 | Individual Contractor | PMU: Driver | 48 | 338 | 16224 | 16224 | 2025-09-30 | Ismael Nacoulma, ABER | 2021-08-31 | ABER PROCUREMENT UNIT | Local | [5 empty] | No |  |  | Single Stage | 7 days after evaluation report | N/A | N/A
42 | Burkina Faso AMP Chlid Project | 6528 | Individual Contractor | PMU: Local Finance and admin Expert | 48 | 1383 | 66384 | 66384 | 2025-09-30 | Ismael Nacoulma, ABER | 2021-09-01 | ABER PROCUREMENT UNIT | International | 2021-09-20 | 2021-10-11 | 21 | 2021-09-20 | Yes | No | No | Yes | Single Stage | 7 days after evaluation report | N/A | N/A
557308
*Please only insert the numbers without comma (,); full stop (.);or curency (USD or US$). The cell format is maintained automatically.
** This date should be the estimated contract signature date.
***Technical Specifications, TOR, SOW
****This should be the date on which final approval is given by RR for cases reviewed by CAP and by ACP Chair for cases reviewed by ACP.
*****Please take into consideration the standard 'CAP Committee Meetings Schedule' while setting these dates.
Formulas:
Issue of TOR and PN = [Issue Date (dd/mm/yyyy)]

## Ref_IC
Type | Evaluation of Proposals | Type of Supply | Y/N | Local/Int
RFQ | Two stage | Individual Consultant | Yes | Local
RFP | Two stage with Combined Weights | Individual Contractor | No | International
| National Shopper (<N2.5million) | Goods | restricted tendering |  | Single Stage based on lowest price | RFQ
| National Competitive bidding (>N2.5million) | goods | Two Stage |  |  | RFQ