| 2024 Annual report | Project title: Support to effective, resilient and inclusive governance systems for health. |
| --- | --- |

| Project title: | Support to effective, resilient and inclusive governance systems for health. |
| --- | --- |
| Project ID: | 00119180 |
| Implementing partner: | Ministry of Health of the Republic of Uzbekistan |
| Period covered in this report: | January 1st – December 31, 2024 |
| Date of the last Project Board meeting: | December 26, 2024. |

Project Performance

- Please list the annual targets for the reporting year as set out in the project document and/or AWP:

Number of PLHIV (men and women) and receiving ARV treatment- 45 700 (80% of estimated number of PLHIV); End year achievement- 44233 (97% of the target) Percentage of people on ART among all people living with HIV at the end of the reporting period (men 50%, women 50%); End year result: men 49%, women 51%. (99% of the target) Percentage of people living with HIV on ART who have suppressed viral loads-83%. End year results-81% (97.5% of the target) Number of medical institutions supported with equipment and medical supplies for the prevention, diagnosis and treatment of COVID-19, target-28 facilities. End year results- 30 facilities. (107% of the target)

# Please specify below what has been the progress towards the above indicated targets during the reporting period:

Immediate project objective. The project's primary objective is to assist the Uzbekistan government in enhancing the national healthcare system's capabilities for successfully executing comprehensive programs and efficiently managing the supply chain. This initiative will significantly contribute to establishing a robust system for providing medicines and medical supplies to the general population, including key groups. It aims to increase access to preventive services, high-quality medications, and health products essential for diagnosing and treating HIV, COVID-19, tuberculosis, non-communicable diseases, and addressing other societal health needs. Additionally, the project focuses on building the Ministry of Health's capacity, as well as that of the Service for Sanitary and Epidemiological Welfare and Public Health, the Republican AIDS Center, the Republican Specialized Scientific and Practical Medical Center for Phthisiology and Pulmonology, and other healthcare institutions, in planning and managing the health system effectively. Aligned with the United Nations Sustainable Development Cooperation Framework 2021-2025, specifically Outcome 4, the UNDP's "Support to effective, resilient and inclusive governance systems for health" project aims to ensure that by 2025, vulnerable populations will have improved access to gender-sensitive, quality health, education, and social services. This project supports the Uzbekistan government in developing robust, sustainable, and inclusive health management systems, minimizing the impact of COVID-19 on successful health program implementation. To realize this project outcome, the focus is on bolstering Uzbekistan's healthcare system in two key areas: (1) proficient supply chain management and the rollout of inclusive programs targeting HIV, tuberculosis, and other diseases; (2) an effective response to the COVID-19 pandemic, mitigating its adverse effects on health project and program implementation. Introduction Since 2005, the United Nations Development Programme (UNDP) has been a cornerstone in implementing Uzbekistan's national health strategies, focusing on the fight against HIV, tuberculosis, and COVID-19 in collaboration with the Ministry of Health. Serving as the principal recipient and procurement partner of the Global Fund, UNDP has managed resources amounting to approximately 150 million USD, ensuring efficiency, transparency, and impact. Recent achievements underline the importance of these efforts. In 2022–2023, strategic bulk procurement resulted in a savings of 1.1 million USD, reinforcing the value of efficient resource utilization. Key successes during this period included national procurement of antiretroviral drugs, emergency deliveries of medical supplies during the COVID-19 pandemic, and the development of digital tools to enhance the effectiveness of healthcare service delivery. These advancements have significantly contributed to building a more resilient and responsive healthcare system in Uzbekistan, laying the groundwork for the achievements of 2024. In 2024, the Health Project played a pivotal role in advancing Uzbekistan’s National HIV response by strengthening the provision of treatment services, championing the digitalization of HIV-related healthcare, and ensuring efficient and effective procurement support. These efforts have not only enhanced patient management and service delivery but also laid the groundwork for systemic reforms in supply chain management across the health sector. As a trusted partner of the Government of Uzbekistan and the Global Fund, the Health Project continues to demonstrate its commitment to improving healthcare outcomes and addressing emerging challenges in the fight against HIV/AIDS. Achievements in 2024 The Health Project achieved significant milestones in 2024, directly contributing to the improvement of the National HIV response. Under UNDP’s leadership, digital solutions were scaled up within the Republican AIDS Service, ensuring seamless patient management and improved accessibility to essential HIV-related services. These systems have streamlined critical operations such as patient registration, pharmaceutical tracking, and data collection, enhancing service delivery efficiency across the country. The Project ensured uninterrupted antiretroviral (ARV) treatment for 44,033 people living with HIV (PLHIV), including 23,350 men and 20,683 women, while providing HIV prevention services to 49,335 individuals from vulnerable groups. These efforts directly align with global targets to end AIDS by 2030. Furthermore, the Health Project advocated for and supported a transformative shift in HIV care funding, enabling the government to allocate 93% of ARV treatment resources from domestic budgets, with only 7% contributed by the Global Fund. Procurement supply and management Since the inception of the program, UNDP has played a pivotal role in the procurement of pharmaceuticals and medical equipment for the Republican AIDS Center (RAC) and the Ministry of Health in Uzbekistan. UNDP’s expertise spans the entire procurement process, from managing international tenders to overseeing customs clearance, transportation, certification, insurance, and distribution. In 2024, the project achieved a significant milestone by successfully procuring and distributing antiretroviral (ARV) medications for 44,233 patients. The adoption of a "best value for money" approach not only enhanced cost-effectiveness but also generated savings that were reinvested into additional ARV procurement. This strategy allowed for the expansion of Uzbekistan’s ARV program and contributed to a notable reduction in the overall cost of Antiretroviral Therapy (ART) regimens by 10–12%. All planned procurement activities for pharmaceuticals and medical supplies—developed in close collaboration with partners and tailored to their specific needs—were successfully completed on schedule. The project’s meticulous procurement management ensured a consistent supply of medications, effectively eliminating the risks of stock shortages or overstocking. This uninterrupted supply chain is a major achievement of the project, underlining UNDP’s commitment to sustaining HIV/AIDS treatment in Uzbekistan. This success was further bolstered by the implementation of an advanced online warehouse management system. This system represents a groundbreaking development, enabling precise forecasting of medication needs, comprehensive inventory monitoring, and the generation of sophisticated analytical insights to guide decision-making. The total budget for the procurement of pharmaceuticals and medical supplies amounted to 2,096,370 USD, of which 64% (1,344,005 USD) was allocated to ARV medications, while 36% (752,365 USD) covered other medical supplies. By ensuring efficient procurement, resource optimization, and innovative systems, UNDP has not only strengthened Uzbekistan’s national HIV response but also set a benchmark for sustainable and effective healthcare supply chain management. Driving Digital Transformation The Project spearheaded the digitalization of HIV services in Uzbekistan through the introduction of three core systems: the HIV Electronic System (HIV ES), the Integrated Bio-Behavioral Survey (e-IBBS), and the Management Information System (MIS). These innovative tools have revolutionized service delivery, enhanced data accuracy, and optimized resource utilization, positioning Uzbekistan as a leader in healthcare technology within Central Asia. In 2024, the HIV ES system was further expanded and integrated into the operations of an additional 465 facilities across the country, including over 400 KIZ cabinets (cabinet of infectious diseases monitoring and treatment) and 65 interregional laboratories. This expansion extended digital surveillance to the primary healthcare level, ensuring a more comprehensive and inclusive approach to HIV care. The HIV ES system has significantly reduced patient registration times, enabling real-time updates immediately following immunoblot results. It has automated pharmaceutical management, with mobile scanners and remote data loggers ensuring efficient tracking and optimal storage conditions. Furthermore, integration with external government databases, such as those of the Ministry of Health and Ministry of Internal Affairs, has simplified patient access to care, extending services to foreign citizens and stateless individuals. System Features and Capabilities The implemented systems boast several advanced features that support their efficiency and effectiveness: - Unified Electronic Patient Card: A centralized patient data system that provides comprehensive and accessible information for all users. - Client Registration by PIN: Each client is assigned a unique identification number, reducing errors and ensuring personalized care. - Issuance of Health Certificates and Reports with QR-Code Verification: Patients gain secure and convenient access to approved digital medical documents. - Integration and Generation of Reporting Documentation: National and international journals, registers, and questionnaires are automatically created and updated, streamlining record-keeping and reporting processes. - Tri-lingual Support: The system is available in three languages, enhancing accessibility for users from various regions and professional backgrounds. - Analytical Capabilities and Multi-level Monitoring: Built-in data analysis tools facilitate trend monitoring, program effectiveness evaluation, and epidemiological risk assessment. - Real-Time Data Access: The web-based platform ensures information is updated in real time, enabling prompt responses to changing epidemiological conditions. - High Data Security: Access is secured through VPN channels and two-factor authentication, protecting sensitive data from unauthorized breaches. - Full Electronic Document Workflow: The transition to electronic documents has minimized human errors and increased the efficiency of information exchange. - Integration with External Databases: Synchronization with government systems ensures coordination and consistency across management levels. Meanwhile, the e-IBBS platform has markedly improved the quality of bio-behavioral data collection, supporting the development of targeted HIV prevention strategies. This system has reduced reliance on international experts and printed materials, achieving bi-annual cost savings of approximately 100,000 USD. By enhancing both cost-efficiency and sustainability, the platform ensures that resources are allocated more effectively to address HIV prevention needs. Through these advancements, the Project has not only enhanced the efficiency of Uzbekistan’s HIV response but also established a sustainable framework for long-term health outcomes. The integration of digital tools into primary healthcare services underscores a commitment to making high-quality HIV care accessible to all, strengthening both national and regional capacities in public health. Innovations in Supply Chain Management In 2024, the Project initiated critical discussions on comprehensive reforms to Uzbekistan’s health supply chain management system. Recognizing the importance of a robust and transparent supply chain for improved healthcare outcomes, the Health Project is actively conceptualizing and developing a proposal for these reforms. This proposal will be shared with potential donors in the first quarter of 2025, marking a significant step toward a modernized and sustainable health supply chain infrastructure. Introduction of the e-Polyclinic Mobile Application To further improve patient management, the Project is in the process of developing a mobile application, e-Polyclinic, which will extend its benefits beyond Uzbekistan’s borders. The application will address several pressing challenges in HIV service delivery, including managing human resource constraints, preventing lost to follow-up (LTFU), and supporting migrant patients. The app will serve as an innovative tool for improving patient care. Automated reminders will ensure timely visits for medication collection, reducing the risk of LTFU and the associated development of resistant HIV strains. Migrant patients, who currently represent a vulnerable population, will benefit from remote communication capabilities to report health status and maintain contact with healthcare providers. Additionally, the app will facilitate the registration of new HIV cases diagnosed abroad, ensuring early linkage to national treatment programs. By streamlining service delivery, the e-Polyclinic will alleviate the workload on healthcare providers while improving patient-centered care through remote consultations and real-time health status updates. This initiative aligns with the Project’s overarching goals of strengthening the ARV supply and management system while improving health outcomes for patients. Overcoming Challenges While the Project achieved remarkable progress in 2024, several challenges were encountered. These included limited technical capacity among healthcare staff, infrastructure gaps in remote regions, and resistance to transitioning from paper-based processes to digital workflows. The integration of digital systems with external government databases required substantial effort to resolve compatibility issues and establish data-sharing protocols. To address these challenges, the Project provided extensive training to over 2,000 specialists, upgraded infrastructure, and employed targeted advocacy to build stakeholder buy-in. Sustained investments in capacity development and system maintenance remain critical to ensuring the long-term success and scalability of these initiatives. Conclusion and Future Outlook In 2024, the Health Project solidified its reputation as a driving force in Uzbekistan’s healthcare transformation. Through innovative digital solutions, efficient procurement practices, and strategic advocacy, the Project has strengthened the national HIV response, improved patient management, and contributed to the sustainability of healthcare systems. Looking ahead, the Project is committed to expanding its impact by advancing supply chain reforms and launching the e-Polyclinic app, which promises to set a new standard for patient care. These efforts underscore the importance of leveraging technology and innovation to achieve equitable, high-quality healthcare for all. By maintaining its focus on sustainability, inclusivity, and patient-centered approaches, the Health Project continues to pave the way toward ending AIDS in Uzbekistan and achieving broader health outcomes in alignment with national and global goals.

- RRF Implementation / Quality Log (to be completed by Project Managers)

Output 1: The national capacity of the health care system of the Republic of Uzbekistan is strengthened for effective supply chain management.

Start date of the Activity 01/01/2024						End Date of the Activity: 31/12/2024

| Quality criteria (i.e how/with what indicators the quality of the activity result will be measured?) Planned Results | Quality method (what method will be used for this criteria?) Means of Verification | # Actual progress made/ User perspective # Progress |
| --- | --- | --- |
| 4 quarter |  |  |
| By the end of 2024, 45700 PLHIV (80%) are enrolled and receiving ARV treatment among all people living with HIV at the end of the reporting period (men 50%, women 50%) | National statistics and Republican AIDS centre annual report. Nominator-number of people enrolled in HIV care Denominator- number of people living with HIV in Uzbekistan | Status-substantially achieved. Project procured and made available ARV medicines for the 50 000 patients. 97% or 44233 of the targeted number of PLHIV received treatment in 2024 making 79% coverage of the estimated number of PLHIVs. Out of which men-53% and women 47%. |
| By the end of 2023, 83% of people living with HIV on ART who have suppressed viral loads (the actual values for this indicator will be reported in gender disaggregated format men 50%, women 50%) | National statistics and Republican AIDS centre annual report. Nominator-number of people who are on ART and have suppressed viral load. Denominator- Number of people who are on ARV treatment | Status-substantially achieved. 28 200/81% of 34 816 of tested HIV patients receiving the ART have suppressed viral load. Women-51% (14583) Men -49% (13617) |

Output 2:The national capacity of the health care system of the Republic of Uzbekistan is strengthened to effectively counter the spread of the COVID-19 pandemic.

Start date of the Activity 01/01/2024			End Date of the Activity: 31/12/2024

| Quality criteria (i.e how/with what indicators the quality of the activity result will be measured?) Planned Results | Quality method (what method will be used for this criteria?) Means of Verification | # Actual progress made/ User perspective # Progress |
| --- | --- | --- |
| 4 quarter |  |  |
| By the end of 2024, 44835 vulnerable populations in need received COVID-19 diagnostic services (the actual values for this indicator will be reported in gender disaggregated format) | RAC, Institute’s for TB, physiatry and pulmonology report. | No longer applicable. Considering that since 2022, the incidence of coronavirus cases has diminished to isolated occurrences, the procurement of test systems and routine monitoring of the number of individuals tested for COVID-19 have been discontinued by the Ministry of Health. Consequently, data on the number of individuals tested are no longer aggregated at the national level and cannot be presented. |
| By the end of 2024, 28 medical institutions supported with equipment and medical supplies for the prevention, diagnosis and treatment of COVID-19 | RAC report | Status-overachieved. Over the course of 2024 30 medical institutions have been supported with equipment and medical supplies for the prevention and diagnosis and treatment of COVID 19. Specifically, the following equipment has been procured Boboxes-10, X-ray-9, GenExpert-6, Distillator-4, Incubator-5. Thus, this target has been overachieved. |

- Issues

- Please specify the issues that were raised during the reporting period to the attention of the Project Board. Describe the steps taken to solve those (Management response in ATLAS).

In response to the Government’s new requirement of processing and affixing digital code on every product arriving to Uzbekistan, the Project has been diligently collaborating with ARV suppliers to ensure that all medicines entering Uzbekistan are registered and fully comply with the new requirement of affixed digital coding, known as Asl Belgisi. Applying for and acquiring digital coding for imported pharmaceuticals is a complex and lengthy endeavor, demanding rigorous scrutiny and compliance with stringent regulatory standards. Each medication necessitates individual evaluation and documentation, encompassing aspects like composition, efficacy, and manufacturing adherence. The ensuing application process, encompassing extensive data collation on clinical efficacy and safety, often extends the timeline due to the thorough review conducted by health authorities. Post-approval, the assigned digital codes facilitate critical tracking and monitoring of the medication's distribution and usage. This essential yet protracted procedure, while vital for ensuring public health safety, can result in significant delays in making new medications accessible within the country, thereby impacting healthcare delivery and patient care.

- Project risks

a) Please provide update on any changes with regard to the above indicated risks (e.g. risk occurred; no change and etc.). Specify the responses taken for each of those.

1) Category-reputational, Impact/probability-intermediate

Sub-standard capacity of national partners may lead to incorrect quantification of medicines thereby jeopardizing implementation of treatment plan.

Risk mitigation measures that were undertaken by the Project:

The risk of incorrect quantification of medicines due to sub-standard capacity of national partners has been effectively mitigated through the full development and rollout of the HIV Electronic System (HIV ES) platform by the project. This advanced digital platform enables real-time monitoring of medicine usage, ensuring accurate data collection and streamlined processes for the quantification of required medications. The HIV ES system provides comprehensive tools to forecast medication needs, track stock levels, and manage distribution with precision. By reducing reliance on manual calculations and minimizing the risk of errors, the platform strengthens the planning and implementation of treatment plans. This robust system has significantly de-escalated the identified risk, ensuring uninterrupted treatment for people living with HIV and contributing to the overall efficiency of the healthcare system.

2) Category-financial, 2.5 sub-category-Delivery Risk level-substantial Impact/probability-intermediate

Delays in disbursement of funds or installment as per Agreement may result in delayed procurement of ARVs and lead to stock out of latter thereby jeopardizing the health outcomes of patients on ART.

Risk mitigation measures that were undertaken by the Project:

Terms and conditions of the global ARV supply agreement between UNDP and UNICEF has been further refined, with the support of UNDP HIST team, to ensure that in force majeure situations ARV is supplied on the basis of request whereas payment can be made when funds are available.

In addition, UNDP on the quarterly basis notified GF on current cash balance status and fund needs. This was done to ensure that GF is updated on emerging needs of ARV programme for funding.

- Lessons learned

As the project enters 2025, its priorities are focused on addressing regulatory challenges, fostering partnerships, enhancing advocacy efforts, and expanding access to HIV treatment. By aligning these priorities with strategic planning and structured stakeholder collaboration, the project is well-positioned to achieve impactful results in the coming year.

1. Strategic Procurement Planning to Overcome Regulatory Challenges
The acquisition of pharmaceuticals, particularly those requiring digital coding, presents a complex and time-consuming process that demands strict adherence to regulatory standards and comprehensive scrutiny. To address these challenges effectively, the project will organize procurement timelines for 2025 to ensure smooth execution. By aligning procurement schedules with anticipated regulatory requirements, the project aims to eliminate bottlenecks and guarantee the timely availability of essential medications.

2. Strengthening Partnerships to Broaden Advocacy
The year ahead will focus on fostering strategic partnerships among international, national, and local stakeholders. Establishing and executing initiatives to enhance their capabilities is critical to broadening the scope of advocacy efforts. By equipping partners with the skills and resources they need, the project will amplify collective efforts to improve HIV service availability and ensure sustainable progress.

3. Structured Stakeholder Engagement for Unified Action
Entering 2025, the project recognizes the importance of structured stakeholder engagement with clearly defined roles and responsibilities. This approach ensures that all partners work cohesively toward the shared goal of enhancing the availability and accessibility of HIV services. A well-coordinated framework will maximize the impact of collective actions, benefiting individuals requiring treatment and support.

4. Enhancing Patient Experience through Expanded ARV Options
The procurement and distribution of diverse antiretroviral (ARV) medication options remain a cornerstone of the project’s 2025 strategy. By focusing on providing medications that minimize side effects, the project aims to improve patient satisfaction and motivation for adherence to treatment. This patient-centered approach not only enhances individual well-being but also contributes to achieving long-term, successful treatment outcomes.

5. Supporting Adherence through Community-Based Initiatives
The timely procurement and delivery of ARVs, while vital, must be complemented by robust community-based support systems. In 2025, the project will continue to emphasize the crucial role of non-governmental organizations (NGOs) and AIDS services in forming and managing self-support groups. These groups provide peer encouragement and accountability, which are instrumental in maintaining adherence to ARV regimens. By creating a supportive environment, these initiatives empower individuals to stay on treatment and improve overall program outcomes.

6. Preparing for Future Opportunities
As the project transitions into 2025, its focus on collaboration, efficiency, and patient-centered care will remain central to its efforts. By strategically addressing procurement challenges, strengthening stakeholder relationships, and advancing community-based initiatives, the project aims to sustain progress in the fight against HIV/AIDS while adapting to emerging opportunities and challenges.

# Prepared by: Akmal Makhamatov, Project Manager

# Cleared by: FP, Sherzodbek Sharipov, Programme Analyst on Effective and Inclusive Institutions and Service Delivery for All

# Approved by: Kamila Mukhamedkhanova, Head of Cluster

Checklist to be completed by the Programme focal point:

To fill this checklist, programme focal point has to visit the Executive Snapshot/Programme & Project Management > Overview of Awards > Select Award ID > Click on “View the Progress Report for this Award.”

☒Yes No Quality Log/Progress report is updated in ATLAS

☒Yes No Risk logs is updated in ATLAS by Project Manager and management response is updated by Programme Officer / programme focal point

☒Yes No Issues logs is updated in ATLAS

☒Yes No Lessons learned are reflected appropriately

Yes☒No N/A Budget revision is approved (if applicable)

If for some boxes, “No” was checked, please provide justification:

The budget revision is under the discussion with the National partner.