| Project title: Promoting conservation, sustainable utilization and fair and equitable benefit-sharing from Lesotho's Medicinal Plants for improved livelihoods |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | Implementing Partner (GEF Executing Entity): Ministry of Defense, National Security and Environment (MDNSE) |  |  | Execution Modality: Assisted National Implementation Modality (NIM) |
| Contributing Outcome (UNSDCF/CPD, RPD, GPD): Outcome 2-All people living in Lesotho enjoy improved food and nutrition security, with transformed national food systems, benefiting from natural resources and green growth that is risk informed and climate resilient. |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  | UNDP Gender Marker: GEN2 |  |
| Quantum Award ID: 00119573 |  |  | Quantum Project ID: 00116027 |  |
| UNDP PIMS ID number: 5819 |  |  | GEF Project ID number: 9799 |  |
| LPAC meeting date: TBD |  |  |  |  |
| Last possible date to submit to GEF: November 2023 |  |  |  |  |
| Latest possible CEO endorsement date: December 2023 |  |  |  |  |
| Project duration in months: 60 |  |  |  |  |
| Planned start date: March 2024 |  |  | Planned completion date: February 2029 |  |
| Expected date of Mid-Term Review (MTR) submission to the GEF: May 2026 |  |  | Expected date of Terminal evaluation (TE) submission to the GEF: September 2028 |  |
| Expected Operational Closure Date: November 2029 |  |  | Expected Financial Closure Date: May 2030 |  |
| Brief project description: The objective to strengthen national and local capacities to implement the Nagoya Protocol on Access and Benefit Sharing (ABS) with a focus on traditional knowledge on medicinal plants in Lesotho and the potential for bioprospecting. This will be achieved through three interrelated components: 1) strengthened institutional capacity and regulatory framework to support the implementation of the Nagoya Protocol on ABS; 2) building capacities for bioprospecting and value-addition of genetic resources; and, 3) gender mainstreaming, knowledge management, and monitoring and evaluation. The project will deliver global environmental benefits using a participatory approach and ensuring the equitable distribution of benefits among men and women, with at least 19,531 people (9,489 men and 10,042 women) directly benefiting from the project at the local level. This will result in biodiversity conservation benefits over 373,886 hectares. The project will span 5 years with a total investment of $2,913,699 USD, which will be provided by the GEF. |  |  |  |  |
| Financing Plan |  |  |  |  |
| GEF Trust Fund grant |  |  | $2,913,699 |  |
| UNDP TRAC resources |  |  | $500,000 |  |
| Confirmed cash co-financing to be administered by UNDP |  |  | $500,000 |  |
| - Total Budget administered by UNDP |  |  | $3,413,699 |  |
| - Total confirmed co-financing to this project not administered by UNDP |  |  | $4,000,000 |  |
| - Grand-Total Project Financing (1)+(2) |  |  | $7,413,699 |  |
| Signatures: |  |  |  |  |
| Signature: |  | Agreed by Government Development Coordination Authority |  | Date/Month/Year: |
| Signature: |  | Agreed by Implementing Partner Ministry of Defense, National Security and Environment (MDNSE) |  | Date/Month/Year: |
| Signature: |  | Agreed by UNDP |  | Date/Month/Year: |

# Table of Contents

I.	Development Challenge	12

II.	Strategy	17

III.	Results and Partnerships	21

IV.	Project Management	23

V.	Project Results Framework	25

VI.	Monitoring and Evaluation (M&E) Plan	30

VII.	Governance and Management Arrangements	38

VIII.	Financial Planning and Management	49

IX.	Total Budget and Work Plan	53

X	Legal Context	57

XI.	Risk Management	57

Annex 1: GEF Budget Template	72

Annex 2: GEF execution support letter	73

Annex 3: Project map and Geospatial Coordinates of project sites	74

Annex 4: Multi Year Work Plan	75

Annex 5: UNDP Social and Environmental Screening Procedure (SESP)	76

Annex 6: UNDP Risk Register	77

Annex 7: Overview of Project Staff and Technical Consultancies	79

Annex 8: Stakeholder Engagement Plan	84

Annex 9: Environmental Social Management Framework (ESMF) and other SES frameworks/plans, if required	85

Annex 10: Gender Analysis and Gender Action Plan	86

Annex 11: Procurement Plan	87

Annex 12: Additional agreements	88

Annex 13: Signed LOA between UNDP and IP requesting UNDP Support Services (if required on exceptional basis and authorized by the GEF)	89

Annex 14: GEF CEO Endorsement/Approval	90

Annex 15: On-Granting Provisions Applicable to the Implementing Partner	91

Annex 16: Terms of Reference for Project Board and Project Team	92

Annex 17: GEF Core indicators	93

Annex 18: GEF Taxonomy	94

Annex 19: Results of the Partners Capacity Assessment Tool (PACT) and HACT Micro Assessment	100

A LIST OF ACRONYMS AND ABBREVIATIONS

| °C | Degrees Celsius |
| --- | --- |
| ABS | Access and Benefit-Sharing |
| AIS | Alien Invasive Species |
| AWP | Annual Work Plan |
| BMP | Biodiversity Management Plan |
| BPPS | Bureau of Policy and Programme Support |
| CBD | Convention on Biological Diversity |
| CBO | Community-based Organization |
| CCF | Community Conservation Forum |
| CITES | Convention on International Trade in Endangered Species of Wild Fauna and Flora |
| CSO | Civil Society Organization |
| DAC | Drakensberg Alpine Centre |
| DoE | Department of Environment |
| DPC | Direct Project Cost |
| DRRM | Department of Range Resources Management |
| DST | Department of Science and Technology |
| EIA | Environmental Impact Assessment |
| ERC | Evaluation Resource Center |
| ERMA | Environmental Resources Management Area |
| FAO | Food and Agriculture Organization |
| FSP | Full Size Project |
| GDI | Gender Development Index |
| GDP | Gross Domestic Product |
| GEB | Global Environmental Benefit |
| GEF | Global Environment Facility |
| GEFSEC | Global Environment Facility Secretariat |
| GoL | Government of Lesotho |
| ha | Hectares |
| HDI | Human Development Index |
| IAS | Invasive Alien Species |
| IEO | Independent Evaluation Office |
| IFAD | International Fund for Agricultural Development |
| IPRs | Intellectual Property Rights |
| ITPGRFA | International Treaty on Plant Genetic Resources for Food and Agriculture |
| IUCN | International Union for Conservation of Nature |
| ICMP | Integrated Catchment Management Plan |
| IWRM | Integrated Water Resources Management |
| KAP/B | Knowledge, Attitudes, Practices, and Behavior |
| km2 | Square kilometers |
| LCN | Lesotho Council of Non- Governmental Organizations |
| LDC | Least Developed Country |
| LRA | Lesotho Revenue Authority |
| M&E | Monitoring and Evaluation |
| MAB | Man and Biosphere Reserve |
| MAFS | Ministry of Agriculture and Food Security |
| masl | Meters Above Sea Level |
| MAT | Mutually Agreed Terms |
| MCST | Ministry of Communications, Science, and Technology |
| MEA | Multilateral Environment Agreement |
| MFAIR | Ministry of Foreign Affairs and International Relations |
| MFRSC | Ministry of Forestry, Range, and Soil Conservation |
| MGYSR | Ministry of Gender, Youth, Sports, and Recreation |
| MLCA | Ministry of Law and Constitutional Affairs |
| MLGCPA | Ministry of Local Government, Chieftainship, and Parliamentary Affairs |
| MoH | Ministry of Health |
| MOU | Memorandum of Understanding |
| MoW | Ministry of Water |
| MDNSE | Ministry of Tourism, Environment, and Culture |
| MTICM | Ministry of Trade and Industry, Cooperatives, and Marketing |
| MTR | Mid-Term Review |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NCA | National Competent Authority |
| NCE | Nature, Climate and Energy |
| NFP | National Focal Point |
| NGO | Non-Governmental Organization |
| NIM | National Implementation Modality |
| NP | Nagoya Protocol |
| NPD | National Project Director |
| NSDP | National Strategy for Development Planning |
| NUL | National University of Lesotho |
| OFP | Operational Focal Point |
| PA | Protected Area |
| PAC | Programme Advisory Committee |
| PIC | Prior Informed Consent |
| PIF | Project Identification Form |
| PIMS | Project Information Management System |
| PIR | Project Implementation Report |
| PMU | Project Management Unit |
| POPP | Programme and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| R&D | Research and Development |
| RMA | Resource Management Area |
| RTA | Regional Technical Advisor |
| SACU | Southern African Customs Union |
| SAP | Strategic Action Programme |
| SDG | Sustainable Development Goal |
| SGP | Small Grants Programme |
| SLM/W | Sustainable Land and Water Management |
| STAP | GEF Scientific Technical Advisory Panel |
| SSTrC | South-South and Triangular Cooperation |
| TBD | To Be Determined |
| TE | Terminal Evaluation |
| TK | Traditional Knowledge |
| TRAC | Target Resource Assignment from the Core |
| TRC | Transformation Resource Centre |
| TRIPS | Trade-Related Aspects of Intellectual Property Rights |
| UNSDCF | United Nations Sustainable Development Cooperation Framework |
| UNDP | United Nations Development Programme |
| UNEP | United Nations Environment Programme |
| UNESCO | United Nations Educational, Scientific, and Cultural Organization |
| USD | United States Dollars |
| WAMPP | Wool and Mohair Promotion Project |
| WIPO | World Intellectual Property Organization |

- Development Challenge

Environmental Context

- The Kingdom of Lesotho is a mountainous southern African country that is land-locked by the Republic of South Africa. The total land area of the Lesotho is 30,360 square kilometers (km2) and it has a population of approximately 2.23 million people, as estimated by the World Bank in 2017. Lesotho straddles the highest part of the Drakensberg escarpment between 1,500 and 3,482 meters above sea level (masl). The country is divided into four agroecological zones: the lowlands (1,500 to 1,800 masl), the foothills (1,800 to 2,200 masl), the mountains (2,200 to 3,000 masl), and the Senqu River Valley, which comprises the extension of the lowlands into the eastern mountains along the greater catchment of the Senqu River – an internationally-shared and economically important river system for the countries of Lesotho, South Africa, Namibia, and Botswana.

- Lesotho has a rich flora forming the largest part of the Drakensberg Alpine Centre (DAC) (Carbutt and Edwards, 2005), which is a globally recognized biodiversity hotspot in the Maluti-Drakensberg Mountains. Lesotho is also home to a system of unique wetlands (Drakensberg Afro-alpine Heathlands), which occur mostly in the eastern alpine areas, and are found nowhere else in the world. These wetlands support a network of unique high-altitude bogs and sponges that are key contributors to the water system of the country, playing a crucial role in hydrological cycles. The country’s unique ecosystems provide critical ecological infrastructure, and offer many goods and services such as food, medicinal plants, firewood, water, land, building materials, and scenery.

- Lesotho is home to about 82 species of mammals, 340 species of birds, 43 species of reptiles, 19 species of amphibians, 14 species of fish, 1,279 species of invertebrates, and 3,093 species of plants. Several of the species are globally significant and endemic to the country. These include the rare and endangered Maloti Lang’s crag lizard (Pseudocordylus langi), the ice rat (Otomys sloggetti), the umbraculate frog (Amietia vertebralis), the endangered Maloti minnow (Pseudobarbus quathlambae), the Sehlabathebe water lily (Aponegeton ranunculiflorus and the spiral aloe (Aloe polyphylla).

- There are approximately 355 plant species in Lesotho (including 23 exotic species) from eight pteridophyte and 76 angiosperm families that are used for various medicinal purposes. In addition, seven species of ferns are used for medicinal purposes, mostly to treat headaches, either through smoking the leaves or inhaling smoke from smouldering leaves. Most of the medicinal plants (287 species) are used to treat conditions in humans, with some age- and gender-specific usage (20 species are used specifically by women, three by men, and 29 for treating children). Some of the medicinal plants are used strictly for livestock (8 species), whereas others are used to treat both humans and animals. Medicinal plants can also be grouped based on the ailment treated, such as problems relating to digestion (84 species), respiration (67 species), fertility and reproduction (31 species), circulation (26 species), and skin and wounds (24 species). At least 50 species are used for magic and sorcery.

- Lesotho has four formally protected areas (PAs) that include the Sehlabathebe National Park – a United Nations Educational, Scientific, and Cultural Organization (UNESCO) Heritage Park (6,952 ha); the Tšehlanyane National Park (5,394 ha); the Bokong Nature Reserve (1,952 ha); and the Letšeng-la-Letsie Ramsar site (434 ha). Sehlabathebe National Park, together with the uKhahlamba Drakensberg Park in South Africa, forms a transboundary PA known as the Maloti-Drakensberg Park. This heritage site is a haven for many threatened and endemic species and is a rich repository of species of traditional medicinal value. The Tšehlanyane National Park and the Bokong Nature Reserve was designated as a Man and Biosphere Reserve (MABs) in 2021. Over and above the formally designated PAs, there are several areas that are either informally designated, or proposed for protection, in various parts of the country. These fall into the International Union for Conservation of Nature (IUCN) Categories II, III, and IV and are managed for different objectives, including for the economic and biodiversity functioning of the region, ecosystem protection and recreation, conservation of specific natural and cultural features, and for sustainable use of natural ecosystems.

Socio-economic Context

- Lesotho is a least developed country (LDC) whose development pathway is susceptible to multiple external and internal impacts. The country’s geo-political situation poses constraints in terms of diversification of foreign trade and foreign relations necessary for driving sustainable development. Increased environmental degradation (compounded by the impacts of climate change), population increase, economic under-development and poor rural land-use planning and management, also present significant challenges. Lesotho is classified as a lower-middle-income country with a per capita gross domestic product (GDP) of $1,141 USD. In recent times, Lesotho’s economic outlook has faced challenges arising from internal political instability and an extended period of slower growth in South Africa, which has led to a decline in Southern African Customs Union (SACU) revenue, creating serious liquidity challenges. Economic growth for the last three years averaged only 1.3 percent and growth is projected to recover modestly in the next three years. Unemployment remains high at 24 to 28 percent on average, and much higher (45 percent) among the youth; this is coupled with high inequality and poverty, which are highly skewed against women in particular.  To address its socio-economic development challenges, Lesotho needs new engines for economic growth, a more streamlined role for the state, and a dynamic private sector to help it seize opportunities to integrate the national economy with regional and global markets.

- Lesotho’s human development index (HDI) value for 2017 was 0.520, which puts the country in the low human development category, ranked at 159 out of 189 countries and territories. According to the 2015 UNDP National Human Development Report, the proportion of the population living in multi-dimensional poverty was estimated at 45.9 percent, with 56.6 percent living below the poverty line in 2015. The report further reveals with a gender development index (GDI) of 0.973, the human development status of women and men is not significantly different when considering life expectancy, schooling, and income, yet female deprivations seem high in terms of health. There are significant disparities in the spatial distribution of wealth, with more than 54 percent of the rural population considered poor, while the proportion of the urban population considered to be poor is significantly lower (3.2 percent).

- The economy of Lesotho is based on agriculture (crops and livestock), manufacturing, and mining, and depends heavily on inflows of workers’ remittances and receipts from SACU. About 70 to 80 percent of Lesotho’s people live in rural areas, and more than three-quarters of these are engaged in subsistence agriculture (rain-fed cereal production, with maize, wheat, sorghum, and barley and pulses being the primary crops) and extensive livestock grazing (sheep, goats, and cattle). The agricultural sector in Lesotho remains important to most households; 23.2 percent of the population in Lesotho was engaged in agriculture in 2014-2015, with 12.4 percent engaged in production for self-consumption. Most of these households own some agricultural land and/or keep some livestock. However, it is estimated that about 30 percent of rural households are landless, despite heavy reliance on agriculture-based livelihoods (e.g., one-third of rural females and two-thirds of rural males engage in some sort of agricultural work). Agriculture’s contribution to GDP, however, has been steadily declining from as much as 89% in the early 1960s, to 5.7% in 2016, with an average of about 24.6% in the intervening period. In 2012, cultivation of crops contributed only 2.3 percent and livestock-keeping 4.1 percent to GDP. Despite this clear decline in the contribution of the sector to GDP, agriculture remains an important source of livelihoods that employs a large number of rural workers.

- The flora of Lesotho provides food, energy, shelter, materials for handicrafts, and medicine for rural populations who depend on natural resources for their livelihoods. Medicinal plants are a fundamental component of Lesotho’s traditional healthcare system and are an affordable and accessible health resource available to local communities (many of whom cannot afford or access conventional alternatives). Although the use of medicinal plants in Lesotho is known to be widespread, and local herbalists and practitioners have valuable traditional knowledge (TK) about these plants, this is not well documented. The rate of harvesting of many medicinal plants for a growing, and largely unregulated, trade industry is believed to be unsustainable; this, together with the destruction of natural habitat, is threating the existence of many medicinal plant species, including those endemic to Lesotho.

- Despite the richness of its ecosystems and high species diversity, Lesotho has struggled to derive any sustained or significant benefits from its natural resources. The country’s weak enabling framework and limited capacity for implementing the Nagoya Protocol (NP) on Access and Benefit Sharing (ABS) – and other aspects of the Convention on Biological Diversity (CBD) – constrains the generation and equitable sharing of such benefits. Lesotho’s genetic resources also remain vulnerable to over-exploitation by both local and international users, as evident in the area of medicinal, aromatic, and ornamental plant species.

Policy, legal, and institutional context

- Lesotho’s Constitution (1993) recognizes the need for sustainable development by embracing the principles of environmental protection, sustainable natural resource use, and biodiversity conservation. Section 36 of the Constitution states that Lesotho shall adopt policies designed to protect and enhance the natural and cultural environment for the benefit of both present and future generations, and shall endeavour to ensure for all citizens a sound and safe environment adequate for their health and well-being.

- Lesotho is a signatory to six multilateral environment agreements (MEAs), including: the CBD; the International Treaty on Plant Genetic Resources for Food and Agriculture (ITPGRFA); and, the Agreement on Trade-Related Aspects of Intellectual Property Rights (TRIPS) – all of which emphasize the importance of safeguarding the rights of owners of genetic resources. The Nagoya Protocol on ABS, to which Lesotho became a party on February 10, 2015, is the only MEA that holistically addresses ABS and traditional knowledge (TK) associated with the use of genetic resources. While Lesotho demonstrated the desire for environmentally sustainable development by becoming a party to these MEAs, the country has limited capacity at the individual, institutional, and systemic levels to implement them.

- Lesotho lacks comprehensive national laws to facilitate comprehensive biodiversity protection and sustainable management of natural resources. Only three pieces of legislation directly address biodiversity conservation: the Historical Monuments, Relics, Fauna, and Flora Act of 1967 (as amended by Legal Notice No. 93 of 2004); the National Parks Act of 1975, the Managed Resource Areas Order of 1993, and a Biodiversity Bill was enacted in 2021. Certain aspects of ABS and traditional knowledge are addressed in some policy instruments and plans that call for conservation of biodiversity in support of sustainable development, but they are not specific to ABS and traditional knowledge. This means that they do not provide adequately for the kind of regulation needed for effective implementation of the Nagoya Protocol in Lesotho.

- Institutions that administer various regulatory frameworks relevant to conservation of genetic resources include: MDNSE; the Ministry of Forestry, Range, and Soil Conservation (MFRSC); the Ministry of Agriculture and Food Security (MAFS); the Ministry of Law and Constitutional Affairs (MLCA); the Ministry of Foreign Affairs and International Relations (MFAIR); the Ministry of Local Government, Chieftainship, and Parliamentary Affairs (MLGCPA); the Ministry of Health (MoH); the Ministry of Trade and Industry, Cooperatives, and Marketing (MTICM); the Lesotho Mounted Police Services; and the Lesotho Revenue Authority. Of these, only the Department of Environment (DoE) of MDNSE, specifically addresses access and benefit-sharing, and the DoE is also the national focal point (NFP) and national competent authority (NCA) for the purposes of the Nagoya Protocol. Currently, there are no institutions addressing issues related to traditional knowledge associated with the use of genetic resources.

- Currently, almost all of the lead institutions with responsibility for conservation of genetic resources (i.e. MDNSE-DoE, MFRSC, and MAFS) have inadequate technical expertise on genetic resources, ABS, and associated traditional knowledge; severe staff shortages; poor and/or no infrastructure; and inadequate financial resources to carry out their mandates effectively. In addition, research and development (R&D) of genetic resources, including medicinal plants, is incipient. Detailed information regarding the current legal and institutional framework is presented in Annex 22.

Threats to biodiversity

- Threats to biodiversity and natural resources (including medicinally important plants) in Lesotho are significant. The country is affected by severe land degradation over much of its area, and this is compounded by rugged topography, extreme climate, fragile soils, and multiple human-induced pressures. Land degradation has resulted in significant loss of vegetation cover with associated loss of biodiversity, increased soil erosion, decreased soil fertility, and a reduction in the extent of productive land. The significant decline in agricultural productivity has contributed to over-harvesting and over-exploitation of wild resources (including ethno-medicines), rising food insecurity and rural poverty, and escalating rural-urban migration leading to mushrooming of informal settlements around main towns. Other anthropogenic drivers of land degradation include inappropriate or weakly-adapted agricultural practices, overgrazing and overstocking of rangelands, and inappropriate location and unsustainable management of impacting activities such as construction works and mining. Poor range management practices have contributed to the spread of invasive alien species (IAS), which out-compete indigenous plants, especially grasses. Only 15 percent of households have access to electricity, and most people (especially in the rural and peri-urban areas), use biomass fuels in the form of trees and shrubs to meet their energy needs. Over-harvesting of limited sources of fuelwood depletes biodiversity, accelerates land degradation, and reduces the carbon sequestration capacity of the country’s landscapes.

- In recent years, the Basotho have turned biological resources into trade commodities, largely as medicinal remedies, to generate income and support livelihoods. Popular medicinal and aromatic plants are collected directly from the wild; harvesting practices are largely unsustainable, not only threatening target species, but also degrading habitats where these occur. Trade in Lesotho is largely unregulated (due to factors such as inadequate institutional and regulatory frameworks and weak capacity for law enforcement), with limited benefits accruing to communities, and limited monitoring for safety assurance of natural products.

- The development of effective conservation strategies for harvested species is constrained by a lack of knowledge and empirical data. Many species of plants, and the genetic resources derived from them, are being over-exploited to meet the increasing trade demand. There is, therefore, growing concern about the impacts of trade on the long-term survival of these species as this directly affects community livelihoods. Lesotho’s Fourth National Report to the CBD indicates that medicinal plants are being over-harvested for the commercial market, rather than for local use. The local usage of indigenous herbs has, however, intensified because of their assumed potency in managing HIV and associated conditions (HIV prevalence rate in Lesotho is 25% in the adult population), and because of their greater accessibility and affordability relative to conventional medication. There is an urgent need to understand the status of genetic resources in Lesotho, if they are to be protected and sustainably managed for equitable access and benefit sharing. Research is needed to understand: a) how many species are involved in the trade and what their conservation status is; b) how many Basotho men and women are involved in trading these resources; c) how much of the trade is contributing to improving livelihoods and the national economy; and d) to what extent the trade is fair to both providers and users.

- Lesotho is expected to experience a shift in temperature and precipitation patterns toward drier and hotter conditions as a result of climate change. Climate change projections suggest an increase in the annual mean temperature of approximately 1.0 degrees Celsius (°C) by 2030, 2.0°C by 2050, and 3.5°C by 2080; while variability in rainfall is expected to occur seasonally. Due to these changes, the intensity and frequency of extreme events such as floods and drought are expected to increase, especially in the western and northern lowlands.

- These climatic fluctuations are expected to have serious impacts on the environment. For example, water resources will be affected negatively by the reduction of precipitation and the increase in temperature. This will result in an increase in evaporative losses and a decrease in runoff and groundwater recharge. Grasslands are expected to be replaced by savannas and, potentially, forests; significant change and loss of habitat is projected for high-altitude locations, with negative consequences for the survival of species of medicinal value, among others.

Underlying causes

- Human activities, such as poor agricultural practices and unsustainable energy consumption patterns, are the primary forces driving biodiversity loss in natural habitats in Lesotho. In the case of medicinal plants, natural populations are over-exploited, and their associated ecosystems and habitats are over-used and degraded. The root cause of loss of biodiversity, including medicinal plants, is the increasing size of the human population and persistent poverty, placing greater demand on finite biological resources. Lesotho has a human population of over 2 million, with the majority of the rural population still largely dependent on natural resources for meeting daily subsistence needs.

- Causes of biodiversity loss in Lesotho are also proximate and fundamental. Most of the population of Lesotho resides in the less-mountainous, western third of the country. In this area, competition for limited land resources is intense, soil erosion is widespread, and appropriate care for the land and its resources is limited. Ninety percent of the household energy needs for cooking and heating in Lesotho are derived from biomass in the form of fuelwood, which is derived from woody shrubs. This has resulted in the removal of woody vegetation, loss of topsoil and soil fertility, and reduced native plant species, including medicinal plants.

- The preferred long-term solution is to reduce threats to Lesotho’s biodiversity, protect its biological and genetic resources, and ensure that the country and people of Lesotho benefit from the conservation, use, and sustainable management of medicinal plants. As an important pillar of the CBD, the Nagoya Protocol on ABS serves as a key instrument for pursuing this goal – building long-term capacity at all levels to effectively implement its provisions will provide the right incentives for improved and sound management of Lesotho’s environment and will contribute to addressing the pressing poverty-environment challenges the country currently faces. However, achieving conservation, sustainable use, and fair and equitable benefit-sharing from Lesotho's medicinal plants for improved livelihoods is currently limited by the following barriers:

- Barrier 1 – Limited institutional and technical capacity to coordinate implementation of initiatives to conserve biodiversity and natural resources, including limited capacity to design and implement appropriate policies and programmes: The technical capacity to plan, implement, and upscale conservation and natural resources management programmes is limited at the national, sub-national, and local levels. This technical limitation is a result of the following: a) insufficient training of staff employed in the relevant government departments, including the MDNSE, MFRSC, and MAFS; b) understaffing of the MDNSE, MFRSC, and MAFS; and c), overall lack of financial resources for management of the environment and natural resources. As a result, mainstreaming of biodiversity and natural resources conservation, including implementation of ecosystem approaches into sub-national development strategies, is hampered.

- Barrier 2 – Lack of an enabling environment (including policies, laws, regulations, and guidelines) to implement the provisions of the Nagoya Protocol on ABS: Even though Lesotho has become a signatory to this convention, there is a lack of capacity to engage effectively with the complex technical and financial requirements for its implementation, including negotiating benefit-sharing agreements on the use of genetic resources. Currently, there are no guidelines in place for sustainable harvesting of genetic resources and the relevant institutions have little capacity to develop such guidelines, meaning there is no regulation of harvesting and use. There is no clear permit system in place, or clear mechanisms to secure the consent of communities who reside where these resources are harvested. The issuing of permits is ad hoc and not informed by an understanding of the resource, its status, threats, or commercial value – as these are unknown and undefined – and permits are issued without consultation with all relevant stakeholders.

- The institutional environment for defining these resources, and regulating their use, is characterized by weak collaboration and conflicting and overlapping mandates, resulting in inefficiencies and a lack of coordinated decision-making. The governance mechanisms are unclear, with both central government institutions and traditional authorities having mandates and power to regulate and manage these resources, and, management decisions are mostly reactive. Currently, the only context within which ABS issues may be considered is within the environmental impact assessment (EIA) process, resulting in development projects (e.g. mining and construction) being prioritized over conservation and sustainable management of natural resources in the quest for economic growth and development.

- Barrier 3 – Under-valuation of indigenous traditional knowledge associated with genetic resources, and lack of benefit-sharing from their harvest and use: Research shows that Lesotho hosts extensive TK about the pharmaceutical properties and medicinal uses of its genetic resources, and that much of this is still in use today. It is evident, however, that very few benefits accrue to the country and its people from the ownership and use of this knowledge and resources. Instead, significant benefits are being lost to other more powerful groups elsewhere in the region (e.g. in South Africa) and beyond, through unfair trade agreements and/or illegal harvesting of the resources and extraction of TK. Lack of research and development (R&D) of genetic resources prevent the equitable sharing of the benefits (both monetary and non-monetary) with the holders of traditional knowledge and holders of the resources. The weak enabling policy and regulatory environment together with limited capacity at the national and local level to conduct R&D are the main barriers to establishing formal ABS arrangements – this not only places the resources under threat, but also prevents the country from benefitting from these resources and also adequately conserving and protecting them. As a consequence, vulnerable groups such as women and herders become worse-off as they continue to be exploited, resources become threatened with over-harvesting and unsustainable use, and the TK held by the Basotho is extracted and may even be lost together with the resources.

- Strategy

- The objective of this project is to strengthen national and local capacities to implement the Nagoya Protocol on Access and Benefit Sharing (ABS) with a focus on traditional knowledge on medicinal plants in Lesotho and the potential for bioprospecting. To achieve this, the project seeks to support the creation of an enabling environment and equip all stakeholders (users, providers, policy makers, researchers, law enforcement officers, and the wider Basotho nation) with the skills, capacity, and resources to sustainably harvest, add value to, manage, conserve, and benefit from genetic resources.

- Project Component 1 will support the creation of an enabling environment at the national level through the development of policies, regulations, strategies, and guidelines that promote the conservation, sustainable use, and benefit-sharing of the country’s biological and genetic resources. Through this component the project will remove regulatory and institutional capacity barriers by supporting policy reviews, developing guidelines, and training government staff, local government authorities, communities, and other stakeholders in the application/implementation and monitoring of policy and regulatory frameworks for biodiversity conservation and sustainable management of natural resources (with particular focus on selected medicinal plants).

- Project Component 2 will build on the capacity and enabling framework established in Component 1.  In particular, it will seek to remove barriers that prevent the valuation of traditional knowledge associated with genetic resources, and benefit-sharing from their harvesting and use. This Component will include building the capacity for bioprospecting as the basis for future natural product development and the establishment of ABS agreements that will determine how the benefits from the use of the selected genetic resources will be shared.

- Project Component 3 is complementary to the other two components. It seeks to support the development and implementation of a gender action plan to ensure that women and other marginalized groups benefit from the project interventions, while being empowered for active participation in ABS-related programmes and interventions.  Barriers will be removed to ensure that women, youth, and other vulnerable groups (such as herders), are aware about the value of Lesotho’s genetic resources and the importance of preserving the associated TK that needs to be preserved.

- Component 3 will also support the exchange of knowledge and lessons learned with other regional and international players who are engaged in similar work, and who may have an interest in Lesotho’s biological and genetic resources sector. Monitoring and evaluation (M&E) of project implementation, outcomes, and outputs will ensure that the project achieves its goals and objectives.

- The project´s Theory of Change is illustrated in Figure 1.  The development objective of the project is to strengthen national and local capacities to implement the Nagoya Protocol on Access and Benefit Sharing (ABS) with a focus on traditional knowledge on medicinal plants in Lesotho and the potential for bioprospecting.  This will be delivered through activities and outputs that: a) strengthen the institutional capacity for implementing the provisions of the Nagoya Protocol on ABS at the national level; b) improve the national capacity to develop the tools and strategies required to operationalize ABS; and c) enforce the related laws, policies, and regulations. This premise will be tested through the development of institutional and local capacity and a regulatory framework that will serve as the basis for future investment in key R&D and bioprospecting initiatives around genetic resources (medicinal plant species) that have potential commercial value. Lessons learned and knowledge from the implementation of this strategy will be documented, shared, and disseminated for their adoption in other landscapes around the country and in Southern Africa.

- The project´s Theory of Change is based on three key assumptions: (i) It is expected that the political will exists to implement, through Component 1, the legal and policy reforms needed to support the implementation of the Nagoya Protocol on ABS, and that the national institutions will have the capacity for effective monitoring and enforcement; (ii) It is assumed that local stakeholders will be willing to participate in capacity development activities for promoting future R&D and the that project team will be successful in engaging them; (iii) It is assumed that climate change and variability will be within normal ranges and the project outcomes will not be affected by this variability.

Contribution to Sustainable Development Goals (SDGs) and to national development priorities

- 16.	The project is relevant to, and will contribute to the following Sustainable Development Goals (SDGs). Firstly, the project will contribute to Gender Equality and Women’s Empowerment (Goal 5) through gender equality and inclusion of women’s interests and experiences into policy development and training, and equal participation in the establishment of at least two research collaboration agreements between users (researchers and academia) and providers (ILCs) of genetic resources. Secondly, it will contribute to the creation of Decent Work and Economic Growth (Goal 8) by enhancing the capacity of small/medium-scale community-based enterprises to participate in ABS and bioprospecting processes.  Thirdly, it will contribute to the development of Industry, Innovation, and Infrastructure (Goal 9) through strengthening and equipping key national research centres to conduct R&D on genetic resources of medicinal plants. Fourthly, the project seeks to contribute to sensitization for Responsible Consumption and Production (Goal 12) through raising awareness on sustainable utilization, conservation and access to and benefit sharing from the use of genetic resources Finally, SDG 15 (Life on Land) will be addressed by building awareness at the local level about the importance of both in-situ and ex-situ conservation of selected resources under communal management, conservation of selected resources in household botanical gardens and nurseries, and in-situ conservation of selected resources within protected areas

- The project builds on several ongoing initiatives led by the GoL for biodiversity conservation, sustainable use, and equitable sharing of benefits arising from the use of biological resources. It is consistent with the GoL’s priorities as set out in several national policy documents and plans and projects, including: Vision 2020; the National Strategic Development Plans (NSDP I and II); the National Biodiversity Strategy and Action Plan (NBSAP); the Environment Act 2008; the Draft Biodiversity Resources Management Bill of 2021; the National Range Resources Management Policy of 2014; and, the Ministry of Water No. 15 of 2008 Act and the related Letseng-la- Letsie Integrated Catchment Management Plan (ICMP) 2013. The project will support mainstreaming of the Nagoya Protocol into these instruments and will contribute to building an enabling environment to facilitate the operationalization of an ABS system in Lesotho, in line with the Nagoya Protocol.

- The project is aligned with achievement of several activities under Lesotho’s National Biodiversity Strategy and Action Plan (NBSAP), which seeks to enable implementation of biodiversity conservation goals (Aichi Target 17).  These are: a) the identification of biological diversity components through research and compiling inventories to improve biodiversity conservation; b) identification of processes likely to threaten Lesotho’s biodiversity; c) implementation of strategies that ensure the sustainable conservation of biodiversity components (PAs, resource management areas [RMAs], environmental resources management areas (ERMAs), botanical gardens, and Maboella); and, d) enhanced management of Lesotho’s unique wetland systems. The project will also contribute to implementation of the NBSAP through: a) strengthening of legal frameworks and measures; b) development of human resources and improving the skills required for biodiversity management; c) increased participation of rural households in relevant activities through their own initiatives, for their own purposes, and under their own control; d) reformation and management of agricultural practices in Lesotho that are responsible for the destruction of biodiversity; e) environmental impact studies performed prior to implementation of activities that are likely to adversely affect biological diversity; f) establishment of benefit-sharing measures; g) development of material incentive programs to change people’s behaviour so that future land title-holders make appropriate conservation decisions; and, h) engagement in international strategies that facilitate the security of national and regional biodiversity components.

Project area

- The project’s area of influence includes: the Sehlabathebe National Park (6,952 ha) located in the south-eastern mountains of the Qacha’s Nek district and is part of the larger Maloti-Drakensberg World Heritage Site; the Tšehlanyane National Park (5,394 ha); the Bokong Nature Reserve (1,952 ha) Corridor between Leribe and Butha-Buthe districts in northern Lesotho; and, the Letša-la-Letsie Ramsar site (434 ha). The project sites include the core protected areas as well as their buffer and transitional zones in surrounding landscapes. A detailed description of the project area, including maps, is provided in Annex 3.

Increased awareness nationally and locally about the provisions of the NAGOYA PROTOCOL on ABS

9,489 men and 10,042 women benefit from the sustainable use and conservation of commercially- important medicinal plants associated to ABS products

Strengthened national institutions to develop, implement, and enforce national legislative, administrative, and policy measures on ABS

Functional national ABS policy and regulatory framework

Project Impacts

Enabling institutional capacity and regulatory framework strengthened to support implementation of the NP on ABS

National R&D strategy on bioprospecting in place

Enhanced capacity of key stakeholders, including ILCs especially women, to participate in ABS and bioprospecting processes

Gender mainstreaming, knowledge management and M&E

Project Outcomes

Institutional capacity development strategy for the ABS framework in place

National Environment Policy and Biodiversity Bill include ABS/NP considerations

Gender strategy developed and used to guide project implementation, monitoring, and reporting

Exchanges of experience program raises awareness about regional/international ABS initiatives

Project Outputs

National guidelines for enforcing ABS regulatory framework developed

National ABS, bioprospecting, and TK regulations proposed

National research centres strengthened to conduct R&D on genetic resources of medicinal plants

Knowledge, attitudes, and practices assessment/surveys carried out and an awareness-raising programme on ABS developed and implemented

Model biocultural community protocol developed considering medicinal plants with potential for bioprospecting

A national CHM in place to assist in the collection, provision, and dissemination of ABS information

Local/community councils by-laws on ABS reviewed and finalized

ABS and TK strategy developed

Valuation of selected genetic resources with known commercial and intangible values conducted

Participatory monitoring, evaluation and learning strategy developed and implemented to support project management, collate, and disseminate lessons

Guidelines for developing biocultural community protocols for ownership, access rights, and benefit-sharing rules adopted

National focal point, competent national authorities, and checkpoints capacity enhanced

Training program for small/medium-scale community-based organizations and enterprises and for national parks implemented

E-permitting system for bio prospectors in place

Codes of conduct, best practices, guidelines and standards for industry and research sectors active in bioprospecting

Guidelines and procedures for obtaining PIC and MAT in place

Project Outcome 2

Project Outcome 3

Project Outcome 1

Lesotho remains susceptible to external and internal impacts, including limited economic growth, unfavourable climatic conditions, land degradation, population increase, and poor rural land use planning and management. Within this context, the national and local capacities to implement the Nagoya Protocol on ABS with a focus on traditional knowledge on medicinal plants in Lesotho and the potential will be strengthened.

Development Challenge

Under-valuation of indigenous knowledge on genetic resources and lack of mechanisms to systemize and share related information

Limited institutional and technical capacity to coordinate implementation of biodiversity and natural resources conservation initiatives, including limited capacity to design and implement appropriate policies and programmes

Lack of enabling environment (including policies, laws, regulations, and guidelines) to implement the provisions of the NAGOYA PROTOCOL on ABS

Barriers

Problems

Existing conservation strategies lack empirical data on medicinal plants limiting their protection and ability to sustainably manage them for equitable ABS

Over-exploitation of genetic resources, including medicinal plants, and habitat degradation where these species occur due to an inadequate institutional and regulatory framework and poor law enforcement to regulate and control the trade of natural resources

Absence of mechanisms to document TK and for replication and scaling-up of best practices for biodiversity conservation, the use and sustainable management of medicinal plants, and gender mainstreaming

Figure 1. Theory of Change

- Results and Partnerships

Expected Results:

Component 1: Enabling institutional capacity and regulatory framework strengthened to support implementation of the Nagoya Protocol on ABS.

- This component will support the creation of an enabling regulatory and institutional environment for establishing a national and local ABS framework for genetic resources and its associated traditional knowledge. This will include the development/strengthening of national laws and regulations and local/community councils’ by-laws to include ABS considerations through a transparent and consultative process ensuring full participation of all relevant stakeholders, including local communities and councils, marginalized groups (i.e. herders), and non-governmental organizations (NGOs). This component will also improve the capacities of the NFP, NCAs, and Checkpoints to process access applications, develop model contractual clauses under MAT, and negotiate and monitor ABS agreements and biodiscovery projects to ensure compliance.

The outcomes and outputs under Component 1 are as follows:

Outcome 1.1: Functional national ABS policy and regulatory framework operational and supportive of ABS from the use of genetic resources.

- Lesotho has no policies, laws, and plans that specifically address ABS of genetic resources, or associated traditional knowledge. This means that the regulatory framework for implementation of the Nagoya Protocol is currently weak. The GoL is currently reviewing its environmental governance policy framework, and a Biodiversity Bill is proposed – this will give priority to ABS, largely to respond to the emerging challenges and threats to Lesotho’s biological and genetic resources as highlighted in the situational analysis conducted during accession to the Nagoya Protocol. In support of this process, this project will deliver the following outputs under Outcome 1.1:

Output 1.1.1: National Environment Policy of 1998 and Biodiversity Bill of 2021 reviewed to address ABS in accordance with the Nagoya Protocol.

- Under the leadership of the MDNSE, develop an ABS policy and regulatory framework for ABS at the national level that adopts the principles of the Nagoya Protocol and focus on the National Environment Policy of 1998 and Biodiversity Bill of 2021. This will include adopting principles related to fair and equitable benefit-sharing, access to TK associated with genetic resources, compliance with MAT, and monitoring the use of genetic resources, among others. Emphasis will be placed on the use of genetic resources as a strategy for biodiversity conservation and its sustainable use.

- Lesotho’s ABS policy and regulatory framework will be developed through a highly participatory process to ensure effective inter-institutional coordination and alignment with legislation or regulatory requirements from multiple sectors. This will include consultation with key government agencies such as the MLGCPA; the MFRSC; the Ministry of Water (MoW); the MLCA; the MAFS; the Ministry of Communications, Science, and Technology (MCST) – Department of Science and Technology (DST); the Ministry of Gender, Youth, Sports, and Recreation (MGYSR); and other key stakeholders such associations of traditional practitioners, the private sector, NGOs, and the Lesotho Revenue Authority (LRA). The activities under this output will be to:

- Conduct a baseline survey of policies relevant to ABS and Nagoya Protocol principles (e.g. National Range Resources Management Policy – 2014, National Forestry Policy – 2007; Science and Technology Policy 2006-2011, among others; a more complete list of policies to be considered is included in Annex 22), and review the experiences and lessons learned in other countries for establishing functional national ABS policy and regulatory frameworks (e.g. South Africa, which has already put national legislation into place that enacts Articles 15 and 8(j) of the CBD, and recognizes the importance of regulated access to genetic resources as well as their associated TK).

- In consultation with stakeholders, revise the National Environment Policy of 1998 to provide guidelines for implementation of the Nagoya Protocol on ABS. Particular attention should be paid to identifying gaps in the existing National Environment Policy and Biodiversity Bill, and to addressing gender issues.

- In light of the review, commission drafting of the updated policy and amended bill and facilitate approval through the MLCA.

- Submit the updated Biodiversity Bill to parliament for enactment, with the participation of the Ministry of Law and Constitutional Affairs – Department of Drafting.

The revised National Environment Policy and Biodiversity Act will be publicized among key stakeholders (MLGCPA; the Ministry of Forestry, Range, and Soil Conservation [MFRSC], MoW, MLCA, MAFS, DST, MGYSR, NGOs, etc.) through Output 3.2.1.

Output 1.1.2: National ABS, bioprospecting, traditional knowledge (TK), and intellectual property rights (IPRs) regulations developed, reviewed, updated, and presented to parliament for approval.

- To complement the national ABS policy (described above, Output 1.1.1) the project will facilitate the development of national-level regulations on ABS, bioprospecting, traditional knowledge, and intellectual property rights (IPRs). These national regulations will include provisions that: (i) ensure that that monetary and non-monetary benefits arising from the use of genetic resources are shared in a fair and equitable way with local communities and traditional practitioners, based on MAT (Article 5 of the Nagoya Protocol) (ii) define the process governing the research phase of biodiscovery, and establish a permitting system for bioprospecting and use/biotrade activities involving any indigenous genetic and biological resources or their derivatives; (iii) establish guidelines on Intellectual Property Rights relating to genetic resources and establish clear links between bioprospecting and the conservation of biodiversity and benefits for local communities; (iv) ensure that TK associated with genetic resources held by local communities and traditional practitioners is accessed with their approval and involvement and that MAT have been established (Article 7 of the Nagoya Protocol); (v) ensure that local customary laws, community protocols, and procedures with respect to TK associated with genetic resources are considered (Article 12 of the Nagoya Protocol); and (vi) protect against the potential misuse of genetic resources and associated TK, and provide a legal framework for negotiations or agreements on ABS.

- The development of the national ABS, bioprospecting, TK, and IPR regulations will be a highly participatory process similar to that described for Output 1.1.1. Specific activities will include the following:

- Conduct a baseline survey of regulations relevant to ABS, bioprospecting, IPRs, and TK (e.g., Lesotho Science and Technology Policy 2006-2011; Universal Medicine Men and Herbalist Act 1978 and other associated regulations; Traditional Medical Practitioners Bill 2000; and Copyright Order 1989, among others).

- Develop the national ABS, bioprospecting, IPRs, and TK regulations, working in coordination with the MLCA and taking lessons from the baseline survey (international and regional best practices).

- Validate the national ABS, bioprospecting, IPRs, and TK regulations through the appropriate fora and processes for parliament’s enactment, working in coordination with the MLCA and the DoE/MDNSE.

The national ABS, bioprospecting, IPRs, and TK regulations will be publicized among key stakeholders (MLG, MFRSC, MoW, MLCA, MAFS, DST, MGYSR, NGOs, local committees, etc.) through Output 3.2.1.

Output 1.1.3: Local/community council by-laws in prioritized districts (guidelines) on ABS reviewed, finalized, and/or developed, considering national frameworks on ABS and biodiversity.

- Despite the current lack of a national ABS policy and regulatory framework, local-level by-laws have been developed for accessing and using genetic resources, including medicinal plants, but these may not address all relevant issues. For example, local bylaws support an active industry around the use of medicinal plants, which local communities use as traditional medicine and harvest for trade, but local council bylaws are uninformed by issues such as sustainability of the resource and equitable sharing of benefits, on which little is currently known.

- Accordingly, the project will review the existing local/community councils’ by-laws in the prioritized districts (Qacha’s Nek, Leribe, Butha-Buthe, and Quthing) to ensure that provisions of the Nagoya Protocol are properly incorporated across the entire industry value chain.  To this end, the following activities will be conducted:

- Undertake a baseline survey of relevant by-laws (guidelines) in the participating community, and place this in context of a comprehensive review of by-laws in all other community councils nationwide.

- Review, update and/or develop existing local/community councils’ by-laws in the prioritized districts, in the context of the national regulations developed in Outputs 1.1.1 and 1.1.2 and working in close consultation with the community councils and local and national environmental authorities (e.g., DoE/MDNSE, MGYSR, MAFS, MLCA, MoA, chiefs, etc).

- Conduct fully inclusive stakeholder consultations and facilitate validation of the updated by-laws.

- Facilitate the approval of draft by-laws and regulations by appropriate authorities through the MLGCPA.

- Translate the approved regulations and by-laws into Sesotho and publicize widely at the local level.

The updated local/community councils’ by-laws on ABS will be publicized among key stakeholders (DoE/MDNSE, MGYSR, MAFS, MLCA, community councils, NGOs, etc.) through Output 3.2.1.

Output 1.1.4: ABS and associated Traditional Knowledge Strategy developed.

- In line with Article 12 of the Nagoya Protocol, the project will develop an ABS and TK Strategy to take into consideration customary laws of local communities relevant to TK associated with genetic resources. Key activities for delivering this output will be to:

- Compile a database of critical TK about medicinal plants of Lesotho and identify existing strategies and key gaps. Data will be gathered through broad-based consultations with all stakeholders, especially holders of TK at the local level and relevant associations at the district and national levels.

- Informed by this information, and a review of similar regional and international strategies, develop a draft ABS and TK strategy for approval by the MDNSE.

- Publish and translate the approved ABS and TK Strategy into Sesotho.

Outcome 1.2: Capacity of national institutions to develop, implement, and enforce national legislative, administrative, or policy measures on ABS, strengthened.

- Under this outcome, the project will provide much-needed training to build technical capacity in key institutions at the national, regional and local levels, for developing the tools and strategies required to operationalize ABS, and enforce ABS laws, policies, and regulations once they are in place.

Output 1.2.1: Capacities of National Focal Point, Competent National Authorities, and Checkpoints enhanced.

- A comprehensive baseline capacity assessment was conducted during the Project Preparation Grant (PPG) phase using the UNDP National ABS Institutional Capacity Scorecard, and capacity development needs and gaps were identified at all levels (individual, institutional, and systemic). The government agencies assessed included the DoE/MDNSE, the MFRSC: Departments of Range Resources Management (DRRM) and Forestry, the Lesotho Mounted Police Services, and the LRA. (The capacity assessment also included an assessment at the local/site level in which traditional practitioners, Community Councils, Community Conservation Fora [CCFs], and the company Bophelo Natural Products were evaluated – their training needs related to ABS will be addressed as part of the Institutional Capacity Development Strategy for ABS to be developed through Output 1.2.2). The project will build on the findings of this assessment (identifying any gaps and weaknesses) as a first step to strengthen the capacity of national institutions to develop, implement, and enforce national legislative, administrative, or policy measures.

Activities under this output will be to:

- Conduct training (workshops, participation in ABS conferences and seminars) for national entities – including the National Focal Point (DoE/MDNSE), Competent National Authorities (e.g., DoE/MDNSE) and Checkpoints (e.g., Lesotho Mounted Police Services, LRA, Department of Lands, Surveys, and Physical Planning) – based on the gap assessment conducted during the PPG phase.

- Assess existing mechanisms to enforce national legislative, administrative, or policy measures related to the conservation and use of natural resources, and update protocols for patrolling, reporting, and sanctioning offenders – including updating relevant databases.

- Review and update the Curriculum of the Police Training Centre to include legal issues on environment and conservation, to enhance their capacity for enforcement of ABS regulations and to ensure that the selected species are not over-harvested. Training will also include strengthening mechanisms for reporting infractions, enhanced coordination with community authorities (chiefs and community councils), and communication mechanisms with communities and harvesters.

- Train LRA officials in ABS and environmental aspects in order to: a) strengthen the control of illegal trade and biopiracy of genetic resources across borders; b) improve communication mechanisms with other agencies (e.g., DoE/MDNSE and MFRSC); c) improve permitting mechanisms considering the Nagoya Protocol framework; and, d) consolidate the certification and permitting process for moving materials to discourage illegal trade across borders. The project will also support activities that complement the surveys of prohibited and restricted goods that are already underway.

- Evaluate activities to enhance capacities on ABS at the mid- and end-points of the project using the UNDP National ABS Institutional Capacity Scorecard.

Output 1.2.2: Institutional Capacity Development Strategy for implementation, monitoring, and enforcement of, and compliance with, the ABS framework developed and rolled out.

- An institutional capacity development strategy will be developed to ensure that government agencies: a) understand the ABS rules and procedures, including granting of permits, assessment of access applications, core principles of prior informed consent (PIC) and MAT and their application, as well as the rights and roles of local communities and vulnerable groups; b) interpret correctly the ABS provisions of national laws, the Nagoya Protocol, the CBD, and other related international agreements such as ITPGRFA; c) understand and keep abreast of negotiations at the World Intellectual Property Organization (WIPO) and Food and Agriculture Organization (FAO) to ensure that all authorities dealing with ABS have a common and coordinated national approach; and d) negotiate ABS agreements. These will ensure better understanding of national and international provisions of ABS, and enhance the implementation of the proposed national ABS law at all levels. The project will build on the findings of this assessment a first step to develop an Institutional Capacity Development Strategy for ABS in Lesotho, and will include the following activities:

- Validate needs and gaps identified during the PPG phase through additional consultations with prioritized stakeholders at the project site, district, and national levels.

- Development of a comprehensive capacity-building plan for the implementation of ABS, including training modules on bioprospecting, ABS value chains, marketing, business planning, codes of conduct, community participation protocols, and research procedures, among others. The capacity-building plan for implementation of ABS will be directed to all stakeholders with interest in the use and trade of genetic resources at the national and local levels.

- Development of training modules for monitoring the use of plant genetic resources at the local levels. This training will be directed to extension officers of the MDNSE and MFRSC, including park managers, park rangers, district environment officers, range management officers, and forest officers at district levels.

- Improve the capacity of local authorities, chiefs, community councils, and CCFs for the protection, conservation, and management of natural resources, especially rangelands and associated genetic resources by: i) improving their ability to use available resources, information and knowledge; ii) training members on key principles of the Nagoya Protocol on ABS, including legal requirements for understanding benefit-sharing protocols, including PIC and MAT; iii) strengthening capacity to build consensus among stakeholders for the development of community-based monitoring systems to enable stakeholders to understand, monitor, and mitigate changes to the conservation, sustainable use, and implementation of fair and equitable benefit-sharing mechanisms for species that are sources of genetic resources; and, iv) consolidation of existing dialogue frameworks with local environmental authorities for enforcement of regulations, and with the national research institutions and academia to research and generate scientific evidence, and validate TK systems to support research R&D for bioprospecting and development of ABS products.

Output 1.2.3: National guidelines for enforcing ABS regulatory framework developed and implemented.

- In line with the Nagoya Protocol, the project will support the development of national guidelines to enforce the implementation of the ABS policy and regulatory framework developed under Outputs 1.1.1, 1.1.2, and 1.1.3. These guidelines will be developed for the compliance of users of genetic resources with domestic legislation or regulatory requirements for ABS (Article 15); compliance of users of genetic resources with domestic legislation or regulatory requirements on TK associated with genetic resources (Article 16); and, monitoring the use of genetic resources (Article 17). Under this output, the following activities will be carried out:

- Publicize at the national and local levels the ABS regulations developed by the project (Outputs 1.1.1, 1.1.2, and 1.1.3), including at the four project sites and among key project stakeholders.

- Identify and agree on critical steps for the implementation of ABS regulations in close consultation with stakeholders, including mechanisms to ensure that: a) TK associated with genetic resources used is accessed in accordance with PIC and MAT and the involvement of local communities; b) appropriate, effective, and proportionate measures to address situations of non-compliance are agreed upon; c) cooperation in cases of alleged violation of domestic ABS legislation or regulatory requirements is enhanced; and that, d) there is transparency regarding the use of genetic resources, including compliance with PIC and MAT requirements.

- Designate Checkpoints and ensure their full recognition by stakeholders (e.g., DoE and community councils) who would be responsible for collecting relevant information related to PIC, the source of the genetic resource, the establishment of MAT, and/or the use of genetic resources.

- Publication and socialization at the national and local levels of the guidelines for implementation of ABS regulations.

Output 1.2.4. A national clearing-house mechanism in place to assist in the collection, provision, and dissemination of ABS information

- A national clearing-house mechanism (CHM) will be established to facilitate access to information, to create transparency, and highlight aspects related to implementation of the NP on ABS in Lesotho. It will be administered by DoE and will facilitate decision-making and co-ordination among different stakeholders interested in implementing ABS-related initiatives. The CHM will be a web-based platform where national, regional, and local information will be available to the public, including: a) legislative, administrative and policy measures on ABS (including aspects developed under Component 1); b) TK associated with genetic resources; c) permits for granting PIC, establishment of MAT, and for advancing R&D; and d) capacity-building and development initiatives to promote synergy and coordination between ABS-related initiatives. Specific activities to be conducted are:

- Design a user-friendly web-based national CHM that is interoperable with other relevant websites.

- Publicize at the national and local levels the national CHM developed.

- Periodically update information and notify stakeholders of updates using social media, e-mail, and other mechanisms.

Outcome 1.3: Management, ownership, and access rights, rules, and procedures over access and use of genetic resources are defined, clarified, and encoded in the legal system (e.g., by-laws/ community protocols).

- Support under this component will be directed towards development of guidelines, procedures, standards, and codes of conduct to operationalize an ABS regime in the country, including providing support to community-level institutions to establish community protocols for governing the access to, and distribution of benefits from, the use and conservation of biological and genetic resources within their control. The following outputs will be supported under this component/outcome:

Output 1.3.1: Guidelines and procedures for obtaining PIC and MAT developed and approved.

- The legal basis for obtaining PIC and MAT will be included as part of the national ABS framework to be developed under Output 1.1.2; accordingly, the guidelines and procedures for obtaining PIC and MAT will comply with these regulations once they enter into force. In addition, the guidelines will be aligned with Article 13 of the Nagoya Protocol. The activities under this output include the following:

- Development of guidelines and procedures for implementing the ABS principles with local authorities through facilitated workshops. With regard to PIC, this will include: a) identifying the competent national authority to whom an application for PIC should be submitted; b) identifying the necessary format of the application and specific items of the information required; c) defining procy6edures for consultation with local communities to give access to genetic resources or TK associated with genetic resources; and, d) defining any other requirements or conditions for obtaining PIC. With regard to MAT, activities will include: a) defining general conditions, obligations, procedures, and mechanisms for establishing agreements to access genetic resources and/or TK; b) developing monitoring and compliance mechanisms; c) developing guidelines to resolve disputes arising from the access to genetic resources considering relevant contractual arrangements and national and local regulations; and d) defining any other requirements or conditions related to compliance with MAT.

- Validation of the PIC and MAT guidelines in appropriate stakeholder fora and adoption by the relevant authorities.

- Publication and socialization of the guidelines to facilitate implementation among stakeholders.

Output 1.3.2: Guideline for developing biocultural community protocols governing management, ownership, access rights, and benefit-sharing rules and procedures are defined and adopted.

- In line with Article 12 of the Nagoya Protocol, the project will support, with the active participation of local communities and authorities (including women within these communities), the development of guidelines for developing biocultural community protocols with the specific goal of defining rules and procedures for the management, ownership, access rights, and benefit-sharing related to genetic resources within their territories. This will include a national dialogue to identify the aspirations of local communities regarding their land, ecosystems and resources, TK, and customary governance within the ABS context and in a broader community-based context. In addition, biocultural community protocols will allow the recognition by users of genetic resources of the customary laws, values, and decision-making processes concerning the management and use of their territories and natural resources and will serve as a tool for asserting rights and affirming responsibilities under traditional and national laws. Although the guidelines for developing biocultural community protocols will be developed by the communities themselves, key government institutions will be involved to ensure buy-in and facilitate official recognition; this will include competent national authorities (e.g., DoE) and local/district authorities. This output includes the following activities:

- Consult with harvesters, practitioners, women, and marginalized groups (including herders) and local communities regarding management, ownership, and access to natural resources, including genetic resources.

- Work in close consultation with local communities and organizations to draft guideline for developing community protocols governing management, ownership, access rights, and benefit-sharing rules and procedures.

- Develop patenting protocols for TK.

- Validate protocols with local community leaders.

- Publish and disseminate guidelines in English and local languages.

Output 1.3.3: Establish codes of conduct, guidelines, best practices, and standards that ensure ethical bioprospecting, sustainable harvesting and fair and equitable benefit-sharing, for industry and research sectors active in bioprospecting.

- In-line with Article 20 of the Nagoya Protocol (Codes of Conduct, Guidelines and Best Practices, and/or Standards), this output will define the basic principles with which industry and research sectors active in bioprospecting in Lesotho will abide. Codes of conduct and guidelines will be drafted so that, among other things, the industry and research sectors will operate considering the provisions under the CBD and the Nagoya Protocol, in line with national ABS laws and regulations (Outputs 1.1.1, 11.2, and 1.1.3), sharing benefits fairly and equitably arising from the use of genetic resources and associated TK (Output 1.1.4), complying with PIC and MAT requirements (Output 1.3.1), and respecting local community customary laws and biocultural community protocols (Output 1.3.2).  Best practice guidelines will provide details about how the code of conduct should be implemented to ensure sustainable harvesting, ethical bioprospecting and fair and equitable benefit-sharing. The activities under this output include the following:

- Conduct consultations with multiple stakeholders regarding what can be included as part of the codes of conduct, best practices, and standards that ensure sustainable harvesting and fair and equitable benefit-sharing.

- Draft codes of conduct, best practices, standards and guidelines that ensure sustainable harvesting, ethical bioprospecting and fair and equitable benefit-sharing, including existing best practices in the country and in the region.

- Validate the codes of conduct, best practices, and standards that ensure sustainable harvesting and fair and equitable benefit-sharing.

- Publish and disseminate codes of conduct, best practices, and standards that ensure sustainable harvesting and fair and equitable benefit-sharing.

Component 2: Building capacities for bioprospecting and value-addition of genetic resources.

Outcome 2.1: Opportunities for bioprospecting strengthened with improved research capabilities to add value to genetic resources

Output 2.1.1: National R&D strategy on bioprospecting, including role of traditional medical practitioners developed and implemented.

- The project will support the development of a national R&D strategy on bioprospecting to identify genetic resources in the wild, and associated traditional knowledge, and to develop commercially valuable ABS products, focusing on medicinal plants. This will include maximizing the commercial value from genetic resources and associated traditional knowledge, while creating a fair compensation system that benefits providers and users of those resources and contributes to conservation of the source species. National research centers such as the NUL and the Department of Agricultural Research will work closely with traditional practitioners and herbalists in developing a R&D strategy on bioprospecting to ensure their participation in all phases of bioprospecting process, including sample collection, isolation, characterization, and product development and commercialization. The planned activities are as follows:

- Conduct stakeholder consultation workshops to canvass the R&D proposal and secure cooperation of traditional practitioners and herbalists, including the compilation and appropriation of traditional knowledge, and agree on benefit-sharing protocols.

- Document traditional knowledge on plant genetic materials, collated under PIC and MAT and in recognition of intellectual property rights. This will include the review and updating of an inventory of medicinal plants to facilitate the production, validation, and publication of a national research and bioprospecting strategy and associated implementation guidelines. The specific bioprospecting surveys and research studies will be commissioned, aligned with principles of PIC in collaboration with holders of traditional knowledge and disadvantaged groups (e.g., herders and women).

- Draft and publish the national research and development strategy on bioprospecting.

Output 2.1.2: National research centers (e.g., herbalist) strengthened to conduct R&D on genetic resources of medicinal plants, in collaboration with traditional medical practitioners’ associations /groups and international partners on bioprospecting.

- Through this output, the project will provide support to national research centers, including the NUL, Department of Agricultural Research, and Katse Botanical Garden, to conduct R&D on genetic resources. The preliminary assessment the capacity of national research centers for bioprospecting conducted during the project design phase indicated that that a range of research and development activities are being undertaken on medicinal plants in the country; however, it is evident that research and development on medicinal plants of Lesotho is at its infancy stage, and is largely undertaken by the NUL and the main output of research and development by this institution is mainly scientific publications, and limited product development. In addition, although there is some level of collaboration of NUL staff with institutions in South Africa and elsewhere (e.g., University of Johannesburg and University of the Witwatersrand, The Council for Scientific and Industrial Research [CSIR], and the Agricultural Research Council (RSA), Nimura Genetic Solutions, etc.), which are more capacitated, particularly in terms of infrastructure, equipment and expertise, there is still limited progress in bioprospecting that can lead to innovation and the development of products for their commercialization and the sharing of benefits. Accordingly, the activities to be implemented are:

- Negotiate and sign a collaboration agreement between DoE, project authorities, and research centers, with specific terms of cooperation for all parties.

- Strengthen capacities through targeted training of experts and technical staff of national research centers, including the NUL, Department of Agricultural Research, and Katse Botanical Garden in R&D associated with medicinal plant. This will ensure that research does not only result in publications, but also leads to development of commercial products.

- Acquire laboratory and processing equipment (e.g., High performance liquid chromatography-Electrospray tandem mass spectrometry [HPLC/ESI-MS], Atomic absorption spectroscopy [AAS], Antimicrobial assay, spectrophotometer, functioning Rotary evaporator, Bench-top shaker, vacuum pump, steam distillation system). The preliminary assessment of lab equipment needs conducted during the project design phase will be updated.

- Establish an accredited testing laboratory, where all the commercial products (including cosmetic, food and traditional herbal remedies) produced in the country would be tested for safety and efficacy before entering the market. This can be established under the National University of Lesotho to ensure operational sustainability beyond the project.

- Identify potential medicinal plants species for value-chain development and improvement, particularly those with known commercial and intangible values and in collaboration with traditional medical practitioners’ associations /groups.

- Facilitate exchange programs with more established product developers (e.g., from South Africa) in order to capacitate local stakeholders and develop commercial products.

- Facilitate establishment of partnerships and collaboration by local product developers with international partners.

Output 2.1.3: A comprehensive valuation of genetic resources with known commercial and intangible values (cultural and spiritual) conducted, includes surveys to assess their conservation status.

- The project will use different methods for the valuation of plant genetic resources with known commercial and intangible values, and for estimating non-market and market benefits. During the project design phase, information gathered from a desktop survey was used to identify and profile 15 medicinal plants of Lesotho, which are being commercialized and six of which some level of research and development is currently being undertaken, mainly by the National University of Lesotho in collaboration with institutions in South Africa. Commercial products developed from the profiled medicinal plants are mainly cosmetic products, beverages and traditional herbal mixtures used for treatment of various ailments Valuation of non-market values (e.g. existence values) will include: (i) assessing the value placed on preserving genetic resources for future generations and the costs and benefits of conservation of genetic resources; and, (ii) identifying incentives for efficient conservation and benefit- and cost-sharing arrangements. Direct-use value and future uses of genetic resources (option value) will consider the current trade and future development of new products of those resources for pharmaceutical use. The assessment of intangible values (cultural and spiritual) will include the participation of local community members and traditional practitioners and herbalists to document how genetic recourses are valued locally, particularly of plant genetic resources for medicinal and other uses. Specific activities will be to:

- Review and analyze the baseline value of the prioritized genetic plant resources to establish their economic, cultural, and scientific value through appropriate economic valuation methods and procedures (e.g. contingent valuation and hedonic pricing). Consideration will be given to ongoing valuation efforts that are being conducted by the LRA for trade purposes (i.e., setting tariffs).

2.1.4. E-permitting system for bio prospectors in place.

- The project will allow the operationalization of a single web-based permit system to apply for permits for bioprospecting, including when traditional knowledge is involved, and for government authorities to review and approve applications. It will also allow monitoring compliance (including tracking of utilization of genetic resources and TK and the commercialization of derived products) and serve as source of information that will feed into the national CHM (Output 1.2.4) and for the government to report on the implementation of the Nagoya Protocol on ABS. DoE will administer the E-permit system and will coordinate with other government agencies (e.g., MAFS, MFRSC, and MOH, etc.), in case the issuing of permits requires their involvement.

- Assess system requirements based on the local needs and capacities for operation, management, and use.

- Develop the electronic platform for the permitting system, including a user-friendly manual.  A model for an online permit and monitoring system developed for implementation of the Nagoya Protocol in the Bahamas under the UNEP-GEF Project “Strengthening Access and Benefit Sharing (ABS) in the Bahamas” (GEF Project ID: 5744) will be consider.

- Publicize at the national and local levels the E-permitting system for bio prospectors.

Outcome 2.2: Enhanced capacity of key stakeholders, including ILCs especially women, to participate in ABS and bioprospecting processes.

Output 2.2.1: Training program for small/medium-scale community-based organizations and enterprises and for national parks implemented for: a) negotiation of PIC, MAT, and ABS agreements; b) development of community protocols; and c) contribution of ABS to conservation and sustainable use of biodiversity.

- The project will train small/medium-scale community-based organizations and enterprises, including women groups, in the negotiation of PIC, MAT, and development of ABS agreements so that these skills will be already in place locally when bioprospecting initiatives are implemented in the future.

Training activities will also emphasize the contribution of ABS to conservation and sustainable use of biodiversity, in particular for in situ conservation of medicinal plant species within PAs and other ecological important areas such as military installations and communal land in the buffer and transition zones, with the participation of CCFs and community councils. Emphasis will be given to the linkages between access to genetic resources and their utilization and the conservation of biodiversity and the sustainable use of its components. The activities to be implemented by the project are the following:

- Conduct a needs assessment for the participation of local communities and organizations (including women and women groups) in the four prioritized sites in training.

- Design a training plan based on the results needs assessment.

- Conduct training activities for community members, including women’s groups and herders, through workshops, field visits, webinars,

- Establish a template for ABS agreements based on a study of best practices and lessons learned from local, regional, and international experiences.

Output 2.2.2: Experience exchange program raises awareness about regional/international ABS initiatives.

- As part of the strategy to enhance the capacity of local stakeholders to participate in bioprospecting, the project will implement a program to learn from existing experiences in southern Africa region and in other parts of Africa and around the world regarding research and development and strengthening ABS value chains and their contribution to the conservation of biodiversity. Local community members from the prioritized districts (Qacha’s Nek, Leribe, Butha-Buthe, and Quthing) and staff from national research centers interested in bioprospecting will have the opportunity to interact with peers from other countries already involved in bioprospecting and the fair and equitable sharing of benefits from the use of genetic resources and traditional knowledge. Specific activities will be to:

- Identify ongoing ABS initiatives in the South Africa region and elsewhere for the exchanges of experience program.

- Define an exchange of experiences plan in consultation with community leaders and of traditional medical practitioners’ associations /group, and select community members and researchers, including women, to participate in exchange of experiences activities.

- Conduct field/country visits and participate in events (workshops, expert meetings, conferences, etc.) to learn about and raise awareness regarding ABS initiatives.

- Document lessons learned from the participation of in exchange of experiences activities and make them available to the public through the national CHM (Output 1.2.4) and other means.

Output 2.2.3: Model biocultural community protocol developed considering medicinal plants with potential for bioprospecting.

- The project will develop a model biocultural community protocol considering the guidelines developed under Output 1.3.2 and based on the comprehensive valuation of genetic resources with known commercial and intangible values conducted under Output 2.1.3. The model biocultural community protocol will primarily address aspects of traditional knowledge related to genetic resources and the in-situ conservation of medicinal plants (e.g., PAs and community lands and gardens). It will also serve as a model on how to engage local community and traditional practitioners with bio prospectors, including defining clear terms and conditions for the government, the private sector, and researchers for engaging with them and accessing their local resources and knowledge. In addition, it will serve as a mechanism for strengthening local governance in relation to access to traditional knowledge associated with genetic resources and the fair and equitable sharing of benefits arising out of the utilization of such knowledge.

Specific activities will include the following:

- Establish a working team consisting of local community leaders and traditional medical practitioners’ associations /groups, including women, from the prioritized districts (Qacha’s Nek, Leribe, Butha-Buthe, and Quthing), government representatives, and the project team.

- Discuss and define the outline of a model biocultural community protocol considering aspects such as selecting sites and identifying communities to be involved, mechanisms for participatory decision-making processes within the communities considering customary values and laws, and defining conditions set out by a given community for granting access to their lands, resources and knowledge, and for obtaining PIC, among other aspects. Experiences and lessons learned in other countries in the region for establishing biocultural community protocols related to the Nagoya Protocol on ABS will be considered.

- Prepare a draft of the model protocol and making it available in English and local languages.

- Validate the draft of the model biocultural community protocol with community leaders and traditional medical practitioners’ associations /groups, including women.

- Make available the model biocultural community protocol through the national CHM (Output 1.2.4) and other means.

Component 3: Gender Mainstreaming & Knowledge Management

- Under this component, the project will support the development and implementation of a gender action plan to ensure that women and marginalized groups benefit from the project interventions and are empowered to become active agents and participants in the ABS regime in Lesotho. It will also support a national awareness-raising program, explore transboundary and south-south and triangular cooperation (SSTrC) in key aspects of the genetic resources development sector, and between communities, and public and private sector players active in the area of bioprospecting. This will promote cross-sectoral learning and generate knowledge in the sector through the use of existing tools and platforms, such as the CBD portal, and ensure learning by, and empowerment of, poorer and marginalized groups. Research data on species of national importance will contribute to strengthening Lesotho’s decision-making on conservation, sustainable use, and ABS from genetic and biological resources. This information will also guide subsequent capacity-building and awareness-raising beyond the life of the project. Outcomes 3.1 and 3.2 of the project will specifically address knowledge management, communication, and awareness-raising issues, and explore opportunities for SSTrC as it pertains to bioprospecting on genetic resources. Finally, this component will support participatory monitoring of project results and impacts and promote up-scaling and replication of best ABS practices and experiences. The component includes the following outcomes and outputs:

Outcome 3.1: Gender mainstreaming lessons learned by the project are used to guide adaptive management, collate and share lessons, in support of upscaling.

- Work under this outcome will facilitate learning and participation at all levels in conservation and sustainable use and ensure a fair and equitable process for distribution of benefits among all participants in the ABS system. The participation of women, men, and youth in implementing the project interventions will be promoted and facilitated by the project, and inclusive and participatory M&E processes will be used to ensure that learning facilitates uptake and upscaling in other parts of the country. The following outputs will be generated:

Output 3.1.1: Gender strategy developed and used to guide project implementation, monitoring, and reporting.

- Targeted assessments and analyses of the gender dynamics associated with the management and use of biological and plant genetic resources were undertaken during the PPG phase, emphasizing the four project sites. These assessments formed the basis for development of the Gender Analysis and Action Plan (Annex 10) to empower poor rural women, men, and youth, as an aspect of promoting inclusive and participatory governance processes and operationalizing ABS as per the provisions of the Nagoya Protocol.

Activities under this output include the following:

- Training and capacity-building of key stakeholders (government, private sector, and civil society) on gender issues related to medicinal plant resources and ABS.

- Produce a gender-based strategy related to management of plant genetic resources.

- Establish a working linkage between DoE and the Department of Gender/MGYSR to mainstream gender issues related to ABS.

- Conduct gender empowerment workshops on ABS with selected women and vulnerable groups (youth and herders).

- Update the Gender Action Plan to guide implementation, monitoring, and reporting.

- Update the Herders Engagement Plan (HEP) (Annex 21) and develop the Traditional Healers and Herbalists Engagement Plan (THHEP).

Outcome 3.2: Awareness about sustainable use, conservation, and access to and benefit-sharing from the use of genetic resources enhanced.

- Work under this outcome will promote learning through participatory processes, as well as communication and outreach on the project activities and the results of project interventions. The following outputs will be delivered:

Output 3.2.1: Knowledge, attitudes, practices, and behavior (KAP/B) assessment/surveys carried out and an awareness-raising program on ABS developed and implemented.

- KAP/B assessment surveys were conducted during the PPG phase, targeting specific groups (e.g., local communities, practitioners, researchers, and the pharmaceutical industry) that may use or benefit from ABS transactions. These surveys were conducted to determine the project’s impact on levels of awareness about the national ABS regulatory framework (Component 1) and the Nagoya Protocol, as well as awareness of the values of biological and plant genetic resources and their sustainable use and conservation. The surveys were also used to mainstream gender in the ABS context among key stakeholders; additional KAP/B assessment surveys will be carried out during project implementation. The following activities will be conducted under this output:

- Produce a gender awareness strategy related to ABS.

- Conduct ABS awareness and sensitization workshops for local authorities and traditional practitioners.

- Document women and men’s TK (including herders) on prioritized medicinal plants.

- Document and share best practices and lessons learned on gender mainstreaming and medicinal plant product development.

- Publicize the national ABS policy and regulatory framework: National Environment Policy and Biodiversity Act (Output 1.1.1); National ABS, Bioprospecting and TK Regulations (Output 1.1.2); Local/Community Councils By-laws (Output 1.1.4); and ABS and TK Strategy (Output 1.1.4).

- Update the KAP/B index and produce reports on the project’s impact on awareness levels concerning ABS, the sustainable use and conservation of medicinal plants, and gender.

- Participate in regional and global ABS networks such as the Pan African Community of Practice, developed under the UNDP-GEF Global ABS Project (GEF ID 9255) to promote knowledge and information exchange with other countries implementing ABS initiatives.

- A communication and knowledge management strategy will be developed to systematize and disseminate knowledge, lessons learned, and best practices in order to promote up-scaling and replication.

Component 4: Monitoring and Evaluation

Output 4.1: Participatory monitoring, evaluation, and learning strategy developed and implemented to support project management, collate and disseminate lessons.

- Participatory M&E of the project’s implementation will be conducted following GEF and UNDP guidelines and according to the M&E plan described in Section VIII of this project document. The main components of the M&E plan include: an inception workshop; annual monitoring of indicators in the project results framework; annual project implementation reports (PIRs); annual NIM audits; ongoing monitoring of environmental and social risks, stakeholder engagement plan, and the gender action plan; project board meetings; oversight mission by the UNDP-GEF team; mid-term and terminal GEF-7 core indicators updates; and independent mid-term review (MTR) and terminal evaluation (TE), among other activities.

Agreement on intellectual property rights and use of the logo on the project’s deliverables and disclosure of information:

- To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed per relevant policies, notably the UNDP Disclosure Policy and the GEF policy on public involvement.

Resources required to achieve the expected result:

- Implementation of the project will require technical, financial, and logistical resources to deliver the expected results.  The key inputs to delivery of the project outputs include PMU staff, consultants and capacity building related procurements such as workshop venues and equipment. UNDP oversight inputs will be provided by the UNDP CO, Regional Technical Advisor and Vertical Funds Compliance Unit at HQ level. Costs for execution goods and services have been detailed in the multi-year budget under Section IX while UNDP oversight costs are covered by the Agency fees.

Partnerships:

- The project will coordinate, complement, and incorporate lessons learned from the following initiatives:

- GEF ID 9054 (UNDP) – Support to the Orange-Senqu River Strategic Action Programme (SAP) Implementation. The objective of this project is to strengthen the joint management capacity for the basin-wide integrated water resources management (IWRM) plan implementation and demonstrating environmental and socioeconomic benefits of ecosystem-based approach to water resources management through the implementation of SAP priority actions in the Orange-Senqu River basin.  Relationship to this project: Lessons learned and best practices from this project will be considered for the implementation of actions to promote the in-situ conservation of selected plant genetic resources, including communal lands and protected areas, and to promote the sustainable harvesting of the species.

- GEF ID 10020 (UNDP) – IWRM for Improved Agro-pastoral Livelihoods in the Sebapala Sub-catchment. The project will mainstream sustainable rangeland management and restoration into the use of watersheds to combat land degradation, enhance the flow of agroecosystem goods and services, and improve the livelihoods of agro-pastoral communities in the Sebapala Watershed in the Lower Senqu Basin. Relationship to this project: The Sebapala project will be implemented in the Quthing district, which also includes the Letšeng-la-Letsie Ramsar site - one of the prioritized landscapes for the project described in the current project document.

Coordination of activities and information will be promoted, particularly regarding landscape restoration and sustainable land management so that the conservation and sustainable use of plant genetic resources and their habitat is considered. Lessons learned on gender mainstreaming and participatory M&E will also be considered.

- GEF ID 5075 (UNDP) – Reducing Vulnerability from Climate Change in the Foothills, Lowlands, and the Lower Senqu River Basin. The project aims at mainstreaming climate risk considerations in the Land Rehabilitation Programme of Lesotho, for improved ecosystem resilience and reduced vulnerability of livelihoods to climate shocks. Relationship to this project: Lessons learned and information on improving ecosystem resilience will be absorbed into the proposed project’s activities to promote in situ conservation of selected plant genetic resources.

- GEF ID 5124 (FAO) – Strengthening Capacity for Climate Change Adaptation through Support to the IWRM Programme in Lesotho. Project objectives: a) implement sustainable land and water management practices (SLM/W) and resource conservation measures in selected watersheds to reduce vulnerability and enhance adaptive capacity at the community level; and b) strengthen diversified livelihood strategies focusing on crop, livestock, and agroforestry systems at the community level in selected watersheds in the three most vulnerable livelihood zones. Relationship to this project: Lessons learned and information on how climate variability affects natural and social assets such as pasture, livelihoods and land-use systems in Lesotho, will be used to shape activities to promote in situ conservation of selected plant genetic resources and their sustainable harvesting.

- GEF ID 6926 (United Nations Environment Programme [UNEP]) – Strengthening Climate Services in Lesotho for Climate-Resilient Development and Adaptation to Climate Change. The project objective is to strengthen the climate monitoring capabilities, early warning systems and human resources in Lesotho in order to effectively address climate impacts and better plan adaptation to climate change. Relationship to this project: Information regarding climate change and variability generated by the Climate Services in Lesotho will be built into the design and implementation of sustainable harvesting plans, thereby building the climate resilience of the associated value chains.

- GEF ID 9255 (UNDP) – Development of Value Chains for Products derived from Genetic Resources in Compliance with the Nagoya Protocol on ABS and the National Biodiversity Economy Strategy. The project aims at strengthening value chains for products derived from genetic resources that contribute to the equitable sharing of benefits and the conservation of biodiversity, with a focus on bioprospecting of indigenous plant species in Southern Africa. Relationship to this project: Exchange of information regarding R&D.

- GEF ID 5731 (UNDP) – Strengthening Human Resources, Legal Frameworks and Institutional Capacities to Implement the Nagoya Protocol. This global project involving 24 countries, including South Africa and other seven African countries, aims at assisting countries in the development and strengthening of their national ABS frameworks, human resources and administrative capabilities to implement the Nagoya Protocol. Activities will focus on: a) strengthening the legal, policy and institutional capacity to develop national ABS frameworks; b) building trust between users and providers of genetic resources to facilitate the identification of bio-discovery efforts; c) strengthening the capacity of indigenous and local communities to contribute to the implementation of the Nagoya Protocol; and d) implementing a community of practices on ABS and South-South Cooperation mechanisms. Relationship to this project: The project will make use of the lessons learned, best practices, and tools developed under this project, including: a) the development and strengthening of national the legal, policy and institutional ABS frameworks; b) establishing partnerships for bio-discovery between users and providers of genetic resources; c) the development of codes of conduct or guidelines for research on TK and genetic resources; and d) clarifying PIC and MAT requirements between users and providers of TK and biological resources.

- The Wool and Mohair Promotion Project (WAMPP; 2014-2022) funded by IFAD. The project will boost resilience to the adverse effects of climate change, and economic shocks among poor rural people across the country. Activities will target smallholder farmers and other poor rural dwellers, giving special attention to poor rural women and young people.

Relationship to this project: The WAMPP will provide valuable information regarding working with vulnerable groups (e.g., women and herders) in the prioritized landscapes, and on implementation of best practices to protect rangelands that provide habitats for the targeted medicinal plant species.

- Small Grants Programme (SGP), UNDP. The SGP was started in 2007 and has funded over 74 projects, including assistance for the establishment of community botanical gardens and enhancing the capacity of NGOs and community-based organizations for project development and management. The program has had a notable effect on soil and water conservation; and has seen more than 50 species of plants conserved and protected. Projects currently under implementation cover a wide range of areas including biological and physical rehabilitation of rangeland resources, landscape conservation and climate-smart agro technologies, and community participation, including rural youth, women, men, and other vulnerable groups.  Relationship to this project: Lessons learnt, best practices and information developed under the SGP will be taken into consideration during project implementation. UNDP officers from the SGP participated during consultations for the final project design, as an initial step to promote cooperation between the SGP and the project.

| Co-financing source | Co-financing type | Co-financing amount (USD) | Included in project results? | If yes, list the relevant outputs |
| --- | --- | --- | --- | --- |
| Ministry of Defense, National Security and Environment (Government) | In kind | 3,475,000 | No | NA |
| University of Lesotho | In-kind | 525,000 | No | NA |
| UNDP Lesotho | Cash | 500,000 | Yes |  |

Risks and Assumptions:

- Based on application of UNDP’s standard Social and Environmental Screening Procedure (SESP), the overall project risk categorization is moderate (see Annex 5). The key risks relate to excluding marginalized minority groups (herders) in benefit sharing (Standard P.5 and P.13). Appropriate mitigation measures to avoid or minimize the potential negative impacts have been elaborated in the SESP.

- As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office and Project Board. The UNDP Country Office will record progress in the UNDP ATLAS risk log. Risks will be reported as critical when the impact and probability are high (i.e. when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher). Management responses to critical risks, as well as environmental and social grievances, will also be reported to the GEF in the annual PIR. The detailed risk management strategy for the project is included in Annex 6.

- Key project assumptions are as follows: (i) It is expected that the political will exists to implement through project Component 1, the legal and policy reforms needed to support the implementation of the Nagoya Protocol on ABS; (ii) that the national institutions will have the capacity for effective monitoring and enforcement; and, (iii) it is assumed that climate change and variability will be within normal ranges and the project outcomes will not be affected.

Stakeholder engagement:

- The successful implementation of the project will largely depend on effective communication and coordination among the multiple project stakeholders, and the implementation of mechanisms to ensure their participation. The key national and sub-national stakeholders include the MDNSE, DST, the Ministry of Health (MoH), MoW, MTICM, MLGCPA, MAFS, among others; civil servants from these ministries will benefit from training efforts. At the local level, the most relevant stakeholders are communities and community groups (e.g., traditional practitioners, herders, custodians, harvesters, users and TK holders), including women’s groups, and are the primary beneficiaries of the project as they will participate in the key project activities such training and awareness raising. On the other hand, research institutions will also benefit from research training and valuation skills. The project’s Stakeholder Engagement Plan is included in Annex 8, and includes information summarizing the main PPG workshops convened and stakeholder meetings conducted, among other aspects; a list of people consulted during project development is included in Annex 23.

South-South and Triangular Cooperation (SSC/TrC):

- The project will promote south-south cooperation with other countries in the region that are implementing related initiatives (e.g., South Africa); this will be achieved through exchanges with the Country Offices and the UNDP Regional Service Centre for Africa. Technically qualified staff and groups of experts on the issues addressed by the project from these countries will have many opportunities to exchange experiences and knowledge. Finally, successful experiences will have a prominent place in the lessons learned that will be disseminated to ensure their widespread adoption and replication in other African countries. In addition, to bring the voice of Lesotho to global and regional fora, the project will explore opportunities for meaningful participation in specific events where UNDP could support engagement with the global development discourse on access and benefit sharing of genetic and indigenous/traditional knowledge. The project will provide regional cooperation opportunities with countries implementing initiatives on Nagoya Protocol on ABS in Lesotho and Southern Africa.

Gender equality and Women’s Empowerment:

- According to the UNDP Gender Marker Rating, the project is categorized as GEN2: gender equality as a significant objective. During the PPG, a gender analysis for the prioritized landscapes was undertaken and a detailed Gender Action Plan (included as Annex 10) was developed to ensure gender mainstreaming in the project; specific gender-based indicators will be used for monitoring and a gender specialist will be part of the Project Management Unit (PMU) to facilitate improvements to gender equality and women’s empowerment.

Knowledge:

- To achieve the project objectives, working with and through existing platforms is paramount to create synergies needed for transformational change and upscaling. This project contributes to the global commitments towards access and benefit sharing of genetic resources, indigenous and traditional knowledge under the CBD and Kunming-Montreal Global Biodiversity Framework. The project will participate and contribute to the biodiversity interactive platforms for exchange of knowledge and multistakeholder dialogue; contribute to global and regional biodiversity platforms such as the UNDP Biodiversity and Ecosystems Network; SADC Plant Genetic Resources Center. The project will participate and contribute to national events and platforms to showcase best practices that can be replicated or scaled and share lessons and experiences; facilitate exchange visits between stakeholders at project sites to enhance peer to peer learning and knowledge transfer. Knowledge management products will include project reports, policy briefs on bioprospecting, published articles and blogs on access and benefit sharing. The project will seek collaboration and knowledge exchanges with other countries implementing Nagoya Protocol.

Innovativeness, Sustainability and Potential for Scaling Up:

- Through support from this project, Lesotho will for the first time engage comprehensively with ABS, bioprospecting and natural product development issues as they pertain to biological and genetic resources (plant species). The project has been designed to ensure that the results will be sustainable over time, including as they relate to environmental aspects, socioeconomic issues, the institutional framework and governance, and financial resources. Through the activities proposed the stakeholders will pilot initiatives and approaches to accessing genetic resources and knowledge about them (i.e. conservation, collection/harvesting), exploring their potential uses and applications (i.e., bioprospecting, scientific research and investigations) and putting in place mechanisms for sharing the benefits from their use (e.g. bioprospecting, value addition, and new product development).

- Environmental sustainability will be achieved by raising awareness at the local level about the linkages between access to genetic resources and their utilization and the conservation of biodiversity and the sustainable use of its components, in particular within and outside protected areas in the four prioritized landscapes, which will contribute to the conservation of highland and rangeland ecosystems.

- Socio-economic sustainability will be achieved through ABS with multiple capacity building activities for local communities and harvesters of genetic resources, including for women and vulnerable groups (herders). This will be directed towards strengthening their participation in decision-making related to the conservation and management of their plant genetic resources, and to empower them and build ownership that will be essential for the sustainability of project outcomes after project closure. The project includes a Gender Action Plan to ensure gender mainstreaming in project activities, to ensure that women and other marginalized groups benefit fairly from the project interventions, and that they are empowered to become active agents and participants in the implementation of the ABS regime beyond the life of the project.

- Institutional and governance sustainability will be achieved principally by building a robust enabling environment under Component 1. The project will help put in place a diversity of policies, regulations, strategies and guidelines governing the conservation, sustainable use and benefit sharing from the utilization of biological and genetic resources in the country. Sustainable governance, monitoring and enforcement will be further enhanced by the establishment of national guidelines for enforcing the ABS regulatory framework that will be developed, and by developing appropriate capacity in the National Focal Point, Competent National Authorities and Checkpoints. Under Component 2, the project will contribute to institutional sustainability by establishing strategic partnerships among the country’s research and academic community, private sector stakeholders, government and public institutions, and the local communities that will participate in training activities.

- Financial sustainability will be promoted by strengthening ABS value chains. This will enable small/medium-scale community-based enterprises to increase their access to markets for natural products from selected genetic resources, and, thereby, increase their incomes. Financial sustainability will also be achieved by supporting bioprospecting and natural product development initiatives that will maximise the commercial value of genetic resources and TK, while creating a fair compensation system that benefits providers and users of those resources. Economic valuation of selected genetic resources with known commercial and intangible values will provide valuable information to support long-term commercial strategies. Finally, the project will develop an exit strategy in its final year of operation, in order to detail actions required for sustainability and to secure agreement among key stakeholders to ensure the sustainability of results.

- The project will focus on capacity building s an entry point to facilitating future practical application of the Nagoya Protocol. The results of this work will inform future directions taken by the country in terms of the conditions required (i.e. policies, laws, and regulations; technical skills and capacity; and resources, including infrastructure and technology) for genetic resources to be conserved, sustainably used, and the benefits from their use better captured and equitably shared. The project outcomes will leave Lesotho better equipped to further explore the benefits that can accrue from fully developing the sector related to genetic resources and their associated industries. Once these benefits are realized and equitably shared, the country can invest strategically in this sector as a new economic growth pathway (i.e. develop a biodiversity economy based on bioprospecting and natural product development) to help drive forward the country’s development agenda.

Digital Solutions:

The project will facilitate establishment and operationalization of a single web-based permit system to apply for permits for bioprospecting, including when traditional knowledge is involved, and for government authorities to review and approve applications. The e-permitting system will allow monitoring compliance (including tracking of utilization of genetic resources and TK and the commercialization of derived products) and serve as source of information that will feed into the national CHM and for the government to report on the implementation of the Nagoya Protocol on ABS.

- Project Management

Cost Efficiency and Effectiveness

- Cost efficiency of the project will be achieved through a) applying best practices in the project design; and, b) establishing close collaboration with related projects and donors by leveraging resources for all project components. In addition, appropriate levels of co-financing have been secured from MDNSE, NUL, and UNDP, which will increase the cost efficiency and impact of the project.

- Component 1 benefits from ongoing or planned investments by the GoL (e.g., DoE/MDNSE and MLCA) in updating the Biodiversity Bill of 2021, to include, inter alia, provisions related to ABS  (Output 1.1.1).  The experience of national NGOs (e.g. the Transformation Resource Centre [TRC], and Lesotho Council of Non- Governmental Organizations [LCN]), and the MLGCPA, will be used to shape the development of biocultural community protocols, which will govern management, ownership, access rights and benefit sharing rules and procedures (Output 1.3.2) and guidelines and procedures for obtaining PIC and MAT (Output 1.3.1), as well as for developing codes of conduct, best-practices and standards that ensure sustainable harvesting, fair and equitable benefit-sharing. The project will also make use of the lessons learned, experiences, and tools developed under the GEF-UNDP global project Strengthening Human Resources, Legal Frameworks and Institutional Capacities to Implement the Nagoya Protocol (GEF Project ID 5731).

- Under Outcome 2, the project will prioritize funding for research centers and universities (e.g., NUL) that have mobilized co-financing, so that project funds have a larger impact in identifying selected genetic resources of medicinal value and enhancing capacities for future development of products for medicinal use.

- Under Outcome 3, the project will cooperate closely with the Department of Gender/MGYSR to establish working linkages with key stakeholders, to mainstream gender issues related to ABS and implement the Gender Action Plan (Output 3.1.1). In addition, the project will make use of the lessons learned, experiences, and tools developed under the GEF Project ID 5731 regarding knowledge management (i.e. community of practices on ABS) and South-South Cooperation mechanisms (Outputs 3.2.1 and 3.2.2).

- The project will seek to maximize the financial resources made available for project activities, which will be included in Annual Work Plans, to be discussed and approved by the Project Board to ensure that proposed actions are relevant and necessary. Cost-effectiveness will be taken into account when implementing project activities without compromising the quality of the outputs. When hiring third party consultants/service providers, the project will follow a standard recruitment and advertising process to have at least three competitors for each consultant position. Selection will be based on qualifications, technical experience and financial proposal, to ensure hiring the best consultant (individual or organization) for an optimal price. Economy fares will be applied for necessary air and road travel, and appropriate lodging facilities will be provided to the project staff to ensure staff safety and cost-effectiveness. Cost-efficiency has also been built into the project’s plan for delivery by limiting the number of   consultants to be hired, which will cut down on the procurement burden and transaction times and costs.

- Expenses will be accounted for according to UNDP rules and in line with GEF policy. The project will follow a tendering process for purchase of equipment and any printing/publishing that accounts for more than USD 10,000, comparing at least three vendors. In case there is a single vendor only for any activity, appropriate official norms will be followed to obtain approval from UNDP to proceed. By housing the Project Management Unit (PMU) within DoE cost-effectiveness will also be achieved as this will reduce management and operational costs (e.g., rent and utilities) and will contribute to building project ownership by the GoL.

Project Management

- The PMU will be based at the MDNSE headquarters in Maseru and will comprise four full time staff, including a Project Manager, a Finance and Administration Officer (who will provide operational support), and two Project Field Facilitators, and a part-time Gender and Safeguards Officer. A Communications and Knowledge Management Consultant will provide part-time services to the project, and a Technical Advisor will be appointed on a part-time and consultancy basis to provide technical backstopping and strategic guidance to the project team, and to support the M&E and quality assurance functions. Project staff and consultants will travel to prioritized landscapes in Lesotho according to need. The PMU will oversee the day-to-day execution of project activities and will have responsibility for, inter alia: a) operational planning, management, and execution of the project, including the direct supervision of project activities sub-contracted to specialists and other institutions; b) coordinating the management of financial resources and procurement; c) reporting on the application of resources and results achieved; d) preparing reports and any proposals for adaptive management of the project, if required, and based on inputs from the project M&E plan; e) promoting inter-institutional synergies; and, f) disseminating project results.

- The PMU will liaise regularly with technical staff based in the MDNSE and will therefore benefit from their expertise and input of time. A variety of government Institutions (MDNSE, Ministry of Local Government and Chieftainship Affairs, Ministry of Forestry, Rangelands and Soil Conservation, Ministry of Water, Ministry of Agriculture and Food Security, Ministry of Trade and Industry, Ministry of Health, Department of Science and Technology) will provide overall strategic oversight to this project, to promote alignment with future programming and ensure greater sustainability.

- Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): Goal 5 – Gender equality; Goal 8 – Decent work and economic growth; Goal 9 – Industry, innovation and infrastructure; Goal 10 – Reduced inequalities; Goal 12 – Responsible consumption and production; Goal 15-Life on Land. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: By 2023, the people of Lesotho use natural resources in a more sustainable manner and the marginalized and most vulnerable are increasingly resilient |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan: 4.1 Natural resources protected and managed to enhance sustainable productivity and livelihoods |  |  |  |  |  |
| Project Objective: | To strengthen national and local capacities to implement the Nagoya Protocol on Access and Benefit Sharing (ABS) with a focus on traditional knowledge on medicinal plants in Lesotho and the potential for bioprospecting. |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks/Assumptions |
|  | Mandatory indicator 1: # of direct project beneficiaries disaggregated by sex (at least 50% women). | 39,060 people with zero benefits (male: 18,977; female: 20,083) Sehlabathebe National Park: a) Male: 4,108 with zero benefit; b) Female: 4,159 with zero benefit Bokong Nature Reserve: a) Male: 4,279 with zero benefit; b) Female: 4,454 with zero benefit Tšehlanyane e National Park: a) Male: 5,390 with zero benefit; b) Female = 5,610 with zero benefit Letšeng-la-Letsie Ramsar site: a) Male: 5,200 with zero benefit; b) Female = 5,860 with zero benefit | 9,766 people with project benefits (male: 4,745; female: 5,021) Sehlabathebe National Park: a) Male: 1,027; b) Female: 1,039 Bokong Nature Reserve: a) Male: 1,070; b) Female = 1,114 Tšehlanyane National Park: a) Male: 1,348; b) Female; 1,403 Letšeng-la-Letsie Ramsar site: a) Male: 1,300; b) Female = 1,465 | 19,531 people with project benefits (male: 9,489; female: 10,042) Sehlabathebe National Park: a) Male: 2,054; b) Female: 2,080 Bokong Nature Reserve: a) Male: 2,140; b) Female: 2,227 Tšehlanyane National Park: a) Male: 2,695; b) Female: 2,805 Letšeng-la-Letsie Ramsar site: a) Male: 2,600; b) Female = 2,930 | Data sources: Gender-based surveys Project final report Updated Gender Action Plan and related reports |
|  | Indicator 2: Legal, policy and institutional frameworks in place for access and benefit sharing of natural resources, biodiversity and ecosystems. | No legal, policy and institutional framework related to ABS | Drafts of key ABS legislation, policies, and guidelines under discussion 40% of the Institutional Capacity Development Strategy for the ABS framework implemented. | Functional legal, policy and institutional framework related to ABS in place | Data sources: Official gazette Project final report National reports on implementation of the Nagoya Protocol |
|  |  |  |  |  | Risks: Project time framework not long enough to achieve the proposed legal, policy and institutional changes Assumptions: Willingness by decision makers to implement the Nagoya Protocol on ABS. |
|  |  |  |  |  | Risks: Gender barriers are difficult to overcome limiting women participation especially in rural areas Herders are relatively less educated and this might bring a challenge in their uptake of the intervention On-going conflict in Letšeng–la–Letsie between communities of two area chiefs might slow progress in the implementation of the project Assumptions: Continued interest from women and men to participate in the project Improvement assumed at 25 percent at mid-term and 50 percent at project end Involvement of NGOs as partners will support herders’ capacity building and address grievances from herders and concerned communities. |
| Component 1 | Enabling institutional capacity and regulatory framework strengthened to support implementation of the Nagoya Protocol on ABS |  |  |  |  |
| Outcome 1.1: Functional national ABS policy and regulatory framework operational and supportive of ABS from the use of genetic resources Outcome 1.2: Capacity of national institutions to develop, implement and enforce national legislative, administrative or policy measures on ABS strengthened Outcome 1.3: Management, ownership and access rights, rules and procedures over access and utilization of genetic resources defined, clarified and encoded in the legal system (e.g. by-laws/ community protocols) | Indicator 3: ABS policy-, legal- and regulatory – framework with gender considerations | - A national environmental policy without ABS regulations - No ABS in TK regulations - No intellectual property (IP) rights guidelines related to ABS | - ABS incorporated into the National Environmental Policy and the Biodiversity Bill, including gender considerations related to ABS | - ABS in TK regulations - IP rights guidelines related to ABS in place | Data sources: Drafts of policies and regulations Official gazette |
|  |  |  |  |  | Risks: Project time framework not long enough to achieve the proposed policy, legal and regulatory reforms Assumptions: Continued political will to strengthen the national regulatory framework to support implementation of the Nagoya Protocol on ABS |
|  | Indicator 4: Improved capacity of institutions to develop, implement, and enforce ABS policies and regulations increased as measured by the UNDP ABS Capacity Development Scorecard: - CR 1: Capacity to engage and build consensus among all stakeholders. - CR2: Capacities to generate, access and use information and knowledge - CR 3: Capacities for strategy, policy and legislation development - CR 4: Capacities for management and implementation - CR 5: Capacities to monitor and evaluate | - CR 1: - Traditional Practitioners = 67% - Community Conservation Forums = 58% - Community Councils = 67% - Private Sector = 58% - CR 2: - Academia = 45% - Community Conservation Forums = 40% - Department of Environment = 45% - CR 3: - Community Conservation Forums = 42% - Community Councils = 33% - National Parks = 42% - Department of Environment = 42% - CR 4: - Department of Environment = 63% - Department of Range Resources Management = 63% - Department of Forestry = 63% - CR 5: - Department of Range Resources Management = 25% - Department of Forestry = 25% - National Parks = 25% - Community Conservation Forums = 25% - Community Councils = 25% - Department of Environment = 25% | - CR 1: - Traditional Practitioners = 81% - Community Conservation Forums = 70% - Community Councils = 89% - Private Sector = 77% - CR 2: - Academia = 60% - Community Conservation Forums = 53% - Department of Environment = 60% - CR 3: - Community Conservation Forums = 56% - Community Councils = 44% - National Parks = 56% - Department of Environment = 56% - CR 4: - Department of Environment = 84% - Department of Range Resources Management = 84% - Department of Forestry = 84% - CR 5: - Department of Range Resources Management = 33% - Department of Forestry = 25% - National Parks = 33% - Community Conservation Forums = 33% - Community Councils = 33% - Department of Environment = 33% | - CR 1: - Traditional Practitioners = 90% - Community Conservation Forums = 78% - Community Councils = 100% - Private Sector = 93% - CR 2: - Academia = 72% - Community Conservation Forums = 64% - Department of Environment = 72% - CR 3: - Community Conservation Forums = 68% - Community Councils = 53% - National Parks = 68% - Department of Environment = 68% - CR 4: - Department of Environment = 100% - Department of Range Resources Management = 100% - Department of Forestry = 100% - CR 5: - Department of Range Resources Management = 40% - Department of Forestry = 40% - National Parks = 40% - Community Conservation Forums = 40% - Community Councils = 40% - Department of Environment = 40% | Data sources: Updated UNDP ABS Capacity Development Scorecard Capacity building participation lists |
|  |  |  |  |  | Risks: Knowledge drain and implementation capacity constraints at government due to the staffing limitations Assumptions: Interest from stakeholders to participate in the training and using tools to be provided by the project Beneficiaries apply additional knowledge acquired The assumed increase is 25% of the baseline per annum |
|  | Indicator 5: Administrative procedures for users and providers of genetic resources to develop, implement and monitor ABS agreements with proper Prior Informed Consent (PIC), Mutually Agreed Terms (MAT) and Benefit Sharing (BS) principles and guidelines | No administrative procedures for implementing ABS available | Drafts of administrative documents for review: a) Guidelines and procedures for obtaining PIC and MAT b) Biocultural community protocols governing ABS c) Codes of conduct, best-practices and standards for equitable benefit-sharing | Administrative procedures for users and providers of genetic resources approved: a) Guidelines and procedures for obtaining PIC and MAT b) Biocultural community protocols governing ABS c) Codes of conduct, best-practices and standards for equitable benefit-sharing | Data sources: Final drafts of administrative documents and principles and guidelines |
|  |  |  |  |  | Risks: Ownership and access rights not clearly defined Assumptions: Continued interest from decision makers to support implementation of the Nagoya Protocol on ABS |
| Outputs: Output 1.1.1: National Environment Policy of 1998 and Biodiversity Bill of 2021 reviewed to address ABS in accordance with the Nagoya Protocol. Output 1.1.2: National ABS, bioprospecting, traditional knowledge (TK), and intellectual property rights (IPRs) regulations developed, reviewed, updated, and presented to parliament for approval. Output 1.1.3: Local/Community Councils By-laws (guidelines) in the prioritized districts on ABS reviewed and finalized considering national frameworks on ABS and biodiversity Output 1.1.4: ABS and TK Strategy developed. Output 1.2.1: Capacities of National Focal Point, Competent National Authorities and Checkpoints enhanced. Output 1.2.2: Institutional Capacity Development Strategy for the ABS framework implementation, monitoring, enforcement and compliance developed and rolled-out. Output 1.2.3: National guidelines for enforcing ABS regulatory framework developed and implemented. Output 1.2.4. A national clearing-house mechanism in place to assist in the collection, provision, and dissemination of ABS information. Output 1.3.1: Guidelines and procedures for obtaining Prior Informed Consent (PIC) and Mutually Agreed Terms (MAT) developed and approved. Output 1.3.2: Guideline for developing biocultural community protocols governing management, ownership, access rights, and benefit-sharing rules and procedures defined and adopted. Output 1.3.3: Codes of conduct, best-practices, guidelines and standards that ensure ethical bioprospecting, sustainable harvesting, fair and equitable benefit-sharing established for industry and research sectors active in bioprospecting. |  |  |  |  |  |
| Component 2 | Building capacities for bioprospecting and value-addition of genetic resources |  |  |  |  |
| Outcome 2.1: Opportunities for bioprospecting strengthened with improved research capabilities to add value to genetic resources. | Indicator 6: Number of people trained to promote bioprospecting | 0 | 75 | 200 | Data sources: Training reports and lists of participants to training events |
|  |  |  |  |  | Risks: Loss of capacities due to high staff turnover in institutions Assumptions: Continued interest from the private and public to conduct studies and research on genetic resources |
|  | Indicator 7: Number of research centres equipped | 0 | At least three (3) | At least three (3) | Data sources: Procurement plans, invoices, and equipment inventories |
|  |  |  |  |  | Risks: Delays in purchasing / procurement processes (import processes). Assumptions: Active engagement of research centres |
| Outcome 2.2: Enhanced capacity of key stakeholders, including ILCs especially women, to participate in ABS and bioprospecting processes. | Indicator 8: Number of research collaboration agreements established between users (researchers and academia) and providers (ILCs) of genetic resources with considerations for gender equity | 0 | At least one (1) | At least two (2) | Data sources: Draft of agreements Signed agreements |
|  |  |  |  |  | Risks: Conditions not met to establish ABS agreements Assumptions: Interest from stakeholders, including local communities in entering into ABS agreements |
|  | Indicator 9: Number of key/local stakeholders trained (50% men and 50% women). | 0 | 350 | 1,000 | Data sources: Training reports and lists of participants to training events |
|  |  |  |  |  | Risks: Delays in training activities. Assumptions: Available markets Interest from men and women/ILCs to participate in ABS and bioprospecting processes. |
| Outputs: Output 2.1.1: National research and development strategy on bioprospecting, including role of traditional medical practitioners developed and implemented. Output 2.1.2: National research centres (e.g., NUL Department of Agricultural Research, and Katse Botanical Garden) strengthened to conduct R&D on genetic resources of medicinal plants, in collaboration with traditional medical practitioners’ associations /groups and international partners on bioprospecting. Output 2.1.3: A comprehensive valuation of genetic resources with known commercial and intangible values (cultural and spiritual) conducted includes surveys to assess their conservation status. Output 2.1.4. E-permitting system for bio prospectors in place. Output 2.2.1: Training program for small/medium-scale community-based organizations and enterprises and for national parks implemented for: a) negotiation of PIC, MAT, and ABS agreements; b) development of community protocols; and c) contribution of ABS to conservation and sustainable use of biodiversity. Output 2.2.2: Experience exchange program raises awareness about regional/international ABS initiatives. Output 2.2.3: Model biocultural community protocol developed considering medicinal plants with potential for bioprospecting. |  |  |  |  |  |
| Component 3 | Gender mainstreaming and Knowledge Management |  |  |  |  |
| Outcome 3.1: Gender inclusive awareness on sustainable utilization, conservation and access to and benefit sharing from the use of genetic resources enhanced | Indicator 10: Level of awareness among key stakeholders about the provisions of the Nagoya Protocol on ABS (measured by KAP/B index) | ≤10 % | 33.75% | 75.94% | Data sources: Updated KAP/B index Risks: Project time period too short to have a noticeable impact on level of awareness Assumptions: Wide-ranging and timely dissemination |
|  | Indicator 11: Ratio of women/ men including herders by age benefitting from project interventions | 0% | 30% | 50% | Data sources: Gender-based surveys Updated Gender Action Plan and related reports Project Completion reports |
|  | Outputs: Output 3.1.1: Knowledge, attitudes, practices, and behavior (KAP/B) assessment/surveys carried out and an awareness-raising programme on ABS developed and implemented. Output 3.1.2 Gender strategy developed and used to guide project implementation, monitoring, and reporting. |  |  |  |  |
| Component 4 | Monitoring and & Evaluation |  |  |  |  |
| Outcome 4.1: Participatory M&E results are used to guide adaptive management, collate and share lessons, in support of up-scaling. | Indicator 12: Quality rating of project reports (PIR, MTR and TE) as per UNDP/GEF requirements | NA | Satisfactory | Satisfactory | Risks: Inadequate M&E capacity of project staff Assumptions: Project resources will be adequate to build the capacity of project staff and partners on M&E. Bureau of Statistics (BOS) strengthened to collect gender disaggregated data on genetic resources development |
| Outputs: Output 4.1: Participatory monitoring, evaluation and learning strategy developed and implemented to support project management, collate and disseminate lessons. |  |  |  |  |  |

- Monitoring and Evaluation (M&E) Plan

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP (including guidance on GEF project revisions) and UNDP Evaluation Policy The UNDP Country Office is responsible for ensuring full compliance with all UNDP project M&E requirements including project monitoring, UNDP quality assurance requirements, quarterly risk management, and evaluation requirements.

- Additional mandatory GEF-specific M&E requirements will be undertaken in accordance with the GEF Monitoring Policy and the GEF Evaluation Policy and other relevant GEF policies. The M&E plan and budget included below will guide the GEF-specific M&E activities to be undertaken by this project.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed – including during the Project Inception Workshop - and will be detailed in the Inception Report.

Minimum project monitoring and reporting requirements as required by the GEF:

- Inception Workshop and Report: A project inception workshop will be held within 2 months from the First disbursement date, with the aim to:

- Familiarize key stakeholders with the detailed project strategy and discuss any changes that may have taken place in the overall context since the project idea was initially conceptualized that may influence its strategy and implementation.

- Discuss the roles and responsibilities of the project team, including reporting lines, stakeholder engagement strategies and conflict resolution mechanisms.

- Review the results framework and monitoring plan.

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP and other stakeholders in project-level M&E.

- Update and review responsibilities for monitoring project strategies, including the risk log; SESP report, Social and Environmental Management Framework (where relevant) and other safeguard requirements; project grievance mechanisms; gender strategy; knowledge management strategy, and other relevant management strategies.

- Review financial reporting procedures and budget monitoring and other mandatory requirements and agree on the arrangements for the annual audit.

- Plan and schedule Project Board meetings and finalize the first-year annual work plan. Finalize the TOR of the Project Board.

- Formally launch the Project.

- The Project Manager will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and will be approved by the Project Board.

- GEF Project Implementation Report (PIR): The annual GEF PIR covering the reporting period July (previous year) to June (current year) will be completed for each year of project implementation. UNDP will undertake quality assurance of the PIR before submission to the GEF. The PIR submitted to the GEF will be shared with the Project Board. UNDP will conduct a quality review of the PIR, and this quality review and feedback will be used to inform the preparation of the subsequent annual PIR.

- GEF and/or LDCF/SCCF Core Indicators: The GEF and/or LDCF/SCCF Core indicators included as Annex 17 will be used to monitor global environmental benefits and will be updated for reporting to the GEF prior to MTR and TE. Note that the project team is responsible for updating the core indicators status. The updated monitoring data must be shared with MTR/TE consultants prior to required evaluation missions, so these can be used for subsequent ground truthing. The methodologies to be used in data collection have been defined by the GEF and are available on the GEF.

- Independent Mid-term Review (MTR): An independent mid-term review (MTR) will be completed by the mid-point of the project. The terms of reference, the MTR process and the final MTR report will follow the standard templates and MTR guidance for UNDP-supported GEF-financed projects available on the UNDP Evaluation Resource Center. The MTR must be submitted to the GEF by the mid-point of the project or 31 May 2026 but no later than 36 months after CEO Endorsement.

- Provisions must be taken to complete and submit the MTR within the submission deadline. Therefore, the MTR process must start no later than 6 months before the expected date of submission of the MTR.

- The MTR will be ‘independent, impartial and rigorous’. The evaluator(s) that UNDP will hire to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be reviewed. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project under review.

- The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the MTR process. Additional quality assurance support is available from BPPS/NCE.

- The final MTR report will be publicly available in English and will be posted on the UNDP ERC by 31 May 2026. A management response to MTR recommendations will be posted in the ERC within six weeks of the MTR report’s submission to the GEF.

- Terminal Evaluation (TE): An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terms of reference, the evaluation process and the final TE report will follow the standard templates and TE guidance for UNDP-supported GEF-financed projects available on the UNDP Evaluation Resource Center. TE must be submitted to the GEF no later than 6 months after the Completion Date. This is a hard deadline that, if not met, can only be extended through a formal extension request.

- To meet the submission deadline, final TE reports must be completed and submitted to BPPS NCE team no later than 2 months in advance of the deadline to allow sufficient time for internal review/clearance that is required prior to submission.

- Provisions must be taken to complete and submit the TE within the submission deadline. Therefore, TE must start no later than 8 months before the expected date of submission of the TE (or 11 months prior to the estimated operational closure date).

- The evaluation will be ‘independent, impartial and rigorous’. The evaluator(s) that UNDP will hire to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project being evaluated.

- The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the terminal evaluation process. Additional quality assurance support is available from BPPS NCE.

- The final TE report will be publicly available in English and posted on the UNDP ERC by the TE submission by 30 September 2028. A management response to the TE recommendations will be posted to the ERC within six weeks of the TE report submission to the GEF.

- Final Report: The project’s final GEF PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

- In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans.

Monitoring Plan: The project results, corresponding indicators and mid-term and end-of-project targets in the project results framework will be monitored by the Project Management Unit annually, and will be reported in the GEF PIR every year, and will be evaluated periodically during project implementation. If baseline data for some of the results indicators is not yet available, it will be collected during the first year of project implementation. Project risks, as outlined in the risk register, will be monitored quarterly. A detailed monitoring plan will be developed during the inception phase of the project implementation.

| Monitoring Activity |  |  |
| --- | --- | --- |
|  | Frequency/Timeframe | Expected Action |
| Inception Workshop and Report | Inception Workshop within 2 months of the First Disbursement | As per above description |
| Track results progress | Annually and at mid-point and closure | Slower than expected progress will be addressed by project management. |
| Monitor and Manage Risk | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |
| Monitor implementation of i) ESMF; ii) Gender Action Plan iii) Herders Engagement Plan; iv) Stakeholder Participation and Engagement Plan; v) Grievance Redress Mechanism; vi) Traditional Healers and Herbalists Engagement Plan. | Ongoing | Document and report implementation of safeguards measures and emerging issues |
| Supervision Missions | Annually | Provide second level oversight support to CO and project teams |
| Learning and Learning Missions | As needed | Relevant lessons are captured by the project team and used to inform management decisions. |
| Annual Project Quality Assurance | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |
| Review and Make Course Corrections | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |
| Annual GEF Project Implementation Report (PIR) | Annually typically between June-September | Mandatory contribution by Project Team, CO and RTA. Strengths and weaknesses will be reviewed by project management and used to inform decisions to improve project performance |
| Project Review (Project Board) | At least once a year | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |

## Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output | UNSDCF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Independent Mid-Term Review (MTR) | NA | 4.1 Natural resources protected and managed to enhance sustainable productivity and livelihoods | By 2023, the people of Lesotho use natural resources in a more sustainable manner and the marginalized and most vulnerable are increasingly resilient. | By 31 May 2026 | UNDP, DoE, PSC, RPs, Beneficiaries |
| Independent Terminal Evaluation (TE) | NA | 4.1 Natural resources protected and managed to enhance sustainable productivity and livelihoods | By 2023, the people of Lesotho use natural resources in a more sustainable manner and the marginalized and most vulnerable are increasingly resilient. | By 30 Sep 2028 | UNDP, DoE, PSC, RPs, Beneficiaries |

Monitoring and Evaluation Budget for project execution

| GEF M&E requirements to be undertaken by Project Management Unit (PMU) | Indicative costs (US$) |
| --- | --- |
| Inception Workshop and Report | GEF Grant: $8,500 Co-financing: None |
| M&E required to report on progress made in reaching GEF core indicators and project results included in the project results framework | GEF Grant: $2,000 at Mid-term) & $2,000 (at Terminal stage) Co-financing: None |
| Preparation of the annual GEF Project Implementation Report (PIR) | GEF grant: none Co-financing: none |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | GEF grant: $7,500 ($1,500/yr) Co-financing: none |
| Monitoring of Stakeholder Engagement Plan | GEF grant: $15,000 ($3000/yr) Co-financing: none |
| Monitoring of Gender Action Plan | GEF grant: $7,500 ($1,500/yr) Co-financing: none |
| Monitoring and Evaluation visits and validation workshops | GEF grant: $10,000 ($7,500 (1,500/yr), $1,000 for yr 1 and $,1500 for yr 2 Co-financing: $17,500- ($7,500 for yr 3 & $10, yr 5) |
| Project board meetings | GEF grant: $12,000 ($2,400/year for 5 yrs) Co-financing: $2,500 ($500 yr 5 yrs) |
| Learning missions | GEF grant: none Co-financing: none |
| Supervision missions | GEF grant: None Co-financing: None |
| Independent Mid-term Review (MTR): | GEF grant: $30,650 Co-financing: none |
| Independent Terminal Evaluation (TE): | GEF Grant: $40,500 Co-financing: none |
| TOTAL indicative COST | GEF grant: US$135,650 Co-financing: US$20,000 |

- Governance and Management Arrangements

Section 1: General roles and responsibilities in the projects’ governance mechanism

Implementing Partner:

- The Implementing Partner for this project is the Ministry of Defense, National Security and Environment (MDNSE) of Lesotho.

- The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

- The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Overseeing the management of project risks as included in this project document and new risks that may emerge during project implementation.

- Procurement of goods and services, including human resources.

- Financial management, including overseeing financial expenditures against project budgets.

- Approving and signing the multiyear workplan.

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

Responsible Parties:

- The implementing partner may enter into a written agreement with other organizations, known as responsible parties, to provide goods and/or services to the project, carry out project activities and/or produce outputs using the project budget. Implementing partners use responsible parties to take advantage of their specialized skills, to mitigate risk and to relieve administrative burdens.

- By definition, UNDP cannot be a responsible party in a UNDP project. In cases when UNDP provides support services to a project, UNDP does so in a separate capacity termed country office support (COS) and this must be pre-approved by the GEF.

- For projects implemented by partners other than UNDP, the relevant legal instrument of the partner institution should be used to engage Responsible Parties. Responsible parties are directly accountable to the implementing partner in accordance with the terms of their agreement or contract with the implementing partner.

- Given that responsible parties play an execution role and are directly accountable to the implementing partner, responsible parties should never serve on the Project Board to avoid a conflict of interest.

- Note that responsible parties are not required to be engaged by a UNDP legal instrument unless UNDP is the Implementing Partner of the project. If UNDP is the implementing partner for this project, or UNDP provides country office support (support to NIM) which includes the engagement of responsible parties by UNDP on behalf of the IP (if approved by the GEF), and the responsible parties have been identified, include the legal instruments used by UNDP to engage a responsible party in Annex to this Project Document. For further guidance on the selection and engagement of Responsible Parties please refer to the relevant section of the PPM.

- Project stakeholders and target groups: Local project committees will be established at the local level where project activities will be implemented; through these committees, local partners will have the opportunity to participate in decision making with regard to project management, including implementation of plans and project reviews, and also with respect to the technical aspects of the project. In addition, at the local level the communities, local organizations, and the private sector will have ample participation in decision-making, agreements, and dialogue for promoting conservation, sustainable utilization and fair and equitable benefit-sharing from Lesotho's Medicinal Plants for in the prioritized landscapes.

- UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes overseeing project execution undertaken by the Implementing Partner to ensure that the project is being carried out in accordance with UNDP and GEF policies and procedures and the standards and provisions outlined in the Delegation of Authority (DOA) letter for this project. The UNDP GEF Executive Coordinator, in consultation with UNDP Bureaus and the Implementing Partner, retains the right to revoke the project DOA, suspend or cancel this GEF project. UNDP is responsible for the Project Assurance function in the project governance structure and presents to the Project Board and attends Project Board meetings as a non-voting member.

- A firewall will be maintained between the delivery of project oversight and quality assurance performed by UNDP and charged to the GEF Fee and any support to project execution performed by UNDP (as requested by and agreed to by both the Implementing Partner and GEF) and may be charged to the GEF project management costs (only if approved by GEF). The segregation of functions and firewall provisions for UNDP in this case is described in the next section.

- UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes overseeing project execution undertaken by the Implementing Partner to ensure that the project is being carried out in accordance with UNDP and GEF policies and procedures and the standards and provisions outlined in the Delegation of Authority (DOA) letter for this project. The UNDP GEF Executive Coordinator, in consultation with UNDP Bureaus and the Implementing Partner, retains the right to revoke the project DOA, suspend or cancel this GEF project. UNDP is responsible for the Project Assurance function in the project governance structure and presents to the Project Board and attends Project Board meetings as a non-voting member.

- A firewall will be maintained between the delivery of project oversight and quality assurance performed by UNDP and charged to the GEF Fee and any support to project execution performed by UNDP (as requested by and agreed to by both the Implementing Partner and GEF) and may be charged to the GEF project management costs (only if approved by GEF). The segregation of functions and firewall provisions for UNDP in this case is described in the next section.

- The UNDP Resident Representative assumes full responsibility and accountability for oversight and quality assurance of this Project and ensures its timely implementation in compliance with the GEF-specific requirements and UNDP’s Programme and Operations Policies and Procedures (POPP), its Financial Regulations and Rules and Internal Control Framework. A representative of the UNDP Country Office will assume the assurance role and will present assurance findings to the Project Board, and therefore attends Project Board meetings as a non-voting member.

- UNDP project support: The Implementing Partner and GEF OFP have requested UNDP to provide support services in the amount of USD24,697 for the full duration of the project, and the GEF has agreed for UNDP to provide such execution support services provided, however, that such costs will not be charged to the project budget but will be fully covered by non-GEF resources (UNDP Co-financing amount). The execution support services – whether financed from the project budget or other sources - have been set out in detail and agreed between UNDP Country Office and the Implementing Partner in a Letter of Agreement (LOA). This LOA is attached to this Project Document.

- To ensure the strict independence required by the GEF and in accordance with the UNDP Internal Control Framework, these execution services will be delivered independent from the GEF-specific oversight and quality assurance services.

Section 2: The project organizational structure

District-level Project Technical Committee

District Administrators (Co-chairs)

District Council Secretaries

Chairpersons of CC

Participating CC Secretaries

District Environmental Officers

Department of Range

Police

District Customs (LRA) Officers

Principal Chiefs

Project Manager

CBOs, representation of marginalized groups

Traditional practitioners’ association (Moetlo le bongaka) representation

Project Board/Steering Committee

Development Partner

UNDP Resident Representative

Project Executive

Ministry of Tourism, Environment and Culture (MDNSE)

Beneficiary Representative:

Private Sector, NGO, academia, and other Government Ministries

Three Tier Project Assurance (country, regional and global)

UNDP Lesotho Programme Officer; Regional Technical Advisor; Principal Technical Advisor

Implementing Partner MDNSE- Project Coordinator

Project Governance Arrangements

UNDP CO Support to Implementation

Identification and recruitment of national and international consultants

Procurement of goods, services, and equipment

Direct Payments

Project Support (PMU)

Project Manager, Gender and Safeguards Officer, Field Facilitators, Driver, Finance and Administration Officer Technical Advisor, Communications and Knowledge Management

Local-level Project Implementation Committee

Project Field Facilitators

Project Manager

District Environment Officers (Chairperson)

Department of Range

District Customs (LRA) Officers

Police

CBO

Representation of marginalized groups (women, herders), Grazing association representatives

Traditional practitioners’ association (Moetlo le bongaka)

First line of defense

- UNDP oversight of project support to IP cannot be UNDP staff providing Project assurance or providing programmatic oversight support to the RR.

Second line of defense

- Regional Bureau oversees RR and Country Office compliance at portfolio level.

- BPPS NCE RTA oversees technical quality assurance and GEF compliance. BPPPS NCE PTA oversees RTA function.

- UNDP GEF Executive Coordinator and Regional Bureau Deputy Director can revoke DOA/cancel /suspend project or provide enhanced oversight.

Section 3: Segregation of duties and firewalls vis-à-vis UNDP representation on the project board:

- As noted in the Minimum Fiduciary Standards for GEF Partner Agencies, in cases where a GEF Partner Agency (i.e. UNDP) carries out both implementation oversight and execution of a project, the GEF Partner Agency (i.e. UNDP) must separate its project implementation oversight and execution duties, and describe in the relevant project document a: 1) Satisfactory institutional arrangement for the separation of implementation oversight and executing functions in different departments of the GEF Partner Agency; and 2) Clear lines of responsibility, reporting and accountability within the GEF Partner Agency between the project implementation oversight and execution functions.

- In this case, UNDP’s implementation oversight role in the project – as represented in the project board and via the project assurance function – is performed by the Resident Representative and Programme Specialist, Energy and Environment. UNDP’s execution role in the project (as requested by the implementing partner and approved by the GEF) is performed by the Procurement Associate; Finance Associate and Human Resource Analyst who will report to the Operations Analyst.

Section 4: Roles and Responsibilities of the Project Organization Structure:

- Project Board: All UNDP projects must be governed by a multi-stakeholder board or committee established to review performance based on monitoring and evaluation, and implementation issues to ensure quality delivery of results. The Project Board (also called the Project Steering Committee) is the most senior, dedicated oversight body for a project.

The two main (mandatory) roles of the project board are as follows:

- High-level oversight of the execution of the project by the Implementing Partner (as explained in the “Provide Oversight” section of the POPP). This is the primary function of the project board and includes annual (and as-needed) assessments of any major risks to the project, and decisions/agreements on any management actions or remedial measures to address them effectively. The Project Board reviews evidence of project performance based on monitoring, evaluation and reporting, including progress reports, evaluations, risk logs and the combined delivery report. The Project Board is responsible for taking corrective action as needed to ensure the project achieves the desired results.

- Approval of strategic project execution decisions of the Implementing Partner with a view to assess and manage risks, monitor and ensure the overall achievement of projected results and impacts and ensure long term sustainability of project execution decisions of the Implementing Partner (as explained in the “Manage Change” section of the POPP).

  - Requirements to serve on the Project Board:

- Agree to the Terms of Reference of the Board and the rules on protocols, quorum and minuting.

- Meet annually; at least once.

- Disclose any conflict of interest in performing the functions of a Project Board member and take all measures to avoid any real or perceived conflicts of interest. This disclosure must be documented and kept on record by UNDP.

- Discharge the functions of the Project Board in accordance with UNDP policies and procedures.

- Ensure highest levels of transparency and ensure Project Board meeting minutes are recorded and shared with project stakeholders.

  - Responsibilities of the Project Board:

- Consensus decision making:

  - The project board provides overall overall guidance and direction to the project, ensuring it remains within any specified constraints, and providing overall oversight of the project implementation.

  - Review project performance based on monitoring, evaluation and reporting, including progress reports, risk logs and the combined delivery report.

  - The project board is responsible for making management decisions by consensus.

  - In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

  - In case consensus cannot be reached within the Board, the UNDP representative on the board will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

- Oversee project execution:

  - Agree on project manager’s tolerances as required, within the parameters outlined in the project document, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded.

- Appraise annual work plans prepared by the Implementing Partner for the Project; review combined delivery reports prior to certification by the implementing partner.

- Address any high-level project issues as raised by the project manager and project assurance;

- Advise on major and minor amendments to the project within the parameters set by UNDP and the donor and refer such proposed major and minor amendments to the UNDP BPPS Nature, Climate and Energy Executive Coordinator (and the GEF, as required by GEF policies);

- Provide high-level direction and recommendations to the project management unit to ensure that the agreed deliverables are produced satisfactorily and according to plans.

- Track and monitor co-financed activities and realisation of co-financing amounts of this project.

- Approve the Inception Report, GEF annual project implementation reports, mid-term review and terminal evaluation reports.

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project.

- Risk Management:

  - Provide guidance on evolving or materialized project risks and agree on possible mitigation and management actions to address specific risks.

  - Review and update the project risk register and associated management plans based on the information prepared by the Implementing Partner. This includes risks related that can be directly managed by this project, as well as contextual risks that may affect project delivery or continued UNDP compliance and reputation but are outside of the control of the project. For example, social and environmental risks associated with co-financed activities or activities taking place in the project’s area of influence that have implications for the project.

  - Address project-level grievances.

- Coordination:

  - Ensure coordination between various donor and government-funded projects and programmes.

  - Ensure coordination with various government agencies and their participation in project activities.

  - Composition of the Project Board: The composition of the Project Board must include individuals assigned to the following three roles:

- The Project Board will be composed of UNDP, the Ministry of Tourism, Environment and Culture, Ministry of Local Government and Chieftainship Affairs, Ministry of Forestry, Rangelands and Soil Conservation, Ministry of Water, Ministry of Agriculture and Food Security, Ministry of Trade and Industry, Ministry of Health, Ministry of Police, Ministry of Small Business, Lesotho Revenue Authority, Department of Science and Technology, Academia, Private Sector/Industry representation, Traditional Practitioners association (Moetlo/Lebollo), financial Institution representation, and NGO/CBOs. The Board can be expanded, upon mutual agreement between the Parties. The MDNSE will represent the project ownership, Co-chairing the Project Board and organizing its meetings at least once a year and upon request of either of the Parties.  The MDNSE as lead Implementing Partner is also the institution responsible, within the government, for following up on the activities for this Project. The MDNSE will appoint a National Project Director (NPD) who will be a senior staff member and will be responsible at the highest level for providing guidance on the technical feasibility of the project and ensuring its implementation leads to the achievement of project’s results. He/she will represent the MDNSE on the Project Board. In addition, the Project Board will approve the appointment and responsibilities of a Project Manager who will be responsible for the daily project execution.

- Project Executive: This is an individual who represents ownership of the project and chairs (or co-chairs) the Project Board. The Executive usually is the senior national counterpart for nationally implemented projects (typically from the same entity as the Implementing Partner), and it must be UNDP for projects that are direct implementation (DIM). In exceptional cases, two individuals from different entities can co-share this role and/or co-chair the Project Board. If the project executive co-chairs the project board with representatives of another category, it typically does so with a development partner representative. The Project Executive is: The Executive is Director for Environment/MDNSE.

- Beneficiary Representative(s): Individuals or groups representing the interests of those groups of stakeholders who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. Often representatives from civil society, industry associations, or other government entities benefiting from the project can fulfil this role. There can be multiple beneficiary representatives in a Project Board. The Beneficiary representative (s) is/are:

  - MDNSE

  - Ministry of Finance

  - Ministry of Development Planning

  - Ministry of Law and Justice

  - Ministry of Forestry, Range and Soil Conservation

  - Ministry of Local Government and Chieftainship Affairs

  - Lesotho Revenue Authority

  - Lesotho Mounted Police

  - Ministry of Trade and Industry

  - Ministry of Small Businesses

  - Bureau of Statistics

  - Ministry of Health

  - Ministry of Gender, Youth, Sports and Recreation

  - Ministry of Water

  - Ministry of Agriculture and Food Security

  - Department of Science and Technology

  - Private sector

  - LNDC

  - Financial Institution representative

  - Chairperson of Natural Resources Cluster Committee

  - Academia

  - NGO/CBOs

  - Association of Herbalist and Traditional Practitioners

  - Representation of marginalized groups

- Development Partner(s): Individuals or groups representing the interests of the parties concerned that provide funding, strategic guidance and/or technical expertise to the project. The Development Partner is UNDP Resident Representative or Deputy Resident Representative.

- Project Assurance: Project assurance is the responsibility of each project board member; however, UNDP has a distinct assurance role for all UNDP projects in carrying out objective and independent project oversight and monitoring functions. UNDP performs quality assurance and supports the Project Board (and Project Management Unit) by carrying out objective and independent project oversight and monitoring functions, including compliance with the risk management and social and environmental standards of UNDP. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager. Project assurance is totally independent of project execution.

- A designated representative of UNDP playing the project assurance role is expected to attend all board meetings and support board processes as a non-voting representative. It should be noted that while in certain cases UNDP’s project assurance role across the project may encompass activities happening at several levels (e.g. global, regional), at least one UNDP representative playing that function must, as part of their duties, specifically attend board meeting and provide board members with the required documentation required to perform their duties. The UNDP representative playing the main project assurance function is the Programme Specialist, Energy and Environment.

- Project Management – Execution of the Project: The Project Manager (PM) (also called project coordinator) is the senior most representative of the Project Management Unit (PMU) and is responsible for the overall day-to-day management of the project on behalf of the Implementing Partner, including the mobilization of all project inputs, supervision over project staff, responsible parties, consultants and sub-contractors. The project manager typically presents key deliverables and documents to the board for their review and approval, including progress reports, annual work plans, adjustments to tolerance levels and risk registers.

- A designated representative of the PMU is expected to attend all board meetings and support board processes as a non-voting representative.

- The primary PMU representative attending board meetings is the Project Manager.

- Financial Planning and Management

- The total cost of the project is $7,413,699. This is financed through a GEF grant of $2,913,699 and UNDP’s $500,000 cash co-financing administered by UNDP and $4,000,000 in-kind in parallel co-financing. UNDP, as the GEF Implementing Agency, is responsible for the oversight of the GEF resources and the cash co-financing transferred to UNDP bank account only.

- Co-financing: The actual realization of project co-financing amounts will be monitored by the UNDP Country Office and the PMU on an annual basis in the GEF PIF and will be reported to the GEF during the mid-term review and terminal evaluation process as follows:

| Co-financing source | Co-financing type | Name of Co-financier | Investment Mobilized | Co-financing amount |
| --- | --- | --- | --- | --- |
| GEF Agency | Cash | UNDP | Investment mobilised | $500,000 |
| Government | In-kind | MDNSE | Recurrent Expenditure | $3,475,000 |
| University | In-kind | NUL | Recurrent Expenditure | $525,000 |
| Total |  |  |  | $4,500,000 |

- Budget Revision and Tolerance: As per UNDP POPP, the project board may agree with the project manager on a tolerance level for each detailed plan under the overall multi-year workplan. The agreed tolerance should be written in the project document or approved project board meeting minutes. It should normally not exceed 10 percent of the agreed annual budget at the activity level, but within the overall approved multi-year workplan at the activity level. Within the agreed tolerances, the project manager can operate without intervention from the project board. Restrictions apply as follows:

- Should the following deviations occur, the Project Manager/IP through UNDP Country Office will seek the approval of the BPPS/NCE-VF team to ensure accurate reporting to the GEF. It is strongly encouraged to maintain the expenditures within the approved budget at the budgetary account and at the component level:

- Budget reallocations must prove that the suggested changes in the budget will not lead to material changes in the results to be achieved by the project. A strong justification is required and will be approved on an exceptional basis. Budget re-allocations among the components (including PMC) of the approved Total Budget and Work Plans (TBWP) that represent a value greater than 10% of the total GEF grant.

- Introduction of new outputs/activities (i.e. budget items) that were not part of the agreed project document and TBWP that represent a value greater than 5% of the total GEF grant. The new budget items must be eligible as per the GEF and UNDP policies.

- Project management cost (PMC): budget under PMC component is capped and cannot be increased.

- UNDP is not in a position to increase the total budget above the amount approved by the donor, therefore any over-expenditure would have to be absorbed from non-GEF resources by the Implementing Partner (GEF Executing Entity)

- Project extensions: The UNDP-BPPS-NCE team Executive Coordinator must approve all requests for extension of the Project Completion Date and for other milestone extensions with hard deadlines. All extensions impose additional time and cost burdens at all levels and the GEF project budget cannot be increased beyond its originally approved amount. A single extension may be granted on an exceptional basis and subject to the conditions and maximum durations set out in the UNDP POPP. The project management costs during the extension period must remain within the originally approved amount, and any increase in PMC costs shall be covered by non-GEF resources; the additional UNDP oversight costs during the extension period must be covered by non-GEF resources, in accordance with UNDP’s policy as set out in UNDP POPP.

- For any extension request, UNDP CO and IP will consult and jointly present a clear plan indicating how and from which specific sources the additional oversight costs that will be incurred by UNDP will be covered during the extended period. The BPPS-NCE Executive Coordinator will consult the Regional Bureaux (RBX) and may reject the extension request if no (external co-financing by the IP or internal UNDP CO resources) can be identified.

- All extension requests, along with all supporting documentation, shall be submitted by the IP to the UNDP CO in line with the requirements and within the deadlines set out in the UNDP SOPs and policies in UNDP POPP.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies. Audit cycle and process must be discussed during the Inception workshop. If the Implementing Partner is an UN Agency, the project will be audited according to that Agencies applicable audit policies. The costs for audit cannot be included under M&E component and budget and must be included under PMC.

- Transfer or disposal of assets: In consultation with the Implementing Partner and other parties of the project, UNDP is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project, however, must be done before the operational closure date. In all cases of transfer, a transfer document must be prepared and kept on file. The transfer should be done before Project Management Unit complete their assignments.

- Completion Date: The project completion date is the date of Project Document Signature plus project duration. This date can only be extended through a formal extension request. Prior to completion date, all UNDP-financed inputs must be provided and related activities for the Project completed. No activities, except for the final clearance of the Terminal Evaluation Report and the corresponding management response and the end-of-project review Project Board Meeting should take place after the Completion Date.

- Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. All costs incurred to close the project must be included in the project closure budget and reported as final project commitments presented to the Project Board during the final project review. The only costs a project may incur following the final project review are those included in the project closure budget.

- Operational Closure: Operational closure must happen within 9 months from project completion date. Prior to operational closure, the Terminal Evaluation must have been submitted and the corresponding TE management response and the end-of-project review Project Board meeting must have been completed. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. Before Operational Closure, the project must have completed the transfer or disposal of any equipment that is still the property of UNDP.

- Financial Closure: Financial closure must happen within 6 months of operational closure or after the date of cancellation. The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to BPPS/NCE for confirmation before the project will be financially closed in Quantum by the UNDP Country Office.

- Cancellation and Suspension: All projects considering going through cancellation or suspension must follow UNDP and GEF requirements. Guidance can be found in the UNDP POPP (SOPs for management actions of Vertical Fund projects escalated to the Executive Coordinator and Guidance for GEF project revisions).

- Refund to GEF: Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the BPPS/NCE team Directorate in New York. No action is required by the UNDP Country Office on the actual refund from UNDP project to the GEF. Unspent project balance is not permitted to be transferred to any other projects.

- Total Budget and Work Plan

| Quantum Business Unit | UNDP-LSO |  |  |
| --- | --- | --- | --- |
| Quantum Project ID: | 00116027 | Quantum Project Title: | Promoting Conservation, Sustainable Utilization and Fair and Equitable Benefit-Sharing from Lesotho's Medicinal Plants for Improved Livelihoods |
| Quantum Award ID: | 00116027.1 | Quantum Award Title: | As in Quantum |
| UNDP-GEF PIMS No. | 5891 |  |  |
| Implementing Partner |  |  |  |

| Quantum Outcome (GEF Component) | Quantum Output (GEF Component) | Quantum Activity (GEF Component) | Quantum Responsible Party (UNDP, IP, or Responsible Party ) | Quantum Fund ID | Quantum Donor ID | Quantum Budgetary Account Code | Quantum Budget Account Description | Amount Year 1 (USD) |  | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) |  | Total (USD) |  | Budget Note # |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Enabling institutional capacity and regulatory framework strengthened to support implementation of the Nagoya Protocol on ABS | Outcome 1 | Output 1 | MoTEC | 62000 | 10003 | 71300 | Local Consultants | 3,500 |  | 14,000 | 0 | 0 | 0 |  | 17,500 |  | 1 |
|  |  |  |  | 62000 | 10003 | 71600 | Travel | 5,000 |  | 5,000 | 5,000 | 5,000 | 0 |  | 20,000 |  | 2 |
|  |  |  |  | 62000 | 10003 | 72100 | Contractual Services-Companies | 38,500 |  | 54,250 | 126,000 | 15,920 | 0 |  | 234,670 |  | 3 |
|  |  |  |  | 62000 | 10003 | 72500 | Supplies | 1,250 |  | 1,250 | 1,250 | 1,250 | 0 |  | 5,000 |  | 4 |
|  |  |  |  | 62000 | 10003 | 74200 | Audio Visual & Print Prod Costs | 10,000 |  | 22,000 | 7,000 | 0 | 0 |  | 39,000 |  | 5 |
|  |  |  |  | 62000 | 10003 | 74500 | Miscellaneous Expenses | 1,355 |  | 1,355 | 1,356 | 1,356 | 1,355 |  | 6,777 |  | 6 |
|  |  |  |  | 62000 | 10003 | 75700 | Training, Workshops and Confer | 52,000 |  | 99,333 | 35,333 | 29,334 | 0 |  | 216,000 |  | 7 |
|  |  |  |  |  |  |  | GEF Sub-total Component 1 | 111,605 |  | 197,188 | 175,939 | 52,860 | 1,355 |  | 538,947 |  |  |
|  |  |  |  |  |  |  | UNDP Sub-total component 1 | - |  | - | - | - | - |  | - |  |  |
| Total Component 1 |  |  |  |  |  |  |  |  | 111,605 | 197,188 | 175,939 | 52,860 |  | 1,355 |  | 538,947 |  |
| Component 2: Sustainable utilization and conservation of selected commercially-important Medicinal Plants for the development of ABS products for the pharmaceutical sector | Outcome 2 | Output 2 | MDNSE/UNDP | 62000 | 10003 | 71200 | International Consultants | 24,000 |  | 24,000 | 24,000 | 24,000 | 24,000 |  | 120,000 |  | 8 |
|  |  |  |  | 62000 | 10003 | 71400 | Contractual Services – Individuals | 65,268 |  | 65,268 | 65,268 | 65,268 | 65,268 |  | 326,340 |  | 9 |
|  |  |  |  | 62000 | 10003 | 71600 | Travel | 6,000 |  | 6,000 | 6,000 | 6,000 | 6,000 |  | 30,000 |  | 10 |
|  |  |  |  | 62000 | 10003 | 72100 | Contractual Services-Companies | 49,206 |  | 168,750 | 271,678 | 146,678 | 92,958 |  | 729,270 |  | 11 |
|  |  |  |  | 62000 | 10003 | 72200 | Equipment and Furniture |  |  | 240,000 | 200,000 | 0 | 0 |  | 440,000 |  | 12 |
|  |  |  |  | 62000 | 10003 | 72800 | IT Equipment | 4,000 |  | 0 | 0 | 0 | 0 |  | 4,000 |  | 13 |
|  |  |  |  | 62000 | 10003 | 74500 | Miscellaneous Expenses | 3,063 |  | 3,063 | 3,063 | 3,063 | 3,063 |  | 15,315 |  | 14 |
|  |  |  |  | 62000 | 10003 | 75700 | Training, Workshops and Confer | 0 |  | 50,000 | 55,047 | 50,000 | 30,000 |  | 185,047 |  | 15 |
|  |  |  |  |  |  |  | GEF Sub-total Component 2 | 151,537 |  | 557,081 | 625,056 | 295,009 | 221,289 |  | 1,849,972 |  |  |
|  |  |  | UNDP | 04000 | 00012 | 72200 | Equipment and Furniture | 40,000 |  |  |  |  |  |  | 40,000 |  | 16 |
|  |  |  |  | 04000 | 00012 | 73400 | Rental and Main. of other equip | 6,353 |  | 8,150 | 8,150 | 8,150 | 8,150 |  | 38,953 |  | 17 |
|  |  |  |  |  |  |  | UNDP Sub-total Component 2 | 46,353 |  | 8,150 | 8,150 | 8,150 | 8,150 |  | 78,953 |  |  |
| Total Component 2 |  |  |  |  |  |  |  | 199,537 |  | 566,081 | 633,206 | 303,159 | 229,439 |  | 1,928,925 |  |  |
| Component 3: Gender mainstreaming Knowledge Management | Outcome 3 | Output 3 | MDNSE | 62000 | 10003 | 71300 | Local Consultants | 72,330 |  | 13,200 | 13,200 | 13,200 | 13,200 |  | 125,130 |  | 18 |
|  |  |  | MDNSE | 62000 |  | 71600 | Travel | 4,000 |  | 6,000 | 6,953 | 6,000 | 6,000 |  | 28,953 |  | 19 |
|  |  |  | MDNSE | 62000 |  | 74200 | Audio Visual&Print Prod Costs | 4,060 |  | 4,060 | 4,060 | 4,060 | 4,060 |  | 20,300 |  | 20 |
|  |  |  | MDNSE | 62000 |  | 75700 | Training, Workshops and Confer | 15,200 |  | 15,200 | 15,200 | 15,200 | 15,200 |  | 76,000 |  | 21 |
|  |  |  |  |  |  |  | GEF Sub Total - Gender and K & M | 95,590 |  | 38,460 | 39,413 | 38,460 | 38,460 |  | 250,383 |  |  |
|  |  |  | UNDP | 04000 | 00012 | 71400 | Contractual Services - Individuals | 28,200 |  | 28,200 | 28,200 | 28,200 | 28,200 |  | 141,000 |  | 22 |
|  |  |  |  |  |  |  | UNDP sub-total - Gender and K & M | 28,200 |  | 28,200 | 28,200 | 28,200 | 28,200 |  | 141,000 |  |  |
| Total Component 3 |  |  |  |  |  |  |  |  | 123,790 | 66,660 | 67,613 | 66,660 |  | 66,660 |  | 391,383 |  |
| Component 4: Monitoring and Evaluation (M&E) | M & E | M & E | UNDP | 62000 | 10003 | 71200 | International Consultants | - |  | - | 15,000 | - | 20,000 |  | 35,000 |  | 23 |
|  |  |  | UNDP | 62000 | 10003 | 71300 | Local Consultants | - |  | - | 12,000 | - | 15,500 |  | 27,500 |  | 24 |
|  |  |  | MDNSE | 62000 | 10003 | 71600 | Travel | 1,500 |  | 1,500 | 7,150 | 1,500 | 8,500 |  | 20,150 |  | 25 |
|  |  |  | MDNSE | 62000 | 10003 | 75700 | Training, Workshops and Conf | 13,900 |  | 9,150 | 10,150 | 9,150 | 10,650 |  | 53,000 |  | 26 |
|  |  |  |  |  |  |  | GEF Sub-Total - M & E Budget | 15,400 |  | 10,650 | 44,300 | 10,650 | 54,650 |  | 135,650 |  |  |
|  |  |  | UNDP | 04000 | 00012 | 75700 | Training, Workshops and Conf | 500 |  | 500 | 8,000 | 500 | 10,500 |  | 20,000 |  | 27 |
|  |  |  |  |  |  |  | UNDP sub-total - M & E Budget | 500 |  | 500 | 8,000 | 500 | 10,500 |  | 20,000 |  |  |
| Total M&E |  |  |  |  |  |  |  |  | 15,900 | 11,150 | 52,300 | 11,150 |  | 65,150 |  | 155,650 |  |
| Project Management Cost (PMC) | PMC | PMC | MDNSE | 62000 | GEF | 71400 | Contractual Services – Individuals | 14,898 |  | 14,898 | 14,898 | 14,898 | 15,155 |  | 74,747 |  | 28 |
|  |  |  | MDNSE | 62000 | GEF | 71600 | Travel | 3,000 |  | 3,000 | 3,000 | 3,000 | 3,000 |  | 15,000 |  | 29 |
|  |  |  | MDNSE | 62000 | GEF | 72500 | Supplies | 1100 |  | 1100 | 1100 | 1100 | 1100 |  | 5,500 |  | 30 |
|  |  |  | MDNSE | 62000 | GEF | 72200 | Equipment and Furniture | 5,000 |  | 0 | 0 | 0 | 0 |  | 5,000 |  | 31 |
|  |  |  | MDNSE | 62000 | GEF | 72400 | Communic & Audio Visual Equip | 3,600 |  | 3,600 | 3,600 | 3,600 | 3,600 |  | 18,000 |  | 32 |
|  |  |  | MDNSE | 62000 | GEF | 72800 | IT Equipment | 5,500 |  | 0 | 0 | 0 | 0 |  | 5,500 |  | 33 |
|  |  |  | UNDP | 62000 | GEF | 74100 | Professional Services | 3,000 |  | 3,000 | 3,000 | 3,000 | 3,000 |  | 15,000 |  | 34 |
|  |  |  |  |  |  |  | GEF Sub Total | 36,098 |  | 25,598 | 25,598 | 25,598 | 25,855 |  | 138,747 |  |  |
|  |  |  | UNDP | 4000 | TRAC | 71400 | Contractual Services – Individuals | 35,070 |  | 35,070 | 35,070 | 35,070 | 35,070 |  | 175,350 |  | 35 |
|  |  |  | UNDP | 4000 | TRAC | 72200 | Equipment and Furniture | 10,000 |  | 0 | 0 | 0 | 0 |  | 10,000 |  | 36 |
|  |  |  | MDNSE/UNDP | 4000 | TRAC | 73400 | Rental and Main. of other equip | 4,000 |  | 4,000 | 4,000 | 4,000 | 4,000 |  | 20,000 |  | 37 |
|  |  |  | UNDP | 4000 | TRAC | 74596 | Direct Project Costs | 4,940 |  | 4,940 | 4,939 | 4,939 | 4,939 |  | 24,697 |  | 38 |
|  |  |  | MDNSE/UNDP | 4000 | TRAC | 74500 | Miscellaneous Expenses | 1,000 |  | 1,000 | 1,000 | 1,000 | 1,000 |  | 5,000 |  | 39 |
|  |  |  | MDNSE/UNDP | 4000 | TRAC | 75700 | Training, Workshops and Confer | 5,000 |  | 5,000 | 5,000 | 5,000 | 5,000 |  | 25,000 |  | 40 |
|  |  |  |  |  |  |  | UNDP Sub-total PMU | 60,010 |  | 50,010 | 50,009 | 50,009 | 50,009 |  | 260,047 |  |  |
| Total PMU |  |  |  |  |  |  |  | 96,108 |  | 75,608 | 75,607 | 75,607 | 75,864 |  | 398,794 |  |  |
| GEF TOTAL |  |  |  |  |  |  |  | 410,230 |  | 828,977 | 910,306 | 422,577 | 341,609 |  | 2,913,699 |  |  |
| UNDP TOTAL |  |  |  |  |  |  |  | 135,063 |  | 86,860 | 94,359 | 86,859 | 96,859 |  | 500,000 |  |  |
| TOTAL PROJECT GRANT |  |  |  |  |  |  |  | 545,293 |  | 915,837 | 1,004,655 | 509,436 | 438,468 |  | 3,413,699 |  |  |

Budget Notes

| Budget note # | Budget Note (Description) |
| --- | --- |
| Component/Outcome 1: Enabling institutional capacity and regulatory framework strengthened to support implementation of the Nagoya Protocol on Access and Benefit Sharing (ABS) |  |
| 1 | This budget is reserved to hire a National (IC) to: a) Provide training to National Focal Point, Competent National Authorities, and Checkpoints. Total cost: $7,000 during years 1 and 2 (Output 1.2.1). b) Support the development of National guidelines for enforcing ABS regulatory framework. Total cost: $10,500 during year 2 (Output 1.2.3). Total estimated cost is $17,500 |
| 2 | Travel costs related to enabling institutional capacity and regulatory framework strengthened to support implementation of the Nagoya Protocol on ABS. The cost will cover from year 1 to 4 (all outputs in component). Total estimated cost is $20,000 |
| 3 | This budget is reserved for contracting a company/consortium that should include the following experts: ABS Legal/Policy Expert (international), ABS capacity development expert; Environmental policy expert who can provide the following: a) Support the development of an enabling institutional capacity and regulatory framework for the implementation of the Nagoya Protocol on ABS. Total cost: $126,000 during 30 months over 3 years (Outputs 1.1.1, 1.1.2, 1.1.3, 1.3.1, 1.3.2, and 1.3.3) b) Develop an ABS and TK Strategy through a participatory process. Total cost: $31,500 during year 1 (Output 1.1.4). c) Develop an institutional Capacity Development Strategy for the ABS framework implementation, monitoring, enforcement and compliance following the validation of needs and gap assessment conducted during the PPG. Total cost: $28,170 during year 2 (Output 1.2.2). d) Design and put into operation a user-friendly web-based national CHM. Total cost: $49,000 during year 1 (Output 1.2.4). Total estimated cost is $234,670. Note: If it is necessary to source such a company/consortium internationally/regionally, it will be a requirement that the team includes national counterparts. |
| 4 | Office and IT supplies in support of Component 1 activities. The cost will cover from year 1 to 5 (all outputs in component). Total estimated cost is $5,000 |
| 5 | This budget is reserved for Communication materials: a) Translation of all relevant legal and policy instruments into local language (i.e., Sesotho). Total cost: $10,000 during year 1 (Outputs 1.1.1, 1.1.2, 1.1.3, and 1.1.4). b) Translation of biocultural community protocols governing management, ownership, access rights and benefit sharing rules and procedures into local language (i.e., Sesotho). Total cost: $8,000 during year 2 (Outputs 1.3.2). c) Printing and production costs of biocultural community protocols governing management, ownership, access rights and benefit sharing rules and procedures. Total cost: $7,000 during year 2 (Output 1.3.2). d) Printing and productions costs of patenting protocols for TK. Total cost: $7,000 during year 2 (Output 1.3.2). e) Printing and productions costs of codes of conduct, best-practices and standards that ensure sustainable harvesting, fair and equitable benefit-sharing. Total cost: $7,000 during year 3. (Output 1.3.3). Total estimated cost is $39,000 |
| 6 | Incidental expenses related to building a systemic and institutional capacity for integrated landscape management at national level. The cost will cover for the entire period for all outputs in the component. Total estimated cost is $6,777 |
| 7 | This budget (multi-year) is reserved for conferences and training events linked to Component 1 Activities and quantified as follows: a) Validation workshops for updating the National Environment Policy of 1998 and Biodiversity Bill of 2021 to incorporate ABS/NAGOYA PROTOCOL considerations. Total cost: $8,000 during year 1. (Output 1.1.1). b) Validation workshops for the development of National ABS, Bioprospecting and TK Regulations. Total cost: $12,000 during year 1 (Output 1.1.3). c) Validation workshops for updating Local/Community Councils By-laws to incorporate ABS and biodiversity conservation considerations. Total cost: $12,000 during year 1. (Output 1.1.3). d) Consultation workshops for the development of an ABS and TK Strategy. Total cost: $12,000 during year 1. (Output 1.1.4). e) Training workshops and meeting for National Focal Point, Competent Authorities and Checkpoints to develop, implement and enforce national legislative, administrative or policy measures on ABS. Total cost: $16,000 during years 1 and 2 (Output 1.2.1). f) Training, workshops, and participation in conferences as part of the implementation of the Institutional Capacity Development Strategy on ABS. Total cost: $88,000 during years 2 to and 4. (Output 1.2.2). g) Consultation workshops for the development of National guidelines for enforcing ABS regulatory framework. Total cost: $12,000 during year 2 (Output 1.2.3). h) Consultations and validation workshops: draft of guidelines and procedures for obtaining PIC and MAT. Total cost: $16,000 during year 2. (Output 1.3.1). i) Consultation and validation workshops: draft of biocultural community protocols governing management, ownership, access rights and benefit sharing rules and procedures. Total cost: $16,000 during year 2 (Output 1.3.2). j) Consultation and validation workshops: draft of patenting protocols for TK. Total cost: $12,000 during year 2 (Output 1.3.2). k) Consultation and validation workshops for the development of codes of conduct, best-practices, and standards that ensure sustainable harvesting, fair and equitable benefit-sharing. Total cost: $12,000 during years 2 and 3 (Output 1.3.3). Total estimated cost is $216,000 |
| Component/Outcome 2. Building capacities for bioprospecting and value-addition of genetic resources |  |
| 8 | This budget is reserved for Technical Adviser to provide technical and strategic guidance and technical backstopping. Total cost: $120,000 over 5 years (all outputs in component). Total estimated cost is $120,000 |
| 9 | This budget is reserved to cover portion of project staff salary: a) Field Facilitators -2 staff (This component will cover 100% of their salaries): field support for building capacities for bioprospecting and value-addition of genetic resources. Total cost: $283,200 for 5 years @ $2,360 per month for one facilitator (all Outputs in Component). b) Driver. Total cost: $43,140 @ $719 per month for 5 years (all Outputs in Component). Total estimated cost is $326,340 |
| 10 | This budget is reserved for Travel expenses related to this component including oversite and stakeholders’ meetings @ $6000/year Total estimated cost is $30,000 |
| 11 | This budget is reserved for contracting several companies/consortia that provide the services related to this component: a) A Company/Consortium that can provide the following services: i. Conduct a national research and development strategy on bioprospecting, including role of traditional practitioners and herbalists. Total cost: $25,000 during years 1 to 4. (Output 2.1.1). ii Conduct a comprehensive valuation of selected genetic resources with known commercial and intangible values (cultural and spiritual): baseline assessment and economic valuation. Total cost: $57,440 during years 2 and 3 (Output 2.1.3). b) A Company to strengthen capacities through targeted training of experts and technical staff of national research centres in R&D associated to medicinal plants. Total cost: $70,000 during year 1 (Output 2.1.2) c) A Company to establish an accredited testing laboratory for safety and efficacy of genetic resources related products including development of Occupational Safety and Health Action Plan (OSHAP). Total cost: $250,000 during years 1 and 2 (Output 2.1.2) d) A Company to identify potential medicinal plants species for value-chain development and improvement. Total cost: 100,000 during years 2 to 5 (Output 2.1.2) e) A Company to develop and E-permitting system for bio prospectors. Total cost: $50,000 during years 2 and 3 (Output 2.1.4). f) A Company to conduct training of small/medium-scale community-based organizations and enterprises and for national parks and establish a template for ABS agreements. Total cost: $80,000 during years 1 to 4 (Output 2.2.1). g) A Company to develop a model biocultural community protocol considering medicinal plants with potential for bioprospecting. Total cost: $46,830 during years 3 (Output 2.2.3). Total estimated cost is $629,270 |
| 12 | This budget is reserved for procurement of equipment: Laboratory and processing equipment for research centres to strengthen the capacity for bioprospecting. Total cost: $440,000 during years 2 and 3 (Output 2.1.2). Total estimated cost is $440,000 |
| 13 | This budget is reserved for procurement of IT equipment for the Field coordinators @ 2000/ per person during the 1st year. Total estimated cost is $4,000 |
| 14 | This budget is reserved for incidental expenses including insurance and bank charges etc a) Insurance vehicle. Total cost: $10,500; $2,100/year during the 5 years b) Incidental expenses related to Building capacities for bioprospecting and value-addition of genetic resources. Total cost: $4,815 during the 5 years (all outputs in component) Total estimated cost is $15,315 |
| 15 | This budget is reserved for meetings/workshops/trainings costs: a) related to exchange programmes with more established product developers to capacitate local stakeholders and develop commercial products. Total cost: $60,000 during years 2 to 5 (Output 2.1.2). b) related to establishment of partnerships and collaboration by local product developers with international partners. Total cost: $55,047 during the 5 years (Output 2.1.2). c) for exchanges of experience program to raise awareness about regional/international ABS initiatives. Total cost: $70,000 during the 5 years (Output 2.2.2). Total estimated cost is $185,047 |
| 16 | This budget is reserved for procurement of equipment: Vehicle (4x4) (transport equipment). Total cost: $40,000 during year 1. Total estimated cost is $40,000 (From UNDP's contribution) |
| 17 | This budget is reserved for running cost of Project vehicle: a) Fuel vehicle. Total cost: $27,500; $5,500/year during the 5 years. b) Maintenance vehicle. Total cost: $11,453 during the 5 years. Total estimated cost is $38,953 (from UNDP's contribution) |
| Component/Outcome 3. Gender mainstreaming 7& Knowledge Management |  |
| 18 | This budget is reserved for hiring National Consultant (IC) to support the following activities: a) Web page design for the project. Total cost: $9,130 during year 1 (Output 3.2.1). b) Gender/Safeguards Officer. Support gender mainstreaming and gender monitoring (Gender Action Plan), monitoring of environmental and social risks, and develop, implement and monitor the IPP and secure PIC. Total cost: 66,000. The cost will cover the support to be provided from year 1 to 5. (Outputs 3.1.1). c) Strategic Environmental and Social Assessment (SESA) and Cultural Heritage Impact Assessment (CHIA). Total cost: $50,000 during Yr1 Total estimated cost is $125,130 |
| 19 | This budget is reserved for travel expenses related to this component: a) Travel costs for the implementation and monitoring of gender mainstreaming activities: Total cost: $15,000 during years 1 to 5 (Output 3.1.1). b) Travel costs for communication and knowledge management activities: Total cost: $13,953 during years 1 to 5 (Output 3.2.1). Total estimated cost is $28,953 |
| 20 | This budget is reserved for communications materials production and staff communication means: Publications and media products related to knowledge management and communication. The cost will cover the support provided under Output 3.2.1 from year 1 to 5. Total estimated cost is $20,300 |
| 21 | This budget (multiyear) is reserved for conferences and training events linked to Component 3 Activities and quantified as follows: a) Awareness and sensitization workshops for local authorities, traditional practitioners and women on ABS. Total cost: $45,000 during years 1 to 5 (Output 3.2.1). b) Workshops and meetings related to IPP and PIC. Total cost: $31,000 over 5 years Total estimated cost is $76,000 |
| 22 | This budget is reserved for hiring Project staff to support the following activities covered by UNDP's co-financing: a) Communications/Knowledge Management Expert: Communication and awareness-raising activities and documentation and systematization of lessons learnt and best practices. Total cost: $141,450 @$2357.50/month during year 1 to 5(60 months. (Output 3.2.1) Total estimate cost is $141,450 (from UNDP's contribution) |
| Component: Monitoring & Evaluation |  |
| 23 | This budget is reserved for hiring international consultant (IC) to support the following activities: a) Mid-Term Review (International Consultant) @ $15,000 in Yr 3; and b) Terminal Evaluation (International consultant) @ $20,000 in Yr 5(Output 3.2.2) Total estimated cost is $35,000 |
| 24 | This budget is reserved for hiring National Consultant (IC) to support the following activities: a) Mid-term project review. Total cost: $10,000 during year 3. (Output 3.2.2) and b) Terminal evaluation. Total cost: $13,500 during year 5. (Output 3.2.2) c) collecting data for MTR core indicator during year 3 @$2000 and for TE core indicator during year 5 @ $2000 Total Estimated cost is $27,500 |
| 25 | This budget is reserved for travel expenses related to this component: a) Travel costs for mid-term project review (including DSA): Total cost: $5,650 during year 3. (Output 3.2.2) b) Travel costs for terminal evaluation (including DSA): Total cost: $7,000 during year 5. (Output 3.2.2) c) Travel costs for M&E of project activities: Total cost: $7,500 during year 1 to 5. (Output 3.2.2) Total estimated cost is $20,150 |
| 26 | This budget (multiyear) is reserved for workshops/conferences and/or training events linked to Component 3 Activities and quantified as follows: a) Project Inception Workshop. Total cost $8,500 during year 1 (Output 3.2.2). b) Knowledge forums to share lessons learnt and good practices with multiple stakeholders. Total cost: $15,000 during years 2 to 5 (Output 3.2.1). c) Mid-term project review related workshops. Total cost: $1,000 during year 3 (Output 3.2.2). d) Terminal evaluation related workshops. Total cost: $1,500 during year 5 (Output 3.2.2). e) Quarterly Project board meetings. Total cost: $12,000, $2,400 per year from year 1 to 5 (Output 3.2.2). f) Monitoring of Environmental and social risks, and corresponding management plan as relevant. Total cost: $7,500 from year 2 to 5 g) Workshops/meetings related to Gender action plan. Total cost $7,500 from year 2 to 5. Total estimated cost is $53,000 |
| 27 | This budget is reserved for workshops/conferences and/or training events linked to Component 3 Activities: a) UNDP's contribution to the Quarterly Project board meetings. Total cost: $2,500, $500 per year from year 1 to 5 (Output 3.2.2). b) MTR validation workshop. Total cost $7,500 during year 3 c) TE validation workshop. Total cost $10,000 during year 5 Total estimated cost is $20,000 (from UNDP's contribution) |
| Project Management Unit |  |
| 28 | This budget is reserved for: Financial/Administrative Officer salary: financial management of the project, accounting, purchasing, and reporting, etc. Total cost: $74,485.20 @ $1,241.42 per month for 5 years Total estimated cost is $74,485.20 |
| 29 | This budget is reserved to PMU related travel. Total cost $15,000 @ $3,000/year for 5 years. Total estimated cost is $15,000 |
| 30 | This budget is reserved for Office supplies: Total estimated cost is $5,500 @ $1,100 per year during the 5 years. |
| 31 | This budget is reserved for Office furniture of PMU staff. Total estimated cost is $5,000. |
| 32 | This budget is reserved for communication and connectivity of PMU staff Costs of internet connection and monthly connectivity fee (telephone bills etc) (@$50/month for 6 project staff for 60 months) @$3,600 per year for 5 years Total estimated cost is $18,000 |
| 33 | This budget is reserved for IT equipment of PMU staff: a) Computer for Project Manager. Total cost: $1,500. b) Computer for Financial/Administrative Officer: Total cost: $1,500 c) Computer for Communication/KM Officer. Total cost $1,500 d) Printer (1). Total cost: $250. e) Digital camera (1). Total cost: $250. f) Projector (1). Total cost: $500. Total estimated cost is $5,500. |
| 34 | This budget is reserved for Annual External audit fee for the 5 years @ $3,000 per year. Total estimated cost is $15,000 |
| 35 | This Project is reserved for: Project Manager's salary: project planning, day-to-day management of project activities, project reporting, maintaining key relationships among stakeholders, etc. Total cost: $175,350 - $2,922.50/month the over 5 years. Total estimated cost is $175,350 (From UNDP's co-financing) |
| 36 | This budget is reserved for the purchase of 2 Motorbikes for Field Coordinators to reach to the remote areas @ $5,000 each on year 1. Total estimated cost is $10,000 (From UNDP's co-financing) |
| 37 | This budget is reserved for the fuel and maintenance cost for the 2 Motorbikes mentioned above @$4,000 per year over the 5 years period. Total estimated cost is $20,000 (from UNDP's co-financing) |
| 38 | This budget is reserved for the Direct Project support (DPC) - Implementation Support Services to be provided through UNDP Lesotho country office at the request of MDNSE in the Service Areas of Finance, HR24, Travel etc, as itemized in the Letter of Agreement between the Implementing Partner and UNDP Lesotho. See under Annex 13 Total estimated cost is $24,697 over the 5 years (From UNDP's co-financing) |
| 39 | This budget is reserved for Miscellaneous expenses and insurance for the project motorbikes @ $1,000 per year for over the 5 years period. Total estimated cost is $5,000 (from UNDP's co-financing) |
| 40 | This budget is reserved for Training, Workshops and Conferences related to PMU to conductus the following: · Project Steering Committee meetings twice a year · Annual planning and other workshops and trainings related to PMU staff: Total estimated cost is $25,000 @ $5,000 per year over the 5 years (From UNDP's co-financing) |

- Legal Context

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Lesotho and UNDP, signed on 22 March 1990. All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be implemented by the Ministry of Defense, National Security and Environment (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

- Risk Management

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner. To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried.

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially, record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

- b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.

- In the implementation of the activities under this Project Document, UNDP places reasonable reliance upon the Implementing Partner for it to apply its laws, regulations and processes, and applicable international laws regarding anti money laundering and countering the financing of terrorism, to ensure consistency with the principles of then in force the UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti-money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document. Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement. Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

- Note: The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

Mandatory Annexes

The following Annexes are included within this Project Document:

- GEF Budget Template (available from BPPS NCE team)

- GEF Execution Support Letter

- Project Map and geospatial coordinates of the project area

- Multiyear Workplan

- Social and Environmental Screening Procedure (SESP), or justification of SESP exemption

- UNDP Risk Register

- Overview of technical consultancies/subcontracts

- Stakeholder Engagement Plan

- Environmental Social Management Framework (ESMF) or other SES frameworks/plans including the Project’s GRM, if required,

The following Annexes have been completed as part of the submission package to the GEF (i.e.  annexed separately):

- Gender Analysis and Gender Action Plan

- Procurement Plan – for first year of implementation especially GEF focal area specific annexes (e.g. METT, GHG calculations, target landscape profile, feasibility study, other technical reports)

- Additional agreements: such as cost sharing agreements, project cooperation agreements signed with NGOs (where the NGO is designated as the “executing entity”), letters of financial commitments etc..

- Signed LOA between UNDP and IP requesting UNDP Support Services (if required on exceptional basis and authorized by the GEF)

- GEF CEO Endorsement/Approval

- On-Granting Provisions Applicable to the Implementing Partner

- Terms of Reference for Project Board and Project Team

- GEF and/or LDCF/SCCF Core indicators (see template below)

- GEF Taxonomy (see template below)

- Results of the Partners Capacity Assessment Tool (PCAT) and HACT Micro Assessment

- UNDP Project Quality Assurance Report (to be completed in UNDP online corporate planning system)

## Annex 1: GEF Budget Template

To be provided by MPSU after TBWP clearance.

## Annex 2: GEF execution support letter

## Annex 3: Project map and Geospatial Coordinates of project sites

## Site Coordinates

| Site | Lat | Long |
| --- | --- | --- |
| Sehlabathebe National Park | 29.904204477 | 29.054546368 |
| Tsehlanyane National Park | 28.9230868445 | 28.384412543 |
| Bokong Nature Reserve | 29.416525926 | 28.616670390 |
| Letsa-la-Letsie Ramsar Site | 30.279628739 | 27.965472953 |

## Annex 4: Multi Year Work Plan

| Task | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Component/Outcome1: Enabling institutional capacity and regulatory framework strengthened to support implementation of the Nagoya Protocol on ABS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.1: National Environment Policy of 1998 and Biodiversity Bill of 2018 reviewed to address ABS in accordance with the Nagoya Protocol. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline survey of relevant policies e.g Range Policy, Forestry Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify and analyze gaps, from a gender perspective, of existing National Environment Policy and Biodiversity Bill |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft recommendation for updating National Environment Policy and Biodiversity Bill |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validation of recommendations with stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit draft Policy to Cabinet for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit Biodiversity Bill to Parliament for enactment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.2: National ABS, bioprospecting, TK, and IPRs regulations developed, reviewed, and presented to parliament for approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline survey of relevant regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop drafting instructions for National ABS, Bioprospecting and TK Regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit National ABS, Bioprospecting and TK regulations to Parliament for enactment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.3: Local/community councils’ by-laws in the prioritized districts (guidelines) on ABS reviewed, finalised, and/or developed considering national frameworks on ABS and biodiversity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline survey of relevant By-Laws (guidelines) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and update existing By-Laws considering the national regulations developed in Output 1.1.1 and 1.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validation of reviewed and updated By-Laws |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit draft By-Laws to Ministry of Local Government and Chieftainship for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Translate all relevant legal instruments to Sesotho |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.4: ABS and TK Strategy developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline survey of relevant strategies to identify gaps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Stakeholder consultations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop draft strategy and submit to the MTEC for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Translate all relevant legal instruments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.1: NFP, Competent National Authorities, and Checkpoints’ capacities enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training to National Focal Point, Competent Authorities and Checkpoints |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assess existing mechanisms to enforce national legislative, administrative, or policy measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and update the Curriculum of Police Training Centre to include ABS considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluate impact of capacity development strategy on ABS using the UNDP National ABS Institutional Capacity Scorecard. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.2: Institutional Capacity Action Plan for the ABS framework implementation, monitoring, enforcement and compliance developed and rolled-out. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validation of needs and gaps considering PPG capacity assessment results and through additional consultations with stakeholders. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft capacity building plan and training modules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Roll-out Institutional Capacity Action Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.3: National guidelines for enforcing ABS regulatory framework developed and implemented. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publicise at the national and local levels the ABS regulations developed by the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify the gaps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and adopt the guidelines in consultation with stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3.1: Guidelines and procedures for obtaining PIC and MAT developed and approved. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify the gaps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft the guidelines in close consultation with stakeholders, including technical support to national and local stakeholders for PIC/MAT guidelines drafting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validate the guidelines and adoption by environmental authority (MTEC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publish and socialize guidelines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3.2: Biocultural community protocols governing management, ownership, access rights and benefit sharing rules and procedures defined and adopted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assessment and consultation with harvesters, healers, women, and marginalized groups (including herders) and local communities regarding management, ownership, access to natural resources, including genetic resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft in close consultation with indigenous and local communities, community protocols governing management, ownership, access rights and benefit sharing rules and procedures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validate protocols with indigenous and local community leaders. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publish and socialize guidelines in English and local languages. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3.3: Codes of conduct, best practices and standards that ensure sustainable harvesting, fair and equitable benefit-sharing established for industry and research sectors active in bioprospecting. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct consultations with multiple stakeholders regarding what can be included as part of Codes of conduct, best-practices and standards that ensure sustainable harvesting, fair and equitable benefit-sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft codes of conduct, best-practices and standards guidelines that ensure sustainable harvesting, fair and equitable benefit-sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validate the Codes of conduct, best-practices and standards that ensure sustainable harvesting, fair and equitable benefit-sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publish and disseminate Codes of conduct, best-practices and standards that ensure sustainable harvesting, fair and equitable benefit-sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component/Outcome 2. Sustainable utilization and conservation of selected commercially-important Medicinal Plants for the development of ABS products for the pharmaceutical sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.1: National research and development strategy on bioprospecting, including role of traditional practitioners and herbalists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct stakeholder consultative workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake institutional mapping and analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and update inventory of the prioritized medicinal plants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct bioprospecting surveys |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production, validation and publication of a national research and bioprospecting strategy document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commission research aligned to principles of FPIC in collaboration with herders, women and local communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.2: The NUL and other research centres are supported to conduct pharmaceutical R&D on selected genetic resources of medicinal value, and conduct R&D and natural product development for pharmaceutical use (with a focus on P. sidoides and H. hemerocallidea) in collaboration with traditional medical associations /groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agree and sign an agreement of collaboration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procure laboratory equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training of researchers and laboratory technicians in pharmaceutical processing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establishing contractual agreements and non-disclosure with traditional medicinal practitioners and herbalist to share their baseline knowledge of the prioritized medicinal plants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct pharmaceutical tests and analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct exploratory research for natural product development for pharmaceutical use |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production, testing and patenting of pharmaceutical products. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake incubation of products for commercial and industrial development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.3: A comprehensive valuation of selected genetic resources with known commercial and intangible values (cultural and spiritual) is conducted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct the review and analysis of baseline value of resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct economic and intangible valuation of key medicinal plants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2.1: Small/medium-scale community-based enterprises and protected areas supported with propagation /re-introduction, business and value-addition skills to harvest, process, package and market natural products from selected genetic resources. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct site suitability studies for propagation and other related research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct baseline assessment for women participation in different value chains |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct capacity building and training of community entrepreneurs including women's groups, herders and other marginalized groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Promote both in-situ and ex-situ conservation of selected resources under communal management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Promote ex-situ conservation of selected resources under household nurseries and communal botanical gardens |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Promote in-situ conservation of selected resources under protected areas and military /police installations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3.1: The Pelargonium BMP updated and the Hypoxis BMP developed, and both plans adopted and implemented, in close collaboration with community enterprises and CSO stakeholders in Lesotho. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct stakeholder consultative workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct field populations studies and biology of plants including regeneration studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and update Pelargonium BMP based on the Lesotho Biodiversity Bill and associated regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce Hypoxis BMP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct propagation and harvest trials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3.2: ABS deals with monetary and non-monetary benefits negotiated between providers and users of P. sidoides (locally known as Khoara). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct institutional mapping of producer and user value chains |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Negotiate and agree MOUs between producers and users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3.3: Model ABS agreements cognisant of the pharmaceutical business models, developed/reviewed and implemented for P. sidoides with a focus on medium enterprises and exporters. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce template agreement for pharmaceutical business deals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct stakeholder consultations to facilitate business agreements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Facilitate business deals between producers and users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component/Outcome 3. Gender mainstreaming, Knowledge Management and M&E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.1 Gender strategy developed and used to guide project implementation, monitoring and reporting. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training and capacity building of stakeholders on gender issues in medicinal plant resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce a gender strategy in plant resource management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish a working linkage between DOE and Department of Gender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop a gender mainstreaming strategy to guide project implementation, monitoring and reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gender empowerment workshops on ABS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and implement the IPP and achieve FPIC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2.1: Knowledge, attitudes, practices, and behavior (KAP/B) assessment/surveys carried out and an awareness-raising programme on ABS developed and implemented. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce a gender awareness strategy on ABS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct awareness and sensitization workshops for local authorities, traditional practitioners and women on ABS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Document women and men's TK (including herders) on prioritized medicinal plants. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Document best practices and lessons on gender mainstreaming in medicinal plants development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publicise the national ABS policy and regulatory framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Update the KAP/B index and produce reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2.2: Participatory monitoring, evaluation and learning strategy developed and implemented to support project management, collate and disseminate lessons |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct M&E of the project’s implementation following GEF and UNDP guidelines and according to the M&E plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 5: UNDP Social and Environmental Screening Procedure (SESP)

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Promoting conservation, sustainable utilization and fair and equitable benefit-sharing from Lesotho's Medicinal and Ornamental Plants for improved livelihoods |
| - Project Number (i.e. Atlas project ID, PIMS+) | PIMS 5891 |
| - Location (Global/Region/Country) | Country - Lesotho |
| - Project stage (Design or Implementation) | Design |
| - Date | 23 February 2023 |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the project mainstreams the human rights-based approach

This is a project designed to promote access and benefit-sharing (ABS) as an integral aspect of natural resources management and conservation, through development of the enabling institutional capacity and regulatory framework to support implementation of the Nagoya Protocol on ABS; and building capacities for bioprospecting and value-addition from genetic resources. By its nature, it is designed to apply a human-rights based approach to natural resources management and biodiversity conservation, particularly through development of regulatory frameworks that enable establishment of formalized agreements (see Outputs 1.3.1, 1.3.2, 1.3.3 and 1.3.4) to ensure equitable beneficiation from the utilization of genetic resources for bioprospecting and natural product development. The ABS discourse, within the context of the CBD and the Nagoya Protocol on ABS, promotes the recognition of Traditional Knowledge (TK) hosted by local communities that have lived next to and utilized such resources throughout history, and advocates that such communities should therefore also have benefits accrue to them (monetary and non-monetary) from the use of such knowledge and resources. This in essence is the equitable sharing of benefits along the value chain, because currently the benefits are skewed towards the ‘developers’ and those who add value to the resources and transform them into products (e.g. food and pharmaceutical industries) even though this value addition and product development is based on indigenous and TK, which is often undocumented and unpatented, as its usually owned/held by poor, marginalized sections of society. The project will therefore support the Government of Lesotho (GoL) to build its capacity to conserve, manage, regulate and facilitate the equitable sharing of benefits with local communities and owners/providers of the knowledge behind the use of these genetic resources. Under Component 1, the project will contribute to strengthening the national ABS regulatory environment – including with respect to traditional knowledge and intellectual property rights, with an ABS and TK Strategy developed under Output 1.1.4 - and will support development of a National R&D Strategy on bioprospecting. The long-term goal is that communities who are suppliers of genetic resources (or who hold TK on genetic resources) can derive benefits from being the first innovators and knowledge generators behind the sector that is now significantly valued. At the national level, the goal of the project is also to ensure that Lesotho is also capacitated to negotiate for a fair and equitable share of the benefits with the potential ‘buyers’/users/extractors of such knowledge and resources from within Lesotho. In implementing the interventions of the project, the overarching principle will be to identify and empower poor, rural and marginalized groups, such as women, herders, youth and poor men, and other groups that may have special needs and interests (e.g. herbalists, traditional medicine practitioners and traders) to ensure that the project interventions take into consideration the gender and power dynamics at play in the project context and puts in place mechanisms to promote equity and fairness at all levels of project design and implementation. Principles of the Human Rights Based Approach have been integrated into the final Project Document as required by GEF and UNDP policies. During the PPG phase, stakeholder analysis was conducted and multiple consultations were conducted with stakeholders at the national and project site levels where they had the opportunity to raise any concerns related to the project, including human rights concerns. Local communities and individuals of the Sehlabathebe UNESCO Heritage Park, Tšehlanyane National Park, Bokong Nature Reserve, and Letša-la-Letsie Ramsar site) and their surrounding landscapes, were given the opportunity to raise human rights concerns regarding the project during the stakeholder engagement process. Based on the stakeholder consultations, a stakeholder participation and engagement plan was developed (see Annex 8 of this Project Document), that will guide these stakeholders and project implementers as to when, how and with whom consultations and exchanges should be undertaken throughout the life of the project including opportunities to express any human rights concerns. The project will also put in place a Grievance Redress Mechanism to ensure that all stakeholders have a formalized channel through which to direct their concerns about impacts the project may have on them, and for these to be addressed.

Briefly describe in the space below how the project is likely to improve gender equality and women’s empowerment

Access to and control over natural resources always has a gender dynamic to it, and so are the costs and benefits of interacting with the environment and natural resources. In the context of Lesotho and the history of use of genetic resources, traditionally and historically defined gender roles determine which genetic and biological resources women have access to and benefit from. These roles are defined by traditional norms and values and taboos restricting interaction with particular species. Interestingly, research on Lesotho people’s (Basotho) historical interaction with indigenous plant species, particularly those used for medicinal purposes, reveals that over 20 and 29 plant species were used to treat women and children’s ailments, respectively. A consideration of gender dynamics around access to, use and control as well as benefit sharing from the use of plant and genetic resources is therefore closely linked to poverty outcomes, considering that a significant number of poor rural communities engage in petty trading of these resources as a source of income. Women are often involved in the harvesting and trading part of the value chain, often receiving disproportionally less than men engaged in the same activities. During the PPG phase, consultations with women’s groups/leaders and a detailed analysis of gender issues were conducted focusing on the four prioritized project sites. In addition, women’s groups/leaders were given the opportunity to raise gender equality concerns regarding the Project during the stakeholder engagement process. Communities around the project sites have constituted legal entities called Community Conservation Forums (CCF), with significant women participation. CCFs will be considered as key entry points in the project’s consultation processes and a channel through which women’s concerns can be raised. Based on the gender analysis and consultations with women groups, a Gender Action Plan for the project was developed (see Annex 10 of the Project Document), considering all gender equality concerns; the implementation of the Plan will ensure women’s’ participation and empowerment. The project will deliver global environmental benefits using a participatory approach and ensuring the equitable distribution of benefits among men and women, with at least 19,531 people (51% women) directly benefiting from the project at the local level. Gender-specific indicators have been included in the project results framework and targets have been defined to ensure that gender issues are considered and monitored during project implementation. Under outcome 3, a gender strategy will be developed and used to guide project implementation, monitoring, and reporting. Key interventions will include i) Training and capacity-building of key stakeholders (government, private sector, and civil society) on gender issues related to medicinal plant resources and ABS; ii) Produce a gender-based strategy related to management of plant genetic resources; iii) Establish a working linkage between DoE/MTEC and the Department of Gender/MGYSR to mainstream gender issues related to ABS; and iv) Conduct gender empowerment workshops on ABS with selected women and vulnerable groups (youth and herders); v) Produce a gender awareness strategy related to ABS; and vi) Document and share best practices and lessons learned on gender mainstreaming and medicinal plant product development. The project will ensure that gender disaggregated data is collected during implementation to inform gender responsive monitoring and reporting. Finally, the project implementation unit will include a gender specialist who will be responsible for ensuring the implementation of the Gender Action Plan and the Herders Engagement Plan and overall gender mainstreaming in the project following UNDP and GEF guidelines.

Briefly describe in the space below how the project mainstreams sustainability and resilience

This project is designed to generate local and global environmental benefits, meaning by its very nature, it is meant to promote and mainstreaming sound environmental management and sustainability. The project interventions are designed to contribute directly to biodiversity conservation and sustainable use of natural resources, and enhance the capacity of government, public and private stakeholders to protect and conserve key threatened biological and plant genetic resources. Project actions will contribute to conserve Afro-alpine wetlands, montane grasslands, and stands of indigenous forest in four protected areas (Sehlabathebe UNESCO Heritage Park, Tšehlanyane National Park, Bokong Nature Reserve, and Letša-la-Letsie Ramsar site) and their surrounding landscapes where the project will be implemented. The interventions that are proposed are environmentally-friendly, promote rehabilitation and restoration of degraded ecosystems, and have overall poverty reduction benefits, an important incentive for promoting biodiversity conservation in line with the NP on ABS and the CBD. The project will contribute to eradication of poverty by establishing ABS mechanisms that bring monetary and non-monetary benefits to local communities that are providers of genetic resources to research institutions and companies that use those resources for research, product development, and commercialization. Working in collaboration with traditional medical associations and international partners, capacitates for technological innovation will be built for bioprospecting on selected genetic resources of medicinal value, and the development and marketing of natural products for pharmaceutical use; promote responsible consumption and production by raising awareness about the linkages between access to genetic resources and their utilization and the conservation of biodiversity and the sustainable use of its components; enhance resilience of genetic resources, and the ecosystems and landscapes where they are found through capacity building for conduct of R&D activities and conservation actions; and build awareness at the local level about the importance of both in-situ and ex-situ conservation of selected resources under communal management, conservation of selected resources in household botanical gardens and nurseries, and in-situ conservation of selected resources within protected areas.

Briefly describe in the space below how the project strengthens accountability to stakeholders

The project will strengthen accountability to stakeholders in two ways: (i) by strengthening effective communication and coordination among all project stakeholders and the implementation of mechanisms to ensure active and representative participation during decision-making and implementation of project interventions that will be guided by already developed Stakeholder Engagement Plan; (ii) by developing a formal Grievance Redress Mechanism in accordance with UNDP`s Social and Environmental Standard Policy to ensure that all stakeholders including both duty-bearers and rights-holders are capacitated to meet their obligations and able to claim their rights respectively through known and transparent channels. All stakeholder will be informed of their right to access UNDP’s Accountability Mechanism (including a UNDP-led Stakeholder Response Mechanism and Compliance Review) in cases where the project-level GRM cannot adequately address the concerns raised. A communication and knowledge management strategy will be developed to systematize and disseminate knowledge, lessons learned, and best practices to promote up-scaling and replication. In line with the project governance structure, the project board will be the main platform for ensuring effective and efficient delivery of the project. Local project committees will be established where activities will be implemented. Through these committees, local partners will have the opportunity to participate in decision making regarding project management, including implementation of plans and project reviews, and also with respect to the technical aspects of the project. At least once a year, the project board will meet to review and approve technical and financial progress reports and annual workplans and budgets ensuring alignment with national priorities and addressing stakeholder needs. In line with the monitoring and evaluation plan, the project will annually prepare an implementation Review Report and undertake Mid Term Review and Terminal Evaluation. All project documentation relevant to safeguards risks and their management will be publicly disclosed, in accordance with UNDP’s policy on Public Disclosure.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Complete SESP Attachment 1 before responding to Question 2. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6. |  |  |  | QUESTION 6: Describe the assessment and management measures for each risk rated Moderate, Substantial or High. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Description (broken down by event, cause, impact) | Impact and Likelihood (1-5) | Significance (Low, Moderate Substantial, High) | Comments (optional) |  | Description of assessment and management measures for risks rated as Moderate, Substantial or High |  |  |  |
| Risk 1: Duty-bearers may not have the capacity to meet their obligations to protect human rights, including the right to accessing information and participation, which may disproportionally impact marginalized groups in the Project. Question P.2 | I = 4 L = 2 | Moderate | Although there is strong commitment of the Government to strengthen the national and local capacities to implement the Nagoya Protocol, there are significant limitations, not only in the institutional and the technical aspects of biodiversity conservation and natural resource management, but also in the capacity to design and implement policies for the effective participation of stakeholders, particularly vulnerable groups, as well as the equitable distribution of benefits. |  | A Strategic Environmental and Social Assessment (SESA) will be undertaken to assess and support the implementation of Components 2 and 3. It will i) assess the context and identify the key social and environmental issues associated with the sector in which the SESA will be carried out; ii) identify the social and environmental priorities through stakeholder dialogue with an emphasis on the participation of TK bearers, herders and other groups with special needs and interests (e.g. traditional medicine practitioners), women and youth; iii) assess the gaps in the policy, institutional, legal, and regulatory frameworks and the existing capacities to manage the environmental and social priorities; iii) recommend capacity-building and governance strengthening to address the gaps and shortcomings. The SESA would include an ESMF to guide activities with downstream social and environmental impacts The Stakeholder Engagement Plan (Annex 8 in the ProDoc) will feed into the participatory component of the SESA. The project will also establish a project-level Grievance Redress Mechanism and all stakeholders will have access to UNDP’s Accountability Mechanism to raise concerns about project impacts on their rights. |  |  |  |
| Risk 2: Holders of traditional knowledge may not have the capacity to claim their rights to genetic resources and their traditional knowledge, leading to their exclusion from the benefits of the project. Questions P.3, P.5, and P.13 . | I = 3 L = 3 | Moderate | One of the major barriers to the implementation of the Nagoya Protocol (NP) is the limited knowledge of ABS among communities and TK holders, which can limit their capacity to effectively negotiate with GR users or monitor implementation of ABS activities. Many of the communities are illiterate and poor, and therefore not always able to engage with formal policies and regulations. Their capacity to engage on issues therefore needs to be built. |  | Local communities and individuals of the Sehlabathebe UNESCO Heritage Park, Tšehlanyane National Park, Bokong Nature Reserve, and Letša-la-Letsie Ramsar site) and their surrounding landscapes, were given the opportunity to raise human rights concerns regarding the Project during the stakeholder engagement process. Based on the stakeholder consultations, a Stakeholder Participation and Engagement Plan was developed (see Annex 8 of the Project Document), that will guide these stakeholders and project implementers as to when, how and with whom consultations and exchanges should be undertaken throughout the life of the project including opportunities to express any human rights concerns. During the PPG stakeholder analysis was conducted and multiple consultations were conducted with stakeholders at the national and project site levels where they had the opportunity to raise any concerns related to the project, including human rights concerns. The Stakeholder Participation and Engagement Plan also includes a Grievance Redress mechanism (GRM) that will be instrumental in addressing the potential grievances/complaints that stakeholders, including marginalized groups, may have concerning project activities that affect them. Under Component 1, the project design includes technical outputs that will strengthen the regulatory environment and build awareness and capacity regarding the protection of people’s traditional knowledge about genetic resources. Key among these are: Output 1.1.4, under which an ABS and Associated TK Strategy will be developed; Output 1.3.1 which (Guidelines and procedures for obtaining PIC and MAT) and Output 1.3.2 (Guidelines for developing biocultural community protocols. |  |  |  |
| Risk 3: Women could be excluded from the policy dialogue and decision-making processes, as well as from taking part in the bioprospecting and laboratory analyses of medicinal plants, further increasing their discrimination and vulnerability. Questions P.10, P11, and 7.6 . | I = 4 L = 2 | Moderate |  |  | During the PPG phase, consultations with women’s groups/leaders and a detailed analysis of gender issues were conducted focusing on the four prioritized project sites. In addition, women’s groups/leaders were given the opportunity to raise gender equality concerns regarding the Project during the stakeholder engagement process. Communities around the project sites have constituted legal entities called Community Conservation forums (CCF), with significant women participation. CCFs will be considered a key consultation mechanism to raise women concerns. Based on the gender analysis and consultations with women groups, a Gender Action Plan for the project was defined (see Annex 10 of the Project Document), considering all gender equality concerns; the implementation of the Plan will ensure women participation and empowerment. Furthermore, activities under Output 3.1.1 will update the GAP, conduct gender empowerment workshops, establish a working relationship between DoE/MTEC and the Department of Gender/MGYSR to mainstream gender issues related to ABS; produce a gender-based strategy concerning the management of plant genetic resources, and develop and strengthen the capacity of key stakeholders on gender issues related to medicinal plant resources and ABS. |  |  |  |
| Risk 4. The wider tangible and intangible dimensions of Cultural Heritage associated with the traditional methods of cultivation and harvesting of medicinal plants may be overlooked, impacting on the cultural integrity of TK bearers, traditional healers/herbalists and herding groups. Questions 4.1, 4.3, and 4.5 | I = 3 L = 3 | Moderate | The Sehlabathebe National Park and World Heritage Site (UNESCO) is included in the project. There are numerous rock art representations and caves, which are utilized for rituals, which may also be associated with the use of medicinal plant and associated paraphernalia. Herders are a heterogeneous group comprising of owners of livestock as well as those employed or those looking after family stock, some of these are not necessarily marginalized. Bioprospecting activities often rely on the utilization of tangible and intangible forms of cultural heritage and TK as a point of departure. The project will work closely with local herbalists and healers. (Output 2.1.3). |  | During the PPG, a Herders Engagement Plan was developed (see Annex 21 of the Project Document) and a Traditional Healers and Herbalists Engagement Plan will be implemented to assure that both herders, as well as traditional healers and herbalists benefit and share the benefits that will accrue from the conservation and utilization of selected plant genetic resources. A targeted Cultural Heritage Impact Assessment (CHIA) to address the tangible and intangible dimensions will be carried out, with the participation of TK bearers and other key stakeholders. The CHIA will feed into the SESA to complement the assessment of non-formal institutions. During Implementation, the Stakeholder Participation and Engagement Plan will be developed to guide monitor the participation of herders and other special interest groups, to ensure that identified impacts are properly addressed, culturally appropriate benefits are provided, participatory processes are followed, and capacity support and institutional arrangements are established. Awareness campaigns and documentation of herders’ TK on the prioritized medicinal plants will be implemented with the involvement of herders (Output 2.2.2). The project’s GRM will take into consideration culturally appropriate channels so that men and women have equal access to the mechanism. The ABS legislation to be developed under Component 1 will involve the active participation of TK bearers and herding groups to ensure that benefits arising from the use of genetic resources that are held by local communities and groups of traditional healers are shared with them in a fair and equitable way, based on MAT (Article 5 of the NP). A national regulation for TK will ensure that TK associated with genetic resources held by local communities and traditional healers is accessed with their approval and involvement and that MAT have been established (Article 7 of the NP); and that local communities’ customary laws, community protocols, and procedures with respect to TK associated with genetic resources are considered (Article 12 of the NP). |  |  |  |
| Risk 5: Although the ABS policy and regulatory framework would lead to benefits for TK bearers and herders in the project area, they may also, unintentionally, induce an intensification of the unsustainable harvesting of the medicinal plants in other regions of the country, because of their commercial value. Questions 1.1, 1.2, 1.3, 5.2, and 5.4 | I = 3 L = 3 | Moderate | Herders, who are largely nomadic in nature, depend largely on rangelands for their survival including their health and that of the animals they look after. Raising awareness at the local level about the linkages between access to genetic resources and their utilization and the conservation of biodiversity and the sustainable use of its components, within and outside protected areas in the four prioritized landscapes, will contribute to the conservation of highland and rangeland ecosystems. |  | Lesotho’s ABS policy and regulatory framework, informed by the SESA, will be developed through a highly participatory process to ensure effective inter-institutional coordination and alignment with legislation or regulatory requirements from multiple sectors. SESA will include meaningful consultations with the associations of traditional practitioners (herbalists and healers), herders, and other stakeholders to identify social and environmental priorities associated with the ABS policy. It will also include an analysis of the legal and institutional frameworks to identify gaps and weaknesses associated with the country’s system to address the social and environmental priorities (Output 1.1.1). SESA's recommendations will lead to an improved governance and a greater capacity of the country’s system (Outputs 1.1.2, 1.1.3, 1.1.4, 1.2.2, 2.1.4, 2.2.1, 2.2.3) to address the social and environmental priorities. Under the ABS policy and regulatory framework, ABS initiatives (Output 2.2.2) would be promoted in other regions of the country. |  |  |  |
| Risk 6: Climate change, particularly hotter and dryer conditions, may impact on the habitats of the target medicinal plants, compromising the development objective of the project, Question 2.2 | L = 3 I = 3 | Moderate | Climate change projections in the country include an increase in the intensity and frequency of extreme events, such as floods and drought, affecting water resources, which, in turn, will lead to an increase in evaporative loss and a decrease in groundwater recharge. Savannas are expected to replace current grasslands, while the loss of habitats in high-elevation areas would pose severe threats to the survival of medicinal plants. |  | Several of the partner projects listed in Output 3.2.2 (GEF ID 5075 [UNDP]; GEF ID 5124 [FAO]; GEF ID 6926 [UNEP]) focus on climate-resilient development and adaptation to climate change. The information generated by these projects, particularly the Climate Services component of GEF ID 6926, will be integrated into the design and implementation of sustainable harvesting plans, thus building the climate resilience of the value chains. |  |  |  |
| Risk 7: The establishment of a laboratory and the processing equipment for safety and efficacy of genetic-resource related products could lead to gender discrimination and to occupational safety and health risks. Questions 1.13, 7.5, and 7.6 | I = 3 L =2 | Moderate | The preliminary capacity assessment of the national research centers for bioprospecting conducted during the project design phase showed that research and development on medicinal plants of Lesotho is at its infancy stage and is very limited in product development. The project will facilitate exchange programs with more established product developers (e.g., from South Africa) and establish partnerships between local product developers and international partners |  | Based on the gender analysis and consultations with women groups, a Gender Action Plan for the project was defined (see Annex 10 of the Project Document), considering all gender equality concerns; the implementation of the Plan will ensure women participation and empowerment. A targeted Occupational Safety and Health Action Plan (OSHAP), which will strengthen the capacities through targeted training of experts and technical staff of national research centers, including the NUL, Department of Agricultural Research, and Katse Botanical Garden in research and development associated with medicinal plants. This will ensure that research on medicinal plants and other commercial products does not only result in publications, but also leads to development of products that would meet high standards of safety and efficacy before entering the market. |  |  |  |
| Risk 7: The spread of COVID-19 could pose a risk to the health of stakeholders during project development and implementation, particularly in activities that involve consultation. Questions 3.4 and 7.6 | I = 2 L =2 | Low | The project will involve extensive consultations with TK bearers and communities Although Lesotho has lifted restrictions in August 2022, community health and safety issues could be triggered during project implementation, if COVID-19 persists or undergoes a resurgence. |  | The project will use agreed COVID-19 protocols that are consistent with the Government’s measures. Consultations will implement specific measures necessary to mitigate any potential risk of exposure, including personal protective gear (i.e., masks). |  |  |  |
|  | QUESTION 4: What is the overall project risk categorization? Note: Project categorization is determined by the highest level of significance of identified risks across all potential risk areas (as rated in Question 3). |  |  |  |  |  |  |  |
|  | Low Risk |  |  | ☐ |  |  |  |  |
|  | Moderate Risk |  |  | X |  | The project is considered of moderate risk. The project involves a strong participatory component, which will emphasize consultation with herders and TK bearers, including herbalists and healers. It will establish a grievance mechanism through which stakeholders can raise their concerns. Environmental and social grievances during implementation would be reported to the GEF in the annual PIR. |  |  |
|  | Substantial Risk |  |  | ☐ |  |  |  |  |
|  | High Risk |  |  | ☐ |  |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are triggered? (check all that apply) |  |  |  |  |  |  |  |
|  | Question only required for Moderate, Substantial and High Risk projects. |  |  |  |  |  |  |  |
|  | Is assessment required? (check if “yes”) |  |  | X |  |  |  | Status? (Completed, planned) |
|  | if yes, indicate overall type and status |  |  |  |  | X | Targeted assessment(s) Gender Analysis | Completed |
|  |  |  |  |  |  |  | Stakeholder Identification and Analysis | Completed |
|  |  |  |  |  |  |  | Cultural Heritage Impact Assessment | Planned |
|  |  |  |  |  |  | ☐ | ESIA (Environmental and Social Impact Assessment) |  |
|  |  |  |  |  |  | X | SESA (Strategic Environmental and Social Assessment) | Planned |
|  | Are management plans required? (check if “yes) |  |  | ☐ |  |  |  |  |
|  | If yes, indicate overall type |  |  |  |  | X | Targeted management plans (e.g. Indigenous Peoples Plan, Resettlement Action Plan, others) |  |
|  |  |  |  |  |  |  | Gender Action Plan (GAP) | Completed |
|  |  |  |  |  |  |  | Stakeholder Participation and Engagement Plan (STEP) | Planned (The Stakeholder Engagement Plan was completed during PPG and will be the basis of the STEP) |
|  |  |  |  |  |  |  | Traditional Healers and Herbalists Engagement Plan (THHEP) | Planned |
|  |  |  |  |  |  |  | Cultural Heritage Management Plan (CHMP) | Planned |
|  |  |  |  |  |  |  | Occupational Safety and Health Action Plan (OSHA) | Planned |
|  |  |  |  |  |  | ☐ | ESMP (Environmental and Social Management Plan) |  |
|  |  |  |  |  |  | X | ESMF (Environmental and Social Management Framework) |  |
|  | Based on identified risks, which Principles/Project-level Standards triggered? |  |  |  |  | Comments (not required) |  |  |
|  | Overarching Principle: Leave No One Behind |  |  | --- |  |  |  |  |
|  | Human Rights |  |  | X |  |  |  |  |
|  | Gender Equality and Women’s Empowerment |  |  | X |  |  |  |  |
|  | Sustainability and resilience |  |  | X |  |  |  |  |
|  | Accountability |  |  | X |  |  |  |  |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management |  |  | X |  |  |  |  |
|  | 2. Climate Change and Disaster Risks |  |  | X |  |  |  |  |
|  | 3. Community Health, Safety and Security |  |  | ☐ |  | The project will not generate risks associated with Standard 3. |  |  |
|  | 4. Cultural Heritage |  |  | X |  |  |  |  |
|  | 5. Displacement and Resettlement |  |  | ☐ |  | No physical or economic displacement will take place because of project activities. |  |  |
|  | 6. Indigenous Peoples |  |  | ☐ |  | No Indigenous Peoples have been identified. |  |  |
|  | 7. Labour and Working Conditions |  |  | X |  |  |  |  |
|  | 8. Pollution Prevention and Resource Efficiency |  |  | ☐ |  | The project will not involve activities that could generate risks associated with Standard 8. |  |  |

Final Sign Off

Final Screening at the design-stage is not complete until the following signatures are included.

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases, PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

## Annex 6: UNDP Risk Register

| Project Title: | Project Number: | Date: Click or tap to enter a date. |
| --- | --- | --- |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (individual accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is a risk that overharvesting of species in the wild continues unregulated or increases even under regulation. | As a result of demonstrated monetary benefits from ABS agreements | Which will impact the long term survival of the targeted species | 1. SOCIAL AND ENVIRONMENTAL (1.4. Biodiversity conservation and sustainable natural resource management) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 1.1: Mitigate-The project is designed to support the development of Lesotho’s institutional capacity and enabling environment to not only access to the benefits from the utilisation of genetic resources but to also conserve these biological resources. Current enforcement of existing regulations is weak, so this project will support strengthening of enforcement mechanisms and support stronger conservation focus for biological and genetic resources. Risk Treatment Owner: Project Manager |
| 2 | There is a risk that lack of coordination between the different stakeholders (national government agencies and/or district local authorities, private sector, research and academic institutions and communities (e.g. harvesters, traders) operating in the biological and genetic resources sector. | As a result of working in silos and mandate driven focus of sectors | Which will impact harmonization of policies across sectors, inadequate information sharing, monitoring, and reporting on ABS related matters. | 4. ORGANIZATIONAL (4.1. Governance) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 2 - Low likelihood Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of MINIMAL) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 2.1: Mitigate-The project will support the development of guidelines, protocols, codes of conduct and standards for coordinated action for the sector and provide training and capacity building for applying/implementing them. Collectively, these tools and systems should improve coordination, led by the relevant government institutions, to ensure that the provisions of the Nagoya Protocol on ABS, and the relevant support national frameworks facilitate a functional operating environment. Risk Treatment Owner: Project Manager |
| 3 | There is a risk that Climate change impacts negatively affect the ecosystems where these genetic and biological resources occur. | As a result of increased vulnerability and reduced resilience | Which will impact productivity, yield and sustainability of supply from target species | 1. SOCIAL AND ENVIRONMENTAL (1.5. Climate change and disaster risks) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 3.1: Mitigate- Several of the partner projects listed in Output 3.2.2 (GEF ID 5075 [UNDP]; GEF ID 5124 [FAO]; GEF ID 6926 [UNEP]) focus on climate-resilient development and adaptation to climate change. The information generated by these projects, particularly the Climate Services component of GEF ID 6926, will be integrated into the design and implementation of sustainable harvesting plans, thus building the climate resilience of the value chains. Risk Treatment Owner: Project Manager |
| 4 | There is a risk that duty-bearers may not have the capacity to meet their obligations to protect human rights, including the right to accessing information and participation, which may disproportionally impact marginalized groups in the Project. | As a result of capacity gaps in knowledge, skills and resources | Which will impact ability of right holders to effectively benefit from the project investments. | 1. SOCIAL AND ENVIRONMENTAL (1.1. Human rights) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 2 - Minor Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 4.1: Mitigate-A Strategic Environmental and Social Assessment (SESA) will be undertaken to assess and support the implementation of Components 2 and 3. It will i) assess the context and identify the key social and environmental issues associated with the sector in which the SESA will be carried out; ii) identify the social and environmental priorities through stakeholder dialogue with an emphasis on the participation of TK bearers, herders and other groups with special needs and interests (e.g. traditional medicine practitioners), women and youth; iii) assess the gaps in the policy, institutional, legal, and regulatory frameworks and the existing capacities to manage the environmental and social priorities; iii) recommend capacity-building and governance strengthening to address the gaps and shortcomings. The SESA would include an ESMF to guide activities with downstream social and environmental impacts The Stakeholder Engagement Plan (Annex 8 in the ProDoc) will feed into the participatory component of the SESA. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 4.2: Mitigate-The project will also establish a project-level Grievance Redress Mechanism and all stakeholders will have access to UNDP’s Accountability Mechanism to raise concerns about project impacts on their rights. Risk Treatment Owner: Project Manager |
| 5 | There is a risk that holders of traditional knowledge may not have the capacity to claim their rights to genetic resources and their traditional knowledge, | As a result of inadequate knowledge, skills and power to demand for their rights… | Which will lead to the exclusion of TK holders from the benefits of the project. | 1. SOCIAL AND ENVIRONMENTAL (1.7. Cultural heritage) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 5.1: Mitigate- Local communities and individuals of the Sehlabathebe UNESCO Heritage Park, Tšehlanyane National Park, Bokong Nature Reserve, and Letša-la-Letsie Ramsar site) and their surrounding landscapes, were given the opportunity to raise human rights concerns regarding the Project during the stakeholder engagement process. Based on the stakeholder consultations, a Stakeholder Participation and Engagement Plan was developed (see Annex 8 of the Project Document), that will guide these stakeholders and project implementers as to when, how and with whom consultations and exchanges should be undertaken throughout the life of the project including opportunities to express any human rights concerns. During the PPG stakeholder analysis was conducted and multiple consultations were conducted with stakeholders at the national and project site levels where they had the opportunity to raise any concerns related to the project, including human rights concerns. The Stakeholder Participation and Engagement Plan also includes a Grievance Redress mechanism (GRM) that will be instrumental in addressing the potential grievances/complaints that stakeholders, including marginalized groups, may have concerning project activities that affect them. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 5.2. Under Component 1, the project design includes technical outputs that will strengthen the regulatory environment and build awareness and capacity regarding the protection of people’s traditional knowledge about genetic resources. Key among these are: Output 1.1.4, under which an ABS and Associated TK Strategy will be developed; Output 1.3.1 which (Guidelines and procedures for obtaining PIC and MAT) and Output 1.3.2 (Guidelines for developing biocultural community protocols. Risk Owner: Project Manager |
| 6 | There is a risk that local communities or individuals, may not have been given the opportunity, to raise human rights concerns regarding the Project during the stakeholder engagement process | As a result of inadequate consultations or approaches used to engage with stakeholders | Which will impact participation and benefits of marginalized populations. | 1. SOCIAL AND ENVIRONMENTAL (1.12. Stakeholder engagement) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 1 - Negligible Risk level: LOW (equates to a risk appetite of MINIMAL) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 6.1: Mitigate-During the PPG multiple consultation were conducted with stakeholders at the national and project site levels where they had the opportunity to raise any concerns related to the project, including human rights concerns. During the PPG, a stakeholder analysis was conducted, and a Stakeholder Participation Plan was developed (see Annex 8 of this Project Document), that will guide these stakeholders and project implementers as to when, how and with whom consultations and exchanges should be undertaken throughout the life of the project including opportunities to express any human rights concerns. Risk Treatment Owner: Project Manager |
| 7 | There is a risk that women could be excluded from the policy dialogue and decision-making processes, as well as from taking part in the bioprospecting and laboratory analyses of medicinal plants, further increasing their discrimination and vulnerability. | As a result of cultural patriarchal traditional institutions and beliefs | Which will impact in their ability to contribute and benefit from project investments… | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 2 - Minor Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 7.1: Mitigate- During the PPG phase, consultations with women’s groups/leaders and a detailed analysis of gender issues were conducted focusing on the four prioritized project sites. In addition, women’s groups/leaders were given the opportunity to raise gender equality concerns regarding the Project during the stakeholder engagement process. Communities around the project sites have constituted legal entities called Community Conservation forums (CCF), with significant women participation. CCFs will be considered a key consultation mechanism to raise women concerns. Based on the gender analysis and consultations with women groups, a Gender Action Plan for the project was defined (see Annex 10 of the Project Document), considering all gender equality concerns; the implementation of the Plan will ensure women participation and empowerment. Furthermore, activities under Output 3.1.1 will update the GAP, conduct gender empowerment workshops, establish a working relationship between DoE/MTEC and the Department of Gender/MGYSR to mainstream gender issues related to ABS; produce a gender-based strategy concerning the management of plant genetic resources, and develop and strengthen the capacity of key stakeholders on gender issues related to medicinal plant resources and ABS. Risk Treatment Owner: Project Manager |
| 8 | There is a risk that the wider tangible and intangible dimensions of Cultural Heritage associated with the traditional methods of cultivation and harvesting of medicinal plants may be overlooked, | As a result of inadequate engagement of TK holders and herders during implementation of project activities. | Which will impact the cultural integrity of TK bearers, traditional healers/herbalists and herding groups. | 1. SOCIAL AND ENVIRONMENTAL (1.7. Cultural heritage) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 8.1: … During the PPG, a Herders Engagement Plan was developed (see Annex 21 of the Project Document) and a Traditional Healers and Herbalists Engagement Plan will be implemented to assure that both herders, as well as traditional healers and herbalists benefit and share the benefits that will accrue from the conservation and utilization of selected plant genetic resources. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 8.2 Mitigate-A targeted Cultural Heritage Impact Assessment (CHIA) to address the tangible and intangible dimensions will be carried out, with the participation of TK bearers and other key stakeholders. The CHIA will feed into the SESA to complement the assessment of non-formal institutions. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 8.3: Mitigate- During Implementation, the Stakeholder Participation and Engagement Plan will be developed to guide monitor the participation of herders and other special interest groups, to ensure that identified impacts are properly addressed, culturally appropriate benefits are provided, participatory processes are followed, and capacity support and institutional arrangements are established. Awareness campaigns and documentation of herders’ TK on the prioritized medicinal plants will be implemented with the involvement of herders (Output 2.2.2). The project’s GRM will take into consideration culturally appropriate channels so that men and women have equal access to the mechanism. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk treatment: Mitigate- The ABS legislation to be developed under Component 1 will involve the active participation of TK bearers and herding groups to ensure that benefits arising from the use of genetic resources that are held by local communities and groups of traditional healers are shared with them in a fair and equitable way, based on MAT (Article 5 of the NP). Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk treatment: Mitigate-A national regulation for TK will ensure that TK associated with genetic resources held by local communities and traditional healers is accessed with their approval and involvement and that MAT have been established (Article 7 of the NP); and that local communities’ customary laws, community protocols, and procedures with respect to TK associated with genetic resources are considered (Article 12 of the NP). Risk Treatment Owner: Project Manager |
| 9 | There is a risk that although the ABS policy and regulatory framework would lead to benefits for TK bearers and herders in the project area, they may also, unintentionally, induce an intensification of the unsustainable harvesting of the medicinal plants in other regions of the country, because of their commercial value. | As a result of increased benefits and demand | Which will impact populations of target species in the wild. | 3. OPERATIONAL (3.5. Partners’ engagement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 30-Sep-29 | IP/UNDP RR | Risk Treatment 9.1: Mitigate- Lesotho’s ABS policy and regulatory framework, informed by the SESA, will be developed through a highly participatory process to ensure effective inter-institutional coordination and alignment with legislation or regulatory requirements from multiple sectors. SESA will include meaningful consultations with the associations of traditional practitioners (herbalists and healers), herders, and other stakeholders to identify social and environmental priorities associated with the ABS policy. It will also include an analysis of the legal and institutional frameworks to identify gaps and weaknesses associated with the country’s system to address the social and environmental priorities (Output 1.1.1). SESA's recommendations will lead to an improved governance and a greater capacity of the country’s system (Outputs 1.1.2, 1.1.3, 1.1.4, 1.2.2, 2.1.4, 2.2.1, 2.2.3) to address the social and environmental priorities. Under the ABS policy and regulatory framework, ABS initiatives (Output 2.2.2) would be promoted in other regions of the country. Risk Treatment Owner: Project Manager |
| 10 | There is a risk that the establishment of a laboratory and the processing equipment for safety and efficacy of genetic-resource related products could lead to gender discrimination and to occupational safety and health risks. | As a result of inadequate awareness and training of workers on health and safety measures, and limited investment in occupational health and safety infrastructure. | Which will impact health of both men and women; reduce workers morale and productivity; reduce economic benefits for women | 1. SOCIAL AND ENVIRONMENTAL (1.10. Labour and working conditions) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 2 - Minor Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 10.1: Mitigate-Based on the gender analysis and consultations with women groups, a Gender Action Plan for the project was defined (see Annex 10 of the Project Document), considering all gender equality concerns; the implementation of the Plan will ensure women participation and empowerment. A targeted Occupational Safety and Health Action Plan (OSHAP), which will strengthen the capacities through targeted training of experts and technical staff of national research centers, including the NUL, Department of Agricultural Research, and Katse Botanical Garden in research and development associated with medicinal plants. This will ensure that research on medicinal plants and other commercial products does not only result in publications, but also leads to development of products that would meet high standards of safety and efficacy before entering the market. Risk Treatment Owner: Project Manager |
| 11 | There is a risk that the spread of COVID-19 could pose a risk to the health of stakeholders during project implementation, particularly in activities that involve consultation. | As a result of person-to-person physical contacts | Which will impact the health and ability of stakeholders to effectively contribute to the project activities | 1. SOCIAL AND ENVIRONMENTAL (1.6. Community health, safety and security) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 2 - Low likelihood Impact: 2 - Minor Risk level: LOW (equates to a risk appetite of MINIMAL) | From: 01-Mar-24 To: 30-Sep-29 | IP/UNDP RR | Risk Treatment 11.1: Mitigate- The project will use established COVID-19 protocols that are consistent with the Government’s measures. Consultations will implement specific measures necessary to mitigate any potential risk of exposure, including personal protective gear (i.e., masks). Risk Treatment Owner: Project Manager |

## Annex 7: Overview of Technical Consultancies/Subcontracts

| Consultant | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| For Project Management |  |  |
| Local / National contracting |  |  |
| Project Manager/Coordinator Rate: $1,200/week | 43 weeks / over 5 years | The Project Manager (PM), together with the Lead Technical Advisor will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. Duties and Responsibilities - Manage the overall conduct of the project. - Plan the activities of the project and monitor progress against the approved workplan. - Execute activities by managing personnel, goods and services, training and low-value grants, including drafting terms of reference and work specifications, and overseeing all contractors’ work. - Monitor events as determined in the project monitoring plan, and update the plan as required. - Provide support for completion of assessments required by UNDP, spot checks and audits. - Manage requests for the provision of UNDP financial resources through funding advances, direct payments or reimbursement using the FACE form. - Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports. - Monitor progress, watch for plan deviations and make course corrections when needed within project board-agreed tolerances to achieve results. - Ensure that changes are controlled and problems addressed. - Perform regular progress reporting to the project board as agreed with the board, including measures to address challenges and opportunities. - Prepare and submit financial reports to UNDP on a quarterly basis. - Manage and monitor the project risks – including social and environmental risks - initially identified and submit new risks to the Project Board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log; - Capture lessons learned during project implementation. - Prepare revisions to the multi-year workplan, as needed, as well as annual and quarterly plans if required. - Prepare the inception report no later than one month after the inception workshop. - Ensure that the indicators included in the project results framework are monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR. - Prepare the GEF PIR; - Assess major and minor amendments to the project within the parameters set by UNDP-GEF; - Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans; - Monitor and track progress against the GEF Core indicators. - Support the Mid-term review and Terminal Evaluation process. - Add technical tasks as necessary |
| Project Assistant |  | Duties and Responsibilities Under the guidance and supervision of the Project Manager, the Project Assistant will carry out the following tasks: - Assist the Project Manager in day-to-day management and oversight of project activities; - Assist the M&E officer in matters related to M&E and knowledge resources management; - Assist in the preparation of progress reports; - Ensure all project documentation (progress reports, consulting and other technical reports, minutes of meetings, etc.) are properly maintained in hard and electronic copies in an efficient and readily accessible filing system, for when required by PB, TAC, UNDP, project consultants and other PMU staff; - Provide PMU-related administrative and logistical assistance. |
| Project Accountant/Finance Assistant/Finance officer |  | Duties and Responsibilities - Keep records of project funds and expenditures, and ensure all project-related financial documentation are well maintained and readily available when required by the Project Manager; - Review project expenditures and ensure that project funds are used in compliance with the Project Document and GoI financial rules and procedures; - Validate and certify FACE forms before submission to UNDP; - Provide necessary financial information as and when required for project management decisions; - Provide necessary financial information during project audit(s); - Review annual budgets and project expenditure reports, and notify the Project Manager if there are any discrepancies or issues; - Consolidate financial progress reports submitted by the responsible parties for implementation of project activities; - Liaise and follow up with the responsible parties for implementation of project activities in matters related to project funds and financial progress reports. |
| International / Regional and global contracting |  |  |
| For Technical Assistance |  |  |
| Outcome 1 |  |  |
| Local / National contracting |  |  |
| Protected Area Capacity Development National Specialist Rate: $300/week | 80 weeks / over 5 years | Under close supervision of Lead Technical Advisor and Project Manager (PM) the Protected Area Capacity Development Specialist (PACDS) will work closely with the Protected Area Capacity Development Advisor (PACDA) to conduct protected area capacity building related to the project under Outputs 1.2 and 1.3 and support a working group for improved protected area capacity building and work with that group to: - Contribute to the development of a capacity development strategy and action plan for increasing the management effectiveness of the PA system. - Coordinate the establishment of PA management standards and a PA and individual performance monitoring system for different categories of PAs. - Contribute to the development of a program of training to raise focal competencies of senior and mid-level protected area managers and practioners. - Contribute to the indentification of incentive mechanisms for increasing the motivation of field staff. - Contribute to the development and institutionalisation of modernized reporting structure and methods. - Contribute to the development of law enforcement and habitat/biodiversity monitoring protocols. - Coordinate the development and institutionalisation of a PA information and knowledge management system enabling learning from, and upscaling of, pilot/individual project activities. - Coordinate the development of official guidelines for community engagement and co-management. |
| Outcome 4: KM and M&E |  |  |
| Project Gender Officer |  | Duties and Responsibilities - Monitor progress in implementation of the project Gender Action Plan ensuring that targets are fully met and the reporting requirements are fulfilled; - Oversee/develop/coordinate implementation of all gender-related work; - Review the Gender Action Plan annually, and update and revise corresponding management plans as necessary; - Work with the M&E officer and Safeguards Officer to ensure reporting, monitoring and evaluation fully address the gender issues of the project; |
| Project Monitoring and Evaluation Officer |  | Duties and Responsibilities - Monitor project progress and participate in the production of progress reports ensuring that they meet the necessary reporting requirements and standards; - Ensure project’s M&E meets the requirements of the Government, the UNDP Country Office, and UNDP-GEF; develop project-specific M&E tools as necessary; - Oversee and ensure the implementation of the project’s M&E plan, including periodic appraisal of the Project’s Theory of Change and Results Framework with reference to actual and potential project progress and results; - Oversee/develop/coordinate the implementation of the stakeholder engagement plan; - Oversee and guide the design of surveys/ assessments commissioned for monitoring and evaluating project results; - Facilitate mid-term and terminal evaluations of the project; including management responses; - Facilitate annual reviews of the project and produce analytical reports from these annual reviews, including learning and other knowledge management products; - Support project site M&E and learning missions; - Visit project sites as and when required to appraise project progress on the ground and validate written progress reports. |
| Outcome |  |  |
| Project Social and Environmental Safeguards Officer |  | Duties and Responsibilities - Monitor progress in development/implementation of the project ESMP/ESMF ensuring that UNDPs SES policy is fully met and the reporting requirements are fulfilled; - Oversee/develop/coordinate implementation of all safeguard related plans; - Ensure social and environmental grievances are managed effectively and transparently; - Review the SESP annually, and update and revise corresponding risk log; mitigation/management plans as necessary; - Ensure full disclosure with concerned stakeholders; - Ensure environmental and social risks are identified, avoided, mitigated and managed throughout project implementation; - Work with the M&E officer to ensure reporting, monitoring and evaluation fully address the safeguard issues of the project; nm |
| International / Regional and global contracting |  |  |
| Lead Technical Advisor Rate: $2,000/week | 20 weeks / over 5 years | The Lead Technical Adviser will be responsible for providing overall technical backstopping and management support to the Project. |
| International PA & Biodiversity Strategy Advisor Rate: $ 2,000/week | 25 weeks / over 5 years | In close coordination with the Project Manager (PM), the international Protected Areas and Biodiversity Advisor (PABA) will provide international perspective, strategic guidance and technical inputs to the implementation of activities under Outputs 1.1 to 1.6, including the following: - For Output 1.1, the PABA will coordinate and provide technical advice to the international and national policy specialists, participate in the policy review process and provide inputs to policy recommendations for strengthening the national PA system - For Output 1.2, the PABA will coordinate and provide technical advice to the international and national capacity building specialists regarding the capacity development strategy and action plan for increasing the management effectiveness of the PA system; development of PA management standards and performance monitoring system; the development and institutionalisation of a modernized PA reporting system; the development of law enforcement and habitat/biodiversity monitoring protocols; and the development and institutionalisation of a PA information and knowledge management system - For Output 1.3, the PABA will provide technical advice to the international and national capacity building specialists, and provide guidance and inputs to the development and delivery of a program of training to raise focal competencies of senior and mid-level protected area managers and practitioners. - For Output 1.4, the PABA will coordinate and provide technical advice to the international and national sustainable financing experts regarding development of a sustainable financing strategy for the PA system, capacity building for implementation of the strategy, the development of a series of studies to inform sustainable financing policies and plans, and integrating PA system concerns into REDD+ programme development. - For Output 1.5, the PABA will coordinate and provide technical advice to the international and national landscape conservation regarding awareness and knowledge building for State, Region and local government units in Kachin State and Sagaing Region on the value of PAs; and implementation of a social marketing campaign linked to cofinanced WCS national communications strategy work. - For Output 1.6, the PABA will provide technical advice and support to the national PABS, NWCD and other stakeholders for implementation of PA gap analysis recommendations; coordinate plans for biological and social ground-truthing surveys for areas of conservation value; and facilitate a cooperative process to identify potential areas for PA creation. |

## Annex 8: Stakeholder Engagement Plan

The main objective of this Stakeholder Engagement Plan is to identify and document key stakeholders who may have a strong interest in or ability to influence the planned Medicinal Plants ABS project in the four prioritized landscapes including national parks (Sehlabathebe National Park, Bokong Nature Reserve, Ts`ehlanyane National Park, and Let`seng la Letsie Ramsar site). The Plan is intended to guide these stakeholders and project implementers as to when, how and with whom consultations and exchanges should be undertaken throughout the life of this ABS project. This plan is based on a stakeholder analysis, which enabled the identification of key stakeholders, their interests in the project, and the form of their engagement in the implementation of the ABS project. Working with a broad range of stakeholders will help to define project parameters and fill key knowledge gaps, and, if necessary, generate alternative ideas regarding project design and potential risks and mitigation measures.

As a matter of principle the analysis that informed this Stakeholder Engagement Plan has been developed from both secondary sources and from consultation with the key stakeholders through different forums. These stakeholders range from community based entities up to policy makers and potential project implementers. A specific herders’ plan (Annex 21) has been developed, based on fieldwork engagement with this marginalized group which resides in the wild most of their lives. While Lesotho does not have distinct indigenous groups, herders are however critical users of medicinal plants for their personal use and that of their livestock hence they have to be involved in the key project activities of propagation, harvesting and utilization of selected medicinal plants. Direct collaboration with key stakeholder groups was utilized through two workshops and community consultations so as to accurately identify stakeholders, their interests, and to plan for their participation in the implementation of the project. The third workshop was a validation of the PPG process, which also added new players and the fourth project site. The PPG Inception Workshop was held in May 2018 in the city of Maseru, Lesotho and its main purpose was to assist project stakeholders to understand the project design, understand their role and responsibilities in the project including during project implementation and monitoring, as well as communications, reporting, and conflict resolution and grievance redress. Among its specific objectives the inception workshop intended to assist the project stakeholders and the PPG project team to understand and take ownership of the project goals and objectives, as well as finalize the preparation of the PPG work plan. In addition the workshop aimed at re-building commitment and momentum among key stakeholders for the PPG phase.

Another consultation event that brought stakeholders together and re-build commitment to ownership of the project was the Results Framework Workshop held on July 2018 in the city of Maseru, Lesotho.  The main purpose of the workshop was to: a) define the Project Results Framework including the revised project outputs, indicators, baseline information, targets, verification mechanisms, and risks and assumptions; b) outline the projects activities for each output/component; and c) preliminary project costing including co-financing. Additional stakeholders were interviewed after workshop so as to extend the net wider and have all those who may have interest in the project considered. Stakeholders were also identified through interviews and focus group discussions during consultations with communities around the protected areas where the ABS project is going to be implemented. The Plan will be updated during project implementation with stakeholders that in addition to confirming the project plan will also review and agree on the stakeholder engagement plan. The Plan articulates involvement and participation of stakeholders premised on the project outcomes and outputs.

A Project Validation Workshop was held on December 2018 to present, discuss, and validate with relevant stakeholders the project concept, results framework, activities, implementation arrangements, and budget of the project proposal to be summited to the GEF. Recommendations from the workshop participants were considered in the development of the final draft of this Project Document. Annex 23 of this Project Document includes the list of the stakeholders who participated in the consultation process during the final workshop.

Stakeholder Analysis

The ultimate goal of a stakeholder analysis is to inform the development of a Stakeholder Engagement Plan that outlines the specific engagement activities to be carried out over the course of the project. A summary of the stakeholder analysis is presented below and presents a brief description of each key stakeholder, their interests, importance, and influence in the successful implementation of the proposed ABS project.

|  | Stakeholders | Interests at stake in relation to project | Effect of project on Interests (+ 0 –) | Importance (scale 1 to 5, 5 = highest) | Influence (scale 1 to 5, 5 = highest) |
| --- | --- | --- | --- | --- | --- |
| 1 | Government Ministries and departments including Authorities/Agencies | Effective citizen participation and benefit sharing | + | 5 | 5 |
| 2 | Universities and research institutes | Knowledge sharing and management, innovation and product development | + | 4 | 2 |
| 3 | Community based organizations | Fair utilization of and benefit from communal genetic resources | + | 5 | 3 |
| 4 | Traditional Healers Associations | Fair participation and protection of TK | + | 4 | 3 |
| 5 | NGO groups | Social justice and greater influence | + | 3 | 4 |
| 6 | Private sector organizations | Opportunities for international markets and maximization of profit | +/– | 4 | 3 |
| 7 | Marginalized groups, including herders | Opportunities to participate and greater influence | + | 5 | 1 |
| 8 | Women’s groups | Opportunities to participate in business opportunities, fairness in ABS regimes | + | 5 | 2 |
| 9 | International Development Partners | Sustainable development goals | + | 5 | 3 |

Stakeholder Engagement and Participation Approach

Stakeholder engagement will be held according to the following principles identified as critical by the UNDP stakeholder engagement guidelines:

| Principle | Stakeholder participation will: |
| --- | --- |
| Adding Value | Be an essential means of adding value to the project. |
| Inclusivity | Include all relevant stakeholders. |
| Accessibility and Access | Be accessible and promote access to the process. |
| Transparency | Be based on transparency and fair access to information. |
| Fairness | Ensure that all stakeholders are treated in a fair and unbiased way. |
| Accountability | Be based on a commitment to accountability by all stakeholders. |
| Constructive | Seek to manage conflict and promote the public interest. |
| Redressing | Seek to redress inequity and injustice. |
| Capacitating | Seek to develop the capacity of all stakeholders. |
| Needs-Based | Be based on the needs of all stakeholders. |
| Flexible | Be designed and implemented in a flexible manner. |
| Rational and Coordinated | Be rationally planned and coordinated, rather than ad hoc. |
| Excellence | Be subject to ongoing selection and commitment. |

Stakeholder Engagement Plan

The extensive stakeholder consultations and engagement that began during the PPG phase will be continued throughout the project implementation. To achieve this the project design has several mechanisms. Among these are:

Project Inception Workshop: The project inception workshop will present the official project document and contract to both direct stakeholders and the public. The project inception is also the official launch of the project and presents stakeholders with the work plan of the project. The inception workshop is the final display of commitment to the project before stakeholders begin to delve into the activities of the project.

Project Board: The Project Board is the main governance body of the project that will ensure the continued participation of key stakeholders in the project planning, implementation, and M&E. The Project Board will be comprised of representatives of the governmental agencies, private sector, and special interest groups. The Project Board will approve the work plans, be represented on recruitment processes, and provide overall strategic guidance to the project.

Whilst it is expected that the Ministry of Tourism, Environment and Culture (MTEC) will lead the project implementation and chair the Project Board; others may chair at different stages of the project cycle in an alternating situation. Other stakeholders may also be invited to participate in meetings of the Project Board, during which strategic guidelines and work plans will be discussed, negotiated, and approved by executing parties.

During the initial phase of project implementation, agreements will be made regarding the development of each of the expected activities. MTEC will take the lead for most of the activities, and may include other institutions as partners in the implementation of the activities based on their roles and mandates within the environmental, natural and genetic resources, range management, pharmacological, financial, and other sectors related to the project. It is suggested that the Department of Gender/MGSYR has a seat on the Project Board to ensure gender mainstreaming. The composition of the Project Board should also strive for gender equality/equity.

Project Management Unit (PMU): The PMU is the operational center of the project and has direct responsibility for its implementation. The PMU is responsible for the implementation of the stakeholder engagement plan, communications plan, gender action plan, grievance redress mechanisms, and M&E. Led by a Project Manager who receives guidance from the Project Board, the PMU ensures the participation of all stakeholders and addresses stakeholder conflicts.

Communications and Dissemination of Information: The PMU will implement a stakeholder’s communication plan to ensure communication with all stakeholders. The medium will be stakeholder specific and utilize both traditional methods such as meetings and telephone calls with newer methods such as a listserv, WhatsApp broadcast messaging, SMS, etc. Attention will be given to jargon-free language and translation of technical information into local languages. The PMU will include a Communications Expert to achieve the objectives of the plan. Additionally, the PMU will have active knowledge management with the documentation of processes and lessons learned, which will be shared with all stakeholders. Component 3 of the project is devoted to communication and knowledge management.

Gender Action Plan: This will secure the involvement of both genders, but especially women who are often marginalized in decision processes regarding the management of natural and plant genetic resources and the derived benefits from their use. The Gender Action Plan will address the impacts of project activities and account for their specific means. The Gender Action Plan, included as Annex 10 of this Project Document, will be guided by the principle of equality or equity.

Grievance Mechanism: A grievance mechanism will be established and published so that all stakeholders are aware of its existence. The Project Manager and the Gender and Safeguards Officer will be responsible for documenting all grievances and ensuring they are addressed in a timely manner, including issues related to issues related to community tenure of the selected medicinal plants.

Activities, Training, and Engagement Plans: All training activities and engagement plans will use a participatory approach that is rights-based and integrates the perspectives of all users using bottom-up approaches, integrating the different views of local stakeholders and beneficiaries with those of institutions, authorities, decision makers, and communities. It will also be gender-responsive.

Decentralized M&E: Project M&E will be done through decentralized assessments including meetings with the local committees, interviews of direct beneficiaries and their representative organizations, local, and national workshops, with local and national stakeholders, as well as meetings with special groups such as women to verify indicators. The Annual Work Plan (AWP) and outputs will be the main tool used for monitoring and tracking indicators, with stakeholder participation monitored in progress evaluations. Progress towards achieving the objectives will be evaluated in terms of the quality and timeliness of products, using appropriate participatory methods that ensure the timely and appropriate adjustment of the project implementation strategy. M&E will be conducted according to UNDP and GEF guidelines and following the project’s M&E Plan.

| Stakeholder Type |  | Stakeholder |  | Role in the Project |  | Activities |  | Results | Component | Duration |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Government institutions, Implementation Agency responsible for project outputs |  |  |  |  |  |  |  |  |  |  |  |
| Government institution, Implementation Agency responsible for project outputs |  | The Ministry of Tourism, Environment and Culture (MTEC)- Department of Environment (DoE). MTEC is responsible for promoting adoption of principles and strategies for the protection and recovery of the environment, sustainable use of natural resources and the introduction of sustainable development principles in the formulation and implementation of public policies. The DoE is the National Focal Point (NFP) and National Competent Authority (NCA) for the purposes of the Nagoya Protocol. |  | The Department of Environment (DoE) will be the Executing Agency of the project. Will be a responsible party for project implementation including stakeholder engagement and project management. Will lead the drafting of national ABS policy and regulatory framework. Will also embrace a gender perspective including the creation of a gender unit that will ensure the mainstreaming of gender in all the project activities. |  | - Updating of National Environment Policy to reflect the Nagoya Protocol principles. - Drafting and presentation of the ABS Bill to parliament - Implementation of the project through the establishment of the Project Management Unit. - Communication and coordination with the GEF and UND (Project Management). - Technical knowledge and expertise to strengthening and supporting the themes of the project: biodiversity conservation, value- addition, gender mainstreaming, and knowledge management. - Lead the Project Board and provide guidance and management of the PMU to achieve the objectives and goals of the project. - Ensure that the project is framed within the international standards and norms related to environmental, and biodiversity conservation. - Ensure that the project complies with GEF safeguard policies, including considerations of gender, and other social policies through the creation and participation of the gender focal point. - Ensure broad-based stakeholder participation. - Create the gender focal point to coordinate the implementation of the Gender Mainstreaming Strategy. All project outputs |  | - National Environment Policy updated to reflect the principles of Nagoya Protocol and the Biodiversity Act, publicised. - ABS policy and regulatory framework in place. - Regulation on conservation and sustainable use in place. - International conventions (Nagoya Protocol) observed and mainstreamed. - Bio-prospecting and TK regulations publicised. - Appropriate communication with the GEF and UNDP to guide the project actions. - Project is implemented and executed in all its aspects: planning, operational, technical, and administrative, with gender considerations. - Appropriate coordination with the project stakeholders to successfully achieve the project outcomes and outputs. - Project Board functioning and accommodating diverse stakeholders, including minority groups. - Gender focal point created as part of PMU to coordinate and facilitate implementation of the project’s Gender Mainstreaming Strategy. | 1, 2, 3 | 5 years |  |
|  |  | UNDP |  | UNDP will be the Implementing partner with the DOE. UNDP will be responsible for monitoring the effective and efficient use of project resources, and achievement of all project objectives. |  | - Record and monitor progress of the project. - Ensure efficient use of project resources. - Provide general oversight provided throughout the term of the project. - Ensuring the standard UNDP and GEF M&E requirements are fulfilled to the highest quality All project outputs |  | - Project progress recorded and monitored. - Mid-term and terminal reviews undertaken. - Regular supervision mission undertaken and reports shared with Project Board and project team. - Compliance to UNDP and GEF M&E requirements fully met. | 1, 2, 3 | 5 years |  |
| Government Ministry |  | National Parks (DOE/MTEC) |  | Sehlabathebe UNESCO Heritage Park (6,952 ha), The Tšehlanyane National Park (5,394 ha) & Bokong Nature Reserve (1,952 ha), Lets`eng la Letsie (XX ha) and communities adjacent to these are already involved in some form of conserving and harvesting genetic resources they host, the Parks collaborate with community conservation forum (CCF) to ensure conservation and sustainable use of the three targeted plant species (P. sidoides, A. polyphylla and H. hemerocallidea). National Parks can be sites for research on plant valuation and pharmaceutical research. |  | - Participate in propagation and re-introduction, and conservation of the three plant species in collaboration with adjacent communities. - Contribute input into development of business and value-addition skills to harvest, process, package, and market natural products from the selected genetic resources in collaboration with the private sector and Community Councils. - Contribute into research and bio-prospecting activities. Outputs 2.1.1, 2.2.1, 2.3.4, 3.2.1 |  | - Biodiversity conservation through the sustainable utilization of selected commercially – important medicinal plants and ABS agreements in four prioritised landscapes. - Training programs undertaken for communities to participate in value addition of the prioritized medicinal plants. | 1, 2, 3 | 5 years |  |
| Government Ministry |  | Ministry of Law and Constitutional Affairs (MLCA) is responsible for providing guidance on constitutional affairs and drafting and enactment of national laws. |  | The MLCA will collaborate in the drafting and enactment of laws and have the capacity to monitor and enforce compliance to ABS regulations, including the medicinal plants harvesting/exploitation and use. |  | - Drafting and presentation of the ABS Bill to parliament. - Support the drafting of ABS policy and regulations. Outputs 1.1.1, 1.1.2, 1.1.3 |  | - National Environment Policy and Biodiversity Bill updated to reflect the principles of Nagoya Protocol. - ABS policy and regulatory framework in place. - Regulation on conservation and sustainable use in place. | 1 | 2 years |  |
| Government Ministry |  | Ministry of Forestry, Range and Soil Conservation (MFRSC) is responsible for conservation and management of forested and range landscape, and biodiversity, in general. The Department of Forestry is currently piloting programmes for devolving the management of State Forest Reserves to the Local Government Community Councils under the Forest Policy and Programme. This process is accompanied by training of communities and their councils on various aspects of forest management, business opportunities and cottage industries |  | Will complement the ABS project on aspects on in-situ conservation and sustainable harvesting Will complement the initiatives for empowering community councils by supporting activities that promote conservation of the plant resources and deliver benefits to local communities in the project areas. |  | - Contribute to the updating of the Environmental Bill and drafting of the ABS policy and regulations. - Assist with stakeholder management and participation in the conservation, sustainable harvesting, value addition and benefit-sharing from genetic resources. - Assist in training of communities, including herders, through its field staff, including rangers about conservation and management of plant genetic resources. - Assist in consolidating the genetic resources bank. Outputs 1.1.1, 1.1.3, 1.3.2, 2.2.1, 2.3.4, 3.2.1 |  | - Guidance provided to the PMU on conservation management issues. - Stakeholder actively involved in the conservation and sustainable harvesting of plant genetic resources. - Community Councils empowered with skills to promote conservation of plant resources within communities. - In–situ conservation and sustainable harvesting selected plat species enhanced. - Genetic resources bank enhanced. | 1, 2, 3 | 5 years |  |
| Government Ministry |  | The Ministry of Agriculture and Food Security (MAFS) is responsible for the implementation of public agriculture policies, the promotion of agribusiness as well as regulation of services linked to the agricultural sector. |  | The MAFS will be responsible for providing information on methods of cultivation and on regulations regarding agro-ecological products and genetic resources. |  | - Contribute information and data to the information management database and monitoring system. - Share technical skills in conservation of plant resources - Sharing of successful agribusiness models. Outputs 2.1.1, 2.2.1, 3.2.2 |  | - Environmental conservation data and information incorporated into database monitoring system. - Project activities adhere to environmental laws and ABS regulations - Farmers’ technology uptake lessons and agribusiness models shared. | 2, 3 | 5years |  |
| Government Ministry |  | Ministry of Water (MoW) is responsible for regulating impacts on water resources and protect and guide the use of water resources such as wetlands, |  | Through the implementation of the Letseng-la- Letsie ICMP the MoW will support the implementation of objectives relating to managing ABS from hydrological and ecological resources (including medicinal plants) from the catchment |  | - Contribute to effective policy and legislative frameworks on benefit sharing for local communities; - Contribute to implementation of community-based natural resources management and natural resource-based enterprise development (CBNRM) principles Outputs 2.1.1, 2.2.1, 3.2.2 |  | - Optimal benefits from medicinal plants accruing to local communities | 1, 2, 3 | 5 years |  |
| Government Ministry |  | Ministry of Labour (MoL) is responsible for among other the protection of workers’ rights. It gives guidance to employers and labour federations on labour laws and provisions. |  | New enterprises that will be supported through this project will create jobs that will need to comply with the decent work agenda. The MoL will therefore assist in ensuring that there is compliance by especially the private sector in fair labour practices including eliminating child labour, which is rife in the rural agricultural sector. |  | - Share information and provide support on to establishing ABS deals with monetary and non-monetary benefits and ABS agreements with the pharmaceutical sector. Outputs 2.3.2, 2.3.3 |  | - Project activities informed by the Decent Work agenda. - Herders’ labour rights in particular protected, social security provided, and benefit-sharing ensured. | 1, 2 | 2 years |  |
| Ministry Department |  | Extension Division, Ministry of Agriculture and Lands. |  | This agency maintains direct relationships with farmers (crop and livestock) for the purpose of administering government support and for rendering technical advisory services with respect to sustainable agricultural technologies and practices. |  | - Provide inputs into training activities on conservation and harvesting practices. - Provide access to the stakeholders and knowledge of stakeholders. - Provide technical advisory services with respect to sustainable harvesting of plant selected plant species and related agricultural technologies and practices. - Provide local and TK for input into project activities. Outputs 2.2.1, 3.2.1, 3.2.2 |  | - Participatory training programmes and activities developed that reach all the relevant stakeholders including herders. - Sustainable harvesting selected plat species enhanced. | 2, 3 | 5 years |  |
| Government Ministry |  | Ministry of Science and Technology (MSTC) through the department of Science and Technology main mandate is to promote scientific and technological research in Lesotho. |  | Will provide information and support on R&D. Will strive to ensure R&D and related technology transfer from any innovation brought by this ABS project. |  | - Support the drafting of ABS policy and regulations. - Provide technical advisory services with respect to R&D. - Input into training programs and activities regarding R&D. Outputs 1.1.2, 1.1.4, 2.1.1, 2.1.2, 2.3.4, 3.2.1 |  | - R&D on plant products enhanced - Capacity developed in innovation and technology adaptation | 1, 2, 3 | 4 years |  |
| Government Ministry |  | Ministry of Police and Public Safety have the responsibility to enforce the law and protect property. They are stationed in different parts across the country. |  | The Police will address issues of biopiracy, especially to the Republic of South Africa and the illegal exploitation and trade of the medicinal plants in both local and international markets. |  | - Will ensure compliance to laws on bio-trading. - Enforcement of laws on biodiversity and ABS. Outputs 1.2.1, 2.2.1, 2.3.1, 2.3.3, 3.2.1 |  | - Cross border bio-trade laws and regulations adhered to. - Biodiversity and related laws adhered to by all, including communities and exporters. | 1, 3 | 5 years |  |
| Government Ministry |  | Lesotho Defense Force (LDF) is a government institution entrusted with law enforcement and security; |  | The LDF has field stations across the country including in next to all the four project sites. Among others the LDF is entrusted to curb illegal cross- border activities. It will ensure enforcement of protection of plant resources from bio-piracy. They can also participate in prorogation and conservation of the medicinal plants in their camps, in this way they will participate and also share in the benefits of conserving and using the biological resources while at the same time enforcing legal trade practices. |  | - Propagate, conserve and sustainably harvest selected medicinal plants - Prohibit cross-border bio-piracy of the plant species Outputs 1.2.1, 1.2.2, 1.3.2, 2.2.1, 2.3.2, 3.2.1 |  | - Biodiversity conservation through the sustainable utilization of selected commercially – important medicinal plants in four prioritised landscapes. - Compliance to laws governing bio-trading. | 1,2, 3 | 5 years |  |
| Government Ministry |  | The Ministry of Trade and Industry (MTI) is mandated to develop policies that promote entrepreneurial skills and transfer of appropriate technology, identify and assist local entrepreneurs and the farming community to utilize export opportunities, facilitate the creation of a conducive and appropriately regulated environment for commercial and marketing activities, and implement the Lesotho Industrial Policy |  | Will assist through the Lesotho National Development Cooperation (LNDC) in developing policies and programmes that will enable local communities to participate effectively in the development of the value chains that will accrue from the project. It will also assist in identifying potential international and local investors to partner in the implementation of the project. It will also assist with provision of necessary industrial infrastructure and access to capital for local investors. |  | - Promote value addition of genetic resources - Support local entrepreneurs and cooperatives, and exporters with skills and capital to effectively participate in natural product development - Ensure gender equality and youth and herders participation mainstreaming in natural product development. - Contribute input into project research and trading of plant genetic resources. Outputs 1.2.2, 2.2.1, 2.3.3 |  | - Enhanced value addition skills - Value chains created. - Increased international market opportunities for local exporters. - Gender mainstreaming strategy implemented to ensure equal sharing of benefits from the value chains accruing from the natural product development. | 1, 2 | 5 years |  |
| Government Ministry |  | Ministry of Local Government, Chieftainship, and Parliamentary Affairs (MLGCPA) is mandated to ensure the decentralization of public services and empowerment of local authorities including that of chiefs to play their administrative roles. Through the Decentralization Unit, District and Community Councils are mandated through the Local Government Act 1997 (amended) to have control over natural resources, environment protection and other communally owned property- chiefs role in addressing conflicts based on social differentiation for purposes of inclusiveness |  | The community councils will participate in this project as local leadership by giving consent for the implementation of the project in the project sites and assist in identifying the specific areas where the project will be implemented, while also participating in drawing the ABS Agreements and Prior Consent instruments that ensure that benefits from the project are equitably shared by the communities. Community Councils leaders will assist community members in ensuring their participation in the propagation, conservation and sustainable harvesting of the genetic resources. The councils will also be the buffer for grievances related to the project activities especially project impacts on herders and issues related to community tenure of the selected medicinal plants. |  | - Ensure that ABS agreements and PIC instruments are drawn with full participation of communities including herders. - Participate in the identification of areas that are active with harvesting of the three targeted plant species. - Allocate land for reintroduction, conservation and sustainable harvesting of genetic resources. - Ensure equal number of men and women, youth and herders are trained on sustainable utilization, conservation and access sharing. - Participate in the project technical advisory committee. - Provide entry point to local and TK for input into project activities. Outputs 2.2.1, 2.3.2, 2.3.3, 3.1.1, 3.2.1, 3.2.2 |  | - Guidelines, procedure and standards and codes of conduct developed for the implementation of the ABS laws and regulations; - Biodiversity conservation through the sustainable utilization of selected commercially – important medicinal plants in four prioritised landscapes. - Community protocols for governing access to and the distribution of benefits from the utilization of genetic resources. | 1, 2, 3, | 5 years |  |
| Government Ministry |  | The Ministry of Health (MoH) is primary mandate is to ensure an effective, efficient and affordable and sustainable delivery system for health services. It is the central authority that is charged with health provision, policy development and sectoral regulation. |  | Will contribute to the implementation of public-private partnerships in the areas of production and quality assurance and standards of the pharmacological products from the medicinal plants. |  | - Provide input in the establishment of quality and standards for natural products, as well as in research on medicinal and pharmaceuticals of the prioritized biological resources Output 2.1.2 |  | - Bio-prospecting undertaken - Pharmaceutical trials undertaken on medicinal plants - Quality assurance and standards developed | 2 | Years 1 to 3 |  |
| Government Ministry |  | Ministry of Small Business Development, Cooperatives and Marketing (MSBDCM), among other things, Is charged with fostering the development of cooperatives and sustainable enterprises through improving access to finance |  | Will assist small/medium-scale community-based enterprises to enhance their organizational skills. Will also assist plant resources entrepreneurs to access capital opportunities |  | - Provide business training for small to medium enterprises and cooperatives (including those owned by women and youth). - Enhance speedy registration and licensing of small-scale plant resources community-based enterprises and cooperatives. Outputs 2.2.1, 3.2.2 |  | - Community-based enterprises and cooperatives (including those owned by women and youth) strengthened and financially supported. - Business models developed. - Business best practice lessons shared. - Quality and standards on plant product development established. | 1, 2,3 | 4 years |  |
| Government Ministry |  | Ministry of Gender and Sports, Youth and Recreation (MGSYR)/Department of Gender (DoG) in is mandated to ensure equality of all opportunities between women, men, girls and boys, so that development efforts have an equal impact on all gender issues. The main goal of the DoG is to facilitate proper integration of gender issues in development to ensure full involvement, participation and partnership of women and men, girls and boys in both their reproductive and productive lives. |  | In collaboration with Gender Links and Women and Law in Southern Africa (WLSA) will support in the implementation of the Gender Action Plan, through capacity building and advocacy and knowledge management program to ensure that both men, women and youth are made aware of the issues pertaining to the conservation and sustainable use of plant genetic resources, and that they fairly and equitably benefit from their conservation and use. Will also promote the inclusion of gender aspects in all the project training and capacity building activities in the conservation and sustainable harvesting and management of medicinal plants. Women’s knowledge of medicinal plants will need to be harnessed to benefit the project while at the same time women benefit from the knowledge they possess; hence the DoG will coordinate advocacy activities around indigenous knowledge and management. |  | - The participation of DoG will ensure that ender is mainstreamed in all project activities as well as through participatory M&E while at the same time participating in gender capacity building, of key implementing agencies. - Will provide gender inputs into the design of environmental policy, biodiversity, ABS laws, regulations and project training materials. - Provide input into the implementation and update of the Gender Action Plan. - Ensure gender equity in the recipients of project benefits. - Provide support in the establishment of the gender focal point in the DoE. - Contribute in the implementation of knowledge management programmes. - Make input into advocacy and awareness programs on conservation, sustainable use and ABS aspects of the genetic resources. Outputs 1.1.1, 1.1.3, 1.3.2, 2.2.1, 3.1.1, 3.2.1, 3.2.2 |  | - Gender Action Plan updated and implemented. - Gender mainstreamed in all project activities including in governance issues. - Gender focal point created and the Gender expert engaged to coordinate and facilitate implementation of the project’s Gender Action Plan. | 1, 2, 3 | 5 years |  |
| Government Authority under the Ministry of Finance |  | The Lesotho Revenue Authority (LRA) is responsible for the assessment, collection, and receipt of specified revenue on behalf of the GoL, for the administration and enforcement of laws relating to such revenue and for related matters. The Customs and Excise Act of 1982 (Amended) is one of the laws enforced by the Authority. |  | Will assist in curbing bio-piracy especially of the three selected plants through the Anti-Smuggling Unit, Customs and Excise, Legal and Policy. Will also assist in enabling efficient and timely cross- border transactions in order to facilitate export and transport of the selected medicinal plants and products. |  | - Provide input in the development of bio-prospecting and TK regulations. - Make inputs in development of codes of conduct, best-practices and standards that ensure sustainable harvesting, fair and equitable benefit-sharing for industry and research sectors active in bio-prospecting; - Will ensure compliance to trade laws concerning protected or prohibited products. Outputs 1.2.1, 1.2.2, 2.1.3 |  | - Bio-prospecting and TK regulations developed - Codes of conduct, best practice, and standards that ensure sustainable harvesting, fair and equitable benefit sharing for industry and research sector active in bio-prospecting established. | 1, 2 | 4 years |  |
| Civil Society |  |  |  |  |  |  |  |  |  |  |  |
| Nongovernmental Organizations (NGOs) and Representative Institutes |  |  |  |  |  |  |  |  |  |  |  |
| NGOs’ main goal is empowering communities by acting as the voice of the voiceless against state oppression or discrimination. Some NGOs work directly on issues that are related to the environment. |  |  |  |  |  |  |  |  |  |  |  |
| NGOs | Transformation Resource Centre (TRC), a local NGO working on protection of human rights and democracy. TRC has collaborated with GEF on training of Mokhotlong communities who will be affected by the construction of the Polihali Dam; the training is intended to transfer skills to beneficiaries on range management and conservation, land reclamation and rehabilitation. |  | Will provide a platform for dialogue and strengthening the bargaining power of communities in the project areas, especially in the drawing of and negotiations on the ABS agreements. Will support local people to share information and knowledge about conservation and harvest of the plant resources and also benefits that accrue from the project, while at the same time managing conflicts that might emanate over communal natural resources. |  | - Carry out advocacy programmes on ABS. - Train local communities in negotiation skills and conflict management in natural resources. - Assist in the development of grievances mechanisms for communities. Outputs 1.3.2, 2.3.2, 2.3.3, 3.2.1 |  | - Communities empowered to participate in drawing of ABS agreements and PIC and MAT instruments. - Communities trained in conflict management skills. - Communities’ TK safeguarded. - Communities trained in negotiating fair deals with buyers of medicinal plants. - Project activities and governance is multi-stakeholder, participatory, and reflective of civil society perspectives. |  | 1,2,3 |  | 3 years |
|  | Lesotho Council of Non- Governmental Organizations (LCN) is a national, nonprofit umbrella organization representing the vast majority of community-based and national NGOs. Its main aim is to build the capacity of NGOs and CBOs and coordinate their work. |  | Will assist in providing information about its membership working in environmental protection. Will also assist in advocacy programmes on ABS regimes and will support the project through membership networks to promote community cooperatives |  | - Will lead advocacy and awareness programmes on land rights of marginalized groups in communities, including herders. - Provide entry point to stakeholders involved in environmental. Outputs 1.1.4, 1.2.2, 1.2.3, 1.3.1, 1.3.2, 1.3.3, 2.3.2, 2.3.3, 3.2.1 |  | - Mapping of stakeholders in environmental issues undertaken. - Local communities (including herders) lands rights protected. - Resources related conflict managed. - Active participation of locals in transparent processes on ABS agreements and PIC and MAT promoted. - Communities’ networks strengthened. - Project activities and governance is multi-stakeholder, participatory, and reflective of civil society perspectives. |  | 1,2, 3 |  | 2 years |
|  | Participatory Ecological Land Use Management (PELUM), a membership NGO whose programmes include capacity building aimed at the growth of smallholder farming, food security and sustainable use and marketing of agricultural produce, and improving sustainable livelihoods. PELUM also promotes the protection and support of local knowledge systems and innovations. |  | Will participate in the implementation of the project by sharing its experiences of working with local communities for improvement of livelihoods and food security. |  | - Share best practice in working with smallholder farmers. - Participate in capacity building programmes of communities, including women and youth as well as herders. - Will also contribute inputs into the documentation of TK. Outputs 1.1.4, 2.2.1, 3.2.1 |  | - Best practice’ lessons documented and shared. - Herders and out-of-school youth trained and effectively participating in conservation, propagation and sustainable utilization of medicinal plants. - Basic literacy, numeracy skills and psychosocial for herders programs rolled out to the four project sites. - Herders consulted and engaged in the drawing of the ABS Regime. - Herders’ TK on medicinal plants documented and protected. - Herders’ labour rights protected and social security promoted. |  | 1, 2, 3 |  | 2 years |
| Sentabale | This charity organization was founded to help the most vulnerable children in Lesotho. It works in the four districts of Lesotho including those that Ts’ehlanyane and Bokong national parks are located. Its primary target includes victims of extreme poverty and HIV& AIDS. One of their programmes focuses on the rights of herd boys who are a marginalized section of communities, especially in rural areas. Services provided include psychosocial support, and health outreach. |  | Will contribute to strengthening the capacity of herders in plant resources propagation, conservation and sustainable harvesting and to engage in formal trading of these plants. |  | - Share best practice in working with marginalized groups. - Participate in project training programmes - Provide access to local stakeholders, in particular herders and youth. - Contribute inputs into the development and implementation of the TK strategy. Outputs 1.1.4, 1.3.1, 1.3.2, 1.3.3, 2.2.1, 2.3.2, 3.1.1, 3.2.1 |  | - Best practice’ lessons documented and shared. - Herders and out-of-school youth trained and effectively participating in conservation, propagation and sustainable utilization of medicinal plants. - Basic literacy, numeracy skills and psychosocial for herders programs rolled out to the four project sites. - Herders consulted and engaged in the drawing of the ABS regime. - Herders’ TK on medicinal plants documented and protected. - Herders’ labour rights protected and social security promoted. |  | 1, 2,3 |  | 3 years |
| Help Lesotho | A charity organization’s work includes strengthening of household and community impact through capacity building of vulnerable groups such as herders, and out of school youth. The leadership development and psychosocial support programmes provide knowledge and promote positive attitude about gender equality and HIV/AIDS with the ultimate aim of building resilience and self-management among beneficiaries |  | Help Lesotho will assist through knowledge sharing of best practice, especially with the vulnerable group (herders), it also contribute capacity building of marginalized groups such as herders and youth, |  | - Share best practice in working with marginalized groups. - Participate in project training programmes. - Provide access to local stakeholders, in particular herders and youth. - Contribute inputs into the development and implementation of the TK strategy. Outputs 1.1.4, 1.3.1, 1.3.2, 1.3.3, 2.2.1, 2.3.2, 3.1.1, 3.2.1 |  | - Best practice’ lessons documented and shared. - Herders and out-of-school youth trained and effectively participating in conservation, propagation and sustainable utilization of medicinal plants. - Basic literacy, numeracy skills and psychosocial for herders programs rolled out to the four project sites. - Herders consulted and engaged in the drawing of the ABS regime. |  | 2, 3 |  | 3 years |
| Community-based Organizations |  |  |  |  |  |  |  |  |  |  |  |
| Community Conservation Forum (CCF) | CCFs are local entities legally registered with Law Office. CCF constitutions and by-laws function as policy guidelines that provide for conservation and harvesting of genetic resources as well as elements of benefit sharing from such resources hosted by the prioritized protected areas. All the four project areas for the ABS project have these agencies. CCFs are made of all community and social groupings from all the villages adjacent to the protected areas including traditional healers. The representatives collaborate with protected areas’ management in ensuring that community members do not over-harvest the resources. |  | They will participate in the project as part of the local technical advisory committee. They will be key actors in drawing of ABS agreements as well as in enforcing PIC obligations. They will be entry point to communities in the prioritized landscapes and protected areas and active participants in identifying value chain enterprises emanating from the project. Their involvement will cut across all the three components as they will be involved by contributing inputs to drafting of laws, policies, ABS agreements, PIC, MAT, while at the same time involved in participatory research that will map the location of the plant species as well as their use for effective, knowledge management and monitoring. |  | - Assist with inputs to the implementation of the project research activities. - Provide local and TK for input into project activities. - Provide direct access to stakeholders and beneficiaries. - Participate as members of the local project committees. -Participation in project planning, training, and community-level implementation. Outputs 1.1.2, 1.1.3, 1.1.4, 1.2.2, 1.3.1, 1.3.2,1.3.3, 2.2.1, 2.3.2, 3.2.1, 3.2.2 |  | - Project activities and governance is multi-stakeholder, participatory, and reflective of civil society perspectives. - Community-based and producer organizations have been consulted, informed, and trained, to facilitate the implementation of rangeland management systems, biodiversity conservation and sustainable harvesting. - TK is captured and protected |  | 1, 2, 3 |  | 5 years |
| Women’s Organizations |  |  |  |  |  |  |  |  |  |  |  |
| Gender Links (GL) | GL works with community councils to mainstream gender in their work; GL has established Centers of Excellence that promote gender equality at community council level |  | In partnership with DoG/ MGSYR, GL will be involved in mainstreaming gender in the main activities of the project, capacity building of gender units of the implementing institutions as well as in coordinating collection of sex disaggregated data from implementing communities. Gender Links in collaboration with community councils can assist in the inclusion of gender issues in general to the ABS project implementing communities. Under component 3 GL participation will assist in ensuring that the gender strategy developed is used to guide the project implementation and M&E as well as reporting. |  | - Participate in ensuring that women and youth are represented in project decision-making opportunities and activities. - Provide support in the participatory processes of the project to ensure women’s involvement. - Facilitate, jointly with the project and the departments of Gender and Youth the incorporation of gender focus and inclusion of marginalized groups into the project activities. - Contribute inputs into the empowerment processes for women and all marginalized groups. - Encourage gender equity and women’s participation in the project value chains. - Assist in capturing and sharing of women’s and herders’ TK - Participation in the implementation of the Project Gender Action Plan. Output 1.1.1, 1.1.3, 1.1.4, 1.2.3, 1.3.2,2.2.1, 2.3.2, 3.1.1, 3.2.1, 3.2.3 |  | - Gender mainstreamed in project governance, activities, and beneficiation. - Appropriate empowerment of women with respect to participation in leadership positions and opportunities for decision-making in project activities. - Active participation of women’s community groups and herders in the project product value addition activities. - Sex disaggregated data from implementing communities documented and shared. - Gender Action Plan implemented and regularly updated. - Women and herders’ TK captured and protected. |  | 1, 2, 3 |  | 5 years |
| Women and Law in Southern Africa – (WLSA) | WLSA is regional advocacy organization working on women and the law as well as human rights. It undertakes action research on issues that affect women; it has been instrumental in influencing the drafting of women specific laws and policies and works with the MGSYR in implementing some of the gender policy strategies. |  | WLSA will assist in mainstreaming gender in laws, procedures and strategies to be developed in the implementation of the project. It will assist with legal advice on the ABS Agreements from a gender perspective. Under Component 1 and Outcome1.1 WLSA will assist in ensuring that gender is mainstreamed in the national ABS policy and regulatory framework. Under Component 3 WLSA participation will also assist in achieving outcome 3.1 in ensuring that the gender strategy developed is used to guide the project implementation and M&E as well as reporting. |  | - Make inputs in the update of the Environmental Laws, Biodiversity Bill and all ABS regime. - Participate in ensuring that women and youth are represented in project decision-making opportunities and activities. - Provide support in the participatory processes of the project to ensure women’s involvement. - Facilitate, jointly with the project and the departments of Gender and Youth the incorporation of gender focus and inclusion of marginalized groups into the project activities. - Contribute inputs into the empowerment processes for women and all marginalized groups. - Encourage gender equity and women’s participation in the project value chains. - Assist in capturing and sharing of women’s and herders’ TK - Assist in the implementation of the Gender Action Plan. Output 1.1.1, 1.1.3, 1.1.4, 1.2.3, 1.3.2,2.2.1, 2.3.2, 3.1.1,3.2.1, 3.2.3 |  | - Gender mainstreamed in project governance, activities, and beneficiation. - Active participation of women’s community groups and herders in the project product value addition activities. - Appropriate empowerment of women with respect to participation in leadership positions and opportunities for decision-making in project activities. - Gender Action Plan implemented and regularly updated. - Sex disaggregated data from implementing communities documented and shared. - Gender mainstreaming strategy developed and full implemented. - Women and herders’ TK captured and protected. |  | 1, 2, 3 |  | 5years |
| Traditional Communities |  |  |  |  |  |  |  |  |  |  |  |
| Lesotho Traditional Healers Association (LTHA) | This is the platform for male and female healers and herbalists whose main purpose is to guard against misuse of traditional medicinal plants and knowledge. Among others, they strive to have strong functional collaboration with the MoH so as to enable ease of referral in cases where the traditional medicine lacks efficiency and vice versa. They are the main collectors and users of plants for medicinal and other purposes including spiritual. |  | As custodians of indigenous knowledge on medicinal plants, traditional healers and herbalists will participate in the project as implementing partners responsible for conservation of the medicinal plants as well as in the packaging and protection & dissemination of indigenous knowledge on the medicinal plants. Their knowledge will be used to inform R&D while at the same time benefiting from new innovations emanating from the project. Because of their knowledge on the medicinal plants the LTHA will also contribute to the project by participating in the identification and mapping of these plants as well as in their propagation. As main harvesters and traders of the medicinal plants they will contribute in the conservation and sustainable harvesting of the 3 species prioritized by the project. |  | - Active participants in the implementation of the project activities. - Contribute inputs in the development and implementation of the TK strategy. - Participate in the bio-prospecting and propagation and conservation of the prioritized medicinal plants. - Make inputs in the mapping and characterization of the medical plants targeted by the project. - Participate in the design and implementation of the ABS regime. - Participate in training activities of herders. - Participate in knowledge dissemination about ABS. Outputs 1.1.2, 1.1.4, 2.3.1, 2.3.3, 3.2.1 |  | - Traditional leaders and healers and medicinal plants harvesters consulted, informed, trained, and benefit from the implementation of the biodiversity conservation in line with the NP. - TK strategy developed and TK products patented. |  | 1, 2, 3 |  | 5 years |
| Special initiatives/ Private sector |  |  |  |  |  |  |  |  |  |  |  |
| Katse Botanical Garden | The garden was created as a result of plant rescue missions to mitigate the impact of the Katse Dam, particularly spiral aloes (A. polyphylla). The collection has a focus on traditional Sotho medicinal plants including the three-targeted species and has a large seed bank. |  | Will participate in the implementation of the project activities including sharing of lessons on community botanical gardens and other related knowledge products. Because of experience in seed preservation and propagation as well as wild collection, it will assist with technical advisory, research and provide input in best business models and upkeep of the botanical gardens. Will also be instrumental in providing support provided to genetic resources banking with respect to the prioritised species. |  | - Collaboration with research institutions in some project activities including biodiversity conservation, bio-prospecting and sharing of lessons learned and knowledge. - Co-financing of some project activities and making available its research and botanic garden facilities and infrastructure. - Assist in creating genetic resources community nurseries and household gardens. - Project partner supporting research and technological development associated with different varieties of plant species. - Contribute research co-financing and provide technical assistance and knowledge about genetic resources banking. Outputs 1.3.2, 1.3.3, 2.1.1, 2.2.1, 2.3.4 |  | - Biodiversity conservation through the sustainable utilization of selected commercially – important medicinal plants in four prioritised landscapes. - Community nurseries and botanical gardens established (with the participation of including herders and marginalized groups). - Synergies and cooperation established and strengthened between businesses involved in biological resources. |  | 1, 2 and 3 |  | 4 years |
| Rosa Canina Company | This company trades in genetic resources of rosehip and Khoara, these species are exported to Europe unprocessed as dried chips. |  | This private company will partner with DoE/MoTCE, MTI, research institutions, and communities through Community Councils for R&D, value addition, ABS agreements, PIC and MAT, while at the same time promoting propagation, sustainable harvesting and development of ABS products. |  | - Participate in natural product development such as tinctures for different ailments and essential oils. - R&D of the prioritized medicinal plants. - Collaborate with community councils on community trainings on sustainable harvesting - Creation of knowledge through bio-prospecting - Co-financing of project some activities. Output 2.1.3, 2.2.1, 2.3.2, 2.3.3 |  | - Biodiversity conservation through the sustainable utilization of selected commercially – important medicinal plants in four prioritised landscapes. - New business models developed. - New value chains created and community enterprises trained in small to medium scale processing, and packaging |  | 1, 2 |  | 5 years |
| Bophelo Natural Products, ROSA CANINA Pty Ltd (trading as The Rosehip Company) | Collects, process, and transport P. sidoides to an intermediary buyer in Germany, the dried material is routed to Parceval (Pty) Ltd in South Africa, a pharmaceutical manufacturer and former subsidiary of German-based Schwabe Pharmaceuticals; it supplies the South Africa market with P. sidoides raw materials and acts as exporter in the international P. sidoides value chain and shipped to Germany. |  | Will partner with DoE/MoTCE, MTI, research institutions, and communities through Community councils R&D, value addition, ABS agreements, PIC and MAT, while at the same time promoting propagation, sustainable harvesting and development of ABS products. |  | - Participate in training programs on promoting propagation and sustainable harvesting of the selected plant species. - Partner with research institutions on product development including establishment of value chains for community enterprises. - Co-financing of project activities through community engagement activities including in the creation of community nurseries and botanical gardens. Output 2.1.3, 2.2.1, 2.3.2, 2.3.3 |  | - Biodiversity conservation through the sustainable utilization of selected commercially – important medicinal plants in four prioritised landscapes. - New business models developed. - New value chains created and community enterprises trained in small to medium scale processing, and packaging. |  | 1, 2 |  | 5 years |
| Research Institutions |  |  |  |  |  |  |  |  |  |  |  |
| National University of Lesotho (NUL) (a public research and academic institution which has an autonomous status but gets subvention from state Ministry of Education) | NUL’s Faculty of Health Sciences- department of Pharmacy, and Department of Biology in the Faculty of Science as well as the newly created Innovation Hub are key partners in the implementation and support of the Project. The NUL’s Innovation Hub is already assisting some industry role players in the screening of active compounds for drug development. The GoL has established a partnership with the NUL and Nimura Genetic Solutions, a Japan-based company. The partnership is expected to facilitate natural product development from the country’s genetic resources as well as ABS implementation. Basotho Post-graduate students are already being trained and will form a human resource pool in the implementation of the project. |  | NUL will be engaged in project implementation by providing technical advisory and research for all components of the project and to ensure their contribution to the knowledge management as well as product development Will be a partner to carry out all R&D activities for medicinal plants and herbal medicinal products in consultation with different stakeholders including herders and traditional healers. Will also collaborate with other research institutions as well as the private sector. With its capacity as a research center the University already has basic research infrastructure that will be used as the springboard in the implementation of the project. |  | - Undertake educational and training activities that reach all levels of stakeholders including healers, herders, and women. - Participate in the bio-prospecting of the 3 plant genetic species of the project. - Conduct pharmaceutical research and product development on the selected genetic resources and develop patenting protocols. - Assist in the contractual agreements and non-disclosure with traditional healers and herbalists. - Leverage knowledge and mechanisms that can be expanded upon or incorporated into this project. Outputs 2.1.1, 2.1.2, 2.3.1, 2.3.3, 3.2.1, 3.2.2 |  | - Research training activities and product development conducted. - Research undertaken in collaboration with herders, women and other marginalized groups. - Bio-prospecting strategy developed. - Inventory surveys and suitability studies for the propagation of the genetic species undertaken. - Gender-disaggregated statistics database in genetic resource utilization developed. |  | 1, 2, 3 |  | 5 years |
| The Agriculture Research Department. | A research unit in the Ministry Agriculture and Food Security mandated to undertake agricultural related research to inform agricultural policies and programs to ensure productivity and food security. Through the Gene Bank is the research unit mandated to conserve and preserve indigenous plants seeds |  | The Gene Bank is already engaged in preservation of plant seeds found in the country, while its capacity needs to be strengthened, there are lessons that can be learned from its experience while at the same time contributing to, |  | - Participate in capacity building of communities on propagation of medicinal plants. - Participate in characterization and multiplication studies of prioritized plant species. - Collect and preserve seeds of the three prioritized plant species. Outputs 2.1.1, 2.3.4 |  | - Genetic banking of prioritized plant resources supported. - Genetic resources’ characterization and multiplication studies undertaken to inform re-introduction and propagation efforts of the three plant species. |  | 1, 2 |  | 3 years |

## Annex 9: Environmental Social Management Framework (ESMF) and other SES frameworks/plans, if required (Not applicable)

## Annex 10: Gender Analysis and Gender Action Plan

https://undpgefpims.org/attachments/5891/216247/1726178/1738833/5891%20Annex%20H_%20Gender%20Analysis%20and%20Gender%20Action%20Plan.docx

## Annex 11: Procurement Plan

## https://pims.undp.org/attachments/5891/216247/1773559/1837983/Procurement%20Plan%20Med%20Plants.xlsx

Annex 12: Additional agreements: such as cost sharing agreements, project cooperation agreements signed with NGOs (where the NGO is designated as the “executing entity”), letters of financial commitments etc.

Co-financing letters:

MDNSE:  https://pims.undp.org/attachments/5891/216247/1771940/1835108/Annex%20K%201%20MDNSE%20Co-Finance%20letter.pdf

National University of Lesotho: https://pims.undp.org/attachments/5891/216247/1771940/1835108/Annex%20K%202%20NUL%20Co-Financing%20Letter_Updated_230918.pdf

UNDP: https://pims.undp.org/attachments/5891/216247/1771940/1835108/Annex%20K%203%20Revised%20UNDP%20Co-Financing%20Letter%2027July2023.pdf

## Annex 13: Signed LOA between UNDP and IP requesting UNDP Support Services (if required on exceptional basis and authorized by the GEF)

https://pims.undp.org/attachments/5891/216247/1725110/1814050/Annex%20N%20%20LOA%20UNDP%E2%80%99s%20execution%20support.pdf

Annex 14: GEF CEO Endorsement/Approval

### Annex 15: On-Granting Provisions Applicable to the Implementing Partner: Not Applicable

On-granting clauses for non-UNDP Implementing Partners can be found here. This applies in cases where on-granting is built into the design and to the extent that it complies with the UNDP Policy on Low Value Grants (LVGs).

## Annex 16: Terms of Reference for Project Board and Project Team

The standard Project Board TOR can be found here.

https://undpgefpims.org/attachments/5891/216247/1726175/1745422/PIMS%205891%20-%20Annex%20D%20ToRs%20for%20Project%20Board%2C%20PMU%20and%20Key%20Consultants.docx

## Annex 17: GEF Core indicators

https://pims.undp.org/attachment-revision-file/index?attachmentRevisionId=1837950

## Annex 18: GEF Taxonomy

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | Type of Engagement |  |  |
|  |  | Information Dissemination |  |
|  |  | Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| Capacity, Knowledge and Research |  |  |  |
|  | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning |  |  |
|  |  | Knowledge Management |  |
|  |  | Innovation |  |
|  |  | Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality |  |  |  |
|  | Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | Gender-sensitive indicators |  |
|  | Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | Capacity development |  |
|  |  | Awareness raising |  |
|  |  | Knowledge generation |  |
| Focal Areas/Theme |  |  |  |
|  | Integrated Programs |  |  |
|  |  | Commodity Supply Chains (Good Growth Partnership) |  |
|  |  |  | Sustainable Commodities Production |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Financial Screening Tools |
|  |  |  | High Conservation Value Forests |
|  |  |  | High Carbon Stocks Forests |
|  |  |  | Soybean Supply Chain |
|  |  |  | Oil Palm Supply Chain |
|  |  |  | Beef Supply Chain |
|  |  |  | Smallholder Farmers |
|  |  |  | Adaptive Management |
|  |  | Food Security in Sub-Sahara Africa |  |
|  |  |  | Resilience (climate and shocks) |
|  |  |  | Sustainable Production Systems |
|  |  |  | Agroecosystems |
|  |  |  | Land and Soil Health |
|  |  |  | Diversified Farming |
|  |  |  | Integrated Land and Water Management |
|  |  |  | Smallholder Farming |
|  |  |  | Small and Medium Enterprises |
|  |  |  | Crop Genetic Diversity |
|  |  |  | Food Value Chains |
|  |  |  | Gender Dimensions |
|  |  |  | Multi-stakeholder Platforms |
|  |  | Food Systems, Land Use and Restoration |  |
|  |  |  | Sustainable Food Systems |
|  |  |  | Landscape Restoration |
|  |  |  | Sustainable Commodity Production |
|  |  |  | Comprehensive Land Use Planning |
|  |  |  | Integrated Landscapes |
|  |  |  | Food Value Chains |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Smallholder Farmers |
|  |  | Sustainable Cities |  |
|  |  |  | Integrated urban planning |
|  |  |  | Urban sustainability framework |
|  |  |  | Transport and Mobility |
|  |  |  | Buildings |
|  |  |  | Municipal waste management |
|  |  |  | Green space |
|  |  |  | Urban Biodiversity |
|  |  |  | Urban Food Systems |
|  |  |  | Energy efficiency |
|  |  |  | Municipal Financing |
|  |  |  | Global Platform for Sustainable Cities |
|  |  |  | Urban Resilience |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Forests |  |  |
|  |  | Forest and Landscape Restoration |  |
|  |  |  | REDD/REDD+ |
|  |  | Forest |  |
|  |  |  | Amazon |
|  |  |  | Congo |
|  |  |  | Drylands |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | International Waters |  |  |
|  |  | Ship |  |
|  |  | Coastal |  |
|  |  | Freshwater |  |
|  |  |  | Aquifer |
|  |  |  | River Basin |
|  |  |  | Lake Basin |
|  |  | Learning |  |
|  |  | Fisheries |  |
|  |  | Persistent toxic substances |  |
|  |  | SIDS : Small Island Dev States |  |
|  |  | Targeted Research |  |
|  |  | Pollution |  |
|  |  |  | Persistent toxic substances |
|  |  |  | Plastics |
|  |  |  | Nutrient pollution from all sectors except wastewater |
|  |  |  | Nutrient pollution from Wastewater |
|  |  | Transboundary Diagnostic Analysis and Strategic Action Plan preparation |  |
|  |  | Strategic Action Plan Implementation |  |
|  |  | Areas Beyond National Jurisdiction |  |
|  |  | Large Marine Ecosystems |  |
|  |  | Private Sector |  |
|  |  | Aquaculture |  |
|  |  | Marine Protected Area |  |
|  |  | Biomes |  |
|  |  |  | Mangrove |
|  |  |  | Coral Reefs |
|  |  |  | Seagrasses |
|  |  |  | Polar Ecosystems |
|  |  |  | Constructed Wetlands |
|  | Chemicals and Waste |  |  |
|  |  | Mercury |  |
|  |  | Artisanal and Scale Gold Mining |  |
|  |  | Coal Fired Power Plants |  |
|  |  | Coal Fired Industrial Boilers |  |
|  |  | Cement |  |
|  |  | Non-Ferrous Metals Production |  |
|  |  | Ozone |  |
|  |  | Persistent Organic Pollutants |  |
|  |  | Unintentional Persistent Organic Pollutants |  |
|  |  | Sound Management of chemicals and Waste |  |
|  |  | Waste Management |  |
|  |  |  | Hazardous Waste Management |
|  |  |  | Industrial Waste |
|  |  |  | e-Waste |
|  |  | Emissions |  |
|  |  | Disposal |  |
|  |  | New Persistent Organic Pollutants |  |
|  |  | Polychlorinated Biphenyls |  |
|  |  | Plastics |  |
|  |  | Eco-Efficiency |  |
|  |  | Pesticides |  |
|  |  | DDT - Vector Management |  |
|  |  | DDT - Other |  |
|  |  | Industrial Emissions |  |
|  |  | Open Burning |  |
|  |  | Best Available Technology / Best Environmental Practices |  |
|  |  | Green Chemistry |  |
|  | Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution |
|  |  |  | Paris Agreement |
|  |  |  | Sustainable Development Goals |
|  |  | Climate Finance (Rio Markers) | Climate Change Mitigation 0 |
|  |  |  | Climate Change Mitigation 1 |
|  |  |  | Climate Change Mitigation 2 |
|  |  |  | Climate Change Adaptation 0 Climate Change Adaptation 1 |
|  |  |  | Climate Change Adaptation 2 |

### Annex 19: Results of the Partners Capacity Assessment Tool (PACT) and HACT Micro Assessment

PCAT: https://pims.undp.org/attachments/5891/216247/1726400/1739201/PIMS%205891_PCAT%20Lesotho%20Consolidated%20Risk-Based%20Partner%20Capacity%20Assess%20Tool.xlsm

HACT: https://pims.undp.org/attachments/5891/216247/1726432/1746312/HACT%20Micro-assessment%20UNDP%20Lesotho%20Ministry%20of%20Tourism%2C%20Environment%20and%20Culture-%20%20Final.pdf

Annex 20: Programme Quality Assurance

Other Annexes

| Annexes | Links |
| --- | --- |
| Annex 21 – Herders Engagement Plan | https://pims.undp.org/attachments/5891/216247/1773554/1837978/Herders%20Engagement%20Plan_Rev%20February2023.docx |
| Annex 22 – Legal and Institutional Framework | https://pims.undp.org/attachments/5891/216247/1773556/1837980/Legal%20and%20Institutional%20Framework.docx |
| Annex 23 – List of People Consulted During Project Development | https://pims.undp.org/attachments/5891/216247/1773557/1837981/List%20of%20People%20Consulted.docx |

https://data.worldbank.org/country/lesotho.

National Environment Secretariat. 2000. National Strategy on Lesotho’s Biological Diversity: Conservation and Sustainable Use.

Moteetee, A., and Van Wyk, B-E. 2011. “The medical ethnobotany of Lesotho: a review.” In Bothalia – African Biodiversity and Conservation 41(1):209-228.

https://whc.unesco.org

I. V. Mashinini & G. Du T. De Villiers (2001). “Lesotho's Sustainable Development Challenges for the 21st Century: A Geo-Political Perspective.” In South African Geographical Journal, 83:1, 56-63, DOI: 10.1080/03736245.2001.9713719.

The Southern African Customs Union (SACU) is an African regional economic organization that includes Botswana, Lesotho, Namibia, South Africa, and Swaziland. The five member states maintain a common external tariff, share customs revenues, and coordinate policies and decision-making on a wide range of trade issues.

https://www.worldbank.org/en/country/lesotho/overview

http://hdr.undp.org/en/countries/profiles/LSO

www.tradingeconomics.com

Mugomeri et al., Afr. J. Tradit. Complement. Altern. Med. (2016) 13(1): 143-156. http://dx.doi.org/10.4314/ajtcam.v13i1.20

Marake et al. 1998.

Dejene, A. S. Midgley, M.V. Marake and S. Ramasamy.   2011. Strengthening Capacity for Climate Change Adaptation in Agriculture: Experience and Lessons from Lesotho. Food and Agriculture Organization of the United Nations.

https://adaptation-undp.org/explore/southern-africa/lesotho

https://www.sanbi.org

From securing raw material supplies by propagation, cultivation, and sustainable wild harvesting, bioprospecting and R&D, processing and packaging, to markets and marketing, and the development of local organizations and businesses.

Oldham, P; Rukundo, O; Meyer, H (2016) An Online Research Permit and Monitoring System to Support National Implementation of the Nagoya Protocol. Concept Paper. DOI:http://dx.doi.org/10.5281/zenodo.57420.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

Please see the Guideline “Embedding Digital in Project Design”.

See https://www.thegef.org/projects-operations/policies-guidelines

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

See https://popp.undp.org/ https://popp-prod.acquia.undp.org/policy-page/close-and-transition.

IFC, Stakeholder Engagement: A Good Practice Handbook for Companies Doing Business in Emerging Markets, (2007), pp. 5-7.