## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | January 1st 2021 - December 31st 2021
| Project Title: | Reducing climate vulnerability and flood risk in coastal urban and semi urban areas in cities in Latin America
| Project Summary: | Adaptation to climate change in coastal cities is a main challenge for both countries (Ecuador and Chile) as coastal areas are more exposed and vulnerable to the negative effects of climate change and the impacts of weather-related disasters. The project objective is to reduce vulnerability to climate-related floods, mud flows and landslides in the three coastal cities by mainstreaming a risk-based approach to adaptation, building collaboration and networking, and develop a culture of adaptation. To achieve this objective, the most prevalent risks were considered in each of the three cities. In the case of the Chilean populations, these are mudflows, while for Esmeraldas floods and landslides were considered. The lessons learned from this initiative are projected to be useful for the entire region of Latin America and the Caribbean. The project has three components: Component 1 focus on priority actions to increase resilience in the three cities. Four outcomes will be generated by mainstreaming DRR into local planning, building infrastructure which incorporate climate-related variables, improving climate monitoring, and strengthening the existing early warning and response systems. Component 2 focus on strengthening the capacities of local government officers and communities, as well as fortifying connections between communities and local and national government. Two outcomes will be generated by developing an online training course on risk-based adaptation for municipal and government officers and technical staff and implementing communication and education strategies to increase local awareness and contribute to build cultural memory. The online course will be open to professionals from other coastal cities of Latin America and the Caribbean. Component 3 focus on nurturing the project´s communities of practice and to document and disseminate the lessons. The backbone of the regional project are the communities of practice that allow the development of collective learning on specific topics. Five communities of practice will be developed.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Development Bank of Latin America (CAF) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity (RIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Chile and Ecuador | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Cities of Antofagasta and Taltal in Chile and Esmeraldas in Ecuador | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 16th 2018
IE-AFB Agreement Signature Date: |  | December 11th 2018 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | January 22nd 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | July 22nd 2022
January 22nd 2025
Original Completion Date:
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | N/A | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://static.adaptacioncc.com/documentos-pdf/proyecto-5.pdf | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Nury Bermudez | Dominican Republic
| Email: | nury.bermudez@undp.org | Ecuador
| Date: | 2019-07-04 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Karina Barrera | Equatoral Guinea
| Email: | karina.barrera@ambiente.gob.ec | Eritrea
| Date: | 2021-03-18 | Estonia
| Name: | Carolina Urmeneta
| Email: | curmeneta@mma.gob.cl
| Date: | 2020-01-22
| Implementing Entity |  | Ethiopia
| Name: | Carolina Cortes | Fiji
| Email: | acortes@caf.com | Finland
| Date: | 2018-12-11 | France
| Executing Agency |  | Gambia
| Name: | Mónica Andrade | Georgia
| Email: | monica.andrade@undp.org | Germany
| Date: | 2019-07-04 | Ghana
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to December, 31st 2020 |  |  |  | Financial information PPR 2. Period: January 2021 - June 2021 |  |  |  | Financial information PPR 2. Period: January 2021 - December 2021 |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [December, 31 2020] | 1181487 |  |  | Estimated cumulative total disbursement as of [June, 30 2021] | 2494307 |  |  | Estimated cumulative total disbursement as of [December, 31st 2021] | 3807128 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 4 years is USD 11,698,513. The second dibursment of $2'625.641 will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 3.5 years is USD 10,385,693. The fourth dibursment of $1'312.820 will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 3 years is USD 9,072,872. The fifth disbursement will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 7766.09 |  | CAF | INVESTMENT INCOME |  |  | Valor CAF | INVESTMENT INCOME | 7635.12 |  | CAF | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1. Stormwater management plan for Antofagasta | 27764.5134 |  |  | 1.1. Stormwater management plan for Antofagasta | 19287.2618 |  |  | 1.1. Stormwater management plan for Antofagasta | 99843.545
| 1.2. Green infrastructure plan for Esmeraldas | 67283.2494 |  |  | 1.2. Green infrastructure plan for Esmeraldas | 74286.8079 |  |  | 1.2. Green infrastructure plan for Esmeraldas | 113571.1473
| 2.1. Mudflow control infrastructure in Antofagasta | 16931.4621 |  |  | 2.1. Mudflow control infrastructure in Antofagasta | 19852.4943 |  |  | 2.1. Mudflow control infrastructure in Antofagasta | 84192.55
| 2.2. Landslide mitigation works in Esmeraldas | 23190.0409 |  |  | 2.2. Landslide mitigation works in Esmeraldas | 20600.5579 |  |  | 2.2. Landslide mitigation works in Esmeraldas | 32550.6673
| 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 48375.0876 |  |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 34368.1654 |  |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 98420.4123
| 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 5746.0339 |  |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 2696.1779 |  |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 28068.0473
| 4.1. Enhanced public warning system in Antofagasta and Taltal | 15980.1927 |  |  | 4.1. Enhanced public warning system in Antofagasta and Taltal | 10189.143 |  |  | 4.1. Enhanced public warning system in Antofagasta and Taltal | 36700.6725
| 4.2. Pilot flood warning system in Esmeraldas | 22019.8113 |  |  | 4.2. Pilot flood warning system in Esmeraldas | 31438.0836 |  |  | 4.2. Pilot flood warning system in Esmeraldas | 49896.7673
| 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 17530.3546 |  |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 12885.321 |  |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 36911.9598
| 5.1. Course on risk-based adaptation in coastal cities | 34755.6387 |  |  | 5.1. Course on risk-based adaptation in coastal cities | 31673.2154 |  |  | 5.1. Course on risk-based adaptation in coastal cities | 50253.9923
| 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 38255.6995 |  |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 22357.5529 |  |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 58003.4423
| 6.2. Narrators´ initiative initiated | 32053.1473 |  |  | 6.2. Narrators´ initiative initiated | 22017.1329 |  |  | 6.2. Narrators´ initiative initiated | 67379.8223
| 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 18792.1212 |  |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 9927.3379 |  |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 25450.8723
| 7.2. Lessons and best practice documented and disseminated | 50007.8224 |  |  | 7.2. Lessons and best practice documented and disseminated | 31565.4679 |  |  | 7.2. Lessons and best practice documented and disseminated | 70645.0823
| Project Execution cost | 33494.85 |  |  | Project Execution cost | 26165.99 |  |  | Project Execution cost | 79084.73
| Project/Programme Cycle Management Fee charged by the Implementing Entity |  |  |  | Project/Programme Cycle Management Fee charged by the Implementing Entity |  |  |  | Project/Programme Cycle Management Fee charged by the Implementing Entity | 42364.22
| TOTAL | 452180.025 |  |  | TOTAL | 369310.71 |  |  | TOTAL | 973337.93 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1. Stormwater management plan for Antofagasta | 377910.9457 | 2022-03-01 |  | 1.1. Stormwater management plan for Antofagasta | 361559.1339 | 2022-10-01 |  | 1.1. Stormwater management plan for Antofagasta | 254590.138 | 2022-10-01
| 1.2. Green infrastructure plan for Esmeraldas | 120548.0312 | 2021-10-01 |  | 1.2. Green infrastructure plan for Esmeraldas | 70305.5607 | 2021-09-01 |  | 1.2. Green infrastructure plan for Esmeraldas | 31027.1582 | 2022-12-01
| 2.1. Mudflow control infrastructure in Antofagasta | 267588.4157 |  |  | 2.1. Mudflow control infrastructure in Antofagasta | 239686.2714 | 2022-11-01 |  | 2.1. Mudflow control infrastructure in Antofagasta | 474209.9578 | 2022-11-01
| 2.2. Landslide mitigation works in Esmeraldas | 244000 | dec-21 |  | 2.2. Landslide mitigation works in Esmeraldas | 270043.6851 | 2022-09-01 |  | 2.2. Landslide mitigation works in Esmeraldas | 374017.1582 | 2023-03-01
| 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 455895.4612 | dec-21 |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 771832.6245 | 2022-02-01 |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 701491.7753 | 2024-12-01
| 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 161000 | dec-21 |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 130581.0351 | 2022-03-01 |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 112598.5673 | 2022-10-01
| 4.1. Enhanced public warning system in Antofagasta and Taltal | 30000 | 2022-03-01 |  | 4.1. Enhanced public warning system in Antofagasta and Taltal (1) | 234094.4027 | 2022-01-01 |  | 4.1. Enhanced public warning system in Antofagasta and Taltal (1) | 250090.9291 | 2022-12-01
| 4.2. Pilot flood warning system in Esmeraldas | 98000 | 2021-05-01 |  | 4.2. Pilot flood warning system in Esmeraldas | 77778.9094 | 2021-12-01 |  | 4.2. Pilot flood warning system in Esmeraldas | 224152.1582 | 2022-12-01
| 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 104506.1412 | 2022-03-01 |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 104821.032 | 2022-01-01 |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 62115.3673 | 2022-11-01
| 5.1. Course on risk-based adaptation in coastal cities | 192000 | aug-21 |  | 5.1. Course on risk-based adaptation in coastal cities | 127512.8076 | 2024-12-01 |  | 5.1. Course on risk-based adaptation in coastal cities | 80954.0673 | 2022-08-01
| 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 142017.7262 | 2021-09-01 |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 96810.1951 | 2024-12-01 |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 157689.0673 | 2022-12-01
| 6.2. Narrators´ initiative initiated | 64000 | 2021-11-01 |  | 6.2. Narrators´ initiative initiated | 65081.1551 | 2024-12-01 |  | 6.2. Narrators´ initiative initiated | 231764.0673 | 2022-12-01
| 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 77534.8812 | dec-21 |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 28128.5351 | 2022-01-01 |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 83632.0673 | 2022-12-01
| 7.2. Lessons and best practice documented and disseminated | 79039.1112 | dec-21 |  | 7.2. Lessons and best practice documented and disseminated | 38200.3451 | dec-21 |  | 7.2. Lessons and best practice documented and disseminated | 155068.7473 | 2022-12-01
| Project Execution cost | 193123.22 | dec-21 |  | Project Execution cost | 130000 | dec-21 |  | Project Execution cost | 233824.5757 | 2022-12-01
| Project/Programme Cycle Management Fee charged by the Implementing Entity |  | dec-21 |  | Project/Programme Cycle Management Fee charged by the Implementing Entity |  | dec-21 |  | Project/Programme Cycle Management Fee charged by the Implementing Entity
| TOTAL | 2607163.9334 |  |  | TOTAL | 2746435.6925 |  |  | TOTAL | 3427225.8014 |  |  | TOTAL | 0 |  |  | TOTAL | 0
(1) The value of the Antofagasta and Taltal EWS is included because the selection process begins this year; however, the contract will be signed at the beginning of 2022.
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Change of central government in Chile. New president and congress will take office in 2018 | N/A | The project was formally launched in January 2020 with a new central government. The project has been presented to the new authorities and is supported by them for its implementation
Change of municipal governments in Antofagasta and Taltal. The new authorities will take office in December 2020. | Moderate | Meetings were held with the newly elected authorities of Antofagasta and Taltal. Project activities and planning for the remainder of the project were presented. The project has the support of the new authorities.
Change of municipal and provincial governments in Esmeraldas. The new authorities will take office in 2019 | N/A | The project was formally launched in January 2020 with a new local government. The project has been presented to the new authorities and is supported by them for its implementation
Support withdrawal from local counterparts, taking into account the change of Governments. | Low | Meetings with key local government authorities to ensure support during implementation. Commitment of institutions to designate technical focal points to ensure project continuity.
The change of Governments could eventually lead to staff re-structuration, meaning that there could possibly be a knowledge gap between the newcomers. | Low | Commitment of institutions to designate technical focal points to ensure project continuity In case there is new staff, meetings will be held to share the progress of the project Periodic activity progress and budgetary implementation reports will be carried out by the project
Lower economic activity in both countries and impact of April´s earthquake in Ecuador | Low | The impact of the April 2016 earthquake in Ecuador has been overcome; however, a significant reduction in economic activity in both countries resulting from COVID-19 has been shown. Within the framework of the project implementation, partner institutions have been supported for the implementation of activities to reduce the risk in case of climate disasters within project intervention areas
Grant not being delivered and/or not being delivered on time. | High | UNDP's cash flow allows it to assume certain commitments through project overdrafts in case of delays.
Increase in budget due to costs miscalculations, and/or due to overprices during project implementation. | Medium | The project was developed 5 years ago, budget changes are needed. The budget changes were first presented to the Project Steering Committee. Once the Steering Committee's approval was obtained, CAF sent it to the Adaptation Fund for review and approval.
GADPE has no experience with meteorological monitoring | High | GADPE is provided with limited technical staff, who do not have a specialization in hydro-meteorological monitoring. A consultancy was hired to improve climate monitoring in Esmeraldas, which incorporates a management model including training the provincial government staff
Baseline studies are not up to date | Low | Changes were made to the baselines of the population composition in project intervention zones in Antofagasta (migration). The baseline is being updated by the project staff as part of the "Estrategia de Relacionamiento Comunitario" In the case of Ecuador, as part of the updating of the baseline studies, the Cerro Gatazo Partial Plan was prepared. In addition, a legal study will be carried out to clarify land tenure in the "20 de noviembre" neighborhood.
Inaccuracy in radar and storm detection system implementation | Low | In Chile, technical advice and support are available by the competent national body DMC. Regular advisory meetings are held to evaluate the progress of the contracted storm detection system. In Ecuador, as approved by the Steering Committee in an extraordinary session held on April 28th, 2021, the acquisition of a radar will not be carried out, both for technical and economic reasons. The hydro-meteorological network of the middle and lower Esmeraldas river basin will be implemented in its place.
Misuse of the online platform created to share best practices between coastal cities. | Low | The Project Communication Strategy developed contains the guidelines for the correct use of the web platform. The platform is currently under development
Lack of understanding of the project, and hence opposition from the local inhabitants. | Moderate | The only activity under this risk is the Cerro Gatazo landslide mitigation works in Esmeraldas. Cerro Gatazo is an informal settlements. Discussions have been taken place with local government and neighborhood leaders. An intense socialization campaign will be carried out with the support of the Municipality to inform about the benefits and co-benefits of the Cerro Gatazo intervention. Informative workshops have been held for local beneficiaries on the activities that the project will develop
Effect of El Niño / La Niña in precipitation and local weather conditions. | Low | Monitoring current collected weather information from the project intervention area
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Authorities and technical staff of government institutions prioritize health emergency activities by COVID-19 | Moderate | Two strategic partners in Ecuador (Municipal GAD in Esmeraldas and SNGRE) in compliance with their competences are directly addressing the health emergency, which has made it difficult to coordinate project actions. Coordination with central and local government institutions, scheduling meetings that enable the fulfillment of project activities
It has been difficult to make an approach with project beneficiaries due to COVID restrictions | High | Performing virtual events (workshops, webinars) when is possible Execution of face-to-face workshops following guidelines established by government. Protection kits have been provided to attendees of face-to-face meetings.
Governments return to strict isolation measures | High | Activities planned in 2022 will be done using virtual modality, as it is possible.
Frequent changes of authorities in project member government institutions. | High | In 2021 there were changes in central government authorities in Ecuador and local government in Chile. Commitment of institutions to designate technical focal points to ensure project continuity. In case there is new staff, meetings will be held to share the progress of the project Periodic activity progress and budgetary implementation reports will be carried out by the project.
Project Unit professionals and/or focal points have the possibility of getting sick by COVID | Moderate | Focal point support technicians must be established so they can be replaced in case of sick leave Provide facilities for the project's technical staff to be vaccinated against COVID 19 Project personnel carry out their activities in virtual mode to avoid contagion.
Change of Central Government Authorities in Chile in March 2022 | Moderate | Once the central government authorities have been positioned, the project will be presented to be provided with their support
Difficulty in implementing activities in the "20 de Noviembre" neighborhood in Cerro Gatazo, due to the alarming increase of violent acts in the area. | High | Coordination with relevant entities to assess the current situation and determine the feasibility of implementing the activities planned for 2022
The need to relocate families located in the intervention area could hinder the infrastructure works. | High | Meetings with the Local Government of Esmeraldas to analyze the different possibilities for the dwelling relocation in the area of intervention.
Local governments do not count with up-to-date cadastral information of the project intervention areas | High | The project team should ask the local government the actualization of cadastral information and land tenure of the project intervention areas.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During 2021, some risk situations identified in the Project Document have been presented related to the change of authorities within the partner institutions, the delay in the receipt of the disbursement for 2021, and the increase of violencia and crime in Cerro Gatazo. In addition, due to the COVID-19 pandemic, mitigation measures were implemented that were not contemplated in the Project Document, such as: difficulty to approach project beneficiaries due to COVID-19. Concerning the change in rotation of authorities, the measures implemented to overcome this situation have focused on requesting the designation of main and alternate focal points in the institutions, which allow continuing with the implementation of the project despite the absence of any of these. In addition, periodic project progress reports are sent to partner institutions so that there is a written record of the activities that are implemented within the project. In the case of the appointment of new authorities, project presentations, objectives, and progress status have been made. All these measures have made it possible to move forward with activities without further delays. On the other hand, according to the results obtained from the Partial Plan for the 20 de Noviembre neighborhood in Cerro Gatazo, the existing cadastral information is deficient, which could hinder the planned infrastructure works. In addition, it is highly probable that there will be a need to relocate families whose homes are in high-risk areas. In view of this situation, discussions are being held with the municipality of Esmeraldas to define the best solution. One risk that is of great concern to the project is the increase in violence and crime in the Cerro Gatazo area. This year, acts of violence have increased exponentially. In light of this situation, none of the project's partner institutions in the territory want to work in the area, including the National Police. There is a high security risk for project team, which has made it difficult to carry out activities in Cerro Gatazo. For security reasons, among the measures taken, it has been decided that the technical team will not enter the area until security conditions are guaranteed. In addition, an evaluation of the situation will be carried out with the other partner institutions regarding the safety of the area. Regarding the difficulty of approaching beneficiaries in the territory, the project has carried out the planned activities virtually as far as possible. A virtual course on Green Infrastructure for public officials in Ecuador is currently underway. In those cases where it has been possible to hold face-to-face workshops, all safety protocols have been followed to minimize the risk of contagion, looking for places with good ventilation and maintaining social distancing. In addition, safety kits have been provided to workshop participants. Similarly, due to the emergency caused by COVID-19, the governments of Ecuador and Chile implemented strong isolation measures for several weeks. As a mitigation measure, project activities have been carried out in virtual mode, progressing as planned. One of the important mitigation activities carried out in the second half of the year was a substantial change in the project, updating activities and budgets. This substantial change was presented to the Steering Committee at an extraordinary meeting. Once the Steering Committee's approval was obtained, CAF sent the documentation to the Adaptation Fund for review and approval. The project is currently awaiting approval of this amendment. The measures implemented have successfully allowed to overcome the risks that have come about and thus continue with the implementation of the project.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Risk: Insufficient alignment with laws and technical standards, especially related to implementation of concrete infrastructure works and climate monitoring under Component 1, Outcome 2 and Outcome 3. Impact: Grey and green infrastructure implementation could not get the Environmental Registry - Ecuador or the Environmental Impact Declaration – DIA for Chile | Grey and green infrastructure works not yet in place Safeguard measures identified in the Project Document: Activity 5. Interventions in Chile have to comply with technical standards, environmental permits and construction code regulations. Activity 6. Interventions in Ecuador have to comply with technical standards, environmental permits and construction code regulations. | Updated studies for implementation of grey and green infrastructure Environmental permit application submitted | 0 updated studies 0 environmental permit application processed | In Ecuador, infrastructure update studies was launched in 2021, unfortunately the proposal received did not meet the required quality ToR was adjusted and a new process will be launched in January 2022. In Chile, the update infraestructure studies has been contracted. Once the studies are updated, all the necessary documentation will be present to obtain the environmental permits in accordance with the regulations in both countries. | The analyses carried out in Cerro Gatazo did not allow to identify land tenure, especially in the area where the infrastructure work are located. (Ecuador) Chile (N/A) | In addition,in order to solve the existing problems in Cerro Gatazo regarding land tenure, the project will carry out a legal analysis in the area.
2 - Access and equity |  |  | Risk: Possible interruption of water supply, energy services or roads / streets accessibility. The beneficiary might have no access to project benefits because of inexistent mechanism to ensure participation of communities, marginalized, vulnerable groups, and stakeholder and local authorities. Impact 1: If the community is not properly communicated and involved in the process of updating the plan, their local knowledge in their surrounding area such as “Campamentos” or in the ravine routes will not be taken into account. Impact 2: If the community does not participate in the process of preparing the green-infrastructure plan for Esmeraldas, the community will not be informed of risks of residing on hill and will repeat and conceive it as a possible settlement place. Impact 3: If the community is not properly communicated and involved in the process of updating the designs of the infrastructure, their local knowledge in their surrounding area such as “Campamentos” or in the ravine routes will not be taken into account. Impact 4: Do not exist conditions to approve the declaration and preserve the protected forest Impact 5: Impossibility to install the radar and meteorological stations in the best location reached. Radar and meteorological stations without maintenance could not operate properly or not lasting the expected lifetime. Community members could harm or steal the monitoring instruments. Impact 6: If the community does not participate or comment the evacuation maps and procedures for Antofagasta and Taltal, they will not help with their local knowledge and own situation. Also, it is important that they are aware of all the ideas and must agree with the plan. If not, human lives could be in danger. Impact 7: Unable to help their community in an emergency situation. Impact 8: Insufficient information available to update the evacuation maps. Human lives could be in danger. Impact 9: Lack of sustainability of the action and population still in danger. Impact 10: If the community is not able to participate in localization of the banners they may be unused increasing the possibility of accidentally Impact 11: The use of the electronic platform may be limited if the community or community - social leaders does not empower themselves to use it. Impact 12: Technical Staff with lack of knowledge would cause misunderstanding of the disaster risk reduction and adaptation subject and create some difficulties on the implementation phase. Impact 13: Trainers without real capacities to manage disaster risk reduction and adaptation issues in their daily working. Impact 14: Technical staff from the local government without real capacities to manage disaster risk reduction and adaptation issues in their daily working. Impact 15: Technical staff of Esmeraldas local government without proper knowledge about green infrastructure or eco-engineering measures to cope with adaptation measures in the future. Impact 16: Local stakeholders no deeply into green infrastructure or eco engineering would cause lack of sustainability of the actions. Impact 17: Not participation of the social community in the communities of practice. The heterogeneity could be lost. Impact 18: The use of the electronic platform may be limited if the community or community - social leaders does not empower themselves to use it. Impact 19: Not awareness of the community in general of the lessons and best practices of the project. | Safeguard measures identified in the Project Document: Activity 1 - 2 - 3 - 4 - 8: The Local Social Specialist for Chile and Ecuador respectively will prepare a “Communication and Participatory Strategy” that will contain all the activities and how the local community should be involved . Activity 4: The process of including climate change considerations will used comprehensive methodology to fulfill the main objective, of mitigate the population living at risk. Activity 6: The Local Social Specialist for Ecuador will communicate about the Grievance mechanism available. The procedure and forms will be accessible to all actors directly involved in the actions. Also the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • If there is any possibility of interruption of the basic services caused such as water shortage or energy disruptions, the operational contractor team shall make communication to the community affected. • The operational contractor team shall be responsible for the coordination action related with traffic and temporary closure of traffic. In accordance with communities, routes and schedules of access to the Gatazo operational area can be planned. • Fences or barriers and pedestrian pathways are required to be installed. • Receive inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed the proceed with the grievance mechanism. Activity 8: Trainings and participatory strategy put in place by the local specialist for social issues during the whole implementation. Media Specialist works in behavioral insights messages to explain the importance of this action for the population own safety. Activity 9 - 10 - 11- 12 - 13 - 14 - 15 - 19: The study to identify the location must analyze different places based on a criteria matrix, such as: accessibility, security, no disturb landscape or other telecom instruments among others. The project will ensure that the government has technician in the area and train them to used and maintain the radar. The community need to be informed clearly, a campaign would be implemented by the Media Specialist to reach different target of population. Activity 16 - 18 - 21: A comprehensive information strategy in place to involve the whole community in the evacuation maps. The process will be conducted by the Local Social Specialist based on the “Communication and Participatory Strategy” Activity 17 - 20 - 22 - 23 - 25: Real involvement of the community in the different phases of the process, based on the Communication and Participatory Strategy. Activity 24: The Local Social Specialists shall be aware that the socialization and presentation of the maps is relevant for their use. The “Communication and Participatory Strategy” shall include workshop to define the localization of the maps. Activity 26 - 35 - 36 - 37: The Regional Media Specialist in the “Communication and Participatory Strategy” shall include the development of the regional electronic platform. Activity 27: The Project Board and the Project Manager of the project will require them to participate in the Courses. The courses will be mandatory for all technical staff in both countries. Activity 28: Motivate the trainers to actively participate in the training prepared for them about green infrastructure and disaster risk reduction strategies. Activity 29: Understand the final beneficiaries of this courses, this one means the personnel from the local governments. Before implementing the courses, a survey will be conducted to understand their knowledge, expertise and behaves. The courses will be prepared based on a comprehensive analysis of this database. Also, the timetable of the classes will be analysis thoroughly to fine the best and productive usage time. Activity 31:Motivate the technical staff to actively participate in the training prepared for them about green infrastructure and eco-engineering. Prepare a comprehensive Course Plan with the best technician on eco-engineering, with experience in tropical areas and with native vegetable species. Activity 32: The whole process about the green infrastructure plan need the involvement of key local stakeholders during the implementation. The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans and be part of the “Communication and Participatory Strategy”. | Number of Communication and Participatory Strategies Number of Technical report of location for equipment installation Number of training workshops for the technical staff of the institutions in charge of the stations Percentage of project technical staff who have taken the regional risk-based adaptation course Number of grievances received related to access to basic services | 0 Communication and Participatory Strategy 0 Technical report of location for equipment installation 0 training workshops for the technical staff of the institutions in charge of the stations 0% project technical staff who have taken the regional risk-based adaptation course 0 grievances received related to access to basic services | Communication and educational strategies were developed for Esmeraldas, Antofagasta and Taltal. A regional communication strategy was also developed. These documents promote the integration of beneficiaries and key stakeholders in the activities carried out by the project. Online and face-to-face workshops have been held with the beneficiaries and stakeholders to gather their contributions and involvement. Twenty workshops and events were held with key actors and project beneficiaries: Ten trainings for the risk and emergency management brigades of LUVATO Island; One to perform a flood simulation; One to socialize the route of narrators in Esmeraldas; Four virtual chats (commemoration of water day, talk on urban resilience, commemoration of the flood in Antofagasta, Climate Change - Esmeraldas) in which the project activities planned to reduce the risk of climate disasters were presented; Two territorial round tables in Antofagasta and Taltal - Two women's roundtables in Antofagasta and Taltal; Socialization of project activities on local radio in Taltal. The Grievance mechanism has been socialized in different workshops and trainings. | Not identified | Not identified
3 – Marginalized and vulnerable Groups |  |  | Risk: The project might impede an access to basic services such as clean air, energy and housing, safe may be affected. This referred to Component 1. Impact: Claims, non-conformity and possible interruption of works may occur. | This risk is activated once the grey and green infrastructure works are carried out in Esmeraldas. In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 6: The Local Social Specialist for Ecuador will communicate about the Grievance mechanism available. The procedure and forms will be accessible to all actors directly involved in the actions. Also the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • The operational contractor team shall be responsible for the coordination action related with traffic and temporary closure of traffic. In accordance with communities, routes and schedules of access to the Gatazo operational area can be planned. • Fences or barriers and pedestrian pathways are required to be installed. • Receive inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed by the grievance mechanism. | Number of grievances received related to problems of access to basic services | 0 grievances received related to problems of access to basic services | In this reporting period, no safeguard measures have been required | Not identified | Not identified
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Risk: Either women or men has unequal opportunities to participate taking into account their working schedules or lifestyles, this referred to in Component 1, Component 2 and Component 3. Impact 1: Only one gender could assist to the course. The gender perspective could be lost, is women cannot assist, children assistance also could be put in risk. Impact 2: Only one gender could assist to the communities of practice. The gender perspective could be lost, if women cannot participate. | The project has promoted equal opportunities for both women and men by taking into account schedules, lifestyle and responsibilities. Safeguard measures identified in the PRODOC: Activity 33: The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. Activity 34: The Local Social Specialist for Chile shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. Activity 35: The Local Social Specialist for Chile and Ecuador shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. | Percentage of women's participation in events held by the project | 0% of event attendees have been women | The participation of men and women is equal. Schedules, lifestyles and responsibilities that may affect the participation of men and women have been considered | Not identified | Not identified
6 – Core labour rights |  |  | Risk: Insufficient alignment with core labour rights, especially related to implementation of concrete infrastructure works and climate monitoring under Component 1, Outcome 2 and Outcome 3 Impact: Persons and workers in the surroundings areas could be injured or affected. | In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 5 - 6: The operational contractor team in Chile and Ecuador shall be responsible for the control of the entire works and implement specific mitigation measures to cope with casualties during construction. • Consider the identified hazards including those that may originate from outside the workplace that are capable of adversely affecting the health and safety of persons under the control of the organization within the workplace. • Applied control related to risk assessment • Follow an accident investigation form. • Recognize extra hours of work, in compliance with the labour regulation of each country. • Be aware of the equipment that the workers use during the infrastructure works. • Take into consideration the medical care emergency kit at the infrastructure works. • Keep in mind the medical check provided at the beginning of the works. • Construction workers must also be provided with identification tags. • Comply with the national legislation – Labour Codes of Ecuador and Chile • Ensure that employment procedures/ policy of the operational contractor is communicated to local stakeholders. • The intention of giving preferential employment to locals is clearly communicated, to discourage an influx of job-seekers from other areas. | Number of grievances received related to problems of violation of labour rights | 0 grievances received | All the procurement process have followed the UNDP Financial Regulations and Rules (2012) as well as a sustainable procurement process including core labour rights. The winning consultants in the different processes must comply with the labor law of each country. | Not identified | Not identified
7 – Indigenous people |  |  | Risk: Indigenous beneficiary families not being adequately informed and engaged to access the range of project benefits. Impact 1: Not use of the information developed. Impact 2: Not participation of the indigenous community in the Narrator’s initiative. The heterogeneity perspective could be lost, is the indigenous community cannot assist. Impact 3: Not participation of the indigenous community in the communities of practice. The heterogeneity could be lost perspective could be lost, is the indigenous community cannot assist. | The project has promoted equal opportunities, incluiding indigenous people and afro-ecuadorina by taking into account working schedules, lifestyle, or languages. This referred to in Component 2. Safeguard measures identified in the PRODOC: Activity 30: The Regional Media Specialist in the “Communication and Participatory Strategy” shall include the development of the regional electronic platform. Activity 33 - 35 - 37: The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans should the in schedules that Chachis can attend and be part of the “Communication and Participatory Strategy”. | Communication and participation strategy guarantees participation of indigenous groups | 0 Communication and participation strategies developed | The project developed communication and education strategy for Esmeraldas which promote the integration of beneficiaries and key stakeholders in the activities carried out by the project. In all the events carried out by the project in the reporting period, all the conditions have been taken to ensure that the participation of indigenous people and afro ecuadorians. Schedules, lifestyles and responsibilities that may affect their participation have been considered | Not identified | Not identified
8 – Involuntary resettlement |  |  | Risk: Temporary physical relocation for the nearest families leaving informal settlements in the proximity of the intervention in Cerro El Gatazo – Esmeraldas, basically related with the removal of mud and soil to stabilize the hill. Impact: Claims, nonconformity and possible interruption of the works could occur. | This risk is activated once the grey and green infrastructure works are carried out in Esmeraldas. In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 6: The Local Social Specialist for Ecuador will prepare a “Communication and Participatory Strategy” that will contain all the Activities and how the local community should participate during their development. Implementation of the activities related with the Landslide mitigation infrastructure in Cerro Gatazo - Ecuador, the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • If there is any possibility of the need of possible temporary resettlements this shall be presented as a Plan to the Project Board. • Receive complaints, inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed by the grievance mechanism. • The GADE team shall be responsible for the coordination action related to the temporary resettlements. • The GADE team shall be responsible for the temporary localization during the project | Number of grievances received related to problems of access to basic services | 0 grievances received | In this reporting period, no safeguard measures have been required | Not identified | Not identified
9 – Protection of natural habitats
10 – Conservation of biological diversity |  |  | Risk: The introduction of non-endemic species for the stabilization of Cerro Gatazo in Esmeraldas may pose a risk for the project. (such decision will come when USP intervention are completely developed) Impact: Introducing non-endemic species could damage the natural biodiversity, even though it is an area already intervened. | In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 2: A study will be undertaken prior to the selection of which species will be used on the implications of introducing different species. Activity 7: The operational contractor has to develop the revegetation in accordance with the Green Infrastructure Plan approved by the Project Board previously. The species that are going to be used should be in the Green Infrastructure Plan. Based on the findings of study, the choice of native species will be appealed. | Technical report on the selection of species to be used for reforestation | 0 Technical reports | In this reporting period, no safeguard measures have been required. However, at the moment the Green Infraestructure Plan has been developed and as part of the plan there is a preliminary analysis of the species to be used in the revegetation process. | Not identified | Not identified
11 – Climate change |  |  | Risk: There is no a risk of significant or unjustified increase in greenhouse gas emissions, considering that the project preliminary will not produce more than 1 MM ton /CO2eq during its lifespan. However, for the sake of the project and the compliance of the E&SP this will be attended with a Carbon Footprint recognized tool. This will be classified as risk. Impact 1: The contribution of GHG emissions directly affects the adaptation of Antofagasta, Taltal and Chile. Impact 2: The contribution of GHG emissions directly affects the adaptation of Esmeraldas and Ecuador. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5 - 6: Carbon Footprint shall be presented Monitoring system of the GHG emissions shall be presented Approval of Carbon Footprint and the Monitoring system of the GHG | Monitoring system of the GHG emissions developed | 0 Monitoring system of the GHG emissions | In this reporting period, no safeguard measures have been required. | Not identified | Not identified
12 – Pollution prevention and resource efficiency |  |  | Risk: The project may be implemented in a way that does not meet applicable standards for minimizing material resource use, the production of wastes, and the release of pollutants. Impact 1: The generation of wastes and pollutants during the construction works will pollute the surrounding area of Antofagasta. Impact 2: Health diseases affecting the population of the surroundings and workers. The generation of wastes and pollutants during the construction works will pollute the urban area of Esmeraldas. As environmental impact of gabion retaining walls is basically the slight increment the of greenhouse emissions taking into account the transport of materials. Impact 3: Impossibility to install the radar and meteorological stations in the best location reached. Impact 4: Radar and meteorological stations without maintenance could not operate properly or not lasting the expected lifetime. Impact 5: Community members could harm or steal the monitoring instruments. Impact 6: Impossibility to install the meteorological stations and the storm detection system in the best location reached. Impact 7: Meteorological stations and the storm detection system without maintenance could not operate properly or not lasting the expected lifetime. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta as well as the installation of meteorological instruments and early warning systems. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5: A construction plan shall be presented to the Project Board. A specific monitoring procedure for the construction works shall be presented to the Project Board. The operational contractor shall implement a monitoring plan to control: • Water consumption. • Fuel consumption. • Type of fuel consumption • Raw material consumption. • Energy consumption. • Solid waste generation. • Wastewater / generation (quality of wastewater). • Construction waste / debris generation. Approve the Construction Plan Activity 6: The mitigation measures are part of the Health Impact Assessment (HIA) A specific monitoring procedure for the construction works shall be presented to the Project Board. Activity 11 - 12 - 13 - 14 - 15 - 19: The study to identify the location must analyze different places based on a criteria matrix, such as: accessibility, security, no disturb landscape or other telecom instruments among others. The project coordinator will ensure that the government has technician in the area and train them to used and maintain the radar. This condition is mandatory to guarantee the sustainability of the action. | Monitoring plan for pollution prevention and resource efficiency developed | 0 Monitoring plan for pollution prevention and resource efficiency | In this reporting period, no safeguard measures have been required. In the next year, studies to update the infrastructure works will begin, and meteorological equipment and early warning systems will be installed | Not identified | Not identified
13 – Public health |  |  | Risk: The project designed and implemented in a way that produces potentially significant negative impacts on public health. Like any common infrastructure work, there is a low probability risk of collapse, especially during the period of construction and if a hazard materialized during this period, hazards such as: heavy rains, earthquake. Impact: Community – public health affected in noise or air pollutants. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5 - 6: A Health Impact Assessment shall be presented to the Project Board. Approval of the HIA. The operational contractor team in Chile and Ecuador shall be formed responsible for the control of all project related to Public Health and will: • Develop an Occupational Health and Safety Management Protocol. • Consider the routine and non-routine activities of the organization to be sure all of them are coordinated. • Beware how all persons accessing the work place including contractors and visitors (clothing, signals, helmets, etc.). • Bear in mind the human behavior, capabilities and other human factors that could increment the potential failure of structural elements of the Project. • Take into consideration how the operational contractor control threats created near the workplace during work -related activities. • Keep in mind how the infrastructure, equipment and materials at the workplace affects construction works. • Consider how the organization identifies changes or proposed changes to its activities or materials it uses. • Consider how modifications to the OH&S protocol / system, whether they be temporary or not, impact on the operations, processes and activities of the organization. • Consider how the project identified legal requirements for health and safety of persons beyond the immediate workplace, including those who are exposed to the workplace activities. • Consider the effects of the design of work areas, processes, installations, machinery/equipment, operating procedures and work project, including their adaptation to human capabilities. | Occupational Health and Safety Management Protocol developed | 0 Occupational Health and Safety Management Protocol developed | In this reporting period, no safeguard measures have been required. | Not identified | Not identified
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | CAF has formally informed all Responsible Parties about the ESMP and potential risks to Environmental and Social Safeguards.
Have the implementation arrangements been effective during the reporting period? |  | Yes, CAF has ensured that the Responsible Parties are aware of the identified safeguards and mitigation measures, as well as targeted assessments identified in the ESMF.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | UNDP has regularly monitored the risks identified and the safeguard measures in the reporting period. UNDP has promoted events to socialize with the beneficiaries the developed activities. In addition, it has ensured the equitable participation of men and women in all events.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. All of this year's safeguard measures were successfully implemented. The events carried out by the project considered a gender approach
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | After a technical-financial analysis carried out by the project, with support from the General Directorate of Water in Chile and INAMHI in Ecuador, the project has identified the location of the meteorological stations to be installed. This activities were analyzed under the 15 environmental and social principles of the Adaptation Fund. The other USP implementation agreements will be made in the following year once the documents updates for the gray infrastructure works are in place.
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | All positions required for the fulfillment of the ESMP are clearly identified and responsibilities are assigned.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | The ESMP has been updated considering the activities related to defining the location of the radars, both in Ecuador and Chile
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Installation of automatic meteorological stations in the watersheds of Antofagasta and Taltal | Yes | There is a risk that project beneficiaries will not be aware of the benefits of installing the weather stations Men or women do not have the same opportunities to participate in events and activities planned because their work schedules or lifestyles are not considered | Yes | Appropriate consultations have been carried out during the identification of risks and impacts for this activity with the respective technical institutions in Chile. The grievance mechanism has been socialized | Yes | Socialization to communities about the location, use and benefits of the meteorological stations for Antofagasta and Taltal, in territorial and women's roundtables. (Community Relations and Education Strategy). | Communication and Participatory Strategies developed Percentage of women's participation in events held by the project
USP 2: Installation of automatic meteorological stations in the watersheds of Esmeraldas | Yes | Project beneficiaries are not aware of the benefits of installing and upgrading hydro-meteorological stations. Men and women do not have the same opportunities to participate in the socialization of the hydrometeorological network and the location of the stations to be installed or upgraded, because their work schedules or lifestyles are not taken into account. Indigenous peoples have unequal opportunities to participate in socialization events of the hydrometeorological network and the stations to be installed and upgraded, because their work schedules, lifestyles, or languages are not taken into account. | Yes | Appropriate consultations have been carried out during the identification of risks and impacts for this activity with the respective technical institutions in Chile. The grievance mechanism has been socialized | Yes | Dissemination of the proposed hydro-meteorological monitoring network for Esmeraldas, in a participatory workshop with key stakeholders, including a proposal for a network management model. Socialization with communities about the location, use and benefits of the hydro meteorological stations to be installed. Dissemination of the proposed hydro-meteorological monitoring network for Esmeraldas, in a participatory workshop with key stakeholders, including an equal number of men and women, considering work schedules and lifestyles. The Esmeraldas Communication and Public Education Strategy considers the participation of vulnerable groups with a gender focus. Socialization with communities, including representatives of indigenous peoples, about the location, use and benefits of the hydro meteorological stations to be installed, considering their work schedules, lifestyles and languages. | Communication and Participatory Strategies developed Percentage of women's participation in events held by the project
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances were filed during the reporting period. |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Men and women protected by improved risk-reduction measures | Objective | Number of men and women protected by improved risk-reduction measures in Antofagasta, Taltal and Esmeraldas. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | End of project Antofagasta = 380,000 (ca., 50% women) Taltal = 10,000 (ca., 50% women) Esmeraldas = 161,000 (ca., 50% women) | Satisfactory. A Storm Detection System is already in operation in Chile, protecting the population of Antofagasta and Taltal as an enhanced risk reduction measure. A Green Infrastructure Plan for Esmeraldas was developed. Five hydrometeorological stations have been upgraded to improve climate monitoring in the low and middle in the Esmeraldas river basin in Ecuador.
Plans that incorporate provisions for adaptation to climate change with gender perspective. | Outcome | Number of plans that incorporate provisions for adaptation to climate change with gender perspective. | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 0 | Mid-term: 1 End of project: 2 | Satisfactory In Chile, the Stormwater Management Plan for Antofagasta is currently being developed. The plan will be finalized in July 2022. In Ecuador, the Green Infrastructure Plan has already been developed. Both plans incorporate a gender approach
Men and women protected by improved infrastructure | Outcome | Number of men and women protected by improved infrastructure | Antofagasta = 0 Esmeraldas = 0 | End of project: 12,840 Antofagasta = (ca., 50% women) Esmeraldas = 500 (ca., 50% women) | Non applicable for the reporting period
Men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), landslides (Esmeraldas) and mudflows (Antofagasta and Taltal) | Outcome | Number of men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), landslides (Esmeraldas) and mudflows (Antofagasta and Taltal) | Antofagasta = 0 Taltal = 0 Esmeraldas (floods) = 0 Esmeraldas (landslides) = 0 | Antofagasta = 380,000 people (ca., 50% women) Taltal = 10,000 people (ca., 50% women) Esmeraldas (floods) = 161,000 people (ca., 50% women) Esmeraldas (landslides) = 161,000 people (ca., 50% women) | Satisfactory. In Ecuador, signage was designed, developed and installed for evacuation routes in the event of flooding on Luis Vargas Torres Island. In Chile, evacuation maps have been designed. The development and installation of the signage will be completed by 2022.
The early warning systems in Antofagasta, Taltal, Cerro Gatazo and Isla Luis Vargas Torres are gender and culturally sensitive and consider the special needs of persons with disabilities. | Outcome | Number of early warning systems | Number of early warning systems Antofagasta = 0 Taltal = 0 Cerro Gatazo = 0 Isla Luis Vargas Torres = 0 | Four early warning systems are gender and culturally sensitive and consider the special needs of persons with disabilities. | Good In Ecuador, the Early Warning System against floods has already been developed. Approval from the Adaptation Fund is currently required for the purchase of equipment for the Early Warning System. In Chile, the Early Warning System is ready. The equipment will be contracted in 2022.
Staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Outcome | Number of staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 Other coastal cities Chile = 0 Other coastal cities Ecuador = 0 | Antofagasta = >50 Taltal = >10 Esmeraldas = >20 Other coastal cities Chile = >10 Other coastal cities Ecuador = >10 About 40% will be women | Good The project conducted a Diagnosis of capacities and competencies on risk-based adaptation in coastal cities. In the second half of the year, a competitive bidding process will be carried out to contract the design and implementation of the course.
Men and women who have participated in awareness activities and events. | Outcome | Number of men and women who have participated in awareness activities and events. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = >30,000 (ca., 50% women) Taltal = >1,000 (ca., 50% women) Esmeraldas = >16,000 (ca., 50% women) | Satisfactory In Chile, territorial roundtables (2) and women's roundtables (2) were held in the cities of Antofagasta and Taltal as part of the project's education and communication strategy. In Ecuador, workshops have been held with beneficiaries about the Early Warning System against floods to be installed on Luis Vargas Torres Island. Also, two videos were made, the first one to present the context and objectives of the project, and the second one to present the incorporation of the climate variable in the design of infrastructure to generate more resilient cities to climate change.
Narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Outcome | Number of narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 10 (ca., 50% women) Taltal = 5 (ca., 50% women) Esmeraldas = 10 (ca., 50% women) | Good Both countries have a communication and education strategy that includes a storytelling component. Due to COVID-19 restrictions, it has been difficult to carry out face-to-face activities. Virtual activities are planned for the 2022 that will be allocated in a virtual platform for the narrator's' initiative. In addition, and as part of the narrators' initiative, a public contest of lullabies, songs and tenths that raise awareness about climate risks in the city of Esmeraldas has been launched.
Men and women who have participated in events for dissemination of lessons and best practice (e.g., workshops, exchange visits, seminars) | Outcome | Number of men and women who have participated in events for dissemination of lessons and best practice | 0 | Mid-term >100 people > 50% women End of project: >200 people > 40% women | Satisfactory In Chile, three virtual events were held (World Water Day commemoration talk, Urban Resilience Talk, commemoration of the 30th anniversary of the flood in Antofagasta) to raise awareness regarding climate change and disaster risk reduction. In Ecuador, two events were held (launching of the Green Infrastructure Plan and Webinar on Climate Change) in which the activities developed by the project were presented as part of the lessons learned and good practices.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | During the reporting period, CAF ensured socialice the importance of compliance the gender policy.
Have the implementation arrangements at the IE been effective during the reporting period? |  | All activities implemented by the project have a strong gender approach.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | UNDP has ensured the equitable participation of men and women in all events carried out. Training to the project team on its policy of Prevention of Sexual Exploitation and Abuse. In addition, as part of the communication and education strategy, territorial women's groups were created to strengthen the management and participation of women as key actors in climate risk management.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. All the events carried out by the project considered a gender approach. In addition, there is an important participation of women in the different workshops and events carried out by the project.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints related to gender equity and women's empowerment have been received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1. Enhanced plans and green infrastructure reduces vulnerability to floods, landslides and mudflows in three coastal cities |  | Outcome 4 | - Update Stormwater Management Plans to cope with climate-related mudflows in Antofagasta - Implementation of the Green Infraestructure course - Prepare green infrastructure plan for the city, with emphasis on protection from flooding and landslides. |  | The activities planned for the second year have been 90% completed. The Green Infrastructure Plan for Esmeraldas has been developed and finalized. The green infrastructure course was successfully completed, with 32 public officials passing the course. The project supported the Municipality of Esmeraldas in the construction of the PUGS. It is important to articulate the Green Infrastructure Plan with the other instruments being developed by the municipality. In Chile, a company was hired to update the Antofagasta Stormwater Management Plan. | HS
| Outcome 2. Reduced vulnerability to floods, landslides and mudflows in two coastal cities |  | Outcome 4 | - Update of the designs of mudflow control infrastructure in Quebrada Bonilla. -Partial Plan of land use and management for the "20 de Noviembre" neighborhood. - Intervention plan in the area selected for the design and construction of the works. |  | Regarding the Outcome 2. The project progressed with the contracting for the update of the designs of mudflow control infrastructure in Quebrada Bonilla (Chile) The Land Use and Management Plan for the "20 de Noviembre" neighborhood has been successfully completed. There is a pre-feasibility project for the implementation of green infrastructure in Cerro Gatazo | MS
| Outcome 3. Improved climate monitoring and means to alert the local population |  | Outcome 1 | - Storm detection system contract for Antofagasta and Taltal - Climate monitoring diagnosis and improvement proposal - Meteorological stations in Antaofagasta and Taltal - Strengthening of the hydro-meteorological network in Esmeraldas |  | Regarding the Outcome 3. The Storm Detection System was contracted in March and is now operational. Ecuador completed the Climate Monitoring Design for Esmeraldas, which was validated by INAMHI and other institutions related to the scope of the study and approved by the Steering Committee . The project will strengthen the hydrometeorological network in Esmeraldas by upgrading existing INAMHI's stations and purchasing new ones. The study also concluded that for technical and financial reasons, it is not advisable to purchase the radar. To date, INAMHI's stations have been upgraded and the selection process for the acquisition of 8 new hydrometeorological stations has been completed. | HS
| Outcome 4. Improved means to respond to floods, landslides and mudflows |  | Outcome 1 | - Early Warning System Design in Antofagasta - Early Warning System Design in Esmeraldas - Implementation of the Early Warning System in Esmeraldas. TOR preparation - Evacuation route maps and signs in Antofagasta, Taltal and Esmeraldas - Printing and placement of flood evacuation maps and signage. |  | Regarding the Outcome 4. In Chile, the design of the evacuation maps was developed with the support of ONEMI. The early warning system will be installed in 2022 once the agreement with ONEMI has been signed. Ecuador, with the support of the Risk Management Service and the Escuela Politécnica del Litoral - ESPOL, designed the Early Warning System (EWS). The project helped the community to form risk and emergency management brigades and has conducted training sessions with the help of the Fire Department, ECU911, and SNGRE; and the evacuation route signage has already been installed. The EWS equipment will be purchased in 2022 once the material change request submitted to the Adaptation Fund is approved. | S
| Outcome 5. Local governments with improved capacity to design and implement adaptation measures |  | Outcome 2 | - Situational diagnosis of existing capacities on risk-based adaptation in coastal cities - Prepare course on risk-based adaptation in coastal cities |  | Regarding the Outcome 5. A capacity / knowledge situational diagnosis was carried out at the regional level with local officials of Antofagasta, Taltal, Esmeraldas for the initial preparation of the course on risk-based adaptation in coastal cities. With the information from the diagnosis, the development of the risk-based adaptation course is under way and is going to be implemented in the following years. | S
| Outcome 6. Local population and government personnel with increased awareness of climate-related risks (floods, landslides, mudflows) |  | Outcome 3 | - Implementation of public education and communication strategy for Antofagasta, Taltal and Esmeraldas - Implementación de la iniciativa de narradores en Antofagasta - Taltal and Esmeraldas |  | Regarding the Outcome 6. In Chile, the project developed communication material to raise community awareness on climate change adaptation and risk management. A platform was also developed to complement the storytelling initiative. Community workshops have also been held in Antofagasta and Taltal as part of the education and communication strategy. In Ecuador, a contest of traditional songs from Esmeraldas is being developed as part of the narrators' initiative. | HS
| Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region. |  | Outcome 8 | - Production videos, images and other communication media for the project´s web platform and news. |  | Regarding the Outcome 7. In Chile, two communication videos have been successfully launched in the first half of the year. The first to socialize the objective of the project and the activities to be carried out, and the second, to publicize the incorporation of the climate variable in infrastructure designs. The project is currently hiring a company to develop the website and will be available in the first quarter of 2022. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Carolina Cortes
| Email: | acortes@caf.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
As the implementing agency, the actions of the project have been followed up through periodic meetings with the ministerial teams of Ecuador and Chile as well as with UNDP Ecuador and Chile and the respective project teams. Likewise, and according to the implementation mechanisms, four meetings were held with the National Technical Committees (one in Ecuador and one in Chile), where the programming for each semester and the Procurement Plan and the progress to date were shared. The meetings in Ecuador were virtually on January 13th, 2021 and on July 8th, 2021. The meetings in Chile were virtually on January 12th, 2020 and July 7th, 2021 . After the National Committees, the third and fourth Steering Committees were held on January 14th, 2021 and July 15th, 2021 respectively. In addition, an extraordinary Steering Committee was held in April, where the project presented the environmental and social risk analysis and the respective mitigation measures for the USPs of the meteorological stations en Ecuador y Chile. Furthermore, the results of the diagnostic study of climate monitoring in Esmeraldas were presented, which concluded that the acquisition of a radar is not recommended. A second extraordinary Steering Committee was held in September 2021, which approved the substantial changes made to the project, prior to submission to the Adaptation Fund. In this period, and despite the presence of the pandemic, the implementation of the project has been satisfactory. The objectives established in the proyect have been successfully met, obtaining the expected results for this year despite de different problems. The presence of the global pandemic due to COVID-19 changed the mechanisms under which a project is implemented, making many activities virtual throughout the semester. However, certain meetings, when necessary, have been held in person, taking care to comply with security protocols.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1. Enhanced plans and green infrastructure reduces vulnerability to floods, landslides and mudflows in three coastal cities |  | Outcome 4 | - Update Stormwater Management Plans to cope with climate-related mudflows in Antofagasta - Implementation of the Green Infraestructure course - Prepare green infrastructure plan for the city, with emphasis on protection from flooding and landslides. |  | The Stormwater Management Plan is under development. To date, the first stage has been developed, which includes the compilation and critical analysis of technical background (2004 Master Plan, population exposed to the threat, zoning of streams), identification of the hydrographic basins and the topographic and aerial survey of the area.. According to plan, will be completed in July 2022. The personnel from the different partner institutions of the project took the Green Infrastructure course, which ended in July 2021. Thirty-two people passed the course and received a certificate of completion. The Green Infrastructure Plan for the city of Esmeraldas has been developed. In addition, technical support has been provided to the Municipality of Esmeraldas for the preparation of the Land Use and Management Plan. | HS
| Outcome 2. Reduced vulnerability to floods, landslides and mudflows in two coastal cities |  | Outcome 4 | - Update of the designs of mudflow control infrastructure in Quebrada Bonilla. -Partial Plan of land use and management for the "20 de Noviembre" neighborhood. - Intervention plan in the area selected for the design and construction of the works. |  | The update of the designs of mudflow control infraestructure in Quebrada Bonilla is under development. At the moment, the first two stages have been developed. The first stage included the compilation and critical analysis of the background of the project design developed in 2000 and the development of the soil mechanics. The second stage included the development of field campaigns by specialist engineers, which included the topographic works and geotechnical surveys required for the development of the project. The Land Use and Management Plan for the "20 de Noviembre" neighborhood has been successfully completed. As part of the Green Infrastructure Plan, a pre-feasibility project for mitigation works at Cerro Gatazo was carried out. | MS
| Outcome 3. Improved climate monitoring and means to alert the local population |  | Outcome 1 | - Storm detection system contract for Antofagasta and Taltal - Climate monitoring diagnosis and improvement proposal - Meteorological stations in Antaofagasta and Taltal - Strengthening of the hydro-meteorological network in Esmeraldas |  | The Storm Detection System for Antofagasta and Taltal was contracted in this year and is in operation. In Ecuador, the "Diagnosis and proposal for climate improvement in Esmeraldas" was completed. The consultancy concluded that to improve climate monitoring in Esmeraldas, it is necessary to strengthen the existing network of hydrometeorological stations and acquire new stations. In addition, for both technical and budgetary reasons, radar acquisition is no recommended. Those results were reported to the Steering Committee in April 2021 and approved by the same committee. In Ecuador, as part of the strengthening of the hydrometeorological network, five INAMHI hydrometeorological stations were upgraded and a contract was awarded for the acquisition of eight new hydrometeorological stations. | MS
| Outcome 4. Improved means to respond to floods, landslides and mudflows |  | Outcome 1 | - Early Warning System Design in Antofagasta - Early Warning System Design in Esmeraldas - Implementation of the Early Warning System in Esmeraldas. TOR preparation - Evacuation route maps and signs in Antofagasta, Taltal and Esmeraldas - Printing and placement of flood evacuation maps and signage. |  | The development of the Early Warning System (EWS) in Antofagasta was carried out with the support of ONEMI. However, in order to move forward with the implementation of the EWS, an agreement with ONEMI is required. The agreement is currently being reviewed by ONEMI's legal department prior to signing. Once the agreement is signed, the equipment will be purchased. The design of the evacuation maps was developed with the support of ONEMI. The design of the Early Warning System for Luis Vargas Torres Island was completed. As part of the process, community risk management committees and emergency brigades were formed and trained. For the acquisition of the Early Warning System equipment, the project requires the approval of the Substantive Change by the Adaptation Fund sent it in November 2021. This change was presented to the Steering Committee at an extraordinary meeting in September 2021 and subsequently approved. This modification is required due to the fact that the budget allocated to this output has been exceeded by more than 10%. In addition, signage was designed, developed and installed for the evacuation of the population of Luis Vargas Torres Island in the event of flooding. | S
| Outcome 5. Local governments with improved capacity to design and implement adaptation measures |  | Outcome 2 | - Situational diagnosis of existing capacities on risk-based adaptation in coastal cities - Prepare course on risk-based adaptation in coastal cities |  | The diagnostic study of risk-based adaptation capacities in coastal cities was completed. The information obtained by the consultant was validated by officials of the project's partner institutions in Antofagasta, Taltal and Esmeraldas through a virtual workshop. This information will be used in the design of the Risk-Based Adaptation course. A university has been selected to develop the contents of the Risk Based Adaptation course and its subsequent implementation. | S
| Outcome 6. Local population and government personnel with increased awareness of climate-related risks (floods, landslides, mudflows) |  | Outcome 3 | - Implementation of public education and communication strategy for Antofagasta, Taltal and Esmeraldas - Implementación de la iniciativa de narradores en Antofagasta - Taltal and Esmeraldas |  | Production of communication materials and events to implement the communication and public education strategy in Antofagasta and Taltal. In addition, territorial roundtables and women's roundtables have been established in the cities of Antofagasta and Taltal as part of the education and communication strategy. Four roundtables were held during the year. In Ecuador, the communication and education strategy for Esmeraldas is in place. As part of the narrators'' initiative, a contest of "arrullos y décimas" is being held with the local population. The results of the contest will be known in the first quarter of 2022. | HS
| Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region. |  | Outcome 8 | - Production videos, images and other communication media for the project´s web platform and news. |  | In Chile, Two videos were made, the first one to present the context and objectives of the project, and the second one to present the incorporation of the climate variable in the design of infrastructure to generate more resilient cities to climate change. The company in charge of the development of the website has been hired. Finally, the project organized an event to launch the Green Infrastructure Plan for Esmeraldas, in which the lessons learned and best practices of this process were shared. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Nury Bermudez
| Email: | nury.bermudez@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has been successfully implemented in the second year, according to the planned activities. This has been possible, thanks to the sustained work of the entire project team, both in Chile and Ecuador, the ongoing supervision of CAF and UNDP offices in the respective countries and, of course, the accompaniment of the Ministries of Environment. Other key players in achieving the results are, at the national level, the SNGRE and INAMHI in Ecuador. In Chile, ONEMI, MOP and the DMC. At the local level, the commitment of the technicians of the municipalities of Esmeraldas, Antofagasta and Taltal, help the intervention to move forward as planned despite the difficulties caused by the health pandemic of the Covid-19. One of the aspects that have required greater focus has been the work with communities, due to the difficulties of mobilization by COVID-19. Despite this, the project in Chile and Ecuador has held face-to-face and virtual workshops with the direct beneficiaries. In Ecuador, flood risk management brigades have been formed on Luis Vargas Torres Island and evacuation signs have been installed. In Chile, territorial and women's committees have been set up to strengthen community participation in risk management issues. Among the most relevant milestones in the reporting period are: In Esmeraldas, the proposal for strengthening climate monitoring defined and agreed upon, the process of upgrading hydrometeorological stations, the Green Infrastructure Plan and the training course on Green Infrastructure for public officials of partner institutions. In Chile: contracting of the Storm Detection System service for Antofagasta and Taltal, the contracting of the consulting services for the Rainwater Master Plan and the updating of the designs for the infrastructure work in Quebrada Bonilla, preparation of communication videos on the project, and the incorporation of the climate variable in the stormwater control infrastructure works. On the other hand, the review and approval process of the enabling documents for the third disbursement by CAF was significantly delayed, which in turn delayed the receipt of the third disbursement of the project by five months. This delay hindered the implementation of activities in the first half of the year. To address this problem, UNDP has had to meet urgent project expenditures through override. In addition, activities were identified that required a higher amount than the one initially planned in the project budget, exceeding it by more than 10%, for this reason the project document was updated. This substantial change has been present to the Steering Committee before the submission to the implementing agency. UNDP as executive entity is waiting approval of this material change to move forward with the acquisition of equipment for the Luis Vargas Torres Early Warning System. Finally, it is important to report that this year there has been an alarming increase in security and crime in the Cerro Gatazo sector. Several acts of extreme violence have been reported in the area, making it difficult for the National Police to enter the area. This situation makes it very difficult to implement project activities in the area.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Juan Monteros, Monitoring and evaluation project techinician
| Email: | juan.monteros@undp.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of men and women protected by improved risk-reduction measures in Antofagasta, Taltal and Esmeraldas. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 361.873 (ca., 50% women) Taltal = 13.317 (ca., 50% women) Esmeraldas = 161,000 (ca., 50% women) | End of project Antofagasta = 380,000 (ca., 50% women) Taltal = 10,000 (ca., 50% women) Esmeraldas = 161,000 (ca., 50% women)
Outcome 1 | Number of plans that incorporate provisions for adaptation to climate change with gender perspective. | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 0 | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 1 | 2
Outcome 2 | Number of physical assets constructed to withstand conditions resulting from climate variability and change. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 0 Esmeraldas = 0 | 2
Outcome 2 | Number of men and women protected by improved infrastructure to withstand climate change and variability-induced stress. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 0 Esmeraldas = 0 | 12,840 Antofagasta = (ca., 50% women) Esmeraldas = 500 (ca., 50% women)
Outcome 3 | Number of weather radar in Esmeraldas and Storm detection system in Antofagasta to monitor precipitation, linked to gender-sensitive early warning systems. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 1 Esmeraldas = 0 | Antofagasta = 1 Esmeraldas = 1
Outcome 3 | Number of meteorological stations to monitor precipitation which affect the cities, linked to gender-sensitive early warning systems. | Antofagasta = 4 Taltal = 1 Esmeraldas = 5 | Antofagasta = 4 Taltal = 1 Esmeraldas = 10 | Antofagasta = 6 Taltal = 2 Esmeraldas = 7
Outcome 4 | Number of men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), landslides (Esmeraldas) and mudflows (Antofagasta and Taltal) | Number of people Antofagasta = 0 Taltal = 0 Esmeraldas (floods) = 0 Esmeraldas (landslides) = 0 | Number of people Antofagasta = 0 Taltal = 0 Esmeraldas (floods) =161,000 people (ca., 50% women) Esmeraldas (landslides) = 0 | Antofagasta = 380,000 people (ca., 50% women) Taltal = 10,000 people (ca., 50% women) Esmeraldas (floods) = 161,000 people (ca., 50% women) Esmeraldas (landslides) = 161,000 people (ca., 50% women)
Outcome 4 | The early warning systems in Antofagasta, Taltal, Cerro Gatazo and Isla Luis Vargas Torres are gender and culturally sensitive and consider the special needs of persons with disabilities. | Number of early warning systems Antofagasta = 0 Taltal = 0 Cerro Gatazo = 0 Isla Luis Vargas Torres = 0 | Number of early warning systems Antofagasta = 0 Taltal = 0 Cerro Gatazo = 0 Isla Luis Vargas Torres = 0 | Four early warning systems are gender and culturally sensitive and consider the special needs of persons with disabilities.
Outcome 5 | Number of staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 Other coastal cities Chile = 0 Other coastal cities Ecuador = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 Other coastal cities Chile = 0 Other coastal cities Ecuador = 0 | Antofagasta = >50 Taltal = >10 Esmeraldas = >20 Other coastal cities Chile = >10 Other coastal cities Ecuador = >10 About 40% will be women
Outcome 6 | Number of men and women who have participated in awareness activities and events. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 1321 (45% women) Taltal = 737 (44% women) Esmeraldas = 620 (49% women) | Antofagasta = >30,000 (ca., 50% women) Taltal = >1,000 (ca., 50% women) Esmeraldas = >16,000 (ca., 50% women)
Outcome 6 | Number of narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 10 (ca., 50% women) Taltal = 5 (ca., 50% women) Esmeraldas = 10 (ca., 50% women)
Outcome 7 | Number of men and women (by nationality) who have participated in events for dissemination of lessons and best practice (e.g., workshops, exchange visits, seminars) | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 0 Taltal = 0 Esmeraldas = 31 (48% women) | >200 people > 40% women
Outcome 7 | Number of visitors per month (annual average) recorded in the network of electronic channels of the regional on-line platform used to disseminate project´ learnings and best practice | Visits 0 Unique visits 0 | Visits 0 Unique visits 0 | Visits >4000 Unique visits >3200

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Due to the COVID-19 pandemic, the governments of the both countries have maintained measures that make it difficult to carry out activities in the field with the beneficiaries. On the other hand, two important bidding processes did not get the expected results. One, because there was no provider and another one because the proposal did not meet the expected quality.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The arrival of Covid-19 in both country cause some delays in the workshops and participatory meetings. To address this situation, virtual events were held as much as possible and the on-site events were conducted under strict biosecurity measures. In Chile, the Rainwater Management Plan was declared void due to the lack of bidders, delaying the activity as initially planned. Terms of Reference were adjusted to ensure bidders participation in a new bidding process. In Ecuador, the competitive process for updating the designs of the infrastructure works in Cerro Gatazo not get the expected results because the proposal did not meet the expected quality. On the other hand, the Early Warning System (EWS) equipment acquisition is stopped due to the fact that the allocated budget for this output exceed 10%. A material change has been sent to the Adaptation Fund for approval, subsequently the equipment acquisition would be reestablished. In Chile, the design of the EWS was made by ONEMI. However, the adquisition process of the EWS equipment require to sign an agreement between ONEMI and the project, the agreement is under revision and is taking a long time to be signed. There was a delay in the disbursement, making project execution difficult. The Executing Entity and the Implementing Entity held meetings to find a mechanism to facilitate the review of the enabling documents and the transfer of the following disbursements.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Output 3.1 and 3.2. Prior to the acquisition of the Radar and the meteorological stations in Esmeraldas, a diagnostic study and proposal for climate improvement in Esmeraldas was carried out. As a result of this study, it was determined that technically and financially it is not advisable to acquire a radar and that the optimal alternative to improve climate monitoring requires consolidating and strengthening a minimum hydrometeorological network. Output 4.2 To strengthen the Early Warning System management, the project promote workshops on risk and emergency management brigades with the people of Luis Vargas Torres Island. Once the brigades were formed, the project, together with the Fire Department, the SNGRE and ECU911, provide training to the brigades. In addition, several agreements will be signed between the institutions lending their facilities to installe the Early Warning equipment.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. The project implement effective measures to avoid unwanted negative environmental and social impacts. Such as: 1. A communication and participatory strategy is now in place. 2. Technical studies were carried out to define the location of the meteorological stations. 3. The design, location and installation of flood evacuation maps and signage on Luis Vargas Torres Island was carried out with the active participation of the beneficiaries. 4. A grievance mechanism is now in place and the communities and beneficiaries has been informed about the process to follow.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Yes, gender considerations has been put in place, such as: 1. Participatory and inclusive approach in all the workshops, events and trainings has been incorporate in the project execution. 2. The project team is gender balance 3. The public communication strategy to empower and engage local communities is now under design. 4. Training of territorial women's roundtables to strengthen their participation in risk management issues in the communities.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A at this stage
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A at this stage
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A at this stage
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A at this stage
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects / programmes implementing concrete adaptation interventions? | N/A at this stage
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A at this stage
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A at this stage
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A at this stage
What measures are being/could have been put in place to improve project/program results? | N/A at this stage
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A at this stage
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A at this stage
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A at this stage
If learning objectives have been established, have they been met? Please describe. | N/A at this stage
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A at this stage
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A at this stage
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A at this stage
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Development Bank of Latin America (CAF)
Type of implementing entity | RIE
Country | Ecuador
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 551000 | 47000 | 504000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding | 2: Partially effective | Total | 47000 | Coastal flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 3 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 100 | Disaster risk reduction | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 50 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 50% | 2: Partially not aware |  | 551000 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness