## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | January 1st 2022 - December 31st 2022
| Project Title: | Reducing climate vulnerability and flood risk in coastal urban and semi urban areas in cities in Latin America
| Project Summary: | Adaptation to climate change in coastal cities is a main challenge for both countries (Ecuador and Chile) as coastal areas are more exposed and vulnerable to the negative effects of climate change and the impacts of weather-related disasters. The project objective is to reduce vulnerability to climate-related floods, mud flows and landslides in the three coastal cities by mainstreaming a risk-based approach to adaptation, building collaboration and networking, and develop a culture of adaptation. To achieve this objective, the most prevalent risks were considered in each of the three cities. In the case of the Chilean populations, these are mudflows, while for Esmeraldas floods and landslides were considered. The lessons learned from this initiative are projected to be useful for the entire region of Latin America and the Caribbean. The project has three components: Component 1 focus on priority actions to increase resilience in the three cities. Four outcomes will be generated by mainstreaming DRR into local planning, building infrastructure which incorporate climate-related variables, improving climate monitoring, and strengthening the existing early warning and response systems. Component 2 focus on strengthening the capacities of local government officers and communities, as well as fortifying connections between communities and local and national government. Two outcomes will be generated by developing an online training course on risk-based adaptation for municipal and government officers and technical staff and implementing communication and education strategies to increase local awareness and contribute to build cultural memory. The online course will be open to professionals from other coastal cities of Latin America and the Caribbean. Component 3 focus on nurturing the project´s communities of practice and to document and disseminate the lessons. The backbone of the regional project are the communities of practice that allow the development of collective learning on specific topics. Five communities of practice will be developed.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Development Bank of Latin America (CAF) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity (RIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Chile and Ecuador | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Cities of Antofagasta and Taltal in Chile and Esmeraldas in Ecuador | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 16th 2018
IE-AFB Agreement Signature Date: |  | December 11th 2018 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | January 22nd 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | April 22nd 2023
January 22nd 2025
Original Completion Date:
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | N/A | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://adaptaclima.org/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Nury Bermudez | Dominican Republic
| Email: | nury.bermudez@undp.org | Ecuador
| Date: | 2019-07-04 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Karina Barrera | Equatoral Guinea
| Email: | karina.barrera@ambiente.gob.ec | Eritrea
| Date: | 2021-03-18 | Estonia
| Name: | Jenny Mager
| Email: | curmeneta@mma.gob.cl
| Date: | 2022-04-01
| Implementing Entity |  | Ethiopia
| Name: | Carolina Cortes | Fiji
| Email: | acortes@caf.com | Finland
| Date: | 2018-12-11 | France
| Executing Agency |  | Gambia
| Name: | Mónica Andrade | Georgia
| Email: | monica.andrade@undp.org | Germany
| Date: | 2019-07-04 | Ghana
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to December, 31st 2020 |  |  |  | Financial information PPR 2. Period: January 2021 - June 2021 |  |  |  | Financial information PPR 2. Period: January 2021 - December 2021 |  |  |  | Financial information PPR 3: Period: January 2022 - December 2022 |  |  |  | Financial information PPR 4: Period: January 2023 - December 2023
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [December, 31 2020] | 1181487 |  |  | Estimated cumulative total disbursement as of [June, 30 2021] | 2494307 |  |  | Estimated cumulative total disbursement as of [December, 31st 2021] | 3807128 |  |  | Estimated cumulative total disbursement as of [December, 31st 2022] | 4498026 |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 4 years is USD 11,698,513. The second dibursment of $2'625.641 will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 3.5 years is USD 10,385,693. The fourth dibursment of $1'312.820 will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 3 years is USD 9,072,872. The fifth disbursement will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200) | To date, the remaining value to be disbursed to the executing entity in the next 2 years is USD 8,381,974. The sixth disbursement will be made once the PPR and procurement plan has been approved by the Project Board |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 7766.09 |  | CAF | INVESTMENT INCOME |  |  | Valor CAF | INVESTMENT INCOME | 7635.12 |  | CAF | INVESTMENT INCOME | 82827.79 |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Accumulated amount of investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1. Stormwater management plan for Antofagasta | 27764.5134 |  |  | 1.1. Stormwater management plan for Antofagasta | 19287.2618 |  |  | 1.1. Stormwater management plan for Antofagasta | 99843.545 |  |  | 1.1. Stormwater management plan for Antofagasta | 211870.601
| 1.2. Green infrastructure plan for Esmeraldas | 67283.2494 |  |  | 1.2. Green infrastructure plan for Esmeraldas | 74286.8079 |  |  | 1.2. Green infrastructure plan for Esmeraldas | 113571.1473 |  |  | 1.2. Green infrastructure plan for Esmeraldas | 55417.5
| 2.1. Mudflow control infrastructure in Antofagasta | 16931.4621 |  |  | 2.1. Mudflow control infrastructure in Antofagasta | 19852.4943 |  |  | 2.1. Mudflow control infrastructure in Antofagasta | 84192.55 |  |  | 2.1. Mudflow control infrastructure in Antofagasta | 426116.151
| 2.2. Landslide mitigation works in Esmeraldas | 23190.0409 |  |  | 2.2. Landslide mitigation works in Esmeraldas | 20600.5579 |  |  | 2.2. Landslide mitigation works in Esmeraldas | 32550.6673 |  |  | 2.2. Landslide mitigation works in Esmeraldas | 30455.89
| 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 48375.0876 |  |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 34368.1654 |  |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 98420.4123 |  |  | 3.1. Increased number of meteorological stations at Esmeraldas, Antofagasta and Taltal, and storm detection service at Antofagasta | 488227.701
| 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 5746.0339 |  |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 2696.1779 |  |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 28068.0473 |  |  | 4.1. Enhanced public warning system in Antofagasta and Taltal | 11878.671
| 4.1. Enhanced public warning system in Antofagasta and Taltal | 15980.1927 |  |  | 4.1. Enhanced public warning system in Antofagasta and Taltal | 10189.143 |  |  | 4.1. Enhanced public warning system in Antofagasta and Taltal | 36700.6725 |  |  | 4.2. Pilot flood warning system in Esmeraldas | 128106.92
| 4.2. Pilot flood warning system in Esmeraldas | 22019.8113 |  |  | 4.2. Pilot flood warning system in Esmeraldas | 31438.0836 |  |  | 4.2. Pilot flood warning system in Esmeraldas | 49896.7673 |  |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 17095.201
| 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 17530.3546 |  |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 12885.321 |  |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 36911.9598 |  |  | 5.1. Course on risk-based adaptation in coastal cities | 60964.111
| 5.1. Course on risk-based adaptation in coastal cities | 34755.6387 |  |  | 5.1. Course on risk-based adaptation in coastal cities | 31673.2154 |  |  | 5.1. Course on risk-based adaptation in coastal cities | 50253.9923 |  |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 154183.511
| 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 38255.6995 |  |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 22357.5529 |  |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 58003.4423 |  |  | 6.2. Narrators´ initiative initiated | 130453.671
| 6.2. Narrators´ initiative initiated | 32053.1473 |  |  | 6.2. Narrators´ initiative initiated | 22017.1329 |  |  | 6.2. Narrators´ initiative initiated | 67379.8223 |  |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 103961.216
| 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 18792.1212 |  |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 9927.3379 |  |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 25450.8723 |  |  | 7.2. Lessons and best practice documented and disseminated | 103453.396
| 7.2. Lessons and best practice documented and disseminated | 50007.8224 |  |  | 7.2. Lessons and best practice documented and disseminated | 31565.4679 |  |  | 7.2. Lessons and best practice documented and disseminated | 70645.0823 |  |  | Project Execution cost | 151974.11
| Project Execution cost | 33494.85 |  |  | Project Execution cost | 26165.99 |  |  | Project Execution cost | 79084.73 |  |  | Project/Programme Cycle Management Fee charged by the Implementing Entity | 3095.78
| Project/Programme Cycle Management Fee charged by the Implementing Entity |  |  |  | Project/Programme Cycle Management Fee charged by the Implementing Entity |  |  |  | Project/Programme Cycle Management Fee charged by the Implementing Entity | 42364.22 |  |  | TOTAL | 2077254.43
| TOTAL | 452180.025 |  |  | TOTAL | 369310.71 |  |  | TOTAL | 973337.93 | [6 empty] | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1. Stormwater management plan for Antofagasta | 377910.9457 | 2022-03-01 |  | 1.1. Stormwater management plan for Antofagasta | 361559.1339 | 2022-10-01 |  | 1.1. Stormwater management plan for Antofagasta | 254590.138 | 2022-10-01 |  | 1.1. Stormwater management plan for Antofagasta | 24260.4655 | 2023-12-01
| 1.2. Green infrastructure plan for Esmeraldas | 120548.0312 | 2021-10-01 |  | 1.2. Green infrastructure plan for Esmeraldas | 70305.5607 | 2021-09-01 |  | 1.2. Green infrastructure plan for Esmeraldas | 31027.1582 | 2022-12-01 |  | 1.2. Green infrastructure plan for Esmeraldas | 104960.9655 | 2023-12-01
| 2.1. Mudflow control infrastructure in Antofagasta | 267588.4157 |  |  | 2.1. Mudflow control infrastructure in Antofagasta | 239686.2714 | 2022-11-01 |  | 2.1. Mudflow control infrastructure in Antofagasta | 474209.9578 | 2022-11-01 |  | 2.1. Mudflow control infrastructure in Antofagasta | 66799.4655 | 2023-11-01
| 2.2. Landslide mitigation works in Esmeraldas | 244000 | dec-21 |  | 2.2. Landslide mitigation works in Esmeraldas | 270043.6851 | 2022-09-01 |  | 2.2. Landslide mitigation works in Esmeraldas | 374017.1582 | 2023-03-01 |  | 2.2. Landslide mitigation works in Esmeraldas | 295098.9655 | 2023-12-01
| 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 455895.4612 | dec-21 |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 771832.6245 | 2022-02-01 |  | 3.1. Weather radar in Esmeraldas and a storm detection system in Antofagasta | 701491.7753 | 2024-12-01 |  | 3.1. Increased number of meteorological stations at Esmeraldas, Antofagasta and Taltal, and storm detection service at Antofagasta | 375092.8855 | 2023-12-01
| 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 161000 | dec-21 |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 130581.0351 | 2022-03-01 |  | 3.2. Increased number of meteorological stations in Antofagasta, Taltal and Esmeraldas | 112598.5673 | 2022-10-01 |  | 4.1. Enhanced public warning system in Antofagasta and Taltal | 227479.4655 | 2023-12-01
| 4.1. Enhanced public warning system in Antofagasta and Taltal | 30000 | 2022-03-01 |  | 4.1. Enhanced public warning system in Antofagasta and Taltal (1) | 234094.4027 | 2022-01-01 |  | 4.1. Enhanced public warning system in Antofagasta and Taltal (1) | 250090.9291 | 2022-12-01 |  | 4.2. Pilot flood warning system in Esmeraldas | 92600.9655 | 2023-12-01
| 4.2. Pilot flood warning system in Esmeraldas | 98000 | 2021-05-01 |  | 4.2. Pilot flood warning system in Esmeraldas | 77778.9094 | 2021-12-01 |  | 4.2. Pilot flood warning system in Esmeraldas | 224152.1582 | 2022-12-01 |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 47486.9655 | 2023-12-01
| 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 104506.1412 | 2022-03-01 |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 104821.032 | 2022-01-01 |  | 4.3. Evacuation route maps and signals in Antofagasta, Taltal and Esmeraldas | 62115.3673 | 2022-11-01 |  | 5.1. Course on risk-based adaptation in coastal cities | 66026.9552 | 2023-08-01
| 5.1. Course on risk-based adaptation in coastal cities | 192000 | aug-21 |  | 5.1. Course on risk-based adaptation in coastal cities | 127512.8076 | 2024-12-01 |  | 5.1. Course on risk-based adaptation in coastal cities | 80954.0673 | 2022-08-01 |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 101664.9552 | 2023-12-01
| 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 142017.7262 | 2021-09-01 |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 96810.1951 | 2024-12-01 |  | 6.1. Public communication and education strategies for Antofagasta, Taltal and Esmeraldas. | 157689.0673 | 2022-12-01 |  | 6.2. Narrators´ initiative initiated | 158394.2652 | 2023-12-01
| 6.2. Narrators´ initiative initiated | 64000 | 2021-11-01 |  | 6.2. Narrators´ initiative initiated | 65081.1551 | 2024-12-01 |  | 6.2. Narrators´ initiative initiated | 231764.0673 | 2022-12-01 |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 70404.4552 | 2023-12-01
| 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 77534.8812 | dec-21 |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 28128.5351 | 2022-01-01 |  | 7.1. Electronic platform to facilitate communication among stakeholders and dissemination of lessons and best practice | 83632.0673 | 2022-12-01 |  | 7.2. Lessons and best practice documented and disseminated | 125251.9552 | 2023-12-01
| 7.2. Lessons and best practice documented and disseminated | 79039.1112 | dec-21 |  | 7.2. Lessons and best practice documented and disseminated | 38200.3451 | dec-21 |  | 7.2. Lessons and best practice documented and disseminated | 155068.7473 | 2022-12-01 |  | Project Execution cost | 140441.8184 | 2023-12-01
| Project Execution cost | 193123.22 | dec-21 |  | Project Execution cost | 130000 | dec-21 |  | Project Execution cost | 233824.5757 | 2022-12-01 |  | Project/Programme Cycle Management Fee charged by the Implementing Entity | 122000 | 2023-12-01
| Project/Programme Cycle Management Fee charged by the Implementing Entity |  | dec-21 |  | Project/Programme Cycle Management Fee charged by the Implementing Entity |  | dec-21 |  | Project/Programme Cycle Management Fee charged by the Implementing Entity |  |  |  | TOTAL | 2017964.5484
| TOTAL | 2607163.9334 |  |  | TOTAL | 2746435.6925 |  |  | TOTAL | 3427225.8014 | [6 empty] | TOTAL | 0
(1) The value of the Antofagasta and Taltal EWS is included because the selection process begins this year; however, the contract will be signed at the beginning of 2022.
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | [7 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing has been identified in the design of the proposal, nor during the execution period. | [6 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing has been identified in the design of the proposal, nor during the execution period. |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing has been identified in the design of the proposal, nor during the execution period. |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing has been identified in the design of the proposal, nor during the execution period.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | [7 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | [7 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Change of central government in Chile. New president and congress will take office in 2022 | Moderate | The project has been presented to the new authorities and is supported by them for its implementation
Change of municipal governments in Antofagasta and Taltal. The new authorities will take office in December 2020. | Moderate | Meetings were held with the newly elected authorities of Antofagasta and Taltal. Project activities and planning for the remainder of the project were presented. The project has the support of the new authorities.
Change of municipal and provincial governments in Esmeraldas. The new authorities will take office in 2023 | Moderate | The project will be presenedt to the new authorities and is supported by them for its implementation.
Support withdrawal from local counterparts, taking into account the change of Governments. | Low | Meetings with key local government authorities to ensure support during implementation. Commitment of institutions to designate technical focal points to ensure project continuity.
The change of Governments could eventually lead to staff re-structuration, meaning that there could possibly be a knowledge gap between the newcomers. | Low | Commitment of institutions to designate technical focal points to ensure project continuity In case there is new staff, meetings will be held to share the progress of the project Periodic activity progress and budgetary implementation reports will be carried out by the project
Authorities and technical staff of government institutions prioritize health emergency activities by COVID-19 | Low | Coordination with central and local government institutions, scheduling meetings that enable the fulfillment of project activities
Local governments do not count with up-to-date cadastral information of the project intervention areas | High | The project team will ask the local government the actualization of cadastral information and land tenure of the project intervention areas.
Lower economic activity in both countries and impact of COVID-19 pandemic | Low | A significant reduction in economic activity in both countries resulting from COVID-19 has been shown. Within the framework of the project implementation, partner institutions have been supported for the implementation of activities to reduce the risk in case of climate disasters within project intervention areas.
Grant not being delivered and/or not being delivered on time. | High | UNDP's cash flow allows it to assume certain commitments through project overdrafts in case of delays.
Increase in budget due to costs miscalculations, and/or due to overprices during project implementation. | Medium | The project was developed 5 years ago, budget changes are needed. Material changes could be a possible solution if overprices increase 10% of each output. The budget changes will be first presented to the Project Steering Committee. Once the Steering Committee's approval is obtained, CAF will sent it to the Adaptation Fund for review and approval.
GADPE has no experience with meteorological monitoring | High | Since GADPE has decided not to take charge of the weather stations in Esmeraldas, the stations will be in charge of INAMHI, the national institution in charge of climate monitoring.
Baseline studies are not up to date | Low | In Antofagasta, studies were carried out to update flood control infrastructure works. In Esmeraldas, the designs of the bridge that serves as an evacuation route for the Luis Vargas Torres Island in case of possible flooding were updated.
Inaccuracy in radar and storm detection system implementation | Low | In Chile, technical advice and support are available by the competent national body DMC. Regular advisory meetings are held to evaluate the progress of the contracted storm detection system.
The need to relocate families located in the intervention area could hinder the infrastructure works. | High | Meetings with the Local Government of Esmeraldas to analyze the different possibilities for the dwelling relocation in the area of intervention.
Misuse of the online platform created to share best practices between coastal cities. | Low | In-person meetings between project partners of both countries. Four thematic visits are forecasted.
Lack of understanding of the project, and hence opposition from the local inhabitants. | Moderate | Public education and communication strategies are being implemented in Esmeraldas, Antofagasta and Taltal. As part of the strategies, activities are carried out on an ongoing basis with the community to involve them in the project activities.
COVID-19 restrictions make it difficult to personally approach the project beneficiaries | Low | Performing virtual events (workshops, webinars) when it is possible Execution of face-to-face workshops following guidelines established by government. Protection kits should be provided to attendees of face-to-face meetings.
Difficulty in implementing activities in the "20 de Noviembre" neighborhood in Cerro Gatazo, due to the alarming increase of violent acts in the area. | High | Coordination with relevant entities to assess the current situation and determine the feasibility of implementing the activities planned for 2022 Search for strategic partners in the territory that can execute actions in the project implementation areas.
Effect of El Niño / La Niña in precipitation and local weather conditions. | Low | Monitoring current collected weather information from the project intervention area
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Interference in the construction of the alluvial control works of Quebrada Bonilla by the aggregate extraction company located in the creek. | High | Coordination of meetings with technical agencies with legal competence such as the Directorate of Hydraulic Works (DOH), Directorate General of Water (DGA), National Property, Sernageomin, Presidential Delegation. The DOH has requested authorization to work on the land from Bienes Nacionales. Once the land has been handed over, the next steps will be reviewed in conjunction with the Seremi de Medio Ambiente.
Interference in Project activities (Cerro Gatazo) due to local violence and crime. | High | Coordination with the National Police to ensure security measures. Establishing relationships with other organizations that can somehow enter conflict zones to work with the community.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During 2022, some risk situations identified in the Project Document have been presented related to the change of authorities within the partner institutions, the delay in the receipt of the disbursement for 2022, and the increase of violence and crime in Cerro Gatazo and and different areas of the city of Esmeraldas. new national and local governments took office in Chile local authorities took office in 28/06/21; the president and the cabinet in 11/03/2022 and the governors took office in 14/07/2021. In Ecuador national authorities (elected president and his cabinet) took office in 24/05/2021. This changes demand additional time to socialize the project and the activities with the new Ministries, focal points and authority elected. One of the risks of greatest concern for the project is the increase in violence throughout the city of Esmeraldas. In 2022, acts of violence were recorded in different parts of the city, including those areas where the project is directly involved, such as Luis Vargas Torres Island and Cerro Gatazo. The government establish State of Emergency with strict curfew in the province of Esmeraldas as of November 1st, 2022, effective for 45 days, generating new delays in the implementation of the project. Some acts of violence occurred in areas where the project is working, such as Luis Vargas Torres Island and Cerro Gatazo. None of the project's partner institutions in the territory want to work in Cerro Gatazo and Luis Vargas Torres Island, including the National Police. There is a high security risk for project team, which has made it difficult to carry out activities in Esmeraldas. For security reasons, among the measures taken, it has been decided that the technical team will not enter the area until security conditions are guaranteed. To mitigate this risk, relationships are being established with other organizations that can in some way enter the conflict zones to work with the community. In the other hand, other potential risk was identified for the construction of the flood control works in Antofagasta. An aggregate extraction company is illegally operating in the project area, which could hinder the start of construction in Quebrada Bonilla. Coordination is underway with the MOP to initiate the eviction of the aggregate extractor company. Based on all these considerations, the project appeals an extension period with no additional funds requisition until January 2026.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Risk: Insufficient alignment with laws and technical standards, especially related to implementation of concrete infrastructure works and climate monitoring under Component 1, Outcome 2 and Outcome 3. Impact: Grey and green infrastructure implementation could not get the Environmental Registry - Ecuador or the Environmental Impact Declaration – DIA for Chile | Grey and green infrastructure works not yet in place Safeguard measures identified in the Project Document: Activity 5. Interventions in Chile have to comply with technical standards, environmental permits and construction code regulations. Activity 6. Interventions in Ecuador have to comply with technical standards, environmental permits and construction code regulations. | Updated studies for implementation of grey and green infrastructure Environmental permit application submitted | 0 updated studies 0 environmental permit application processed | In Ecuador, due to crime problems at Cerro Gatazo, the start of the works design update was delayed. Preliminary feasibility studies for the works have been carried out and in early 2023 In Chile, the update infraestructure studies is in its final stage. Once the studies are updated, all the necessary documentation will be present to obtain the environmental permits in accordance with the regulations in both countries. | Ecuador: Difficulty in accessing the Cerro Gatazo area to move forward with the updating of the infrastructure designs. Chile: There is an aggregate extraction company in the area where the infrastructure works will take place. This could be a problem for the start of the works. | Ecuador: Seek strategic alliances with other institutions such as Caritas or the Army Corps of Engineers to carry out this activity. Chile: Work jointly with the MOP and Public Property to evict the aggregate extraction company from the area.
2 - Access and equity |  |  | Risk: Possible interruption of water supply, energy services or roads / streets accessibility. The beneficiary might have no access to project benefits because of inexistent mechanism to ensure participation of communities, marginalized, vulnerable groups, and stakeholder and local authorities. Impact 1: If the community is not properly communicated and involved in the process of updating the plan, their local knowledge in their surrounding area such as “Campamentos” or in the ravine routes will not be taken into account. Impact 2: If the community does not participate in the process of preparing the green-infrastructure plan for Esmeraldas, the community will not be informed of risks of residing on hill and will repeat and conceive it as a possible settlement place. Impact 3: If the community is not properly communicated and involved in the process of updating the designs of the infrastructure, their local knowledge in their surrounding area such as “Campamentos” or in the ravine routes will not be taken into account. Impact 4: Do not exist conditions to approve the declaration and preserve the protected forest Impact 5: Impossibility to install the radar and meteorological stations in the best location reached. Radar and meteorological stations without maintenance could not operate properly or not lasting the expected lifetime. Community members could harm or steal the monitoring instruments. Impact 6: If the community does not participate or comment the evacuation maps and procedures for Antofagasta and Taltal, they will not help with their local knowledge and own situation. Also, it is important that they are aware of all the ideas and must agree with the plan. If not, human lives could be in danger. Impact 7: Unable to help their community in an emergency situation. Impact 8: Insufficient information available to update the evacuation maps. Human lives could be in danger. Impact 9: Lack of sustainability of the action and population still in danger. Impact 10: If the community is not able to participate in localization of the banners they may be unused increasing the possibility of accidentally Impact 11: The use of the electronic platform may be limited if the community or community - social leaders does not empower themselves to use it. Impact 12: Technical Staff with lack of knowledge would cause misunderstanding of the disaster risk reduction and adaptation subject and create some difficulties on the implementation phase. Impact 13: Trainers without real capacities to manage disaster risk reduction and adaptation issues in their daily working. Impact 14: Technical staff from the local government without real capacities to manage disaster risk reduction and adaptation issues in their daily working. Impact 15: Technical staff of Esmeraldas local government without proper knowledge about green infrastructure or eco-engineering measures to cope with adaptation measures in the future. Impact 16: Local stakeholders no deeply into green infrastructure or eco engineering would cause lack of sustainability of the actions. Impact 17: Not participation of the social community in the communities of practice. The heterogeneity could be lost. Impact 18: The use of the electronic platform may be limited if the community or community - social leaders does not empower themselves to use it. Impact 19: Not awareness of the community in general of the lessons and best practices of the project. | Safeguard measures identified in the Project Document: Activity 1 - 2 - 3 - 4 - 8: The Local Social Specialist for Chile and Ecuador respectively will prepare a “Communication and Participatory Strategy” that will contain all the activities and how the local community should be involved . Activity 4: The process of including climate change considerations will used comprehensive methodology to fulfill the main objective, of mitigate the population living at risk. Activity 6: The Local Social Specialist for Ecuador will communicate about the Grievance mechanism available. The procedure and forms will be accessible to all actors directly involved in the actions. Also the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • If there is any possibility of interruption of the basic services caused such as water shortage or energy disruptions, the operational contractor team shall make communication to the community affected. • The operational contractor team shall be responsible for the coordination action related with traffic and temporary closure of traffic. In accordance with communities, routes and schedules of access to the Gatazo operational area can be planned. • Fences or barriers and pedestrian pathways are required to be installed. • Receive inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed the proceed with the grievance mechanism. Activity 8: Trainings and participatory strategy put in place by the local specialist for social issues during the whole implementation. Media Specialist works in behavioral insights messages to explain the importance of this action for the population own safety. Activity 9 - 10 - 11- 12 - 13 - 14 - 15 - 19: The study to identify the location must analyze different places based on a criteria matrix, such as: accessibility, security, no disturb landscape or other telecom instruments among others. The project will ensure that the government has technician in the area and train them to used and maintain the radar. The community need to be informed clearly, a campaign would be implemented by the Media Specialist to reach different target of population. Activity 16 - 18 - 21: A comprehensive information strategy in place to involve the whole community in the evacuation maps. The process will be conducted by the Local Social Specialist based on the “Communication and Participatory Strategy” Activity 17 - 20 - 22 - 23 - 25: Real involvement of the community in the different phases of the process, based on the Communication and Participatory Strategy. Activity 24: The Local Social Specialists shall be aware that the socialization and presentation of the maps is relevant for their use. The “Communication and Participatory Strategy” shall include workshop to define the localization of the maps. Activity 26 - 35 - 36 - 37: The Regional Media Specialist in the “Communication and Participatory Strategy” shall include the development of the regional electronic platform. Activity 27: The Project Board and the Project Manager of the project will require them to participate in the Courses. The courses will be mandatory for all technical staff in both countries. Activity 28: Motivate the trainers to actively participate in the training prepared for them about green infrastructure and disaster risk reduction strategies. Activity 29: Understand the final beneficiaries of this courses, this one means the personnel from the local governments. Before implementing the courses, a survey will be conducted to understand their knowledge, expertise and behaves. The courses will be prepared based on a comprehensive analysis of this database. Also, the timetable of the classes will be analysis thoroughly to fine the best and productive usage time. Activity 31:Motivate the technical staff to actively participate in the training prepared for them about green infrastructure and eco-engineering. Prepare a comprehensive Course Plan with the best technician on eco-engineering, with experience in tropical areas and with native vegetable species. Activity 32: The whole process about the green infrastructure plan need the involvement of key local stakeholders during the implementation. The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans and be part of the “Communication and Participatory Strategy”. | Number of Communication and Participatory Strategies Number of Technical report of location for equipment installation Number of training workshops for the technical staff of the institutions in charge of the stations Percentage of project technical staff who have taken the regional risk-based adaptation course Number of grievances received related to access to basic services | 0 Communication and Participatory Strategy 0 Technical report of location for equipment installation 0 training workshops for the technical staff of the institutions in charge of the stations 0% project technical staff who have taken the regional risk-based adaptation course 0 grievances received related to access to basic services | Communication and educational strategies were developed for Esmeraldas, Antofagasta and Taltal. A regional communication strategy was also developed. These documents promote the integration of beneficiaries and key stakeholders in the activities carried out by the project. - Online and face-to-face workshops were held on activities related to the early warning system in Esmeraldas,the update of landslide control works in Antofagasta, the Esmeraldas Green Infrastructure Plan, the Antofagasta Rainwater Master Plan, the installation of meteorological stations in Esmeraldas, Antofagasta and Taltal, updating the designs of the flood control works in Antofagasta, and the strategy for storytellers, among others. - A diploma course on disaster risk management and adaptation to climate change was implemented with the participation of public officials from local and national governments in Chile and Ecuador, as well as part of the project's technical team. 70 people passed the diploma course offered by the Universidad de Chile. - Capacity-building processes were carried out for women in disaster risk management and climate change adaptation through women's roundtables in Esmeraldas, Antofagasta and Taltal. - Socialization of project activities on local radio in Esmeraldas, Antofagasta and Taltal - The Grievance mechanism has been socialized in different workshops and trainings. There is a specific section on the project website to receive complaints, doubts and suggestions related to the project activities. | Not identified | Not identified
3 – Marginalized and vulnerable Groups |  |  | Risk: The project might impede an access to basic services such as clean air, energy and housing, safe may be affected. This referred to Component 1. Impact: Claims, non-conformity and possible interruption of works may occur. | This risk is activated once the grey and green infrastructure works are carried out in Esmeraldas. In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 6: The Local Social Specialist for Ecuador will communicate about the Grievance mechanism available. The procedure and forms will be accessible to all actors directly involved in the actions. Also the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • The operational contractor team shall be responsible for the coordination action related with traffic and temporary closure of traffic. In accordance with communities, routes and schedules of access to the Gatazo operational area can be planned. • Fences or barriers and pedestrian pathways are required to be installed. • Receive inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed by the grievance mechanism. | Number of grievances received related to problems of access to basic services | 0 grievances received related to problems of access to basic services | In this reporting period, no safeguard measures have been required | Not identified | Not identified
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Risk: Either women or men has unequal opportunities to participate taking into account their working schedules or lifestyles, this referred to in Component 1, Component 2 and Component 3. Impact 1: Only one gender could assist to the course. The gender perspective could be lost, is women cannot assist, children assistance also could be put in risk. Impact 2: Only one gender could assist to the communities of practice. The gender perspective could be lost, if women cannot participate. | The project has promoted equal opportunities for both women and men by taking into account schedules, lifestyle and responsibilities. Safeguard measures identified in the PRODOC: Activity 33: The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. Activity 34: The Local Social Specialist for Chile shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. Activity 35: The Local Social Specialist for Chile and Ecuador shall be aware that the socialization and presentation of the plans should the in schedules that women can attend and be part of the “Communication and Participatory Strategy”. | Percentage of women's participation in events held by the project | 0% of event attendees have been women | The participation of men and women is equal. Schedules, lifestyles and responsibilities that may affect the participation of men and women have been considered. In addition, through the women's roundtables, specific training has been conducted on gender and climate change and disaster risk management. | Not identified | Not identified
6 – Core labour rights |  |  | Risk: Insufficient alignment with core labour rights, especially related to implementation of concrete infrastructure works and climate monitoring under Component 1, Outcome 2 and Outcome 3 Impact: Persons and workers in the surroundings areas could be injured or affected. | In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 5 - 6: The operational contractor team in Chile and Ecuador shall be responsible for the control of the entire works and implement specific mitigation measures to cope with casualties during construction. • Consider the identified hazards including those that may originate from outside the workplace that are capable of adversely affecting the health and safety of persons under the control of the organization within the workplace. • Applied control related to risk assessment • Follow an accident investigation form. • Recognize extra hours of work, in compliance with the labour regulation of each country. • Be aware of the equipment that the workers use during the infrastructure works. • Take into consideration the medical care emergency kit at the infrastructure works. • Keep in mind the medical check provided at the beginning of the works. • Construction workers must also be provided with identification tags. • Comply with the national legislation – Labour Codes of Ecuador and Chile • Ensure that employment procedures/ policy of the operational contractor is communicated to local stakeholders. • The intention of giving preferential employment to locals is clearly communicated, to discourage an influx of job-seekers from other areas. | Number of grievances received related to problems of violation of labour rights | 0 grievances received | All the procurement process have followed the UNDP Financial Regulations and Rules (2012) as well as a sustainable procurement process including core labour rights. The winning consultants in the different processes must comply with the labor law of each country. | Not identified | Not identified
7 – Indigenous people |  |  | Risk: Indigenous beneficiary families not being adequately informed and engaged to access the range of project benefits. Impact 1: Not use of the information developed. Impact 2: Not participation of the indigenous community in the Narrator’s initiative. The heterogeneity perspective could be lost, is the indigenous community cannot assist. Impact 3: Not participation of the indigenous community in the communities of practice. The heterogeneity could be lost perspective could be lost, is the indigenous community cannot assist. | The project has promoted equal opportunities, incluiding indigenous people and afro-ecuadorina by taking into account working schedules, lifestyle, or languages. This referred to in Component 2. Safeguard measures identified in the PRODOC: Activity 30: The Regional Media Specialist in the “Communication and Participatory Strategy” shall include the development of the regional electronic platform. Activity 33 - 35 - 37: The Local Social Specialist for Esmeraldas shall be aware that the socialization and presentation of the plans should the in schedules that Chachis can attend and be part of the “Communication and Participatory Strategy”. | Communication and participation strategy guarantees participation of indigenous groups | 0 Communication and participation strategies developed | The project developed communication and education strategy for Esmeraldas which promote the integration of beneficiaries and key stakeholders in the activities carried out by the project. In all the events carried out by the project in the reporting period, all the conditions have been taken to ensure that the participation of indigenous people and afro ecuadorians. Schedules, lifestyles and responsibilities that may affect their participation have been considered | Not identified | Not identified
8 – Involuntary resettlement |  |  | Risk: Temporary physical relocation for the nearest families leaving informal settlements in the proximity of the intervention in Cerro El Gatazo – Esmeraldas, basically related with the removal of mud and soil to stabilize the hill. Impact: Claims, nonconformity and possible interruption of the works could occur. | This risk is activated once the grey and green infrastructure works are carried out in Esmeraldas. In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 6: The Local Social Specialist for Ecuador will prepare a “Communication and Participatory Strategy” that will contain all the Activities and how the local community should participate during their development. Implementation of the activities related with the Landslide mitigation infrastructure in Cerro Gatazo - Ecuador, the Operational contractor shall: • Re-Identify the vulnerable groups in the area of influence before the implementation of the project and organize a consultation meeting with the direct beneficiaries and affected groups. • If there is any possibility of the need of possible temporary resettlements this shall be presented as a Plan to the Project Board. • Receive complaints, inquires, suggestions from beneficiaries and communities involved during the consultancy process and if needed by the grievance mechanism. • The GADE team shall be responsible for the coordination action related to the temporary resettlements. • The GADE team shall be responsible for the temporary localization during the project | Number of grievances received related to problems of access to basic services | 0 grievances received | In this reporting period, no safeguard measures have been required | Not identified | Not identified
9 – Protection of natural habitats
10 – Conservation of biological diversity |  |  | Risk: The introduction of non-endemic species for the stabilization of Cerro Gatazo in Esmeraldas may pose a risk for the project. (such decision will come when USP intervention are completely developed) Impact: Introducing non-endemic species could damage the natural biodiversity, even though it is an area already intervened. | In this reporting period, no safeguard measures have been required. Safeguard measures identified in the PRODOC: Activity 2: A study will be undertaken prior to the selection of which species will be used on the implications of introducing different species. Activity 7: The operational contractor has to develop the revegetation in accordance with the Green Infrastructure Plan approved by the Project Board previously. The species that are going to be used should be in the Green Infrastructure Plan. Based on the findings of study, the choice of native species will be appealed. | Technical report on the selection of species to be used for reforestation | 0 Technical reports | In this reporting period, no safeguard measures have been required. However, at the moment the Green Infraestructure Plan has been developed and as part of the plan there is a preliminary analysis of the species to be used in the revegetation process. | Not identified | Not identified
11 – Climate change |  |  | Risk: There is no a risk of significant or unjustified increase in greenhouse gas emissions, considering that the project preliminary will not produce more than 1 MM ton /CO2eq during its lifespan. However, for the sake of the project and the compliance of the E&SP this will be attended with a Carbon Footprint recognized tool. This will be classified as risk. Impact 1: The contribution of GHG emissions directly affects the adaptation of Antofagasta, Taltal and Chile. Impact 2: The contribution of GHG emissions directly affects the adaptation of Esmeraldas and Ecuador. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5 - 6: Carbon Footprint shall be presented Monitoring system of the GHG emissions shall be presented Approval of Carbon Footprint and the Monitoring system of the GHG | Monitoring system of the GHG emissions developed | 0 Monitoring system of the GHG emissions | In this reporting period, no safeguard measures have been required. | Not identified | Not identified
12 – Pollution prevention and resource efficiency |  |  | Risk: The project may be implemented in a way that does not meet applicable standards for minimizing material resource use, the production of wastes, and the release of pollutants. Impact 1: The generation of wastes and pollutants during the construction works will pollute the surrounding area of Antofagasta. Impact 2: Health diseases affecting the population of the surroundings and workers. The generation of wastes and pollutants during the construction works will pollute the urban area of Esmeraldas. As environmental impact of gabion retaining walls is basically the slight increment the of greenhouse emissions taking into account the transport of materials. Impact 3: Impossibility to install the radar and meteorological stations in the best location reached. Impact 4: Radar and meteorological stations without maintenance could not operate properly or not lasting the expected lifetime. Impact 5: Community members could harm or steal the monitoring instruments. Impact 6: Impossibility to install the meteorological stations and the storm detection system in the best location reached. Impact 7: Meteorological stations and the storm detection system without maintenance could not operate properly or not lasting the expected lifetime. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta as well as the installation of meteorological instruments and early warning systems. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5: A construction plan shall be presented to the Project Board. A specific monitoring procedure for the construction works shall be presented to the Project Board. The operational contractor shall implement a monitoring plan to control: • Water consumption. • Fuel consumption. • Type of fuel consumption • Raw material consumption. • Energy consumption. • Solid waste generation. • Wastewater / generation (quality of wastewater). • Construction waste / debris generation. Approve the Construction Plan Activity 6: The mitigation measures are part of the Health Impact Assessment (HIA) A specific monitoring procedure for the construction works shall be presented to the Project Board. Activity 11 - 12 - 13 - 14 - 15 - 19: The study to identify the location must analyze different places based on a criteria matrix, such as: accessibility, security, no disturb landscape or other telecom instruments among others. The project coordinator will ensure that the government has technician in the area and train them to used and maintain the radar. This condition is mandatory to guarantee the sustainability of the action. | Monitoring plan for pollution prevention and resource efficiency developed | 0 Monitoring plan for pollution prevention and resource efficiency | Ecuador: Workshops have been held with the community to explain the importance of weather stations and the early warning system and the importance of their care. Chile: The studies to update the infrastructure works in Antofagasta were completed. As part of the studies, the need to implement a pollution prevention plan is indicated. Meteorological stations and Early Warning System equipment to be installed by 2023 | Not identified | Not identified
13 – Public health |  |  | Risk: The project designed and implemented in a way that produces potentially significant negative impacts on public health. Like any common infrastructure work, there is a low probability risk of collapse, especially during the period of construction and if a hazard materialized during this period, hazards such as: heavy rains, earthquake. Impact: Community – public health affected in noise or air pollutants. | This risk is activated once the grey infrastructure works are carried out in Esmeraldas and Antofagasta. In this reporting period, no safeguard measures have been required Safeguard measures identified in the PRODOC: Activity 5 - 6: A Health Impact Assessment shall be presented to the Project Board. Approval of the HIA. The operational contractor team in Chile and Ecuador shall be formed responsible for the control of all project related to Public Health and will: • Develop an Occupational Health and Safety Management Protocol. • Consider the routine and non-routine activities of the organization to be sure all of them are coordinated. • Beware how all persons accessing the work place including contractors and visitors (clothing, signals, helmets, etc.). • Bear in mind the human behavior, capabilities and other human factors that could increment the potential failure of structural elements of the Project. • Take into consideration how the operational contractor control threats created near the workplace during work -related activities. • Keep in mind how the infrastructure, equipment and materials at the workplace affects construction works. • Consider how the organization identifies changes or proposed changes to its activities or materials it uses. • Consider how modifications to the OH&S protocol / system, whether they be temporary or not, impact on the operations, processes and activities of the organization. • Consider how the project identified legal requirements for health and safety of persons beyond the immediate workplace, including those who are exposed to the workplace activities. • Consider the effects of the design of work areas, processes, installations, machinery/equipment, operating procedures and work project, including their adaptation to human capabilities. | Occupational Health and Safety Management Protocol developed | 0 Occupational Health and Safety Management Protocol developed | In this reporting period, no safeguard measures have been required. | Not identified | Not identified
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, the process of substantial changes approved in April 2022 included the improvement of the bridge that connects Roberto Luis Cervantes Island with the mainland and serves as a flood evacuation route on Luis Vargas Torres and Roberto Luis Cervantes Islands. Since this is a new activity, it was not part of the ESMP, so the environmental and social risk compliance analysis was conducted and the following risks were identified: 1. The inhabitants of the area will temporarily have limited free circulation on the bridge during the reinforcement works (estimated three months). 2. Men or women in the community do not have the same opportunities to participate in the socialization workshops, because their work schedules or lifestyles are not considered. 3. The workers at the construction site could have an occupational accident during the construction process of the bridge reinforcement. 4. Temporary disruptions to the free movement of people have been identified during the reinforcement works, which could temporarily affect the livelihoods of the population in the area.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | Risk 1. - Socialization through workshops and implementation of a communication and public education strategy. - The population will be adequately informed and the alternate exit route to the mainland will be signaled. - Other measures may be implemented to mitigate the impact, especially aimed at vulnerable populations, such as: availability of transportation. Risk 2. - Dissemination of the proposal to reinforce the pedestrian bridge in participatory workshops with the beneficiary community, including an equal number of men and women, taking into account work schedules and different lifestyles and needs. - The measures established to minimize the impact of accessibility restrictions on the bridge will be monitored during construction to minimize any specific impact on women and vulnerable groups. Risk 3. - The contracted construction company will be responsible for the preparation and correct application of the occupational risk management plan throughout the construction process. - The contracted supervisor will oversee the application and compliance with the occupational risk management plan throughout the construction process. Risk 4. - Socialization and temporary signage of alternate routes and travel times. - To minimize this impact, a prior communication process will be carried out with the residents of Roberto Luis Cervantes Island and transportation will be offered in specific cases of vulnerable groups. Considering the identified risks and mitigation measures, the ESMP has been updated.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | CAF has formally informed all Responsible Parties about the ESMP and potential risks to Environmental and Social Safeguards.
Have the implementation arrangements been effective during the reporting period? |  | Yes, CAF has ensured that the Responsible Parties are aware of the identified safeguards and mitigation measures, as well as targeted assessments identified in the ESMF.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | UNDP has regularly monitored the risks identified and the safeguard measures in the reporting period. UNDP has promoted events to socialize with the beneficiaries the developed activities. In addition, it has ensured the equitable participation of men and women in all events.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. All of this year's safeguard measures were successfully implemented. The events carried out by the project considered a gender approach
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8] |  | Once the studies for updating the infrastructure works in Antofagasta are available, the analysis of compliance with the Social and Environmental Policies of the Adaptation Fund has been carried out. The other USP implementation agreements will be made in the following year once the documents updates for the gray infrastructure works are in place.
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | All positions required for the fulfillment of the ESMP are clearly identified and responsibilities are assigned. - CAF as IE has in the Climate Action and Positive Biodiversity Management the team of Environmental and Social Evaluation and Monitoring Coordination (CESAS) which are in charge of all the Environmental and Social Safeguards. Additioinally CAF has the Ethical Committee which is in charge to help solve the grievance developed during the implementation. In addition, it will verify that the ESMP is updated as compliance with the USPs initially established is resolved. - UNDP as EE is implementing the actions established in the ESMP. For this purpose it has a technical work team comprised of a M&E regional technician with specific functions assigned to comply with. In the case of USPs identified in the Project Document or new activities that have not been included in the ESMP, UNDP has been analyzing to comply with the 15 environmental and social principles and clear mitigation measures has been implemented.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | The ESMP has been updated considering the information from the Installation of automatic meteorological stations in the watersheds of Antofagasta and Taltal
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Installation of automatic meteorological stations in the watersheds of Antofagasta and Taltal | Yes | It has been identified that in the areas surrounding the construction sites, there is a larger population of women, and due to their social conditions, they may be affected by the construction work. There is a risk that workers who are working on the construction site may suffer some type of accident during the course of construction, or due to a possible accident, rain, and/or earthquake that may occur during the construction period. The generation of waste and pollutants during the construction of the alluvial control infrastructure. | Yes | Appropriate consultations have been carried out during the identification of risks and impacts for this activity with the respective technical institutions in Chile and with the local population of the communities near the construction sites that will benefit from this activity. The grievance mechanism has been socialized | Yes | Dissemination of the construction program, presentation of the construction plan and dissemination of the importance of landslide control works to save lives in the event of a climatic event. Women's roundtables will be held to train women in disaster risk reduction and the importance of flood control works. The contracted construction company will be responsible for the development and proper implementation of a risk management plan throughout the construction process. It will be requested in the bidding process of the work. The contractor must comply with what is indicated in the Environmental Relevance Report and in accordance with the Updated Applicable Environmental Regulations described in said report, which indicates the respective subject matter to be contaminated and the manner of compliance. The contractor shall submit the construction plan and specific monitoring procedure for the construction works including: - Water consumption. - Fuel consumption. - Type of fuel consumption. - Raw material consumption. - Energy consumption. - Solid waste generation. - Wastewater / generation (wastewater quality). - Construction waste/debris generation. | Number of grievances received related to problems of access to basic services Number of grievances received related to problems of violation of labour rights Monitoring plan for pollution prevention and resource efficiency developed
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances were filed during the reporting period. |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Men and women protected by improved risk-reduction measures | Objective | Number of men and women protected by improved risk-reduction measures in Antofagasta, Taltal and Esmeraldas. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | End of project Antofagasta = 362,000 (ca., 50% women) Taltal = 13,000 (ca., 50% women) Esmeraldas = 161,000 (ca., 50% women) | Satisfactory. A Storm Detection System is already in operation in Chile, protecting the population of Antofagasta and Taltal as an enhanced risk reduction measure. A Green Infrastructure Plan for Esmeraldas was developed. Thirteen meteorological stations are in operation in the low and middle in the Esmeraldas river basin in Ecuador.
Plans that incorporate provisions for adaptation to climate change with gender perspective. | Outcome | Number of plans that incorporate provisions for adaptation to climate change with gender perspective. | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 0 | Mid-term: 1 End of project: 2 | Satisfactory In Chile, the Stormwater Management Plan for Antofagasta has already been developed. In Ecuador, the Green Infrastructure Plan has already been developed. Both plans incorporate a gender approach
Men and women protected by improved infrastructure | Outcome | Number of men and women protected by improved infrastructure | Antofagasta = 0 Esmeraldas = 0 | End of project: 12,840 Antofagasta = (ca., 50% women) Esmeraldas = 500 (ca., 50% women) | Poor Men and women will be protected by green and gray infrastructures only at the end of the project. Implementation is in place.
Men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), landslides (Esmeraldas) and mudflows (Antofagasta and Taltal) | Outcome | Number of men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), and mudflows (Antofagasta and Taltal) | Antofagasta = 0 Taltal = 0 Esmeraldas (floods) = 0 | Antofagasta = 362,000 people (ca., 50% women) Taltal = 13,000 people (ca., 50% women) Esmeraldas (floods) = 161,000 people (ca., 50% women) | Satisfactory. In Ecuador, signage was designed, developed and installed for evacuation routes in the event of flooding on Luis Vargas Torres Island. In Chile, evacuation maps have been designed and socialized with the beneficiaries. The installation of the signage will be completed by 2023.
The early warning systems in Antofagasta, Taltal, Cerro Gatazo and Isla Luis Vargas Torres are gender and culturally sensitive and consider the special needs of persons with disabilities. | Outcome | Number of early warning systems | Number of early warning systems Antofagasta = 0 Taltal = 0 Isla Luis Vargas Torres = 0 | Three early warning systems are gender and culturally sensitive and consider the special needs of persons with disabilities. | Satisfactory In Ecuador, the Early Warning System against floods has already been developed. The equipment for the Early Warning System has been purchased and installed. The EWS is currently in the technical testing phase. In Chile, an agreement was signed with ONEMI to proceed with the implementation of the Early Warning Systems. The development of the EWS in Antofagasta was carried out with the support of ONEMI. The equipment will be purchased next year.
Staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Outcome | Number of staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Cities in Chile = 0 Cities Ecuador = 0 | Cities in Chile = >70 Cities Ecuador = >30 About 40% will be women | Satisfactory The Disaster Risk Management and Climate Change Adaptation course was designed and implemented. The course was given by Universidada de Chile. Seventy students from Chile and Ecuador graduated (46% women)
Men and women who have participated in awareness activities and events. | Outcome | Number of men and women who have participated in awareness activities and events. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = >30,000 (ca., 50% women) Taltal = >1,000 (ca., 50% women) Esmeraldas = >16,000 (ca., 50% women) | Satisfactory Several activities were carried out in compliance with the communication and public education strategies: - Women's roundtables were held in Esmeraldas, Antofagasta and Taltal to strengthen women's capacities to face climate risks. - Launching of risk management education products at the Zicosur 2022 International Book Fair in Chile - Puppet shows in several educational institutions in Antofagasta and Taltal to raise awareness of the floods - A traditional song contest in Esmeraldas - Workshops for university and high school students on climate risks, so that they can replicate the knowledge acquired. - Radio spots in Antofagasta, Taltal and Esmeraldas to raise public awareness of climate risks - Creation of 5 murals on climate risks and adaptation to climate in representative sites in Esmeraldas.
Narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Outcome | Number of narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 10 (ca., 50% women) Taltal = 5 (ca., 50% women) Esmeraldas = 10 (ca., 50% women) | Satisfactory 13 storytellers from Esmeraldas (62% women), 16 from Antofagasta (38% women) and 14 from Taltal (71% women) were selected, far exceeding the planned goal. The narrators' stories were recorded and will be uploaded to the project's virtual platform. In Esmeraldas a "Arrullos" contest was held with students from 9 educational institutions that raise awareness about climate risks in the city
Men and women who have participated in events for dissemination of lessons and best practice (e.g., workshops, exchange visits, seminars) | Outcome | Number of men and women who have participated in events for dissemination of lessons and best practice | 0 | Mid-term >100 people > 50% women End of project: >200 people > 40% women | Satisfactory The first exchange of experiences between public institutions of Ecuador and Chile related to climate monitoring, disaster risk management and adaptation to climate change took place. Socialization of the construction process of the Antofagasta Rainwater Master Plan was carried out. A regional webinar on resilient infrastructure was held with the participation of speakers from different countries.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | During the reporting period, CAF ensured socialice the importance of compliance the gender policy.
Have the implementation arrangements at the IE been effective during the reporting period? |  | All activities implemented by the project have a strong gender approach.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | UNDP has ensured the equitable participation of men and women in all events carried out. Training to the project team on its policy of Prevention of Sexual Exploitation and Abuse. In addition, as part of the communication and education strategy, territorial women's groups were created to strengthen the management and participation of women as key actors in climate risk management.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. All the events carried out by the project considered a gender approach. In addition, there is an important participation of women in the different workshops and events carried out by the project.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints related to gender equity and women's empowerment have been received
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating | Status
Implementing Entity: | Outcome 1. Enhanced plans and green infrastructure reduces vulnerability to floods, landslides and mudflows in three coastal cities |  | Outcome 4 | - Update Stormwater Management Plans to cope with climate-related mudflows in Antofagasta - Implementation of the Green Infraestructure course. Version 2 - Approval of municipal ordinance for implementation of the Green Infrastructure Plan - Reforestation in the urban and peri-urban sector of the city of Esmeraldas |  | Regarding the Outcome 1: The activities planned for the third year have been 90% completed. The Green Infrastructure Plan for Esmeraldas was approved by municipal ordinance The desing of the version 2 of the green infrastructure course was successfully completed. Reforestation activities could not be carried out during this period due to insecurity problems in the city of Esmeraldas. In Chile, the Stormwater Management Plan was satisfactorily finalized and widely socialized. The methodology used in this plan constitutes a reference for other plans at the regional level in the sense of including the climate variable in the plan. | HS | On track
| Outcome 2. Reduced vulnerability to floods, landslides and mudflows in two coastal cities |  | Outcome 4 | - Update of the designs of mudflow control infrastructure in Quebrada Bonilla. - Update of the designs of the landslide control infrastructure works in Cerro Gatazo. |  | Regarding the Outcome 2: The design update of the infrastructure works are almost ready. The final designs of the works are currently under review. The launching of the storm visualization platform was carried out and installed in the DMC premises at the central level. Due to insecurity issues in Esmeraldas, it was not possible to update the design of the infrastructure works in Cerro Gatazo There is a pre-feasibility project for the implementation of green infrastructure in Cerro Gatazo | S | Delayed
| Outcome 3. Improved climate monitoring and means to alert the local population |  | Outcome 1 | - Storm detection system contract for Antofagasta and Taltal - Meteorological stations in Antaofagasta and Taltal - Strengthening of the hydro-meteorological network in Esmeraldas - Monitoring and control of the climate network of Esmeraldas. - Real-time visualization platform for Esemaldas weather stations. |  | Regarding the Outcome 3. The Storm Detection System for Antofagasta and Taltal is currently up and running and is providing weather information. Eight sensors installed in the northern region of Chile to improve data accuracy. DMC technical personnel were trained in the operation of the system. Meteorological stations were acquired for Antofagasta and Taltal to be installed in 2023 In Ecuador, new (8) and upgraded (5) stations are operating. INAMHI is the institution in charge of the stations. The project has also supported INAMHI in monitoring and controlling the meteorological stations in Esmeraldas. It has also supported the development of mobile applications to warn of possible floods. | HS | On track
| Outcome 4. Improved means to respond to floods, landslides and mudflows |  | Outcome 1 | - Early Warning System in Antofagasta and Taltal - Implementation of the Early Warning System in Esmeraldas. - Evacuation route maps and signs in Antofagasta, Taltal - Improvement of the evacuation route of Luis Vargas Torres Island in case of flooding. |  | Regarding the Outcome 4. In Chile, the project signed an agreement with ONEMI to work on the Early Warning System for Antofagasta and Taltal. At present, the EWS design and evacuation routes are in place. The equipment and signage will be installed in 2023. In Ecuador, equipment for the Early Warning System against floods was installed on Luis Vargas Torres Island. Technical tests are currently being carried out to guarantee its correct operation. The drill planned for this year could not be carried out due to the lack of safety conditions. The decision was taken by the Municipality of Esmeraldas and the SNGRE. Also, the designs for the bridge that connects Roberto Luis Cervantes Island with the mainland were updated and discussed with the beneficiaries. Due to safety conditions, it was not possible to move forward with the bridge improvement works. Strategies are being analyzed to carry out this activity in 2022. | S | On track
| Outcome 5. Local governments with improved capacity to design and implement adaptation measures |  | Outcome 2 | - Course on risk-based adaptation in coastal cities |  | Regarding the Outcome 5. The course was implemented by Universidad de Chile, who developed the syllabus with 4 modules. The virtual classes began on May 24, 2022 and culminated on August 31, 2022 with a virtual graduation ceremony. 70 students were beneficiaries, 32 from Ecuador and 38 from Chile. | HS | On track
| Outcome 6. Local population and government personnel with increased awareness of climate-related risks (floods, landslides, mudflows) |  | Outcome 3 | - Implementation of public education and communication strategy for Antofagasta, Taltal and Esmeraldas - Implementation of the narrators' initiative in Antofagasta - Taltal and Esmeraldas |  | Regarding the Outcome 6. Various activities were carried out in compliance with the communication and public education strategies. The following activities are highlighted - Women's roundtables were held in Esmeraldas, Antofagasta and Taltal to strengthen women's capacities to face climate risks. - Launching of risk management education products at the Zicosur 2022 International Book Fair - Puppet shows in several educational institutions in Antofagasta and Taltal to raise awareness of the floods - A traditional song contest in Esmeraldas - Workshops for university and high school students on climate risks, so that they can replicate the knowledge acquired. - Radio spots in Antofagasta, Taltal and Esmeraldas to raise public awareness of climate risks - Creation of 5 murals on climate risks and adaptation to climate in representative sites in Esmeraldas. As for the narrators' strategy, videos were recorded with the stories of the selected people in the three cities. The videos will be available on the web. The virtual platforms that will host the videos are currently being developed. | HS | On track
| Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region. |  | Outcome 8 | - Development of the project's web platform - Exchange of experiences between Ecuador and Chile - Production videos, images and other communication media for the project´s web platform and news. |  | Regarding the Outcome 7. The project's website is up and running A regional webinar was held on experiences in resilient infrastructure. Speakers from Chile, Ecuador and CAF participated in the event. A technical team from the Ecuadorian project and partner institutions visited Chile to learn about its experience in environmental policies, climate monitoring and disaster risk management. Several videos were made to socialize project activities and promote awareness among the population of Antofagasta, Taltal and Esmeraldas. | HS | On track
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Carolina Cortes
| Email: | acortes@caf.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
As the implementing agency, the actions of the project have been followed up through periodic meetings with the ministerial teams of Ecuador and Chile as well as with UNDP Ecuador and Chile and the respective project teams. Likewise, and according to the implementation mechanisms, two meetings were held with the National Technical Committees (one in Ecuador and one in Chile), where the programming for each semester and the Procurement Plan and the progress to date were shared. The meetings in Ecuador were virtually on February 10th, 2022 and on August 18th, 2022. The meetings in Chile were virtually on March 2nd, 2022 and July 7th, 2022 . After the National Committees, the fifth and sixth Steering Committees were held on March 4th, 2021 and July 20th, 2021 respectively. During this period, the activities carried out by the project team in Chile and Ecuador have progressed satisfactorily, fulfilling most of the planned activities. Important events such as the webinar on resilient infrastructure or the exchange of experiences between the two countries counted with the direct participation of CAF. It is also important to highlight milestones achieved, such as the updating of the Antofagasta rainwater master plan, the updating of the designs of the Antofagasta flood control works, the operation of the Esmeraldas hydrometeorological network, the Early Warning System against floods on Luis Vargas Torres Island, the course on Disaster Risk Management and Climate Risk Adaptation, and other activities framed within the communication and public education strategies to raise awareness of climate risks among the population. It is important to note that in Esmeraldas there is a complicated situation related to the increase in violent acts carried out by organized crime. Several face-to-face activities such as workshops or work with the community have had to be cancelled due to the lack of security guarantees. This implies a delay in important planned activities such as the update of the designs for the landslide control work in Cerro Gatazo and reforestation activities. In turn, this delay will affect compliance with the project's deadline, so a request will be submitted for an extension of the project's deadline.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1. Enhanced plans and green infrastructure reduces vulnerability to floods, landslides and mudflows in three coastal cities |  | Outcome 4 | - Update Stormwater Management Plans to cope with climate-related mudflows in Antofagasta - Implementation of the Green Infraestructure course. Version 2 - Approval of municipal ordinance for implementation of the Green Infrastructure Plan - Reforestation in the urban and peri-urban sector of the city of Esmeraldas |  | The Stormwater Management Plan has been satisfactorily completed, meeting the deadlines established at the beginning of the study. In addition, a study socialization day was held with the project partners, counterparts and interested entities, showing the main results, findings and recommendations. Version 2 of the Green Infrastructure course has been developed and is ready for implementation through the Learning for Nature global platform. The course will start in February 2023 Approval of the Green Infrastructure Plan by the Esmeraldas Municipal Council through an ordinance. The process for the award of the reforestation activities was declared void due to the absence of bidders. It is possible that no bids were submitted due to insecurity conditions in Esmeraldas. | HS
| Outcome 2. Reduced vulnerability to floods, landslides and mudflows in two coastal cities |  | Outcome 4 | - Update of the designs of mudflow control infrastructure in Quebrada Bonilla. - Update of the designs of the landslide control infrastructure works in Cerro Gatazo. |  | The update of the designs of the mudflow control infrastructure in Quebrada Bonilla, comprising 5 stages. At the moment it is in the last design stage. The proposed works were designed to meet the requirements to withstand climatic events associated with a return period of 100 years quantified with climate change projections (scenario RCP8.5). Stage 5 is currently under review. Due to insecurity issues in Esmeraldas, it was not possible to update the design of the infrastructure works. Instead, with the authorization of the Steering Committee, a pre-feasibility study of 4 sub-projects of the Esmeraldas Green Infrastructure Plan are being carried out. | S
| Outcome 3. Improved climate monitoring and means to alert the local population |  | Outcome 1 | - Storm detection system contract for Antofagasta and Taltal - Meteorological stations in Antaofagasta and Taltal - Strengthening of the hydro-meteorological network in Esmeraldas - Monitoring and control of the climate network of Esmeraldas. - Real-time visualization platform for Esemaldas weather stations. |  | The Storm Detection System was contracted and is now operational. Eight sensors were installed to support the Storm Detection System, which allowed the system's reach to be extended. Eight training sessions have been held for the professional teams of the Chilean Meteorological Directorate. On November 10, the official launching and delivery of the visualization platform of the storm and lightning detection system to the DMC took place, which will strengthen the early warning system in the northern part of the country. The meteorological stations for Antofagasta and Taltal were acquired. They will be installed in 2023. In Ecuador, the five repowered stations and eight new stations are in operation. This year, scheduled maintenance has been performed on the stations. In addition, an agreement has been signed between UNDP and INAMHI to strengthen climate monitoring in Ecuador. Support to INAMHI to generate alerts of failures in meteorological station equipment and request maintenance. In addition, as part of the support to INMAHI, an application is being developed to generate alerts via Telegram and email on floods in the rivers of the Esmeraldas basin. Likewise, a hydro-meteorological viewer is being developed, where the information from the stations can be viewed in real time, as well as data from historical records. As part of the compromises assumed by the project, discharge curves were generated for the hydrological stations in the middle and lower basin of the Esmeraldas River. | MS
| Outcome 4. Improved means to respond to floods, landslides and mudflows |  | Outcome 1 | - Early Warning System in Antofagasta and Taltal - Implementation of the Early Warning System in Esmeraldas. - Evacuation route maps and signs in Antofagasta, Taltal - Improvement of the evacuation route of Luis Vargas Torres Island in case of flooding. |  | An agreement was signed with ONEMI for technical cooperation, where the institution will provide the required support for the implementation of the Early Warning System and the generation of maps and evacuation routes in Antofagasta and Taltal. The design of the evacuation maps was developed with the support of ONEMI. In Ecuador, the Early Warning System against floods has already been developed. The equipment for the Early Warning System has been purchased and installed. The EWS is currently in the technical testing phase. Due to insecurity conditions in the city of Esmeraldas, it was not possible to carry out the first drill with all the inhabitants of the island in October 2022. On the other hand, structural evaluation and design update of the pedestrian bridge linking Roberto Luis Cervantes Island with the mainland, one of the main evacuation routes of the early warning system against flooding of Luis Vargas Torres Island. A first socialization with the beneficiary community took place in October. In November 2022, an expression of interest was requested from construction companies interested in participating in the construction of the work; however, no bids were received, given the difficult context of the city of Esmeraldas due to the presence of criminal groups. | S
| Outcome 5. Local governments with improved capacity to design and implement adaptation measures |  | Outcome 2 | - Course on risk-based adaptation in coastal cities |  | The diploma course implemented by the University of Chile began in May. Seventy participants graduated from the course, 38 professionals from Chile and 32 from Ecuador, mostly public officials from local and national governments. | S
| Outcome 6. Local population and government personnel with increased awareness of climate-related risks (floods, landslides, mudflows) |  | Outcome 3 | - Implementation of public education and communication strategy for Antofagasta, Taltal and Esmeraldas - Implementation of the narrators' initiative in Antofagasta - Taltal and Esmeraldas |  | The following activities were carried out in relation to the communication and public education strategy: - First cycle of training to more than 40 women from the city of Antofagasta and Taltal. - Educational products were launched at the XI International Book Fair Zicosur 2022, held in Antofagasta. - In Antofagasta, 4 sessions of citizen participation processes were held to present the progress of the design of the Quebrada Bonilla alluvial control project. - There was a discussion on climate change and floods; "La Ruta: Conociendo y Aprendiendo sobre aluviones" (The Route: Knowing and Learning about Floods); and a puppet show ¿Qué un aluvión? - A traditional song contest in which 9 educational institutions in Esmeraldas participated. - Training workshops and community activities for vector control during the winter season in Esmeraldas. - Creation of 5 murals on climate risks and adaptation to climate change on school walls and representative sites in the city of Esmeraldas. - Implementation of the women's roundtable and training in Esmeraldas. - Training workshops on climate change and climate risks with students from PUCE Esmeraldas. - Train-the-trainer workshop on climate change and climate risks with students from the Luis Vargas Torres University. - Interactive fairs on climate change and climate risks with 8 educational units in the city of Esmeraldas. - Radio spots on two of the most popular radio stations in the city of Esmeraldas, with topics on flood and landslide risk prevention and climate change adaptation measures. As for the narrators' strategy, in both Ecuador and Chile, narrators were selected and videos of their experiences were recorded, which will be posted on the virtual narrators' platform that is currently being designed. | HS
| Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region. |  | Outcome 8 | - Development of the project's web platform - Exchange of experiences between Ecuador and Chile - Production videos, images and other communication media for the project´s web platform and news. |  | The project's web page is up and running and allows the socialization of project activities. In addition, social networks on Twitter and Facebook were created to share the activities carried out and a quarterly newsletter is issued. Resilient infrastructure webinar in which lessons learned from the Esmeraldas Green Infrastructure Plan and the Antofagasta Rainwater Master Plan were shared. The first face-to-face exchange of experiences between Ecuador and Chile took place. During the meeting, experiences related to environmental policies, disaster risk management and climate monitoring were shared. Several socialization and awareness-raising videos on climate risks and the activities developed by the project have been produced. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Nury Bermudez
| Email: | nury.bermudez@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has been successfully implemented in the third year, according to the planned activities. This has been possible, thanks to the sustained work of the entire project team, both in Chile and Ecuador, the ongoing supervision of CAF and UNDP offices in the respective countries and, of course, the accompaniment of the Ministries of Environment. Other key players in achieving the results are, at the national level, the Municipality of Esmeraldas, SNGRE and INAMHI in Ecuador. In Chile, SENAPRED, MOP and the DMC. At the local level, the commitment of the technicians of the municipalities of Esmeraldas, Antofagasta and Taltal, help the intervention to move forward as planned. Among the most relevant milestones in the reporting period are: In Esmeraldas, the pproval of green infrastructure plan by the Esmerladas cantonal council, the operation of the Esmeraldas meteorological network, the installation of the EWS, the updating of the design of the bridge that serves as a flood evacuation route on Luis Vargas Torres Island. In Chile: the installation of sensors to enable the operation of the Storm Detection System, the acquisition of weather stations for Antofagasta and Taltal, the update of the Antofagasta Rainwater Master Plan and the update of the design of the Antofagasta alluvial control works. In addition, regional activities included a webinar on resilient infrastructure, the exchange of experiences between Ecuador and Chile, and the launch of the project's web platform and social networks to socialize the project's activities and raise awareness of climate risks among the population. Finally, in both countries, storytellers were selected to share their experiences of past climate events. It is important to mention that during the current reporting period, issues of concern to the project have arisen that may imply an extension of the project completion time. On the one hand, in Chile, in the area where the flood control works will be built, there is an irregular settlement of sandpits that could hinder the start of the works. On the other hand, in Esmeraldas there has been an exponential increase in violence caused by organized crime in the city, causing several partners and the national police not to want to carry out activities in the territory. This has halted activities such as reforestation in urban and peri-urban areas, the start of work to improve the bridge that serves as an evacuation route on Luis Vargas Torres Island, and the updating of studies for infrastructure works on Cerro Gatazo. Despite the difficulties, the project has made significant efforts to move forward with the planned activities and is exploring different alternatives to meet the proposed goals.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | Number of men and women protected by improved risk-reduction measures in Antofagasta, Taltal and Esmeraldas. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 362.000 (ca., 50% women) Taltal = 13.000 (ca., 44% women) Esmeraldas = 161,000 (ca., 50% women) | End of project Antofagasta = 362,000 (ca., 50% women) Taltal = 13,000 (ca., 44% women) Esmeraldas = 161,000 (ca., 50% women)
Outcome 1 | Number of plans that incorporate provisions for adaptation to climate change with gender perspective. | Stormwater management plan Antofagasta = 0 Green infrastructure plan Esmeraldas = 0 | Stormwater management plan Antofagasta = 1 Green infrastructure plan Esmeraldas = 1 | 2
Outcome 1 | Number of hectares restored/revegetated in Esmeraldas | Esmeraldas = 0 | Esmeraldas = 0 | End of the project 40 ha restored/ revegetated
Outcome 2 | Number of physical assets constructed to withstand conditions resulting from climate variability and change. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 0 Esmeraldas = 0 | 2
Outcome 2 | Number of men and women protected by improved infrastructure to withstand climate change and variability-induced stress. | Antofagasta = 0 Esmeraldas = 0 | Antofagasta = 0 Esmeraldas = 0 | 12,840 Antofagasta = (ca., 50% women) Esmeraldas = 500 (ca., 50% women)
Outcome 3 | Number of and Storm detection system in Antofagasta to monitor precipitation, linked to gender-sensitive early warning systems. | Antofagasta = 0 | Antofagasta = 1 | Antofagasta = 1
Outcome 3 | Number of meteorological stations to monitor precipitation which affect the cities, linked to gender-sensitive early warning systems. | Antofagasta = 4 Taltal = 1 Esmeraldas = 5 | Antofagasta = 4 Taltal = 1 Esmeraldas = 13 | Antofagasta = 6 Taltal = 2 Esmeraldas = 13
Outcome 4 | Number of men and women covered by alert and evacuation route signs to respond to floods (Esmeraldas), and mudflows (Antofagasta and Taltal) | Number of people Antofagasta = 0 Taltal = 0 Esmeraldas (floods) = 0 | Number of people Antofagasta = 0 Taltal = 0 Esmeraldas (floods) =161,000 people (ca., 50% women) | Antofagasta = 362,000 people (ca., 50% women) Taltal = 13,000 people (ca., 44% women) Esmeraldas (floods) = 161,000 people (ca., 50% women)
Outcome 4 | The early warning systems in Antofagasta, Taltal, and Isla Luis Vargas Torres are gender and culturally sensitive and consider the special needs of persons with disabilities. | Number of early warning systems Antofagasta = 0 Taltal = 0 Isla Luis Vargas Torres = 0 | Number of early warning systems Antofagasta = 0 Taltal = 0 Isla Luis Vargas Torres = 1 | Three early warning systems are gender and culturally sensitive and consider the special needs of persons with disabilities.
Outcome 5 | Number of staff (men and women) of local governments and pertinent entities trained on risk-based adaptation with a gender perspective in coastal cities. | Chile = 0 Ecuador = 0 | Chile = 38 Ecuador = 32 46% women | Cities in Chile = >70 Cities Ecuador = >30 About 40% will be women
Outcome 6 | Number of men and women who have participated in awareness activities and events. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 29.389 (58% women) Taltal = 15.762 (53% women) Esmeraldas = 44,864 (50% women) | Antofagasta = >30,000 (ca., 50% women) Taltal = >1,000 (ca., 50% women) Esmeraldas = >16,000 (ca., 50% women)
Outcome 6 | Number of narrators (men and women) trained to maintain cultural memory of climate-related disaster and risks. | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 16 (38% women) Taltal = 14 (71% women) Esmeraldas = 13 (62% women) | Antofagasta = 10 (ca., 50% women) Taltal = 5 (ca., 50% women) Esmeraldas = 10 (ca., 50% women)
Outcome 7 | Number of men and women (by nationality) who have participated in events for dissemination of lessons and best practice (e.g., workshops, exchange visits, seminars)* | Antofagasta = 0 Taltal = 0 Esmeraldas = 0 | Antofagasta = 109 (65%) Taltal = 0 Esmeraldas = 31 (48% women) Otro =75 | >200 people > 40% women
Outcome 7 | Number of visitors per month (annual average) recorded in the network of electronic channels of the regional on-line platform used to disseminate project´ learnings and best practice** | Visits 0 Unique visits 0 | Visits = 21733 Unique visits = 21654 | Visits >4000 Unique visits >3200
* Participation of people in a webinar on resilient infrastructure is included. No information on the city of the webinar participants is available. **Includes information from the project's social networks (facebook and twitter). In social networks it is not possible to determine the number of unique visits.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The signing of technical cooperation agreements with partners such as INAMHI in Ecuador and ONEMI in Chile has enabled excellent progress to be made in climate monitoring and risk management, respectively. The support received has been fundamental to achieving the goals planned for this period. The main problem faced by the project this year has been the increase in crime in Esmeraldas, which has hindered the implementation of several important activities. | Challenges and Opportunities
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During the current period, delays are mainly due to the high level of crime in Esmeraldas. Activities such as updating the design of the landslide control works at Cerro Gatazo, the reforestation process in urban and peri-urban areas of Esmeraldas, and the bridge improvement works have been paralyzed because there are no bidders to carry out these activities. In view of this situation, the project is analyzing different alternatives, including signing agreements with institutions that have easier access to certain areas in the territory and can carry out the work, such as the Army Corps of Engineers and the Caritas Foundation. | Challenges
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Output 1.2 The Green Infrastructure course was improved and placed on the Learning for Nature platform, which has global reach and will be available in English and Spanish. Output 4.1 With the signing of the agreement with ONEMI, technical support was obtained for the design of the EWS and evacuation signage. This made it possible to extend the installation of sirens to other locations such as Mejillones and Tocopilla, as well as Antofagasta and Taltal. Output 4.2 To complement the results of the Early Warning System against flooding on Luis Vargas Torres Island, it was decided to improve the bridge that connects the island with the mainland, which is one of the main evacuation routes. This activity was included as part of the Project Document amendment approved in april 2022. Output 6.2 The implementation of the narrators' route will be done virtually. People's experiences have been recorded and will be available on the project's platform, which will have a wider reach and will be available at any time. | Challenges and Opportunities
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. The project implement effective measures to avoid unwanted negative environmental and social impacts. Such as: 1. A communication and participatory strategy is now in place. 2. The active inclusion of the beneficiaries in the activities developed by the project, especially in cases such as the Antofagasta rainwater master plan, the updating of the designs of the Antofagasta flood control works or the improvement of the bridge as a flood evacuation route on Luis Vargas Torres Island. 3. A grievance mechanism is now in place and the communities and beneficiaries has been informed about the process to follow. | Opportunities
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Yes, gender considerations has been put in place, such as: 1. Participatory and inclusive approach in all the workshops, events and trainings has been incorporate in the project execution. 2. The project team is gender balance 3. Public communication strategy to empower and engage local communities is in place. 4. Training of territorial women's roundtables to strengthen their participation in risk management issues in the communities. | Opportunities
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | - From the design stages, it is important to articulate the beneficiaries and the local and national government institutions that have jurisdiction over the activities to be implemented. This can mean important advances in the execution or important delays in the project. - Thanks to COVID-19, virtual activities were enhanced, which boosted activities such as virtual courses or the storytellers' platform. It is important to consider the potential of online tools for future projects. - Guarantee the sustainability of post-project actions is fundamental. Government support is essential to continue with the processes, as in the case of the Storm Detection System in Chile or the Esmeraldas meteorological network in Ecuador. - The disbursement mechanism between the executing and implementing agency must be very clear so that there are no delays in disbursements. - It is important to identify key activities that can be replicated in other areas and encourage the exchange of experiences. - Women play a very important role in the community in relation to risk management and climate change adaptation actions. It is important to strengthen their knowledge, skills and participation in the activities developed by the project.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Several of the activities implemented by the project to date have great potential for replication in other cities or regions. Such is the case of the Storm Detection Service contracted by the project. The scope and accuracy of the system surpasses similar systems used by the Chilean government. The project's experience will make it possible to expand this system to other areas of the country. Similarly, the inclusion of the climate variable in Antofagasta's rainwater master plan is a milestone in the country, as it is the first plan to include this future climate analysis. The methodology used has been shared with the MOP so that it can be replicated in plans for other cities. Likewise, the Esmeraldas Green Infrastructure Plan is the first planning instrument in Ecuador that includes concrete ecosystem-based adaptation measures focused on fostering adaptation to climate change. For its part, the narrators initiative has great potential to be replicated in other cities and with great impact. The project expanded the scope of this activity by also carrying it out virtually. The experiences narrated by the people will be available on the project's platform.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A at this stage
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A at this stage
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects / programmes implementing concrete adaptation interventions? | Among the lessons learned from the interventions carried out this year, the following could be highlighted: - In order to obtain the expected results, inter-institutional coordination and articulation with all the previously identified project partner institutions is required. It is also important to get to know new actors that can strengthen project management. This year, two agreements were signed with institutions such as ONEMI (Chile) and INMAHI (Ecuador) to carry out risk management and climate monitoring activities, respectively. -Another fundamental axis for a successful intervention corresponds to the active participation of the beneficiaries in all stages of the planned activities. Under this scenario, it is possible to understand the effectiveness of the participation of the people of Luis Vargas Torres Island in the activities carried out by the project aimed at reducing the risk of flooding. - When planning activities, it is important to consider the technical and financial capacity of the project's main partner institutions. In Chile, the situation of the governmental institutions has been good and has allowed joint and satisfactory progress in obtaining products such as the Early Warning System for Antofagasta, as well as the determination of evacuation routes. In Ecuador, even though the constraints of the public sector (budget and staff reduction) the counterparts has a high commitment with the project, following regularly the progress of each component. - In situations of strong social conflict, such as that experienced in Esmeraldas, it is possible to seek alliances with other institutions that may have a greater facility to intervene in danger zones. In the case of the project, an agreement is being analyzed with Caritas to implement activities of the communication and public education strategy.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Activities implemented during this period such as the Storm Detection Service or the Green Infrastructure Plan have a high potential to be replicated in other areas. -The contracted storm detection service has a greater range and accuracy than similar systems that have been contracted by the Chilean government. The positive results of this experience open the possibility of contracting the same service for other areas of the country. - The inclusion of the climate variable in Antofagasta's rainwater master plan is a milestone in the country, as it is the first plan to include this future climate analysis. The methodology used has been shared with the MOP so that it can be replicated in plans for other cities. -The narrators initiative has great potential to be replicated in other cities. It is an initiative that does not require major resources and has a significant impact on the population. In addition, it can be recorded and uploaded to the network to have a greater reach.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The beneficiaries have been very involved in the processes carried out by the project. They have participated in processes such as the rainwater master plan, the updating of the design of the landslide control works for Antofagasta, the installation of the hydrometerological network in Esmeraldas, the updating of the design of the bridge on Roberto Luis Cervantes Island, the installation of the Early Warning System on Luis Vargas Torres Island, and the installation of the Early Warning System on the island of Luis Vargas Torres. They have also participated directly in activities such as territorial roundtables, women's roundtables, traditional song contests, mural making, and the narrators' initiative, among others.
What measures are/have been put in place to ensure sustainability of the project/program results? | Close coordination with national and local level, with an important involvement in all the project´ decisions, through a National Technical Board and also bilateral meetings. Close understanding of the needs and constraints of each entity and open dialogues help to find the best mechanism and suitable solutions for the time been. This year, two agreements were signed with institutions such as ONEMI (Chile) and INMAHI (Ecuador) to carry out risk management and climate monitoring activities, respectively.
What measures are being/could have been put in place to improve project/program results? | Sign alliances with other institutions that may have a greater facility to intervene in danger zones. In the case of the project in Esmeraldas, an agreement is being analyzed with Caritas to implement activities of the communication and public education strategy, Pontificia Universidad Católica del Ecuador, Esmeraldas, for reforestation activities, and the Army Corps of Engineers for infrastructure works.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Official information, technical, legal documents and statistics data from public institutions were used to generate and develop different products. When necessary, additional information was gathered and analyzed, as in the case of the Rainwater Master Plan of Antofagasta or theupdating of the design of the landslide control works for Antofagasta. As primary source of information the people knowledge was also considered.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Relevant stakeholders are involved throughout the implementation. The project shares with them every consulting product. The dissemination channel this year was the project's web platform, the project's social networks and the quarterly newsletter that is shared with a large number of professionals and people linked to disaster risk management and climate change adaptation.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | • Virtual course on green infrastructure for coastal cities (https://www.learningfornature.org/en/courses/green-infrastructure/) • Antofagasta's Rainwater Master Plan (https://www.paiscircular.cl/ciudad/adaptaclima-presento-el-plan-maestro-de-evacuacion-y-drenaje-de-aguas-lluvias-de-la-ciudad-de-antofagasta/) • Storm Detection System (https://www.futuro360.com/videos/sistema-deteccion-cambio-climatico_20221111/) • Resilient Infrastructure Webinar (https://www.youtube.com/watch?v=NUuZh7A8OWM) • Installation of hydrometeorological stations in Esmeraldas (https://twitter.com/Adapta_Clima/status/1527300020273557504) • Early Warning System against floods on the island Luis Vargas Torres (https://twitter.com/Adapta_Clima/status/1536766489654591488) • Improvement of flood evacuation route on Luis Vargas Torres Island (https://twitter.com/Adapta_Clima/status/1537143249852407808) • Disaster Risk Management and Climate Change Adaptation course (https://adaptaclima.org/2022/09/08/ceremonia-de-titulacion-del-diploma-en-gestion-de-riesgos-de-desastres/) • Signing of the INAMHI - UNDP agreement (https://www.undp.org/es/ecuador/news/pnud-e-inamhi-fortalecer%C3%A1n-monitoreo-clim%C3%A1tico-del-pa%C3%ADs) • Disaster Risk Management and Climate Change Adaptation Course • Esmeraldas Narrators Initiative (https://twitter.com/Adapta_Clima/status/1540384016435912704) • Women Roundtables in Antofagasta and Taltal. (https://www.youtube.com/watch?v=swJRgZ9_ee0) • Elaboration of murals (https://twitter.com/adapta_clima/status/1531670633255403520?s=24&t=mp0cXF0oxygL2TcIxTL8uA) • Traditional songs contest on climate change (https://adaptaclima.org/2022/08/22/clausura-concurso-de-arrullos-sobre-riesgos-climaticos/) • University students will be trained as "Trainer of Trainers" on climate risks in Esmeraldas (https://adaptaclima.org/2022/07/18/formador-de-formadores-riesgos-cllimaticos/) • Antofagasta Landslide Commemoration (https://www.biobiochile.cl/noticias/artes-y-cultura/actualidad-cultural/2022/06/14/conmemoran-los-31-anos-del-aluvion-en-antofagasta.shtml) • Taltal Landslide Commemoration (https://www.undp.org/es/chile/news/pnud-en-actividad-regional-taltal-conmemora-aluvi%C3%B3n-de-2015-con-mirada-puesta-en-cambio-clim%C3%A1tico-0) (https://www.youtube.com/watch?v=eCIEKn3OU2U) • Exchange of experiences between Ecuador and Chile (https://adaptaclima.org/2022/09/30/intercambio-de-experiencias-en-adaptacion-al-cambio-climatico/) • Educational products - Filzic 2022 (https://termometro.cl/2022/06/25/medio-ambiente-y-urbanismo-destacaron-en-segunda-jornada-de-filzic-2022/) • Promotional video (https://bit.ly/3uVKNVQ ) • Community relationship (https://bit.ly/3ILdZVk ) • Newsletter (https://bit.ly/3PEGJkL) (bit.ly/3AxWMgh) (https://mailchi.mp/df610e634391/adaptaclimanewsletter-octubre)
If learning objectives have been established, have they been met? Please describe. | Yes, the Disaster Risk Management and Climate Change Adaptation course was designed and implemented. The course was given by Universidada de Chile. Seventy students from Chile and Ecuador graduated (46% women)
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | It has been difficult to obtain updated information from the land registry of Esmeraldas, which is important to advance with the design studies of the infrastructure work in Esmeraldas. The project scale up the need of this relevant info to the Esmeraldas Major and some mitigation measures are now in place.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, all the learning objectives of the project will contribute to the Outcome of the project and allow to scale-up the thematics in the region, thanks to the Component 3 Outcome 7. Lessons and best practice on reducing vulnerability to climate related flooding, landslides and mudflows in coastal cities have been shared in the region.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The Storm Detection Systems using satellite services provided by a international company is a very innovative way to count on more accurate information, giving the people more accurate meteorology prognosis of this area. The Antofagasta Rainwater Master Plan includes an analysis of climatic variables with 50-year projections, the first plan of its kind to include such an analysis.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Development Bank of Latin America (CAF)
Type of implementing entity | RIE
Country | Ecuador
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 537000 | 47000 | 490000 | Total | 523660 | 33660 | 490000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding | 2: Partially effective | Total | 47000 | Coastal flooding | 4: Effective | Total | 47000 | Coastal flooding | 4: Effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 3 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 1 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 100 | Disaster risk reduction | 4: High capacity | Total | 70 | Disaster risk reduction | 4: High capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted | 46% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 40% | Public |  | 70 | 46% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 50 |  | Disaster risk reduction |  | 71% |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 50% | 2: Partially not aware |  | 47000 | 50% | 4: Mostly aware |  | 33660 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 3: Moderately responsive (Some defined elements) |  | Disaster risk reduction | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness