# MONITORING ACTION AND STANDARD PROGRESS REPORT

# Support to Armenia’s Justice and Rule of Law Reforms: Phase 2

# 27 September 2021 – 31 December 2022

Contents

I.	Project overview	2

II.	Resources and financial performance	3

III.    Results	3

IV.    Gender mainstreaming, crosscutting results, targeting	7

V.	Risks, proposed changes to prodoc, horizon scanning, evaluation	8

VI.    Partnership. Communication and knowledge products	8

VII.   Validation of results (field visits). Quality assurance. Lessons learned. Project boards. Donor reports	9

VIII.  Future actions, work plan	10

IX.    Results framework	11

X.	Offline risk log	12

XI.    Annual/multiyear work plan and budget from prodoc  	13

Reporting Agency:	UNDP
Country:		Armenia

# MONITORING ACTION AND STANDARD PROGRESS REPORT

No. and title:		00121670 Support to Armenia’s Justice and Rule of Law Reforms: Phase 2

Reporting period:	27 September 2021 – 31 December 2022

# Project overview

- Present project’s goal, objectives, duration, theory of change, implementing partner, responsible parties, other critical information.

Project goal and objectives: In the framework of “Support to Armenia’s Justice and Rule of Law Reforms: Phase 2” Project (Project) UNDP Country Office (CO) supports the Government of Armenia (GoA) in its legal and judicial reforms to promote the rule of law, increase transparency and efficiency of justice and strengthen the anti-corruption ecosystem in Armenia. The project focuses on improving judge selection, establishing an arbitration and mediation centre, digitizing the legal and judicial field, promoting access to justice and developing the capacity of the patrol service. The project has a gender-responsive approach and aligns with the RoA Legal and Judicial Strategy 2019-2023, enabling UNDP to plan for medium and long-term support for Armenia’ reforms under three main areas:

- Integrity, independence and efficiency of the judiciary supported through national policies and new mechanisms in place.

- Access to justice improved through increased service orientation of the judiciary.

- Anti-corruption ‘’ecosystem’’ in the country improved and strengthened.

Duration: 27 September 2021 – 31 December 2022

Implementing partner: United Nations Development Programme

# Resources and financial performance

- Matrix showing project’s total, annual and delivered resources and percentage by donor funds.  Indicate amount of leveraged resources, even if a parallel funding.

| Donor | Total Project Budget | Current Year (2022) |  |  | All Years Delivery as of SPR date (USD) | All Years Delivery rate as of SPR date (%) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Annual Budget | Delivery as of SPR date (USD) | Delivery rate as of SPR date (%) |  |  |
| SIDA | 200,000 | 182,252.48 | 180,525.17 | 99% | 198,272.72 | 99% |
| Total | 200,000 | 182,252.48 | 180,525.17 | 99% | 198,272.72 | 99% |

# Results

- A snapshot of higher-level results: Present/discuss results vis-à-vis UNSDCF/CPD/UNDP SP, SDG outcomes, outputs, indicators, baselines, targets in line with Project Document (Prodoc) Results Framework (RRF). Update RRF in annex. Other important Project level achievements. Annual Work Plan: Present in below table a snapshot of the current year’s workplan (planned targets, resources, achievement status). Attach in annex the updated Multi-Year Work Plan or Annual Work Plan as relevant.

Results vis-à-vis UNSDCF, UNDP CPD, SDGs

| UNSDCF6/CP Outcome 3: People benefit from effective and accountable governance systems and institutions that safeguard human rights, uphold the rule of law, and public administration that ensures effective and human-centred service delivery for all. | Project’s contribution The continuous implementation of the psychological testing platform in the procedure of the selection of judge- candidates contributed to transparency and merit-based approach in the selection procedure. The transparency and efficiency of the judicial system and free legal aid mechanisms increased through provision of expert advice, capacity building and public awareness activities. |
| --- | --- |
| UNDP CPD Output 3.2: Capacities, functions and financing of rule of law, national human rights institutions/systems strengthened to protect human rights, expand access to justice and combat discrimination, with a focus on women and marginalized groups (IRRF 2.2.3). | Support provided for the establishment of the new Arbitration and Mediation Center of Armenia (AMCA) significantly contributed towards improving the efficiency of the judiciary and access to justice in Armenia. |
| Sustainable Development Goal: 16 Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels. | The project has made a direct contribution to SDG 16, recognizing the interconnectedness and interdependence between justice, the rule of law, inclusivity, and peaceful societies. It has ensured that this approach is incorporated into government reforms and programming. The project has directly contributed to the achievement of several targets under SDG 16, including targets 16.3, 16.6, 16.7, and 16.10. Moreover, it has implicitly contributed to targets 16.4 and 16.5 by increasing trust in institutions, enhancing the effectiveness of the judiciary, particularly in combating corruption, promoting free legal aid, and improving the efficiency of patrol officers. |

Project Progress and Final Results

Improving the efficiency of the Judiciary through the implementation of a mechanism for the merit-based selection of judges, support for the establishment of AMCA and promotion of automation of processes in the courts system

- Merit-based selection for judge candidates through a psychological testing mechanism implemented

UNDP provided support to the Ministry of Justice (MoJ) and Supreme Judicial Council (SJC) in implementing psychological testing of judge candidates and interpreting the results through a web portal during the September 2021 to December 2022 election rounds (which involved around 70 candidates). Additionally, UNDP assisted the SJC in conducting interviews with judge candidates by engaging international experts.  Based on feedback from the SJC and MOJ, a needs assessment of the existing pilot mechanism was conducted, and recommendations were presented to national partners for enhancing the merit-based selection process.

- Study on business model for AMCA (financial processes and management) conducted

UNDP supported the MoJ in designing the AMCA business model through a local consultant. This included developing estimations and mechanisms for the center to become self-sustainable, with perspectives and mechanisms of development. To inform this process, a study was conducted focusing on a comparative analysis of international best practices in the business model design of arbitration centers, resulting in reasoned recommendations for policy options for AMCA's business model. UNDP also helped the MoJ to develop reasoned recommendations for designing the AMCA budget, including detailed budget lines and possible financial sources, as well as a modus of remuneration for arbitrators.

- Comprehensive PR and raising awareness campaign for AMCA implemented

UNDP supported the design of the title and logo of AMCA and helped develop posters for a campaign promoting the benefits of solving disputes via AMCA. These posters are intended for dissemination through various digital platforms (AMCA website, social media, etc.) as well as outdoor means such as billboards. UNDP also developed an interview-format video that describes the idea behind the establishment of AMCA and its main functions. Additionally, an animation video storyboard and a short animation video were created to be used for AMCA's media and awareness-raising campaigns which can be accessed here.

- Executive ToR tailored for the e-module on criminal procedure developed for MoJ

A detailed description of the business processes for the executive ToR was developed specifically for the e-module on criminal procedure, including an anti-corruption component. The work informed the development of the final TOR for the criminal e-module, which will be integrated into the e-court system. The ToR outlines solutions to make information and documents accessible online to different parties simultaneously and remotely. It also includes features to create and analyze case information, track cases as they proceed through the system and facilitate communication and collaboration between different parties and stakeholders. It is worth noting that in the framework of the current activity the specifics of the business processes of the criminal procedure of corruption-related crimes were described and a section on anti-corruption component was included in the final ToR.

Access to justice improved

- Survey/study to measure public perception on and to understand the experiences of the identified target groups with the free legal aid mechanisms in two border marzes of Armenia launched

The Project provides support to the Chamber of Advocates (ChA) /Office of the Public Defender (PDO) in conducting a comprehensive study in two border regions of Armenia, namely Syunik and Tavush. The study aims to achieve the following objectives: a) measure public awareness about state-guaranteed free legal aid (FLA) mechanisms, (b) assess the public perception of the PDO among the population, and (c) analyze the experiences of the identified target groups (FLA beneficiaries) in applying for and receiving FLA with the goal of revealing problems and making recommendations for improving the FLA mechanisms with the particular emphasis on gender dimension.

- Efficient communication strategy for the ChA/ PDO developed

The Project has provided support to the ChA/PDO in the development of an efficient and sustainable communication strategy that the PDO can use with its limited financial and human resources. The main goals of the communication strategy are to raise awareness about the PDO's activities, drive a large amount of traffic to the PDO's official website, and create a positive image of the PDO while informing the public of the high quality of its services. The strategy aimed primarily at the general public, beneficiary groups of the PDO, and legal specialists in the field, with the objective to create a positive perception of the PDO and its services through effective communication.

- Communication (raising awareness) campaign for the PDO launched and implemented

The Project launched a national communication and public awareness campaign aimed at target groups and the general public. The campaign was dedicated to raising public awareness and educating the public about the free legal aid through various means. As part of this campaign, the Project developed short videos (video 1, video 2, and video 3) and conducted a tailored social media campaign. The activity addressed gender dimension ensuring that the campaign reaches and impacts women and men equally.

- Organization of a meeting for presentation and discussion of the third interim UPR report of the RoA supported

The Universal Periodic Review (UPR), as a process involving review of the human rights records of the state, providing a platform for the state to present the human rights situation in the given country and the measures undertaken to meet the human rights obligations is of utmost importance and relates to many spheres, including access to justice, gender-related human rights issues, etc. Taking into account the above-mentioned and upon a request from the Ministry of Foreign Affairs of Armenia (MFA), in the framework of the Project, UNDP CO supported MFA in organizing a multi-stakeholder meeting for presentation and discussion of the third interim UPR report of the RoA.

Additionally, the Project in partnership with the MFA organized a conference to present and discuss the third UPR interim report of Armenia. The meeting held on December 14, 2022 was launched with the opening remarks of the Resident Representative of the UNDP CO and the Deputy Minister of Foreign Affairs, followed by keynote speeches of high-level representatives of the MoJ, MFA and other ministries of Armenia. The meeting was attended by 50 representatives of state agencies, NGOs and international organizations and discussed such issues as human rights commitments, access to justice, independence of the judiciary and fair trial standards.

- Anti-corruption “ecosystem” in the country improved and strengthened

To complement other initiatives in the field, the Project assessed the results and impact of the 5 months trainings of the new patrol police officers to promote police reform and enhance the anti-corruption ecosystem in the country.

The primary purpose of the assessment that involved 390 respondents was to evaluate the practicality and relevance of the knowledge and skills acquired during the training program, as well as to measure relevance of the program to the daily duties of the officers. The study analyses the existing shortcomings and offers in-depth recommendations for improving the system.

Overall, the initiative largely contributed towards promoting police trainings and continuous education and the implementation of the recommendations will help to ensure that newly recruited officers are well-equipped to handle their daily duties in the field in a professional and competent manner, and that citizens are satisfied with the level of service provided by the police.

Performance snapshot of the planned deliverables

|  |  | 2022 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity/ Output | Annual Targets / Indicators |  | Planned |  |  |  | Actual |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Status | Comments |
| Integrity, independence and efficiency of the judiciary supported through national policies and new mechanisms in place | Implementation of the psychological testing mechanism of the merit-based selection of judge-candidates. |  |  |  | x | x | Implemented |  |
|  | Designing the AMCA business model based on the comparative analysis of international best practices, developing recommendations for designing the AMCA budget, and elaborating the modus of renumeration of arbitrators. |  |  |  |  | x | Implemented |  |
|  | Implementation of a comprehensive PR and awareness raising campaign for AMCA, including design of the title and logo of the Center, preparation of materials for poster campaign and videos for marketing and awareness raising campaign |  |  |  | x | x | Implemented |  |
|  | Designing business processes and developing ToR tailored for the e-module on criminal procedure |  |  |  |  | x | Implemented |  |
| Access to justice mechanisms improved | Development of efficient communications strategy for the ChA/ PDO |  |  |  | x |  | Implemented |  |
|  | Conducting a communication (public awareness) campaign for the PDO |  |  |  |  | x | Implemented |  |
|  | Conducting a survey/ study on FLA mechanisms in two border regions |  |  |  |  | x | Implemented |  |
|  | Facilitation of conducting a meeting for presentation and discussion of the third interim UPR report of the RoA |  |  |  |  | x | Implemented |  |
| Anti-corruption “ecosystem” in the country improved and strengthened | Assessment of the Results and impact of the training program delivered to the newly recruited patrol officers |  |  |  | x | x | Implemented |  |

Innovative and transformative aspects:

The Project has introduced several innovative components that aim to transform the justice sector in Armenia. One such component is the implementation of a psychological testing platform in the selection process for judge candidates. This tool is a ground-breaking solution to assess the main characteristics and behavioural parameters of candidates not only in Armenia but worldwide. Only a few countries (for example, Ukraine and the Netherlands), have taken similar steps to increase the integrity of the selection process for judges. This mechanism is an innovative tool that can be further developed and improved based on lessons learned during the piloting stage. It can be expanded to the process of selecting public servants in different institutions.

The Project also supported the establishment of the Arbitration and Mediation Center of Armenia. While many countries around the world have already embraced alternative dispute resolution (ADR) methods, such as arbitration and mediation, these approaches are rarely used in Armenia. The state's support for advancing arbitration and mediation in Armenia is an innovative approach to resolving the issue of workload and increasing the efficiency of the judiciary. The successful establishment and operation of AMCA will have a transformative effect not only in the justice sector but also in terms of strengthening social cohesion by promoting a culture of dialogue in society.

The Project has also facilitated the introduction of an innovative e-court tool by the Ministry of Justice through the development and validation of an executive ToR for criminal procedure with an anti-corruption component. Additionally, UNDP's collaboration with the Chamber of Advocates and Public Defender's Office has created a solid foundation for identifying the needs and gaps in the regulation of the free legal aid system, and for developing transformative solutions to promote the provision of free legal aid and pro bono services in Armenia.

Overall, the Project's innovative components represent significant steps towards transforming the justice sector in Armenia, promoting integrity, efficiency, and social cohesion.

# Gender mainstreaming, crosscutting results, targeting

- Indicate project’s gender marker (GEN0-3), gender mainstreaming strategy/approaches in line with corporate/CO Gender Equality Strategy, mentioning particular gender-responsive (GEN2) or gender-transformative (GEN3) results. If possible, GEN0-1 projects shall be revisited for upgrade. Present the project’s targeting strategy and application of Leaving No One Behind (LNOB) approach. Present the project’s cross-cutting aspects and ‘enablers’ in such areas as cross-portfolio interventions, human rights-based approach, risk informed development, mainstreaming innovation, social and environmental responsiveness, user-driven design, citizen engagement, leveraging private financing.

Project corresponds to UNDP Gender Marker Gen 2:

To advance gender equality in both access to justice and the free legal aid services, the Project executed a series of communication and public awareness initiatives in collaboration with ChA/PDO, with a particular focus on a gender-sensitive approach. Furthermore, the Project conducted a comprehensive survey/study aimed at gauging public awareness levels concerning free legal aid mechanisms and assessing the degree of satisfaction with PDO's performance in addressing gender-related issues.

Recognizing the need for incorporating gender sensitivity into the implementation of the psychological testing mechanism for judge candidates, the Project conducted a gender-inclusive pilot of this mechanism. This ensured that the testing process remained equitable and unbiased, promoting diversity and inclusivity.

Additionally, the Project scrutinized the development of business processes for the perspective arbitration centre, ensuring that a gender-sensitive perspective is embedded in the implementation process.

# Risks, proposed changes to prodoc, horizon scanning, evaluation

- Risks, Changes to ProDoc: Present/discuss the current risks status and mitigation strategies. Update risks in Atlas and in attached Log. The closed risks shall remain in the list. Present changes to ProDoc necessitated by horizon scanning or other factors. Indicate all project revisions, reasons and dates. Evaluation: Indicate if ProDoc defines evaluation for this project. For conducted evaluations present the implementation of recommendations/management response.

Critical Risks: The Project, during its implementation from September 2021 to December 2022, recognized potential risks that could impede the timely execution of activities. These risks included several factors, including the impact of COVID-19 in Armenia, political instability, a shift in the Government's priorities, insufficient financial resources, and border hostilities.

These challenges had an adverse impact on the timeline of certain activities, such as the launch of the FLA survey and FLA communication’s campaign. However, the Project team actively engaged in discussions and consultations with national partners to realign the timeline and mitigate the risks. Through accelerated implementation strategies, the Project team was ultimately able to overcome the delays and ensure successful project completion. Despite the challenges faced, the Project team remained committed to delivering high-quality results and advancing the project's goals.

Prodoc changes, horizon scanning: The Project underwent some adjustments to accommodate changing Government priorities and emerging consultancy needs. For instance, the Project developed the business model for the Arbitration and Mediation Centre of Armenia and executive ToR for the e-module on criminal procedure. Also, having faced challenges as described in part V, the Project applied for a three-month no-cost extension. This allowed to carry out the project activities as outlined in the Project document.

Continuing this work in the justice field is crucial, given that national stakeholders depend heavily on UNDP's expertise. It is also vital to build upon the results achieved through this Project.

# Partnership. Communication and knowledge products

- Present partnership strategies, discuss South-South/Triangular cooperation, inter-agency or other collaboration, mentioning the learning or leading roles. Collate in a table knowledge and communication materials and links. Indicate planned flagship publications and discuss their strategic importance.

The Project effectively collaborated with key stakeholders in the justice sector, including the MoJ, SJC, ChA and PDO. The timely implementation of the Project activities in partnership with named stakeholders underscored the Project's commitment to its objectives. Regular meetings, discussions, and consultations were conducted to chart the course and potential directions for future cooperation.

Furthermore, the Project maintained close cooperation with relevant international organizations, such as the EU, CoE, SIDA, OECD, GIZ and USAID. This collaborative approach was essential to prevent any duplication of efforts and to enhance the overall effectiveness of our work in the pursuit of justice and rule of law.

# Validation of results (field visits). Quality assurance. Lessons learned. Project boards. Donor reports

- Project Coordinator shall prepare and countersign with Portfolio Leads a field visit/output verification document (template see in annex) in line with ProDoc, POPP, and CO M&E Plan. For HACT and RP-related projects use M&E report and field visit template for programme monitoring. Risks and lessons learned shall be part of HACT/RP programmatic monitoring. Formulate lessons learned through lifetime of the project in highly strategic language. Present a schedule of Project Board (PB) meetings and implementation status. Present a schedule of donor reports and implementation status. Prepare quality assurance report in UNDP system and discuss with Portfolio Lead (assurer). For newly developing projects/outputs Design quality assurance reports shall be prepared, assured, and approved in the system. For ongoing project Implementation quality assurance reports shall be prepared once in two years. For closing projects Closure Quality Assurance Reports shall be prepared, assured, and approved in the system. Closure QA shall contain all evidence and approval documents (LPAC, PB minutes, final RB minutes, monitoring reports, etc).

Field visits have been conducted and the results of the Project validated.

The key lessons learnt are:

- The importance of consistently monitoring progress with all stakeholders involved;

- Developing new projects based on the evaluation and assessments of previous results is essential to keep improving and meeting the needs of the partner institutions;

- Preparing contingency plans to address unexpected challenges and changing circumstances;

- Conducting regular meetings with national partners to maintain strong relationships and ensure effective collaboration;

- Being proactive in presenting new proposal in case of shifting priorities or unexpected circumstances to stay responsive and relevant to the needs of the partners and beneficiary institutions.

Evaluations:

- The project's support resulted in the successful implementation of psychological testing for judge candidates and the involvement of international experts in candidate interviews, enhancing the quality and transparency of the judicial selection process.

- Through needs assessments and consultations, the project contributed to the refinement of the merit-based selection process for judges, ensuring a fair and competitive approach.

- The project developed a sustainable business model for AMCA, enabling it to operate independently and serve as a reliable dispute resolution platform.

- Detailed recommendations for the AMCA budget, including sources of funding, were established, providing clear financial guidance for its operations.

- A structured remuneration system for arbitrators was devised, ensuring fairness and transparency in their compensation.

- Various communication materials, including posters, interview-format videos, and animations, were produced to promote awareness and understanding of AMCA.

- Comprehensive business processes and a finalized ToR for the e-module on criminal procedure were developed, ensuring solid basis for tendering processes.

- A well-crafted and sustainable communication strategy for the PDO was created, enhancing its outreach and impact.

- A successful national communication campaign was executed, raising awareness of the ChA and PDO among target groups and the broader public.

- A comprehensive survey in two regions shed light on FLA practices, providing valuable insights for future improvements.

- The project facilitated a multi-stakeholder meeting to discuss the third interim Universal Periodic Review (UPR) report of the RA, enhancing engagement in the UPR process.

- An assessment of training programs for newly recruited patrol officers provided valuable feedback and insights for improving police capacity and education.

# Results framework

| Intended Outcome as stated in the UNDAF/Country [or Global/Regional] Programme Results and Resource Framework: People benefit from effective and accountable governance systems and institutions that safeguard human rights, uphold the rule of law, and public administration that ensures effective and human-centred service delivery for all |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome indicators as stated in the Country Programme [or Global/Regional] Results and Resources Framework, including baseline and targets: Capacities, functions and financing of rule of law, national human rights institutions/systems strengthened to protect human rights, expand access to justice and combat discrimination, with a focus on women and marginalized groups (IRRF 2.2.3) |  |  |  |  |  |  |  |
| Applicable Output(s) from the UNDP Strategic Plan: Outcome 2 - Accelerate structural transformations for sustainable development. Expected CPD Output 3.2.: Capacities, functions and financing of rule of law, national human rights institutions/systems strengthened to protect human rights, expand access to justice and combat discrimination, with a focus on women and marginalized groups. |  |  |  |  |  |  |  |
| Project title and Atlas Project Number: Support to Armenia’s Rule of Law and Justice Reform: Phase 2 (ATLAS ID 00121670, 00128554) |  |  |  |  |  |  |  |
| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | TARGETS (by frequency of data collection) |  | DATA COLLECTION METHODS & RISKS, COMMENTS |
|  |  |  | Value | Year | Year 1 (2021) |  |  |
|  |  |  |  |  | Planned | Actual |  |
| Output 1.1. Continuous implementation of the merit-based selection of judge candidates ensured | 1.1.1. Judge-candidates selected through the piloted psychological testing mechanism. | Reports on the procedure of psychological testing and interviews of judge candidates (with recommendations for further improvement of the procedure) developed by international experts. | Merit-based procedure for judge-candidates at place | 2022 | Selection of all judge candidates with the implementation of a piloted psychological testing platform | Completed | Data collection methods: electronically submitted psychological tests revised, interviews conducted in present of national psychologists and international experts in the field of organizational psychology with addressing, inter alia, the gender dimension Reports on merit-based selection of judge candidates in place Risks: lack of sustainability of the mechanism and dependence on international expertise |
| Output 1.2 AMCA business model designed | 1.2.1 MoJ (AMCA) institutional and expert support provided | Reports of the national consultant | Provision of institutional and expert support to the MoJ for AMCA establishment | 2022 | Institutional/ expert support provided | Completed | Data collection methods: international best practice review, review of the national legislation and available statistics, consultations and meetings. Risks: limited and/or law quality statistical materials |
| Output 1.3 AMCA marketing and raising awareness campaign conducted | 1.3.1. AMCA logo designed, the title of the Center and slogan elaborated, two thematic videos prepared, poster campaign materials developed | The relevant package presented and validated | The marketing and raising awareness campaign for a to be established arbitration and mediation center conducted for the launch of its activities right after establishment | 2022 | MoJ institutional/ expert support provided | Completed | Data collection implemented in close cooperation with the MoJ authorised representatives. Risks: no specific risks indicated. |
| Output 1.4 Executive ToR tailored for the e-module on criminal procedure developed | ToR for the announcement of the competition developed | The relevant package presented and validated | With the ToR on the criminal e-module the relevant e-module will be developed and integrated into the e-court system | 2022 | MoJ institutional/ expert support provided | Completed | Data collection: data collection implemented in close cooperation with the MoJ authorised representatives. Risks- lack of clear state vision on the application and integration of e-justice and e-court systems |
| Output 2.1 Communications strategy developed and raising awareness campaign conducted | Communication strategy provided to and validated by the ChA/PDO, raising awareness campaign videos and posts published in social media | The PDO official and social media sites, promotion of the videos via TV channels (e.g. Armenia TV) | Promotion of FLA in Armenia through better informed beneficiaries | 2022 | ChA/ PDO institutional/ expert support provided | Completed | Data collection: review of legislation and available statistics, needs assessment based on meetings and consultations, as a result of which the gender responsive strategy was developed. Data collection implemented in close cooperation with the ChA/ PDO. Risks: no specific risks identified |
| Output 2.2 Comprehensive survey/study on FLA mechanisms in two border regions conducted | The awareness of the population about FLA mechanisms measured, the problems of the FLA mechanisms revealed and recommendations for improvement provided | Reports of consultant | Advancement of FLA mechanisms in Armenia | 2022 | ChA/ PDO institutional/ expert support provided | Completed | Data collection methods: data collection implemented in close cooperation with the ChA and PDO, secondary literature review and statistical review conducted Risks: security issues due to frequent hostile acts on the border regions of Armenia, which might hinder the travels to the identified border regions, possible high drop out rate of respondents due to sensitivity of the topic |
| Output 2.3 Supporting in organizing a meeting for discussion of the third interim UPR report of the RoA | Discussion of the third interim UPR report of the RoA organized | News updates | Promotion of human rights in general, and access to justice and gender equality in particular | 2022 | Financial support provided | Completed | Data collection methods: in close cooperation with the Ministry of Foreign Affairs Risks: no specific risks identified |
| Output 3.1 Assessment of the Results and impact of the training program delivered to the newly recruited patrol officers conducted. | The results and impact of the training assessed and recommendations presented. | Expert report with analysis of the assessment (survey with 390 participants) submitted and validated | The gaps of the training programmes revealed and recommendations provided for improvement of the patrol services in Armenia | 2022 | Expert support provided | Completed | Data collection methods: policy (including legal) review, desk research, survey Risks: lack of serious attitude towards the survey among the patrol officers which may affect the findings |

# Offline risk log

| # | Description | Risk Category | Impact & Probability | Risk Treatment / Management Measures | Risk Owner |
| --- | --- | --- | --- | --- | --- |
|  | Enter a brief description of the risk. Risk descriptions should include future events and cause. | Social and Environmental, Financial, Operational, Organizational, Political, Regulatory, Strategic, Other | Describe the potential effect on the project if the future event were to occur. Enter probability based on 1-5 scale (1 = Not likely; 5 = Expected) Enter impact based on 1-5 scale (1 = Low; 5 = Critical) | What actions have been taken/will be taken to manage this risk? | The person or entity with the responsibility to manage the risk. |
| 1 | COVID-19 pandemic and its impact | Financial Operational Organizational Political Regulatory Strategic | I:1 P:4 | Close cooperation and partnerships with relevant state agencies allowed to minimize the implementation risks | UNDP, MoJ, SJC, ChA/PDO |
| 2 | War situation and its negative circumstances | Social and Environmental Financial Operational Organizational Political Regulatory Strategic | I:4 P:5 | Project team has been closely following the developments in the country and will adjust its position accordingly. In this case excellent cooperation and partnership with ChA/PDO are at utmost importance | UNDP, ChA/PDO |
| 3 | Lack of clear state vision on the application and integration of e-justice and e-court systems | Political Strategic | I:5 P:3 | The Project team conducted consultations with the relevant stakeholders and with engagement of international experts to discuss the possible solutions and present the best practices in the field | UNDP |
| 4 | Unpredictable reprioritization of issues | Financial Operational Organizational Political Regulatory Strategic | I:3 P:2 | This risk may have a specifically high impact on planning of the future activities of the UNDP CO in the field of justice and rule of law. Project team is constantly in touch with the lead/ coordinating state institutions in order to be able to timely react to the change in priorities | UNDP |
| 5 | Lack of resources (human resources, informational resources etc.) | Financial Operational Organizational Regulatory | I:4 P:3 | Scarceness of human resources is a serious problem in the PDO, because opposed to a very high number of applicants for free legal aid services there are not enough positions for public defenders envisaged by the legislation, which makes their work especially stressful and requires them to prioritize tasks as per their urgency. Project team has established excellent cooperation with ChA/PDO and manages the situation accordingly, at the same time possible solutions to the scarceness of human resources in PDO is planned to be reflected in the new Project Proposal. Another issue is the lack or poor quality of statistical materials in the field of rule of law and justice. To this end, effective cooperation with the relevant state stakeholders has helped to mitigate the negative consequences of the risk, at the same time Project team will suggest solutions to the issue in the new Project Proposal. | UNDP |

# Annual/multiyear work plan and budget from prodoc

- All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME 2021/2022 |  |  |  |  |  | RESP. PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 |  | Funding Source | Budget description | Amount in USD |
| Output 1 Integrity, independence and efficiency of the judiciary supported | 1.1 Improve legal and institutional mechanisms of psychological testing of candidate judges |  |  |  |  | X | X | UNDP | UNDP | International and local consultants Translation | 15,000 |
|  | 1.2. Conduct capacity building trainings for local psychologists to improve their capacities on conducting psychological assessment and behavioural interviews |  |  | X | X | X | X |  |  | International and local consultants Trainings workshops Travel | 15,000 |
|  | 1.3. Upgrade established electronic platform by introducing new innovative approaches |  | X | X | X | X | X |  |  | Contractual services – Companies | 10,000 |
|  | 1.4. Develop (a) ethics and Integrity modules and (b) psychological standards for Justice Academy |  |  |  | X | X | X |  |  | International and local consultants Trainings workshops Translation | 10,000 |
|  | 1.5. Deployment of a long-term international RoL adviser, to enhance strategic visioning, support leveraging the portfolio and helping with fund raising | X | X | X | X | X | X |  |  | International and local consultants | 30,000 |
|  | Sub-Total for Output 1: |  |  |  |  |  |  |  |  | 80,000 |  |
| Output 2 Access to justice and free legal aid mechanisms further promoted and strengthened | 2.1. Provide new methodologies and mechanisms of the legal aid funding based on international practices, as well as the internal procedures of the MoJ |  | X | X | X | X | X | UNDP | UNDP | International and local consultants Translation | 5,000 |
|  | 2.2. Launch a national public awareness campaign on state-guaranteed free legal aid services |  |  | X | X | X | X |  |  | International and local consultants Contractual services – Companies | 15,000 |
|  | 2.3. Adopt relevant measures aimed at promoting the culture of pro bono legal aid provision in Armenia |  |  | X | X | X |  |  |  | International and local consultants Trainings workshops Translation | 10,000 |
|  | Sub-Total for Output 2: |  |  |  |  |  |  |  |  | 30,000 |  |
| Output 3 The establishment of Arbitration Centre supported | 3.1. Assist in developing the ToR and structure of new Arbitration Centre. |  | X | X | X | X |  | UNDP | UNDP | International and local consultants Translation | 5,000 |
|  | 3.2. Establish cooperation with the international arbitration centres and arbitrators to engage them in the arrangement, planning, and creation of documents related to the establishment and operation of the Arbitration centre. | X | X | X | X | X |  |  |  | - | - |
|  | 3.3. Assist in the awareness-raising activities on arbitration. |  |  | X | X | X | X |  |  | Contractual services – Companies | 14,000 |
|  | 3.4. Support the development of rules of procedures and rules of conduct for arbitrators. |  |  | X | X | X | X |  |  | International and local consultants Trainings workshops | 5,000 |
|  | Sub-Total for Output 3: |  |  |  |  |  |  |  |  | 24,000 |  |
| Output 4 The capacities of Patrol officers further enhanced and strengthened | 4.1. Conduct assessment of the results and impact of the first-ever training programme delivered to the newly recruited patrol officers and provide recommendations for amelioration of the system | X | X | X | X | X |  | UNDP | UNDP | International and local consultants Translation | 10,000 |
|  | 4.2. Further improve and upgrade the training programs and curricula for building up modern skills and capacities of patrol officers |  |  | X | X | X |  |  |  | International and local consultants Trainings workshops | 5,000 |
|  | Sub-Total for Output 4: |  |  |  |  |  |  |  |  | 15,000 |  |
| Project management | Staff /full-time Task Lead & 20% Project Assistant | X | X | X | X | X | X | UNDP | UNDP |  | 30,000 |
|  | DPC, Comms facilities, General Management Support – 8% |  |  |  |  |  |  |  |  |  | 21,000 |
|  | Sub-Total for Project management: |  |  |  |  |  |  |  |  | 51,000 |  |
| TOTAL BUDGET |  |  |  |  |  |  |  |  |  | 200,000 |  |

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards. Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.