Final Project Completion Report

| # Project Code | # UZB1033 |
| --- | --- |
| # Country | # UZBEKISTAN |
| # Grant Title | # Technical Assistance (TA) to develop the enabling environment for Green Sukuk in Uzbekistan |
| # Executing Agency | # National Agency of Perspective Projects, Uzbekistan |
| # Approval Date | # 23-12-2020 |
| # Effectiveness Date | # 30-01-2022 |
| # Approved Amount (USD) | # 220K USD |
| # Last Date of Disbursement | # 30-03-2026 |
| # Quarter / Year | # Q1/2021-Q1/2026 |

Background

Since 2017 Uzbekistan has embarked on an ambitious reform agenda, with the considerable attention being paid to development of sustainable and inclusive society. Clearly, the ability to implement these reforms relies on, among other, identifying optimal approaches to development financing. Uzbekistan’s spending needs are large and will require careful consideration of funding options. Early 2020 UNDP supported Development Finance Assessment which pointed that achieving SDGs requires at least estimated annual additional investments worth USD 6 billion, with important additional spending required in agriculture, health sector and in energy and transport infrastructure. Clearly, development financing will need to be scaled up significantly, which would require thorough analysis of opportunities and constraints presented by various funding sources (state budget, foreign and domestic borrowing, ODA, alternative finance instruments, etc.).

As the financing systems around the world are becoming more sophisticated and are discovering new operating models, sukuk has emerged as a new promising instrument to attract financing into sustainable development. Globally, sukuk issue totaled more than 979 billion US dollars.The annual market capitalization of stocks meeting the criteria for the Dow Jones Islamic Market Index in Islamic countries is estimated at more than $ 12 trillion. Sukuk instruments are based on assets or business ownership and gaining recognition not only in the Muslim countries, but also worldwide. Sukuk has been issued over the past seventeen years as an alternative to conventional bonds and has been signed on by a wide base of investors. The issuance of green bonds increased globally to an aggregate value of approximately USD 258 billion during 2019 with green sukuk accounting for USD 7.9 billion. The optimism surrounding green finance generally has extended to social financing which is likely to gain greater prominence as part of the COVID-19 recovery.

In Uzbekistan too, the Government is exploring new opportunities presented by various financing solutions. It has identified several innovative financial instruments that can complement existing financing sources to close the gap to achieve the sustainable development agenda with green sukuk being one of them. In Uzbekistan, where more than 90 percent of population comprises Muslims, there is an immense potential for introducing Islamic financial instruments. Introduction of green Islamic Finance could play a crucial role in boosting green economy and addressing serious climate change and natural resources management concerns that Uzbekistan faces today.

Introduction of green sukuk in Uzbekistan will require establishing a proper enabling environment in the country, which would foster implementation of sustainable development projects in such sectors as renewable energy, energy and waste management, sustainable transportation and others. It is expected that green sukuk can be a steppingstone on a journey to channel finances towards sustainable development in Uzbekistan. Moreover, introduction of sukuks could pave the wave for development of other instruments based on Islamic finance principles and help achieve greater financial inclusion of Uzbekistan’s population.

Considering this, the Islamic Development Bank, together with UNDP initiated a Technical Assistance project – to assist the Government in establishing a proper enabling environment for green sukuk in Uzbekistan. The goal is to develop relevant legislative, institutional and regulatory framework as well as strengthening the national capacities at the institutional and individual level. The main project activities were grouped around the following Outputs:

1. Market gap analysis. Conducting strategic assessment study on green sukuk ecosystem, as well as capital markets analysis to evaluate the market readiness and the legal basis for introduction of Islamic fund-raising instruments, including green sukuk in Uzbekistan.

2. Enhancing the Enabling Environment for Green sukuk in Uzbekistan by:

a) drafting of legal, regulatory, supervisory documents, Shariah and Corporate Governance

Framework, and

b) National Green Sukuk Framework as a guidance document for future issuances.

3. Awareness rising compaign

4. Capacity building and training

Main Results achieved during the project implementation.

Summary

During 2021-2026 the project activities have been implemented as per the initially agreed multi-year Work Plan. Based on the Market Gap analysis conducted in late 2020 a full package of legal and regulatory documents including relevant amendments to the existing ones for introduction of Sukuk and Green Sukuk in Uzbekistan was developed. The draft legal/regulatory documents have been incorporated into the draft Capital Market Law of Uzbekistan that contains a specific chapter and provisions on Islamic (Sukuk) securities.

In compliance with international good standards (ICMA, etc.) a Framework document for the National Green, Social and Sustainability Sukuk was developed to provide a guidance for future sukuk issuances.

More than 250 representatives from the government, private sector, academic community and civil society were capacitated and improved their knowledge and skill in the area of Islamic Finance, sukuk and green sukuk. Additionally, several technical and knowledge products were developed the further strengthen the national capacities in the area concerned.

More detailed descsiption of the activities and achieved results are provided below:

Output 1.

A Strategic Assessment Study of the Green Sukuk Ecosystem in Uzbekistan has been conducted under the support of the UNDP Istanbul Centre for Private Sector in Development and Pre-Feasibility Study on Green Sukuk Issuance in Uzbekistan was developed to provide an institutional and capital market gap analysis as well as to evaluate the market readiness and the legal basis for introduction of sukuk and green sukuk in Uzbekistan.

https://www.undp.org/uzbekistan/publications/pre-feasibility-study-green-sukuk-issuance-republic-uzbekistan

The Report was presented and discussed with the stakeholders (60 participants) including the representatives of interested ministries and government agencies, research institutions, commercial banks, the private sector and international partners during the Validation workshop held virtually on 25 November 2020. Additionally, international good practices including the Malasian experience of corporate green sukuk issuances and Indonesian sovereign green sukuk issuances were presented during the event.

https://www.uz.undp.org/content/uzbekistan/en/home/presscenter/pressreleases/2020/11/presentation-green-sukuk-securities-in-uzbekistan.html

Output 2. Dveloping the legal and regulatory framework

Based on Market Gap analysis the following activities have been implemented and results achieved:

1. A Concept paper for development of legal framework for Sukuk and Green Sukuk in Uzbekistan has been developed and presented/discussed with stakeholders (55 participants including 40 male and 15 female) representing the government, investors, private sector, public, international partners, etc. during the Workshop held on 30 June 2022.

O'zbekiston Respublikasi Moliya Vazirligi - Oʻzbekiston Respublikasida “Sukuk” va “Yashil Sukuk” uchun huquqiy-meʼyoriy bazani ishlab chiqish boʻyicha vebinar (mf.uz)

2. An International (White & Case) and local (Azizov & Partners) law companies have drafted a full package of legal and regulatory documents including relevant amendments to the existing ones for introduction of Sukuk and Green Sukuk in Uzbekistan. The draft legal/regulatory documents have been incorporated into the draft Capital Market Law of Uzbekistan and submitted to the Government.

3. The National Agency of Perspective Projects – a newly designated capital market regulator in Uzbekistan and the main beneficiary of the Green Sukuk initiative developed a new version of the draft Law "On Capital Market in Uzbekistan" that contains a specific Chapter on Islamic (Sukuk) securities. The draft Law was circulated among the relevant ministries and government agencies for collecting the comments and feedback as well as presented for public review in late August 2024.

4. Project team organized and facilitated a round table event on “Introduction of Islamic Finance in Uzbekistan: opportunities and challenges” aimed to present the draft Law of “On Capital Market in Uzbekistan” focusing on the chapters related to introduction of Islamic (Sukuk) securities, as well as to facilitate the discussion and exchange of views among key stakeholders with respect to the opportunities and existing challenges related to introduction of the new Islamic financing instruments in the country. The event was held on 13 September 2024 and attended by more than 30 representatives of the key stakeholders.

UNDP in cooperation with the Islamic Development Bank supports the Government of Uzbekistan in developing the enabling environment for Islamic Finance instruments | United Nations Development Programme

Currently the draft Capital Market Law is in the process of final review at the Administration of the President of Uzbekistan and further submission to the Parliament for further review and adoption. Project Team is planning to facilitade the discussion of the Darft Law at the Parliament.

5. In late 2024 UNDP Project team facilitated the elaboration and discussion of the National Green Sukuk Framework for Uzbekistan that will provide a guidance for future sukuk and green sukuk issuances.

https://napp.uz/uz/news/yashil-sukuk-tuzilmasini-rivojlantirish-bo-yicha-uchrashuv

6. With the support of of UNDP Istanbul International Center for Private Sector in Development (IICPSD) a Framework document for the National Green, Social and Sustainability Sukuk was developed and submitted to the Governemnt.

Output 3. Awareness rising compaign and events

A webinar titled “Sukuk Bonds as a Promising Alternative Financing Source for Uzbek Issuers and Investors” has been conducted on 25 March 2022 jointly by UNDP, the Ministry of Finance, Islamic Corporation for Development of the Private Sector (ICD), and Ansher Capital LLC with participation of more than 60 participants (40 male and 20 female) representing the government, investors, private sector, public, international partners, etc. The event served as a convenient platform for discussing the ongoing reforms and activities related to the introduction of Islamic finance instruments including the green sukuk in Uzbekistan.

Green Sukuk to Help Uzbekistan Achieve Sustainable Development Goals and Address Climate Change Issues | United Nations Development Programme (undp.org)

Output 4. Capacity Building and Training.

The main project activities were accompanied by the following capacity building events:

1. The Project supported the participation of a selected staff (4 officials) of the Capital Markets Development Department with the Ministry of Economy and Finance at the Workshop on Islamic Banking and Finance conducted during 14-16 March 2023 in Tashkent, Uzbekistan by ALHUDA CIBE FZ LLE.

2. With the support of UNDP Istanbul International Center for Private Sector in Development (IICPSD) a two-day intensive training workshop on Islamic Finance and Green Sukuk was organized for the key stakeholders. The main objective of the training was to strengthen and promote Islamic Finance and Sukuk, which serve as an alternative source of financing for sustainable development besides conventional finance. The event was held from 17-18 October 2024 in a hybrid format and attended by 60 representatives of the government, private sector, academia and other stakeholders.

3. A study visit to Türkiye was organized during 19-21 November 2024 for a group of Senior Officer (6 participants) from the NAPP and the MoEF to learn international good practices in Islamic Finance and Green Sukuk. The Uzbek delegation members have met with industry experts, practitioners, and stakeholders in Türkiye's Islamic finance sectors and established valuable networks, exchange knowledge, and explore potential collaboration opportunities

Pending project activities in Y2026:

1. To support the Government (National Agency of Perspective Projects) in facilitating the discussion and adoption of the draft Law "On Capital Market in Uzbekistan" at the Parliament.

2. To conduct a comprehensive awarenessrising event to present the Capital Market that contains a specific Chapters and provision on Islamic (Sukuk) securities with participation of a broad range of stakeholders including the Parliament,  government, investors, private sector, public, international partners, etc.

3. To finalize and publish the analytical and knowledge products developed during the project implementation.

Challenges and Issues.

During thw active phase of the project implementation the administrative reforms in the Government of Uzbekistan and staff turn-over caused by this significantly affected the project. According to the President’ Resolution dated on 02.09.2023 the functions of the capital markets regulation were transferred from the Ministry of Economy and Finance to the National Agency for Prostective Projects (NAPP) that became a new implementing partner and beneficiary of the project. This change of the capital market regulator with the government made substantial impact on the timely delivery of the planned project activities. It caused severe delays in delivering the relevant outputs due to the change of the staff responsible for the project, insufficient capacities of the new regulator in the area of Islamic Finance and sukuk, etc.

Despite of these difficulties the Project team facilitated the smooths transfer of all technical products, knowledge matarials and other documents from the Ministry of Economy and Finance to the NAPP. The Project team also actively and effectively communicated with the responsible NAPP staff to continue the implementation of the planned project activities.

Budget and Finance

In accordance with the TA Agreement the funding from the Islamic Development Bank were disbursed in 4 (four) tranches USD 50K, USD 75K, USD 75K and USD 20K respectively and totaling USD 220K. Additionally UNDP provided a co-financing in amount of USD 100K. The table below outlines the budget expenditure breakdown by outputs and delivery percentage. The current budget delivery is 93,75%

| Outputs/Components | IsDBI (USD) | UNDP (USD) | % Completion |
| --- | --- | --- | --- |
| Output 1. Market Gap analysis | 0,0 | 30,000 | 100,0% |
| Output 2. Drafting legal and regulatory documents. National Green Sukuk Framework UNDP Management fee | 156,400 13,600 | 50,000 | 95% |
| Output 3. Awarenessrising compaign UNDP Managemnet fee | 18,400 1,600 | 10,000 | 67% |
| Output 4. Capacity building and training UNDP Management fee | 27,600 2,400 | 10,000 | 100% |
| Total | 220,00 | 100,000 | 93,75% |

Fayzulla Salakhuddinov

Project Manager

https://www.williamfry.com/newsandinsights/news-article/2020/05/20/where-to-next-for-islamic-finance