Project Progress Report (2023 version)

项目进展报告（2023版）

Name of Project项目名称: Restoration of Degraded Natural Forests and

Soil Erosion Management Improvement in Erosion-Prone Regions of China

中国典型水土流失区退化天然林用地修复与管理

Date of report报告完成日期: Click or tap to enter a date.

A. PROJECT PROFILES项目概况

| Quantum Project ID编号 | 00119054 |
| --- | --- |
| Project overall duration项目总周期 | 2022.12.1--2027.12.1 |
| Location(s)执行地点 | Beijing, Xiaolongshan, Gansu Province; Wuxi County, Chongqing Municipality; Xishuangbanna area, Yunnan Province; Libo County, Guizhou Province; Changting County, Fujian Province, 北京，甘肃省小陇山，重庆市巫溪县，云南省西双版纳地区，贵州省荔波县，福建省长汀县 |
| Implementing partner执行伙伴 | NFGA 国家林草局 |
| Responsible party (if any) 责任方（如有） |  |
| UNDP Programme Officer UNDP项目官员 | Dr. Ma Chaode 马超德博士 |

| Gender Marker性别标记 (GEN 1/2/3) | GEN 2 |
| --- | --- |
| Relevant CPD 2021-2025 output 国别方案文件2021-2025的相关产出 | CPD Output 2.1: Adaptive policies developed at target level (subnational), financed and applied for nature-based systems to align with multilateral agreements and transboundary platforms. 国家方案文件产出2.1：在目标级（国家以下各级）制定适应性政策，为基于自然的系统提供资金并加以应用，以与多边协定和跨界平台保持一致。 |
| Relevant SP output 战略规划的相关产出 | SP Output 4.1 Natural resources protected and managed to enhance sustainable productivity and livelihoods. SP Output 4.2 Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions 产出4.1保护和管理自然资源，以提高可持续生产力和生计。 产出4.2为生物多样性、水、海洋和 气候提供公共和私有投资机制的解决方案 |

Guidance. Please ensure data below are in line with the UNDP Quantum system.

| Annual budget 年度预算 | 301,058.00 |
| --- | --- |
| Expenditure (to 27 Nov 2023) 项目支出（截至报告撰写日期） | 120,691.60 （截至2023年11月27日） |
| Delivery rate (to date) 执行率（截至报告撰写日期） | 40% （截至2023年11月27日） |

B. RESULTS结果

B.1 Results Towards the Annual Work Plan基于年度工作计划的进展和结果

Guidance.

- On the “Project outcome/output statement”, please stick to those project outcomes and outputs stated in the AWP. The reporting should be based on the first level of the structure.

- On the “Result, backed up by evidence and segregated data” columns, please focus on the results of the project (instead of the “process”) with credible evidence and segregated data. The report should also focus more on gender equality and women empowerment, digitalization, innovation and partnerships, as applicable.

- On the “Indicator” section, please stick to the the indicators, baselines, and final targets from the AWP, and provide the actual level.

说明

- 在“项目成果/产出说明”一列，请填写项目的年度工作计划中所确定的成果与产出。

- 在“有证据和分类数据支持的结果”栏中，请重点关注具有可信证据和分类数据的项目结果（而不是“过程”）。报告还应更多地关注性别平等和妇女赋权、数字化、创新和伙伴关系（如适用）。

- 在“指标”一列，请填写项目的年度工作计划中的指标、基线和最终目标，并提供实际水平。

| Project outcome/output statement 项目成果与产出 | Results, backed up by evidence and segregated data 结果、数据及证据 | Indicator 指标 | Baseline Level 基线水平 | Level as of end-2023 2023年底水平 | Annual Target Level 年度计划 |
| --- | --- | --- | --- | --- | --- |
| Outcome 1： Multi-level governance and landscape approaches for FLR and LDN in degraded NFUL areas enabled through strengthened policy frameworks and institutional capacities at national and subnational levels 成果1：通过加强国家和地方各级的政策框架和机构能力，实现在天然林退化区域对森林景观恢复和土地退化零增长的多层级治理和景观方法。 | Five landscapes have prepared and been executing their project work plan according to the TYWP. 五个景观区已经根据双年度工作计划制定并正在执行他们的项目工作计划。 | Indicator 4: Enabling environment strengthened, as measured by (a) a national level road-map for sustainable management of NFUL endorsed and supported by an improved policy framework; and (b) the number of landscapes NFUL strategies approved. 指标4：有利环境得到加强。衡量标准是：（a） 国家级的天然林用地可持续管理路线图得到批准，并得到改进后的政策框架的支持；以及 （b） 天然林用地景观战略的数量获得批准 | (a) Ecological Rehabilitation Program (ERP) updated in 2020; and (b) Provincial Forestry Bureaus plans are made according to the ERP. （a）生态修复工程（ERP）于 2020 年更新；以及 （b） 省林业主管部门根据生态恢复方案制定计划 | On-going 进行中 | N/A 不适用 |
| Output 1.1: National, provincial and local NFUL conservation statutes reviewed and amended, or new statutes introduced to promote FLR of NFUL. 产出1.1：审查和修订国家、省和地方天然林用地保护法规，或引入新法规，以促进天然林用地的森林景观恢复。 | National Policy Development Consultants for the national and the subnational have been recruiting to carry out updated policy gap analysis, and prepare policy briefs 招聘国家级和地方级的政策发展顾问，以开展最新的政策空缺分析，并编写政策简报 |  | 0 | On-going 进行中 | Policy gap analysis, and policy briefs 政策空缺分析，并编写政策简报 |
| Output 1.2: National-level roadmap for sustainable management of NFUL adopted by NFGA and transcribed into landscape level NFUL strategies with secured resources and mechanisms for implementation. 产出1.2：国家林草局采纳天然林用地可持续管理的国家路线图，并转化为具有保障资源和实施机制的景观层面天然林用地策略。 | National NFUL Roadmap Consultant has been recruited to carry out updated review national level strategies / plans for NFUL restoration. 正在聘请国家天然林用地（NFUL）路线图顾问对国家级NFUL恢复战略/计划进行最新审查。 |  | 0 | On-going 进行中 | Updated review national level strategies/plans for NFUL restoration. 更新了NFUL恢复的国家级战略/计划审查。 |
| Output 1.3: Indicator system for monitoring and evaluating the implementation of FLR of NFUL developed, demonstrated in the project landscapes, and adopted in other NFUL areas in China. 产出1.3：开发指标体系，用于监测和评估天然林用地森林景观恢复项目的实施，在五个景观区开展示范，并在中国其他天然林用地区域推广应用。 | Sub-contractor's service has been purchased to develop an indicator system for monitoring and evaluating the implementation of FLR of NFUL. 购买分包商的服务，以开发用于监测和评估NFUL FLR（森林景观恢复）实施情况的指标系统。 |  | 0 | On-going 进行中 | N/A 不适用 |
| Output 1.4: National and subnational institutional capacities strengthened for sustainable management of NFUL 产出1.4：加强国家和地方各级的机构能力，设计和实施天然林用地区域的多层级森林景观恢复治理。 | On 16 March, UNDP China delivered the training on UNDP-GEP project management for PMOs in Beijing. On 25-26 Sep, training was delivered to all stakeholders during the inception workshop in Changting, Fujian Province. On 10, Dec, training was delivered for NFGA and 5 landscapes in Chongqing. The training was focused on UNDP-GEF project management for PMOs. Altogether 150+ participants (30% female) joined these sessions. The presenters were from UNDP, experts, and 5 landscapers’ representatives, etc. 3月16日，开发计划署中国办事处在北京为项目办举办了开发计划署-全球环境方案项目管理培训。 9月25日至26日，在福建长汀举行启动研讨会上，向利益相关者提供了培训。 12月，在重庆举行5个景观区的培训。 上述培训的重点是项目管理。共有150多名参与者（约30%为女性）参加了这些会议。主讲人来自联合国开发计划署、专家和5个项目景观区的代表等。 | Indicator 5: Capacities of forestry institutions improved, as measured by increases in the cumulative values of the Capacity Development (CD) Scorecard for (a) NFGA, (b) Gansu, (c) Chongqing, (d) Yunnan, (e) Guizhou, (f) Fujian. 指标5：林业机构的能力得到提高。以（a）国家林草局、（b） 甘肃、（c） 重庆、（d） 云南、（e） 贵州、（f） 福建的能力发展计分卡累计值的增加来衡量。 | Cumulative CD scores: (a) NFGA: 28 (b) Gansu: 17 (c) Chongqing: 19 (d) Yunnan: 20 (e) Guizhou: 27 (f): Fujian: 20 累计CD分数： （a） 国家林草局：28 （b） 甘肃：17 （c） 重庆：19 （d） 云南：20 （e） 贵州：27 （f） 福建：20 | On-going 进行中 | Institutional capacity development plan, deliver capacity building to national and sub-national institutional stakeholders 机构能力发展计划，向国家和地方各利益相关方提供能力建设 |
| Outcome 2: Innovative, participatory FLR interventions demonstrated and upscaled in NFUL, facilitated by multi-level and multi-stakeholder landscape governance mechanisms 成果2：在多层级、多利益相关方的景观治理机制的推动下，在天然林用地区域示范及扩大创新的参与式森林景观恢复方法。 |  | Indicator 6: Local participation in FLR improved, as measured by the number of sustainable livelihood models operationalized through strengthened or new associations (e.g., cooperatives, women’s groups, enterprises, etc.) in the project landscapes, gender disaggregated. 指标6：改善当地对森林覆盖率的参与。以项目地区通过加强或新建协会（如合作社、妇女团体、企业等）实施的可持续生计模式的数量来衡量，按性别分类 | Limited or no existing sustainable livelihood model operational in the project landscapes 项目地现有的可持续生计模式有限或根本不存在 | On-going 进行中 | N/A 不适用 |
| Output 2.1: FLR demonstration management plans developed and endorsed by multi-level, multi-stakeholder landscape governance mechanisms 产出2.1：由多层级、多利益相关方的景观治理机制开发和认可的森林景观恢复示范管理计划。 | The project's PSC, NPMO, PPMO and LPMO has been set up. Multi-stakeholder, multi-level mechanisms has been established and operationalized. 项目已经建立指导委员会，国家级、省级和景观区的项目办。多层级多方利益相关方机制已经建立并投入运作。 |  | No 无 | On-going 进行中 | Multi-stakeholder, multi-level mechanisms 多层级多利益相关方 |
| Output 2.2. Sustainable livelihoods for local beneficiaries demonstrated and enhanced through capacity building and partnership building, with particular emphasis on gender mainstreaming 产出2.2：通过能力建设和伙伴关系建设（强调性别主流化），示范和加强当地受益者的可持续生计。 | PPMO and LPMO have been preparing to identify livelihood opportunities. 省级和地方级项目办正在准备去确定生计的机会 |  | No 无 | On-going 进行中 | Identify livelihood opportunities based on FLR demonstration plans 根据森林景观恢复的示范计划确定生计的机会 |
| Output 2.3. FLR demonstration and management plans implemented in the five project landscapes 产出2.3：在五个项目景观区实施森林景观恢复的示范和管理计划 | PPMO and LPMO have prepared to execute since the second year 项目办将从明年开始准备 | Indicator 7: Sustainable long-term flows of ecosystem services from NFUL enhanced, as measured by innovative participatory FLR approaches demonstrated on the project mainstreamed into the annual operating work plans of the five (5) provincial/municipal forestry bureaus. 指标7：天然林地生态系统服务的可持续长期流动得到加强。具体衡量标准是将项目中展示的创新参与式森林景观恢复方法纳入五省/市林草主管部门年度业务工作计划 | provincial/municipal Participatory FLR approaches not budgeted by orestry bureaus. 参与式森林景观恢复方法未编入 省/市林业主管部门预算 | Preparation 准备中 | N/A 不适用 |
| Output 2.4. Best practices of FLR innovative, participatory approaches upscaled in other NFUL areas based on results and lessons of demonstrations in project landscapes 产出2.4：总结项目创新的、参与式的森林景观恢复的成果和经验，形成最佳实践，推广到其他天然林用地区域。 |  |  | No 无 | N/A 不适用 | N/A 不适用 |
| Outcome 3: Incentive systems improved and expanded for durable investment in sustainable management of NFUL 成果3：改善和扩展天然林用地可持续管理的持久投资激励机制 |  |  |  | N/A 不适用 | N/A 不适用 |
| Output 3.1: Improved ecological compensation mechanisms formulated using targeted scenario analysis approaches and advocated for adoption in the project landscapes and in other NFUL in China. 产出3.1：利用目标情景分析法制定改善的生态补偿机制，并在项目景观区和中国其他天然林用地区域倡导推广应用。 |  | Indicator 8: NFUL conservation integrated into ecological compensation mechanisms, as measured by the number of existing or new ecological compensation mechanisms that integrate the value and services of NFUL and equitably target women beneficiaries. 指标 8：将天然林用地保护纳入生态补偿机制，以充分体现天然林用地服务价值和女性权益的现有的或者新增加的生态补偿机制的数量作为衡量标准。 | NFUL values and services are not integrated into existing ecological compensation mechanisms 天然林用地的价值和服务未纳入现有的生态补偿机制 | N/A 不适用 | N/A 不适用 |
| Output 3.2: Expanded types and sources of financing for sustainable management of NFUL through public-private-community partnerships 产出3.2：通过公私社区伙伴关系扩大天然林用地可持续管理的融资类型和来源。 | Guizhou Qiming Agricultural Technology Development Co. Ltd. had built ecological planting base of nearly 1333 ha for Chinese traditional medicine material Dendrobium Officinale, and created employment opportunity for local community. 贵州启明农业科技发展有限公司已建成中药材石斛生态种植基地近1333公顷，为当地社区创造了就业机会。 | Indicator 9: Stakeholder participation in FLR approaches expanded, as measured by the number of business enterprises in the project landscapes entering new public-private-community partnerships, each incorporating fair inclusion of women stipulations 指标 9：扩大利益相关方对森林景观恢复方法的参与。项目景观中加入新的公私-社区伙伴关系的私营企业数量，每种伙伴关系都包含公平纳入妇女的规定 | Limited application of FLR approaches by the stakeholders 利益相关方对森林景观恢复方法的应用有限 | Guizhou Qiming Agricultural Technology Development Co. Ltd. prepared to develop public-private-community partnership. 贵州启明农业科技发展有限公司拟发展公私合作伙伴关系。 | N/A 不适用 |
| Outcome 4: Integrated coordination, knowledge management, and monitoring and evaluation to enhance capacities for upscaling 成果4：综合协调、知识管理、监测与评估，以增强复制扩大的能力 | KAP baseline survey will be designed and conducted for 5 landscapes. More than 750 answers will be collected (50:50 gender balance). And the end-of-project KAP survey will be designed. 将在5个项目景观区开展KAP基线调查，计划收集750多个答案（男女比例大致平等），确定KAP的项目终期调查的。 | Indicator 10: Key stakeholder groups’ understanding of the value of NFUL conservation improved, as measured by results of knowledge, attitude and practices (KAP) surveys (disaggregated by women, ethnic minorities, and youth), among the following stakeholder groups: (a) Subnational governmental stakeholders (b) Local communities (c) Private sector. 指标 10：根据知识、态度和做法（知识、态度和实践）调查结果（按妇女、少数民族和青年分类），在以下利益攸关方群体中提高主要利益攸关方群体对天然林使用和土地保护价值的认识： （a） 国家以下各级政府利益相关方 （b） 地方社区 （c） 私营部门 | Baseline to be established in the first year. 基线将在第一年确定 | - KAP surveys will be conducted, covering stakeholders among NFGA, and five landscapes. 2) KAP surveys report will be prepared and the KAP baseline was established. 1） KAP调查将涵盖NFGA和五个景观区的各利益相关方。 2） 将编制KAP调查报告，并确定KAP基线。 | Establish the baseline 基线建立 |
| Output 4.1: Project implementation overseen by a representative PSC, and durability of project results guided through development of a project sustainability plan. 产出4.1：通过项目指导委员会的管控确保项目实施，通过项目可持续计划的实施确保项目成果持久性。 | Project board was set up, and 1st PSC meeting was convened on 25 Sep, 2023. The PSC has approved in principle both the Project Inception Report and the TYWP (2023-2024), and agreed the adaptive adjustments according to the actual needs of the implementation. 成立了项目指导委员会，并于2023年9月25日召开了项目指导委员会第一次会议。指导委员会原则上批准了项目启动报告和双年度工作计划（2023-2024）》，并同意根据实施的需要进行适应性调整。 |  | No 无 | PSC was set up, and PSC approved the TYWP and inception report at the 1st PSC meeting. 指导委员会成立，指导委员会在第一次会议上批准了启动报告和双年度工作计划。 | Set up PSC, arrange 1st PSC meeting 建立项目指导委员会， 组织第一次会议 |
| Output 4.2: Knowledge management and communication systems implemented for supporting scaling up of best practices. 产出4.2：实施知识管理和传播系统，推广最佳实践。 | Subcontractor service of knowledge management was purchased to develop the knowledge management strategy and action plan. 知识管理的分包商服务，以制定知识管理战略和行动计划。 | Indicator 11: Knowledge sharing effectiveness improved, as measured by (a) the cumulative number of visits/downloads of knowledge products on Internet and social media platforms, and (b) the number of people reached through dissemination of knowledge products, participation in workshops, etc. (gender disaggregated) 指标 11：提高知识共享的有效性。衡量标准为：（a）互联网和社交媒体平台上知识产品的累计访问量/下载量，以及（b）通过传播知识产品、参加讲习班等方式接触的人数（按性别分类） | No knowledge sharing online platform, limited concerted effort exists in promoting knowledge management and dissemination of FLR best practices 没有知识共享在线平台，在促进知识管理和传播森林景观恢复最佳做法方面的力量有限 | Sub-contractor began to prepare Knowledge Management strategy and action plan, based on the KAP survey 分包商开始根据KAP调查结果制定知识管理战略和行动计划 | Sub-contract service of Knowledge Management 知识管理分包服务 |
| Output 4.3: Inclusive participation and adaptive management supported through participatory monitoring and evaluation of the gender action plan, SESP, stakeholder engagement plan, and other safeguard management frameworks and plans. 产出4.3：通过参与式监测评估项目成果包括实施性别平等行动计划、社会与环境筛查程序、利益相关方参与计划和其他保障管理框架及计划等，支持包容性参与和适应性管理。 | The Gender and Safeguards Consultant has been recruited. And the project safeguard plan was prepared, and the assessment was conducted in the 5 landscapes. 招聘了性别与保障专家，编制项目保障方案，对5个项目景观区开展评估调研。 | According to UNDP-GEF related policy 根据UNDP-GEF的相关政策 | During the PPG, the SESP, and stakeholder engagement plan were prepared. PPG期间，编制了SESP和利益相关方参与计划。 | Preparation 准备中 | N/A 不适用 |

B.2 Project Impact项目影响

Guidance: It is crucial to maintain a broader perspective that connects the dots between overall project activities, outputs, outcomes, and impact. In Section B.2, please go beyond discussing immediate activities and focus on the long-term impact of the project. Use 1-2 paras (more are welcome) to discuss (a) how this project have contributed to broader societal, economic, or environmental goals, and/or (b) how the project informs policy-making process in China and/or (c) how it contributes to national and local priorities, etc.

说明：保持更广泛的视角，将整个项目活动、产出、结果和影响联系起来，这一点至关重要。在B.2节中，请重点关注项目的长期影响。使用1-2段（欢迎更多）讨论（a）该项目如何为更广泛的社会、经济或环境目标做出贡献，和/或（b）该项目是如何为中国的决策过程提供信息的，和/或者（c）它是如何为国家和地方的优先事项做出贡献的，等等。

After the first-year implementation, the project has moved forward the tasks, in terms of strengthening institution, and innovative participatory FLR interventions. (1) The project’s institutional structure has been set up at all levels, from PCS, National PMO (NPMO), Provincial Project Management Offices (PPMOs) to Landscapes Project Management Offices (LPMOs), which strengthening the multi-level governance approach for forest landscape restoration and sustainable management.  (2) Project inception workshops were organized in the five landscapes, the TYWP was agreed by PSC, and FLR demonstration management plans have been developed and incorporated into the NFGA’s and five landscapes work for managing NFUL areas in China, and endorsed by multi-level, multi-stakeholder landscape governance platform.

项目实施第一年，在创新的参与式森林景观恢复方面加强了机构建设。（1） 项目已在各级建立机构，从指导委员会到国家级、省级、区级以及景观区的项目办公室，加强了森林景观恢复和可持续管理的多层级治理机制。（2） 项目在五个景观区组织了项目启动研讨会，项目指导委员会批准了双年度工作计划，森林景观修复示范管理计划已经制定并纳入了国家林草局生态中心和五个景观区的工作中，并形成了多层级多利益相关方的景观治理平台。

Through the design and deliver baseline Knowledge, Attitudes and Practices (KAP) survey  more than 750 answers (50:50 gender balance) were received from multi-stakeholders in NFGA and 5 landscapes, the KAP baseline of the project was defined as a reference to develop knowledge management strategy and action plan. The gender and safeguards assessments were conducted in 5 Landscape, each incorporating methodology and content consistent with the requirements of a scoped Environmental and Social Impact Assessment – ESIA, as per UNDP SES Policy – and applying FPIC where relevant, which promote the awareness of the gender mainstreaming and risks control management.

通过知识、态度和实践（KAP）问卷调查，覆盖国家层面和5个景观区层面的多层级多利益相关方，收集约750多份答卷（男女人数：大致相同），将为制定知识管理战略和行动计划提供参考。在5个景观区中开展性别和社会环境保障现状的评估，每个评估都包含符合环境和社会影响评估要求的方法和内容，符合联合国开发计划署社会和环境的标准，并在相关情况下应用自由、事先和知情同意的原则，以提高对性别主流化和风险控制管理的认识。

C. RISK风险

Guidance.

- Please populate the offline matrix with those risks as identified on the pro doc, and update the status. Please bring in or strike out a risk, if it’s recently found or addressed. Be sure to distinguish “cause”, ‘’event”, “impact”. i.e. Because of [cause], [event] may occur, which would lead to [impact].

- Following the finalization and submission of this report, UNDP Programme Officer shall update the risks in Quantum.

说明

•请在表格中填入项目文件中确定的风险，并更新状态。如果最近发现或解决了风险，请引入或删除风险。一定要区分“成因”、“活动”、“影响”。即由于[原因]，可能发生[事件]，从而导致[影响]。

•本报告定稿并提交后，开发计划署项目官员应更新Quantum表中的风险。

| # | Category 分类 | Cause 成因 | Event 活动 | Impact 影响 | Risk Valid Period 风险有效期 | Risk Level - Impact & Likelihood 风险水平 影响和可能性 | Treatment(s) 措施 | Risk Owner 风险责任人 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Social and Environmental 社会与环境 | The project involves the introduction of policies, regulations, management plans, and compensation measures. 项目涉及政策、法规、管理计划和补偿措施的出台。 | The project – through introduction of policies, statutes, management plans and compensation measures, may impact on the lands, natural resources, territories, and traditional livelihoods of ethnic minorities in ways that lead to erosion of cultural heritage, and infringement of human rights. 风险 1：通过引入政策、法规、管理计划和补偿措施，项目可能会对少数民族的土地、自然资源、领地和传统生计产生影响，导致文化遗产受到侵蚀，人权受到侵犯。 | These new policies, regulations, management plans, and compensation measures may impact the livelihoods of ethnic minorities, potentially leading to further erosion of cultural heritage and infringement of human rights. 这些新的政策、法规、管理计划和补偿措施可能会影响少数民族的生计，可能导致文化遗产的进一步侵蚀和人权的侵犯 | Ongoing 09/01/2023 to 31/12/2025 | I = 3 L = 3 | The project is conducting an investigation to gather comprehensive site-level data in five project landscapes, especially in Guizhou and Yunnan to review this risk rating. 项目正在进行调查，以收集 五个项目景观区（特别是在贵 州和云南两个景观区）的综合 水平数据， 以审查风险评 级。 | Gender-Safeguards Specialist, M&E-KM Officer 性别与社会环境保障专家、监测评估与知识管理官员 |
| 2 | Social and Environmental 社会与环境 | Project related activities and the introduction of new management plans, policies, and regulations, may restrict local people from accessing resources, especially forest resources. 与项目相关的活动以及新的管理计划、政策和法规的出台，可能会限制当地人获得资源，尤其是森林资源。 | Restricted access to resources as a result of new management plans, statutes and policies, might lead to economic displacement of communities, and this could be exacerbated if the anticipated livelihood benefits to local people (including from ethnic minorities) do not materialize as planned. 风险 2：由于新的管理计划、法规和政策，资源的获取受到限制，这可能会导致社区经济失衡，如果当地人（包括少数民族）预期的生计利益不能按计划实现，这种情况可能会更加严重。 | Due to restrictions on the use of forest resources, local residents, especially minority groups, may face changes in their lifestyles and economic displacement. This could affect the project objective of respecting the rights of indigenous peoples and local communities. 由于对森林资源使用的限制，当地居民，特别是少数民族，可能面临生活方式的改变和经济流离失所。这可能影响到尊重原住民和当地社区权利的项目目标。 | Ongoing 09/01/2023 to 31/12/2024 | I = 3 L = 3 | 2 actions were taken: - An Indigenous Peoples Planning Framework (IPPF) has been prepared and annexed to the Project Document. - The project is conducting a participatory survey in natural forest protection and restoration areas to find whether local people can still sustainably utilize some forest resources according to regulations or not. 采取了2项行动： •已经编制了原住民规划框架（IPPF），并作为项目文件的附件。 •在天然林保护和恢复地区进行参与式调查，以了解当地人是否仍能根据法规可持续利用森林资源。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Social and Environmental Safeguard Specialist, M&E-KM Officer, Landscape Coordinators 项目经理、国家技术顾问、可持续森林管理专家、性别与社会环境保障专家、监测评估与知识管理官员、景观协调员 |
| 3 | Social and Environmental 社会与环境 | Due to a lack of awareness or corresponding activities, women may have fewer opportunities to participate in forest ecological restoration projects compared to men 由于缺乏认识或相应的活动，与男性相比，女性参与森林生态恢复项目的机会可能更少 | Project activities and approaches might not fully incorporate or reflect views of women and girls and ensure equitable opportunities for their involvement and benefit; and there is a risk that a prolonged or recurrent COVID-19 pandemic would exacerbate gender inequality. 风险 3：项目活动和方法可能无法充分纳入或反映妇女和女童的观点，也无法确保她们有公平的机会参与其中并从中受益；COVID-19大流行病的长期或反复发生可能会加剧性别不平等。 | This could affect various equal opportunities for the participation of women and children in ecological restoration activities, further impacting their empowerment. 这可能影响妇女和儿童参与生态恢复活动的各种平等机会，进一步影响赋予他们权力。 | Ongoing 09/01/2023 to 31/12/2026 | I = 3 L = 3 | 1 actions were taken: - On September 26, 2023, Gender-Safeguards Specialist conducted specialized gender training and discussion activities for decision-makers and staff in five target landscape areas in Changting County, to enhance awareness of female participation and gender mainstreaming in project implementation 采取了1项行动： •2023年9月26日，性别与社会环境保障专家在长汀县为五个目标景观区的决策者和工作人员进行了专门的性别培训和讨论活动，以提高对项目实施中女性参与和性别主流化的认识 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Gender-Safeguards Specialist 项目经理、国家技术顾问、可持续森林管理专家、性别与社会环境保障专家 |
| 4 | Social and Environmental 社会与环境 | The demonstration intervention area is not located within the protected area, but certain portions of the target landscape are classified as critical ecological functional zones. Improperly designed project activities or policies may pose a risk of environmental damage." 项目区不在保护区内，但目标景观的某些部分被归类为关键生态功能区。项目活动或政策设计不当可能造成环境破坏的风险。 | Poorly designed or executed project activities could damage environmentally sensitive areas, including through the introduction of invasive alien species during forest land restoration. 风险 4：设计或执行不当的项目活动可能会破坏环境脆弱地区，包括在林地恢复过程中引入外来入侵物种。 | Poorly designed project activities may trigger widespread environmental risks, such as soil erosion, landslides, etc., especially in environmentally sensitive areas. 设计不当的项目活动可能引发广泛的环境风险，如土壤侵蚀、山体滑坡等，尤其是在环境敏感地区。 | Ongoing 09/01/2023 to 31/12/2027 | I=4 L=2 | Two actions were taken: - Biophysical characteristics of the five project target landscapes, as well as locations and severities of degraded natural forest areas, completed restoration work and current priorities of national and local forest management entities have been analyzed during the PPG phase and documented into landscape profiles, which are annexed to the project document - We are carrying out a survey on the environmental risks, triggered by poorly designed or executed project activities, such as soil erosion, landslides, etc., especially in environmentally sensitive areas. 采取了两项行动： •在项目准备阶段，对五个项目目标景观的生物物理特征、退化天然林区的位置和严重程度、已完成的恢复工作以及国家和地方森林管理实体的当前优先事项进行了分析，并将其记录在项目文件的景观简介中。 •我们正在对设计或执行不当的项目活动引发的环境风险进行调查，如土壤侵蚀、山体滑坡等，尤其是在环境敏感地区。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Environmental Safeguard Specialist, M&E-KM Officer, Landscape Coordinators 项目经理、国家技术顾问、可持续森林管理专家、性别与社会环境保护专家、监测评估与知识管理官员、景观协调员 |
| 5 | Social and Environmental 社会与环境 | Climate change-induced temperature rise and changes in precipitation patterns may impact the growth and distribution of tree species, with certain species potentially facing challenges in adapting to new climate conditions. Droughts and extreme weather events triggered by climate change could lead to disaster risks such as forest fires, soil erosion, and landslides in natural forest ecosystems. 气候变化引起的气温上升和降水模式的变化可能会影响树种的生长和分布，某些物种在适应新的气候条件方面可能面临挑战。气候变化引发的干旱和极端天气事件可能导致自然森林生态系统中的森林火灾、土壤侵蚀和山体滑坡等灾害风险。 | Climatic unpredictability, periodic droughts, changes in rainfall distribution, altered frequency of extreme weather events, rising temperatures may affect project results, restoration of degraded forest lands; and a potential economic downturn as a result of a prolonged or recurrent COVID-19 pandemic (or similar) may increase the vulnerability and coping capacities of local government units and communities. 风险 5： 气候的不可预测性、周期性干旱、降雨分布的变化、极端天气事件频率的改变以及气温的升高可能会影响项目成果、退化林地的恢复；COVID-19 大流行病（或类似疾病）的长期或反复发生可能导致的经济衰退可能会增加地方政府单位和社区的脆弱性和应对能力。 | The risks caused by climate change may increase the difficulty of natural forest restoration and decrease the effectiveness of protection, thereby affecting the outcomes of the project. 气候变化带来的风险可能会增加天然林恢复的难度，降低保护的有效性，从而影响项目的成果。 | Ongoing | I=3 L=3 | Existing climate-risk management systems and structures in the project target landscapes were incorporated into the risk mitigation measures. These include early warning systems (including automatic weather stations operated by provincial and county level disaster management entities, wildfire lookout towers operated by county forest bureaus), county and village level emergency response teams, etc. 项目景观区现有的气候风险管理系统和结构已纳入风险缓解措施。其中包括预警系统（包括省和县一级灾害管理实体运营的自动气象站、县林业局运营的野火了望台）、县和村一级应急小组等。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Landscape Coordinators 项目经理、国家技术顾问、可持续森林管理专家、景观协调员 |
| 6 | Social and environmental 社会与环境 | The prevalence of COVID-19 may affect project activities and project personnel 新冠肺炎的流行可能会影响项目活动和项目人员 | Local community members involved in project activities may be at a heightened risk of COVID-19 virus exposure, e.g., stakeholder meetings, workshops and trade fairs, community field work, etc. 风险 6： 参与项目活动的当地社区成员接触 COVID-19 病毒的风险可能会增加，例如利益相关方会议、研讨会和交易会、社区实地工作等。 | Training meetings, workshops, field work and other project activities may be delayed due to COVID-19 由于新冠肺炎，培训会议、研讨会、现场工作和其他项目活动可能会推迟 | Completed 已经结束 | I=1 L=1 Low | The COVID-19 around the world has been declared to be over, and has been downgraded to Category B in China, so it is impossible to have any impact on project activities and local community members. 世界各地已经宣布新冠肺炎结束，中国的风险已降级为B类，因此不可能对项目活动和当地社区成员产生任何影响。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Landscape Coordinators, Social and Environmental Safeguard Specialist 项目经理、国家技术顾问、可持续森林管理专家、景观协调员、性别与社会环境保障专家 |
| 7 | Social and environmental 社会与环境 | Harmful pesticides and other agricultural chemicals such as insecticides may be used in the forest restoration activities of this project 本项目的森林恢复活动中可能使用有害农药和杀虫剂等其他农用化学品 | Workers involved in field restoration activities might be exposed to hazards in their use and handling of pesticides and other agrochemical inputs without adequate personal protective equipment, training and safeguards, or which might be subject to international bans. 风险 7： 参与田间恢复活动的工人在使用和处理杀虫剂及其他农业化学投入品时，如果没有足够的个人防护设备、培训和保障措施，或可能受到国际禁令的限制，可能会面临危险。 | Pesticides are likely to be used in some of the restoration activities, e.g., clearing invasive alien species. Obsolete pesticide stocks are common in many countries. And workers could be ill-informed about the hazards of pesticides and correct health and safety procedures. 农药可能用于一些恢复活动，例如清除外来入侵物种。废弃农药库存在许多国家很常见。工人可能对杀虫剂的危害以及正确的健康和安全程序知之甚少。 | Ongoing 09/01/2023 to 31/12/2025 | I=3 L=3 Moderate | Through communication and investigation with local residents in five target landscape restoration areas, it was found that workers involved in the application of agricultural and forestry chemical agents undergo rigorous training and are equipped with appropriate protective equipment. 通过与五个景观区当地居民沟通和调查，发现参与农林化学制剂应用的工人接受了严格的培训，并配备了适当的防护设备。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Landscape Coordinators, Social and Environmental Safeguard Specialist. 项目经理、国家技术顾问、可持续森林管理专家、景观协调员、性别与社会环境保障专家。 |
| 8 | Social and environmental 社会与环境 | Unsafe use and handling of pesticides and associated hazardous wastes generated (e.g., used containers) may release harmful pollutants to the environment. 杀虫剂和产生的相关危险废物（如用过的容器）的不安全使用和处理可能会向环境释放有害污染物。 | Project interventions involving pesticides and other agrochemical inputs may result in release of pollutants to the environment and in the generation of hazardous waste. 风险8：涉及杀虫剂和其他农用化学品投入的项目干预措施可能会导致污染物排放到环境中并产生危险废物。 | N/A 不适用 | Completed 09/01/2023 to 31/12/2023 | I=2 L=2 | Two actions were taken: - Chemical hazard assessments have been carried out as part of developing FLR Demonstration and Management Plans for each intervention supported by the project. - The project is conducting an investigation in five landscape areas regarding the use of fertilizers and pesticides, as well as their potential environmental impacts. 采取了两项行动： •化学品危害评估是为项目支持的每项干预措施制定FLR示范和管理计划的一部分。 •该项目正在五个景观区就化肥和农药的使用及其潜在的环境影响进行调查。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Gender and Safeguard Specialist 项目经理、国家技术顾问、可持续森林管理专家、性别与社会环境保障专家 |
| 9 | Social and environmental 社会与环境 | The activities implemented with the complementary funding provided by NFGA, provincial forestry bureaus, and the private sector may not be fully consistent with U the relevant social and environmental standards and principles of UNDP 利用国家林草局、省级林业主管部门和私营部门提供的补充资金开展的活动可能不会完全符合联合国开发计划署的相关社会和环境标准和原则 | NFGA, and the provincial forestry bureaus will implement the project through USD 26.98 million in recipient government co-financing, and private sector partners will be engaged for delivery of Output 3.2. Co-financed activities may not be fully consistent with UNDP SES, potentially triggering social and environmental risks without adequate mitigation measures in place. 风险9： 国家林草局以及各省林业主管部将通过受援国政府共同出资 2,698 万美元来实施本项目，并将聘请私营部门合作伙伴来实现成果3.2。共同出资的活动可能不完全符合联合国开发计划署的社会和环境标准，如果没有适当的缓解措施，可能会引发社会和环境风险。 | This may trigger social and environmental risks, including community opposition, environmental degradation, and other issues, thereby adversely affecting the project 这可能引发社会和环境风险，包括社区反对、环境退化和其他问题，从而对项目产生不利影响 | Ongoing 09/01/2023 to 31/12/2025 | I = 3 L = 2 | On September 26, 2023, Gender and Safegurad Specialist conducted specialized training and discussion activities for multiple stakeholders including NFGA, provincial forestry bureaus, and the private sector, providing a detailed interpretation of social and environmental standards of the UNDP. 2023年9月26日，性别与社会环境保障专家为包括国家林草局、省级林业主管部门和私营部门在内的多利益相关方进行了专门的培训和讨论活动，详细解释了联合国开发计划署的社会和环境的标准。 | Gender and Safeguard Specialist 性别和社会环境保障专家 |
| 10 | Operational, Strategic 运营策略 | Local people are conservative and unwilling to accept the concept and approaches of project implementation 当地人比较保守，不愿意接受项目实施的理念和方法 | Local communities resistant to changing their approaches and practices, not seeing the value in engaging with approaches promoted by the project 当地社区抵制改变他们的方法和做法，没有看到参与项目推广的方法的价值 | The primary beneficiaries of the project are the local communities in the target landscapes. Lack of genuine participation could impact the effectiveness and sustainability of the project. 该项目的主要受益者是景观区的当地社区。缺乏真正的参与可能会影响项目的有效性和可持续性。 | Ongoing 09/01/2023 to 31/12/2024 | I = 3 L = 3 | Sustainable Forest Management Specialist conducted systematic training for local community representatives from the five landscape restoration areas, aligning with the project's principles and primary objectives. This training, coupled with insights into community development, aimed to help them realize the potential benefits the project could bring to the local community and its residents, thereby mobilizing their enthusiasm for project participation. 可持续森林管理专家根据项目的原则和主要目标，对来自五个景观恢复区的当地社区代表进行了系统培训。这种培训，再加上对社区发展的见解，旨在帮助他们认识到该项目可能给当地社区及其居民带来的潜在好处，从而调动他们参与项目的热情。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, 项目经理，国家技术顾问，可持续森林管理专家， |
| 11 | Operational 运营 | Local people in landscape community do not fully understand the project philosophy and approaches, thus failing to fully fulfill some of the project guidelines and certain criteria 景观社区的当地人没有完全理解项目理念和方法，因此未能完全满足一些项目指南和某些标准 | Capacity building efforts not sufficiently effective in facilitating changes in local practices, or farmers unable to fulfill certain criteria (e.g., quality, reliable supply, etc.). 能力建设工作在促进当地做法的改变方面不够有效，或者农民无法满足某些标准（如质量、可靠供应等）。 | Building capacities and shifting attitudes and practices among local communities will require concerted focus. 地方社区之间的能力建设以及态度和实践的转变需要协调一致。 | Ongoing 09/01/2023 to 31/12/2025 | I = 3 L = 2 | The project is conducting systematic training for local community representatives from the five landscape restoration areas to help them understand the project philosophy and approaches. 项目正在对来自五个景观区的当地社区代表进行系统培训，以帮助他们了解项目理念和方法。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Landscape Coordinators 项目经理、国家技术顾问、可持续森林管理专家、景观协调员 |
| 12 | Political, Regulatory 法规法制 | The government did not approve the proposed policy reforms during the project implementation period 在项目实施期间，政府没有批准拟议的政策改革 | The legislative approval process does not match the project implementation timeframe 立法审批流程与项目实施时间表不一致 | If proposed policy reforms are not instituted within the project lifespan, some of the momentum gained could be lost when GEF funding ceases. 如果拟议的政策改革没有在项目期限内实施，那么当全球环境基金的资金停止时，所获得的一些动力可能会丧失。 | Ongoing 09/01/2023 to 31/12/2025 | I = 3 L = 3 | Two actions were taken: - The National Forestry and Grasslands Administration (NFGA), the lead Implementing Partner for the project, has been actively involved throughout the project preparation phase, and the project was developed to provide incremental value to the ongoing National Forest Protection Program. - The subnational forestry bureaus in the project landscapes report directly to the NFGA, and subnational policy improvements are envisaged to be directly linked to those made at the national level. Therefore, proposed policy reforms and momentum policy will be completed on schedule. 采取了两项行动： •国家林草局（NFGA）是该项目的主要实施伙伴，在整个项目准备阶段一直积极参与，该项目的开发旨在为正在进行的国家森林保护计划提供增量价值。 •项目景观区的林业主管部门直接向国家林草局报告，国家以下政策的改进预计将与国家级的政策改进直接挂钩。因此，拟议的政策改革将如期完成。 | NFGA, Project Board, Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Landscape Coordinators 国家林草局、项目指导委员会、项目经理、国家技术顾问、可持续森林管理专家、景观协调员 |
| 13 | Political, Operational, Regulatory 政策， 运营 | The new ecological compensation mechanism may not be accepted 新的生态补偿机制可能不会被接受 | Fund management entities reluctant to amend or introduce new ecological compensation mechanisms. 基金管理实体不愿修改或引入新的生态补偿机制。 | The values and services of NFUL can not be introduced to the landscape restoration areas, which may affect the objective of the project. 天然林用地的价值和服务不能引入景观修复区域，这可能会影响项目的目标。 | Ongoing 09/01/2023 to 31/12/2025 | I = 2 L = 3 | The project is confirming whether fund management entities including The National Forestry and Grasslands Administration (NFGA) and local governments will be willing to amend or introduce new ecological compensation mechanisms or not. 项目正在确认包括国家林草局（NFGA）和地方政府等是否愿意修改或引入新的生态补偿机制。 | NFGA, Project Board, Project Manager 国家林草局、项目指导委员会、项目经理 |
| 14 | Strategic, Operational 策略，运营 | The project landscapes are situated in five different provinces, with some differences in socioeconomic conditions and institutional capacities. They cannot fully achieve or delay the project objectives in a consistent timeframe 项目景观位于五个不同的省份，在社会经济条件和机构能力方面存在一些差异。他们无法在一致的时间内完全实现或延迟项目的目标 | Uneven and/or delayed achievement of project objectives in the five project landscapes 五个项目景观区项目目标的实现不均衡和/或延迟 | This may affect the overall progress of achieving objectives at a project level 这可能会影响项目层面实现目标的总体进度 | Ongoing 09/01/2023 to 31/12/2025 | I = 3 L = 4 | Five management offices have been established in the five target landscape areas for the project. The recruited coordinators and relevant staff will all work under the guidance of the Project Management Office. In addition, the State Forestry and Grassland Administration will centrally manage and coordinate the work in the five target landscape areas. These measures can ensure the simultaneous coordination and implementation of project activities and related policies. 项目的五个景观区域设立了五个管理办公室。招聘的协调员和相关工作人员都将在项目管理办公室的指导下工作。此外，国家林草局将集中管理和协调五个景观区的工作。这些措施可以确保项目活动和相关政策的同时协调和实施。 | NFGA, Project Board, Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, Landscape Coordinators 国家林草局、项目指导委员会、项目经理、国家技术顾问、可持续森林管理专家、景观协调员 |
| 15 | Operational, Organizational 运营，管理 | The landscape coordinators of local forestry bureaus may lack the time or ability to effectively coordinate project activities, especially for some sub national co-financing contributions. 地方林业主管部门的景观协调员可能缺乏时间或能力来有效协调项目活动，特别是对于一些地方共同融资捐款。 | Insufficient coordination at the local level and a lack of ownership can result in inadequate or insufficient monitoring and maintenance of restored areas. 地方协调不足和缺乏自主权可能导致对恢复地区的监测和维护不足或不足。 | This may have an impact on the effective restoration and monitoring of landscape restoration areas 这可能会对景观区的有效恢复和监测产生影响 | Ongoing 09/01/2023 to 31/12/2024 | I = 3 L = 3 | One action was taken: - Provincial project management offices (PMOs) have been established through co-financing contributions in each of the target landscapes to provide a direct linkage to NFGA oversight at the central level. 采取了一项行动： 通过在每个目标地区共同出资，建立了省级项目管理办公室，以便与国家林草局的监督建立直接联系。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist,项目经理、国家技术顾问、可持续森林管理专家 |
| 16 | Financial, Political 财务， 政治 | The funds for national and sub national government programs funded by national and local governments have not been in place in a timely manner or the amount is insufficient 国家和地方政府资助的国家和地方各级政府项目资金没有及时到位或数额不足 | Co-financing contributions, including those from the private sector, were not realized as planned 共同捐款，包括来自私营部门的捐款，没有按计划实现 | Insufficient or untimely Co-financing contributions will affect the effective implementation of project activities | Ongoing 09/01/2023 to 31/12/2025 | I = 3 L = 2 | The project has once again discussed with two private sector entities, including Menghai Jinsha Agricultural Technology Development Co., Ltd. and Guizhou Qiming Agricultural Technology Development Co., Ltd. Both companies have reconfirmed their co-financing contributions. 项目再次联系两家私营企业（包括勐海金沙农业技术开发有限公司和贵州启明农业技术开发股份有限公司有限公司）。两家公司都再次确认了共同出资。 | NFGA, Subnational Forestry Bureaus, UNDP CO, Project Manager, National Technical Advisor, Sustainable Forest Management Specialist 国家林草局、地方林业主管部门、UNDP、项目经理、国家技术顾问、可持续森林管理专家 |
| 17 | Operational, Financial 运营，财务 | The COVID-19 or other public health events may have an impact on the project activities 新冠肺炎或其他公共卫生事件可能对项目活动产生影响 | Impacts of ongoing COVID-19 pandemic or similar public health crisis on the continuity and delivery of the project. 持续的新冠肺炎大流行或类似公共卫生危机对项目连续性和交付的影响。 | Project implementation activities could be suspended or delayed in case of recurrence of the COVID-19 pandemic or similar. training, field work, and workshops 如果新冠肺炎大流行或类似情况再次发生，项目实施活动可能会暂停或推迟。培训、实地工作和研讨会 | Completed 完成 | I = 3 L = 3 | Two actions were taken: - The COVID-19 has been controlled in China and has been downgraded to Category B and Category B. - The UNDP CO and the NFGA will guide project responses through proactive correspondence for ongoing situations, as required. 采取了两项行动： •新冠肺炎已在中国得到控制，并已降级为乙类。 •UNDP和国家林草局将根据需要，通过积极主动的沟通，指导项目应对工作。 | UNDP CO, NFGA UNDP 国家林草局 |
| 18 | Financial 财务 | The macroeconomic externalities such as exchange rate fluctuations and a possible economic recession will occur during project implementation. 项目实施过程中将出现宏观经济外部因素，如汇率波动和可能的经济衰退 | Impacts of exchange rate fluctuations and/or a possible global economic recession on project delivery. 汇率波动和/或可能的全球经济衰退对项目交付的影响。 | Project delivery may be impacted by macroeconomic externalities such as exchange rate fluctuations and a possible economic recession. 项目交付可能受到宏观经济外部因素的影响，如汇率波动和可能的经济衰退。 | Ongoing 09/01/2023 to 31/12/2024 | I = 3 L = 2 | Two actions were taken: - The Chinese economy has demonstrated a robust recovery momentum in 2023. In just a few short months, it has undergone a transformation from the low point of the pandemic to a rapid upturn. This is not expected to have a significant impact on the project. - GEF-financed projects have been implemented in China over the past decade with limited impacts associated with currency fluctuation. Inflation rates in recent years been close to 2%. 采取了两项行动： •2023年，中国经济呈现强劲复苏势头。在短短几个月内，它经历了从疫情低谷到迅速好转的转变。预计这不会对项目产生重大影响。 •过去十年，全球环境基金资助的项目在中国实施，但与货币波动相关的影响有限。近年来的通货膨胀率接近2%。 | UNDP, NFGA UNDP 国家林草局 |
| 19 | Organizational, Social and environmental, Political 组织、社会和环境、政治 | one or more of the co-financing private sector companies fail to meet UNDP’s Social and Environmental Standards in project implementation. 一家或多家共同出资的私营部门公司在项目实施中未能达到联合国开发计划署的社会和环境标准 | Unfavorable environmental, social and governance (ESG) related issues arise with one or more of the co-financing private sector companies, due to a failure to meet UNDP’s Social and Environmental Standards in project implementation. In particular issues related economic displacement, conflict in land tenure and/or ownership, conflict with ethnic minorities, exposure to hazardous chemicals. 一家或多家共同融资的私营部门公司由于在项目实施中未能达到开发署的社会和环境标准，出现了与环境、社会和治理相关的不利问题。特别是与经济流离失所、土地保有权和（或）所有权冲突、与少数民族的冲突、接触危险化学品有关的问题。 | Potential adverse social and/or environmental impacts could undermine the gains achieved on the project. Poor publicity for UNDP, potentially impacting the viability of the cooperation with the private sector co-financing company. 潜在的不利社会和/或环境影响可能会破坏项目取得的成果。 开发计划署宣传不力，可能影响与私营部门共同融资公司合作的可行性。 | Ongoing 09/01/2023 to 31/12/2026 | L=2 I=3 | Two actions were taken: - The project has invited private sector co-financing companies as members of the multi-stakeholder, multi-level landscape mechanisms. - On September 26, 2023, Gender and Safegurad Specialist and UNDP Staff conducted systematic training for stakeholders, including private sector co-financing companies, for the five landscape restoration areas to explain the UNDP social and environmental standards and principles. 采取了两项行动： •该项目邀请私营部门共同融资公司作为多方利益相关方、多层级景观机制的成员。 •2023年9月26日，性别与社会环境保障专家和联合国开发计划署工作人员为包括私营部门共同融资公司在内的利益相关方准备了系统培训，以解释联合国开发署的社会和环境标准和原则。 | Social and environmental Safeguard Specialist, Project Manager, UNDP CO 性别与社会环境保障专家，项目经理，UNDP |
| 20 | Organizational, Regulatory, Political 组织、监管、政治 | The co-financing private sector companies did not comply with relevant laws or regulations 共同融资的私营企业不符合相关法律法规 | One of more of the co-financing private sector companies violates national law or disputes arise with local government agencies or project-affected communities. 一家或多家共同融资的私营部门公司违反了国家法律，或与当地政府机构或受项目影响的社区发生纠纷。 | This could affect the project's impact and even the reputation of UNDP 这可能会影响项目的影响，甚至影响开发计划署的声誉 | Ongoing 09/01/2023 to 31/12/2027 | L=2 I=3 | Two actions were taken: - The project has conducted checks on the co-financing private sector companies, including their financial status and whether there are any legal violations. - The project is conducting regular monitoring of the activities and finances of private companies involved to ensure that project activities did not violate relevant laws and regulations. 采取了两项行动： •该项目对共同资助的私营部门公司进行了调查，包括其财务状况以及是否存在任何违法行为。 •该项目正在对参与的私营公司的活动和财务进行定期监测，以确保项目活动不违反相关法律法规。 | Project Manager, National Technical Advisor, Sustainable Forest Management Specialist, NFGA, UNDP CO 项目经理、国家技术顾问、可持续森林管理专家、国家林草局、UNDP |

D. GENDER 性别

Guidance. please provide details on incorporation of gender perspectives in various aspects of project management. Please provide quantitative data, qualitative case studies and success stories whenever necessary to illustrate the most significant contributions to gender equality.

Please choose the Gender marker rating of this project: ☐GEN-3; ☒GEN-2; ☐GEN-1

| Outputs 产出 |  |  |
| --- | --- | --- |
| 1 | Please describe all activities undertaken within this project during the reporting year that directly or indirectly contributed to the advancement of women’s empowerment and gender equality. This may include initiatives promoting women's economic empowerment, enhancing women's decision-making capacities, and changing the harmful gender bias and stereotypes, etc. 请说明本报告年度在本项目范围内开展的所有直接或间接有助于提高妇女权能和两性平等的活动。这可能包括促进赋予妇女经济权力、提高妇女决策能力、改变有害的性别偏见和陈规定型观念等举措。 | The Inception workshop, including project board meeting, project workshop, stakeholder workshop, advocacy events and trainings from UNDP was held on 25-26 September, 2023 in Changting, Fujian. 13 of 49 participants were female. A Gender-Safeguard specialist has been recruited. Companies offering services on organizing awareness raising and advocacy campaigns, and ones taking charge of KAP surveys were chosen. A Stakeholder workshops will be held in Dec. 2023 and 30% of 40 participants will be women. The Surveys of KAP, gender and safeguard will be taken in the early of December 2023. 启动研讨会于2023年9月25日至26日在福建长汀举行，包括项目指导委员会第一次会议、项目研讨会、和联合国开发计划署的培训等。49名参与者中有13名为女性。 招聘了一名性别与社会环境保障专家。确定了KAP的分包公司，并开展KAP调查。 2023年12月将举办利益相关方培训会，计划30%参加者将为女性 KAP基线、性别与社会环境等调查将于2023年12月初进行。 |
| Outcomes 成果 |  |  |
| Please elaborate on the contributions and impacts this project has made to ONE or MULTIPLE relevant Gender Equality Strategy 2022-2025 priority areas of work during the reporting year. Please provide relevant evidence to support the claims. 请详细说明本项目在报告年度对2022-2025年一个或多个相关性别平等战略优先工作领域的贡献和影响。请提供相关证据支持。 |  |  |
| 2 | Promote women’s economic empowerment, employment, and access to resources, and diminishing the structural barriers in economies that keep women behind. 促进妇女的经济赋权、就业和获得资源，减少经济中使妇女落后的结构性障碍。 | Gender safeguard specialist will support the project with delivering gender trainings, carry out monitoring and evaluation missions, make recommendations for adaptive management measures to ensure project benefits for women are fulfilled. 性别与社会环境保障专家将通过提供性别培训来支持项目，执行监测和评估任务，就适应性管理措施提出建议，以确保项目惠及妇女。 |
| 3 | Support the incorporation of gender considerations into local economic and social development plans, accelerate women’s equal representation in local governance, especially in rural areas. 支持将性别考虑纳入地方经济和社会发展计划，加快妇女在地方治理中的平等代表性，特别是在农村地区。 | N/A 不适用 |
| 4 | Support building gender-responsive resilience to a wide range of shocks and crises, including conflict, climate change, disasters, environmental degradation and epidemics. 支持建立对性别问题有敏感认识的抵御能力，以应对各种冲击和危机，包括冲突、气候变化、灾害、环境退化和流行病。 | N/A 不适用 |
| 5 | Support women’s improved access, use, and control of resources, and enhance women’s participation and leadership role in climate action. 支持妇女更好地获得、使用和控制资源，并加强妇女在气候行动中的参与和领导作用。 | N/A 不适用 |
| 6 | Promote gender equality in green energy systems, policies, decision-making and ownership, as well as at the technical and service provision levels. 在绿色能源系统、政策、决策和所有权以及技术和服务提供层面促进两性平等。 | N/A 不适用 |
| 7 | Raise awareness on gender equality and challenge the gender stereotype and biased social norms that limit women’s equal rights and opportunities 提高对两性平等的认识，挑战限制妇女平等权利和机会的性别陈规定型观念和有偏见的社会规范 | Gender analysis surveys will help to identify key elements of gender issues in project landscapes to further evaluate and adjust gender actions in next years. 性别分析调查将有助于确定项目景观中性别问题的关键要素，以便在未来几年进一步评估和调整性别行动。 |
| Resources Allocation 资源配置 |  |  |
| 8 | How much of the annual project budget/resources has been allocated to address the identified needs of women and men? If no investment has been made, does the project plan to increase project investment to support women’s empowerment and gender equality? 年度项目预算/资源中有多少用于满足妇女和男子的明确需求？如果没有投资，项目是否计划增加项目投资，以支持妇女赋权和性别平等？ | Until the end of Nov. 2023, $17,280 was planned to support women’s empowerment. 截至2023年11月底，共计划拨款17280美元支持赋予妇女权力。 |
| Challenges & Lessons Learned 挑战与经验教训 |  |  |
| 9 | What are some key challenges/potential risks faced by the project in (further) promoting women's empowerment and gender equality? What are the possible mitigation measures the project will adopt to tackle those challenges? 该项目在（进一步）促进妇女赋权和性别平等方面面临哪些关键挑战/潜在风险？项目将采取哪些可能的缓解措施来应对这些挑战？ | Key challenges faced by the project are the stronger need for forestry technical services and under-representation in forestry technical services teams of women, and the unequal share of household responsibilities. The possible mitigation measures include encouraging equal opportunity recruitment of women for positions in forestry technical services teams, supporting the establishment of business ventures that are run by women, providing targeted training and technical assistance to women beneficiaries to ensure that more than half of direct beneficiaries of the project are women. 该项目面临的主要挑战是妇女对林业技术服务的需求更大，但是在林业技术服务团队中的代表性不足，以及家庭责任分担不平等。 可能的缓解措施包括鼓励平等机会招聘妇女担任林业技术服务团队的职位，支持建立由妇女经营的企业，向妇女受益者提供有针对性的培训和技术援助，以确保该项目的直接受益者中有一半以上是妇女。 |
| Knowledge Management 知识管理 |  |  |
| 10 | Have success story(ies) of female beneficiaries have been featured and shared as examples of the project’s key achievement in promoting women’s empowerment and gender equality? Are both women and men represented and visible in the communication products? 女性受益人的成功故事是否已作为该项目在促进妇女赋权和性别平等方面取得的关键成就的例子进行了介绍和分享？在传播产品中，女性和男性都有代表性和可视性吗？ | N/A 不适用 |

E. COMMUNICATION AND VISIBILITY沟通宣传

Guidance. Please provide URLs specific to this project (for example, project websites, social media sites, media coverage, etc.) as far as this is applicable. Note that some of these links would be the evidence and data sources for Section B above.

| # | Details of communications activities | Date | External link (if applicable) |
| --- | --- | --- | --- |
| 1 | The Project Management Training Workshop was successfully held on March 16, 2023. Nearly 70 people from ERPMC, NPMO, Fujian, Chongqing, Guizhou, Yunnan, and Gansu participated. This training workshop introduced the knowledge about the "Results-oriented UNDP-GEF Project Management Policy and Procedure" and shared successful experiences from other GEF projects. Media Reporting Channels: NFGA Official Website, ERPMC WeChat Official Account 2023年3月16日，GEF项目管理培训班顺利举办。国家林草局生态中心，天保GEF项目国家执行办公室，福建、重庆、贵州、云南、甘肃五省有关单位近70人参加培训。本次培训介绍了“以结果为导向的UNDP-GEF项目管理流程”和同类项目的成功经验。 媒体报道渠道：国家林草局官网及微信公众号 | 03/22/2023 | NFGA Official Website https://www.forestry.gov.cn/stzx/4/20230322/085141768899589.html |
|  |  | 03/22/2023 | ERPMC WeWhat Official Account https://mp.weixin.qq.com/s/jKrMyIe-yWkQs64dtn2XTQ |
| 2 | On July 11, the division chief and her team from the ERPMC went to Changting County to conduct project investigation and research. They conducted on-site inspections of demonstration sites that showcased methods for improving forest quality and controlling soil erosion. They also investigated the local preparations for implementing project-related activities. Media Reporting Channel: Longyan City Forestry Bureau WeChat Official Account 7月11日，生态中心处长一行到长汀县开展项目考察调研。实地考察了森林质量提升、水土流失治理示范点情况。调研了当地GEF项目筹备工作的进展情况。 媒体报道渠道：龙岩市林业局微信公众号 | 7/13/2023 | Longyan City Forestry Bureau WeChat Official Account https://mp.weixin.qq.com/s?__biz=MzU4MDA5NDgwMw==&mid=2247554281&idx=2&sn=06f20f4f8017b5171e003a769d13c71f&chksm=fd5e4ad5ca29c3c3fbd4c6f3add89bf6d6e381325b88df207fe5a2e4e0b497051c36dce49a65&scene=27 |
| 3 | On July 11, the NPMO visited the UNDP-GEF Strengthening Marine Protected Areas Project and the Flyway Conservation Network Project at the Academy of Forestry Inventory and Planning to communicate and exchange experiences related to project management, financial management, publicity strategy, and methods to improve the quality of project implementation. Media Reporting Channels: NFGA official website, ERPMC WeChat Official Account 2023年7月11日，国家项目办赴国家林草局调查规划院交流研讨，与GEF海洋保护地管理和保护迁飞网络项目办成员就项目管理、财务管理、宣传推广、提高项目质量的方法等方面交流经验。 媒体报道渠道：国家林草局官网及生态中心微信公众号 | 7/17/2023 | NFGA Official Website https://www.forestry.gov.cn/c/stzx/zhgl/512161.jhtml |
|  |  | 7/17/2023 | ERPMC WeWhat Official Account https://mp.weixin.qq.com/s/eIgFLZS_wHOSIi23cXpfOQ |
| 4 | On September 25, 2023, the Project Inception Workshop and the 1st meeting of the PSC were held in Changting County, Fujian Province. Nearly 70 people participated. The project Inception Report and the TYWP (2023-2024) were reviewed and approved during the PSC meeting. Media Reporting Channel: Multiple national and subnational news platforms and television stations. 9月25日，项目启动会暨指导委员会第一次会议在福建省长汀县召开。近70人参加本次会议。项目指导委员会审议并通过了项目启动报告和2023-2024双年度工作计划。 媒体报道渠道:多个国家级和省级官方新闻媒体和新闻网站 | 09/26/2023 | Changting County Media Center https://mp.weixin.qq.com/s?__biz=MjM5MDg0MzY2NQ==&mid=2650570770&idx=1&sn=33b20ce1e5b0a6a05db357f804c5ab03&chksm=beb6b66c89c13f7a40c5602cab6e353d9566d507f0538ccc89e937b37d769e405690d1575e8f&scene=27 |
|  |  | 09/26/2023 | SOHU https://www.sohu.com/a/723759462_121123834 |
|  |  | 09/26/2023 | NFGA Official Website https://www.forestry.gov.cn/c/stzx/zxzx/524966.jhtml |
|  |  | 09/27/2023 | Fujian Province Official Website http://www.fj.gov.cn/xwdt/fjyw/202309/t20230927_6265153.htm |
|  |  | 09/27/2023 | Changting County Official Website http://www.changting.gov.cn/xwzx/ctxw/202309/t20230927_2040818.htm |
|  |  | 09/27/2023 | Fujian Daily https://fjrb.fjdaily.com/pc/con/202309/27/content_308904.html |
|  |  | 09/27/2023 | FJSEN.com http://fjnews.fjsen.com/2023-09/27/content_31420758.htm |
|  |  | 09/27/2023 | Sina https://finance.sina.com.cn/jjxw/2023-09-27/doc-imzpazmr4246223.shtml |
|  |  | 09/28/2023 | Longyan City Forestry Bureau WeChat Official Account https://mp.weixin.qq.com/s?__biz=MzU4MDA5NDgwMw==&mid=2247556421&idx=4&sn=a375efa2286af6424f42475ff02d491e&chksm=fd5e4379ca29ca6fad0bfa90c9f1e5586f02837ce52dfa70b77a74ebdd16d622a759e1466561&scene=27 |
|  |  | 10/03/2023 | Longyan Government Official Website http://www.longyan.cn/jeecms/html/ywzytw3/20231003/91988.html |
|  |  | 10/07/2023 | Xishuangbanna State Official Website https://www.xsbn.gov.cn/nbhbhq/114954.news.detail.dhtml?news_id=2900234 |
|  |  | 10/11/2023 | isenlin.cn http://www.isenlin.cn/sf_3E3CA13782564E9FAD3D6246BEFFF4C3_209_55FFF1A1306.html |
|  |  | 10/13/2023 | NFGA Official Website https://www.forestry.gov.cn/c/stzx/zxzx/526565.jhtml |
|  |  | 10/13/2023 | ERPMC WeChat Official Account https://mp.weixin.qq.com/s/B9v1q9Z2W1bj4v13Of4EPg |
| 5 | On October 31, the Yunnan Inception Workshop and Forest Landscape Restoration Workshop of the Project were held in Menghai County. The meeting conveyed the essence of the 1st PSC Meeting, which marked the official launch of the project in Yunnan Province. During the meeting, project-related tasks were assigned, the demonstration area and technical routes were finalized, and project management was further strengthened. These efforts will ensure the smooth and organized implementation of the project. Media Reporting Channel: Multiple national and subnational news platforms and television stations. 10月31日，天保GEF项目云南启动暨森林景观恢复工作研讨会在勐海县召开。会议传达国家天保GEF项目启动会会议精神，启动云南省天保GEF项目，研究部署相关工作，确定森林景观恢复示范区域地块及技术路线，进一步强化项目管理，有序推进项目实施。 媒体报道渠道:多个国家级和省级官方新闻媒体和新闻网站 | 11/06/2023 | Menghai County Media Center (video news) http://www.xsbnrtv.cn/cms/a/10622735/content |
|  |  | 11/7/2023 | isenlin.cn http://www.isenlin.cn/sf_1B7D9E040F354DFB942F2884707198FF_209_B6F995B2631.html |
|  |  | 11/7/2023 | Forestry and Grassland Bureau of Yunnan Province WeChat Official Account https://mp.weixin.qq.com/s/PeI6gnPeLpU7BhslZCu5ZA |
|  |  | 11/09/2023 | Forestry and Grassland Bureau of Yunnan Province Official Website http://lcj.yn.gov.cn/html/2023/zuixindongtai_1109/70177.html |
|  |  | 11/10/2023 | NFGA Official Website https://www.forestry.gov.cn/c/stzx/zxzx/531006.jhtml |
|  |  | 11/10/2023 | ERPMC WeWhat Official Account https://mp.weixin.qq.com/s/EMoi4-O9dX-_M1k0Uarc-Q |

F. LESSONS LEARNED AND WAY FORWARD  经验教训和向前推进

F.1 Lessons Learned经验教训

Guidance. Describe any lessons that will be applied to address challenges or improve the implementation pace. Outline any good practices, as applicable.

说明：描述将用于应对挑战或提高项目实施进度的任何经验教训。概述任何适用的良好做法。

F.2 Way Forward向前推进

Guidance. List key issues which need to be followed up and addressed for the next reporting period.

说明：列出下一个报告期需要跟进和解决的关键问题。

| # |  | Issue/observation | Action to be taken | Responsible | Timeline |
| --- | --- | --- | --- | --- | --- |
| 1 |  | [e.g. A project deliverable has been damaged due to the fire incident, impeding acceptance and final payment.] | [e.g. Check with legal dept/lawyers on the liabilities of the incident] | [e.g. xxx government] | [e.g. ASAP]] |
| 2 |  |  |  |  |  |
| [+] |  |  |  |  |  |

G. ANNEXES

Guidance. Include any detailed project information here, e.g. meeting minutes, detailed action plan, agreement signed, etc. Chinese version is also acceptable.

- Minutes of the 1st PSC meeting.

Annex 1 Minutes of the 1st PSC meeting

Minutes of the 1st Project Steering Committee (PSC) Meeting

Project name: UNDP-GEF Restoration of Degraded Natural Forests and Soil Erosion Management Improvement in Erosion-Prone Regions of China Project

Date: 25 September, 2023

Venue: Conference room, 3rd floor, Changting Hotel, Changting County, Fujian Province

Online: Tencent Conference 326-666-043

Facilitator: Fu Changjie, National Project Director of the Project

On 25 September 2023, the Project Inception Workshop and the 1st PSC meeting were held in Changting County, Fujian Province, with 50 participants from Ministry of Finance (online), National Forestry and Grassland Administration, UNDP China, Provincial Forestry and Grassland Bureaus of Fujian, Chongqing, Yunnan, Guizhou, and Gansu, National Project Management Office, PMUs of the related provinces and landscape areas, cooperation enterprises, and UNDP-GEF C-PA 4 Project PMO, and so on (See Annex 2 for the list of participants).

At the Inception Workshop, Mr. Lai Jinyi (Secretary of CPC Committee of Changting County), Mr. Liu Yasheng (Deputy Director General of Fujian Provincial Forestry Bureau), and Dr. Ma Chaode (Assistant Resident Representative of UNDP China) delivered opening speeches. Mr. Ma Guoqing (Director General of ERPMC of NFGA) delivered a keynote speech. The project was officially kicked off under the joint witness of all participants and guests.

The 1st PSC meeting was held following the Inception Workshop. Mr. Fu Changjie (National Project Director) announced the list of PSC members. The UNDP-GEF project management policies and procedures were also introduced by Dr. Ma Chade of UNDP China, and then the project inception report and the TYWP (2023-2024) were discussed and reviewed. Mr. Ma Guoqing (Chairman of PSC, and Director General of ERPMC of NFGA) made closing remarks (See Annex 2 to the meeting agenda. The meeting minutes are recorded as follows:

The Inception Report was passed and the following clarifications and adjustments of the Project Document have been agreed for project implementation:

Although total budget and work plan are stipulated in the Project Document, adaptive adjustments can be made according to the actual needs within the scope of the UNDP-GEF project during project implementation, which shall be submitted to the PSC and UNDP for approval in advance, before being reflected in the TYWP. The adjustment items listed below of the ProDoc were agreed in principle at the PSC meeting.

1.1 The Renaming of the IP. (a) National Forestry and Grassland Administration (NFGA) went through an internal institutional reform since August 2021. Two existing agencies including the Natural Forest Protection Programme Office (NFPPO) and the Grain for Green Center under NFGA were amalgamated into a new agency, named the Ecological Rehabilitation Programme Management Center (ERPMC), which was officially established in November 2021. (b) The staffing and function of the NFPPO are fully integrated into the ERPMC to specifically implement the protection and restoration of natural forests in China. The internal control framework relating to operational & management policy and procedures within the organization remains unchanged.

1.2 Staffing an International Safeguard Consultant. As per the advice given by UNDP, considering the indispensable role of Safeguard in SES compliance during project implementation, an International Safeguard Consultant is added for assessment and ESMP development, so as to ensure the risk assessment and management plan can be developed before the implementation of the project activities especially at the project landscapes. The cost of an International Safeguard Consultant is up to $20,000 in 2024 for 30 working days, and the budget has been shifted from part of the budget ($42,000 in total) of the International Sustainable Forest Management Specialist to cover the cost of International Safeguard Consultant.

1.3 Changes in the demonstration areas Based on current situation of natural forest and its land use for natural forest, after scientific analysis and comprehensive evaluation, part of the FLR demonstration area from Taoping forest farm has been allocated to Shanmen forest farm in Xiaolongshan landscape, as shown in the table below. Thus, both Taoping forest farm and Shanmen forest farm will jointly complete the FLR demonstration tasks. The total amount of FLR demonstration area for the project remains unchanged.

The FLR demonstration area breakdown table in Xiaolongshan, Gansu Province

(Unit: hectare)

|  | Monoculture upgraded to mixed forest | Planting of mixed forest on bare land | Managed natural regeneration | Corridors between natural forest areas | Restoration of degraded natural forest | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Taoping Forest Farm | 2700 | 300 | 7500 | 200 | 4500 | 15200 |
| Shanmen Forest Farm | 1000 |  | 1200 |  | 13500 | 15700 |
| Total | 3700 | 300 | 8700 | 200 | 18000 | 30900 |

2. The PSC reviewed and adopted the TYWP (2023-2024).

The PSC reviewed and adopted the TYWP (2023-2024), and required the National PMO to move forward with the project orderly and strictly in accordance with UNDP-GEF international project management measures and China central financial funds management regulations.

3. The project risks and challenges were reviewed.

The overall risk classification of the project was moderate based on the screening of the Social and Environmental Screening Procedures (SESP) during the PPG. Up to now, the project has no major adjustment and change, and the identified risks and impacts have not been changed. The National PMO and local PMOs will strictly comply with the relevant environmental and social risk management requirements of UNDP, duly assess the potential environmental and social impact, and develop environmental and social risk management plan before conducting activities which might trigger project risks during the implementation of the project.

Signatures on behalf of the PSC

Ma Guoqing, Chairman of the PSC

Director General of Ecological Rehabilitation Programme Management Center

National Forestry and Grassland Administration, P.R.C

Ma Chaode, Deputy Chairman of the PSC

Assistant Resident Representative of UNDP China

Please refer to UNDP Gender Equality Strategy 2022-2025 for more details: https://genderequalitystrategy.undp.org/#