## India-UN Development Partnership Fund

## Abaco Shelter Project Update

| Project Title: Abaco Hurricane Shelter |  |
| --- | --- |
| Country: Bahamas | Report Date: July 4, 2023 |
| Project start date: 1 July 2022 | Project end date: 30 September 2023 |
| Implementing Partner: Disaster Reconstruction Authority |  |

- Key timelines and updates:

The Abaco Shelter Project seeks to support the Government of the Bahamas in strengthening its resilience to the impacts of hurricanes through the construction of a multi-purpose shelter in the Abacos.

Outlined below are the key timelines and updates on the project’s progress:

- Project Endorsement:

  - The project was endorsed on 27 May 2022 by key stakeholders from the Disaster Reconstruction Authority, the Ministry of Public Works, and the Office of the Prime Minister.

- Project Document Finalized and Signed:

  - The project document was finalized and signed on 31 May 2022 with all prerequisites being completed.

- Project End Date:

- The project end date as per the signed agreement is 30 September 2023.

- The project has experienced delays, and an extension request is being finalized.

- Financial:

- UNDP Expenditure – USD 450,970.00

- UNDP Balance – USD 549,030.00

- Government of the Bahamas co-investment – USD 3,500,000.00

- Government of the Bahamas expenditure-       USD 1,334,532.87

- Implementation:

  - The procurement of a construction firm to undertake the establishment of the Development Shelter has been completed and Wilkheim Construction has been awarded the contract.

  - Procurement – The procurement of the building materials has been initiated. Implementation will be accelerated upon completion of the corrective actions that are ongoing.

  - South-South Exchange – On June 1st, the first knowledge exchange was convened. The series provides a platform for the sharing of best practices in disaster resilience. Series 1 entitled: resilient, Ready & Raring to Go was a public webinar, utilizing the format of a fireside chat during which lessons from Jamaica, Dominica, and Bermuda’s experience in establishing resilient buildings were shared with stakeholders in the Bahamas. The exchange facilitated the sharing of best practices in disaster resilience and contributed to strengthened networks between disaster coordination organizations within the countries.

Construction

  - Site Assessment -Upon review of the building site, the Geo-technical team identified pockets of organic matter that require corrective action before the shelter is established.

  - Corrective Action- To comply with the Bahamas Building codes and to ensure that the shelter is safe, resilient, and sustainable, eight (8) additional structural columns have been established.

  - Completion of the foundation works is ongoing and steps have been taken to extend the stem walls to the top of the foundation level. The foundation fill is now being placed and compacted.

  - By July 28th, the project will be at floor level dealing with the mechanical and electrical services and making ready-to-pour floor slabs.

Annex:

- Video link and Photographs in action.

https://www.youtube.com/watch?v=bZaLQEK0mYw