United Nations Development Programme

| Project title: Sustainable Forest and Forest Land Management in Viet Nam’s Ba River basin landscape |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: Viet Nam | Implementing Partner (GEF Executing Entity): Ministry of Agriculture and Rural Development (MARD)/Forest Inventory and Planning Institute (FIPI) |  |  |  | Execution Modality: Full NIM |
| Contributing Outcome (UNDAF/CPD, RPD, GPD): Outcome 2 - People in Viet Nam, especially those at risk of being left behind, will benefit from, and contribute to safer and cleaner environment resulting from Viet Nam’s effective mitigation and adaptation to climate change, disaster risk reduction and resilience building, promotion of circular economy, the provision of clean and renewable energy, and the sustainable management of natural resources. |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Substantial |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Award ID: 00128603 |  |  | Atlas Project/Output ID: 00122552 |  |  |
| UNDP-GEF PIMS ID number: 5887 |  |  | GEF Project ID number: 10539 |  |  |
| LPAC meeting date: Dec 3, 2022 |  |  |  |  |  |
| Last possible date to submit to GEF: February 11, 2022 |  |  |  |  |  |
| Latest possible CEO endorsement date: September 2, 2022 |  |  |  |  |  |
| Project duration in months: 48 months |  |  |  |  |  |
| Planned start date: January 1, 2023 |  |  | Planned end date: December 31, 2026 |  |  |
| Expected date of Mid-Term Review: September 30, 2024 |  |  | Expected date of Terminal evaluation: September 30, 2026 |  |  |
| Brief project description: The biodiversity and natural resources of the Ba River basin provide the ecological foundation upon which the inhabitants of the basin depend on for their physical, cultural, social and economic well-being. The river basin provides food, fiber, fuel and hydropower, freshwater, medicinal plants and building material. The forests in the basin also support a rich array of ecosystems and species which under growing pressure due to land-use change, illegal resource use, infrastructure development, and deforestation as a result of immigration and development of market crops. While conservation efforts have been made in the past to conserve these high value forests, including in protected areas and forest reserves, much more needs to be done to preserve these hotspots of biodiversity. This will require the promotion of a comprehensive and integrated approach to mainstream land, resource management, and biodiversity conservation into forest management and local and sub-regional socio-economic development and community resource management. Such an approach will require taking into account the inter-connectivity of various ecosystems within the river basin, ensure that relevant forest managers and development planners have adequate capacities to promote integrated approaches and tackle the threat to biodiversity and promote effective natural resources and forest management and use indigenous knowledge and practices of ethnic minorities to conserve biodiversity, restore and enhance the condition of degrading forests, and promote the environmental sustainable use of forest products. To achieve this outcome, the project intends to promote a holistic, multi-sectoral and multi-stakeholder approach to resource governance within the Ba River basin. Strategies include protecting existing forests, establishing connectivity between forest areas, improving the management effectiveness of protected areas, mainstreaming biodiversity into forest production and protection areas, improving opportunities for community co-management of forests in commune lands, promotion of livelihood improvement programs and strengthening financial incentives to local communities through payment for forest ecosystem services. This will be achieved through the following three Components: Component 1: Mainstreaming biodiversity and ecosystem services into landscape-level planning, monitoring and enforcement Component 2: Conserving globally significant biodiversity and ecosystem services in forested landscapes of Ba River basin Component 3: Gender mainstreaming replication and knowledge exchange |  |  |  |  |  |
| Financing Plan (only cash transferred to UNDPs bank account and included in the TBWP for this specific GEF project should be included under this section (1), all others should be included under section (2). |  |  |  |  |  |
| GEF Trust Fund grant |  |  | USD 2,183,105 |  |  |
| - Total Budget administered by UNDP |  |  | USD 2,183,105 |  |  |
| co-financiers that will deliver project results included in the project results framework (Funds not administered through undp accounts) |  |  |  |  |  |
| - Total confirmed co-financing to this project not administered by UNDP |  |  | USD 18,633,000 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | USD 20,816,105 |  |  |
| Signatures: |  |  |  |  |  |
|  |  | Agreed by Government Development Coordination Authority |  | Date/Month/Year: within 25 days of GEF CEO endorsement |  |
| Signature: print name below |  | Agreed by Implementing Partner |  | Date/Month/Year: within 25 days of GEF CEO endorsement |  |
| Signature: print name below |  | Agreed by UNDP |  | Date/Month/Year: within 25 days of GEF CEO endorsement |  |

- Table of Contents

I.	Table of Contents	4

II.	 Development Challenge	7

III.	Strategy	18

IV.	Results and Partnerships	29

V.	Project Results Framework	81

VI.	Monitoring and Evaluation (M&E) Plan	89

VII.	Governance and Management Arrangements	105

VIII.	Financial Planning and Management	110

IX.	Total Budget and Work Plan	113

X.	Legal Context	121

XI.	Risk Management	121

XII.	Mandatory Annexes	124

Annexes

      - GEF Budget Template

      - Project Map and geospatial coordinates of the project area

      - Multiyear workplan

      - UNDP Social and Environmental Screening Procedure (SESP)

      - UNDP Risk Register

      - Overview of Project Staff and Technical consultancies

      - Stakeholder Engagement Plan

      - Environmental Social Management Framework (ESMF) or other SES frameworks/plans if required (not included, currently in preparation)

      - PPG Consultations

      - Gender Analysis and Action Plan

      - Procurement Plan

      - GEF Core indicators

      - GEF Taxonomy

      - METTS (14a) and FAO-EXACT (14b)

      - Provincial Capacity Development Scorecards [Phu Yen (15a) and Gia Lai (15b)]

      - Summary Analysis and Project Implications/Opportunities for Covid-19

      - Summary Analysis and Project Implications for Climate Change Considerations

      - Livelihood Options

      - Forest Restoration Strategy

      - Co-financing Letters

      - PCAT (21a) and HACT Micro Assessment (21b)

      - UNDP GEF Audit Checklist

Figures:

Figure 1: Situation Analysis – Page 15

Figure 2: Theory of Change – Page 25

Tables:

Table 1: Geographical, Biological and Socio-economic features of project landscape -Page 22

Table 2: Partnership Arrangements – Page 47

Table 3: Project risks and Mitigation Matrix – Page 49

Table 4: Summary of safeguards triggered based on screening conducted during project preparation – Page 59

Table 5: Consultation meetings – Page 60

Table 6: Stakeholder Involvement Plan – Page 62

Abbreviations

| ADB-BCC | Biodiversity Corridors Conservation Project |
| --- | --- |
| ADB-CEP | Core Environment Program and Biodiversity Conservation Corridors Initiative, Phase II |
| CEMA | Committee for Ethnic Minority Affairs |
| CPC | Commune People’s Committees |
| CSO | Civil Society Organizations |
| DARD | Department of Agriculture and Rural Development |
| DEM | Department of Ethnic Minority |
| DOF | Department of Finance |
| DONRE | Department of Natural Resources and Environment |
| DPI | Department of Planning and Investment |
| EBA | Endemic Bird Area |
| EPMF | Ethnic Peoples Management Framework |
| ESMF | Environment and Social Impacts Management Framework |
| EU | European Union |
| FCPF | Forest Carbon Partnership Facility |
| FIPI | Forest Inventory and Planning Institute |
| FMB | Forest Management Board |
| FMU | Forest Management Unit |
| FORMIS | Management Information Systems for the Forestry Sector in Viet Nam |
| FPD | Forest Protection Department |
| FPDF | Forest Protection and Development Fund |
| FPIC | Free Prior and Informed Consent |
| FPMB | Forest Protection Management Board |
| FRMS | Forest Resource Monitoring System |
| FSP | Full Sized Project |
| GEF | Global Environment Facility |
| GEFS | Global Environment Facility Secretariat |
| HCS | High Carbon Stock |
| HCVF | High Conservation Value Forest |
| IAS | Invasive Alien Species |
| ICT | Information and Communication Technology |
| IP | Indigenous People |
| IUCN | International Union for the Conservation of Nature |
| JICA | Japan International Cooperation Agency |
| KBA | Key Biodiversity Areas |
| LDN | Land Degradation Neutrality |
| MARD | Ministry of Agriculture and Rural Development |
| METT | Management Effectiveness Tracking Tool |
| MONRE | Ministry of Natural Resources and Environment |
| MOU | Memorandum of Understanding |
| MSP | Medium Sized Project |
| NDC | Nationally Determined Contribution |
| NP | National Park |
| NTFP | Non-timber forest products |
| OCOP | One Commune One Product |
| PA | Protected Area |
| PFES | Payment for Forest Ecosystem Services |
| PFM | Participatory Forest Monitoring |
| PIF | Project Identification Form |
| PIR | GEF Project Implementation Report |
| POPP | Program and Operations Policies and Procedures |
| PPC | Provincial Peoples Committee |
| PPG | Project Preparation Grant |
| REDD | Reduced Emissions from Deforestation and Forest Degradation |
| SFC | State Forest Company |
| SFM | Sustainable Forest Management |
| SFMP | Sustainable Forest Management Plan |
| SIP | Stakeholder Involvement Plan |
| SNRM | Sustainable Natural Resource Management |
| SNV | Dutch Development Agency |
| STAP | GEF Scientific Technical Advisory Panel |
| SUF | Special Use Forests |
| UNFCCC | United Nations Framework Convention on Climate Change |
| WTO | World Tourism Organization |
| WU | Women’s Union |

- Development Challenge

- This project aims to address the negative impacts of deforestation, degradation and fragmentation that threaten biodiversity and the maintenance of ecosystem services in the Ba River basin from unsustainable sector-led development practices, illegal encroachment and agricultural expansion. To address these impacts, the project intends to establish and operationalize a comprehensive planning and landscape management approach that harmonizes socio-economic development, sustainable management of forest resources, improved land management and provision of incentives to enhance the participation of local, forest dependent communities in conservation of biodiversity within the Ba River basin. The project’s intervention is to ensure that existing protected areas and surrounding high conservation value natural forests are managed to support viable populations of globally threatened species and allow for the movement of wildlife, pollination and reproduction, and other processes that support the recovery and improve natural resiliency to external development and climatic shocks. The project comes at a time when increased degradation of natural habitats from deforestation and conversion to agriculture and expanding infrastructure development, pollution, invasive alien species (IAS) and climate change are becoming an ever-increasing threat to critical habitats, ecosystems and their attendant biodiversity in the Ba River basin. The Central Highlands of Viet Nam that accounts for 16.8 % (or around 35% of the forest area) of the country’s area is reported to have lost nearly 14% of its forest area between 2008 and 2015. More importantly, the Central Highlands are associated with ethnic minority communities that have a rich cultural and livelihood relating with the forest, from the traditional use of forest resources such as shifting cultivation, hunting and gathering in the traditional border areas of the village to the related policies of forest management and protection activities, forest land use changes and market mechanisms. Consequently, the conversion of forests to other purposes, and illegal encroachment of forestland have negative impacts on the ethnic minority’s socioeconomic development and environment.

- Viet Nam’s natural forests are of outstanding global importance and critical for the achievement of national commitments under international biodiversity, land degradation and climate change conventions. However, these are areas of dynamic change and the biodiversity and ecosystem services they support are at risk due to ongoing forest loss and degradation and broader landscape change. In Viet Nam as a whole, national forest cover has increased in recent years, rising from 28% in 1993 to more than 41% in 2017. However, this gain has been due to the expanding area of forest plantations, which rarely if ever provide sufficient habitat for biodiversity or other ecosystem services (other than timber production), comparable to those provided by native forests. According to forest reference emission levels submitted by Viet Nam to the United Nations Framework Convention on Climate Change (UNFCCC) in 2016, approximately two-thirds of the country’s natural forests are in poor condition and/or are regenerating. Closed-canopy forests constitute only five percent of total forest area and are, not surprisingly, highly fragmented. For these and other reasons, conserving natural forests and maintaining or, where possible, enhancing their connectedness remain high priorities for the country. Failure to do so will result in an ongoing impoverishment of the country’s forest biodiversity, within a context of continued deforestation and forest degradation.

- There is a complex mix of landscape changes across a mosaic of forest types, units and management structures that plays out clearly in the Ba River basin, the largest river basin in Central Viet Nam. The basin includes extensive forest areas totaling approximately 600,000 hectares. The majority of forests in the Ba River basin are located within the ecologically important Central Highlands region, part of the WWF Southern Annamites Montane Rain Forests ecoregion. The upper reaches of the Ba River basin, particularly in the Gia Lai province is part of the Central Highlands Region of central Viet Nam and encapsulates most of the remaining forests with high biodiversity value in Viet Nam. The montane rainforests of Northern and Southern Annamite Mountain ranges (that form the boundary between Laos, Cambodia and Viet Nam) are highlighted as a global ecoregion. This designation indicates that these areas contain geographically unique species, communities and conditions, with globally outstanding biodiversity. Most famously, Annamite montane rainforests and Indochinese dry dipterocarp forests, include regionally significant conifer species richness. In an analysis of biodiversity of ecoregions in the Indo-Pacific, based on combined species richness and endemism, it was found that within the Indo-Burma biodiversity hotspot, the Southern Annamite montane rainforest had the highest biodiversity. More than 410 bird species are known from this ecoregion. Five of these species are near endemic, and five are endemic. Among the other bird species that need conservation attention are the globally threatened white-winged duck (Cairina scutulata), the critically endangered Edwards's pheasant (Lophura edwardsi), and the threatened Siamese fireback (Lophura diardi), green peafowl (Pavo muticus), and Germain's peacock-pheasant (Polyplectron germaini). Several other species such as the great hornbill (Buceros bicornis), Austen's brown hornbill (Anorrhinus austeni), wreathed hornbill (Aceros undulatus), and crested argus (Rheinardia ocellata) are indicators of low disturbance levels and relatively intact forests. The ecoregion also overlaps with two Endemic Bird Areas (EBAs) identified by BirdLife International, the Da Lat Plateau and South Vietnamese Lowlands, which have eight and three restricted-range bird species, respectively. In the Ba River basin, the relatively high proportion of its remaining natural forest area is high conservation value forest (HCVF), which supports high levels of globally-significant biodiversity. Within the Kon Ka Kinh – Kon Chu Rang corridor at the northernmost part of the basin alone, biological surveys have confirmed the presence of at least 18 International Union for the Conservation of Nature (IUCN)-red listed mammal species at vulnerable and higher categories, and 29 rare and endangered plant species.

- The forests of the Central Highlands of Viet Nam protect the upper watersheds of the Mekong River and some of central and southern Viet Nam’s most important river systems. These rivers support agriculture and fisheries, generate power, and deliver clean water for domestic and industrial consumption supporting the livelihoods and economic well-being of millions. These same forests also support some of Viet Nam’s richest remaining biodiversity. Unfortunately, growing pressure on land, illegal resource use, and infrastructure development are exerting extreme pressure on remaining forests and the environmental services they provide. Despite the great ecological diversity of the Central Highlands, biodiversity in this region is subject to pressures typical throughout Viet Nam, including deforestation as a result of immigration and the development of market crops, logging and dams.

Key Threats to natural resources management and biodiversity

- The primary threats to biodiversity and direct causes of ecosystem degradation in the Ba River basin are:

- Deforestation, degradation and fragmentation: This landscape is under dynamic change, which is threatening biodiversity and the maintenance of ecosystem services. Direct loss of habitat is a key threat, with forest cover in the basin decreasing from 661,180 hectares in 2010 to 600,223 hectares in 2018. In addition to deforestation, problems of forest degradation and fragmentation have expanded. There is intense competition for land, which means that setting aside and maintaining land for forest protection is in direct competition with other, often more remunerative land uses. The main driver of deforestation and forest degradation is agricultural expansion, which moves in tandem with expansion of rural infrastructure such as road construction. Coffee plantations likely pose the greatest threat. The sector also faces an ongoing need to renew coffee plantations, a factor which will continue to increase demand for forest acquisition and conversion. Timber plantations are also expected to grow and pose further threats to natural forest areas, in the context of increasing demand for paper and pulp and other wood-based products. In the case of the Central Highlands, coffee production has expanded mainly at the expense of existing agricultural (subsistence) crops, rather than directly into forests. However, this process has in turn displaced annual subsistence crops, and their producers, further away from population and economic centers and towards marginal and still forested lands. As capital investment drives land acquisition, especially for production of commodity export crops like coffee, the poorest populations are among those most likely to be displaced. Ironically, these populations, particularly members of ethnic minority groups, also tend to be the most heavily dependent on forest resources for their incomes and livelihoods.

- Encroachment and over-exploitation of forest products within Forest Management Units: These processes, which are also linked to continuing population growth, often lead to illegal encroachment into remaining natural forests within Forest Management Units (FMUs). This can include encroachment of forestland for shifting cultivation, illegal hunting and trapping of wildlife; illegal logging of protected and rare timber species; and exploitation of non-timber forest products (NTFPs). Poaching and low effective wildlife protection led many iconic species of the Ba River basin become locally extinct in the landscape. Notable examples are the Asiatic elephant (Elephas maximus), Indochinese tiger (Panthera tigris corbetti), and kouprey (Bos sauveli). Many others have become seriously threatened such as the douc langur (Pygathrix spp), yellow checked gibbons (Nomascus gabriellae), gaur (Bos gaurus), and Indochinese green peafowl (Pavo munticus). The drivers and root causes of these threats are increasing human populations, increasing demand for timber, spread of wildlife poaching and trafficking, and depleted natural production forests that cannot meet demand resulting in timber supply shortages, depleted wildlife populations, lack of tenure rights and secure access to productive land and resources for forest-dwelling communities, and entrenched poverty among local and indigenous communities – ultimately resulting in the unsustainable landscape management observed today and the continued erosion of the Basin’s biodiversity and ecosystem services.

- Climate Change: Viet Nam is considered one of the ten countries most negatively impacted by climate change and will be among the most affected in the coming decades. Ecosystems weakened by fragmentation are less resilient to the impacts of climate change and more vulnerable to mass species loss. The increase in temperature will change the geographic distribution of many ecosystems and population structure of species as species loss and migration increases. Increased temperatures are also likely to increase the frequency and severity of forest fires. According to the scenario of climate change and sea level rise in Viet Nam, projections foresee average annual temperature increases by 0.8°C to 2.7°C nationwide by the 2060s and a concurrent 75-100 cm sea level rise. The sea level rise would cause 20-38% of the Mekong Delta and about 11% of the Red River Delta to be negatively affected, including 78 of Viet Nam’s 286 “Critical Natural Habitats”, 46 protected areas (PAs), 10 biodiversity sites of national and international importance (including Biosphere Reserves) and 23 other important biodiversity sites. Forest fires are also likely to increase beyond current rates that have destroyed about 2,500 ha of forests annually from 2007 to 2013. Increased temperatures as well as the frequency and duration of drought spells are also expected to reduce native forest cover, increased frequency and severity of forest fires and increased pests.

Long-term vision and barriers to achieving it:

- The long-term vision is conservation of forest biodiversity and maintained/improved flow of ecosystem services across the Ba River Basin. The project solution to achieve this is for biodiversity conservation and land degradation neutrality to be mainstreamed into sustainable forest management planning and practices, through a collaborated landscape-wide approach including enhanced management and connectivity of protected areas, buffer zones, State-owned and privately-managed natural forests, and community co-managed areas.

- The inter-relationships between the different barriers and threats are defined in Figure 1. The five barriers are the following:

- Barrier 1: Lack of information on biodiversity conservation assets, condition and trend: The efficient protection of Vietnam’s forest resources requires up-to-date information in order to make sustainable management decisions. However, despite some progress in trying to build Vietnam’s forest, factors such as illegal logging, unsustainable harvesting and forestry practices, hack-and-slash agriculture, forest fires, and infrastructural expansions to feed Viet Nam’s rapidly growing economy is resulting in both deforestation and the general degradation in the quality and strength of Viet Nam’s forests. Furthermore, forest recovery projects active in Viet Nam are often hampered by the lack of accurate information with which to make decisions for appropriate and effective action. To counter this weakness, the development of a Management Information System for the Forestry Sector  was launched in 2009 to provide a solution to this lack of accurate information and facilitate effective decision-making around forest management; reducing emissions from deforestation and forest degradation, and forest law enforcement, governance, and trade activities. However, there is still a dearth of information on forest resources and issues that affect it that makes it difficult to effectively integrate biodiversity concerns in forest management operations. Reliable data on the soil and water protective function of forest can help sustainable forest management for water security and sediment- and water-related disaster resilience and the application of modern ICT can offer huge benefits in terms of improved cost-effectiveness and transparency in forestry. In the Ba River basin, there are significant limitations in terms of specific information on forest resources in the basin, including current fauna and flora status, forest quality, flora and fauna distribution and recovery trends. There is limited information on the extent and status of HCVF, how HCVFs have been managed and what information does exist on biodiversity assets is not up-to-date and not well connected to management decisions. The Sustainable Forest Management (SFM) planning process in the Ba River basin requires up-to-date data and monitoring on forests and forest resources that is restricting the consideration of biodiversity within forest management and land use plans. In addition, limited understanding of site-based threats such as agricultural encroachment, illegal logging and poaching into high biodiversity forest areas, illegal logging and widespread use of snares/traps for wildlife poaching and their impact on biodiversity and ecosystem functions limits and constraints effective surveillance and patrolling efforts. There is not yet effective use of remote sensing technologies to provide near real-time information on forest change and use it to inform decision-making and enforcement. Boundaries between different land uses are in places not well identified compounding these issues. There are many areas where management and/or ownership are not clear—a situation that can lead to conflicts. These issues have significant impacts on forest management and biodiversity conservation in the project area.

- Barrier 2: Insufficient operational guidance and enforcement which impede implementation of the policy framework and mainstreaming of biodiversity conservation into forest and land use planning: Viet Nam’s Forestry Law was updated and approved in 2017. A key aspect of the new law is the promotion of sustainable forest management that requires forest owners (FMUs) to make and implement sustainable forest management plans.  The preparation of these SFM plans requires the assessment of natural, socio-economic, national defense and security conditions of the forests; defining the status quo of the forest ecosystem, biodiversity, biological genetic resources, historical and cultural relics and landscapes on the basis of which the scope of sustainable forest management is defined along with measures for forest management, protection, conservation, restoration, development and use. However, implementation of the new law has been hindered by a lack of awareness, capacity and techniques to guide forest owners in the development and implementation of SFM practices and plans. Gaps in particular include: (i) the lack of awareness of forest rangers on their expected transformational role in forest management in relation to the new forest policies; (ii) absence of capacity and technical skills among forest managers and Forest Management Boards on planning and implementation of SFM, in particular on incorporation of co-management approaches, promotion of sustainable forest resource use among local communities, mobilization of financing and promotion value addition and processing of forest products.  Technical guidance and capacity for incorporation of biodiversity conservation priorities have not yet been actively integrated into forest planning processes, In the absence of this and enhanced awareness and commitment to biodiversity conservation within SFM plans there is a risk that the potential benefits of the implementation of these plans for biodiversity conservation and ecosystem services will be not be fully materialized.  This will require, specific efforts to strengthen effective coordination between central and local levels among ministries/sectors to drastically and effectively carry out the examination, inspection, supervision and timely and strictly enforce violation of laws, improving coordination among provincial authorities across the Ba River basin is important to combat wildlife poaching, trafficking and logging groups that are shifting from Phu Yen to Gia Lai and transporting illegal products across the basin. While there are some existing mechanisms in place for coordination on forest law enforcement these tend to focus on forest encroachment and offences and do not pay sufficient attention to wildlife-related offences such as poaching. Without enhanced capacity and tools to collect, share and use data and develop collaborative strategies for enforcement, this Directive will remain difficult to implement and illegal activities will persist.  Similarly, the integration of forestry and biodiversity outcomes in provincial master planning is constrained by lack of provincial coordination mechanisms and capacity and skills to monitor its integration as well as testing and validation of relevant Decrees, Regulations and Guidelines that support the implementation of the Forestry, Planning and Biodiversity Acts.

- Barrier 3: Limited experience in developing and implementing biodiversity conservation and land degradation priorities as part of forest management and lack of technical capacities and tools to do so: Although Vietnam has a long history of forest management, the shift to implementing SFM practices, including biodiversity conservation, is relatively new. Similarly, target setting related to Land Degradation Neutrality (LDN), in particular related to deforestation for cultivation or conversion of land use from forests to other land uses has led to forest cover reduction and over-exploitation of natural forests. In this respect, Vietnam’s LDN policy seeks to enhance forest cover, protect national forests, restore degraded forest areas, undertake afforestation and reforestation, regenerate degrading forests and  promote forest certification. However, these concepts are relatively new to most forest owners. Despite, this, on the basis of Circular 28, most forest companies have begun developing these SLM plans. However, there is a lack of experience and capacity among forest owners on biodiversity conservation priorities, proven approaches to forest conservation, including among PA managers, which is impeding the management effectiveness of Protected Areas (PAs) and of other high-biodiversity forest areas, and impeding forest law enforcement. Forest owners face many problems in developing and implementing forest management plans, funding limitations and limited technical capacities on how to integrate biodiversity considerations and priorities, at landscape and site scale, into forest plans and operations. This has created a substantial need for technical cooperation, training and equipment by forest owners to prepare and implement SFM plans, and for participatory processes that put forest managers, including local communities, at the center of this process. Since 1995, Viet Nam local government (district people’s committees) have been allowed and encouraged to allocate forest lands to local households for the purpose of forest protection and planting, however, there is lack of capacity, skills and proven examples of best practices that area available to forest owners. Similarly, there is a lack of transparency in allocating forests and forestland various sustainable uses, lack of effective mechanisms to prevent and solve forest resource use conflicts, inadequate attention paid to gender and issues related to access of forest resources and benefit sharing mechanisms.

- Barrier 4: Lack of coordination among managers of individual FMUs and lack of experience maintaining connectivity among forest fragments: While, the Government of Vietnam supports collaborative management approaches that engage local communities in co-management of forests, most recently through the 2017 Law on Forestry, procedures are complex and time consuming, the pace of uptake is correspondingly slow and there is an ongoing need for successful demonstrations to be conducted and uptake encouraged. Most managers are narrowly focused on management of the area for which they are responsible, and attention is focused on general forest protection rather than explicit consideration of biodiversity assets and conservation needs. This leaves a gap in terms of management of landscape-level ecological processes, which may involve ten or more FMUs and numerous additional forested areas under the responsibility of Commune People’s Committees (CPCs), depending on the scale of the landscape. Addressing this issue requires landscape-level analytics and bringing managers together to develop and share plans and lessons learned, neither of which is typically done at present. Institutional capacity and responsible management to test different approaches to achieving landscape level conservation is lacking, thus inhibiting efforts to promote habitat connectivity and collaboration across different forest units within a particular landscape, such like the Ba River basin. Action here is constrained by insufficient incentives and weak landholders’ capacities for internalizing biodiversity conservation and other aspects of sustainable land and forest management in land management activities, working across institutional silos and promoting a more integrated approach to forest management at a broader landscape level. Existing forests are not always adequately zoned, lack connectivity across the landscape and consequently forest management does not fully reflect their biodiversity values and the ecosystem services they provide. This has led to the degradation of HCVF within protection forests as well as in currently ‘open areas’ such as those under the control of CPCs. There is an urgent need to map out HCVF areas and strengthen management in order to ensure that important species and ecosystem services are maintained. There is also a need to ensure linear ecological corridors (primary linkages) and stepping stone corridors (secondary linkages) for enhanced ecosystem services provision, wildlife movement, and as an adaptation measure against climate change.

- Barrier 5: Limited awareness and understanding of forest ecosystem service values, and inadequate use of financial incentives to support mainstreaming of these values in planning and management practices: The forests of the Ba River basin are vital for regulating water flows and for protecting water quality. They regulate water runoff during times of heavy rain, reducing flood events, and prevent soil runoff that increases the siltation of hydroelectric reservoirs. These services are essential to ensure future water and electricity supplies in Viet Nam. Forests also provide natural products such as rattan and NTFP for local populations and nationally important nature-based tourism resources. However, these ecosystem services and their economic values are not fully recognized or valued, and land managers in the Ba River basin lack incentives to effectively manage the land for biodiversity conservation and ecosystem service maintenance, or to increase the protection areas to enhance protection and connectivity. In addition to the need for stronger recognition of the value of forest ecosystem services, there is a need for those values to be internalized through financial mechanisms and incentives for conservation. Forest communities need to have incentives for keeping forests and biodiversity intact. Insufficient investment in SFM has often been framed as an issue of scarce finances. While there are several available opportunities, such as central government allocations and both public and private financial capital and funds, many are either untapped or used inefficiently. For example, Viet Nam’s payment for forest ecosystem services (PFES) program is deployed in the communities of the Ba River basin, but the functioning of this program on the ground is quite limited. It does not include sufficient monitoring to properly link provision of ecosystem services with payments received. In addition, certification of environmental-friendly forest products is increasingly being applied and developed in Viet Nam to strengthen the linkage between SFM practices and the production of commodities. However, these programs are not initially targeted for Gia Lai and Phu Yen provinces, and there is a need for the provincial and district decision-makers, and the communities living in Ba River Forest landscapes, to increase their awareness and understanding of ecosystem services financing mechanisms, so they may begin to take advantage of these opportunities. A second problem related to finance is that State Forest Companies (SFCs) and Forest Protection Management Boards (FPMBs), both of which manage large areas of natural forests (especially those at buffer zones), have no legal basis to make biodiversity-related budgetary requests.

- The long-term outcome of the project is to provide adequate incentives for local communities to conserve its native biodiversity, natural ecosystems and ensure sustainable forest management by reducing direct threats affecting the project target areas and their relationships with a range of indirect factors (root causes) are illustrated in Figure 1, with entry points for project intervention strategies indicated. The relationship between the barriers and the project intervention logic is further illustrated in the theory of change diagram in Figure 2

Baseline Scenario and Associated Baseline Projects

- A range of recent policy reforms and initiatives provide a supportive baseline for the project, helping address the threats, drivers and barriers outlined above. The Prime Minister of Viet Nam has issued a moratorium to ban harvesting of natural forests in Central Highlands and has ordered to stop further development of hydropower projects or any projects that involve natural forest conversion in the region. This high-level announcement indicates the strong commitment from the government to conserve natural forests and biodiversity.

- The new Planning Law (2017) provides a blueprint for more integrated and sustainable planning. Planning of many sectors of the economy, including forestry is covered by Article 25 of the new law. Among other changes, the new law mandates integration of climate change and environmental considerations into planning and includes measures to reduce the overlap of planning activities in many sectors, in order to bring greater transparency to the overall planning process. Provincial master plans for the period 2021-2030 are now under development across Viet Nam, including in the proposed project provinces.

- National forestry planning planned for 2020 and 2021 represents an important basis on which the present project can build and support the integration of forest monitoring results and forest issues more broadly into the new, integrated province plans emerging under the 2017 Planning Law. Viet Nam’s Forest Inventory and Planning Institute (FIPI), for its part, has developed a proposal for implementation of the National Forestry Development Planning for the period 2021-2030 and vision to 2050, based in part on regulations contained in the 2017 Planning Law. The plan is expected to be finalized in coming months and will provide a good foundation for the PPG. Under its mandates of forest monitoring and assessment, FIPI is scheduled to implement a National Forest Inventory, Monitoring and Assessment project in period of 2021-2025 (NFIMAP6) in order to update its database of forest resources. However, this inventory does not generally take account of biodiversity aspects.

- VNFOREST is the agency responsible for developing secondary legislation and the policy framework supporting the Forestry Law 2017. They are also responsible for managing the Central Highlands project. In 2019, the Vietnamese Government issued Decision No. 297 on Approving the Scheme on Protection, Restoration and Sustainable Development of the Central Highlands in the 2016-2030 period. This is an important foundation for forest investment and development activities, as well as protection of forest habitats and biodiversity conservation. It is expected to make an important contribution to Viet Nam’s LDN targets and Nationally Determined Contribution (NDC) achievements.

- The Government of Viet Nam aims to sustainably protect and develop 100% of the existing forests. Decree 118/2014 encourages SFCs to focus on delivering “public services” rather than timber. SFCs operating in many natural forests are thus meant to redirect efforts away from “timber production” to “public service production”, largely reflecting the poor quality of their forests. However, adequate management and financing mechanisms for these forests—needed to ensure their regeneration and protection from conversion, illegal logging and agricultural encroachment and to promote certification for some areas—remain to be defined.

- Provincial budgets include the management of protected areas that fall under the administration of the respective Provincial People’s Committees. PAs such as Kon Ka Kinh National Park and Kon Chu Rang Nature Reserve in Gia Lai, and Krong Trai Nature Reserve in Phu Yen are managed as Special Use Forests, with their own forest management/ranger units and management board.

- In support of Directive No. 430/NQ-HDND dated 09/05/2021 of Gia Lai People's Assembly on the plan to allocate the medium-term public investment plan for the 2021-2025 period in Gia Lai province, the capital envisaged includes budgetary support of US$15.272.000 for the following projects: 1) Forest protection and development for Gia Lai province, period 2021-2025; 2) Capacity building on forest fire prevention, forest management and protection in Gia Lai province, period 2022-2025; 3) Investment in sustainable forest management in Kon Ka Kinh National Park, period 2022-2025. This funding is emerging from Directive No. 430/NQ-HDND.

- Further, Gia Lai Provincial People’s Committee is expected to approve a KfW project, following Report No. 1047/ People's Committee-NL dated July 29, 2021 on the Investment Proposal for the project “Mitigating the impacts of the Corona epidemic on the economy and society through Protection, restoration and sustainable development of forests sustainable development in the Central Highlands, the Gia Lai province component" is funded by the German Government's ODA. The proposed project has a loan capital (ODA) of EUR 11,000,000, and a grant of EUR 1,900,000. The co-sponsorship section here only counts grants of EUR 1,900,000 equivalent to USD 2.0 million (rounded).

- Following Resolution No. 14/NQ-HDND dated June 29, 2021 approving the proposed medium-term public investment plan for the period of 2021-2025 in Phu Yen province. This is the capital source for forest protection and development for Phu Yen province, in the period of 2021-2025 is 23.7 billion VND, equivalent to 1.0 million USD.

- Further more, Phu Yen Provincial People’s Committee is expected to approve a KfW project, following Report No. 116/TTr-UBND dated October 30, 2020 on the appraisal of the report on investment policy proposals for the project “Sustainable forest restoration and management in the central and northern regions of Vietnam-KfW9, phase Section 1, Phu Yen Province”. The proposed project has a loan (ODA) of EUR 4,439,173 and a grant of EUR 1,885,069. The co-financing section here only counts grants of 1,886,069 EUR or 2.1 million USD (rounded).

- There are good opportunities for mainstreaming biodiversity conservation into forest management. For example, two State-owned forestry companies, Dak Rong and Tram Lap, plan to convert areas under their management into Special Use Forest, in conjunction with the new approval to establish a Kon Ha Nung Plateau Biosphere Reserve by the Gia Lai Provincial People’s Committee on 11 December 2021. The areas managed by the companies, which cover nearly 26,000 ha, include at least 10,000 ha of natural and biodiversity-significant forests within an important corridor located between Kon Ka Kinh National Park and Kon Chu Rang Nature Reserve and have become deforestation hotspots due to their relatively low level of protection (compared with Special Use Forests and Protection Forests). The interest in converting these production forests to Special Use Forest is an excellent opportunity to set-aside these as HCVF areas for protection and enhancement of connectivity between existing PAs and within the Kon Tum Plateau KBA. There is strong commitment and political support from Gia Lai province for this proposal, which will shortly be submitted for endorsement of the Provincial People’s Committee and MARD. Meanwhile, a project to assist local representatives in biodiversity conservation management and socio-economic development, for the period 2018-2025, is receiving approximately US$800,000 from the People Resources and Conservation Foundation Viet Nam Country Program. This area was also supported by prior GEF-3 investment through the UNDP-supported project “Making the Link: The Connection and Sustainable Management of Kon Ka Kinh National Park and Kon Chu Rang Nature Reserve)” over 2006-2011 which strengthened capacity and built community and forest company awareness for sustainable forest management and biodiversity conservation – investment that has helped catalyze the current interest to convert some of this area to a Special Use Forest. There are commitments at government level and sectoral level as in the Vietnam Forestry Sector Development plan 2021-2030, vision to 2030 gave priority for improving sustainable forest management, strengthening the management of natural resources and biodiversity, improving water security and land degradation, and mitigating the impact of climate change. Therefore, there’s high opportunity for the project to not only contribute helping the province to fulfilling its commitments but also at the sectoral and national level on forest management and biodiversity conservation.

- Viet Nam is one of the few countries to have established a PFES scheme for hydropower and clean water that recognizes the service provided by forests in maintaining watersheds. The Viet Nam Payment for Forest Environmental Services scheme, which has been operational since 2010, is implemented by provinces, which have some flexibility in defining how the scheme is carried out. From 2013-18, payments into the fund in Gia Lai have amounted to VND 528.8 billion (US$22.78 million), while Phu Yen has received VND 40.06 billion (US$1.73 million). PFES funds have helped finance forest management and protection, supported forestry companies and forest management boards to prevent logging of natural forests, and given timely support for mountain-dwelling people to protect forests with money to improve their living standards in the context of difficult state budget. Overall, however, PFES payments remain too small to significantly impact behavior in a way that will ensure effective forest conservation.

- Other relevant donor-funded efforts, which will form the foundation and partnerships on which the present project will build, include the following:

- The KfW 9 and KfW 10 projects support SFM in the project landscapes. The KfW 10 project “Protection and Inclusive Management of Forest Ecosystems in Quang Nam, Kon Tum and Gia Lai provinces” implemented from 2014-2020 with a total budget of €11,290,000 (US$12.574 million) has supported sustainable management and protection of natural production forests in Gia Lai, along with livelihood development. In the case of KfW 9, titled “Rehabilitation and sustainable forest management in Central and Northern Viet Nam”, Phu Yen province will receive support from 2021-2027, with budget for the province of €5,935,173 (US$6.6 million). Project components include: (1) Improving management of special use forests and national parks; (2) Improving management of protection forests and community forests; (3) Implementing environmental education measures.

- The GEF-funded Mainstreaming Natural Resource Management and Biodiversity Conservation Objectives into Socio-Economic Development Planning and Management of Biosphere Reserve in Viet Nam implemented from 2020-2024 with a total budget of US$6.66 million. The project is aimed at addressing these multiple threats by harmonizing socio-economic development, sustainable management of natural resources and biodiversity conservation through an integrated landscape approach in the planning and management of Biosphere Reserves in Vietnam.

- The JICA-funded project on Enhancing Sustainable Natural Resource Management Phase 2 implemented from 2021-2025. The project with overall goal is to enhance country's capacity for maximizing multiple benefits derived from forest ecosystems, which contributes to improved livelihoods of local people and mitigation of climate change impact through promotion of Sustainable Forest Management (SFM), REDD+ and biodiversity conservation.

- The ADB Biodiversity Corridors Conservation Project (ADB-BCC) implemented from 2011-2020 in Quang Nam, Quang Tri and Thua Thien Hue provinces to: (i) provide forest tenurial security to poor households and indigenous groups for collective management of forest resources; (ii) restore habitat on degraded communal forest lands; (iii) improve livelihoods and income-enhancing small-scale infrastructure, and; (iv) generate employment. In addition, the ADB Core Environment Program and Biodiversity Conservation Corridors Initiative, Phase II (ADB CEP-BCI II) regional initiative over 2013-2022 will build environmental planning systems, methods, and safeguards; improve management of transboundary biodiversity conservation landscapes and local livelihoods; establish climate-resilient and low-carbon strategies, and; improve institutions and financing for sustainable environmental management. The present project will build on good practices and lessons from these projects and try to visit project demonstration sites/villages to learn from their approaches.

- Viet Nam has had extensive engagement in REDD+, including UN-REDD, World Bank Forest Carbon Partnership Facility (FCPF – who funded initial REDD+ preparation activities) and support from Japan International Cooperation Agency (JICA) and Dutch Development Agency (SNV). The Central Highlands is a key area for REDD+ investment (although this has been largely outside of the proposed project provinces). For example, SNV Netherlands Development Organization implemented from 2010-2014 the “Participatory Forest Monitoring (PFM)” project in Lam Dong Province. PFM is an ‘operating system’ with social, climate and governance applications useful to restoration. The present project will look to build on SFM/REDD+ work with community forest groups within Ba River landscapes.

- A project on “Rehabilitation, Restoration and Sustainable Management of Protection Forests” (also known as ‘JICA2’) in 11 provinces, including Phu Yen, will be carried out in the period of 2012-2021. Its specific objectives are to: (1) restore and develop watershed protection forests; (2) strengthen capacity for local government and protection forest owners, and; (3) support improved livelihood for communities participating in managing protection forests. The total budget for this project is around US$123,479,000. The project can offer lessons on capacity development approaches and community livelihoods support.

- The People Resources and Conservation Foundation/Viet Nam Country Program is working with the Gia Lai DARD through the project entitled “Support on community-based biodiversity conservation in Kon Ha Nung Highland Landscape, Gia Lai province” over 2018-2025. The project is working in 18 villages (15 villages of Dak Rong commune, and 3 villages of Son Lang) to support assessments and documentation for the proposal to establish a community-based reserve in the production forests located between Kon Ka Kinh National Park and Kon Chu Rang Nature Reserve, with a budget of US$800,000. This project can offer incremental support for the establishment of this PA through dedicated capacity building for ranger staff and support for biodiversity conservation, monitoring, patrolling and surveillance.

- An upcoming European Union (EU)-funded €5 million (US$5.957 million) project on “Integrated sustainable landscape management through deforestation-free jurisdiction project in Lam Dong and Dak Nong” implemented by UNDP with MARD and PPCs of Lam Dong and Dak Nong Provinces, is expected to take place between 2021-2025. This project is focused on deforestation-free value chains but includes support for district land use planning processes and monitoring, which can provide knowledge and lessons exchange with this project.

- In the Central Highlands, the following projects are also being implemented, such as (i) Project “Conservation, Sustainable Use of Forest Biodiversity and Ecosystem Services in Viet Nam” (GIZ-Bio) financed by the German Ministry for Economic Cooperation and Development (BMZ) with counter-part funds from the Vietnamese Government. It is the continuation of a project with the same name that took place from 2015-2021 (Phase I and Phase II); and (ii) project Delivering Multiple Benefits from REDD+ in Southeast Asia (MB-REDD), implemented by SNV – The Netherlands Development Organization.

Landscape level conservation emphasis lacking among forest management units

Forest managers focused on forest protection rather than on conservation of biological assets

Limited attention to promoting community co-management of forests

Limited guidance on planning and implementation of sustainable forest management

Outcome 1: Enabling framework and systemic tools to improve land use planning and monitoring

Component 2: Biodiversity and protected areas strengthened through improved coordination

Lack of emphasis on linear corridors and stepping stones to enhance conservation and ecosystem values

Direct Threat

Contributing Factor

Project Intervention

Strategy

Impacts

LEGEND

Global emissions

Declining agricultural productivity and food security

Deficient community livelihoods

Loss of natural ecosystem functions and resilience

Loss of key species and biodiversity

Water and soil pollution and loss

Hunting and poaching

Encroachment into natural forests

Mid-Term Impacts

Over-exploitation of forest resources

Deforestation, degradation and fragmentation of forests

Climate Change

Weak community capacity for sustainable resource management

Emphasis on short-term means for survival

Land displacement has driven marginalized communities to increase dependence on forests

Inadequate consideration of financial instruments as tools for conservation

Limited awareness of forest services and values

Forest communities have limited incentives for protecting forests

Communities do not fully recognize and value ecosystem services

Limited tools and experience in promoting conservation and land management priorities in forest operations

Limited technical support, equipment and tools to prepare sustainable forest management plans

Lack of capacity to assess biodiversity priorities, needs and approaches for forest management

Lack of regulations and guidelines hinder application of legal instruments

Inadequate guidance impedes application of policy for mainstreaming biodiversity into forest and land use planning

Component 3: Knowledge management, capacity support and replication of improved forest management

Poverty and marginalization of forest communities

Immense competition for land

Conflicting priorities of sector agencies and stakeholders

Lack of information on biodiversity assets, condition and trends

Inadequate understanding of site-based threats prevents adequate responses

Limited information constraint ability to integrate biodiversity into forest management plans

Weak capacity and information to address forest and land degradation

Increased population growth and demand for land and natural resources

Commune forests not effectively managed

Insufficient incentives and capacity to internalize biodiversity and sustainable management practices

Limited coordination and experience in maintaining connectivity between forest fragments

Availability of capital investments encourage forest clearance

Figure 1: Conceptual Diagram for the Project

Long-Term Impacts

Alignment with national and global priorities:

- The project is aligned with the following national and global strategies and plans that link directly to global conventions and related initiatives:

(a) Alignment with national priorities

- Vietnam’s National Biodiversity Strategy to 2020, Vision to 2030,  has the following  strategic goals that are aligned to the project outcomes, namely: consolidation and completion of the system of PAs, conservation of ecosystems of national and international importance; preventing the decline of threatened species, particularly endangered, rare and precious species; enhancing the effectiveness of conservation units; sustainable use of ecosystems; control of unsustainable activities and illegal hunting and trade, promote biodiversity as a means to respond to climate change; development of biological corridors to increase connectivity, integrating biodiversity in policy development, and increase financial resources for biodiversity conservation.

- Vietnam’s Biodiversity Master Plan to 2020, with orientation to 2030 call for the following (i) to combine in-situ conservation with ex-situ conservation and other forms of conservation to ensure effective conservation, consistency and conformity with conditionsof each region in the whole country without affecting national defense and security;(ii) To harmoniously combine conservation and rational exploitation and use ofbiological resources, attaching importance to maintaining and developing ecosystemservices, environment and landscape of biodiversity;(iii) To consistently comply with the criteria set out in the Law on Biodiversity on the basis of inheriting to the utmost the achievements and maintaining the stability of the existing special-use forest, marine and inland water conservation zones; (iv) To ensure safety of biodiversity, mitigate the degradation and depletion of natural resources, mitigate and adapt to climate change; and (v) To mobilize all resources and experiences of organizations, individuals and communities in the biodiversity conservation; to ensure the principles of equitable and harmonious sharing of interests of the stakeholders

- Vietnam National Capacity Self-Assessment (NCSA) under UNCBD, UNFCCC, UNCCD: recognizes the need for multi-stakeholder consensus and decision-making, interaction of capacity building in wider efforts to achieve sustainability, promotion of partnerships and collaboration to maximize impacts and create synergies, etc. that can have a positive impact in conservation of species, habitats and ecosystem services in the Central Highlands.

- National Adaptation Program of Action (NAPA), Draft 2021-2030: The project will contribute directly to four of the priority climate change adaptation areas of activity, namely: securing climate smart agricultural and livestock production practices; mainstreaming of climate change into development and implementation of strategies and plans, and strengthening capacity building to respond to climate risks.

- Vietnam’s Aligned National Action Program To Combat Land Desertification and achievement of Vietnam’s Voluntary National Land Degradation Neutrality (LDN) targets for period of 2017-2020 with vision to 2030, prioritizes sustainable land management with a focus on ‘hotspots’, one of which is the Central Highlands which has partial overlap with the Ba River Basin. Nine of the 11 national voluntary land degradation targets refer directly to the Central Highlands. In 2017-18, Viet Nam undertook a number of activities related to the LDN Target Setting Programme. These included development of a so-called ‘leverage plan’, assessment of the trends and drivers of land degradation and estimating baselines and national voluntary LDN targets. The assessment highlighted “deforestation for cultivation or conversion of land use from forest to other land clearing to forest cover reduction and over-exploitation of natural forests leading to reduction in forest reserves” as a key driver. The national voluntary LDN targets that emerged from the process included two sections: agriculture and forestry. Regarding the latter, the targets relevant to the project include: forest protection (three million ha) and natural forest restoration (410,000 ha), to be achieved through a mix of domestic and international support. Both of these targets are associated with the North West and Central Highlands area. Gia Lai Province is located in the Central Highlands.

(b) Alignment with International priorities

- Within the global context, the project will contribute to achieving the UNCBD Aichi Biodiversity Targets, in particular:

- Strategic Goal B - Reduce the direct pressures on biodiversity and promote sustainable use: Target 5 By 2020 the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced; Target 7 By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity; Target 10 By 2015, the multiple anthropogenic pressures on coral reefs, and other vulnerable ecosystems impacted by climate change or ocean acidification are minimized, so as to maintain their integrity and functioning.

- Strategic Goal C  - To improve the status of biodiversity by safeguarding ecosystems, species and genetic diversity: Target 12 by 2020, the extinction of known threatened species has been prevented and their conservation status, particularly of those most in decline, has improved and sustained.

- Strategic Goal D - Enhance the benefits to all from biodiversity and ecosystem services: Target 15 By 2020, ecosystem resilience and the contribution of biodiversity to carbon stocks has been enhanced, through conservation and restoration, including restoration of at least 15 percent of degraded ecosystems, thereby contributing to climate change mitigation and adaptation and to combating desertification.

- The project also contributes to the post-2015 development agenda, notably with respect to the following Sustainable Development Goals (SDGs):

- SDG 15 Protect, restore, and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss, by supporting targets 15.1 (conservation and sustainable management of forests in Vietnam, including PA networks), 15.2 (sustainable forest management), 15.3 (reducing desertification, restoring degraded land) and 15.5 (reduced degradation of natural habitats).

- Strategy

- The long-term goal of the project is to establish a comprehensive and integrated landscape planning and management framework to mainstream land and natural resource management and biodiversity conservation objectives into forest management and sub-national and sector socio-economic development and community resource management within key biodiversity landscapes in the Ba River basin. Its objective is to operationalize integrated landscape management of forested landscapes to generate multiple benefits including effective conservation of globally threatened species and high conservation value forests, reduce deforestation and degradation and enhance local biodiversity-friendly livelihoods. The project recognizes implementation of such an integrated strategy is an integral part of achieving a balanced approach to development and community resource use that conserves biodiversity in biologically rich landscapes. To achieve this objective, the GEF alternative aims to: (i) take into account the interconnectivity of various ecosystems in the Ba river basin and their impacts on biodiversity, ecological processes and functions of forest management, local economic planning and local community activities; (ii) ensure that relevant forest agencies and actors have adequate capacities to promote integrated approaches and tackle the threat to biodiversity and promote effective natural resources and forest management; and (iii) advocate use of indigenous knowledge systems and practices to conserve biodiversity, restore degraded forest areas and promote environmentally sustainable use of forest products. The project will be implemented over a 4-year period based on the following principles:

- Promoting a holistic, multi-sectoral and integrated landscape management approach to resource governance in the Ba River basin as compared to the exclusive protected area centric approach to facilitate the maintenance of the ecological integrity of the biological landscape and its constituent parts. This will, in particular focus on (i) establishing connectivity between HCVFs within and outside protected areas to bridge existing conservation gaps within the landscape sites and reducing fragmentation through creation of new, and/or expansion of existing protected areas and restoration of degraded forests and riparian areas: (ii) improving management effectiveness of existing protected areas to reduce threats and enhance conservation outcomes; (iii) enhanced mainstreaming of biodiversity within production and protection forests and support for sustainable forest management practices so as to contribute towards conservation of endemic and threatened species, habitats and enhanced ecosystem services; (iv) Improved co-management of commune managed forests and biodiversity-friendly livelihood development in buffer zones of protected areas to serve as stepping stones for species conservation within the landscapes; and (v) promotion of financial incentives, including more effective use of PFES approaches to strengthen local community involvement and support for conservation in forest patches within the landscape as a means for conservation and restoration of species, improving connectivity and enhancing forest-based revenues. The above-referenced approach entails improved conservation, restoration and mainstreaming of biodiversity across the range of forest management types (e.g.,, Special Use Forests – PAs, Protection Forests, Production Forests) along with integration into broader jurisdictional planning processes and the socioeconomic development of local communities.

- The project’s incremental or catalytic value lies in testing and validating existing regulations/guidelines and practices for effective implementation of the Forestry and Planning Acts of 2017, in particular relating to role of forest rangers and Forest Management Boards in special-use and production forests; planning, implementation and monitoring the effectiveness of SFM plans; integration of forest and biodiversity conservation in provincial master planning; linking PFES funding to conservation and SFM outcomes; and improving and diversifying funding to Forest Management Boards to improve financial sustainability;

- Supporting and implementing a participatory/consultative bottom-up planning and implementation approach that focuses on provincial, district and community priorities and decisions that integrate conservation, sustainable forest management, climate risk management and livelihood outcomes;

- Strengthening the role of communities (including ethnic minorities indigenous), provincial, district and local government institutions, community-based organizations and non-governmental organizations and increasing their potential for becoming agents of change in promoting sustainable natural resource management, climate risk management and biodiversity conservation;

- Strengthening capacities of communities, Civil Society Organizations (CSOs), Non-Government Organizations (NGOs) and private sector for implementing effective biodiversity-friendly income generation and livelihood activities;

- Ensuring that in its development and implementation, gender is mainstreamed so that the project contributes to equality and equity, through the creation of equitable opportunities and benefits for both women and men;

- Ensuring an adaptive management approach that progressively identifies and addresses threats to biodiversity and natural resources and associated challenges, including those related to ecological, demographical, climatic, market, technological and economic factors in the biological corridors;

- Ensuring free prior and informed consent (FPIC) that can be patterned after UN-REDD (Viet Nam) FPIC guidance document of 2020 as the basis for negotiating investments for local communities, especially ethnic minorities, and ensuring that any displacement of incomes or access to resources are adequately compensated through alternative livelihood improvement plans;

- Being selective in terms of identification of locations and nature of interventions to serve as demonstration models in the Ba River basin and in addressing the nature of challenges that operate therein taking into considerations the existing institutional capacity and resource constraints; and

- Improving awareness and knowledge and strengthening gender mainstreaming and monitoring and evaluation as means to improve conservation impacts.

- In order to ensure a clear, practical and cohesive implementation strategy, the proposed project will introduce a structured planning and integrated framework for managing biodiversity across targeted landscapes in the Ba River basin. This framework will engender a two-pronged, mutually re-enforcing approach of (i) strengthening efforts for conservation of biodiversity in large biological landscapes, and (ii) demonstrating sustainable forest management and livelihood initiatives for tackling reduction of pressures and threats to biodiversity while strengthening benefits to local communities. Targeted activities under both directional focuses will be implemented under a linked provincial and local level coordinated planning and management umbrella platform, supported by updated planning and operational guidance documents as well as the strengthened inter-sectoral planning and management mechanisms.

- Investment at the landscape-level, will be defined through an increased understanding of landscape-level biodiversity and ecosystem services priorities as needed – and to underpin this, enhanced dedicated analytical tools and monitoring frameworks will be developed under Component 1. Such tools are required to inform site-level management and serve as a means for integration into provincial and district master planning processes to arrest forest degradation and loss, including through the spatially explicit consideration of important biodiversity areas alongside the priorities of other sectors. Open and active dialogue across multiple stakeholder groups is needed to build a common understanding of priorities, co-benefits and areas of conflict that need to be resolved. Building on the analytical tools and monitoring protocols developed under Component 1, investment activities (under Component 2) in the Ba River basin are strategically located to demonstrate tangible impacts and outcomes and avoid the ineffective spread of activities. To do so, the project will attempt to locate a suitable mix of project investments in selected locations of high conservation value areas within the river basin, where tangible impacts on biodiversity conservation, improved conservation-oriented forest management practices and threat reduction can be demonstrated. The selection of target locations is based on specific criteria that help determine areas that are most biologically significant for conservation and/or able to demonstrate new approaches to landscape conservation. Consequently, the key biodiversity areas (KBAs) within the targeted landscapes will form the basis for demonstration of investments and achievement of conservation outcomes. Each target location/area will encompass existing PAs, production and protection forests, commune managed areas and areas adjacent to them that are necessary to provide critical conservation linkages necessary to maintain ecological integrity and species dispersal within the river basin. Through this approach, on-the-ground initiatives in targeted locations in the Ba River basin will both be guided by, and provide feedback loops into, enabling policy, institutional and regulatory initiatives at the national and provincial level (under Component 3), while linking conservation-oriented actions with socio-economic, sectoral and livelihood-focused actions at the river basin level.

- In summary, in the proposed alternative scenario, Ba River Basin forests and constituent biodiversity and ecosystem services are being managed more strategically with the enhanced participation of local, forest-dependent communities and private sector. Biodiversity conservation and forest restoration investments and other actions are being based on a broader, landscape-level understanding of ecological processes, connectivity, and landscape-level threats. Protected areas and other significant natural forests are being managed more sustainably, with explicit consideration of biodiversity conservation and better management of threats to biodiversity at site- and landscape-level. Lessons learned and experiences are being shared with managers and decision makers across the Basin and nationally, facilitating necessary regulatory and policy changes to support broader replication and uptake. The project objective is to be achieved through the implementation of three inter-related and mutually complementary components that are focused at addressing the barriers discussed in the previous section of this report and represented in Figure 1. The three components of the project are:

- Component 1: Mainstreaming biodiversity and ecosystem services into landscape-level planning, monitoring and enforcement

- Component 2: Conserving globally significant biodiversity and ecosystem services in forested landscapes of Ba River basin

- Component 3: Gender mainstreaming replication and knowledge exchange

- The project strategy was approved at national and provincial-level validation workshops.

- To achieve this objective the project will utilize 3 strategies (Project Components) with intervention pathways described in the theory of change diagram in Figure 2 below. The Components (GEF project alternative) will aim to remove the barriers to accomplishing the long-term solution (see Fig. 1). The details of the suggested Theory of Change are shown in Figure 2.

Project Areas

- The Ba River basin is the largest basin in the South-Central region of Viet Nam, covering an area of approximately 14,528 km2 over 22 districts and cities of three provinces, namely Dak Lak and Gia Lai provinces in Central highland region and coastal province of Phu Yen in South central region. The Ba River basin is formed from the combination of three main sub-river basins and reservoirs, including La Yun River, Krong H’Nang river and Hinh river, and lakes of Ayun Ha, Song Hinh, Ba Ha, Krong H’nang, KaNak and An Khe. Based on the forest cover data of 2019, total area of forestland is about 639,000 ha, that includes 563,000 ha of natural forests, 62,000 ha of mature plantation forests, and 14,000 ha of young plantation forests. In term of the forest functions, the forested areas are classified as 90,000 ha of special use forests, 120,000 ha of protection forests, 411,000 ha of production forests, and 18,000 ha of forests outside forestry use plan.

- The following are the eight Forest Management Units within the Gia Lai and Phu Yen provinces that would be the focus of the project within the Ba River basin. In addition, the project will support community co-management in around 1,000 ha of Commune managed forestland.

| Provinces | Forest Management Units | Extents (Hectares) |
| --- | --- | --- |
| Gia Lai Province | Kon Ka Kinh National Park | 41,445 |
|  | Kon Chu Rang Nature Reserve | 15,425 |
|  | Chu Mo Forest Protection Management Unit | 23,915 |
|  | Kong Chieng Forest Company | 15,270 |
|  | Tram Lap Forest Company | 10,286 |
|  | Dak Rong Forest Company | 15,544 |
| Phu Yen Province | Krong Trai Nature Reserve | 13,767 |
|  | Son Hoa Forest Protection Management Unit | 14,141 |

Table 1: Geographical, Biological and Socio-economic Features of target Landscapes in Ba River Basin

| Geographic and Biological Features of target landscapes | Socio-Economic Features of target landscapes |
| --- | --- |
| Gia Lai Province |  |
| Kon Ka Kinh National Park and Kon Chu Rang Nature Reserve and its connecting areas are located at the junction between Pleiku plateau and Kon Ha Nung plateau. The PAs with its connecting area (Tram Lap and Dak Rong) form the main part of the Kon Ha Nung plateau. Topography of the landscape gradually lowers from North to South. The low area is Ba River (570 m to the highest peak Kon Ka Kinh mount (1,748 m). The landscape is dominated by evergreen forest mix deciduous forest, mixed bamboo forest, and a few small pockets of grassland. The landscape is home to some of rarest wildlife in Indochina region include the Kon Ka Kinh laughing thrush (Garrulax konkakinhensis), large antled muntjac Muntiacus vuquangensis, dark muntjac Muntiacus truongsonensis, and northern, yellow-checked gibbon Nomascus annamensis, grey-shanked douc Pygathrix cinerea and many other highly threaten bird, reptile, and amphibian and plant such as the Vietnamese rosewood Dalbergia oliveri and Siamese rosewood Dalbergia cochinchinensis. Linking the two protected areas are the Tram Lap and Dak Rong forest companies which sharing similar biological and geographical condition that perfectly connecting the two PAs forming a great conservation landscape in central highland as well as strategic watershed of the Ba River. The connecting conservation corridor Tram Lam and Dak Rong is sharing the same biodiversity and landscape features with the Kon Ka Kinh and Kon Chu Rang. A recent biodiversity survey confirmed that the corridor is home to at least 46 species of mammals, 124 species of birds, 38 amphibian species, 29 reptiles and over 501 species of terrestrial vascular plants (GreenViet and PanNature, 2019). Among those, there are 18 mammal species listed in the Viet Nam Red Data Book (2007) and IUCN Red List of Threatened species as Vulnerable (VU) and higher categories. The list of important mammal species for monitoring and conservation purposes in the corridor includes Gray-shanked Douc Pygathrix cinerea; Northern yellow-cheeked gibbon Nomascus annamensis; Pygmy Loris Nycticebus pygmaeus; Serow Capricornis Sumatraensis; sunda pangolin Manis javanica; Giant muntjac Muntiacus vuquangensis and Truong Son Muntjac Muntiacus truongsonensis. Six bird species are listed in the Viet Nam Red Data Book and Global IUCN Red List as VU and higher categories. For amphibians and reptiles, 12 species are named in the Viet Nam Red Data Book and IUCN Red List as VU and higher in the classification. The most notable species is the Rice Frog Microhyla sp. The recorded terrestrial vascular plants include 29 rare and endangered plant species, of which 10 are Endangered (EN) according to the Viet Nam Red Data Book (2007). These include Drynaria fortunei, Fokienia hodginsii, Rhopalocnemis phalloides, Afzelia xylocarpa, Dalbergia cochinchinensis, Dalbergia oliveri, Pterocarpus macrocarpus, Calamus poilanei, Anoectochilus spp. and Dendrobium spp. and many other highly threatened Paphiopedilum orchids and medicinal plants. | Kon Ka Kinh National Park: The total population of the 6 buffer zone’s communes were 24,906 in 2019. The Kinh group had 5,022 inhabitants (20.16 percent). Banar and other ethnic minorities had 19,884 inhabitants (79.84 percent). Most are engaged in agriculture and forestry; a small proportion has non-farm jobs. Kon Chu Rang Nature Reserve: The buffer zone of the Kon Chu Rang Nature Reserve had a population of 8,377 inhabitants in 2019. The Kinh people were 2,728 inhabitants (32.6 percent). The rest was Banar people and others, of which the Banar occupies 65 percent of the population. The local labor force had 6,483 people within labor age range of which women occupied 50 percent. Most engage in agricultural production while a few people have other jobs. Local incomes remain low, and unemployment high. Local residents living in the buffer zone of Kon Ka Kinh National Park and Kon Chu Rang Nature Reserve (Gia Lai province) are predominantly Banar people. E De are Ethnic Minority (EM) living mostly in buffer zone of Krong Trai Nature Reserve (Phu Yen province). They own their traditional culture and customs and is led by an elected village head. Traditional customs exist with matriarchal social features where women are highly appreciated in the family and clan. The Banar and Ede are historically matri-focused and matrilineal, in contrast to the majority Kinh’s patriarchal tradition. The Banar and Ede women have traditionally been heads of families. Accordingly, wealth and land are passed from mother to daughter. Son did not inherit assets from their mother, but now there is equality in the asset division between daughter and son. The Banar and Ede women also decide issues related to the household affairs. However, a comprehensive transition to a male-dominated patriarchal society is taking place, narrowing women’s sphere to domestic life while broadening men’s role in household management. Ethnic women collect a variety of forest products that they are likely to devote directly to family use, although they also sell several products to meet basic household needs. During the upland cultivation season, the energy and time of many women is devoted to swidden fields and the care of small children. Despite these constraints, firewood, bamboo shoots, medicinal plants and vegetables are collected for their daily consumption. Bamboo shoots appear to be regularly harvested as a supplement to the Banar’s basic staple of rice and cassava. During times of hunger and rice shortage, firewood and bamboo shoots can also be sold in the local market to buy rice. In recent years, the collection of bamboo shoots has been decreasing because the forest area has become smaller, and the shoots have become less available in the forest. In some areas, bamboo shoots are now rarely found in the nearby forest. Collecting “broom grass” (Thysanolaena maxima) in the forest and making charcoal in some hamlets have brought regular cash income for women. Broomgrass is collected from fallow and bare lands by the Banars in Kon Ka Kinh national park. Hunting, often done by men, is a traditional activity of the Banar and Ede groups, but in recent years, hunting has declined. Trapping is the main method of catching animals, such as squirrels, wild pigs, rats, muntjac, and other small animals. Both men and women collect honey from the hives of wild bees. However, in recent years, honey has become scarcer, suggesting that this resource has been overexploited. |
| Phu Yen Province |  |
| The Krong Trai Nature Reserve is situated in the transition area between the Central Highlands and South-central coastal region. The topography of the reserve includes East and Northeast is dominant by low hills, including Mo O (434 m), Ha Gian (431 m), Ca Te (560 m), Hon Dat (590 m), Hon O (574 m) and Hon Tao (414 m). Other areas in the reserve are flat areas in low hills at the average 150 m in elevation. Water bodies and streams in the eastern of reserve feed the Cha Rang River. Streams in the reserve run into Ba rivers. Krong Trai Nature Reserve is dominant of evergreen forest, semi-evergreen and deciduous forest and other habitats present include natural grassland, scrub and swamp (Krong Trai, 2020). The forest in this reserve is dominated by species of the Dipterocarpaceae and Fabaceae families. According to the most recent biodiversity survey (Krong Trai, 2020), conform there are at least 989 of vascular plant include some endangered species include Aquilaria crassna, Dalbergia oliveri, D. cochinchinensis; 83 mammal species and 218 bird species and 42 reptile, 19 species of amphibian. Among the threatened wildlife, there are some important species include the Green Peafowl Pavo munticus, Lesser Adjutant Leptoptilos javanicus. The reserve was formerly known as a key area for wildlife cattle such as the gaur Bos gaurus and the Banteng Bos javanicus however the two species are now believed to be extirpated from this reserve because of poaching. Still, the reserve is believed to be a suitable habitat for ungulates and raptor. | Krong Trai Nature Reserve: The total population of Krong Trai Nature Reserve buffer zone is 16,384 inhabitants in 2019 and consists of 8 EM groups, including E De (35.8 percent), Kinh (33.3 percent), Cham Hroi (20.7 percent), and the rest are Tay, Bana, Gia Rai and others (10.24 percent). E De are EMs living mostly in the buffer zone of Krong Trai Nature Reserve (Phu Yen Province). They have traditional culture and customs and are led by an elected village head. Ede families are still matriarchal. The head of the family is always a woman. Children bear their mother’s surname and sons are not entitled to an inheritance. The groom moves to his wife’s house to live. Daughters inherit the ancestors’ assets. The youngest daughter inherits the house to continue worshipping the ancestors and is responsible for looking after her aging parents. Women are responsible for family management, childcare, and ancestral graves. Men are responsible for doing business with the outside communities and related to religious and political matters, so that the role and position of Ede men outside the society is very large. Unlike other ethnic groups in Phu Yen province like the Cham and the Banar, the Ede ethnic women people have retained their traditional weaving craft. In addition to their traditional long houses, papooses and hunting tools, weaving looms are indispensable in their lives. Ede women in Son Hoa district have for years been weaving various patterns of brocade. Women in Suoi Trai commune, Son Hoa district own a traditional brocade technique, but brocade products are mainly served for local fashion at traditional festivals and some orders from outsiders. Previously, the Ede were engaged in hunting, fishing, farming, knitting and weaving. Now they practice the alternation of crops and plant industrial trees like coffee, rubber, pepper and cacao. Some raise buffaloes and cows. Ede handicraft items include cloth, bronze, wooden and pottery products, and jewelry. The farming practices of the Ede community have not yet developed, and little scientific and technical progress has been applied in rice cultivation. They cultivate paddy rice with 1-2 crops a year with traditional cultivation methods. The Ede are yet to practice more intensive farming methods so the productivity is not high. Cassava is also the main crop of buffer zone’s communes of the Nature Reserve due to a cassava flour processing facility located in Son Hoa district. In recent years, local people converted paddy cultivation to sugarcane production due to the establishment of a sugar processing facility in the area. In terms of livestock, cow raising/fattening is the main production, but local practice is extensive, relying on forest benefits without feeding. Pig and poultry production is not developed in the area. Other ethnic groups such as the Cham Hroi, Tay, Ba Na, Gia Rai have main livelihoods of cultivation and husbandry. In general, Son Hoa district government prioritized the district’s economic development focusing on cassava and sugarcane planting and cow raising. Local people also benefit from forests such as gleaning bamboo shoots, honey, mushrooms, and local ginseng and wild animal hunting for their consumption. Exploitation of high-value forest tree species such as Lộc vừng Barringtonia acutangula, Thiên tuế Cycas rumphii, Nhội Bischofia javanica, Đa, Sung Ficus occur for commercial purposes, but have negative impacts on forest biodiversity. |

Repication, scaling up and sustainability plan and Communication strategy enhancing support of policy makers and community groups

Awareness and training guide forest owners in sustainable actions

Outcomes

Impacts

Forest and biodiversity restored

Biodiversity integrated into provincial land use and sector actions

Improved coordination across agencies at landscape

Current Situation

Replication of best conservation practices strongly supported

Problems to be resolved

Loss of key species and biodiversity

Loss of ecosystem resilience

Deficient community livelihoods

Declining agricultural productivity

Global emissions

Forests under co-management and sustainable practices that improve ecosystem services

Greenhouse gas mitigation

Improved well-being of communities and ethnic minorities

Improved connectivity of forests and habitats

Improved status of native species and biodiversity

Long-Term Conservation and Development Targets

Conservation and Development Targets

Project Outcomes and impacts

Project Outputs

Project Outputs

Project Outputs

Legend

Figure 2: Theory of Change

Forest owners take actions to conserve forests

Forests and biodiversity effectively managed in commune lands

Forests produce sustainable goods and services

Improved habitat connectivity between forest patches

Protected areas and forest estates effectively managed

Communities derive incentives from forest management

Annual forest management plans integrate biodiversity outcomes

Forest and biodiversity monitoring and inventory applied

Improved surveillance, monitoring and enforcement

Forest management and restoration strategies in land use plans

Communication and knowledge sharing of sustainable forest management and biodiversity best practices

Monitoring and evaluation incorporating gender

Enhanced capacity and awareness of forest owners to integrate biodiversity and ecosystem services into sustainable land management plans

Component 3

Participatory monitoring and inventory on biodiversity assets operationalized at protected area and forest management units

Biodiversity priorities integrated into sustainable forest management plans and operations

Improved protected area management and creation of new special use forest category

Community-based participatory forest management

Livelihood development for women, including forest value chains and entrepreneurship

Landscape connectivity through restoration using indigenous species

Financial intensive mechanisms used effectively for resource mobilization for enhancing conservation and sustainable forest use

Component 2

Enhanced coordination on wildlife and forest monitoring and enforcement at inter-provincial level

Monitoring and assessing forest resource changes and biodiversity

Component 1

Spatially-explicit biodiversity and high conservation value forest conservation and restoration strategies integrated into provincial and district land use plans

Multi-stakeholder platforms at provincial level support multi-sector dialogue on mainstreaming biodiversity into land use and master planning

GEF Alternate Strategy

Outputs

Theory of Change Narrative

- The objective of the project is to conserve forest biology and maintain or improve the flow of ecosystem services through sustainable forest management embedded in a coordinated landscape-level approach across the Ba River Basin.

- Based on the above analysis of barriers to promoting conservation of high biodiversity forests and forest biology, the Theory of Change (refer Figure 2) is based on three impact pathways: (i) Strengthened enabling framework and systemic tools to monitor biodiversity and ecosystem services and incorporate these into land use and forest planning, monitoring and enforcement; (ii) Demonstration of forest restoration and management practices across a range of forest management systems aimed at conserving priority forests, improving sustainable forest management practices and enhancing local livelihoods; and (iii) design and implementation of systems to ensure monitoring and evaluation, knowledge management and gender mainstreaming to facilitate replication.

- These impact pathways will enable Forest managers, provincial administration and local stakeholders (including ethnic minorities) to agree on management objectives for over 150,000 hectares of high biodiversity value forests and multiple use landscape with the Ba River Basin, starting the process of reducing degradation and over exploitation of such forests and halting environmentally unfriendly and unsustainable land use practices. In the short-term, this will improve management of 71,106 hectares of natural forests within the protected areas, upgrade 10,000 hectares of forest company forests to protected area status to improve biological connectivity, undertake forest restoration in 500 hectares of degraded or degrading forests, bring around 56,658 hectares of production and protection forest under improved biodiversity conservation practice and promote community co-management in commune managed forests and improved and sustainable agricultural practice in a total of around 17,827 hectares. In addition, the pathways will directly benefit around 3,000 local communities, including ethnic minorities through improved access to sustainable harvest of forest products, livelihood practices, gender mainstreaming and improved environmental conditions. Over the medium to long term, the pathways will contribute to realizing conservation targets in the biologically rich Central Highlands, securing current carbon stocks, and in stabilizing biodiversity and ecosystem services within the Ba River Basin. This will be achieved while simultaneously improving the economic stability of local communities and ethnic minorities, compliance with best practices that integrate species and biodiversity conservation in forest management practices, achievement of environmental, social and gender standards for forest management. Adopting an integrated landscape management approach (through piloting in selected target sites under different management regimes) will provide learning and best practices for its mainstreaming throughout the Ba River Basin, and elsewhere in the country. The coordination platforms established at the provincial level and inter-provincial collaboration systems for managing illegal wildlife activities will help create processes and decision-making that is built on enhancing the conservation of forests, safeguard ecosystem services and enable multiple actors (forest owners, development planners, local communities and ethnic minorities) to pursue their individual and shared interests in managing the forest and biological resources, and the services they provide within the Ba River Basin. These systems will be promoted and replicated within the basin.

Impact Pathway 1: Strengthened enabling framework and systemic tools to monitor biodiversity and ecosystem services and incorporate these into land use and forest planning, monitoring and enforcement

- The first impact pathway will build on developing a set of enhanced dedicated analytical tools and monitoring frameworks to inform site-level management and also serve as a means for integration into provincial and district master planning processes to arrest forest degradation and biodiversity loss. It will help enhance information and capacities that would enable open and active dialogue across multiple stakeholder groups to build a common understanding of priorities, co-benefits and areas of conflict that need to be resolved. It will strengthen the capacity and skills of the forest agencies, development planners and decision makers to enable development of appropriate forest management and restoration strategies, improve inter-provincial monitoring, surveillance and enforcement measures.

- The Coordination Platform for multi-level planning and management will be strengthened. Recommendations and guidelines for forest management and standards for ensuring integration of biodiversity considerations into forest planning would be developed so that priorities for conservation, restoration and sustainable forest management practices will be implemented to ensure that the landscape continues to deliver ecosystem goods and services to all stakeholder groups, while minimizing loss of forests and biodiversity. This set of interventions will create an enabling framework for effective management of the remaining high value forests in the Ba River basin, enhance their connectivity and viability and help optimize sustainable forest and land and management and biodiversity conservation. This would help mainstream biodiversity conservation practices into provincial and district development planning, as well as the conditions for undertaking interventions at landscape level and promoting replication, ensuring that the future forest and development actions does not compromise biodiversity and ecosystem functions. Collectively, these measures would advance the country towards establishing forest degradation neutrality in the Ba River Basin as well.

Impact Pathway 2: Demonstration of forest restoration and management practices across a range of forest management systems aimed at conserving priority forests, improving sustainable forest management practices and enhancing local livelihoods

- Practical ways of implementing integrated sustainable forest management and conservation interventions will be demonstrated to manage the ecological, social and economic inter-relationships to deliver positive synergies. The project will investigate options for introduction of innovative financial solutions to provide benefits to encourage local communities and ethnic minorities to invest in priority actions that are needed to conserve the high biodiversity and production forests in the Ba River Basin. To facilitate this process, the project will identify and test some promising improved technical solutions to improving forest conservation, enhance community co-management of commune forests, strengthen protected area management and new small enterprises and financial solutions (mainly through PFES) to support the conservation outcomes recognized in outputs supported under Impact Pathway 2.

- In order to address forest degradation and ensure threatened and endemic biodiversity, the project will put at least 10,000 ha of current forest company lands under protected area status to protect biodiversity and enhance connectivity and viability between two existing protected areas in the Central Highlands. Further, it will strengthen the existing protected areas and improve conservation in protection and production forests. This will be achieved by improved methods and tools for forest and biodiversity inventory and support integrated sustainable forest management practices through preparation of annual work plans. Community-based Forest management in the vicinity of protected areas and forest restoration will help enhance the conservation of biodiversity. Improved agricultural practices in the vicinity of the forests and incentives through benefits from payment for forest ecosystem services (PFES) will reduce pressure on forest encroachment, poaching and wildlife killings and build community support. Improved agronomic practices and livelihoods will support around 3,000 local persons that support promotion of biodiversity friendly, sustainable land and forest management and livelihoods. Improved value chains to ensure that multiple products and services will enhance the economic viability of the local people, empower women, build resilience to climate change, define new small-scale business models, streamline the value chain operations and promote nature-based tourism.

- To ensure that potential negative impacts on livelihoods from possible changes in land use practices are minimized, the project will actively engage communities in developing multi-cropping agro-forestry systems and environmental friendly livelihood planning and in identifying and agreeing on activities and suitable land for establishment of these programs, with in-depth Environment and Social oversight, targeted Impact Assessment that will be undertaken within the first year of implementation, based on which a targeted Environment and Social Impacts Management Plan (ESMP) will be prepared and implemented [also see Social and Environmental Screening Procedures (SESP) in Annex 4, Environment and Social Impacts Management Framework (ESMF) and Ethnic Peoples Planning Framework (EMPF in Annex 8b].

Impact Pathway 3: Design and implementation of systems to ensure monitoring and evaluation, knowledge management and gender mainstreaming to facilitate replication

- Implementation of the project will be guided by strong gender mainstreaming and stakeholder engagement. Participatory monitoring and evaluation and knowledge management processes will be used to enable adaptive project management and inform stakeholders at all levels on the nature and extent of impacts intended and achieved. This is particularly important because ensuring the long-term political and economic sustainability will require buy-in and commitment from all stakeholders (including policy makers) to ensure that the impacts on biodiversity and forests are managed with full consideration of the biological, social, and environmental aspects.

- Results and Partnerships

Alignment with GEF Focal Area Strategy

- The project’s multi-sectoral and multi-stakeholder river basin approach to safeguarding forests and biodiversity and maintaining ecosystem services  aligns well with the goal of the GEF-7 Biodiversity Focal Area strategies, namely: BD-1-1: to mainstream biodiversity across sectors as well as landscapes and seascapes through biodiversity mainstreaming in priority sectors and BD-2-7 to address drivers to protect habitats and species and improve financial sustainability, effective management and ecosystem coverage of the global protected area estate.

- More specifically, in terms of GEF program BD-1-1 (to mainstream biodiversity across sectors as well as landscapes and seascapes through biodiversity mainstreaming in priority sectors), the project contributes to this focal area program by: (i) demonstrating how river basins can be sustainably managed in a holistic and integrated manner across the full spectrum of stakeholders (i.e. agriculture/forestry/livestock/tourism), while focusing specifically on safeguarding the natural functioning of terrestrial and aquatic systems as well as community production systems; (ii) improving focus on working with local communities through participatory processes, towards enhancing activities that contribute to enhancing sustainable forest management, improving protected area management effectiveness, biodiversity conservation and new income opportunities. Mainstreaming will be delivered through improved inter-sectoral coordination, sharing of information and improved tools for decision-making, GIS and spatial mapping, technical support and capacity building, demonstration and knowledge sharing and provisions of incentives to change land management practices that degrade biodiversity.

- In terms of the GEF program BD-2-7 (address drivers to protect habitats and species and improve financial sustainability, effective management and ecosystem coverage of the global protected area estate), the project will support the identification and conservation of HCVFs and areas for forest rehabilitation and inform landscape-level conservation priorities. Along with the managers of the Protected Special Use Forests (PAs) and Production Forests this will help ensure that PAs and the production forests objectives and priorities are fully integrated into the surrounding river basin geographies. It will strengthen the integration of biodiversity-friendly practices into SFM and PA plans and practices, enhance opportunities for improving connectivity between PAs and production forests, including potential extension of existing PAs boundaries to include HCVFs in their surroundings. The GEF increment will: (i) provide technical support and training to support the upgrade of SFM plans for production forests; (ii) technical support and investment to enhance management effectiveness of PAs; (iii) technical capacity building and investment to enhance community forest co-management; etc. and (vi) awareness raising and knowledge sharing including with other river basins in the country on sustainable PA and SFM practices.

- In terms of the GEF program LD 1-2 (maintain or improve flow of ecosystem services, including sustainable livelihoods of forest dependent people, through sustainable forest management) the project will use SFM as a tool for maintaining or improving the flow of ecosystem services, including sustainable livelihoods and agricultural and grazing practices as an incentive to change current unsustainable land use practice in support of voluntary LDN targets. The project will also support the integration of SFM and biodiversity considerations into provincial and district land use planning and enhance monitoring capacity and protocols to measure the effectiveness of its integration into these plans and programs.  It will ensure safeguard measures will be demonstrated to protect and rehabilitate production system, as well as address unsustainable land use practices.

Global environmental benefits (GEFTF)

- The project will contribute to safeguarding globally significant biodiversity and its ecosystem goods and services, including the security of community production systems. First and foremost is the fundamental value of piloting a river basin catchment management approach because once mainstreamed it could transform sustainable management of native biodiversity and production systems in a relatively contained system.

- The Ba River Basin catchment, will benefit from holistic, integrated sustainable management of PAs, production forests, community forests and agricultural and livestock management systems to safeguarding the integrity and functioning of ecosystems and community productive systems; and, if successful, this should be sufficient incentive to mainstream such an approach across other river basins in the country. Direct global benefits from targeting the Ba River basin include:

- 56,658 ha of landscape under improved management to benefit biodiversity (excluding PAs) that would include in part, significant areas of natural forests;

- 71,106 ha of terrestrial protected area will be under improved IAS management; and

- 10,000 ha of high value forests converted to PA status

- 17,827 ha of community forests and agricultural lands under improved management to benefit biodiversity

- 500 ha of degrading forests and forest land rehabilitated

- 1,541,810 tCO2 eq-e mitigated over a 20-year period

- The investment will directly benefit an estimated 3,000 community members (50% female, 50% male), distributed across the targeted areas in the Ba River basin through SFM and forest resource use, livelihood and agricultural improvements. This includes: (a) around 1,200 beneficiaries from improved community forest management covering about 3 communes adjacent to boundaries of PAs and/or protection forests who will benefit from sustainable non-forest product collection, forest vegetable collection, mushroom collection, firewood collection, etc. (b) approximately 800 beneficiaries from improved and sustainable management of production lands, such as agricultural and grazing lands, home gardens, organic farming and locally owned industrial plantations (coffee, macadamia, pepper, cashew, etc.) and livestock management through linkages with cooperatives and private sector to provide technical support, extension, market access, new varities, etc. (c) around 500 beneficiaries from improved livelihood opportunities linked to ecotourism product and services, small scale enterprise development and processing (honey, fruit juice extraction, brocade and local crafts, etc.) and (d) around 500 benefiting from improved and efficient PFES monitoring, management and investments linked to conservation actions.  Currently there are 1,541 PFES beneficiaries in the 2 provinces in the BA River Basin (around 1/3 of which are in the project areas). Raising awareness and understanding about SFM, sustainable practices and threats from unsustainable activities will improve community participation.

- Long-term solution: The project is designed to achieve long-term sustainable management of protected areas, production and protection forests, commune managed areas and other significant natural forests in the Ba River basin with explicit consideration of biodiversity conservation and improved management of threats to biodiversity and ecosystem services at site and landscape levels. This will be achieved through broader, landscape-level understanding of ecological processes, connectivity and management of landscape-level threats. To ensure progress towards achieving such long-term solution, the project will introduce the following innovative approaches and practices:

- An integrated area-based framework for planning, managing, compliance, monitoring, enforcement and decision-making;

- Improved site-level planning, regulatory, monitoring and implementation framework for demonstration of integrated planning and management target sites in the river basin;

- Improved site-level conservation-oriented forest management systems for rich ecosystems and community and community-based private sustainable land and forest management, sustainable livelihood investments and small-     scale business ventures; and

- Improved understanding and awareness on basin-wide biodiversity conservation and threat management that encourage support and commitment from policy makers, planners and local communities to conservation.

- Assessment of relevant existing regulations/guidelines for supporting policy frameworks related to implementation of Forestry, Planning and Biodiversity Acts based on on-the-ground experience to provide guidance for policy and implementation change and for potential scaling up.

- The Project Objective is: to conserve forest biodiversity and maintain or improve the flow of ecosystem services through sustainable forest management embedded in a coordinated landscape-level approach across Ba River basin. To achieve this objective, the project is designed to develop and test a holistic and well-integrated multi-sectoral and multi-stakeholder approach to planning and management within targeted locations the Ba River basin. This is underpinned by mechanism(s) that address current limitations in multi-stakeholder and sub-national integrated development planning and coordination between key stakeholders within the river basin, improved forest management and improved local community and indigenous people’s access and control of resource use to generate improved livelihoods, incomes and benefits.

- The GEF project’s added value lies in being able to demonstrate the development of conservation-oriented forest management within the forest estate in the Ba River basin, improved community-based management of forests and forest uses, community small-scale enterprise based sustainable forest resource practices and sustainable livelihoods for local communities in the selected target locations in the river basin. This approach will concurrently strengthen the conservation of biodiversity, enhance conservation practices in forest management, restore and rehabilitate forest areas, enhancing biological connectivity, maintain ecosystem values and ameliorate climate change impacts. An existing spatial and remote sensing data management system will be strengthened for monitoring forest change and generating real-time information on forest loss and threats that will inform decision-making at the provincial, district and forest management unit level. The monitoring will provide a ‘dash-board’ for provincial and district authorities and forest managers to assess forest change and implications on biodiversity significance, identify forest and biodiversity priorities and monitor progress and compliance with established land use plans. This will serve as a means to inform enhancement of national VNFOREST Management Information Systems for the Forestry Sector in Viet Nam (FORMIS). Project lessons will influence development of guidelines on monitoring forest/landscape change and recommendations on integration with national monitoring and inventory systems in the country. It will also help develop capacities and required enabling frameworks through "learning-by-doing" approaches in the selected target landscapes. The project will be able to develop and demonstrate a matrix of best practices for Viet Nam ecosystems and biodiversity conservation as well as review of existing policies, regulations and guidelines for integration for scaling up and replication in other river basins in the country. A series of knowledge management publications and awareness events will support the achievement of these targets.

- The above-objective will be achieved through the following Components, Outcomes, Outputs and activities:

Component 1: Mainstreaming biodiversity and ecosystem services into landscape-level planning, monitoring and enforcement

Total Cost: US$5,252,222; GEF project grant requested: US$552,222; Co-financing: US$4,700,000

Outcome 1: Enhanced enabling framework and systemic tools to monitor biodiversity and ecosystem services and incorporate landscape-level needs into land use and forest planning, monitoring and enforcement

Baseline conditions for this outcome (without GEF project):

- Viet Nam’s Forestry Law approved in 2017 that includes revisions, supplements and added new requirements from the previous law of 2004, is likely to continue with limited guidance on: (i) applying integrated forest management approaches at the river basin level; (ii) developing guidelines and tools to enhance biodiversity outcomes in sectoral, provincial and local development planning; (iii) planning and implementation of conservation-oriented and sustainable forest management in special-use forests, protection and production forests and commune managed areas; and (iv) applying effective monitoring and compliance of existing laws. The importance of biodiversity connectivity (integrating KBA in forest management areas) will remain unclear resulting in biological landscapes being managed less effectively, and threats to biodiversity will likely remain poorly controlled. The circular on Guidelines for Sustainable Forest Management schemes of 2014 and subsequent Circular on Sustainable Forest Management (2018), requiring that forest owners develop SFM plans will continue to be slow at incorporating biodiversity conservation and land management priorities, as well as enforcement mechanisms, on account of the lack of understanding and experience on integration of biodiversity conservation within SFM plans. Without GEF financing, on account of continuance of limited provincial and district level collaboration across sectors and, there is unlikely to be: (i) an effective multi-level integration between provincial and district level institutions and sectors in terms of biodiversity conservation and its integration into local level planning; (ii) an effective management of biodiversity and threatened species in existing protected areas, HCVFs and other categories of conservation and/or resource use areas to maintain important ecosystem services of the Ba river basin; (iii) an effective consultation between different institutional levels and sectors in support of biodiversity conservation within forest management units, and (iv) an effective means to integrate community and ethnic minorities’ needs and priorities into forest management.

- Without the GEF increment, there will also likely continue to be an incomplete institutional framework for coordination on forest law enforcement that would only focus on forest encroachment and offences, without paying sufficient attention to wildlife-related offences such as poaching and illegal wildlife trade. This would continue to be further hampered by the availability of tools and protocols to collect and share data and develop collaborative strategies for enforcement and prosecution of crimes. Due to the current status (as described in the sections above), process of planning, monitoring and enforcement are likely to ignore issues at the landscape level and accordingly, there will likely be a downhill trend of degradation of biological systems in the Ba River basin, which will further increase fragmentation of forests and biological habitats and the local extinction of endemic and endangered species.

Alternative for this outcome (with GEF project):

- Under this Outcome, the GEF increment will support strengthening coordination, governance and regulatory arrangements to facilitate mainstreaming of biodiversity conservation into broader river basin (plus Kon Ha Nung Plateau Biosphere Reserve) level planning, monitoring and enforcement. This will include establishing an institutional coordination framework in the two provinces to facilitate information sharing, engagement, consultation, planning and mobilization on the strategies and decision-making tools. The provincial coordination mechanisms will provide leadership where mandated by various existing laws and agreements or where existing capacities exist to enhance support to provincial forest management entities on the issues relevant to biological landscapes. Guidelines, plans and best practices for landscape-level biodiversity and its mainstreaming in provincial and district development master planning will be applied, along with enhanced systems for monitoring and assessing forest resource change, including a set of minimum standards, to guide responsible practices in the forestry and related development sectors in support of biodiversity conservation outcomes. These plans will build on, and integrate relevant and existing tools, strategies and lessons gained through the baseline work. These tools will also be used to provide a stronger planning, monitoring and enforcement framework to avoid, reduce and mitigate adverse impacts on biodiversity, and emphasis will specifically be placed on maintaining the ecological integrity of the biological landscapes, in particular, in Special Use Forests, Production and protection Forests and Commune Managed Areas. At the same time, the project will strengthen the capacity of respective forest and protected area management institutions at the provincial levels to improve inter-provincial forest management and protection cooperation.

- This Outcome would be achieved through four Outputs, which will contribute to achieving the overall goal of developing frameworks for integrated landscape-based planning, management and enforcement in the Ba River basin to conserve biodiversity and in establishing capacity for planning, implementation and monitoring of conservation outcomes and threats.

Output 1.1: Multi-stakeholder platforms on biodiversity and ecosystem services established at provincial level, supporting multi-sector dialogue on mainstreaming biodiversity into land use and master planning.

- Under this Output, the project will support the mainstreaming of biodiversity and ecosystem services into provincial level planning, monitoring and enforcement. First, the project will support the establishment of multi-stakeholder platforms on mainstreaming biodiversity and ecosystem services into provincial and land use planning and sector operations. The Planning Law of 2017, and its related Decree 37/2019 and Circular 38/2019 lays out the norms and processes for multi-sectoral integrated master planning (including land use, forestry, environmental protection, agricultural production, etc.) at national, sectoral and provincial level that provides the legal entry point for the multi-stakeholder coordination mechanism.  The multi-sectoral provincial platforms will bring together a range of stakeholders across government, industry and community into a common dialogue on the biodiversity assets and landscape-level conservation needs of the Ba River basin and their integration into master planning and land use planning. The project will establish provincial-level platforms in Gia Lai and Phu Yen province. These will provide a participatory mechanism for the identification of landscape-level conservation priorities (see Output 1.2) and a multi-stakeholder platform that can support the implementation of the 2021-2030 provincial master plans (under development and due be adopted by the end of 2020), along with their monitoring, review and revision.

- The following are indicative activities in relation to establishment and functioning of the provincial multi-stakeholder platforms:

- Review the existing coordination arrangements for management of forest and landscapes within the two provinces and propose either relevant improvements to existing coordination platforms, or new coordination arrangements, as appropriate to improve coordination at the landscape levels;

- Development of provincial statutes, as necessary that determine composition, mandates, decision-making, functions, reporting and role and responsibilities and operational management of the provincial coordination committees;

- Establishing inter-provincial stakeholder platform for two provinces, with staffing and meeting budget for its effective functioning;

- Strengthening capacity of Provincial Administration for providing coordination and guidance for support to the coordination platforms;

- Design of basin-wide advocacy strategy including outreach, resource mobilization for financing, and budgets; and

- Defining annual/biannual meeting protocols for dissemination and feedback.

- The tasks of the Provincial coordination committees would include the following:

- Addressing directives, guidelines, manuals, and standards for landscape governance: The Project will support the development of guidelines and standards for basin-wide biodiversity mainstreaming elaboration;

- Coordinating development of regulations and protocols to strengthen provincial landscape planning, including proposing standards, drafting directives, supporting regulation and protocol development and developing plan review and feedback mechanisms

- Proposing specific framework guidelines to mainstream biodiversity conservation into production and protection forests and other key forest-related sectors;

- Overviewing the baseline information repository and facilitating information flows between entities;

- Encouraging provincial institutions (including FMUs) to adopt management practices to mainstream biodiversity conservation through a holistic approach;

- Supporting and facilitating the participatory activities during the elaboration of the land use plans;

- Supporting coordination between landscape governance and planning and other potentially related policies, initiatives, and projects

- Supporting fund raising to implement policies and plans to mainstream biodiversity conservation into forestry and other key sectors;

- Coordinating and supporting the development and implementation of capacity building program for all stakeholders involved in the forest planning and management process;

Output 1.2: Spatially explicit landscape-level biodiversity and HCVF conservation and restoration strategy developed and integrated into provincial and district planning/policies. The strategy will also be used to prioritize on-ground conservation action under Component 2.

- Under Output 1.2, the project will build off the strong government baseline of planning that is currently underway in accordance with the 2017 Planning Law (and its Decree 37/2019 and Circular 38/2019) and support spatially explicit biodiversity and ecosystem services considerations into land use planning. The project will develop a HCVF conservation and restoration strategy, identifying the location of priority conservation areas (including HCVF, e.g.,, following the steps in the 2019 “High Conservation Value (HCV) Screening: Guidance for identifying and prioritizing action for HCVs as part of jurisdictional and landscape approaches”) within the Ba River basin, habitat connectivity and ecosystem services provision, and key threats and vulnerabilities to these assets. The strategy will be developed under the overall direction of the People’s Provincial Committees with inputs from the platforms established under Output 1.1. The strategy will be used to inform the on-ground conservation activities delivered under Component 2 – and further, the project will support the integration of the identified priority conservation areas/assets into provincial master planning and district planning. As the current planning round is being finalized in 2022 (based on Decision 502/2020 issued by Prime Minister approving tasks/contents for developing the Phu Yen provincial master planning and Decision 1015/2020 issued by the Prime Minister for developing the Gia Lai provincial master planning), these spatially explicit inputs will feed into the review of these plans midway through the planning cycle and their readjustment for 2026-2030. Project support will include provision of spatial data layers and maps (see Output 1.3) for the review of progress towards current plans and the development of participatory, spatially explicit land use plans considering biodiversity and ecosystem needs in at least two districts. The improved spatial and remote sensing data that will be generated will serve as an important contribution to these planning processes and district and FMU decision-making. The following are indicative activities:

- Mapping of the Ba River basin forest cover and flagship species (rapid exercise using existing available information with ground validation) that highlight strategic conservation areas, strategic watershed and headwaters protection areas, habitat connectivity and vulnerabilities to threats;

- Based on the above mapping, this would provide the baseline information for the Ba River basin to assist provincial and district level planning for further improvement of forestry and biodiversity management outcomes into social-economic development/provincial master planning at the mid-term review stage of the current provincial masterplans for the two provinces.

- Prepare a Ba River basin forest management and restoration strategy to guide forest protection and restoration efforts in the whole basin as well as to guide sectoral (provincial) and local plan (district) to ensure biodiversity compatible development within the whole basin. This might require undertaking a scoped SESA and ESIA to ensure that there is no displacement of current resource access as well as use of FPIC procedures

- Train FMUs and stakeholders to do HCVF assessment to prepare a guideline for HCVF assessment for all FMUs in Ba River basin. The assessment will highlight all HCVFs assessment steps and to guide future efforts to improve HCVF management, improve connectivity and potential upgrading of existing PAs and/or creation of new PAs within the basin.

- This effort will provide a road map for future conservation management of the Ba River basin and a means to monitor the effectiveness of mainstreaming conservation outcomes into development or provincial master planning in the two provinces (refer Outcome 1.3 in terms of enhancing capacity for monitoring and assessing forest performance/change).The outcome of this performance monitoring will enable discussion with the Provincial Authorities and Policy makers on progress in implementation versus what was planned that would then enable policy recommendations for enhancing and/or improving planning and mainstreaming of biodiversity and sustainable forest management outcomes in provincial master planning at mid-term review stage.

Output 1.3: Enhanced systems for monitoring and assessing forest resource changes (i.e., deforestation and plantation/restoration) and biodiversity, incorporating remote sensing techniques, demonstrated at landscape level, with lessons provided to support national-level upscaling.

- Improved use of spatial and remote sensing data will be an important contribution to these planning processes and district and FMU decision-making. The project will enhance existing systems for monitoring forest change and generating alerts related to forest loss by building capacity for the use of high-resolution remote sensing data. There is now a range of remote sensing and spatial data mapping platforms (e.g., UN Biodiversity Lab, Planet-NICFI, Terra-i, Global Forest Watch, USGS, ESA) freely available, however these are not yet widely used to inform decision-making at provincial, district and forest management unit level. Increasing access to such information and building capacity to use it was noted as a key need of forest managers during PPG consultations. In particular, Forest Management Boards are entrusted under Circular 28/2018 (within the ambit of the Forestry Law of 2017) to monitor the effectiveness of implementation of their SFM plans (including forest changes) but lack capacity, experiences and guidelines for monitoring forest resource change, while Circular 33/2018 regulates measures for inventory and monitoring forest changes. The project will use existing freely-accessible platforms to access and analyze high-resolution multi-time/near real-time remote sensing images to generate regular deforestation and forest degradation warnings for districts and forest managers, providing more dynamic information on vegetation change as a key driver of biodiversity loss. This will be analyzed with other existing spatial data on biodiversity and ecosystem services (e.g., datasets on protected area/KBA coverage, threatened species richness, key usage areas for water security, carbon stores, carbon sequestration potential etc. available in UN Biodiversity Lab, Global Forest Watch, and datasets on forest resources from FORMIS system) to identify risks and threats to forest resource and biodiversity assets of the Ba River basin.

- An enhanced system with combination of both existing data and information on forest resources (derived from VNFOREST Management Information System for the Forestry Sector in Viet Nam (FORMIS)) and available high-resolution multi-time/near real-time remote sensing data (accessible freely from available platforms) will provide a ‘dashboard’ for provincial and district authorities and forest managers to assess forest change and implications on biodiversity significance, identify forest and biodiversity priorities and monitor progress and compliance with established land use plans. The project will provide training and equipment for provincial and district stakeholders involved in forest monitoring (e.g., DARDs, district administrations, forest/PA rangers, forest companies, communities with forest land allocations) to build their spatial literacy and capacity to use high-resolution spatial data and maps to support decision-making. The training will be supported by preparation of curriculum and training materials in collaboration with the Vietnam National University of Forestry (VNUF) (also refered to the  Forestry University of Vietnam) which is affliated to MARD as part of the intent to institutionalize the training. VNUF provides training in forest GIS mapping, SFM and forest development planning, sustainable forest resource use, climate change adaptation, forest survey and monitoring, PFES planning and monitoring, integration of forest management and biodiversity conservation in socio-economic development planning as well as support for development of national standards and technical regulations and technical norms for AFM, forest ecology, etc. The University has a campus in the Central Highlands that is within the Ba River basin. The real-time monitoring demonstration at provincial level will be used to inform enhancements to the national VNFOREST Management Information System for the Forestry Sector in Viet Nam (FORMIS) system. Project lessons will be used to develop guidelines on monitoring forest/landscape change and recommendations on integration with national monitoring and inventory systems for consideration by MARD.

- The following are indicative activities:

- Review existing spatial data mapping platforms (e.g., UN Bio Lab, Planet-NICFI, USGS, ESA, UMD-GLAD, Global Forest Watch) or cloud platforms (e.g., Google Earth Engine (GEE) and FAO-SEPAL) which are able to provide spatial information and data including free high-resolution satellite imagery data for planning process and decision-making at provincial, district and FMUs scales, especially in forest resource monitoring and assessment (e.g. deforestation, a/reforestation…), and biodiversity;

- Review of existing biodiversity, land degradation, invasive species and threat monitoring methods, information use and capacities across the relevant entities to assess usefulness of data and information collection methods. The review will also address constraints and weaknesses in data collection, sharing and management and opportunities for filling gaps in baseline information and measures for improving the quality of data collection. The review will also seek to identify means for verification, reporting and analysis of information to enhance protocols for data management and protection of sensitive biological information (threats, changes and forest condition);

- Based on the review above, identify suitable existing freely accessible available platforms to access high-resolution multi-time/near real-time remote sensing images to generate regular deforestation and forest degradation warnings for districts and forest managers, providing more dynamic information on vegetation change as a key driver of biodiversity loss (e.g., UN Bio Lab, Planet-NICFI, USGS, ESA, Global Forest Watch, GEE, FAO-SEPAL);

- Pilot the enhanced system with support of existing information/data (FORMIS data) and high-resolution multi-time/near real-time satellite images (accessible freely from available platforms) for improving the capacity in monitoring and assessing the forest resource change and biodiversity at key project sites including one Protection Forest Management Board in Gia Lai province and Krong Trai nature reserve in Phu Yen;

- Provide training and capacity-building for staff of relevant agencies at provincial, district, commune and forest and protected area management levels in effective data collection, verification, monitoring and management, and benefits of conservation- planning with support of the enhanced systems;

- Provide supporting equipment (e.g.GPS, etc.) for FMUs under the Project’s sites to monitor and assess changes in forest resources and biodiversity; and

- Based on experiences in the pilot phase at the Project’s sites, provide recommendations and develop and test technical guidelines on monitoring forest/landscape change at the project areas for integration with national monitoring and inventory systems (FORMIS). VNForest will, based on demonstration in Gia Lai and Phu Yen provinces formalize and issue the monitoring guidelines/training manual for dissemination and application through the country to support effective implementation of Circulars 28/2018 and 33/2018.

Output 1.4: Enhanced coordination on wildlife and forest monitoring and enforcement at landscape levels, through broadening the inter-provincial forest management and protection cooperation regulation MOU to cover wildlife offences alongside forest offences.

- Output 1.4 will support enhanced coordination on wildlife and forest enforcement at landscape level with particular attention on improving information exchange and coordination on wildlife-related offences. At inter-provincial level, the project will provide technical support to broaden the existing forest management and protection cooperation regulation Memorandum of Understanding (MOU) between Phu Yen and Gia Lai PPCs/Provincial Forest Protection Departments to integrate biodiversity conservation and landscape-scale considerations into their existing coordination meetings and MOU, which currently only covers illegal logging and forest encroachment issues. The cooperation will also be extended to provinces that share neighboring forest areas (e.g.,, between Dak Lak, Gia Lai and Quang Ngai/Kon Tum) to enhance cross-provincial coordination on wildlife snaring, poaching and trafficking offences in law enforcement information exchange and operations.

- The GEF increment will support the following key indicative activities:

- Review of monitoring, surveillance and enforcement systems (including in particular relating to Decree 01/2019 regulating forest rangers and specialized forest protection force)  to assess quality of monitoring and performance of the specialized forest force) and capacities at the Provincial level

- Development of cross-sector plans, actions, protocols, procedures and baselines underlining roles and responsibilities of key provincial entities to improve joint monitoring, surveillance and enforcement ensuring the landscape level;

- Development and/or update of provincial level regulations that facilitate monitoring and enforcement based of assessment of performance as defined under 1.4.1 in relation to Decree 01/2019. This assessment will provide recommendations for improved training, empowerment of forest rangers, capacity and enhanced support required to improve quality and performance of monitoring that could be applied nationwide by Forest Protection and Special Use Forest Management Boards

- Training forest managers, forest management boards and forest communities in monitoring, surveillance and enforcement, in the selected demonstration landscapes will be undertaken in collaboration with VNUF;

- Development of appropriate protocols/guidelines and enforceable standards for biodiversity and/or SFM/SLM for landscape conservation and restoration, monitoring and enforcement.

- Development and agreement on inter-provincial cooperation to cover wildlife offences alongside forest offences, initially between Gia Lai and Phu Yen provinces, and based on this success, its later extension to neighboring provinces such as Quang Ngai and Kon Tum

- Development of protocols for inter-provincial coordination, including sharing information, joint patrolling and monitoring, training and awareness creation

Component 2. Conserving globally significant biodiversity and ecosystem services in forested landscapes of Ba River basin

Total Cost: US$10,956,092; GEF project grant requested: US$1,156,092; Co-financing: US$9,800,000

Outcome 2: Forests and biodiversity are restored, and protected areas strengthened at landscape scale, through coordinated management across Forest Management Units and Community-managed areas

Baseline conditions for this outcome (without GEF project):

- There is an extensive area of around 600,000 hectares of forests within the Ba River basin, most of which are in the ecologically important Central Highlands region and mostly constitute high conservation value forest areas. Within the river basin, there is a large extent of forests outside of the traditional protected areas that will likely continue to be managed with limited efforts at enhancing biodiversity conservation outcomes and improving connectivity across the landscape. Consequently, protected areas, including KBAs will continue to be managed as “islands” and threats from surrounding landscapes will likely continue to increase, undermining the conservation values of these KBAs and increase fragmentation of the corridor habitats. Although the potential role of ethnic minorities and local communities in directly supporting biodiversity conservation has been recognized, these areas would continue to be managed independent of their needs and aspirations, thus losing an opportunity for integrating traditional knowledge and support for conservation of the large forest estate. In addition, the immense potential for production systems in forestry and agriculture to incorporate biodiversity-friendly and targets relating to land management may likely not be recognized. Designation of new other protected areas and enhancement of community management of forest resources might come too late after heavy degradation of the habitats and there will be insufficient resources and capacity to properly manage the areas even after establishment. KBAs would continue to be inadequately managed to achieve no net loss to biodiversity and human well-being.

- In addition, sectoral and geo-political approaches that prevail in terms of land-use decision-making in forest and watershed planning will likely continue to not incorporate KBAs and ecosystem, landscape considerations nor community forest management approaches. Provincial and district policies and planning systems are likely to continue to pay less attention to support forestland use optimization to sustain resource resilience and facilitate operationalization of the KBAs and ecosystem services considerations. Enforcement capacities to ensure compliance with ecological standards in forest management and reduction of high levels of trespassing in use of forests will remain weak.

Alternative for this outcome (with GEF project):

- Under the GEF increment, the strategy is to focus on the following: (i) establishing connectivity between HCVFs within and outside protected areas to bridge existing conservation gaps within the landscape sites and reducing fragmentation through creation of new protected areas or restoration of degraded forests and riparian areas; (ii) improving management effectiveness of existing protected areas to reduce threats and enhance conservation outcomes; (iii) enhanced mainstreaming of biodiversity within production and protection forests and support for sustainable forest management practices so as to contribute towards conservation of endemic and threatened species and enhanced ecosystem services; (iv) Improved co-management of commune managed forests and biodiversity-friendly livelihood development in buffer zones of protected areas to serve as stepping stones for species conservation within the landscapes; and (v) promotion of financial invectives, including more effective use of PFES approaches to strengthen local support for conservation in forest patches within the landscape as a means for conservation and restoration of species, improving connectivity and enhancing forest-based revenues.

- On the basis of the above-defined strategy, the GEF project will support the improved management of the existing network of forested areas within the Ba river basin through the following actions: (i) improve management effectiveness of 71,106 hectares within 3 existing protected areas (Kon Ka Kinh National Park, Kon Chu Rang Nature Reserve and Krong Thai Nature Reserve), (ii) inclusion of around 10,000 hectares of high conservation value forests that is currently managed by the government owned Dak Rong and Tram Lap Forest Companies in the Central Highland region within two existing protected areas (Kon Ka Kinh National Park and Kon Chu Rang Nature Reserve) to enhance biological connectivity; (iii) improving biodiversity-friendly practices in 56,658 hectares of existing production and protection forest landscapes; and (iv) improving sustainable management of 17,827 hectares of agricultural and community forest lands. These actions will be conducted in accordance with safeguard management measures in accordance to ESS and defined in Table 4 of the ESMF. The project will provide an opportunity to monitor progress in implementation of METT (Management Effectiveness Tracking Tool) in order to evaluate the management effectiveness and efficiency of existing PAs through the coming years. Support will also be provided for capacity building and training of PA and forest staff, community and ethnic minority groups and other relevant personnel to support effective PA and forest management and operationalization, including for law enforcement. The training will be complemented with the development of curriculum and training materials with the support of VNUF so a measure to ensure the institutionalization of the training for replication in other provinces as well. Existing KBAs will form the core of the landscape areas and will include land within the KBAs that need to be rehabilitated and sustainably managed to enhance connectivity and improve conservation outcomes. The project will also train and equip forest and wildlife managers (PA and forest staff and community organizations) for implementing monitoring and enforcement systems to reduce violations and wildlife crime. Overall, the aim of this cross-training and co-involvement of PA and forest staff and community organizations/local communities, largely through protected area, forest management and community-based management agreements will improve efforts not only within PAs, but also coordination and integration of these efforts across the larger landscape.

- The project will support the development of integrated forest management approaches in the Ba River basin, the mainstreaming of biodiversity conservation aspects in forest management and provincial and district level planning frameworks, through extensive consultation and in cooperation with local organizations. These plans will, inter alia: (a) identify high biodiversity areas within protection and production forests to receive higher conservation/protection status; (b) identify gaps and measures to enhance management effectiveness of PAs; and (c) prescribe appropriate biodiversity-friendly forest management practices, and commune managed areas thus avoiding, reducing and mitigating the impacts to biodiversity. It is anticipated that, through the mainstreaming of landscape principles, SLM and SFM strategies will be employed to achieve some level of LDN within the landscape areas

- This outcome will be achieved through the following seven outputs, which will contribute to achieving the overall goal of expansion and improved management of biological landscapes in the Ba River basin.

Output 2.1: Participatory monitoring and inventory on HCVF/biodiversity assets operationalized with training conducted for PA and forest managers and communities living in and around high-biodiversity areas.

- Under Output 2.1, the GEF increment will be used to establish participatory biodiversity and forest resource monitoring and inventory, including HCVF assessment, to better understand the assets in each individual FMU and their status and condition. This will include provision of training and equipment for PA and forest managers and for communities living in and around high-biodiversity areas, helping build engagement in sustainable forest management. Monitoring results will be used to guide the identification of FMUs’ forest resource and biodiversity conservation priorities at site level including HCVF extent, which will be particularly important to guide the protection and enhanced management of HCVF in the proposed PA in Dak Rong and Tram Lap FMUs. The following are indicative activities:

- Review and assess the current status of monitoring and inventory of forest and biodiversity resources at local and central levels, especially selected forest management units including Kon Ka Kinh national park, Kon Chu Rang and Krong Trai nature reserves, state forest companies of Tram Lap, Dak Rong and Kong Chieng, and Son Hoa and Chu Mo protection forest management boards.

- Identify and select an effective approach and methodology in participatory forest and biodiversity resources monitoring and inventory, and apply the method for FMUs, especially in the HCVF areas (Tram Lap and Dak Rong forest companies).

- Provide technical support to FMUs to conduct resource and biodiversity monitoring and inventory in engagement with their sustainable forest management plans.

- Develop guidelines and standards for information collection, indicators, and templates on forest and biodiversity assets at local scale, focusing on forest tree species and density, forest status and forest quality, forest biomass assessment, and wildlife species. Based on lessons learned at local scale, develop recommendations for application of forest, biodiversity resource monitoring and inventory at a larger scale.

- Build the capacity for relevant agencies and staffs at local levels and FMUs (PA and forest managers) in design and implementation of forest and biodiversity assets monitoring and inventory activity in their institutions through training activity that will be supported by VNUF.

Output 2.2: Landscape and site-level biodiversity priorities and actions identified and integrated into sustainable forest management plans, annual work plans and operations. This will include technical support, extension and demonstration of priority measures including threatened species conservation and habitat management, biodiversity threat reduction, assisted natural regeneration/restoration of degraded habitats.

- As part of the GEF increment, this Output will support the integration of these biodiversity assets and conservation priorities identified into the respective SFM plans and associated annual work plans of the Forest and PA Management Boards in the Ba River basin. SFM planning is a new requirement of the Government of Viet Nam and for Special Use Forests, these plans will serve as the management plan for integration of sustainable forest management practices and will be critically important to guide in the protection of species, habitat and biodiversity conservation values. Initial SFM plans are being developed by consultancy agencies with little ownership of the forest managers, however due to low capacity and awareness of biodiversity conservation among forest managers (including in PAs), these initial plans are likely to not fully consider biodiversity conservation, or effectively integrate broader conservation objectives in a practical and technically sound manner into the SFM work plans for on-ground investment, especially for PFMBs and State Forestry Companies. GEF funds will be used to help close this gap. The project will provide technical support and extension to build biodiversity conservation capacity and commitments. PA/forest managers will be provided with technical assistance to identify biodiversity conservation priorities and develop appropriate conservation actions for SFM plans and their annual work plans to protect these values. Best practices will be demonstrated, and extension services will help facilitate the use and adoption of technically sound biodiversity conservation practices (e.g.,, threatened species conservation, habitat management and enrichment, IAS management, use of spatial set-asides, management of edge effects, regeneration/restoration) into forest management/PA management practices). Project lessons and improved capacity will help support enhanced consideration of biodiversity conservation within the subsequent review and update of SFM plans for 2026-2030 and a participatory review of the implementation of 2021-2025 SFM plans (combined with monitoring results under Output 2.1) will be completed in the project FMUs to help inform this process and continue to build PA and forest manager capacity and engagement in biodiversity conservation.

- This Output will be achieved through the following actions:

- Conducting internal dialogue and planning among DARD, DONRE, PA and Forest management boards, forest companies, district and commune peoples’ committees and other stakeholders as preliminary input to support consensus building (recognizing HCV criteria as additional parameters for PA and forest and commune management as key drivers for landscape conservation);

- Assembling existing information, stocktaking and preparation of target landscape level maps reflecting the various forest and land uses and management regimes under different sectors (forestry, conservation, agriculture, etc.) that influence and impact biodiversity. This will build on the work done under Outputs 1.2 and 1.3)

- Conduct inter-disciplinary discussion to assemble, review available baseline information on forest management, biodiversity conservation, review proposed updates of KBAs and proposed target landscape components and prioritize information gaps to be addressed (the content of this discussion can be combined with dialogues from Output 1.2 if possible);

- Organization of, and support to the provincial multi-sectoral coordination committees through co-facilitation of the concerned provincial institutions (the content of this discussion can be combined with dialogues from Output 1.2 if possible);

- In-depth Assessment of biological, socio-economic, environmental and institutional aspects to prioritize actions for SFM plans and defining governance arrangements for ecologically sound forest and land use and reaching agreements on standards for monitoring (based on guidance from Output 1.4);

- Establish and consolidate management responsibilities (PA management boards, forest management boards, forest companies and commune peoples’ committees in support of landscape management; and

- Implementation of priority management actions, followed by mid-term and end of project change detection study to ascertain impacts of landscape interventions on biodiversity conservation, SFM and threat reduction.

- Technical support to forest managers in developing annual work plans to make sure biodiversity priorities and actions are mainstreaming into SFM plans, especially for Production and Protection Management Boards (FPMBs) FMBs and State Forestry Companies whereas biodiversity is not prioritized.

- Technical support to forest managers in FPMBs and State Forestry Companies to identify biodiversity conservation priorities and develop appropriate conservation actions in the annual work plans to protect these values.

- Provide training on biodiversity survey techniques and key/flagship species monitoring for PA’s conservation staff  in collaboration with VNUF to enable its replication elsewhere in the country.

Output 2.3: Improving PA management, including operationalization of the Special Use Forest proposed for establishment in areas under Tram Lap and Dak Rong State-owned forestry companies

- Complementary to Output 2.2, this Output will help strengthen the management of target PAs in the project landscape, responding to capacity needs identified by PA managers and responding to challenges of illegal poaching, logging and encroachment faced by the PAs and FMUs. In collaboration with VNUF, GEF funds will provide training, equipment and operational support to PA managers to strengthen patrolling and surveillance, complete boundary identification/realignment (e.g.,, realignment of boundaries to exclude low biodiversity areas where communities are living and replace them with higher-biodiversity neighboring areas) through a participatory process with communities and enhance community and stakeholder engagement and co-management. These activities will include capacity development of conservation area of Dak Rong and Tram Lap State Forestry Companies. These areas contain significant amounts of HCVF that are at risk of degradation, and increasing surveillance of these areas is an immediate priority, along with building capacity of forest rangers for biodiversity conservation and PA management.

- In terms of the proposed new conservation and/or its integration into the existing Kon Ka Kinh national park and/or Kon Chu Rang nature reserve, this output will support survey and management planning for the area. The following are indicative activities under this output:

- Undertake the development of a proposal as regulated by Viet Nam for inclusion the forest area of Dak Rong and Tram Lam FMUs into existing protected areas to improve connectivity.

- Facilitate the approval process for the addition of areas into existing protected areas according to the regulation in the Forestry Law (2017) with proper consultation process with local communities and stakeholders.

- Prepare operational plan for the extended PAs including training to build capacity for the new conservation area and engagement plan for local community in forest protection and biodiversity monitoring.

- Undertake assessment to identify high risk poaching map for the three PAs to better target and prioritize patrol areas for various types of threats

- Support strengthening SMART patrols incorporating local communities in the 3 PAs, including training for staff and communities and set up data and reporting systems

- Improve staff capacities to analyze, manage and monitor information from SMART patrols, so that it can be better used by Senior management for decision-making and effectively targeting the threats

Output 2.4: Enhanced support for participatory community-based forest management

- As a means to enhance community-based conservation of forest biodiversity, which is critical to achieve mutually      beneficial outcomes for conservation and local livelihoods, this Output will provide technical support for the process of ensuring co-management of commune forests by local communities. In at least two areas where forest lands are managed by local communities, the project will implement a participatory process to develop the initial SFM plan for these community forests so that community views and priorities for forest management are central to the process, and to build awareness and capacity in integrating biodiversity conservation into community SFM plans. A gender mainstreaming approach will be applied to ensure women’s participation and equal flow of benefits to women. The project aims to pilot a co-management model on forest and biodiversity that can be up scaled across the Ba River basin. GEF funds will also support livelihood diversification in community-managed areas and PA buffer zones, including development of NTFP, agro-forestry and forest income generation models.

- Criteria for selection of priority communities for project’s livelihood support (for Outputs 2.4 and 2.5) are intended to ensure that there is a direct link between threats to forests for which purpose the selection of communes will be based, so as: (i) communes located within neighboring buffer zones of the national parks/nature reserves; (ii) communes located in corridors between core areas and within biodiversity rich areas or areas with recognized potential for meaningful ecosystem restoration; or (iii) communes within identified forest rehabilitation areas or are allocated forest area for community forest management. Within the selected communes, selected households are identified on the basis of the following criteria: (i) households that are greatly dependent on forest resources within buffer zones of the national parks/nature reserves and forest restoration areas for their livelihood or that conduct such actions which directly threaten forest biodiversity; (ii) households that are willing to participate in community forest management and related sustainable use of forest resources, (iii) households that are categorized as ethnic minorities or disadvantaged groups that are typically forest dependent; or (iv) households that are already organized into interest groups, production groups or cooperatives. In selection of communes and communities for forest co-management consultations will be undertaken with ethnic minorities and other communities following application of FPIC procedures to ensure that such decisions are made in the best interests of these communities, themselves. Forest-based livelihood opportunities will be centered around the co-management principles for on creation value-chains. Project interventions would focus on: (i) providing technical training for communities to improve product quality,  productivity and sustainability; (ii) providing technical support to ensure community capacity to recognize and manage their production within sustainable limits; (iii) supporting environmentally friendly harvest techniques so as to not compromise on the environment and biodiversity; and (iv) fostering partnerships between producer groups and partners from the private sector for product development and marketing. In terms of potential for ecotourism, this output would help establish linkages between community groups and the tourism market, including: (i) identifying potential groups (including women groups) and interested tourism agents to facilitate access, (ii) Identifing a suite of ecotourism activities that are non-destructive, promotes conservation outcomes and results; (iii) developing tourism and livelihood products associated with production process or traditional craft demonstration models to help them understand the real value of the handicraft products, (iv) supporting small-scale tourism activities, including homestays, to the extent there is community interest; (v) ensuring that community actions towards conservation are linked to promotion of livelihood and ecotourism products and services;  and (vi) connecting production groups with tourism activities in nearby locations to increase their chances of selling their products to tourists. In development ecotourism approaches, these will be subjected to SES and FPIC procedures as defined in table 4 of ESMF.

- This Output will be achieved through the following indicative actions:

- Conduct a review to identify capacity need for PA, forest management unit, and local community on biodiversity conservation, sustainable forest management and capacity and skills need to engage local community in forest management more effectively, in particular to address requirements defined through Decrees 156/2018 and 83/2020.

- Implement training for PA and FMU’s managers and staff on community-driven sustainable co-management forest operations.

- To help support a participatory planning process for co-management of forest/forest land by village communities and develop the initial sustainable forest management (SFM) plan for community forest management with a gender consideration to ensure women’s participation and equal flow of benefits to women;

- Access technical feasibility of proposed forest-based small community-based enterprise development towards value chain approaches

- Prepare a handbook and implement training on community forest planning and management of resources, wildlife monitoring and sustainable nature resources management for local community

- Establish links between community enterprises and private sector business to provide technical support, extension and training to communities to develop value-addition products and marketing

- Assess environmental and social risks associated with the proposed value chains and propose risk management and mitigation measures as well as monitoring the benefits (through a set of measurable indiactors of conservation and livelihood benefits);

- Support efforts to create sustainable financial mechanisms at community level, including developing specific livelihood demonstration models, operation of village revolving funds and/or access to low interest credit facilities

Output 2.5: Livelihoods development for women, including training in forest value chains and entrepreneurship, and establishment of women’s groups in forest-dependent communities.

- Women in the buffer zone’s communes of the national parks/nature reserves, especially ethnic minority women, are mainly engaged in agricultural production. They collect a variety of forest products, such as firewood, bamboo shoots, medicinal plants, and vegetables that they are likely to devote directly to family use, although they also sell several forest products to earn money to meet basic household needs. In addition, Kinh women participate in national and provincial entrepreneurship and start up initiatives, and small businesses under "Support for women’s start-up in 2017-2025" program that is aimed to raise women's awareness on government’s policies and laws on entrepreneurship, promoting the realization of business ideas. This program provides a “Women's Start-up Fund” managed by women to support innovative ideas in production and business (e.g.,, a grant of approximately USD 1,400 -2,400 for an innovative and feasible idea of production and business) at the commune level. In general, supporting women to enhance economic opportunities and start a business in particular has become an important strategy in economic development and job creation for women in Viet Nam, especially in rural areas. Development of one start-up demonstration model of women entrepreneur in each targeted commune which can be linked to the One Commune One Product (OCOP) initiative can be a good option, in which start-up initiatives could be small and medium size businesses, community tourism, re-organization of existing production models shifting from household production in the form of self-sufficiency to large-scale commercial production models. To complement these activities, the project can seek to assess challenges and opportunities of ethnic minority women entrepreneurship and propose strategies, mechanisms, and measures to strengthen start-up initiatives. Other livelihood developments for women include the establishment of production groups, cooperatives, or interest groups managed by women; providing support to access affordable inputs, credit, technical trainings, extension services, market information, and connecting these groups with traders, businessmen, cooperatives, and enterprises in the private sector to help them improve market access. In addition, trade fairs at district level to introduce and exchange agricultural products, vocational trainings for women linked with recruitment units and labor market with particular focus on non-farm careers, trainings for women groups on advanced production techniques, forest-based value chains, start-up and business development, business plan, marketing, financial management, fundamental accounting; and roadshows/forums to disseminate successful models of business, production and entrepreneurship owned or managed by women should be organized in order to expand income generating activities for women and increase women's confidence and motivation in participating in livelihood development activities as well.

- Special attention will be focused under Output 2.5 on supporting livelihoods improvement for women. The selection of communes and households for livelihood investments will follow the same criteria as enunciated in Output 2.4. GEF funds will support the establishment of hand strengthening of women’s groups in forest-dependent communities, targeted training on FMU management, forest-based value chains and entrepreneurship, and invest in targeted livelihood models that offer specific opportunities for women’s empowerment and benefits. At the community level, the project will help develop community capacity for sustainable management and use of forest resources, especially in commune managed areas, thereby also increasing local women’s adaptive capacity. Training for sustainable livelihoods will incorporate a gender perspective, to ensure that the needs of women, who frequently form a marginalized group in livelihood areas such as agriculture, farm animal raising, firewood collection, non-timber forest resource collection, organic agriculture, or eco-tourism are considered and that implementation through the project could promote gender equality. During project implementation, capacity building in activity planning will be specifically focused on ensuring that women are actively engaged in all aspects of the pilot activities, and efforts will be made to consult and engage local Women’s Union to improve sources of income for women and enhance their engagement in these pilot programs. Livelihood activities that will specifically target women would be assessed and technical, extension support, training and financial support provided for their implementation. In particular, specific livelihood targeted at women, including ethnic minorities, might include crop-livestock systems, small-scale cash crops, small enterprises connected with sustainable use and forest-based value chains centered around NTFPs, small-scale coffee, root crops, wet rice in mixed cropping systems, fishponds, small-scale ecotourism including trekking, bird watching, homestays, etc. Other options include brocade weaving, sewing, wild honey, agricultural tourism, lotus cultivation, etc.

- This Output will be achieved through the following actions:

- To conduct of a commune specific and detailed gender analysis (that builds on the gender analysis related to livelihoods that was conducted at PPG stage and referenced in Annex 18 of UNDP Project Document),  the intent being to specifically understand the gender role, access to and control of resources, gender division of labor, poverty, power relations and legal rights, barriers and obstacles of women's participation in livelihood activities, existing national and local policies to support livelihood development for women, including ethnic minority women;

- Assess technical, economic, social, and environmental feasibility of livelihoods appropriate for women (ensuring consideration of SES compliance as defined in table 4 of ESMF) in order to determine livelihood interventions for women (e.g. organic agriculture, animal husbandry, community tourism, small business, traditional handicraft, start-up, establishment of production groups, cooperatives, or establishment of interest groups managed by women and provision of technical, financial and market supports to them);

- Establish mechanisms for livelihood support for women, including developing specific livelihood demonstration models;

- To provide technical support, e.g., training on cultivation/planting techniques, seeds, seedlings, fattening, feeding, caring, harvest, and postharvest;

- To assess risks associated with livelihood interventions and proposing risk management and mitigation measures;

- To replicate successful livelihood models managed by women in order to increase women's confidence and motivation in participating in livelihood development activities.

Output 2.6: Landscape connectivity for wildlife improved through restoration using indigenous species over 500 ha of degraded natural forests.

- Landscape connectivity will be enhanced through restoration of at least 500 ha of degraded natural forests to enhance movement of significant wildlife across the landscape and reduce fragmentation in HCVF. Under Output 2.6, support will include identification of restoration areas (informed by the landscape-scale biodiversity and HCVF restoration strategy developed under Output 1.2) including consultation and validation with local communities, investment in technically sound restoration processes and the development of technical guidelines on restoration techniques to support replication and broader uptake across the Ba River basin. The area targeted is likely to include the area between Kon Ka Kinh NP and Kon Chu Rang NR in the north of the landscape, given its high biodiversity significance and KBAs.

- This Output will be achieved through the following indicative actions:

- Identification and survey of locations for forest restoration to improve connectivity (following mapping exercise in Output 2.2) ensuring compliance with safeguards (refer Table 4 of ESMF)

- Provision of technical support to Forest Management Boards and Forest Companies, as relevant for development of forest restoration and protection plans for the identified sites, and defining working restoration methodologies (including selection of native species, soil and water conservation, soil fertility improvements, planting and maintenance techniques, etc.) based on national and regional best practices;

- Investigation of potential for collaboration in forest restoration through complementary provincial initiatives, such as Reduced Emissions from Deforestation and Forest Degradation (REDD+), Payment for Forest Environmental Services (PFES), other donors’ programs, etc.;

- Provide technical support to ensure that proposed forest restoration designs/programs better integrate sustainable forest management and benefit sharing guidelines and practices;

- Community consultations and participation in forest restoration, including for the establishment and maintenance of a suitable mix of protection and other community-based conservation and maintenance measures such as social fencing to reduce grazing, wood collection and sustainable NTFP extraction; fire control, etc.;

- Support for implementation of restoration and protection plans in line with SES compliance and promoting soil moisture improvements, weed clearance, water harvest and erosion control, seeding and planting, protection and maintenance;

- Monitoring and evaluation of forest restoration progress and impacts, including assessment of biological, ecological and community benefits; and

- Preparation of a manual that describes restoration approaches for different degraded forest types.

Output 2.7: Existing financial incentive mechanisms, including PFES, are utilized more effectively, including increased resource mobilization connected to performance and better targeted disbursement mechanisms, to support sustainable forest use and biodiversity and HCVF conservation.

- As part of the effort to enhance community and stakeholder support for sustainable forest use and biodiversity and HCVF conservation within the Ba River basin landscapes, Output 2.7 will support the enhanced use of existing financial incentive mechanisms, including PFES, aimed at increasing resource mobilization for forest development and management, biodiversity conservation and establishing closer links between payments and conservation results. Decree 99/2010 provides the national mandate/policy for requiring users of forest environmental services to make payments to suppliers of these services and over 20 legal instruments, such as Decrees, Prime Minister Decisions and Circulars have been subsequently issued in support of PFES. Considering financial resources mobilization for forestry and biodiversity conservation activities, PFES has played an important role in forest conservation. In the period of 2015-2020, PFES contributed approximately USD 11.5 million in financial resource mobilization within Ba River basin. PFES revenue is mainly from hydroelectric producers (99.7%) that pays for service for land protection, erosion or sedimentation control in lake beds/riverbeds/stream beds, regulating and maintaining water resources used for hydroelectric production. A small percentage (0.3%) comes from regulating and maintaining water resources for clean water production. PFES revenues are channeled effectively for different purposes, for example, activities of forest development, protection and management, biodiversity conservation as well as livelihood development of local forest-dependent communities. This output will include raising awareness with forest owners on the incentives available and provide technical support to improve the existing PFES framework through enhanced performance monitoring and to ensure better target payments to improvements in environmental and ecological conditions. In addition, given the time-consuming process and risks associated with cash transfers for PFES, the intent is to pilot PFES payments in Gia Lai and Phu Yen through e-payments which are safer, quicker and more transparent than cash transfers.

- This Output will be achieved through the following indicative actions:

- Review of existing financial incentive mechanisms for mobilization of resources to strengthen conservation for forest and its sustainable use. Financial resources can be derived from: (i) state budgets; (ii) investment, contribution, assistance or sponsorship by domestic and international entities; (iii) revenue from use of forest products, forest and forest land lease; (iv) revenue from payment for replacement afforestation when forests are repurposed; (v) revenue from provision and lease of forest environmental services; (vi) credit capital by domestic and international credit institutions, and (vii) other financial resources prescribed in regulations of law.

- In terms of PFES, particularly where it is currently being applied, evaluate the options for further strengthening at the provincial, district and commune levels in terms of: (i) compliance with policy for PFES in the provinces; (ii) functioning of Fund for Forest Protection and Development; (iii) Status of provincial plans and clarity in terms of roles and responsibilities for PFES implementation; (iv) provincial capacity for management and monitoring of PFES; (v) extension support for formation and operation of PFES groups; (vi) level of awareness at commune and community level; (vi) level of oversight and supervision of procedures at commune level; (viii) monitoring and evaluation; (ix) status of PFES groups; (x) PFES fund management and distribution; and (xi) livelihood development based on PFES funds more clearly linked to conservation outcomes or mutual community conservation commitments etc.

- Based on evaluation of PFES above, provide technical support, training, extension and awareness creation to further strengthen PFES operations, including in particular for; (i) improvement of forest inventory and data on forest area and quality; (ii) improving technical and financial capacity for PFES implementation; (iii) Improved coordination among government agencies; (iv) simplifying cumbersome administrative procedures for PFES implementation and financial; (v) communication and awareness; (vi) potential for combining PFES with other forestry and economic support programs to direct adequate levels of funding for forest protection; (vii) taking into consideration local perceptions of equity to improve PFES effectiveness and efficiency; (viii) improving and promoting more safer, quick and transparent processes of transfer of PFES funds to households and communities through e-payment through service providers (banks, post office or Viettel) and (viii) options for combining direct cash payments alongside non-monetary benefits to improve uptake.

- Where PFES currently does not operate, the project will investigate options for PFES introduction based on other services. The other PFES options can be investigated and expanded to other sectors in the Ba River basin area including: (i) PFES for industrial activity in which industrial producers will have to pay service charges for regulating and maintaining water resources used for industrial productions; (ii) PFES for eco-tourism activity in which entities trading in ecotourism, hospitality or entertainment will have to pay service charges for protecting and maintaining natural landscape beauty and conserving biodiversity of forest ecosystems; (iii) PFES for carbon stock and sequestration activity in which producers and traders causing massive greenhouse gas emission have to pay service charges for absorbing and storing carbon in forests, and (iv) PFES for aquaculture activity in which producers off aquatic products will have to pay service charges for providing spawning grounds, food sources, natural breeding stock, water resources, environmental elements and forest ecosystems for aquaculture. The evaluation of new potential PFES options into its financial viability, environmental and social sustainability and community acceptance.

Component 3. Gender mainstreaming replication and knowledge exchange

Total Amount: US$3,470,876; GEF project grant requested: US$370,876; Co-financing: US3,100,000

Outcome 3: Knowledge documentation, capacity support, replication and uptake of improved forest management practices

Baseline conditions for this outcome (without GEF project):

- There are gaps in policy mainstreaming and gender inequities in terms of information sharing, knowledge, and attitudes. Similarly, there will continue to be limited understanding of the value of forests in the Ba River basin in regulating water flows and protection of water quality. Ecosystem services values in terms of regulating water run-off, reducing flood events and soil erosion that can ensure future water and electricity services will not be fully appreciated. Similarly, traditional knowledge will likely continue to be guarded and segregated by gender, and while there are some efforts at sharing knowledge using public media and other social networks, this is likely to continue to advance at its own slow pace. Knowledge and understanding of the relationship between biodiversity conservation, protected areas and sustainable forest and land management and human welfare will remain low. Likewise, priorities for information collection to include gender, ethnic minorities and vulnerable people’s concerns will not be fully appreciated and understood in decision-making in terms of gender roles.

Alternative for this outcome (with GEF project):

- The goals of Outcome 3 are: (i) improving application of existing forest and land management policies; (ii) enhancing knowledge and information collection and management systems to enhance awareness about best practices on conservation of forests and forest lands and their associated biodiversity and ecosystems through communication, documentation and dissemination; (ii) supporting the strengthening programs that support conservation and sustainable use; (iii) ensuring gender considerations are mainstreamed into forest and related natural resources planning and management; and (iv) monitoring and evaluating project impacts to ensure that these are meeting project outcomes and contribute to conservation and ongoing development agendas in the Ba River basin. To achieve such an objective requires the improved understanding and participation of key target groups (decision makers and staff from key sectors), non-governmental organizations, as well as community groups (including ethnic minorities), researchers and others,       particularly women and the most vulnerable segments of the population.

- The knowledge management and communication activities will help promote meaningful stakeholder awareness and understanding, informed decision-making and collaboration in biodiversity conservation, sustainable forest management and forest use and biodiversity-friendly livelihoods as well as document, disseminate and scale up successful lessons and best practices in forest resource conservation more widely in the country. This will be accomplished through awareness campaigns, and creation and maintenance of an accessible information system for decision makers (including online public access database and documentation repository). Expanding the role of knowledge management is key to moving towards parity. The GEF alternative will also enable a gender-equity perspective and analysis of the way that information is prioritized. In accordance with this a Gender Analysis and Mainstreaming Action Plan (see Annex 10) has been developed. This Outcome will be implemented through four Outputs.

Output 3.1: Enhancing capacity of forest owners to effectively integrate biodiversity conservation and ecosystem services into their sustainable land management plans and investments

- This Output will help facilitate forest owners in the Ba River basin working with local stakeholders in their provinces, Gia Lai and Phu Yen, to be motivated, proactive and capable in adopting and operationalizing new policies to implement their Sustainable Forest Management Plans (SFMPs) and conservation targets which have been formulated in accordance with Circular 28/2018/TT-BNNPTNT on sustainable forest management and respective regulations on biodiversity. Under the Forestry Law 2017, an updated new Decree 156 on investment policies for forest protection and development, and processing and trade of forest and another new policy on investment and development of special use forest and protection forest that are being developed by VNFOREST/MARD, and expected to be approved, legally enforced and implemented by provincial authorities and forest owners from 2022. These policies are critical for guiding forest owners to determine their priority of works, mobilization of financial resources, and collaboration and arrangement of relevant stakeholders to implement and achieve their management and conservation targets setting for 2021-2025 and 2026-2030 that is defined by each forest of PA management board. The new guidance is expected to regulate and increase payments to buffer zone communities engaged in co-management that is at the deposal to communities for livelihood related activities. To enable their compliance, GEF funds will be used to strength awareness and capacity of forest owners within and outside the Ba River basin landscape in Gia Lai and Phu Yen to closely work with their provincial agencies e.g., DARD, Department of Natural Resources and Environment (DONRE), Department of Planning and Investment (DPI), Department of Finance (DOF), Department of Ethnic Minority (DEM), district/communal authorities and buffer-zone village communities in order to determine what the province should budget and/or finance for achieving targets by 2025 (and 2030) with respect to conservation of biodiversity values, sustainable forest protection, restoration and management, development of ecosystem services, and community engagement and livelihood support. At least 6 management boards of special use forest and protection forest within the basin landscape will be supported by the GEF project to demonstrate their participatory planning and budgeting capacity, embracing relevant stakeholders through engagement, consultation, verification and approval processes given to their proposals on investment for sustainable forest protection and development and biodiversity conservation.  The forest managers and management boards will also have increased capacity and skills for planning, implementation, monitoring and enforcement of their SFM plans that integrate biodiversity conservation, climate resilience, sustainable resource use, etc. and PFES application that could provide guidance for replication elsewhere in the country.  This effort will further support the aim of the National Forest Development Strategy (2021-2030) that calls for the Special Use Forest (PA) and Forest Protection Management Boards to have the capacity to provide non-business public services/expertise related to forest management, protection and restoration, biodiversity conservation and related ecotourism, PFES, co-management etc., including trying to develop some level of financial autonomy. The feedback of project results from Output 3.1, provides information of key actions (development of manuals, documentation of best practices, workshops, communication and KM products, etc.) as a means to promote these above two efforts on a boarder scale. Results and lessons learnt from this demonstration will be shared among managing agencies and other forest owners in Gia Lai and Phu Yen through sustainable landscape-building learning platforms, including exchange workshops and policy briefings. Through these platforms, the GEF funds will also be used to support the provinces to convene conservation experts, forest managers and pro-biodiversity business entities to review and update the provincial master planning, ensuring that priorities on biodiversity conservation, sustainable forest restoration and management, and nature-based solutions towards landscape sustainability that are well identified and included for their implementation in the period 2025-2030.  This Output will rely on the extensive knowledge and guidance that is available from both within and outside the country.  In particular, the project will seek to build on the guidance developed through a number of international entities, including the International Tropical Timber Organization (ITTO) such as guidelines for sustainable management of natural tropical forests, forest landscape restoration for the conservation of biodiversity in production forests, adoption to the needs and capacities of forest users to inculcate SFM into forestry practices, monitoring systems for assessing the effectiveness of SFM practices, forest landscape restoration, enhancing carbon stocks, etc. that has been developed in the region.  The project will also seek efforts (to the extent feasible) to ec]xchange knowledge and expertise with regional institutions such as the ITTO to implement the project.  The Learning and experiences from this Output will support development of policy and planning notes (in addition to workshops, field visits and information sharing) that address current constraints (awareness, capacity, technical skills and coordination mechanism) relating to planning and implementation of sustainable forest management and integration of biodiversity conservation practices into forest development in support of the new forest and planning laws (that is covered in Output 3.2) as well as efforts to enhance the capacity of the management boards to be able to provide public services and guidance related to forest management, protection and restoration, biodiversity conservation and related ecotourism, PFES, co-management as required under Decree 60/2021 that makes financial autonomy aapplicable to public non-business units.

- This Output will be achieved through the following indicative actions:

- Develop and organize training workshops to raise awareness, motivate and guide forest owners and involving actors (DARD, DPI, DOF, DEM, etc.) to adopt and implement new policies on resource mobilization and investment for sustainable forest development, conservation and management in special use forest and protection forest. The new policy guidance is expected to relate to: (i) forest protection and management, including the role and responsibilities of local communities engaged in co-management; (ii) financial flows for livelihood support to buffer zone communities; (iii) forest fire management, forest plantation restoration, wildlife rescue, education, etc.; and (iv) investment and development of ecotourism and PFES.

- Provide 06 selected forest owners/management boards of special use forest and protection forest within the Ba River basin landscape with consultancy to technically assist and facilitate 06 selected forest owners to identify and develop their development investment plans to 2025 aligning with integration of biodiversity conservation and ecosystem services in correspondence to effective implementation of their approved SFMPs and stakeholder engagement and consultation processes, as well as better allocation of funding, better use of PFES funds and priority setting based on resoutce mobilization;

- Support selected forest owners in the basin landscape to conduct stakeholder consultation, particularly with local grassroot authorities (districts, communes) and buffer zone village communities and enable consolidating inputs for their investment proposals (e.g. extent of forests to be protected by local communities, PFES allocations to villages, identifying alternatives to illegal activities, community livelihood improvements and support, outreach, communication and awareness on forest protection and wildlife conservation) prior of submission, verification and approval by provincial authorities;

- Provide consultancy to review the provincial master planning and assess how biodiversity conservation, sustainable forest management, ecosystem services and nature-based solutions are included and updated under the guidance of the Planning Law 2017 and supporting policies; and

- Support provinces to organize provincial landscape-building leaning platforms/workshops on progress and experience in adoption of new forest investment policies and update of provincial master planning, financial resource mobilization and development of policy guidance notes that will can feed into national level policy dialogue and update of guidelines and circulars

Output 3.2: Communication and Knowledge shared and exchanged on SFM and forest biodiversity best practices and innovations, including through FMU websites, site-based exchanges and best practice case studies in support of potential replication, scaling-up and long-term sustainability.

- Output 3.2 will support the creation of awareness and sharing and exchange of knowledge on SFM integrating biodiversity conservation priorities, the landscape approach, and forest biodiversity best practices and innovations so that project knowledge can be more widely shared and serve to stimulate uptake and replication of best practices across the Ba River basin and across Viet Nam. To achieve the above, would require the preparation of a concrete upscaling, replication and long-term sustainability strategy/plan that would be based in particular on supporting the update of existing policies, Decrees, Circulars and guidelines following review of (i) the role of forest rangers in special-use forests and protection forest management boards as defined by Decree 01/2019 (Output 1.4); (ii) application of technical guidelines on monitoring forest/landscape change to support effective implementation of Circulars 28/2018 and 33/2018 (Output 1.3); (iii) performance in the integration of forest sector planning within provincial master planning as defined by 2017 Planning Law (and its Decree 37/2019 and Circular 38/2019) and Decision 502/2020 issued by Prime Minister approving tasks/contents for developing the Phu Yen provincial master planning and Decision 1015/2020 issued by the Prime Minister for developing the Gia Lai provincial master planning; (iv) effectiveness of mobilization of financial mechanisms for conservation of forests and its sustainable use as defined in Decree 99/2010 in relation to use of PFES (Outputs 2.7 and 3.1) and Decree 60/2021 that makes financial autonomy applicable to public non-business units (Output 3.1); (v) effectiveness of incorporation of biodiversity and ecosystem-services related parameters into forest inventory under Decree 37/2019 and Circular 38/2019 (Outputs 1.2 and 1.3); and (vi) effectiveness and capacity of FMUs to support community forest management in relation to Decrees 156/2018 and 83/2020.  This will be supported by enhanced communication and knowledge sharing events that will include project beneficiary websites, fan-pages, FMU/district site exchange visits and building a network among PA and forest managers,so that they can serve as a local community of practice on lessons and best practices exchange. Consultations with provincial and national decision-makers will enable exchanges for potential policy considerations and reform.

- This Output will be achieved through the following indicative actions:

- Communication programs to enhance awareness of conservation outcomes and actions. This will entail preparation and conduct of awareness programs for local communities, undertaking Knowledge, Attitudes and Practices (KAP) surveys to assess level of awareness

- Documentation and dissemination of case studies, best practices and lessons learned from the project for use by Protected Area Management Boards, FMUs, Forest Companies, Commune Peoples Committee, etc.

- Development of guidance documents that addresses current constraints and gaps in implementation of existing policies and legislation (including in particular in relation to the forest and planning laws relating to SFM, integration of biodiversity conservation outcomes in forest and provincial level planning and sectoral and provincial/national coordination and monitoring and evaluation) as defined in Paragraph 102 above. This will include a series of policy notes, consultation meetings with national and provincial policy makers, technical manuals and guidance notes for forest managers on planning and implementation of SFM plans, provincial planning, monitoring of performance, financial incentives, etc., for enhacing integration of biodiversity conservation, climate resilience, sustainable resource use, and forest co-management;

- Technical reports, publications and other knowledge management products (including in local languages and accessible to Ethnic Minorities (EMs) documented and disseminated via mass media;

- Documentation of Ethnic Minority cultural system (based on application of Free, Prior and Informed Consent or FPIC principles) related to natural resources management and disseminated to constrain or avoid the erosion of Indigenous Peoples’ cultures and justify increased public investments support to ancestral domains;

- National and Provincial technical and policy related workshops to facilitate dissemination of field lessons and help inform legal and policy reform relevant to implementation of forest, planning and biodiversity laws and their relevant Decrees, Circulars and Guidelines. The initial documentation of these lessons will be included as part of the participatory monitoring process, that would be complemented by additional national technical support to distil and document lessons and experiences. The project will support workshops at the provincial level (Year 4) to share lessons and experiences and a national workshop at the end of Year 4) to facilitate the sharing of lessons more widely, but importantly to be able to further develop and refine successful approaches for replication nationally;

- Efforts would be made to institutionalize some of the best practices through promotion of policies and guidelines in order to secure support for replication and up-scaling.

- Inclusion of public engagement pages on national and provincial websites and social media platforms that link to information about the project and its products, including development of a specific public information sharing platform. This could serve to share information with Protected Area and Forest Management Boards provincial and district people’s committees, NGO and government entities

- Preparation of a replication, scaling up and long-term sustainability strategy/plan based on project experiences and best practices for promotion of integrated landscape management, including institutional, financial and resource requirements, partnerships and coordination arrangements. In particular, this strategy/plan will provide overall guidance (based on on-the-ground application and review of existing regulations and guidelines for effective integration of biodiversity and sustainable forestry outcomes in implementation of the Forestry, Biodiversity and Planning Acts) for validation, update and policy reforms related to these Acts. The preparation of the strategy/plan will entail an in-depth analysis of financial options for sustaining the policy dialogue and reform;

- A MARD based Implementer’s Manual and Lessons Learned guide (with contributions from project partners) that captures the process of project implementation, and describes Integrated Biodiversity Management Strategies for biological corridors and SFM, SLM, OECMs (Other Effective Conservation Measures) approaches, Sustainable Livelihood improvements, mainstreaming of biodiversity in sector planning at sub-national level, etc. within biological corridors; and

- End of project national seminar on outcomes and replication for integrated biological landscape management practices in Viet Nam

Output 3.3: Gender mainstreaming and safeguard management

- This Output will focus on gender mainstreaming and management of safeguards. Full adherence to safeguards and recognition of community rights including Free, Prior and Informed Consent (FPIC) of ethnic minority groups will be a key part of this process (see Annex 8b).

- This Output will be achieved through the following indicative actions:

- Implementation of a gender analysis and mainstreaming action plan so that: (i) a gender and socially inclusive perspective is applied to every set of activities; (ii) research on gender and social roles in biological corridors inform resulting plans and ensures equitable distribution of benefits; and (iii) information is collected and shared across gender and social divides. Training of staff on application of gender mainstreaming in project communication and project activities;

- Implementation of ESMP and IPP as to: (i) ensure that there is free, prior and informed consent (FPIC); (ii) EMs fully participate and are represented at all levels in the decision-making process, in particular on those that may affect their development and environment rights; (iii) that their rights to self-determination are recognized; (iv) ensure that their culture, social and religious beliefs are not compromised; and (v) integration of EMs perspectives and concepts in the development process, etc. FPIC principles will be applied to Outputs 1,2; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 and 3.1.

- Monitoring the implementation of the ESMP and IPP

- Conduct of gender, indigenous peoples and biodiversity focused training and development of training materials

Output 3.4. Monitoring and evaluation

- A project-based M&E system will be implemented to support project impact and evaluation and will include the following indicative activities:

- Development and implementation of monitoring framework, based on the Results Framework Agreement to validate baselines and monitor progress in achieving project outcomes and impacts

- Review and regular update of M&E plan, including results framework baselines, tracking tools, Theory of Change to subsequently adopt these findings to implement all aspects of the project; and

- Conduct mid-term and terminal evaluation in line with UNDP/GEF requirements and incorporate and adapt recommendations of MTR to revised project plans and monitor their implementation.

Partnerships:

- The proposed project will coordinate with selected government programs and donor projects associated with them to generate positive results through combined action (where appropriate) and to share lessons learned and best practices. The key national Environment, Forestry and Natural Resources programs to work with include those in Table 2.

- In the context of the above and related core programs, the project will collaborate with agencies on knowledge and lessons learned from important, recently completed projects (which are described in the various sections of the project design), as well as ongoing and pipeline projects (usually assisted by donor/development partners). Collaboration with ongoing and pipeline projects would primarily aim to synergize planning and implementation with concerned projects in common sites. For projects without common sites, the main purpose is to build on each other’s field methodologies and share information needed for policy dialogue. The following are the key ongoing and pipeline projects.

Table 2. Partnership Arrangements

| Name of on-going and planned program/project, years of implementation and sites | Program/project objectives and targets | How proposed UNDP/GEF project will collaborate with the program/project? |
| --- | --- | --- |
| UNDP-GEF project “Mainstreaming Natural Resource Management and Biodiversity Conservation Objectives into Socio-Economic Development Planning and Management of Biosphere Reserve in Viet Nam” | Harmonizing socio-economic development, sustainable management of natural resources and biodiversity conservation through an integrated landscape approach in Biosphere Reserves | Regular meeting and information sharing will be maintained between the project to share experience and best practices include site visits, co-organize workshop/seminar to share information, share documentation and join training to share and promote similar approach and best practices |
| The People Resources and Conservation Project ‘Support on community-based biodiversity conservation in Kon Ha Hung Highland Landscape, Gia Lai province’ implemented by Gia Lai DARD | Community-based conserving at the landscapes with high conservation values in Kon Ha Nung, including supporting representative communities in biodiversity conservation management and sustainable socioeconomic development | Maintain regular meetings and information sharing on implementation plan; conduct join-training between project to promote information sharing and best practices; conduct site visit (pilot sites, models) for project staff and relevant stakeholders |
| EU-funded, UNDP-implemented project for “Integrated sustainable landscape management through deforestation free jurisdictions in Lam Dong and Dak Nong” | Improving environmental sustainability and social inclusion and resilience of food production systems and supply chains | Regular meeting and information sharing will be maintained between the project to share experience and best practices include site visits, co-organize workshop/seminar to share information, share documentation and join training to share and promote similar approach and best practices |
| The KfW 9 and KfW 10 projects in two districts of Gia Lai province | Improving management of special use forests and national parks; Improving management of protection forests and community forests; and implementing environmental education measures. | Regular meeting and information sharing will be maintained between the project to share experience and best practices include site visits, co-organize workshop/seminar to share information, share documentation and join training to share and promote similar approach and best practices |
| ADB Biodiversity Corridors Conservation Project in Viet Nam in the central provinces of Quang Nam, Quang Tri and Thua Thien Hue | Conservation and management of biodiversity rich forests in central provinces to help restore and maintain connectivity of ecosystems and benefit local communities | Sharing project document, best practices and lesson learn include site visit to witness project approach, outcome and lesson (The BCC will completely close when this project start). |
| JICA-funded project on “Rehabilitation, Restoration and Sustainable Management of Protection Forests” | Restore and develop watershed protection forests; strengthen capacity for local government and protection forest owners; and support improved livelihood for communities participating in managing protection forests. | Sharing project document, best practices and lesson learn include site visit to witness project approach, outcome and lesson |
| Proposed project will contribute to the implementation of the forest protection programs in Gai Lai and Phu Yen provinces (under the broader umbrella of Central Highlights project 297) and the National Forestry Development Planning 2021-2030 | Improving forest protection, planning and monitoring and establishing community-based reserve in production forest. | Sharing project document, best practices, lessons learned, and outcomes at site level to support better planning process at national level taking consideration of actual implementation and support needed from the ground level |
| International Tropical Timber Organization (ITTO) | Internationally available policy guidelines for sustainable management of natural tropical forests, forest landscape restoration for biodiversity including in production forests | Sharing best practices, guidelines technical knowledge, expertise and information from ITTO through participation in GEF 7 project stakeholder events, knowledge sharing events, workshops and website use |

- In terms of co-financing, the co-financing commitments are discussed in the table below:

Table 3: Co-financing Commitments

| Co-financing Source | Co-financing Type | Co-financing amount | Included in project results | If yes, list the relevant outputs |
| --- | --- | --- | --- | --- |
| Government- Forest Inventory and Planning Institute (FIPI) of Ministry of Agriculture and Rural Development (MARD) | In cash and In-Kind (Recurrent Expenditure) | 1,000,000 | No | NA |
| Government - Provincial People’s Committee, Gia Lai | Investment Mobilized: Public Investment | 15,272,000 | No | NA |
|  | In-kind: Recurrent Expenditure | 861,000 | No | NA |
| Government - Provincial People’s Committee, Phu Yen | Investment Mobilized: Public Investment | 1,000,000 | No | NA |
|  | In-kind: Recurrent Expenditure | 500,000 | No | NA |
| Total |  | 18,633,000 |  |  |

- The co-financing activities and risks and risk management strategies are presented as follows:

- Forest Inventory and Planning Institute (FIPI) of Ministry of Agriculture and Rural Development (MARD) in-cash and in-kind contribution will be in the form of state budget and recurrent expenditure based on costs related to staff and facilities that are already at disposal of MARD

- Provincial People’s Committee, Gia Lai, includes Public Investment of USD 15,272,000 for Planned financing for (i) forest protection and development and (ii) capacity building of rangers in fire prevention and sustainable forest management and in-kind contribution of USD 861,000 for Project management, office space, staff time, etc. for all Forest Management Units and PAs within the province. There are limited risks with the Investment mobilized as these represent planned commitments from the provincial government and donor support.  The risk from in-kind is also low as this entails use of existing staff time and available facilities

- Provincial People’s Committee, Phu Yen includes Public Investment of USD 1,000,000 for forest protection and development and forest restoration and management in northern regions of Phu Yen province and in-kind contribution of USD 500,000 for Project management, office space, staff time, etc. for all Forest Management Units and PAs within the province. There are limited risks with the Investment mobilized as these represent planned commitments from the provincial government.  The risk from in-kind is also low as this entails use of existing staff time and available facilities

Risks:

- As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log (Annex 5).

Table 4: Project Risk and Mitigation Matrix

| Project risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| A. General Risks |  |  |  |  |  |
| Description | Type | Impact, Probability and Risk Level | Mitigation Measures | Owner | Status |
| Risk 1: Challenges in engaging local resource users in ethnic minority communities | Institutional | Moderate I-3, L-2 | The project will apply participatory processes to ensure engagement of local partners and communities during project implementation and in the preparation of activity plans drawing on lessons from previous OPD projects. | PD | Implementation |
| Risk 2: Forest management institutions may have inadequate capacity to sufficiently uptake SFM practices for implementation | Institutional | Moderate I-3, L-2 | An initial assessment undertaken as part of the PPG indicated that based on the requirement of Decree 156/2019, all forest owners (Forest Management Boards) are required to prepare SFM. Most forest owners have already prepared their SFM plans. However, the capacity of these forest owners is limited in both human resources and budget allocation. As such, the risk can be significant to ensure that appropriate SFM practices are introduced. This risk will be reduced by strong and intensive capacity building program. The capacity building will not only provide for the forest owners ‘s staff (PA, NR, PFMB) but also extended to relevant communities if needed during the project implementation. This program will be closely monitored to ensure that they are environmentally and socially sound. | PD | Implementation |
| Risk 3: If assumptions made in the theory of change are not forthcoming during project implementation, such as the institutional framework for addressing integrated basin conservation or that capacity of forest managers and local communities are not upgraded to improve SFM and conservation outcomes there is a possibility that project outcomes may not be met. | Institutional | Moderate I-3, L-2 | UNDP CO will monitor and track progress to ensure that adaptive and timely actions are taken to correct any shortcomings or implementation problems. | PMU and UNDP CO | Implementation |
| Risk 4: Inability or risks associated with management of project funds and assets and accurate and timely reporting of ineffectiveness of control systems can increase costs, reduce quality, delay impacts and cause social instability | Financial | Moderate I-3, L=3 | The following management measures are taken into consideration: As part of the PPG assessment, UNDP undertook a Partner Capacity Assessment exercise to assess the managerial, administrative and financial capabilities of FIPI (the Implementing Partner for the project) and based on UNDP norms the risk was assessed as ‘low’ and the PCAT confirmed that there were no evidence of financial fraud with FIPI In addition, in terms of procurement of goods and services, FIPI will use electronic procurement as required by regulations and a Procurement Review Committee will oversee and monitor all procurements. UNDP CO will have regular meetings with IP and monitor annual work plans and funds releases UNDP CO will undertake safeguard measures such as annual audits and conduct spot checks to ensure that expenditure matches quarterly work plans and expenditure statements UNDP CO staff will make field visits to verify works have been undertaken in accordance with work plans and agreed norms A Grievance Redressal Mechanism will be established to enable beneficiaries to make any complaints regarding misappropriation of costs and other irregularities | PD and UNDP CO | Implementation |
| Social and Environmental Risks |  |  |  |  |  |
| Risk 5: The Forest Management Units in the project area might not effectively engage and ensure participation of all stakeholders in particular in sharing of forest products, livelihood benefits and other benefits and thereby impact on the rights and interests, lands, territories, resources, and/or traditional livelihoods of ethnic minorities resulting in violation of human rights. They might also not effectively apply FPIC procedures thus posing significant risks to achieving project outcomes. | Social | Substantial I-4, L-3 | The following management plans/frameworks were prepared at PPG stage to understand and try to address the potential environmental and social impacts of the project. These included the following: A Stakeholder Engagement Plan that defines the clear role and responsibilities of each stakeholder, including local communities and EMs in the implementation, A Gender Analysis and Gender Mainstreaming Action Plan that identifies the potential role of women in resource management and related activities, current constraints to participation of women and vulnerable communities in decision-making and sharing An Indigenous People framework with guidelines of FPIC to ensure FPIC to be secured multiple times during the project timeline, ensure that EMs are actively engaged in project activities, their cultural, social and traditional practices are recognized, maintained and enhanced, that they share equitable benefits from the project (livelihoods, resource use and ABS benefits), that there are special investments focused on these groups. A grievance redress mechanism for the project, based on the existing government and UNDP mechanisms to provide an avenue to articulate any project specific grievances A Livelihood Action Plan(s) will be developed during early project implementation, in case there is any inadvertent restriction on access to resources An ESMF has been prepared. The ESMF lays out procedures and actions to identify and assess potential impacts of project activities. Further meaningful engagement and consultations will be carried out with project affected peoples (including ethnic minorities) in the conduct of SES-assessments that will be conducted during project implementation. This includes the development of a SESA and scoped ESIA(s) . As a complement to the above measures, the project will apply participatory processes and approaches to all activities relevant to local communities where principles of FPIC will be further emphasized and demonstrated through providing timely information related to opportunities and risk of the proposed interventions for the beneficiaries to enable them to make decisions. In case community concern or inability to secure FPIC emerge the following mechanisms would be applied as adaptive management: • Additional stakeholder consultations/workshops will be conducted using technical support to further refine project activities and approaches to address any concerns. Any such changes would be captured in the annual work planning process and summarized in PIRs; • In a situation were to arise where FPIC could not be obtained or whatever reason, any activities requiring FPIC such as expansion of existing PAs, forest restoration, ecotourism will not take place. | PD | Implementation |
| Risk 6: Project activities related to sustainable forest management, community forest management and livelihood might not fully incorporate the views and needs of women | Social | Moderate I-3, L-2 | The Gender Action Plan (GAP) has specific actions targeted to women (and in particular EM women), including: (i) specific awareness and training to sensitize central and local level SFM, PA and Management Board staff on gender related issues; (ii) ensuring adequate representation and active participation of women in relevant decision-making bodies; (iii) involving women in sustainable forest management and livelihood development activities at the Project site; and (iv) provide technical trainings for women on various project related activities, etc. These activities have been also presented under Output 2.5. A comprehensive stakeholder engagement plan, IPF, Gender and ESMF has been prepared during the PPG, and a FPIC process will continue with affected stakeholders during project implementation. | PD | Implementation |
| Risk 7: Enhanced management of PAs/FMUs, targeted forest restoration, and realignment of PA boundaries could result in changes or restrictions in access to forest lands and forest resources. | Social | Substantial I-4, L-3 | Consultations with local stakeholders (Tram Lap, Dak Rong Forest Companies, local authorities) and ethnic minorities communities guaranteed that there will not be physical relocation, but there could be possibility for economic (e.g.,, NTFP collection). Allocation of forest for community forest management, while a positive development can have potential to exclude other neighboring communities from access to these resources. Issues pertaining to access restriction induced risks/adverse impacts will be identified , assessed and managed through two distinct elements, i.e. (i) scoped ESIA(s) at the project site level, (ii) a process framework. In addition to the above, the conduct of a SESA for “upstream:” project elements have been proposed. This will also screen and assess potential future/indirect risks relating to access restriction. | PD | Implementation |
| Risk 8: Long-term sustainability of the positive project outcomes could be negatively impacted by climate change, including community forest management, livelihood and small-scale enterprise activities. In the short-term climate induced natural hazards and weather events could impede smooth implementation of the project. | Environment | Moderate I-3, L-2 | During the community livelihood investment planning process, specific focus will be taken on selection of agricultural and livelihood practices that are likely to be less vulnerable to climate change, include climate sensitive crop varieties and cropping patterns. The selection of species in sustainable forest and forest land management will focus on species that are more resistant to large fluctuations in climatic conditions. Enhanced management and conservation practices would improve protection and management of critical ecosystems services as well as wildlife habitat, which should help to increase the overall resilience of the natural systems to climate risks in the areas compared to business as usual. Ensure that measures/activities are implement by the project to enhance women and EMs capacity to adapt to climate impacts; In terms of the Monitoring Plan, the condition of the natural ecosystems would be monitored to ensure that activities do not damage these sensitive ecosystems so that it is in a better overall situation to adapt to climate changes. The Management Knowledge and Communications outputs are key to improve awareness of climate and ensuring measures to improve climate resilience See Section below: “Summary analysis and project implications for climate change considerations” | PD | Implementation |
| Risk 9: Poorly designed or executed forest management, NTFP usage, ecotourism, livelihood and small-scale rural enterprise activities, could unintentionally damage critical or sensitive habitats and ecosystems | Environment | Moderate I-3, L-2 | The sites selected for project investment conformed to the project’s objective of ‘enhancing the conservation of biodiversity through mainstreaming of biodiversity into planning policies and practices into the Ba River landscapes. The project intends to have interventions that will benefit improved conservation, support environmentally friendly agricultural and land use practices to reduce impacts on species and ecosystems, improved monitoring of species and ecosystem health, participation of forest management boards in environmentally-friendly practices (including reduced clearing and improved management of corridor and forest areas), rehabilitation of degraded areas with native species or through natural regeneration processes, and enhanced environmental stewardship of landscape resources by local communities. As an effort to support conservation outcomes, all community agriculture and production systems and livelihood activities will take place outside the high value biodiversity areas (including in buffer zones) to the extent feasible through appropriate mapping and zoning arrangements. The Preparation of a screening checklist developed (refer ESMF) will be applied to screen all investments to ensure that they comply with sound social and environmental principles and are sustainable. Such a checklist would also include the identification of investment location in relation to protected areas and biologically important areas and critical wildlife corridors. . Refer Annex 19 of UNDP Project Document for sustainable approaches to forest management and restoration has been developed at PPG stage in accordance with the government (MARD) approved rules. As part of the screening process, the MARD rules will be assessed for the compliance with SES guidelines Setting acceptable sustainable limits on harvest of non-timber forest products based on status and health of such populations and establishment of monitoring protocols. These considerations have positioned the project into a framework of synergy between the natural environment and the actors within it. Technically qualified biodiversity and SFM specialists of Provincial DARDs will support the Provincial PMUs and/or Forest Management Units to monitor and coordinate the risk management strategies. | PD | Implementation |
| Risk 10: Alien Invasive Species (IAS) could inadvertently be introduced to project demonstration sites, in particular during forest restoration activities.. | Environment | Moderate I =3, L =2 | Project activities will be carefully planned in consultation with relevant DARD experts in forest restoration and local communities. These restoration management plans will be based on MARD forest restoration guidelines (and assessed with their compliance with SES standards) and would be completed prior to any technical demonstration activities taking place and potential perverse impacts and safeguards will be considered as part of this process, along with required standards and guidelines such as mandating use of native species for plantings, measures for IAS control and management, adherence with established SOPs and guidelines of national/local authorities. As part of the effort to manage IAS, this would entail training to key development partners on the project to identify potential IAS and institute measures, along with the local community to eliminate, control and/or manage these species. Technically qualified biodiversity and SFM specialists of Provincial DARDs will support the Provincial PMUs and/or Forest Management Units to monitor and coordinate the risk management strategies | PD | Implementation |
| Risk 11: The project sites could potentially intersect with globally and locally important sites with cultural, historical, religious, artistic and traditional values. It is unlikely that the project activities will have structural adverse impacts on these sites but may adversely impact traditional knowledge and practices that are part of the communities for centuries and that are deep-rooted in their cultural practices | Social | Moderate I-3, L-2 | The implementation of the EMPFwill form the basis for dealing with the interests of the EMs and other special interest groups. Any project related economic development initiatives proposed by communities and EMs will rest on the maintenance of the integrity of their culture and defined using FPIC procedures The use of a screening checklist (refer ESMF) will ensure that these take into consideration all potential impacts and implementation would be monitored to ensure that there are no impacts on cultural heritage of EMs or special interest groups. Gender/ participatory expertise will be obtained during the project to guide and monitor these activities, establish procedures for identification and managing such risks. Although the potential for ecotourism is low in the project sites, any potential ecotourism activities will take into consideration the following: - Appropriate waste management measures - Location of campsites, washing areas, grazing areas in locations that are not ecologically sensitive and of cultural significance - Train Community tour guides to manage tourist in order to avoid and minimize adverse impacts of visitation on the biodiversity and cultural sites. - Ensure that the tour guides brief visitors on “DOs and DONTs” in the project area and adhere to it. - Visitations to cultural heritage sites to fulfill local cultural requirements based on cultural appropriate visitation. - Capacity development training and awareness-raising for local stakeholders, communities and tour operators on the guidelines and their application of culturally sensitive ecotourism principles | PD | Implementation |
| Risk 12: Use of pesticides, herbicides or insecticides could potentially pose risk to community health and lack of adequate guidelines on usage and storage of these chemicals could result in generation of hazardous waste through different migration pathways (soil, water, or air). | Environment | Moderate I-4, L-2 | To avoid or minimize the use of chemicals, the forest restoration activities will largely focus on assisted natural restoration methods that do not qualify for extensive use of chemicals. During project implementation, the project will follow a strict SOP for the application of any pest management substances/activities. This will include adhering to the following: - The project will ensure that it would follow the list of prohibited pesticides, herbicides and insecticides. - The storage, transport, disposal and use of pesticides will follow standard and acceptable standards - Communities and staff using pesticides will be provided training of the safe use and application of pesticides The use of any chemicals will be prohibited within 25 meters from waterways, settlements and high biodiversity value forests | PD | Implementation |
| Risk 13: Surveillance and patrolling activities on PAs could lead to escalated conflict or safety-related risks if rangers have contact with poachers. These activities could also have safety risks for local communities if rangers are not properly trained, managed and overseen with a human-rights based approach to law enforcement taken. Anti-poaching patrols could pose safety risks to local communities if they are not properly trained, managed or overseen. | Social | Substantial I=4, L=3 | As part of project design, the capacity needs of PA staff have been assessed to understand to what extent they have the skills to address conflict and potentially violent situations. Establishment and implementation of a Standard Operating Procedures (SOP) for management of illegal activities, that will specifically include safety and security-related procedures is defined as part of the ESMF. The project intends to embed local community members within the patrols so that they can help build better relationships between PA staff and communities. In addition, a grievance redress mechanism has been prepared and a comprehensive stakeholder engagement plan has been developed and implemented in the project cycle as well | PD | Implementation |
| Risk 14: Forest management institutions may have inadequate capacity to sufficiently uptake SFM practices without impact on biodiversity and natural resources | Environment | Moderate I = 3, L = 2 | An initial assessment undertaken as part of the PPG indicated that based on the requirement of Decree 156/2019, all forest owners (Forest Management Boards) are required to prepare SFM plans. Most forest owners have already prepared their SFM plans. However, the capacity of the forest owner is limited in both human resources and budget allocation to ensure that appropriate SFM practices are introduced. The findings from the initial capacity assessment during PPG have informed project design. A key aspect of this project focuses on capacity building for local communities with regards to SFM. As such, this risk will primarily be managed through the activities associated with Component 2: - Provide technical support to FMUs to conduct resource and biodiversity monitoring and inventory in engagement with their sustainable forest management plans - Develop guidelines and standards for information collection, indicators, and templates on forest and biodiversity assets at local scale, focusing on forest tree species and density, forest status and forest quality, forest biomass assessment, and wildlife species. Based on lessons learned at local scale, develop recommendations for application of forest, biodiversity resource monitoring and inventory at a larger scale. - Build the capacity for relevant agencies and staffs at local levels and FMUs (PA and forest managers) in design and implementation of forest and biodiversity assets monitoring and inventory activity in their institutions through training activity. In addition to the above, capacity building will not only be provided for the forest owners and staff but also extended to relevant communities if needed during the project implementation. | PD | Implementation |
| Risk 15: The COVID-19 outbreak could accelerate resource exploitation due to economic disruptions in other livelihoods, pose serious difficulties for effective project implementation and disrupt tourism markets (Refer Annex 16 -Summary Analysis and Project Implications/ Opportunities for Covid-19 for additional details) | Environment | Moderate I=3, L=3 | During the early part of project implementation particularly during the preparation of livelihood and small business enterprise planning, a rapid assessment of the current social and economic impacts of ongoing Covid-19 (likely as part of IPP), in particular on vulnerable populations in to assess the options for provision of income generation opportunities. The gender actions will also specifically focus on vulnerable women population in high Covid-19 risk areas. The livelihood and enterprise planning exercises will help develop suitable investment plans for responding to and ensuring income recovery for affected vulnerable populations. Special efforts would be made to enhance technical support, extension services and materials to enable the successful implementation of such activities. The Government of Vietnam has certain measures in place for staff, particularly at the provincial and local levels to ensure that they continue to perform their official duties. Meetings can be conducted in small groups and via other communication methods, to the extent these are feasible in given situations. The Provincial Governments have now become more effective with dealing with their responsibilities and ensuring that staff response times are normal, as much as possible. Provincial Governments were fully engaged with this proposal at PPG stage, and expect UNDP and GEF to move forward with the work. At the Provincial levels, governments are functioning at normal, or near normal with precautions in place. However, engagement of communities and private sector will likely require precautions if there is an outbreak of infection, including following government Covid19 protocols, meeting at the community levels will be restricted to smaller numbers of staff and community members, using precautions of masks and social distancing. Convening discussions with financial institutions, particularly the green funding programs available in the country to catalyze interactions and increase options for direct financing for these livelihood activities, including grant support for tiding over the initial difficult period of recovery. Efforts will be made to increase awareness of local communities on measures to reduce the infection rates | PD | Implementation |
| Overall Rating |  | Substantial |  |  |  |

- During project development, the project was reviewed using UNDP’s social and environmental screening procedure (SESP).  The analysis identified a range of potential social and environmental impacts associated with the project activities. The SESP report (Annex 4) details the specific environmental and social risks that apply.  The significance of each risk, based on its probability of occurrence and extent of impact, has been estimated as being Low, Moderate, Substantial or High.  Where a risk is identified and assessed as being of Moderate, Substantial or High risk, it triggers the relevant standard or principle.  Risks that are assessed as “Low” do not trigger the related principle or standard. Based on the significance of these individual risks, the project has been allocated an overall SESP risk categorization rating of “Substantial”, the overall risk category being taken from the highest rating allocated to any individual risk.

- The SESP identified 11 risks for this project that could have potential negative impacts in the absence of safeguards.  Two of the risks were rated ‘Substantial’, 7 rated ‘Moderate’ and 2 rated as ‘low’. The screenings indicate that ten of the social and environmental principles and standards have been triggered due to these risks.  They are:

- Principle: Human Rights, due to the risk that project benefits could have inequitable adverse impacts on people living in poverty or marginalized or excluded individuals or groups, and that local inter-village disputes related to land or marine area use could be exacerbated by the project, that implementing partners and recipients of low value grants may lack the capacity to meet their obligations in the project.

- Principle: Gender Equality and Women’s Empowerment. The SESP identified a risk that project activities and approaches might not fully incorporate or reflect views of women and girls and ensure equitable opportunities for their involvement and benefit.

- Principle: Accountability. This Principle is also triggered due to the risk that vulnerable or marginalized groups might be excluded from project design and fail to enjoy the project benefits.

- Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management. The risk is identified that poorly-designed or executed project activities could damage critical or sensitive habitats, including through the inadvertent introduction of invasive alien species.

- Standard 2:  Climate Change Mitigation and Adaptation, due to the risks posed by climate change.

- Standard 3: Community Health, Safety and Security. The Covid-19 pandemic, or a similar disease outbreak, may have implications for the project at international, national and local levels, including potentially affecting stakeholder meetings.

- Standard 4: Cultural Heritage: On account of activities being implemented in culturally sensitive areas of the EMs

- Standard 5:  Forestry and related activities may cause restrictions in availability and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities.

- Standard 6: Indigenous People.  Given the presence of a number of ethnic minorities in the project sites, the project can pose human rights and other related cultural impacts

- Standards 7: Labor and Working Conditions related to the ongoing potential for Covid prolongation

- Standard 8: Pollution Prevention and Resource Efficiency. The standard is triggered as there is a risk that local communities, project workers, or community members taking part in agricultural and forestry activities, might be exposed to hazards in their use of chemical inputs.

- A summary of the risk significance under each SES principle and standard, and the project-level safeguard standards triggered by each project is shown in Table 5 below.

Table 5: Summary of safeguards triggered based on screening conducted during project preparation

| Overarching Principle / Project-level Standard | Rating |
| --- | --- |
| Principle: Human Rights | ✔ Substantial |
| Principle: Gender Equality and Women’s Empowerment | ✔ Moderate |
| Principle: Accountability | ✔ Substantial |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management | ✔ Substantial |
| Standard 2: Climate Change and Disaster Risks | ✔ Moderate |
| Standard 3: Community Health, Safety and Security | ✔ Substantial |
| Standard 4: Cultural Heritage | Moderate |
| Standard 5: Displacement and Resettlement | ✔ Moderate |
| Standard 6: Indigenous Peoples | ✔ Substantial |
| Standard 7: Labor and Working Conditions | ✔ Moderate |
| Standard 8: Pollution Prevention and Resource Efficiency | ✔ Moderate |
| Number of risks in each risk rating category |
| High | 0 |
| Substantial | 3 |
| Moderate | 8 |
| Low | 2 |
| Total number of project risks | 11 |
| Overall Project Risk Categorization | Substantial |
| Number of safeguard standards triggered | 11 |

## Procedures for Screening, Assessing and Managing Social and Environmental Impacts

- The overall risk for the project is classified as ‘Substantial’ based on the assessment undertaken at the PPG stage. The following risk management measures will be in place to during the project implementation:

- No activities which may cause economic displacement, or which may have adverse impacts on Indigenous People, can commence until agreed mitigation or risk management methods are in place.   These activities require formal broad community consent, through a process of Free, Prior Informed Consent.  Provisionally, these activities are assessed as follows.

| Activity No. | Description |
| --- | --- |
| 1.2.3 | Preparation of Ba River Strategy |
| 2.2.7 | Implement priority management activities for biodiversity conservation, SFM, etc. |
| 2.3.1 | Development of proposal for inclusion of forest areas into existing PAs |
| 2.4.3 | Development SFM plans for community forest co-management |
| 2.4.4 | Implementation of community enterprise development activities |
| 2.5.3 | Establish mechanisms for implementation of livelihood support for women |
| 2.6.2 and 2.6.4 | Development and implementation of forest restoration activities |
| 2.7.4 | Investigation of options for PFES extension into new areas |

Note that the above list is provisional, and may be amended as required, and as project activities and exact locations are established.

Targeted Screening:

- Site- and activity-specific SESP screening.   At the current stage of project development, precise locations and on-the-ground activities are not finalized.  The SESP has been conducted based on the broad scope of activities envisaged, and impacts listed are therefore generic rather than site-specific. While catchment areas have been established, exact locations for on-the-ground activities (and hence the project’s direct beneficiaries and project-affected communities), have not been specified at the present stage of project development.  Additionally, specific activities with a physical footprint are not currently defined and may in themselves present additional risks/impacts. Locations, and proposed project activities specific to those locations, will be defined during the first year of the project. Some outputs, specifically those mentioned in the table above, may require that selection of sites, species and means of control, are screened on a targeted basis with the SESP, as an integral part of activity formulation, and identified risks are taken into consideration.

- The relevance of the currently identified risks may vary across sites, and the significance or likelihood of the risks or impacts identified by the current SESP will not necessarily be uniform across at all locations.  Further screening is required to identify risks’ site-specific significance, and to effectively target any required further impact assessment or management.

Strategic Environmental and Social Assessment for Upstream Activities:

- A Strategic Environmental and Social Assessment (SESA) will be undertaken to cover the following project activities:

| Activity No. | Description |
| --- | --- |
| 1.1.2 | Development of provincial statutes, as necessary that determine composition, mandates, decision-making, functions, reporting and role and responsibilities and operational management of the provincial coordination committees |
| 1.2.3 | Preparation of BA River basin forest management and restoration strategy |
| 1.2.4 | Guideline for HCVF assessment for all FMUs in Ba River basin. The assessment will highlight all HCVFs assessment steps and to guide future efforts to improve HCVF management, improve connectivity and potential upgrading of existing PAs and/or creation of new PAs within the basin. |
| 1.4.1 | Review of monitoring, surveillance and enforcement systems (including regulations, protocols, coordination, etc.) and capacities across the multiple existing entities at the Provincial level |
| 1.4.2 | Development of cross-sector plans, actions, protocols, procedures and baselines underlining roles and responsibilities of key provincial entities to improve joint monitoring, surveillance and enforcement ensuring the landscape level |
| 1.4.3 | Development and/or update of provincial level regulations that facilitate monitoring and enforcement |
| 1.4.5 | Development of appropriate protocols/guidelines and enforceable standards for biodiversity and/or SFM/SLM for landscape conservation and restoration. |
| 1.4.6 | Development and agreement on inter-provincial cooperation to cover wildlife offences alongside forest offences, initially between Gia Lai and Phu Yen provinces, and based on this success, its later extension to neighbouring provinces such as Quang Ngai and Kon Tum |
| 1.4.7 | Development of protocols for inter-provincial coordination, including sharing information, joint patrolling and monitoring, training and awareness creation |
| 2.3.1 | Undertake the development of a proposal as regulated by Viet Nam for inclusion the forest area of Dak Rong and Tram Lam FMUs into existing protected areas to improve connectivity |
| 2.3.3 | Prepare operational plan for the extended PAs including training to build capacity for the new conservation area and engagement plan for local community in forest protection and biodiversity monitoring |
| 2.4.3 | Development of SFM plans for community forest co-management |
| 2.7.4 | Investigation of options for PFES extension into new areas |

The SESA process will ensure that impacts to local communities, their livelihoods, rights, resources and the biophysical receptor environment are taken into consideration in the decision-making process while developing legislative tools and strategies. Any institutional and capacity gaps identified during this process will be addressed through the training that will be conducted for the specified activities.

Scoped Environmental and Social Impact Assessment for selected sites/downstream activities

Four main project activities will require scoped ESIAs, and shall not commence until such reports have been produced and disclosed (following UNDP SES requirements on information disclosure periods). Scoped ESIA’s will be required for:

Activity 1.2.1 Mapping of the Ba River basin forest cover and flagship species (rapid exercise using existing available information with ground validation) that highlight strategic conservation areas, strategic watershed and headwaters protection areas, habitat connectivity and vulnerabilities to threats

Activity 2.4.7 Assess environmental and social risks associated with the proposed value chains and propose risk management and mitigation measures

Activity 2.6.1 Identification and survey of locations for forest restoration to improve connectivity (following mapping exercise in Output 2.2)

Activity 2.6.2 and 2.6.4  Development and implementation of forest restoration activities

Prior to the commencement of any of the above listed activities, a site-specific/scoped  environmental and social impact assessment (ESIA) will be conducted in accordance with UNDP’s SES policy and the UNDP SES Guidance Note on Assessment and Management.

Stakeholder engagement and south-south cooperation:

- A wide range of consultations with stakeholders were conducted during the PPG stage. Initial stakeholder analysis during the PIF stage was followed up with consultation during the PPG stage in terms of the design of the project. During the PPG stage, following consultations at the national level and in the provinces of Gia Lai and Phu Yen, the stakeholder analysis was updated and elaborated following consultations undertaken by the PPG consultants at the biological landscape sites and with the provincial and district governments addressing both institutional stakeholders in the context of their statutory involvement in the project, and more broadly for non-governmental stakeholders (IPs, communities and CSOs) including forest resource-dependent communities. Several landscape level consultations were conducted to obtain the perspective of the different stakeholders during the period November 2020 through March 2021. Several bilateral meetings with future partners were also conducted. A series of validation workshops were conducted in Hanoi and the two provinces to discuss the project design and reach general consensus on project outcomes, outputs, activities and institutional arrangements for the project. See Table 6 below of listing of consultations. Also refer to ESMF and EMPF for additional consultations conducted in terms of preparation of safeguard documents. The list of stakeholders consulted has been downloaded in PIMS.

Table 6: Consultations Meetings

| KEY CONSULTATIONS | DATE | STAKEHOLDERS |
| --- | --- | --- |
| Consultations with provincial agencies, forest owners, district and commune agencies in Gia Lai province | 9-13 December 2020 11-14 January 2021 25-29 January 2021 | Provincial agencies: - Department of Agriculture and Rural Development (DARD) - Department of Natural Resources and Environment (DONRE) - Department of Planning and Investment (DPI) - Forest Protection Department (FPD) - Forest Protection and Development Fund (FPDF) - Committee for Ethnic Minority Affairs (CEMA) - Women’s Union (WU) Forest owners: - Kon Ka Kinh National Park - Kon Chu Rang Nature Reserve - Tram Lap State Forest Company - Dak Roong State Forest Company - Koong Chieng State Forest Company - Chu Mo Protection Forest Management Board District agencies: - K’ Bang District: K. Bang District People’s Committee, K’ Bang district DONRE, K’ Bang district Agriculture Department, K’ Bang Forest Protection Department, K’ Bang district Committee for Ethnic Minority Affairs, K’ Bang district Women’s Union Commune agencies: - Kon Pne commune, K. Bang district: Kon Pne Commune People’s Committee (CPC), Kon Pne Women’s Union, Kon Pne Farmer Union; Kon Pne Commune Forestry and Agriculture Officer, Kon Pne Commune Cadastral Officer, Kon Pne communities. - Son Lang commune, K. Bang district: Son Lang Commune People’s Committee (CPC), Son Lang Commune Women's Union, Son Lang Commune Farmers' Union; Son Lang Commune Ranger, Son Lang Commune Cadastral Officer, Son Lang communities; - Dak Roong commune, K. Bang district: Dak Roong Commune People’s Committee (CPC), Dak Roong Women’s Union, Dak Roong Farmer Union, Dak Roong Commune Ranger, Dak Roong Commune Cadastral Officer, Dak Roong communities; - Ia Tul commune, K. Bang district: Ia Tul Commune People’s Committee (CPC), Ia Tul Women’s Union, Ia Tul Farmer Union; - Chu Mo commune, Ia Pa district: Chu Mo Commune People's Committee Others: - KfW 10 Project |
| Consultations with provincial agencies, forest owners, district and commune agencies in Phu Yen province | 14-15 December 2020 11-14 January 2021 | Provincial agencies: - Department of Agriculture and Rural Development (DARD) - Department of Natural Resources and Environment (DONRE) - Department of Planning and Investment (DPI) - Forest Protection Department (FPD) - Forest Protection and Development Fund (FPDF) - Committee for Ethnic Minority Affairs (CEMA) - Women’s Union (WU) Forest owners: - Krong Trai Nature Reserve - Son Hoa Protection Forest Management Board District agencies: - Son Hoa District: Son Hoa District People’s Committee, Son Hoa district DONRE, Son Hoa district Agriculture Department, Son Hoa district Committee for Ethnic Minority Affairs, Son Hoa district Women’s Union, Son Hoa communities. Commune agencies: - Suoi Trai Commune, Son Hoa district: Suoi Trai Commune People’s Committee (CPC), Suoi Trai Women’s Union, Suoi Trai Farmer Union, Suoi Trai communities. Others: - JICA2 project - Forest Inventory and Planning Sub-Institute for South Central and Highlands (Sub-FIPI) |

- The purpose of the Stakeholder Involvement Plan (SIP) for the project is to ensure long-term sustainability of the project achievements, based on transparency and the effective participation of the key stakeholders. The objectives include the following: (a) to identify the main stakeholders of the project and their basic roles and responsibilities in relation to the project; and (b) to take advantage of the experience and skills of the main stakeholders, safeguard their active participation in different activities, reduce obstacles in project implementation, and sustain gains after project completion. The approach is based on the principles of fairness and transparency in selection of stakeholders, ensuring consultation, engagement and empowerment of relevant stakeholders. This is to ensure: (i) better coordination between them from planning to monitoring and assessment of project interventions; (ii) access of information and results to relevant persons; (iii) accountability of stakeholders; (iv) implementation of grievance and redress mechanism; and (v) sustainability of project interventions after its completion.

- Stakeholder involvement will enhance the planning and management of landscape conservation in the Ba River basin. Their engagement will secure the conservation of globally and nationally important biodiversity within these landscapes, and mainstream biodiversity and sustainable forest management and resource use in the forest estate in the Ba River basin. Provincial DARD’s will be instrumental in establishing collaborative links with other provincial, district and commune level entities, CSOs, private sector, IPs and local communities, while provincial governments will facilitate coordination across sector and administrative levels. The Project may solicit the services of NGOs/Civil Society Organizations (CSOs) to implement project activities.

Identification of Potential Stakeholders

- The SIP involves the identification of stakeholders at the provincial, district and commune levels that would be engaged as project partners. These include government entities, CSOs and local and IP communities.

Role and responsibilities of key stakeholders and their Involvement Mechanisms and Strategies

- Mechanisms and strategies for stakeholder involvement will ensure that relevant shareholders: (i) receive and share information, (ii) provide inputs in the planning, design, implementation, monitoring and evaluation of project initiatives, and (iii) play a role in sustaining the initiatives during and after the closure of the project. Roles and responsibilities of main stakeholders of the project are summarized in Table 6 below. Early in project implementation, FIPI (with support from Provincial DARDs) will develop a more detailed Stakeholder Engagement plan that would ensure: (a) stakeholders’ involvement in project planning, implementation and monitoring; (b) stakeholders engagement in social and environmental screening and risk monitoring; (c) free, fair and transparent methods of information sharing; (d) implementation of gender mainstreaming strategy and action plan; (e) measures to empower stakeholders and potential project beneficiaries; and (f) disclosure and accessibility of information.

Table 7: Stakeholder Involvement Plan

| Key Stakeholder | Role and responsibilities / mandate | Proposed role in the project and involvement mechanism |
| --- | --- | --- |
| Forest Inventory, Planning Institute (FIPI), of Ministry of Agriculture and Rural Development (MARD) | MARD is a government ministry responsible for rural development and the governance, promotion and nurturing of agriculture and the agriculture industry in Viet Nam. MARD has the responsibility for exercising the State management over forest protection and development nationwide through its Viet Nam Forestry Administration (VNFOREST). MARD is responsible for management of national protected area (PA) and enforcing wildlife protection regulations. FIPI is a professional scientific and technical institution responsible for assisting MARD/VNForest in forest inventory, monitoring, planning and periodical reporting of forest status/change at both technical and policy making levels; providing capacity and services to provinces and forest owners on development of forest management planning and plans, including biodiversity survey. | MARD/FIPI is the designated Project Executing Entity and project owner. FIPI/MARD will be directly involved in all aspects of project implementation. MARD is responsible for project planning, coordination, management, monitoring, evaluation and reporting. MARD will assume all duties assigned to the Project Executing Entity and chair the Project Steering Committee and assume a leading role in engaging national and local level stakeholders in implementing project activities. MARD/FIPI will lead annual review meetings on project planning and reporting, and will appraise and approve all project related documents, including Annual Work Plans and Quarterly Work Plans and resulting. FIPI will play the role of project owner as regulated. FIPI will coordinate and oversee the implementation, management and monitoring of the project activities. MARD/FIPI will be the chief executing entity and coordinate the implementation of the project with the 2 provinces, ensure coordination of training and capacity building with MARD’s Forestry University of Vietnam to institutionalize the training activities as well as promote dissemination of best practices and replication. FIPI/MARD will ensure quarterly meetings, initiate inception workshop, communication strategy, community consultations and capacity building activities (trainings, workshops, field visits). |
| Viet Nam Forest Administration (VNForest), of the Ministry of Agriculture and Rural Development (MARD) | VNFOREST is an agency under the Ministry of Agriculture and Rural Development (MARD). VNFOREST performs the function of advising and assisting MARD in State management and implementing State management tasks on forestry in the country, and managing and instructing public service activities under the VNFOREST management scope. VNForest is the agency responsible for developing secondary legislation and the policy framework supporting Forestry Law 2017. VNForest administers the central Forest Protection Department (FPD) that has the mandate of performing the governmental management of forestry and formulating programs, plans for forest protection and management, forest fire safety, ensuring the compliance with law on forestry. VNForest also has a Department of Protection Forest and Special Use Forest management, which is responsible for biodiversity, HCVF and threatened species in Special Use and Protection Forests. | VNFOREST will provide guidance on state management on forestry issues, including in forest management, restoration, fire management and species conservation in SUFs and HCVFs. VNFOREST will be involved via mechanisms such as PSC meetings, inception workshop, communication strategy and capacity building activities (trainings, workshops, field visits). VNFOREST will also be involved in support for development of guidelines, manuals and best practices notes |
| The Vietnam National University of Forestry (VNUF) affiliated to MARD | VNUF is affliated to the MARD as per Government decision no. số 2699/QĐ-BNN-TCCB dated 30/6/2016. The University provides training to staff of the forest sector, economic planning sector, environmental sector etc. In terms of the forestry sector, it provides short and long terms training in forest GIS mapping, SFM and forest development planning, sustainable forest resource use, climate change adaptation, forest survey and monitoring, PFES planning and monitoring, integration of forest management and biodiversity conservation in socio-economic development planning as well as support for development of national standards and technical regulations and technical norms for AFM, forest ecology, etc. The University has a campus in the Central Highlands that is within the Ba River basin. | VNUF will participate and support the preparation/upgrading of curriculum and training materials and support the conduct of training activities as part of the intent to institutionalize the training within MARD to enable its replication elsewhere in the Central Highlands initially, and later in the rest of the country. |
| General Department of Land Administration (GDLA), of Ministry of Natural Resources and Environment (MONRE) | MONRE is a government ministry in Viet Nam responsible for state management of land, water resources; mineral resources, geology; environment; hydrometeorology; climate change; surveying and mapping; and management of the islands and the sea. The wide-ranging state management functions of MONRE include the management of air, land and water resources under the amended Law of Environmental Protection (2020), as well as biodiversity under Viet Nam’s Law of Biodiversity (2008). MONRE’s mandate also includes coordination with ministries, ministerial committees and government agencies in providing guidance for implementation of resource use, environmental protection and biodiversity conservation in the sector areas managed by these ministries and agencies. The GDLA is responsible for the development, dissemination and implementation of policy, regulations and strategy on forest land allocation and management. It also takes the lead in developing land management plans and guidelines for land allocation at district, provincial, and central levels and issues land use certificates and land development certificates. It monitors land use according to the land allocation plan. | The GDLA will be invited to work closely with FIPI on the implementation of relevant outputs under components 1 and 2. The GDLA will advise on land allocation for co-management, monitoring of allocation plans, etc. GDLA. MONRE will participate in PSC meetings, capacity building activities (trainings, workshops, field visits) and providing guidance on forest allocation for co-management. |
| Departments of Agriculture and Rural Development (DARD) of Gia Lai and Phu Yen Provinces | DARD is a specialized agency under the provincial people’ committee, (PPC): advise and assist PPC in state management function on agriculture, fisheries and aquaculture. DARD also has considerable experience of managing PAs. The provincial DARD departments have responsibility for overseeing implementation of forest management on the ground. | DARD is the primary specialized management government partner of the project with key partner support being provided by DONRE. DARD will participate in the provincial Project Management Team, and in development of an integrated vision, and detailed planning of the project activities, including forest restoration areas, EIA, guiding sustainable livelihood activities, including tourism, etc. DARD will be involved via mechanisms such as PSC meetings, PMU quarterly meetings, inception workshop, communication strategy, community consultations and capacity building activities (trainings, workshops, field visits) |
| Departments of Natural Resources and Environments (DONRE) of Gia Lai and Phu Yen Provinces | DONRE is responsible for managing natural resources and environment at the provincial level. Responsibilities include land administration, pollution monitoring. DONRE plays an increasing role in supporting biodiversity management and in assisting PPCs in managing national park/nature reserve. | DONRE will participate in the Project Management Team, and in development of an integrated vision, mapping of natural resources and detailed planning of project activities, including HCV set-aside areas, forest restoration areas, EIA, guiding sustainable livelihood activities, including tourism as well as provide guidance of policy related issues. |
| Departments of Planning and Investment (DPI) of Gia Lai and Phu Yen Provinces | DPI supports the provincial people’s committee in the field of planning and investment, including the provision of general advice on strategies and plans on socio- economic development, on mechanism and policies for general economic management and some specific fields, on domestic and foreign investment, etc. | DPI will be a beneficiary of the project results, specifically related to integrated vision on land and natural resources use, sectoral responsibilities to mainstream forest biodiversity conservation into strategies and planning in line with sustainable forest management. DPI will provide guidance on integration of conservation outcomes in provincial and local level planning, supporting the inter-provincial coordination and ensuring cost-effectiveness of interventions |
| Department of Culture, Sport and Tourism (DCST) of Gia Lai and Phu Yen Provinces | DCST is responsible for public services on culture, sports and tourism of the province. DCST is also responsible for provincial level tourism development. | DCST will support tourism related initiatives, including private-partnerships, and models for sustainable tourism practices. DCST will support training, skills development and interpretation of policies related to tourism development DCST will be involved via mechanisms such as PSC meetings, inception workshop, communication strategy and capacity building activities (trainings, workshops, field visits). |
| Provincial People’s Committees (PPCs) in Gia Lai and Phu Yen Provinces | PPCs are headed by a Chairman and supported by Vice-Chairmen for each major sector including a Vice Chairman for agriculture and forestry. Under Viet Nam’s decentralization policies, PPCs play a major role in provincial development and sector planning and implementation, including on environmental management and biodiversity conservation. PPCs also have an important role in ensuring that biodiversity is integrated into sectoral plans and programs at the local level. Specifically, they are responsible for coordinating the biodiversity conservation activities of various line departments at the provincial (and city) level. PPCs currently have management responsibility for those PAs – SUFs, Integrated Water Management and MPAs - that lie entirely within their provincial territory. | The PPCs in Gia Lai and Phu Yen and their subsidiary agencies at the provincial level will be key partners in project planning and implementation, providing information, support and co-financial contributions. The PPCs will coordinate and oversee implementation, management and monitoring as well as provincial level budgeting of project activities assigned to PPCs, including: (i) review work plans and approve budgets; and (ii) preside over inter-agency coordination meetings including district authorities as well as sectoral stakeholders. The PPCs in Gia Lai and Phu Yen will be involved via mechanisms such as PSC meetings, PMU quarterly meetings, inception workshop, communication strategy and capacity building activities (trainings, workshops, field visits). The PPCs will ensure that co-financing activities, including the KfW funded projects are coordinate closely with the GEF project to ensure synergies, complementarity of activities and collaboration. |
| District People’s Committees (DPCs) (District Administrations of priority districts) in Gia Lai and Phu Yen Provinces | District administrations (including Divisions on Agriculture, Forest Ranger, Natural resources and environment) are key local-level stakeholders in forest management. District PCs play a key role in supporting local socio-economic development. Being the closest state organization to local communities, they play an important role in overseeing and supporting development activities in their districts. Thus, DPCs have a key role to play in terms of ensuring environmental sustainability and avoiding overexploitation, particularly in relation to activities such as agriculture (including rice and other forms of agricultural production), fishing, aquaculture, as well as industrial development and tourism activities. | DPCs will be key project partner at the project site level, particularly in relation to implementing activities targeting at reducing threats to biodiversity arising from current economic development and livelihood practices. DPCs will be involved via mechanisms such, community consultations, supporting the communication strategy and participate in the capacity building activities (trainings, workshops, field visits). |
| Commune People’s Committees (CPCs) in selected communes in Gia Lai and Phu Yen Provinces | CPCs are key local authorities in managing land use and forest activities. They are responsible, inter alia, for allocating forestland under their control for co-management by communities. CPCs play a key role in supporting local socio-economic development in agricultural production, fishing, aquaculture, industrial development and tourism activities and in overseeing and supporting development activities in their communes. | CPCs will be key project partners at the project commune level, particularly in relation to implementing activities in supporting forest co-management, livelihood and value addition programs. CPCs will supply key baseline data at the local level, such as numbers of households, land use types, key land degradation issues and forest use data. They particularly will participate in the allocation of forestland under their control to communities for co-management and implementation of activities targeted at improving forest conservation outcomes as well as improved livelihood in selected communes and households. |
| PA Management Boards (PA MBs) and Protection FMBs | PA and PF MBs are designated authorities responsible for the management of the existing formally established protected areas, including Special-Use Forests, Protection Forests under forest protection and development regulations, and nature reserves under provincial regulations. | PA MBs and PF MBs will be directly involved with the planning, implementation and monitoring of project activities in their respective PAs, national parks/nature reserve/forest areas through providing information, identifying priority issues at each site, and participating in priority interventions on strengthening conservation of forest biodiversity, including through targeted livelihood activities as relevant. PA MBs will also support strengthening conservation activities in identified HCV landscapes. PF MBs will be directly involved in preparation of SLM plans, monitoring of forest trends and threats etc. |
| Local communities / local resource users | Local communities are custodians, primary users and managers of the landscape resources and key target groups for all components of the project. They are engaged in agricultural production, agro-forest, eco-tourism activities, NTFP collection within the national parks and nature reserves. They are the most critical stakeholders for the success of the project. | Local communities will participate in the implementation of project activities and be direct beneficiaries of project investments in the conservation of forest biodiversity and sustainable land and forestland management in national parks and nature reserves. Appropriate land and natural resources regulations in different zones of the national parks and nature reserves will be formulated with their full participation and agreement, to ensure both continuation of income from traditional or suitable alternative livelihood activities in combination with strengthened consideration for forest biodiversity conservation. Specifically, they will engage in: (i) preparation of community forest management plan, including mapping of commune resources, identifying threats and responses to threats, identifying forest management plans and livelihood activities, (ii) the implementation of community forest management, including though relevant community groups and micro-revolving funds, and (iii) training programs aimed at improving resource use and livelihood development, etc. |
| Ethnic minority groups | Ethnic minorities include indigenous groups living for many generations in national parks and nature reserves, each having a different history, traditions, and diverse material lives. They mainly rely on natural resources, especially forests, for their livelihoods, and as such are one group linked to the degradation of natural resources and biodiversity. In many areas, poverty rates are significant. Communities in buffer zones of PAs include the following ethnic minority groups: Kon Ka Kinh National Park’s buffer zone covers 23 village communities of 7 communes across three districts (Mang Yang, KBang and Dak Doa), which are mainly inhabited by the Bana ethnic minority group. They have a long history of dependence on extraction of forest resources for their livelihoods, which continues to place pressures on forest protection and management due to illegal encroachment, poaching and firewood collection. Krong Trai Nature Reserve’s buffer zone covers 22 villages across 5 communes of Son Hoa district, Phu Yen province, which are inhabited by the largely Ede ethnic minority group. The traditional cultivation is mostly monoculture, micro-scale and scattered. They have shifted to paddy rice cultivation in recent years, but the productivity remains limited. Kon Chu Rang Nature Reserve’s buffer zone covers six villages in two communes of K’Bang district, which are mainly inhabited by Ba Na ethnic minority people. Crop production— including upland rice, paddy rice, cassava and maize—is the main source of local income. Recently, coffee plantations have just been established and expanded, but mainly by immigrants and/or employees of state-own forest companies. In addition, local livelihoods also depend heavily on forest resources, including shifting cultivation, illegal logging, poaching and extraction of NTFPs. | Ethnic minorities will directly participate in decision-making processes at the commune level, development of community forest management plan, implementation of livelihood initiatives and in benefit sharing. Specific investment for households of ethnic minorities will be instituted through the community forest management process to ensure strengthening their current livelihood and sustainable forest management. |
| Government and academic research institutions | Several universities/institutes at national and provincial levels have strong environment research units with knowledge and experience relevant to this project. The Viet Nam Academy of Natural Science & Technology (VAST), conducting multi-disciplinary studies in socio-economic development, ecology and environmental management, policy analysis, culture. The Research Institute for Forest Ecology and Environment (RIFEE) is a research institution under MARD’s Viet Nam Academy of Forest Science (VAFS) focusing on sustainable uses of forests and forestland as well as monitoring and assessment of forest biodiversity. Other universities and institutes, for example, Viet Nam National University of Forestry – Gia Lai Branch, Tay Nguyen University, Viet Nam Academy of Forest Sciences in the South Central and Central Highlands, and the Central Highlands Institute for Agriculture and Forestry Sciences (WASI) are responsible for undertaking academic research and technological transfer in agriculture, forestry, livestock, biotechnology, protection of ecological environment for the development of agriculture and forestry. | Appropriate partner organizations will be identified during project implementation, as relevant and in line with their thematic focus and experience. Research institutions will be involved in consultancy activities, including on legal-regulatory framework, field studies on mapping and inventory, forest biodiversity monitoring for the benefit of formulating informed recommendations to the project and its national and local government partners. Academic research institutions will be involved via mechanisms such as inception workshop, Memorandum of Agreements (MOA) for the implementation of defined activities, community consultations, communication strategy and capacity building activities (trainings, workshops, field visits). |
| Civil Society Organizations | Several social organizations are working on sustainable forest management (SFM) and biodiversity conservation issues in Viet Nam, including both international NGOs and national social organizations. | Some social organizations may be engaged in project activities, such as collecting baseline biodiversity data, community engagement, participatory monitoring, and project education and awareness activities. Civil Society Organizations will be involved via mechanisms such as community mobilization, conduct of training, awareness and communication support, and capacity building |
| Mass media organizations, including national and provincial television and radio networks, private communication agencies, printed media, and online media. | Mass media has the responsibility for the dissemination of information and awareness on state policies, strategies and plans to the general public at the national and regional level through mainstream channels of television, radio and print. | Partnerships with key media organizations will support dissemination of information at global, regional and national levels, including on project workshops and seminars, training and capacity building events as well as results and best practices from targeted activities at the national level and in the project site. Approaches will include direct communication, press meetings and press releases, field visits, etc. Mass media organizations will be involved via mechanisms such as inception workshop, communication and awareness, knowledge management and dissemination of best practices |
| Agricultural Services Cooperatives | These entities entity have an enterprise legal foundation operating under the 2012 Vietnam Law on Cooperatives. This stakeholder plays an important role in the agricultural commodities supply chain in the context of fragmented and small production in rural and mountainous areas in Vietnam. They play a role as agricultural input providers including seeds, fertilizers, irrigation services, pesticides and herbicides; commodities collectors at harvest seasons, pre-processors, transportation, products promotion marketing; products legal compliance ensures; technical services and trainings to farmers; and sharing of knowledge. There are potential Agricultural Services Cooperatives in Gia Lai and Phu Yen for project engagement in the implementation process. In Gia Lai province, there are more than ten agricultural services cooperatives operating in Gia Lai province Quang Vinh Medical Herbs Cooperative, Agricultural Doan Ket K. Bang Cooperative, Kon Pne Cooperative (providing fertilizers, pesticides and seeds to farmers) Mang Yang Agricultural Service Cooperative producing some medical herb products with brand An Binh Phat. There are also BB Cooperative in Son Lang Commune that specializes in greenhouse plant production Chop Chai Cooperative in Suoi Bac commune which specializes in livestock production and distribution. | These cooperatives will be actively engaged in supporting the respective communes in agricultural and other crop production system in providing technical support, training and skills development; access to markets, product development etc. |
| Local, national and international NGOs | NGOs play an important role in a variety of sectors like biodiversity conservation; sustainable forest management, minimizing impacts from development, pollution abatement, improving rural livelihoods, as well as addressing the needs of local communities, including on themes like policy and legislation, research, education and awareness raising. Relevant local, national and international NGO active in the project-relevant fields of protected area management, sustainable livelihood support with links to the project’s thematic and/or spatial focus include the following: PRCF, PanNature GreenVIET, Tropenbos | Appropriate partner organizations will be identified during project implementation. The project will build on and collaborate with relevant initiatives conducted by local and international NGOs in relevant conservation, monitoring, livelihood development, community-based natural resources management, benefit sharing and other related activities. Local, national and international NGOs will be involved via mechanisms such as inception workshop, Memorandum of Agreements (MOA) for the implementation of defined activities, communication strategy and capacity building activities (trainings, workshops, field visits). Local NGOs may also be engaged as third parties in overseeing and support community programs in terms of livelihood improvement, ecotourism, community forest management etc. |
| Private Sector – Private Enterprises | Private Enterprises play an important role in the development and implementation of livelihood initiatives (e.g., medical planting, eco-tourism, community tourism, agro-forest modalities) at commune and district levels. e.g. Truong Sinh Group (medicinal plant products) Thuạn Thien Phuc Company (NTFP and agro-forestry) Thuạn Thien Phuc Company Ltd (forest livelihoods) Other wholesalers and retailers for product marketing and promotion | The project will engage the private sector enterprises, wholesalers and retailers to engage the private sector in the proposed project activities on livelihoods development and diversification. During the project implementation, these private sector entities operating within the target landscapes, including additional companies responsible for management of production forests, will be engaged in order to identify additional potential partnerships. Private sector will be involved via provision of technical support to local communities and market and product information and promotion, and retailers and wholesalers to provide market access and sales promotion |
| Private Sector – Tourism groups | Hoteliers, tour operators and service providers are engaged in tourism related activities within the project areas | These groups will be engaged to support the community tourism initiatives by (i) providing training for community members to establish ecotourism products and services; (ii) build private-community partnerships to facilitate community participation in ecotourism activities by identifying and design appropriate tourism locations and products, provide information on potential options, assist in market access, etc. |
| Private Sector – Other Industries such as: Industrial Producers GHG Producers Tourism Industry Aquatic resource producers | In terms of dependents on the forests, these entities use water for the forests (e.g., agricultural, forest and aquaculture products processing industry, textile and garment industry, beverage industry, building material industry, machine equipment production industry, pulp and paper manufacturing process industry, mining, building material industry, oil and gas refining companies, thermal power plant, ecotourism, hospitality or entertainment services and aquatic farming entities) provide an opportunity to testing small scale PFES operations, even though the scope might be limited | The project will undertake evaluation of potential for 1-2 new options for PFES through assessment, consultation, etc. to ascertain options for collaboration |
| Other donor agencies | Several donor organizations (or development partners), including KFW, JICA, WB/IDA, IDH, SNV, and others, have on-going projects either in the project site or covering themes of interest to the project. | Relevant donor organizations will be engaged as partners to facilitate coordination and collaboration at national and landscape levels, to ensure convergence of ongoing programs. The Project will maintain close relations with all relevant donors, as appropriate, invite them to participate in project related meetings and workshops as relevant. Other donor agencies may participate in project oversight and guidance structures during implementation, either through the project steering committee, or via technical working groups leveraged to guide the project. Other donor agencies will be involved via mechanisms such as inception workshop, PMU quarterly meetings, communication strategy and capacity building activities (trainings, workshops, field visits) and coordination of actrivities. |
| International Tropical Timber Organization (ITTO) | ITTO are key partners in SFM and forest management for natural forest conservation, landscaope conservation, SFM, provision of technical axpertise, knowledge sharing and exchages in the region that is very relevant to the GEf 7 project | The project will draw on information, best practices and guidance from ITTO to facilitate efforts to conserve biodiversity and ecosystem services in the forested catchments of the BA river through invitation to participate in stakeholder consultation workshops, lessons sharing events and other relevant communication methods. The GEF 7 project will actively make use of SFM guidelines, monitoring guidelines for SFM, manual for forest restoration and other information available from ITTO. The project will also assess means to access technical expertise through ITTO asd deemed appropriate |

- Highlight here specific actions on south-south and triangular cooperation to present opportunities for replication in other countries, and to facilitate dissemination through global ongoing South-South and global platforms, such as Africa Solutions Platform, ITTO, the UN South-South Galaxy knowledge sharing platform and PANORAMA. In addition, to bring the voice of Viet Nam to global and regional fora, the project will explore opportunities for meaningful participation in specific events where UNDP could support engagement with the global development discourse on forestry and biodiversity. The project will furthermore provide opportunities for regional cooperation with countries that are implementing initiatives on forestry and biodiversity in geopolitical, social and environmental contexts relevant to the proposed project in Viet Nam.

Gender equality and Women’s Empowerment:

- Women’s roles in forestry value chains in Viet Nam tend to be those associated with the well‐being, and food and energy security, of their rural households. However, women are often disadvantaged in terms of their access to, and control over, forest resources and in the availability of associated economic opportunities along those value chains (processing, marketing, etc.). While the Government of Viet Nam has developed several laws and policies to promote women’s rights, women are still structurally disadvantaged in areas like access to credit, land and information. Within the Central Highlands and project landscape, women and men have different roles, rights, responsibilities, knowledge, management of and access to forests. Women’s roles are linked to fulfilling subsistence needs for fuel wood, medicinal products, wild foods, fodder for livestock and selling small quantities of fuel wood in local markets. In comparison, men’s roles are more linked to timber and NTFP for commercial purposes. The differing roles of men and women in use of forests mean that potential restrictions on access to protected forests could particularly increase women’s labor and time demands. Forestry is one of the sectors where the workforce consists mainly of women. Women carry out most of the forestry activities and more women participate in processing and agro-product sales than men. However, women’s representation in forestry governing bodies tends to be low and gender disparities exist across multiple layers of government.

- The ability of men and women to participate in and benefit from sustainable forest management and biodiversity conservation is complex and gender-based inequalities persist for a range of cultural, socio‐economic and institutional reasons. Women’s time and energy are tied with agricultural work, and they have greater responsibilities in family and household care, meaning that they have limited time to engage in training and skills development compared to men. Ethnic minority women are bound by existing customs and traditions that often restrict access to knowledge and participation in decision-making – and there is evidence from REDD+ assessments that ethnic minority women lack self-confidence on technical issues such as climate change and REDD+. Women’s rights over (forest) land remain less than men’s due to the Vietnamese system of household registration requiring a “household head’’, which tends to be a man except where in cases of women-headed households (due to widowhood, abandonment or divorce). Although the law requires Land Use Right Certificates, including those for forest land, to bear the names of both husband and wife, land use decisions are most often made by men. Allocation of lands to communities has therefore provide more benefits for men compared to women.

- The project will provide targeted support to empower women in the forest sector, including support for women entrepreneurs, access to finance, etc. Women will be clearly targeted as project beneficiaries and a target for at least 50% women beneficiaries has been set. Specific gender mainstreaming opportunities that the project will explore include targeted livelihoods development opportunities for women in forest-dependent communities including the establishment of grassroots women’s groups; the empowerment of women to participate in governance and decision-making bodies including the setting of mandatory gender participation targets; ensuring adequate engagement and participation of women in stakeholder consultations (including FPIC as needed) including separate consultation processes and meeting timing/location decisions that allows for women’s engagement and provides a supportive environment for their inputs (e.g. separate consultations on technical issues where there awareness or self-confidence may be lower than men); targeted training, awareness-raising and/or capacity development for women including on biodiversity monitoring, planning and PFES (these opportunities will be extended to women’s groups and relevant CSOs operating in the project landscape); integrating women’s rights and safeguards into the community co-management model for allocation of forestlands to village communities to ensure benefits flow equally to men and women; and ensuring that the PMU and project partners receive gender mainstreaming awareness training.

- A detailed gender analysis was undertaken during the PPG stage. The analysis helped assess opportunities to enhance the status of women with respect to forest-sector activities, to address the gender gap in the sector and to help design project activities and indicators that will ensure women’s full participation as beneficiaries (and deliverers) of technical cooperation and knowledge building efforts. Consultation sessions were held to obtain views and inputs of a wide range of local stakeholders, including women, to develop project activities and to inform a robust stakeholder involvement plan with full gender considerations. A corresponding gender mainstreaming plan for the project has been developed (see Annex 10). Gender-disaggregated targets and indicators are within the project results framework. Gender-responsive evaluation and adaptive learning is also included.

- Based on the gender analysis, the Gender mainstreaming in the project will be addressed (see Annex 10) through the following actions:

- Ensure that project materials, including meeting agendas, reporting templates, communications materials, and all written policies include gender and social mainstreaming.

- Create and require minimum standards for planning teams, including representation from multiple gender and social groups and/or tasking of planning team members to speak for vulnerable peoples.

- Capacity building and training for project staff and planning team facilitators, staff of Women Unions, Youth Unions to better engage multiple gender and social groups               .

- Support research and mapping of: (i) current gender roles and how they have changed between generations in each of the development sectors (forest management, NTFP collection, grazing, and tourism, etc.; (ii) gender and social group uses and use patterns of land habitats; (iii) market access by gender; (iv) mapping of the economic sector by gender and social group; and (vi) applying a gender and socially inclusive lens to all research plans and priorities to ensure that multiple groups’ data needs are filled.

- Invest in staff to enable adequate connections with multiple groups. Instead of general community meetings, meetings with (i) women’s groups; (ii) men’s groups; (iii) youth groups; and (iv) individuals with access to or influence over vulnerable people (e.g., IP leaders, landowners, or church leaders).

- Capacity building and training for project staff and planning team facilitators to better engage multiple gender and social groups.

- Apply a gender and socially inclusive lens to every meeting, report, plan, and activity.

- Apply sex disaggregated targets and baselines where appropriate, as part of project monitoring plan.

- Conduct economic and social analyses of proposed land and forest plans resulting from the project, and all other outputs (such as proposed protected areas and implementation plans for best practices).

- Implement the Communications Strategy, including holding multiple, targeted meetings by disaggregated groups.

- Make better use of digital platforms in order to create oral/audio content, with less emphasis on writing to better communicate with IP groups, rural women, farmers, and youth.

- Incorporate gender and socially sensitive indicators and collect sex disaggregated data for monitoring and evaluating project results.

- Recruitment of gender specialist to facilitate the implementation and monitoring of the gender plans and for capacity building and training of key implementing agency staff.

Innovativeness, Sustainability and Potential for Scaling Up:

Innovation

- The integrated approach being implemented through the project, will provide an innovative example that is expected to: (i) generate important lessons for other districts/provinces in the country as well as in other areas of Southeast Asia, and (ii) build national expertise in new areas. The project will illustrate a new approach to landscape level planning as it brings together the various stakeholders within Ba River basin landscapes and seeks to integrate this into planning at both a finer scale (practical FMU planning and implementation under Component 2) and broader planning processes (via technical inputs for provincial master plans and spatially explicit district land use plans). Jurisdictional planning processes under the 2017 Planning Law are in their first rotation, with provincial plans in the demonstration landscape currently under development for 2021-2025. The project has been developed to integrate with the timing of these baseline processes and support the monitoring of plan implementation and their mid-term review and adjustment for 2026-2030 – this is attempting to be innovative in the way it aligns to the baseline processes to ensure that the project will be able to integrate with these government efforts. Similarly, the project will seek to demonstrate greater use of available real-time remote sensing and GIS technology at provincial and district levels, to facilitate greater awareness and capacity in these technologies, and increase their use in site-based and broader landscape and jurisdictional decision-making. While this technology and remote-sensed data is now readily available, to date there is limited application of its use at sub-national levels.

Sustainability

- This project builds on a strong baseline that will support its sustainability and long-term ownership by government and local communities. First, an extensive policy and institutional framework for forest management and jurisdictional planning already exists, and the project has been developed to integrate, strengthen capacity of forest owners and provincial adminstrators on provincial master planning, district land use planning, and SFM planning. Second, there is a strong commitment from Government to address forest and land degradation issues in the Central Highlands region, as this is one of the target areas of investment in the country that hosts still intact forests and will build on the extensive activities taking place under the baseline scenario. Many of the industries are dependent on the ecosystem services that forests provide, e.g.,, downstream agriculture is reliant on forests for flood prevention. Third, the project supports financial sustainability, through a number of means well as through the extension of the PFES scheme.  In terms of sustainability and institutionization of the training and capacity building, the project will work closely with the Vietnam National University of Forestry (VNUF) that is affliated to MARD. The project will provide technical support to assist the VNUF to develop training curriculum, training materials, upgrade the skills of trainers with the VNUF and initiate the training to build and institutionalize the training within VNUF to ensure sustainability and potential for expansion of training to other provinces as well. Institutional and financial sustainability is addressed based on evaluation of gaps in policy and and lack of best practices in forest management.  In terms of the former, a number of activities have been integrated into the project design, including in particular (i) establishment of inter-provincial platforms (Output 1.1); (ii) development of spatially explicit tools and development of roadmap for conservation in the BA River (Output 1.2); (iii) capacity and tools for monitoring and assessing forest changes using remote sensing data (Output 1.3); (iv) training and capacity development of forest managers in monitoring and enforcement and institutionalization of all training within the Institute of Forestry Ecology and Environment of the Vietnam National University of Forestry that is affiliated to MARD (Output 1.4); (v) further expansion of community forest management (Output 2.4) the lessons of which can serve as best practice; (vi) development of technical manual for SFM implementation, monitoring and enforcement that can be used nationally (Output 3.1), etc. In terms of financial sustainability the project will support (vii) enhancing the effectiveness of existing PFES mechanisms and linking investments to direct conservation outcomes, and investigating options for new PFES opportunities (Output 2.7) and (viii) in keeping with National Forest Development Strategy (2021-2030) pilot efforts to promote Forest Management Boards as non-business public service entities so that they can move towards attracting public and private funding that can provide some sort of financial autonomy (Output 3.1).

- In terms of financial sustainability on the longer-term for activities being supported under the project related to implementation of policy and legislation, this will continue to be financed through budgetary resources that are mandated under different Circulars and Decrees as described herewith: (i) Decree 502/2020 for developing Phu Yen provincial master plan and Decree 1015/2020 for Gia Lai Provincial Master Planning mandates funding from central and provincial budgetary resources; (ii) The Department of Investment Planning is mandated under Circular 113/2018 (norms for planning) and Circular 08/2019 (financing of planning services) to provide financing to DARD and FPD for implementation of activities under Forestry Act 2017 in relation to SFM; (iii) Circular 28/2018 and Decree 156 mandates allocation of funding from state (for investment activities) and provincial (for regular activities) budgets, including SFM and monitoring.  The Provincial Peoples Committee is mandated through these instruments to allocate funds for these activities; (iv) Circular 04/2018 mandates the Ministry of Finance to guide the management and use of PFES funds; (v) the financial sustainability of provincial stakeholder platforms for integrated planning of provincial master planning is required as condition for implementation of Decree 37/2019 (provincial master planning) and condition for implementation of Decree 156/2018 (and its amended Decree 83/2020) in relation to forest master planning; and (vi) Decree 60/2021 guides the enhancement of financial autonomy for public non-business units such as the Forest Management Boards.  The project intends to implement some of these specific instruments, test their effectiveness and provide guidance for replication.

- The key gaps in the current process are capacity and coordination among all the spheres of government and stakeholders to recognize the value of forest resources and the ecosystem values they provide, both of which this project specifically addresses. The project aims to empower local stakeholders (district authorities, private and State-owned Forest managers, communities, PA managers) to become custodians of important natural resources and build their engagement, capacity and awareness of benefits flowing from sustainable forest management, which will support their commitments after the project has closed.

Potential for Scaling-up

- The project will present multiple opportunities for scaling-up sustainable forest management across the landscape. First, the project is working on the ground in only two of the five provinces within the Ba River basin. While it will be working in areas covering the majority of the basin, there will be opportunities for replicating and scaling up the lessons and good practices of the project in forested districts in Kon Tum, Binh Dinh and Dak Lak provinces, which neighbor Gia Lai and Phu Yen provinces. This will in fact be critical in the longer-term, to avoid “leakage” of forest resource (mis)use from the districts of Gia Lai and Phu Yen province that will be under SFM and improved resource management, as key large forest blocks within the Ba River landscape stretch across administrative boundaries. Districts targeted for replication in other provinces will include Vinh Thanh and Van Canh districts in Binh Dink province, M’Drak and Ea Kar districts in Dak Lak province, Kon Plong district in Kon Tum province, and Ba To district in Quang Ngai province. To support replication and up-scaling in key districts in neighboring provinces, Output 3.2 provides a range of activities to be undretaken, including communication programs to enhance awareness of conservation outcomes and actions; documentation and dissemination of case studies, best practices and lessons learned from the project; development of policy guidance notes that addresses current constraints and gaps in existing policies and legislation; technical reports, publications and other knowledge management products (including in local languages and accessible to Ethnic Minorities (EMs) documented and disseminated via mass media; documentation of Ethnic Minority cultural system related to natural resources management and disseminated to constrain or avoid the erosion of Indigenous Peoples’ cultures and justify increased public investments support to ancestral domains; national and provincial workshops to facilitate dissemination of field lessons and help inform legal and policy reform; institutionalization of some of the best practices through promotion of policies and guidelines in order to secure support for replication and up-scaling; inclusion of public engagement pages on national and provincial websites and social media platforms that link to information about the project and its products, preparation of a replication and scaling up strategy based on project experiences and best practices for promotion of integrated landscape management, including institutional, financial and resource requirements, partners and coordination arrangements; a MARD based Implementer’s Manual and Lessons Learned guide and end of project national seminar on outcomes and replication for integrated biological landscape management practices in Viet Nam.  In addition, the project will support study tours bringing relevant provincial and district officials to visit project activities in the project’s pilot districts. The project’s work to better integrate biodiversity and maintenance of ecosystem services through SFM into macro-level planning processes will have implications for forest management at the national level, while targeted policy and regulatory improvements will strengthen prevention and enforcement of forest offences across Viet Nam. Similarly, the development of guidelines related to project approaches and lessons will support provincial and national uptake of project outputs and build the overall impact of GEF investment. As part of the scaling up, the project will support preparation of a replication, scaling up and long-term sustainability strategy/plan based on project experiences and best practices for promotion of integrated landscape management, including institutional, financial and resource requirements, partnerships and coordination arrangements. The preparation of the strategy/plan will entail an in-depth analysis of financial options for sustaining the policy dialogue and reform. In particular, this strategy/plan will provide overall guidance (based on on-the-ground application and review of existing regulations and guidelines for effective integration of biodiversity and sustainable forestry outcomes in implementation of the Forestry, Biodiversity and Planning Acts) for validation, update and policy reforms related to these Acts, The strategy/plan will be supported by the: (i) development of guidance documents that addresses current constraints and gaps among forest managers and management boards in implementation of existing policies and legislation (including in particular in relation to SFM, integration of biodiversity conservation outcomes in forest and provincial level planning and sectoral and provincial/national coordination and monitoring and evaluation as discussed in detail under Paragraph 132 and 133 above. Based on the above, the strategy for replication, includes the following: (ii)  development of policy notes for dessimination and discussion with key policy makers at national and provincial level to promote provincial and forest master planning change; (iii) review and dialogue of effectiveness of implementation of existing policies and decisions to identify key constraints and weakenesses in order to encourage revisions and updates; (iii) VNForestry and MARD to testing and refining guidelines for monitoring of SFM implementation, in particular to assess changes in forest condition that will be developed and promoted nationally; (iv) based on the learning from the project, preparation of a replication and scaling up strategy with the support of VNForest and MARD for wider application; (v) development of a technical manual for forest managers on planning, implementation and monitoring of SFM plans that integrate biodiversity conservation, climate resilience, sustainable resource use, and co-management; and (vi) institionalization of training within the Vietnam National University of Forestry (VNUF) that is affliated to MARD (as discussed in paragraph 132 above).

- Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): SDG 15 Protect, restore, and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss |  |  |  |  |
| --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome (UNDAF/CPD, RPD, GPD): Outcome 2 - People in Viet Nam, especially those at risk of being left behind, will benefit from, and contribute to safer and cleaner environment resulting from Viet Nam’s effective mitigation and adaptation to climate change, disaster risk reduction and resilience building, promotion of circular economy, the provision of clean and renewable energy, and the sustainable management of natural resources. |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline Must be determined during PPG phase | Mid-term Target Expected level of progress before MTR process starts | End of Project Target Expected level when terminal evaluation undertaken |
| Project Objective: To conserve forest biodiversity and maintain or improve the flow of ecosystem services through sustainable forest management embedded in a coordinated landscape-level approach across Ba River basin | Mandatory Indicator 1: Number of direct beneficiaries disaggregated by gender (GEF Core Indicator 11): | 0 | 1,000 individuals (500 women) Note: At least 1,000 individuals, directly benefit through sustainable forest resource management, sustainable use of NTFPs and livelihood improvement approaches (at least 500 women and 500 men beneficiaries, of which at 30% represent IPs) | 3,000 individuals (1,500 women) Note: At least 3,000 individuals, directly benefit through sustainable forest resource management, sustainable use of NTFPs and livelihood improvement approaches (at least 1,500 women and 1,500 men beneficiaries, of which at 30% represent IPs) |
|  | Mandatory Indicator 2: Number of hectares of Terrestrial Protected Area expanded or under improved management effectiveness. Improved management effectiveness measured by improvement in METT in selected PAs, namely, Kon Ka Kinh National Park, Kon Chu Rang Nature, and Krong Rai Nature Reserve. ( GEF Core Indicator 1) | PA expanded: 0 HA PA brought under improved management: 0 HA Existing PAs METT baselines: Kon Ka Kinh National Park – 48 Kon Chu Rang Nature Reserve -44 Krong Rai Nature Reserve - 35 | (i) PA expanded: 0 HA (ii) PA brought under improved management: 0 HA (At least a 10- point average increase in METT scores from baseline) Kon Ka Kinh National Park – 58 Kon Chu Rang Nature Reserve -54 Krong Rai Nature Reserve - 45 Note: Survey and demarcation of additional forest company lands into Kon KA Kinh NP and Kon Chu Rang NR to enhance connectivity | (i) PA expanded:10,000 HA (ii) PA brought under improved management: 71,106 HA (At least a 25 - point average increase in METT scores from baseline) Kon Ka Kinh National Park – 73 Kon Chu Rang Nature Reserve -69 Krong Rai Nature Reserve - 60 Note: At least 10,000 hectares of forest lands added to existing Kon Ka Kinh NP and Kon Chu Rang NR to enhance connectivity |
|  | Mandatory Indicator 3: Total HA of forest and forest land restored GEF Core Indicator 3 | 0 HA Note: Remaining HCV forests under threat of further fragmentation, particularly in Central Highlands | 200 HA | 500 HA |
|  | Mandatory Indicator 4: Area of landscape under improved management practices (excluding protected areas) GEF Core Indicator 4 Sub-Indicator 4.1: Area of landscapes under improved management to benefit biodiversity in Forest Management Units This is measured by the following: (i) Provincial multi-stakeholder coordination platform defines protocols for improving conservation practices within landscape (ii) Commitment of provincial government for support for planning and funding for improving conservation outcomes within forested landscape; (iii) Enhanced SFM plans and budgets allocated for improving conservation outcomes Production and protection Forests; (iv) Implementation of Community-based Forest management in Commune managed lands (v) Agreement of enhancing connectivity in key high biodiversity areas; (vi) Monitoring system operational to monitor improved conservation outcomes Sub-Indicator 4.3 Area of landscape under sustainable land management in production systems This is measured by: a) Commitment of Commune People’s Committee to support biodiversity-friendly practices (b) Commitment of local communities to implement improved conservation practices (c) Implementation of co-management agreements by local communities (d) Monitoring system to monitor improved outcomes | Forest lands under production systems in forest management units and commune agriculture and forest management areas do not adequately consider biodiversity-friendly practices and SFM and SLM programs do not adequately integrate conservation outcomes | Total area under improved management is 25,000 hectares comprising the following: Sub-Indicator 4.1: Areas identified for integration of improved conservation practices in sustainable forest management strengthened and approved and budgetary resources allocated from provincial governments and at least revised SFM management for improved conservation outcomes prepared and approved, and funds allocated to initiate conservation-relation activities in around 20,000 hectares of forest management units Sub-Indicator 4.3: Commune People’s Committees initiate biodiversity-friendly activities in around 5,000 hectares of agricultural and commune managed forest lands | Total area under improved management is 74,485 hectares comprising the following: Sub-Indicator 4.1 - At least 56,658 hectares of landscape (excluding PAs) in forest management units managed to benefit biodiversity Sub-Indicator 4.3 – At least 17,827 hectares of commune forest and agricultural lands in commune managed areas under improved management to benefit biodiversity |
|  | Indicator 5: Greenhouse Gas Emissions Mitigated (measured by million metric tons of carbon dioxide equivalent over a 20- year period) (GEF Core Indicator 6) | 0 | 0 | 1,541,810tCO2-e mitigated through enhanced protection and avoidance of forest degradation measured over a 20-year period |
| Project component 1 | Mainstreaming biodiversity and ecosystem services into landscape-level planning, monitoring and enforcement |  |  |  |
| Project Outcome 1 Enhanced enabling framework and systemic tools to monitor biodiversity and ecosystem services and incorporate landscape-level needs into land use and forest planning, monitoring and enforcement | Indicator 6: Operational status of multi-stakeholder coordination platforms in two provinces (Gia Lai and Phu Yen) | Multiple sector and stakeholder coordination institutional arrangements for planning and management of landscape-level approaches absent or limited within the country | Multi-stakeholder and multi-sector coordination platforms established in the two provinces, protocols established for coordination, planning and budgeting | Multi-stakeholder and multi-sector coordination platforms functional in Gia Lai and Phu Yen provinces and facilitating mainstreaming of biodiversity and ecosystem services in local level planning systems |
|  | Indicator 7: Level of integration of biodiversity and HCVF outcomes adopted and integrated into district land use planning | Provincial, district and forest management plans have limited attention to mainstreaming biodiversity and ecosystem consideration into their planning systems | Strategy for conservation developed identifying specific actions to mainstream biodiversity | Biodiversity conservation and HCVF strategies integrated and adopted into at least 2 district level land use and planning systems |
|  | Indicator 8: Spatially explicit tools for monitoring and response to forest loss and change have been demonstrated in Ba River landscape. Existing tools available are: (i) “deforestation warning’ Tool, (ii) UN Biodiversity Lab tool; and (iii) SMART tool | At least three existing spatially explicit tools available for detecting forest loss and change that is not applied | Assessment and validation of available tools completed, and appropriate tools identified for application, staff trained and monitoring initiated | At least 1-2 existing spatially explicit tools functional and monitoring forest changes |
| Outputs to achieve Outcome 1 | Output 1.1: Multi-stakeholder platforms on biodiversity and ecosystem services established at provincial level, supporting multi-sector dialogue on mainstreaming biodiversity into land use and master planning. Output 1.2: Spatially explicit landscape-level biodiversity and HCVF conservation and restoration strategy developed and integrated into provincial and district master planning/land-use planning processes. The strategy will also be used to prioritize on-ground conservation action under Component 2. Output 1.3: Enhanced systems for monitoring and assessing forest resource changes (i.e.,, deforestation and plantation/restoration) and biodiversity, incorporating remote sensing techniques, demonstrated at landscape level, with lessons provided to support national-level upscaling. Output 1.4: Enhanced coordination on wildlife and forest monitoring and enforcement at landscape levels, through broadening the inter-provincial forest management and protection cooperation regulation MOU to cover wildlife offences alongside forest offences. |  |  |  |
| Outcome 2 Forests and biodiversity are restored, and protected areas strengthened at landscape scale, through coordinated management across 8 FMUs (including 3 existing PAs and 1 new PA) and two community-managed areas | Indicator 9: Status of native species diversity in selected Taxa in existing and proposed PAs. The diversity of species will be measured in the following taxa: - Mammals - Bird - Reptile - Amphibian - Fish | Key species groups under continued threat from forest loss and degradation and poaching. Baselines are Kon Ka Kinh NP Mammals - 88 Bird - 326 Reptile - 77 Amphibian - 58 Fish - NA Kon Chu Rang NP Mammals - 80 Bird - 228 Reptile - 38 Amphibian - 43 Fish - 33 Krong Trai Nature Reserve Mammals - 83 Bird - 218 Reptile - 42 Amphibian - 19 Fish - NA Tram Lap-Dak Rong proposed PA Mammals - 46 Bird - 214 Reptile - 49 Amphibian - 38 Fish - NA Baselines validated in Year 1 | Key species diversity in selected taxa stable or increasing from baseline values | Key species diversity in selected taxa stable or increasing from baseline values |
|  | Indicator 10: Improved status of population of threatened northern buff-cheeked gibbon (Nomascus annamensis) in Kon Chu Rang NP and Kon Ka Kinh NP | Baseline density of population in key PAs in Central Highlands as: Kon Chu Rang NP – 0.53 groups/km2 Kon Ka Kinh NP – 0.12 groups/Km2 | Stable or increased group density of northern buff-cheeked gibbon (Nomascus annamensis) | Increased group density of northern buff-cheeked gibbon (Nomascus annamensis) |
|  | Indicator 11: Reduction in number of forest/wildlife violations in 3 selected PAs (Kon Ka Kinh NP, Kon Chu Rang NP, and Kromg Trai NR): Forest Fires Animal Traps | Baseline as follows: Kon Ka Kinh NP: 96 recorded violations 400 animal traps removed Kon Chu Rang NP: 2 recorded violations Kromg Trai NR: 24 recorded violations | Baseline for 2021/2021 established. Improved system for reporting developed and implemented | 10-20% decrease in forest violations from baseline values 10-20% decrease in wildlife violations from baseline values |
|  | Indicator 12: Level of institutional capacities for planning, implementation and monitoring integrated landscape management planning as measured by UNDP’s capacity development scorecard for the following institutions: Gia Lai Provincial Institution Phu Yen Provincial Institution | Limited institutional capacities for planning, implementation and monitoring of multiple use landscapes as measured by UNDP Capacity Development Scorecard baseline values as indicated below: Gia Lai Province – 27 Phu Yen Province – 26 | Average increase of institutional capacity as measured by 10% increase in UNDP Capacity Development Scorecard from baseline values for the respective institutions | Average increase of institutional capacity as measured by 25% increase in UNDP Capacity Development Scorecard from baseline values for the respective institutions |
|  | Indicator 13: Diversified livelihood options and % increase in incomes for two communities from sustainably harvested NTFPs, including measurable benefits for women | Bas Baselines of average incomes will be validated in Year 1 for each target community managed site. Current average incomes in rural forest communities estimated as follows: Gia Lai Prov. -$1,300/year. Phu Yen Prov. -$1,950-2,600/year | At least 5% average increase in income for 25% of participating households at least 20% beneficiary households must be women-headed). | At least 15% average increase in income for 50% of participating households (at least 20% beneficiary households must be women-headed) based on action plans for improved business models agreed and under implementation initiated (at least 20% beneficiary households must be women-headed). |
|  | Indicator 14: Improved and efficient PFES applications and utilization linked to conservation outcomes | Of the 1,541 PFES beneficiaries in the 2 provinces in the BA River Basin, around 1/3 (or around 500 beneficiaries are in the project sites. However, effective PFES application is constrained by cumbersome administrative procedures, equity considerations, limited capacity among forest managers for monitoring and evaluation, slow transfer of funds and lack of full linkages of PFES to conservation outcomes | Completion of evaluation of PFES program in project areas and initiation of actions at least in one project site to improve efficiency and effectiveness of PFES operations, monitoring and linkages to conservation outcomes | At least around 500 beneficiaries functioning under improved and efficient PFES monitoring, management and fund flow arrangements and investments are linked to conservation actions. |
| Outputs to achieve Outcome 2 | Output 2.1: Participatory monitoring and inventory on HCVF/biodiversity assets operationalized with training conducted for PA and forest managers and communities living in and around high-biodiversity areas. Output 2.2: Landscape and site-level biodiversity priorities and actions identified and integrated into sustainable forest management plans (= PA management plans), annual work plans and operations. This will include technical support, extension and demonstration of priority measures including threatened species conservation and habitat management, biodiversity threat reduction, assisted natural regeneration/restoration of degraded habitats. Output 2.3: Improving PA management, including operationalization of the Special Use Forest proposed for establishment in areas under Tram Lap and Dak Rong State-owned forestry companies. Output 2.4: Enhanced support for participatory community-based forest management. Output 2.5: Livelihoods development for women, including training in forest value chains and entrepreneurship, and establishment of women’s groups in forest-dependent communities. Output 2.6: Landscape connectivity for wildlife improved through reforestation/restoration using indigenous species over 500 ha of degraded natural forests. Output 2.7: Existing financial incentive mechanisms, including PFES, are utilized more effectively, including increased resource mobilization connected to performance and better targeted disbursement mechanisms, to support sustainable forest use and biodiversity and HCVF conservation. |  |  |  |
| Project component 2 | Conserving globally significant biodiversity and ecosystem services in forested landscapes of Ba River basin |  |  |  |
| Outcome 3 Knowledge documentation and exchange supports policy guidance, replication and national uptake of improved forest management practices | Indicator 15: Number of policy guidelines/notes on biodiversity and SFM enunciated e.g. - Replication, scaling-up and long-term sustainability strategy/plan - Policy guidance document on enhancing biodiversity conservation outcomes in SFM investment plans; and - Policy guidelines for mainstreaming biodiversity into provincial master planning | Current policies are limited to mainstream biodiversity and SLM within forest management and provincial master planning based on ecological principles and processes for the survival of species, maintenance of ecological services, and habitat connectivity. | Gaps assessment for enhancing SFM investment planning guidelines completed and revised guidelines issued. Guidelines for mainstreaming into provincial master planning under preparation, consultations completed, and requirements assessed | Issuance of Replication, scaling-up and long-term sustainability strategy/plan and at least two policy guidance notes on biodiversity and SFM, with application of new SFM investment guidelines for production and protection forests completed |
|  | Indicator 16: Level of awareness on conservation and threatened species conservation in the landscapes as indicated by KAP survey. | Baseline survey will be established in Year 1 Currently coordinated outreach on conservation landscape planning and threats lacking. Limited awareness of impact of unsustainable forest approaches among general public. | At least 20% (of which at least 50% women) of sampled community members, government and sector agency staff, private sector and other stakeholders aware of potential conservation threats and adverse impacts of unsustainable forest developments and behavior change for biodiversity outcomes | At least 60% (of which at least 50% women) of sampled community members, government and sector agency staff, private sector and other stakeholders aware of potential conservation threats and adverse impacts of unsustainable forest developments and behavior change for biodiversity outcomes |
|  | Indicator 17: Number of best practices documented and disseminated as part of replication strategy | Limited number of good practices in conservation and sustainable forest resource management codified, disseminated and applied | Best practices topics identified, data and monitoring collection in progress | Documentation and Dissemination of at least 10 project best practices and lessons learned. |
| Outputs to achieve Outcome 3 | Output 3.1: Enhancing capacity of forest owners to effectively integrate biodiversity conservation and ecosystem services into their sustainable land management plans and investments Output 3.2: Communication, knowledge shared and exchanged on SFM and forest biodiversity best practices and innovations, including through project website, site-based exchanges and best practice case studies in support of potential replication scaling-up and long-term sustainability. Output 3.3: Gender mainstreaming and safeguard management Output 3.4: Monitoring and evaluation |  |  |  |
| Project component 3 | Gender mainstreaming replication and knowledge exchange |  |  |  |

- Monitoring and Evaluation (M&E) Plan

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP (including guidance on GEF project revisions) and UNDP Evaluation Policy. The UNDP Country Office is responsible for ensuring full compliance with all UNDP project M&E requirements including project monitoring, UNDP quality assurance requirements, quarterly risk management, and evaluation requirements.

- Additional mandatory GEF-specific M&E requirements will be undertaken in accordance with the GEF Monitoring Policy and the GEF Evaluation Policy and other relevant GEF policies. The M&E plan and budget included below will guide the GEF-specific M&E activities to be undertaken by this project.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed – including during the Project Inception Workshop - and will be detailed in the Inception Report.

Minimum project monitoring and reporting requirements as required by the GEF:

- Inception Workshop and Report:  A project inception workshop will be held within 2 months from the First disbursement date, with the aim to:

- Familiarize key stakeholders with the detailed project strategy and discuss any changes that may have taken place in the overall context since the project idea was initially conceptualized that may influence its strategy and implementation.

- Discuss the roles and responsibilities of the project team, including reporting lines, stakeholder engagement strategies and conflict resolution mechanisms.

- Review the results framework and monitoring plan.

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP and other stakeholders in project-level M&E.

- Update and review responsibilities for monitoring project strategies, including the risk log; SESP report, Social and Environmental Management Framework (where relevant) and other safeguard requirements; project grievance mechanisms; gender strategy; knowledge management strategy, and other relevant management strategies.

- Review financial reporting procedures and budget monitoring and other mandatory requirements and agree on the arrangements for the annual audit.

- Plan and schedule Project Board meetings and finalize the first-year annual work plan.  Finalize the TOR of the Project Board.

- Formally launch the Project.

GEF Project Implementation Report (PIR):

- The annual GEF PIR covering the reporting period July (previous year) to June (current year) will be completed for each year of project implementation. UNDP will undertake quality assurance of the PIR before submission to the GEF. The PIR submitted to the GEF will be shared with the Project Board. UNDP will conduct a quality review of the PIR, and this quality review and feedback will be used to inform the preparation of the subsequent annual PIR.

GEF Core Indicators:

- The GEF Core indicators included as Annex 12 will be used to monitor global environmental benefits and will be updated for reporting to the GEF prior to MTR and TE. Note that the project team is responsible for updating the indicator status. The updated monitoring data should be shared with MTR/TE consultants prior to required evaluation missions, so these can be used for subsequent ground truthing. The methodologies to be used in data collection have been defined by the GEF and are available on the GEF website. The required Protected Area Management Effectiveness Tracking Tool (METTs) and FAO EXACT have been prepared and the scores included in the GEF Core Indicators.

Independent Mid-term Review (MTR):

- The terms of reference, the review process and the final MTR report will follow the standard UNDP templates and UNDP guidance for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC).

- The evaluation will be ‘independent, impartial and rigorous. The evaluators that UNDP will hire to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project under review.

- The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the evaluation process. Additional quality assurance support is available from the BPPS/NCE-VF Directorate.

- The final MTR report and MTR TOR will be publicly available in English and will be posted on the UNDP ERC by December 31, 2024. A management response to MTR recommendations will be posted in the ERC within six weeks of the MTR report’s completion.

Terminal Evaluation (TE):

- An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance for GEF-financed projects available on the UNDP Evaluation Resource Center. TE should be completed 3 months before the estimated operational closure date, set from the signature of the ProDoc and according to the duration of the project. Provisions should be taken to complete the TE in due time to avoid delay in project closure. Therefore, TE must start no later than 6 months to the expected date of completion of the TE (or 9 months prior to the estimated operational closure date).

- The evaluation will be ‘independent, impartial and rigorous. The evaluators that UNDP will hire to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project being evaluated.

- The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the BPPS/NCE-VF Directorate.

- The final TE report and TE TOR will be publicly available in English and posted on the UNDP ERC by March 30, 2026. A management response to the TE recommendations will be posted to the ERC within six weeks of the TE report’s completion.

Final Report:

- The project’s terminal GEF PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

- Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

| Monitoring and Evaluation Budget for project execution: |  |  |
| --- | --- | --- |
| GEF M&E requirements to be undertaken by Project Management Unit (PMU) | Indicative costs (US$) | Time frame |
| Inception Workshop and Report (including consultant costs and travel) | 20,000 | Inception Workshop within 2 months of the First Disbursement |
| M&E related workshops | 10,000 |  |
| M&E of GEF core indicators and project results framework | 25,780 | Annually and at mid-point and closure. |
| Monitoring of project safeguards management frameworks and/or plans and gender action plans here | As per the multiyear workplan | On-going |
| Supervision missions | NA | Annually |
| Independent Mid-term Review (MTR) | 20,000 | September 30, 2024 |
| Independent Terminal Evaluation (TE) | 20,885 | September 30, 2026 |
| TOTAL indicative COST | 96,665 | Provided as a separate section in the TBWP |

Monitoring Plan

| Monitoring | Indicators | Targets | Description of indicators and targets | Data source/Collection Methods | Frequency | Responsible for data collection | Means of verification | Risks/Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project objective: To conserve forest biodiversity and maintain or improve the flow of ecosystem services through sustainable forest management embedded in a coordinated landscape-level approach across Ba River basin | Indicator 1: GEF Number of direct beneficiaries disaggregated by gender Core Indicator 11: | MTR: At least 1,000 individuals comprising 50% men and 50% women (at least 30% represent ethnic minorities) TE: least 3,000 individuals comprising 50% men and 50% women (at least 30% represent ethnic minorities | Direct beneficiaries of livelihood, forest enterprise development and PFES support | Consultations with beneficiaries and women groups. Regular livelihood surveys | Annually reported in DO tab of the GEF PIR | Provincial Technical Coordinators reporting to national PMU | An Annual project work plans and budgets; Independent social and gender evaluations M&E reports National PMU and provincial PMU report /minutes on the assessment on results of implemented activities | Assumptions: -Local communities, private sector and provincial governments understand need for ecological security and agree to participate in restoration works. - Provincial Governments consider it priority to support integrated planning of its landscape for species conservation Risks: -Natural disaster/climate change may affect the restoration work. -Lack of capacity in local government, private sector and communities to meet obligations related to project. -Political transitions leave plans unused. - Lack of involvement from private sector and/or resource users with continued unsustainable practices -The Provincial government, CBOs, private sector and communities would work in close collaboration for preparation of landscape frameworks |
|  | Indicator 2: GEF Core Indicator 1 Number of hectares of Terrestrial Protected Area (i) expanded or (ii) under improved management effectiveness | (i) MTR: Survey and demarcation of forest lands for inclusion in existing PAs; surveys completed and management plans updated; TE: At least 10,000 hectares of forest lands added to existing PAs (i) MTR: At Least 10- point increase in METT scores TE: At least 25- point increase in METT scores | (i) The target of 10,000 hectares will include HCVFs within the Tram Lap and Dak Rong Forest Company lands to improve connectivity between existing PAs of Kon Ka Kinh NP and Kon Chu Rang NR (ii) Improved management effectiveness of Existing PAs METT baselines of: Kon Ka Kinh National Park – 48 Kon Chu Rang Nature Reserve -44 Krong Rai Nature Reserve - 35 | METT scorecards increase measured by: (i) integration of IAS prevention and management actions in management plans of 3 PAs and 3 CCAs covering 7,208 hectares; and (ii) demonstration of control of key IAS in each PA and CCA through improved land management practices, sanitary measures, removal and restoration of natural vegetation and IAS prevention measures METT scorecards increase measured through (i) improved PA management annual plans; monitoring protocols developed; (iii) staff trained in PA management; (iv) enhanced SMART patrols; and (v) reduce threats | MTR and TE | Gia Lai Provincial PMU and Kon Ka Kinh and Kon Chu Project Management Boards | Government document indicating expansion of existing PAs; Project Progress Reports New boundary survey plans and digital and hard copy maps National PMU and provincial PMU report /minutes on the assessment on results of implemented activities GEF METT Scorecard and Provincial PMU annual reports |  |
|  | Indicator 3: GEF Core Indicator 3. Total hectares of forest and forest land restored | MTR: Management plans for restoration developed and approved and work in progress for about 100 hectares TE: At least 500 hectares of degraded forests and forest lands under restoration to enhance connectivity | Use of MARD guidelines on restoration techniques to support connectivity and likely to include the area between Kon Ka Kinh NP and Kon Chu Rang NR in the north of the landscape, given its high biodiversity significance | Forest Management Board consultations, Review of progress in restoration sites Measurement of plant survival and/or regeneration | Annually | Forest Management Units | Restoration Plans and progress reports National PMU and provincial PMU report /minutes on the assessment on results of implemented activities |  |
|  | Indicator 4: GEF Core Indicator 4 Area of landscape under improved management practices (excluding protected areas) Sub-Indicator 4.1: Area of landscapes under improved management to benefit biodiversity and Sub-indicator 4.3 Area of landscape under SLM in production systems (excluding protected areas) | (4.1) MTR: SFM practices initiated in around 20,000 hectares in forest management units TE: At least 56,658 hectares of landscape (excluding PAs) in forest management units managed to benefit biodiversity (4.3) MTR: Commune People’s Committees initiate biodiversity-friendly activities in around 5,000 hectares of agricultural and commune managed forest lands TE: At least 17,827 hectares of commune forest and agricultural lands in commune managed areas under improved management to benefit biodiversity | This is measured by the following: (i) Provincial multi-stakeholder coordination platform definess protocols for improving conservation practices within landscape (ii) Commitment of provincial government for support for planning and funding for improving conservation outcomes within forested landscape; (iii) Enhanced SFM plans and budgets allocated for improving conservation outcomes Production and protection Forests; (iv) Implementation of Community-based Forest management in Commune managed lands (v) Agreement of enhancing connectivity in key high biodiversity areas; (vi) Monitoring system operational to monitor improved conservation outcomes | Forest Management Board consultations, Measurement of forest cover | MTR and TE | Forest Management Units | Forest resource surveys National PMU and provincial PMU report /minutes on the assessment on results of implemented activities |  |
|  | Indicator 5: GEF Core Indicator 6: Greenhouse gas emission mitigated (tCO2e) | MTR: TE: At least 1,074,459tCO2-e mitigated over a 20- year period | Mitigation through enhanced protection and avoidance of forest degradation | Consultations with FMUs and Provincial PMU Field visits | TE | Provincial PMUs | SFM and SLM plans Annual work plans Progress reports Aerial surveys National PMU and provincial PMU report /minutes on the assessment on results of implemented activities | Assumptions -FMUs are willing to engage in SFM actions -Local communities recognize benefits of improving their agricultural and land management practices Risks -Communities might not have capacity for supporting SLM |
| Project Outcome 1: Enhanced enabling framework and systemic tools to monitor biodiversity and ecosystem services and incorporate landscape-level needs into land use and forest planning, monitoring and enforcement | Indicator 6: Operational status of Multi-stakeholder coordination platforms in two provinces (Gia Lai and Phu Yen) | MTR: Multi-stakeholder and multi-sector coordination platforms TE: Multi-stakeholder platforms supporting mainstreaming | Provincial platforms functional in Gia Lai and Phu Yen provinces and facilitating mainstreaming of biodiversity and ecosystem services in local level planning systems | Consultations with Provincial committee members and participation in meetings | Annually | Provincial PMUs | Government decision establishing committees, Minutes of committee meetings National PMU and provincial PMU report /minutes on the assessment on results of implemented activities | Assumptions -Adequate interest and capacity of provincial governments to collaborate across sector -There is adequate capacity and technical support available to facilitate integration into land use plans Risks: - Sector agencies might be unwilling to work outside their mandates and priorities |
|  | Indicator 7: Level of integration of biodiversity and HCVF outcomes adopted and integrated into provincial/district land use planning | MTR: Biodiversity conservation and HCVF strategies integration initiated in 2 districts TE: Biodiversity conservation and HCVF strategies integration and adopted into at least 2 district level land use and planning systems | Land use plans in target districts and communes include specific actions to conserve biodiversity and HCVFs | Consultation with target district and commune people’s parties | Annual | Provincial PMUs | District and commune land use plans Progress reports National PMU and provincial PMU report /minutes on the assessment on results of implemented activities |  |
|  | Indicator 8: Spatially explicit tools for monitoring and response to forest loss and change have been demonstrated in Ba River landscape. Existing tools available are: (i) “deforestation warning’ Tool, (ii) UN Biodiversity Lab tool; and (iii) SMART tool | MTR: Spatial planning tools validated TE: At least 1-2 existing spatially explicit tools functional and monitoring forest changes | Assessment and validation of available tools completed, and appropriate tools identified for application, staff trained and monitoring initiated | Consultation with key national and provincial entities | MTR and TE | PMU | National PMU and provincial PMU report /minutes on the assessment on results of implemented activities | Assumptions -Adequate interest and capacity of provincial labs to effective monitoring measures Risks: - Lack of adequate staff to undertake monitoring -Financial constraints |
| Project Outcome 2 Forests and biodiversity are restored, and protected areas strengthened at landscape scale, through coordinated management across 8 FMUs (including 3 existing PAs and 1 new PA) and two community-managed areas | Indicator 9: Status of native species diversity in selected Taxa in existing and proposed PAs. The diversity of species will be measured in the following taxa: | MTR: Key species diversity In selected taxa stable or increasing from baseline values TE: Key species diversity in selected taxa stable or increasing from baseline values | Status of key species group diversity in existing and proposed PAs, namely for: - Mammals - Bird - Reptile - Amphibian - Fish - Insect Kon Ka Kinh NP Mammals - 88 Bird - 326 Reptile - 77 Amphibian - 58 Fish - NA Kon Chu Rang NP Mammals - 80 Bird - 228 Reptile - 38 Amphibian - 43 Fish - 33 Insect? Krong Trai Nature Reserve Mammals - 83 Bird - 218 Reptile - 42 Amphibian - 19 Fish - NA Insect? Tram Lap-Dak Rong proposed PA Mammals - 46 Bird - 214 Reptile - 49 Amphibian - 38 Fish - NA Insect? | Species Surveys | Annual | FMUs | Survey data reports with clear evidences National PMU and provincial PMU report /minutes on the assessment on results of implemented activities | Assumption: -Adequate technical capacity available for undertaking monitoring of presence/absence of key species -Monitoring results are readily available for decision-making Risk: -External factors beyond the control of the project (e.g., climate change) might effect presence/absence of species/taxa negatively |
|  | Indicator 10: Status of population of threatened northern buff-cheeked gibbon (Nomascus annamensis) | MTR: Stable or increased group density of northern buff-cheeked gibbon TE: Stable or increased group density of northern buff-cheeked gibbon | Baseline density of population in key PAs in Central Highlands as: Kon Chu Rang NP – 0.53 groups/km2 Kon Ka Kinh NP – 0.12 groups/Km2 | Surveys | Annual | FMUs | Survey reports National PMU and provincial PMU report /minutes on the assessment on results of implemented activities | Assumption: -Adequate technical capacity available for undertaking stringent monitoring species populations -Monitoring results are readily available for decision-making Risk: -External factors beyond the control of the project (e.g., climate change) might affect populations negatively |
|  | Indicator 11: Reduction in number of forest/wildlife violations in 3 selected PAs (Kon Ka Kinh NP, Kon Chu Rang NP, and Krong Trai NR): Forest Fires Animal Traps | MTR: Baseline for 2021/2021 established. Improved system for reporting developed and implemented TE: 10-20% decrease in forest violations from baseline values 10-20% decrease in wildlife violations from baseline values | Baseline as follows: Kon Ka Kinh NP: 96 recorded violations 400 animal traps removed Kon Chu Rang NP: 2 recorded violations Kromg Trai NR: 24 recorded violations | Surveys and Questionnaires | Annual | PMU | Survey reports National PMU monitoring reports | Assumptions Adequate technical and community capacity available for undertaking stringent monitoring of threats -Monitoring results are readily available for decision-making Risk: -Under-reporting |
|  | Indicator 12: Level of institutional capacities for planning, implementation and monitoring integrated landscape management planning as measured by UNDP’s capacity development scorecard for the following institutions: | MTR: Average increase of institutional capacity as measured by 10% increase in UNDP Capacity Development Scorecard from baseline values for the respective institutions TE: Average increase of institutional capacity as measured by 25% increase in UNDP Capacity Development Scorecard from baseline values for the respective institutions | Institutional capacity of DARDs (in two provinces) monitored | Consultations and surveys of provincial entities | MTR and TE | National PMU | UNDP capacity scorecard reports | Assumption: -The national and provincial government will develop institutional and technical measures that facilitate integrated landscape planning and management in a timely manner. -Development strategies and management plans will be officially approved by Provincial governments with allocation of appropriate staff and funding for their implementation -The provinces will take active part in developing the strategies and implementation using new knowledge and skills provided by the project -Local communities are convinced mainstreaming biodiversity into key development sectors is in their long-term interests Risks: -Priorities of provincial governments and local communities might shift if development benefits take long to manifest - Plans are developed by not used, particularly by resource users (e.g.,, private sector) - Planning bodies that build capacity are not effective in implementation |
|  | Indicator 13: Diversified livelihood options and % increase in incomes for two communities from sustainably harvested NTFPs, including measurable benefits for women | MTR: At least 5% average increase in income for 25% of participating households at least 20% beneficiary households must be women-headed). TE: At least 15% average increase in income for 50% of participating households (at least 20% beneficiary households must be women-headed). | - Baselines of average incomes will be validated in Year 1 for each target community managed site. Current average incomes in rural forest communities estimated as follows: Gia Lai Prov. -$1,300/year. Phu Yen Prov. -$1,950-2,600/year | Monitoring based on action plans for improved business models agreed and under implementation initiated | MTR and TE | Provincial PMUs | Livelihood survey reports National PMU and provincial PMU report /minutes on the assessment on results of implemented activities | Assumptions: -Local communities understand need for ecological security and agree to participate in restoration works. Risks: -Natural disaster/climate change may affect the restoration work. -Lack of capacity in communities to meet obligations related to project. -Livelihood benefits may be limited for communities to give up current unsustainable practices -The Provincial government, and communities would work in close collaboration |
|  | Indicator 14: Improved and efficient PFES applications and utilization linked to conservation outcomes | MTR: Completion of evaluation of PFES program in project areas and initiation of actions at least in one project site to improve efficiency and effectiveness of PFES operations, monitoring and linkages to conservation outcomes TE: At least around 500 beneficiaries functioning under improved and efficient PFES monitoring, management and fund flow arrangements and investments are linked to conservation actions. | Of the 1,541 PFES beneficiaries in the 2 provinces in the BA River Basin, around 1/3 (or around 500 beneficiaries are in the project sites. However, effective PFES application is constrained by cumbersome administrative procedures, equity considerations, limited capacity among forest managers for monitoring and evaluation, slow transfer of funds and lack of full linkages of PFES to conservation outcomes | Monitoring based on new guidelines and procedures for PFES agreed and implemented | MTR and TE | PMU | PFES guidelines and procedures PFES financial reports and work plans | Assumptions: -Forest Department staff has improved capacity and skills to monitor and report on PFES -Community capacity to manage PFES and investment improved Risks: -Poor oversight of PFES might lead to inefficient use of PFES resources for conservation action |
| Project Outcome 3 Knowledge documentation and exchange supports policy guidance, replication and national uptake of improved forest management practices | Indicator 15: Number of policy guideline notes on biodiversity and SFM enunciated e.g. | MTR: Gaps assessment for enhancing SFM investment planning guidelines completed and revised guidelines issued. Guidelines for mainstreaming into provincial master planning under preparation, consultations completed, and requirements assessed TE: Issuance of Replication, scaling-up and long-term sustainability strategy/plan and at least two policy guidance notes on biodiversity and SFM, with application of new SFM investment guidelines for production and protection forests completed | Current policies are limited to mainstream biodiversity and SLM within forest management and provincial master planning based on ecological principles and processes for the survival of species, maintenance of ecological services, and habitat connectivity. | Investment learning and development | MTR and TE | PMU | Policy documents | Assumption: -The national and provincial government willingness to policy development -Policy notes will be formally agreed with key partners |
|  | Indicator 16: Level of awareness on conservation and threatened species conservation in the landscapes as indicated by KAP survey. | MTR: At least 20% (of which at least 50% women) of sampled community members, government and sector agency staff, private sector and other stakeholders TE: At least 60% (of which at least 50% women) of sampled community members, government and sector agency staff, private sector and other stakeholders’ outcomes | Measure of awareness of potential conservation threats and adverse impacts of unsustainable forest developments and behavior change for biodiversity outcomes | surveys | Year 1, MTR and TE | PMU | KPA survey reports | Assumption: - Gender and Social Inclusion Mainstreaming Plan followed and benefits distributed equitably. -Stakeholders willing to actively participate in the review process. |
|  | Indicator 17: Number of best practices documented and disseminated as part of replication strategy | MTR: Best practices topics identified, data and monitoring collection in progress TE: Documentation and Dissemination of at least 10 project best practices and lessons learned. | Limited number of good practices in conservation and sustainable forest resource management codified, disseminated and applied | Questionnaires and reports | MTR and TE | PMU | Best practice reports | Assumptions -Community willingness to accept learning and experiences -Capacity exists to document best Practices |

.

.

- Governance and Management Arrangements

Section 1: Roles and responsibilities of the project’s governance mechanism:

- Implementing Partner: The Implementing Partner for this project is the Ministry of Agriculture and Rural Development (MARD)/Forest Inventory and Planning Institute (FIPI).

- The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

- The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting. This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Overseeing the management of project risks as included in this project document and new risks that may emerge during project implementation;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets;

- Approving and signing the multi-year workplan;

- Approving and signing the combined delivery report at the end of the year;

- Signing the financial report or the funding authorization and certificate of expenditures.

- Responsible Parties: The Responsible Parties are the Provincial People Committees of Gia Lai and Phu Yen provinces, for which their representatives are members of the Project Steering Committee (or Project Board). Provinces also can delegate alternative individuals, for instance DARD leaders, to participate in the Project Board under nomination made by PPCs.

- Project stakeholders and target groups: The project target groups are the Protected Area and Forest Management Boards within the Ba River basin in the two provinces that will be responsible for implementation of protected areas and sustainable forest management actions. The Commune Peoples Committees will actively engage in promotion of co-management of commune forest lands and local communities and ethnic minorities will be beneficiaries of forest management, livelihood and payment for forest ecosystem services.

- UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes overseeing project execution undertaken by the Implementing Partner to ensure that the project is being carried out in accordance with UNDP and GEF policies and procedures and the standards and provisions outlined in the Delegation of Authority (DOA) letter for this project. The UNDP GEF Executive Coordinator, in consultation with UNDP Bureau and the Implementing Partner, retains the right to revoke the project DOA, suspend or cancel this GEF project. UNDP is responsible for the Project Assurance function in the project governance structure and presents to the Project Board and attends Project Board meetings as a non-voting member.

Section 2: Project organization structure:

Project Governance Arrangements Project Board / Steering Committee. Development Partner UNDP Resident Representative; Project Executive MARD Leader; Beneficiary Representatives: Local Governments, other ministries, Civil Society Representatives. Project Assurance; Project Support. UNDP Country Office Environment Focal Point; Implementing Partner; Project Management Unit National Project Director (Co-financing) National Project Coordinator Chief Accountant (Co-financing) Accountant Other staff (co-financing). MARD/FIPI. Responsible Parties Gia Lai Provincial Project Management Team DARD Office (co-financing); Phu Yen Provincial Project Management Team DARD Office (co-financing). Provincial Project Director (co-financing) Technical Coordinator Local Forest Management Units (co-financing); Provincial Project Director (co-financing) Technical Coordinator Local Forest Management Units (co-financing). Provincial Landscape’s Beneficiaries. Provincial, district, communal authorities; Forest management units; local communities; women unions, farmer associations, ethnic minority institutions, private sectors, research institutes, etc..

Second line of defense:

  - Regional Bureau oversees RR and Country Office compliance at portfolio level

  - BPPS NCE RTA oversees technical quality assurance and GEF compliance. BPPS NCE PTA oversees RTA function

  - UNDP GEF Executive Coordinator and Regional Bureau Deputy Director can evoke DOA/cancel/suspend project or provide enhanced oversight.

- The UNDP Resident Representative assumes full responsibility and accountability for oversight and quality assurance of this Project and ensures its timely implementation in compliance with the GEF-specific requirements and UNDP’s Program and Operations Policies and Procedures (POPP), its Financial Regulations and Rules and Internal Control Framework. A representative of the UNDP Country Office will assume the assurance role and will present assurance findings to the Project Board, and therefore attends Project Board meetings as a non-voting member.

Section 3: Segregation of duties and firewalls vis-à-vis UNDP representation on the project board

- As noted in the Minimum Fiduciary Standards for GEF Partner Agencies, in cases where a GEF Partner Agency (i.e. UNDP) carries out both implementation oversight and execution of a project, the GEF Partner Agency (i.e. UNDP) must separate its project implementation oversight and execution duties, and describe in the relevant project document a: 1) Satisfactory institutional arrangement for the separation of implementation oversight and executing functions in different departments of the GEF Partner Agency; and 2) Clear lines of responsibility, reporting and accountability within the GEF Partner Agency between the project implementation oversight and Section 4 execution functions.

- In this case, UNDP is only performing an implementation oversight role in this project vis-à-visour role in the project board and in the project assurance function and therefore a full separation of project implementation oversight and execution duties has been assured.

Section 4: Roles and Responsibilities of the Project Organization Structure

- The Project Board (also called Project Steering Committee) is responsible for taking corrective actions as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value for money, fairness, integrity, transparency and effective international competition.

The two main (mandatory) roles of the project board are as follows:

- High-level oversight of the execution of the project by the Implementing Partner (as explained in the “Provide Oversight” section of the POPP). This is the primary function of the project board and includes annual (and as-needed) assessments of any major risks to the project, and decisions/agreements on any management actions or remedial measures to address them effectively. The Project Board reviews evidence of project performance based on monitoring, evaluation and reporting, including progress reports, evaluations, risk logs and the combined delivery report. The Project Board is responsible for taking corrective actions as needed to ensure the project achieves the desired results.

- Approval of strategic project execution decisions of the Implementing Partner with a view to assess and manage risks, monitor and ensure the overall achievement of projected results and impacts and ensure long term sustainability of project execution decisions of the Implementing Partner (as explained in the “Manage Change” section of the POPP).

Requirements to serve on the Project Board:

- Agree to the Terms of Reference of the Board and the rules on protocols, quorum and minuting.

- Meet annually; at least once.

- Disclose any conflict of interest in performing the functions of a Project Board member and take all measures to avoid any real or perceived conflicts of interest. This disclosure must be documented and kept on record by UNDP.

- Discharge the functions of the Project Board in accordance with UNDP policies and procedures.

- Ensure highest levels of transparency and ensure Project Board meeting minutes are recorded and shared with project stakeholders.

Responsibilities of the Project Board:

- Consensus decision making:

  - The project board provides overall guidance and direction to the project, ensuring it remains within any specified constraints, and providing overall oversight of the project implementation.

  - Review project performance based on monitoring, evaluation and reporting, including progress reports, risk logs and the combined delivery report;

  - The project board is responsible for making management decisions by consensus.

  - In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

  - In case consensus cannot be reached within the Board, the UNDP representative on the board will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

- Oversee project execution:

  - Agree on project manager’s tolerances as required, within the parameters outlined in the project document, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded.

- Appraise annual work plans prepared by the Implementing Partner for the Project.

- Address any high-level project issues as raised by the project manager and project assurance

- Advise on major and minor amendments to the project within the parameters set by UNDP and the donor and refer such proposed major and minor amendments to the UNDP BPPS Nature, Climate and Energy Executive Coordinator (and the GEF, as required by GEF policies);

- Provide high-level direction and recommendations to the project management unit to ensure that the agreed deliverables are produced satisfactorily and according to plans.

- Track and monitor co-financed activities and realisation of co-financing amounts of this project.

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project.

- Risk Management:

  - Provide guidance on evolving or materialized project risks and agree on possible mitigation and management actions to address specific risks.

  - Review and update the project risk register and associated management plans based on the information prepared by the Implementing Partner. This includes risks related that can be directly managed by this project, as well as contextual risks that may affect project delivery or continued UNDP compliance and reputation but are outside of the control of the project. For example, social and environmental risks associated with co-financed activities or activities taking place in the project’s area of influence that have implications for the project.

  - Address project-level grievances.

- Coordination:

  - Ensure coordination between various donor and government-funded projects and programmes.

  - Ensure coordination with various government agencies and their participation in project activities.

Composition of the Project Board: The composition of the Project Board must include individuals assigned to the following three roles:

- Project Executive: This is an individual who represents ownership of the project and chairs (or co-chairs) the Project Board. The Executive usually is the senior national counterpart for nationally implemented projects (typically from the same entity as the Implementing Partner). The Project Executive is a Senior Representative from MARD. The name and the title will be determined prior to the project inception workshop.

- Beneficiary Representatives: Individuals or groups representing the interests of those groups of stakeholders who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. Often representatives from civil society, industry associations, or other government entities benefiting from the project can fulfil this role. There can be multiple beneficiary representatives in a Project Board. The Beneficiary representative (s) is/are: (1) Provincial Authority Representative(s) - Representatives from the Gia Lai and Phu Yen Provincial People’s Committee, (2) Representatives from other Ministries; (3) Representatives from the Civil Society Organizations and Non-for-profit organizations, and other representatives are to be determined prior to the project inception workshop.

- Development Partner(s): Individuals or groups representing the interests of the parties concerned that provide funding, strategic guidance and/or technical expertise to the project. The Development Partner is UNDP (Represented by UNDP Resident Representative).

- Project Assurance: Project assurance is the responsibility of each project board member; however, UNDP has a distinct assurance role for all UNDP projects in carrying out objective and independent project oversight and monitoring functions. UNDP performs quality assurance and supports the Project Board (and Project Management Unit) by carrying out objective and independent project oversight and monitoring functions, including compliance with the risk management and social and environmental standards of UNDP. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager. Project assurance is totally independent of project execution.

A designated representative of UNDP playing the project assurance role is expected to attend all board meetings and support board processes as a non-voting representative. It should be noted that while in certain cases UNDP’s project assurance role across the project may encompass activities happening at several levels, at least one UNDP representative playing that function must, as part of their duties, specifically attend board meeting and provide board members with the required documentation required to perform their duties.  The UNDP representative playing the main project assurance function is the UNDP Country Office Environmental Focal Point.

- Project Management: National Project Management Unit (NPMU): Under the leadership and management capability exercised by National Project Director, the NPMU (will provide project leadership and operational project management oversight in accordance with the Project Document and the UNDP guidelines and procedures for implementation of project activities, including:

- Provide overall project implementation support across all components. Assurance of successful completion of the project in accordance with the Project Results Framework;

- Provide overall leadership and guidance to the staff of the PMU and Provincial Project Management Teams

- Serve as secretary of the Project Board and recommend agenda for Project Board;

- Lead the process of planning for implementation strategy, annual work planning, reporting to Project Steering Board and UNDP, and in the preparation of implementation guidelines;

- Based on agreed upon strategies and plan targets set by the project, direct and facilitate the preparation of work packages and TORs, identify and facilitate agreements with responsible partners for their implementation;

- Oversee the development and execution of a monitoring and evaluation system (M&E);

- Track and manage project spending in accordance with the project budget, as well as UNDP rules and procedures to ensure transparency, responsibility, and timely fulfilment of both program targets and budget targets;

- Oversee the preparation and submission of annual Project Implementation Reviews and other required progress reports to the Project Board, UNDP, and GEF in accordance with applicable requirements, in English languages;

- Approve and sign the annual workplan and quarterly workplan and relevant project financial reports

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Manage, monitor and assess the main products of the project

- Approving and signing the combined delivery report at the end of the year; and,

- Ensure communication of project issues, innovations, and learnings among key officials of the MHURECC and member agencies of the PSB.

- Responsible Parties: The Responsible Parties' primary responsibility is to provide technical leadership and ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Responsible Parties will inform the Implementing Partner and the Project Assurance of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted. The Responsible Parties will establish provincial management team that is appropriate with the provincial context and requirements. To ensure the implementation of the project in the project, each province will have one technical coordinator. Specific responsibilities of provincial technical coordinators include:

- Manage the overall coordination and guidance of the technical aspects of the project, in particular the preparation of the FMU and PA plans, monitoring plans and oversee the implementation of technical aspects related to PA management, SFM, training of field staff, community management of forests and community protocols.

- Overseeing and coordination of the technical inputs from the international and national consultants

- Develop and support a capacity building and training programs for all relevant provincial, district and commune agencies, ethnic minorities and local communities

- Support the conduct of technical consultations and workshops to develop guidelines, tool kits and manuals for facilitating of planning at FMU levels, rules and regulations for financial mechanism for conservation of biodiversity, etc.

- Development and organization of awareness and publicity programs and materials

- Support plans and protocols for inter-agency coordination during the preparation of land use plans that integrated biodiversity

- Plan the activities of the project and monitor progress against the approved work plan.

- Monitor events as determined in the project monitoring plan, and updated plan as required.

- Provide support for completion of assessments required by UNDP, spot checks and audits.

- Monitor progress watch for plan deviations and make course corrections when needed within project board-agreed tolerances to achieve results.

- Ensure that changes are controlled and problems addressed.

- Perform regular progress reporting to the project board as agreed with the board, including measures to address challenges and opportunities.

- Manage and monitor the project risks – including social and environmental risks - initially identified and submit new risks to the Project Board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Capture lessons learned during project implementation.

- Prepare revisions to the multi-year work plan, as needed, as well as annual and quarterly plans if required.

- Prepare the inception report no later than one month after the inception workshop.

- Ensure that the indicators included in the project results framework is monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR.

- Assess major and minor amendments to the project within the parameters set by UNDP-GEF;

- Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans;

- Monitor and track progress against the GEF Core indicators.

- Support the Mid-term and Terminal Evaluation process

- Financial Planning and Management

- The total cost of the project is USD 24,916,105. This is financed through a GEF grant of USD 2,183,105 administered by UNDP,  and additional support of  USD 22,733,000 in co-financing. UNDP, as the GEF Implementing Agency, is responsible for the oversight of the GEF resources.

- Confirmed Co-financing: The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. Note that all project activities included in the project results framework that will be delivered by co-financing partners (even if the funds do not pass-through UNDP accounts) must comply with UNDP’s social and environmental standards. Co-financing will be used for the following project activities/outputs:

| Co-financing source | Co-financing type | Co-financing amount |
| --- | --- | --- |
| Forest Inventory and Planning Institute (FIPI) of Ministry of Agriculture and Rural Development MARD | In-kind - Recurrent Expenditure | 1,000,000 |
| Department of Agriculture and Rural Development, Gia Lai | Investment Mobilized: Public Investment | 13,272,000 |
|  | In-kind – Recurrent Expenditure | 861,000 |
|  | Investment Mobilized: Donor investment | 2,000,000 |
| Department of Agriculture and Rural Development, Phu Yen | In-Kind - Recurrent Expenditure | 500,000 |
|  | Investment Mobilized: Public Investment | 1,000,000 |
| Total (USD) |  | 18,633,000 |

- Budget Revision and Tolerance: As per UNDP POPP, the project board may agree on a budget tolerance level for each detailed plan under the overall multi-year work plan. The agreed tolerances should be written in the project document or approved project board meeting minutes.  It should normally not exceed 10 percent of the agreed annual budget at the activity level, but within the overall approved multi-year workplan at the activity level. Within the agreed tolerances, the project manager can operate without intervention from the project board. Restrictions apply as follows:

- Should the following deviations occur, the Project Manager and UNDP Country Office will seek the approval of the BPPS/NCE-VF team to ensure accurate reporting to the GEF. It is strongly encouraged to maintain the expenditures within the approved budget at the budgetary account and at the component level:

- Budget reallocations must prove that the suggested changes in the budget will not lead to material changes in the results to be achieved by the project. A strong justification is required and will be approved on an exceptional basis. Budget re-allocations among the components (including PMC) of the approved Total Budget and Work Plans (TBWP) that represent a value greater than 10% of the total GEF grant.

- Introduction of new outputs/activities (i.e., budget items) that were not part of the agreed project document and TBWP that represent a value greater than 5% of the total GEF grant. The new budget items must be eligible as per the GEF and UNDP policies.

- Project management cost (PMC): budget under PMC component is capped and cannot be increased.

- Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g.,      UNDP TRAC or cash co-financing).

- Project extensions: The UNDP Resident Representative and the UNDP-GEF Executive Coordinator must approve all project extension requests. Note that all extensions incur costs and the GEF project budget cannot be increased. A single extension may be granted on an exceptional basis and subject to the conditions and maximum durations set out in the UNDP POPP; the project management costs during the extension period must remain within the originally approved amount, and any increase in PMC costs will be covered by non-GEF resources; the additional UNDP oversight costs during the extension period must be covered by non-GEF resources, in accordance with UNDP’s guidance set out in UNDP POPP.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies. Audit cycle and process must be discussed during the Inception workshop. If the Implementing Partner is an UN Agency, the project will be audited according to that Agencies applicable audit policies.

- Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. All costs incurred to close the project must be included in the project closure budget and reported as final project commitments presented to the Project Board during the final project review. The only costs a project may incur following the final project review are those included in the project closure budget.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. Operational closure must happen at the end date calculated by the approved duration after the Project Document signature or at the revised operational closure date as approved in the project extension. Any expected activity after the operational date requires project extension approval. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the Implementing Partner and other parties of the project, UNDP is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file. The transfer should be done before Project Management Unit complete their assignments.

- Financial completion (closure): The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; and d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 6 months of operational closure or after the date of cancellation. If Operational Closure is delayed for any justified and approved reason, the Country Office should do all efforts to financially close the project within 9 months after TE is completed. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the BPPS/NCE-VF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

- Refund to GEF: Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the BPPS/NCE-VF Directorate in New York. No action is required by the UNDP Country Office on the actual refund from UNDP project to the GEF Trustee.

- Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Award ID: | 00128603 | Atlas Output Project ID: 00122552 | 00122552 |
| Atlas Proposal or Award Title: | Sustainable Forest and Forest Land Management in Viet Nam’s Ba River basin landscape |  |  |
| Atlas Business Unit | VNM10 |  |  |
| Atlas Primary Output Project Title | Sustainable Forest and Forest Land Management in Viet Nam’s Ba River basin landscape |  |  |
| UNDP-GEF PIMS No. | 5887 |  |  |
| Implementing Partner | MARD |  |  |

| Atlas Activity (GEF Component) | Atlas Implementing Agent (Responsible Party[2] , IP or UNDP) | Atlas Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Account Description | Amount Year 2022 (USD) | Amount Year 2023 (USD) | Amount Year 2024 (USD) | Amount Year 2025 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Mainstreaming biodiversity and ecosystem services into landscape-level planning, monitoring and enforcement | MARD | 62000 | GEF | 71200 | International Consultants | 6,000 | 12,000 | 6,000 | - | 24,000 | 1 |
|  |  |  |  | 71300 | Local Consultants | 64,224 | 84,960 | 57,888 | 50,400 | 257,472 | 2 |
|  |  |  |  | 71600 | Travel | 9,000 | 23,250 | 8,000 | 3,500 | 43,750 | 3 |
|  |  |  |  | 72100 | Contractual Services-Companies | 22,500 | 72,500 | 10,000 | 10,000 | 115,000 | 4 |
|  |  |  |  | 72200 | Equipment and Furniture | - | 10,000 | - | - | 10,000 | 5 |
|  |  |  |  | 75700 | Training, workshop, conference | 23,200 | 38,000 | 32,800 | 8,000 | 102,000 | 6 |
|  |  |  |  | Total Outcome 1 |  | 124,924 | 240,710 | 114,688 | 71,900 | 552,222 |  |
| Component 2: Conserving globally significant biodiversity and ecosystem services in forested landscapes of Ba River basin | MARD | 62000 | GEF | 71200 | International Consultants | - | 6,000 | 18,000 | 24,000 | 48,000 | 7 |
|  |  |  |  | 71300 | Local Consultants | 7,680 | 59,712 | 36,480 | 21,120 | 124,992 | 8 |
|  |  |  |  | 71600 | Travel | 11,000 | 37,100 | 42,400 | 17,500 | 108,000 | 9 |
|  |  |  |  | 72100 | Contractual Services-Companies | 150,000 | 168,000 | 169,000 | 87,000 | 574,000 | 10 |
|  |  |  |  | 72200 | Equipment and Furniture | - | 3,000 | 4,000 | - | 7,000 | 11 |
|  |  |  |  | 75700 | Training, workshop, conference | 28,500 | 97,600 | 150,000 | 18,000 | 294,100 | 12 |
|  |  |  |  | Total Outcome 2 |  | 197,180 | 371,412 | 419,880 | 167,620 | 1,156,092 |  |
| Component 3. Gender mainstreaming replication and knowledge exchange | MARD | 62000 | GEF | 71200 | International Consultants | - | - | - | 12,000 | 12,000 | 13 |
|  |  |  |  | 71300 | Local Consultants | 24,960 | 19,200 | 29,760 | 16,320 | 90,240 | 14 |
|  |  |  |  | 71600 | Travel | 4,500 | 8,500 | 7,000 | 10,000 | 30,000 | 15 |
|  |  |  |  | 72100 | Contractual Services-Companies | 10,000 | 20,000 | 10,000 | 25,000 | 65,000 | 16 |
|  |  |  |  | 75700 | Training, workshop, conference | 14,500 | 25,000 | 13,000 | 24,471 | 76,971 | 17 |
|  |  |  |  | Total Outcome 3 |  | 53,960 | 72,700 | 59,760 | 87,791 | 274,211 |  |
| M&E | UNDP | 62000 | GEF | 71200 | International Consultant | 9000 | - | 9,000 | 9000 | 27,000 | 13 |
|  |  |  |  | 71300 | Local Consultant | 3840 | 1280 | 6,080 | 6080 | 17,280 | 14 |
|  | MARD |  |  | 71600 | Travel | 2275 | 2275 | 8,918 | 8917.5 | 22,385 | 15 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 9,000 | 3,000 | 3,000 | 15,000 | 30,000 | 17 |
|  |  |  |  | Total M&E |  | 24,115 | 6,555 | 26,998 | 38,998 | 96,665 |  |
| PROJECT MANAGEMENT (PMC) | MARD | 62000 | GEF | 71800 | Contractual Services-Imp Partn | 20,229 | 20,229 | 20,229 | 20,229 | 80,915 | 18 |
|  | UNDP |  |  | 74100 | Professional Services | 5,750 | 5,750 | 5,750 | 5,750 | 23,000 | 19 |
|  |  |  |  | Total Management |  | 25,979 | 25,979 | 25,979 | 25,979 | 103,915 |  |
|  |  |  |  | PROJECT TOTAL |  | 426,158 | 717,356 | 647,304 | 392,287 | 2,183,105 |  |

|  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Total |
| --- | --- | --- | --- | --- | --- |
| GEF grant administered by UNDP | 426,158 | 717,356 | 647,304 | 392,287 | 2,183,105 |
| Government | 3,600,000 | 6,400,000 | 5,200,000 | 3,433,000 | 18,633,000 |
| TOTAL | $4,026,158 | $7,117,356 | $5,847,304 | $3,825,287 | 20,816,105 |

| Budget note number | Comments: Budget note should be output based rather than input based. Even for individual consultants’ outputs of the consultants must be clear. Include cost breakdown and calculation basis (e.g., daily fee and number of days/weeks, unit cost and number), as well as a total amount for the budget line. |
| --- | --- |
| Component 1: Mainstreaming biodiversity and ecosystem services into landscape-level planning, monitoring and enforcement |  |
| 1 | International Consultants - $24,000 - Preparation of Ba River forest management and restoration strategy - 20 days at $600/day = $12,000 (Output 1.2) - Development of protocols for inter-provincial coordination -20 days at $600/day = $12,000 (Output 1.4) |
| 2 | Local consultants - $257,472 - Review existing provincial coordination mechanisms, develop provincial coordination roles and prepare advocacy strategy – 65 days at $192 =12,480 (Output 1.1) - Support for forest management and restoration strategy – 25 days at $192/day = $4,800 (Output 1.2) - Spatial data mapping assessment, guidelines for data collection, training and skills development, monitoring guidelines and application of FRMS systems –67 days at $192/day = $ 12,864 - (Output 1.3) - Review monitoring, surveillance and enforcement systems, provincial regulations, protocol and guideline development and protocols for inter-provincial data sharing – 134 days at $192/day = $25,728 (Output 1.4) - Provincial Technical Coordinators (2) at $100,800/Coordinator for 4 years = 201,600 |
| 3 | Travel = $43,750 Lump sum travel costs for international and national consultants, Provincial Technical Coordinators, FMU and PA staff and national, provincial staff for workshops, monitoring etc. |
| 4 | Contractual Services –Companies = $115,000 - Development of basin wide advocacy and outreach program - $40,000 (Output 1.1) - Mapping of forest cover and species composition/distribution and guideline for HCVF assessment for all FMUs in Ba River basin - $75,000 (Output 1.2) |
| 5 | Equipment = $10,000 Consists of laptops (3), smart phones (5), binoculars (5), GPS devices (10) and field monitoring kits for staff (20) for species monitoring |
| 6 | Training workshops and conferences = $102,000 - Meetings related to develop coordination arrangements and protocols, training meetings, meetings to development advocacy strategy, and bi-annual provincial coordination meetings = $38,000 (Output 1.1) - Workshops to validate mapping of forests and species, basin forest management and restoration strategy and guidelines for HCVF development = $18,400 (Output 1.2) - Meetings and training workshop for spatial data mapping, information and data management, data collection, verification and monitoring = $17,200 (Output 1.3) - Meetings, workshops and training on surveillance and enforcement, SMART patrols, standards for SFM and inter-provincial data management and exchange - $28,400 (Output 1.4) |
| Component 2: Conserving globally significant biodiversity and ecosystem services in forested landscapes of Ba River basin |  |
| 7 | International Consultant - $48,000 - Consolidation of roles and management responsibilities of PA and FMU Management Boards and guidance for integrating biodiversity conservation outcomes in SFM planning and forest restoration – 60 days at $600/day = $36,000 (Output 2.2 ad 2.6) - Development of management actions for additional areas added to existing PAs – 20 days at $600/day = $12,000 (Output 2.3) |
| 8 | Local consultants- $124,992 - Forest resource mapping and inventory and training local staff in forest and biodiversity asset monitoring – 50 days at $192/day = $9,600 (Output 2.1) - Assessment of biodiversity values and threats of KBAs, forest restoration and connectivity, and annual planning support and training on survey techniques – 120 days at $192/day = $23,040 (Output 2.2) - Organization support for provincial multi-sectoral coordination and governance arrangements for forest management and annual planning support, - 52 days at $192/day = $9,984 (Output 2.2) - Facilitation support for assessment of poaching risk management mapping and prioritizing locations for risk management – 40 days at $192/day = $7,680 (Output 2.3) - Capacity needs assessment for community forest management, training, establishment of participatory processes, - 85 days at $192/day = $16,320 (Output 2.4) - Technical support for establishment of forest- based enterprises, training, business development and value chain and financial mechanisms, women livelihood development – 100 days at $192/day = $19,200(Output 2.4 and 2.5) - Gender mainstreaming training and risk management=30 days at $192/day = $5,760 (Output 2.5) - Forest restoration planning and management & manual preparation = 100 days at $192/day = $19,200 (Output 2.6) - Financial incentive mechanism assessment, PFES strengthening and new options- 74 days at $192/day = $14,208 (Output 2.7) |
| 9 | Travel - $108,000 Lump sum to cover travel of international and national consultant, contractual companies, national & Provincial project team, FMU and PA staff for work and training related travel, workshop travel costs etc. |
| 10 | Contractual Services – Companies - $574,000 - Forest and biodiversity assessment and inventory, guidelines and standards for information collection in FMUs and provision of technical support and equipment for resource inventory - $165,000 (Output 2.1) - Provision of training for PA extension and management, proposal of new conservation area, operational plan development, conservation management planning and SMART patrol development - $182,000 (Output 2.3) - Training and management of community forest co-management and design and implementation of financial models - $99,000 (Output 2.4) - Livelihood support for women-based enterprise development and management - $52,000 (Output 2.5) - Technical and implementation support to FMUs for forest restoration -$76,000 (Output 2.6) |
| 11 | Equipment & supplies - $7,000 For livelihood support activities |
| 12 | Workshops, training and conferences - $294,100 - Meetings and workshops for review of status of monitoring and inventory, methodology development, guidelines and standards development and training of staff for of all FMUs for biodiversity and forest inventory - Ba River conservation and forest management strategy development -$41,600 (Output 2.1) - Training and workshops for landscape and site-level integration of biodiversity into SFM plans and operations, annual plan development etc. - $44,000 (Output 2.2) - Training and workshops, community meetings etc. for PA management plans development and operationalization of expansion of existing PAs - $40,000 (Output 2.3) - Consultation, workshops and training for Poaching risk assessment and roadmap, SMART patrol establishment and monitoring - $59,000 (Output 2.3) - Consultation meetings, workshops and training sessions for training of PA and FMU staff in co-management, support community capacity building for co-management, community small enterprise and value chain programs- $45,000 (Output 2.4) - Consultation meetings, workshops and training sessions for livelihood and small enterprise development for women, including nursery techniques, etc. $46,500 (Output 2.5) - Training workshops for forest restoration, monitoring and management for forest managers - $5,000 (Output 2.6) - Training and workshops for enhancing management of PFES and new options for financial incentives - $13,000 (Output 2.7) |
| Component 3: Gender mainstreaming replication and knowledge exchange |  |
| 13 | International Consultants - $39,000 - Development of communication and knowledge sharing best practices – 20 days at $600/day = $12,000 (Output 3.2) - Mid- term and terminal evaluations – 15 days each at $600/day = $18,000 (Output 3.4) - Establishment of monitoring framework for project monitoring – 15 days at $600/day -$9,000 (Output 3.4) |
| 14 | Local consultants - $107,520 - To conduct training of forest managers on integrating conservation and SFM outcomes in forest plans and management – 120 days at $192/day = $23,040 (Output 3.1) - To document and support development of best practices, including manuals and establishment of website and social media platforms – 3 national consultants – 175 days total at $192/day = $33,600 (Output 3.2) - Gender safeguard consultant – 60 days at $192/day = $11,520 (Output 3.3) - Preparation of targeted ESMP, IPP, SESA and Targeted ESIA – 115 days at $192/day = $22,080 (Output 3.3) - Monitoring and evaluation support – 20 days at $192/day = $3,840 (Output 3.4) - Consultant for inception, MTR and TE – 70 days at $192/day = $13,440 (Output 3.4) |
| 15 | Travel – $52,385 Travel covers national consultants to visit FMUs and PAs in relation to implementation of communication, training of forest managers, monitoring, gender and safeguard oversight and MTR and TE evaluations |
| 16 | Contractual Services - $65,000 (a) Support for communication and awareness programs - $65,000 (Output 3.2) |
| 17 | Training, Workshops and conferences - $106,971 - Consultation meetings and workshops and training for forest managers and field staff for conservation, SFM and co-management - $32,500 (Output 3.1) - Consultation workshops, training workshops and meetings for documentation, dissemination and promotion of best practices - $18,471 (Output 3.2) - Consultation workshops, training and meetings relation to gender, safeguards, etc. - $26,000 (Output 3.3) - Consultation workshops and workshops relating to M&E - $30,000 (Output 3.4) |
| Project Management |  |
| 18 | National project management unit staff – $80,915. Other PMC costs associated with travel, supplies, comms, IT, office, etc will be paid from co-financing |
| 19 | Professional services - $23,000 Project Assurane Activity (Micro assessment, audits, spot checks) at $5,750/year |

- Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Vietnam and UNDP, signed on (date).  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by the Ministry of Agriculture and Rural Development (MARD) (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

The designations employed and the presentation of material on this map do not imply the expression of any opinion whatsoever on the part of the Secretariat of the United Nations or UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

- Risk Management

Consistent with the Article III of the SBAA, the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner. To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment.

a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

- The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds. The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document. Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement. Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note: The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

- Mandatory Annexes

      - GEF Budget Template

      - Project Map and geospatial coordinates of the project area

      - Multiyear workplan

      - UNDP Social and Environmental Screening Procedure (SESP)

      - UNDP Risk Register

      - Overview of Project Staff and Technical consultancies

      - Stakeholder Engagement Plan

      - Environmental Social Management Framework (ESMF) or other SES frameworks/plans if required

      - PPG Consultations

      - Gender Analysis and Action Plan

      - Procurement Plan

      - GEF Core indicators

      - GEF Taxonomy

      - METTS (14a) and FAO-EXACT (14b)

      - Provincial Capacity Development Scorecards [Phu Yen (15a) and Gial Lai (15b)]

      - Summary Analysis and Project Implications/Opportunities for Covid-19

      - Summary Analysis and Project Implications for Climate Change Considerations

      - Livelihood Options

      - Forest Restoration Strategy

      - Co-financing Letters

      - HACT Assessment

      - UNDP GEF Audit Checklist

Meyfroidt and Lambin, 2008 Forest transition in Vietnam and its environmental impacts, Global Change Biology, 14

D.M. Olson, E. Dinerstein, E.D. Wikramanayake, et al. Terrestrial ecoregions of the world: a new map of life on earth

BioScience, 51 (2001)

G.A. Krupnick, W.J. Kress (2003). Hotspots and ecoregions: a test of conservation priorities using taxonomic data. Biodiversity and Conservation, 12)

Stattersﬁeld, A. J., Crosby, M. J., Long, A. J. and Wege, D. C. (1998) Endemic bird areas of the world: priorities for Biodiversity Conservation. Cambridge, U.K. BirdLife International. (BirdLife Conservation Series No. 7)

National Biodiversity Strategy and Action Plan (2015)

National Biodiversity Strategy and Action Plan (2015)

The information in this map do not imply the expression of any opinion whatsoever on the part of the United Nations Development Programme concerning the legal status of any country, territory, city or area or of its authorities, or concerning the delimitation of its frontiers or boundaries.

https://panorama.solutions/en

Baseline, mid-term and end of project target levels must be expressed in the same neutral unit of analysis as the corresponding indicator. Baseline is the current/original status or condition and needs to be quantified. The baseline can be zero when appropriate given the project has not started. The baseline must be established before the project document is submitted to the GEF for final approval. The baseline values will be used to measure the success of the project through implementation monitoring and evaluation.

Target is the change in the baseline value that will be achieved by the mid-term review and then again by the terminal evaluation.

Outcomes are medium term results that the project makes a contribution towards, and that are designed to help achieve the longer-term objective. Achievement of outcomes will be influenced both by project outputs and additional factors that may be outside the direct control of the project.

These numbers will be validated in Year 1 of the project

See https://www.thegef.org/gef/policies_guidelines

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

Includes cost for international consultant ($9,000), national consultant ($3,840) and travel and M& E related workshop costs ($17,160)

Includes cost of NC for developing monitoring framework ($3,840), travel and workshop/meeting costs ($21,940), Cost of monitoring will be borne by national project coordinator

Includes cost of IC ($9,000), NC ($4,800) and travel costs ($6,200)

Includes cost IC ($9,000), NC ($4,800) and travel and travel costs ($7,085)

Data collection methods should outline specific tools used to collect data and additional information as necessary to support monitoring. The PIR cannot be used as a source of verification.

Beneficiary Representatives are representatives from the provincial people’s committees. Their functions will be separate from the project implementation.

The MARD Leader can nominate a senior official on his/her behalf.

These members will be specifically nominated at the project implementation phase.

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.