| Promoting Resilience Through Integrated Approach to Water, Environment and Disaster Risk Management in Somalia Final Completion Report |  |  |
| --- | --- | --- |
|  |  | A national youth consultation workshop on green jobs and entrepreneurship skills in Somalia, involving young innovators and climate advocates to explore high-potential climate-smart sectors. Photo: Ministry of Youth & Sport & Ministry of Environment and Climate Change |
| ### Executive Summary ## Promoting Resilience Through an Integrated Approach to IWRM, Environmental Governance, and DRR The Sida/UNDP supported initiative has brought about significant improvements in Somalia’s capacity to address the interlinked challenges of water scarcity, environmental degradation, climate change, and disaster risks.Through a comprehensive and integrated approach—combining Integrated Water Resources Management (IWRM), Environmental Governance, Disaster Risk Reduction (DRR), and Youth Climate Platform —the project strengthened institutions, enhanced community resilience and elevated Somalia’s role in building resilience at local, state and national discourse . ### Integrated Water Resources Management (IWRM) The project marked a historic milestone with the launch of Somalia’s first-ever Master of Science programme in Integrated Water Resource Management at Somali National University. The programme enrolled 35 students—30% women—and graduated as skilled professionals, establishing a gender-inclusive cadre equipped to lead sustainable water governance. Beyond academia, over 738 federal and state officials (M: 514, F: 224) were trained in inclusive IWRM approaches, embedding practical tools and technical expertise across all governance levels. Institutional capacity was further boosted by the creation of a dedicated Geospatial Unit within the Ministry of Energy and Water Resources (MoEWR), fully equipped and staffed by 20 trained specialists to drive data-driven water resource planning and monitoring. The project institutionalized multi-level IWRM coordination platforms, strengthened leadership engagement between federal and state actors, and produced peer-reviewed research to inform policy and academic advancement. These actions directly support SDGs 6 (Clean Water and Sanitation), 13 (Climate Action), 4 (Quality Education), and 5 (Gender Equality), benefiting both decision-makers and marginalized communities through improved water access, equitable governance, and enhanced resilience to droughts and floods. ### Environmental Governance Strengthening Somalia’s environmental governance was central to addressing ecosystem degradation and building climate resilience. The project enhanced institutional capacities of the Ministry of Environment and Climate Change, state ministries, and the Banadir Regional Authority (BRA) to enforce environmental compliance in line with national legislation and global best practices. The National Environmental Strategy and Action Plan (NESAP) was operationalized at federal and municipal levels, and National Environmental Quality Standards (NEQS) were developed and validated, creating clear benchmarks for monitoring and accountability. Working with Somali National University, the project advanced evidence-based policymaking through targeted environmental studies. It also developed Somalia’s first Integrated Solid Waste Management Strategy and operational roadmap, embedding circular economy principles in urban services to reduce pollution and improve resource efficiency. Public awareness was amplified through nationwide campaigns, including World Environment Day, fostering behavioral change in plastic waste management. Over 400 youth leaders (approximately half women) were mobilized to champion marine conservation, climate security, and integration of environmental targets into municipal planning. Collectively, these measures contribute to SDGs 13 (Climate Action), 12 (Responsible Consumption and Production), 15 (Life on Land), and 14 (Life Below Water), improving environmental health and resilience for both urban and rural communities. ### Disaster Risk Reduction (DRR) The project spearheaded a paradigm shift from reactive disaster response to proactive risk reduction, working closely with the Somalia Disaster Management Agency (SoDMA) and the Ministry of Humanitarian Affairs and Disaster Management (MoHADMs). Somalia’s first comprehensive and gender-responsive National DRR Plan was finalized, creating a unified framework for risk mitigation across federal and state institutions. Capacity-building initiatives engaged 237 officials (M: 149, F: 88) in gender-responsive DRR frameworks, while 15 municipalities and high-risk districts developed tailored DRR plans. Local disaster volunteer networks—221 members strong—were established to support grassroots disaster preparedness and recovery. The National Emergency Operation Centre (NEOC) was operationalized and upgraded to improve multi-agency emergency coordination, while community-based early warning systems were rolled out in Federal Member States. These initiatives have improved the timeliness and effectiveness of disaster alerts, strengthened local preparedness, and reduced vulnerability to hazards such as droughts and floods. They directly contribute to SDGs 13 (Climate Action), 11 (Sustainable Cities and Communities), and 5 (Gender Equality). ### Somalia Youth Climate Platform (SYCP) Youth engagement emerged as a transformative cross-cutting achievement. The Somalia Youth Climate Platform (SYCP) was established as a national hub for youth-led climate action, training over 350 young leaders (50% women) in climate resilience, environmental sustainability, and disaster preparedness. The platform developed a strategic roadmap, launched a dedicated website and initiative database, and built strong partnerships with the Ministry of Youth and Sports, the Ministry of Environment and Climate Change, UN agencies, and NGOs. Somali youth actively influenced climate policy, contributing to Somalia’s Nationally Determined Contributions (NDCs) and representing the country at COP27 and COP28. They also engaged in Stockholm+50 and Green SDG dialogues, ensuring that local solutions and gender perspectives shaped global climate discourse. By integrating climate-security into the Youth, Peace, and Security National Action Plan in four states, the SYCP positioned youth as key actors in building climate-resilient peace, contributing to SDGs 13 (Climate Action), 5 (Gender Equality), and 16 (Peace, Justice, and Strong Institutions). ### Overall Impact The project has built a skilled, gender-inclusive cadre of professionals, empowered a new generation of climate leaders, strengthened environmental and disaster governance systems, and mobilized communities across Somalia. Direct beneficiaries include over 1,700 trained officials, academics, youth leaders, and volunteers, while millions of Somalis—particularly marginalized, climate-vulnerable populations—stand to benefit indirectly through improved resource management, reduced environmental degradation, and enhanced disaster preparedness. By aligning with Somalia’s National Development Plan and advancing multiple SDGs, this integrated approach has laid the foundations for sustainable, inclusive, and climate-resilient development—creating inroads and positioning Somalia to better safeguard its people, ecosystems, and future prosperity.. Project data Project ID; Project: 122656 (Output: 00128746). Geographical coverage; All regions. Project duration; From 23 November 2020 to 31 March 2025. Total approved budget; US$ 8,866,045.58. Programme funding level; US$ 8,866,045.58. Estimated delivery rate; 100%. Participating UN entities; The project activities has been implemented in close coordination and collaboration with a number of UN agencies in Somalia, including UNEP, UN OCHA, FAO, UN DRR etc.. Implementing partners; UNDP. Project beneficiaries; Disaster vulnerable population. NDP pillar; 4. UNCF Strategic Priority; 1. SDG. Gender Marker; 2. Focal persons; Tarik-ul-Islam, Chief Technical Adviser, UNDP Somalia, tarik.islam@undp.org, +252 619 259 439 Rashid Mohamed, DRR Coordnator, UNDP Somalia Rashid.mohamed@. |

Report submitted by:

|  | PUNO | Report approved by: | Position/Title | Signature |
| --- | --- | --- | --- | --- |
| 1 | UNDP | Lionel Laurens | Resident Representative |  |

Section 1: Executive summary

Brief introduction to the project UNDP Somalia and the Swedish International Development Agency (SIDA) have signed an agreement to build the capacity of the Federal Government of Somalia (FGS) and the Federal Member States (FMS) with an overarching focus on promoting resilience of the water-stressed, ecologically-fragile, and disaster vulnerable communities in the country. The project promotes an integrated approach and addresses capacity gaps and national priorities for water, environment, and disaster risk management. It unleashes the potential of their synergies into a coherent and more integrated programming framework. The project builds on past experiences, complements and aligns with national initiatives such as the National Development Plan (NDP-9) for 2020–2024 and the ongoing National Transformation Plan for 2025–2029 and calls for an integrated approach to deliver results on the ground in the areas of integrated water resources management, environmental governance, and disaster risk management. The overall project objective and the three inter-linked components are summarized as follows: Overall objective: The project aims to build the capacity of the Somali authorities in their efforts to promote sustainable and resilient development through targeted support in the areas of integrated water resource management, environmental governance, and disaster risk reduction. With funding support from the Swedish Government, UNDP will undertake targeted interventions in three inter-related components in achieving the above objective. Component 1 – IWRM: Within the integrated approach to promoting sustainable and resilient development in Somalia, the specific objective of the component1 will be to build targeted capacities, both at the individual and institutional levels, to promote integrated water resource management (IWRM) in Somalia. In doing so, Somali institutions and the officials will be equipped with enhanced skills, tools, and systems on IWRM that would promote effective decision making on water allocations and efficient utilization of water resources at all levels. Component 2 – Environmental Governance: The specific objective of the component2 will be to enhance the capacities of the Somali authorities, both at federal and state levels, to address the ecological challenges and priorities toward improved environmental governance in the country. In doing so, the Directorate of Environment and the Federal Member States will be capacitated towards strengthened environmental management, effective monitoring, and assessment and raise awareness through environmental education and advocacy. Component 3 – Disaster Risk Reduction: The objective of this component is to strengthen Somali institutions at Federal and State levels and put in place capacities, systems, and tools to support the transition from a culture of reactive responses to the practice of comprehensive disaster risk management in Somalia. A government-wide, multi-hazards, and multi-stakeholders’ approach will be adopted to integrate DRR in the planning and programming, across sectors and levels, focusing on promoting resilience of the disaster vulnerable communities.

Situation update / Context of the Project Period The UNDP/Sida-funded initiative, "Promoting Resilience Through an Integrated Approach to Water, Environment, and Disaster Risk Management in Somalia" has delivered measurable outcomes despite the volatile political and security context, severe climate shocks, and fiscal constraints. It contributed to Somalia’s broader development goals and demonstrated a model for integrated, inclusive, and climate-resilient programming by strengthening institutional frameworks, building human capacity, empowering youth, and enhancing community resilience. The achievements and lessons learned from this initiative position Somalia to scale up successful pilots and advance a transformative agenda aligned with the National Transformation Plan and global sustainability commitments. While the project has made significant strides in fostering resilience and sustainable development, ongoing challenges such as complex interplay of political, security, and humanitarian challenges in Somalia require continued commitment and adaptive strategies to ensure the well-being of vulnerable communities in the region. In its first year, the project faced delays primarily due to the complex political landscape marked by a protracted impasse over indirect elections. Despite some progress in adhering to the electoral agreements from September 2020 and May 2021, complaints of irregularities and a lack of transparency plagued the process. While the upper house elections were completed, the lower house elections extended into early 2022. The security situation remained volatile, with Al-Shabaab as the primary threat, maintaining operational strength despite intensified military efforts. Furthermore, Somalia faced an acute humanitarian crisis exacerbated by severe drought conditions, which led the Federal Government to declare a state of emergency. The drought, compounded by COVID-19, severely impacted livelihoods, resulting in widespread displacement and food insecurity. During this period, consultations were held with national counterparts and donors to develop Annual Work Plans (AWPs) and Letters of Agreements (LoAs), emphasizing the critical role of the Ministries of Humanitarian Affairs and Disaster Management in fostering sustainable development. In its second year, the project grappled with prolonged electoral processes and heightened security risks while also addressing drought emergencies. Leadership transitions at the federal level influenced the pace of implementation, particularly in environmental governance and disaster risk reduction components. The completion of the electoral process culminated in the inauguration of the eleventh Parliament and the election of President Hassan Sheikh Mohamud. While the elections were generally viewed as peaceful, ongoing security threats from Al-Shabaab persisted, despite some successful military operations against the group. The humanitarian situation remained dire, with the drought declared historic, leading to increased humanitarian needs affecting nearly half of the population. Project activities continued, focusing on strengthening institutional frameworks and establishing partnerships at federal and state levels. In its third year, the project encountered delays due to heightened security risks and the need for institutions to respond to drought impacts and El Niño-induced flooding. However, new partnerships emerged, particularly with the Ministry of Youth and Sports, emphasizing youth participation in climate resilience initiatives. A Midterm Evaluation highlighted the effectiveness of the project in promoting gender equality and recommended scaling successful practices, including sustained funding for scholarships and capacity-building initiatives. The evaluation underscored the importance of public awareness, community involvement, and the coordination of efforts among federal member states, local institutions, and civil society organizations. Significant achievements included the establishment of the Youth Climate Platform, enhancing youth engagement in climate action, and promoting sustainable practices through training workshops. Despite ongoing humanitarian challenges, including a severe drought affecting agricultural productivity, Somalia managed to achieve moderate economic recovery and significant milestones, such as joining the East African Community and reaching the Heavily Indebted Poor Countries (HIPC) completion point etc. As the project approached its fourth year, critical funding shortfalls posed significant challenges, delaying key interventions and hindering momentum in resilience-building efforts. Nevertheless, the project focused on optimizing available resources and proposed a cost extension to facilitate the completion of ongoing initiatives, particularly the Master’s Programme in Integrated Water Resource Management. Key accomplishments included fostering partnerships with Federal Member States to enhance disaster risk reduction and resilience programming. The project engaged diverse community groups in disaster preparedness activities, promoting principles of "building back better and greener." Initiatives targeting coastal communities addressed marine pollution and biodiversity conservation, while the successful completion of the IWRM Master's Programme equipped students with essential skills for addressing water resource challenges. Despite notable achievements, the humanitarian crisis in Somalia continued to worsen due to climate shocks, conflict, and poverty, with millions still in need of assistance. As Somalia launched its National Transformation Plan (2025–2029), which emphasizes inclusive growth, resilience, and sustainable development, the project’s achievements and lessons learned positioned it as a model for integrated, inclusive, and climate-resilient development. On the security front, Al-Shabaab remains a significant threat, capitalizing on gaps in governance and security. The transition from ATMIS to Somali-led security, supported by AUSOM, marks a pivotal moment for Somalia. While this transition strengthens national sovereignty, it also brings risks that require ongoing international backing and strong institutional support. The mission faces persistent threats from Al-Shabaab, funding constraints, and coordination challenges. Its priorities are enhancing command structures, fostering political unity, advancing coordinated counterterrorism efforts, and ensuring stable financial resources to reinforce security and resilience across Somalia.

Highlights of the Project Period Integrated Water Resource Management (IWRM) - Somalia launched its first MSc in IWRM at Somali National University, graduating 34 students (30% women), building a new generation of water governance professionals. - Over 1,000 federal and state officials were trained in IWRM, significantly boosting institutional capacity for inclusive water governance. - A Geospatial Unit was established at MoEWR, with 20 staff (M: 17, F: 3) trained to support data-driven water resource planning and monitoring. - The project produced 34 peer-reviewed research papers, enriching national and global water policy and academic discourse. - Multi-level coordination was institutionalized through IWRM Leadership Forums, aligning federal and state water governance efforts. - IWRM training curricula were modernized with WaterNet and experts to meet international standards and local needs. - A regional partnership with IGAD/ICPAC laid the groundwork for a Geospatial Centre to support transboundary water monitoring. Environmental Governance - Government institutions enhanced their capacity to enforce environmental compliance and align with global environmental agreements. - The National Environmental Strategy and Quality Standards were localized and operationalized across federal and municipal levels. - Technical and operational capacities for environmental monitoring and enforcement were expanded to support SDG progress. - Academic partnerships with Somali National University promoted evidence-based policymaking through impactful environmental research. - Somalia developed a national solid waste strategy integrating circular economy principles into municipal waste management. - Over 400 youth led marine conservation and climate security initiatives, embedding environmental SDGs into local governance. - Public campaigns raised awareness on plastic waste and circular economy, strengthening community resilience to degradation. - Municipalities developed SDG-aligned environmental action plans, translating national goals into local priorities. Disaster Risk Reduction (DRR) - Somalia institutionalized its first gender-responsive National DRR Plan, unifying risk mitigation across all government levels. - Local DRR financing frameworks were introduced and implemented in nine high-risk districts to support sustainable preparedness. - Municipal and district-level DRR plans were developed in 15 locations, empowering local authorities with tailored strategies. - National and state officials received extensive training, shifting disaster management from reactive to proactive approaches. - The National Emergency Operation Centre was upgraded, enhancing Somalia’s emergency coordination and response capacity. - A gender-inclusive DRR framework was adopted, training 237 officials to embed equity in risk management. - A Disaster Volunteer Network of 221 members was established to support grassroots disaster response and recovery. - Urban resilience was strengthened through recovery guidelines, infrastructure upgrades, and municipal capacity building. - National campaigns raised awareness on climate risks and sustainable land management practices. - Drought preparedness improved through early warning systems and coordinated policy implementation. - Community-based early warning systems were established across FMS, enhancing local disaster alert capabilities. - Somalia aligned its DRR priorities with the Sendai Framework through a successful Mid-Term Review with UNDRR-ROAS. Somali Youth Climate Platform (SYCP) - SYCP became a national hub for youth climate action, strategic roadmap, and partnerships with MoYS, MoECC, and UN agencies. - Somali youth participated in COP27, COP28, and national consultations, contributing to Somalia’s NDC and global climate policy. - Climate-security was integrated into youth agendas and the Youth, Peace, and Security National Action Plan in four states. - The SYCP website was launched to enhance coordination, visibility, and engagement among youth-led climate initiatives. - Targeted campaigns improved youth awareness of climate funding avenues, increasing participation in resilience-building programs. - Empowered youth volunteers increased disaster preparedness across Somalia’s vulnerable regions, directly contributing to resilience against climate-related shocks.s

Section 2: Progress Report Results Matrix

| OUTCOME STATEMENT The communities in Somalia are capacitated to become resilient with demonstrated ability to respond, recover and sustainably manage the shocks and stresses from water, environment, and disaster risks. |  |  |  |
| --- | --- | --- | --- |
| SUB-OUTCOME 1 STATEMENT Building capacities of the authorities and institutions at all levels to empower and promote resilience of the water-stressed, ecological, and disaster vulnerable communities through integrated support in the areas of sustainable water resource management, environmental governance, and disaster risk reduction. |  |  |  |
| COMPONENT 1: INTEGRATED WATER RESOURCE MANAGEMENT (IWRM) |  |  |  |
| Output 1.1: Enhanced Individuals Capacities for IWRM |  |  |  |
| INDICATOR | TARGET | PROGRESS ON OUTPUT INDICATOR |  |
|  |  | Duration of the Project | CUMULATIVE (2020 - 2025) |
| 30 students completed Masters Level Degree Project – (10 women and 20 men) | 30 | 35 | 35 |
| 90 officials trained from FGS & FMS (30 women and 60 men). | 90 | 0 | 118 (85; F:33) |
| 15 seminars on seminars organized a total of 450 participants at Federal and State levels (one-third women participants) | 15 | 0 | 11 |
| 180 officials trained from the FGS/FMS (one-third women participants) | 180 | 0 | 65 |
| 20 training events to be held at local level – each training event to have 20 participants. Total 200 participants trained (1/3rd of total participants to be women). | 200 | 0 | 4,024 |
| 80 Officials/staff will be supported to enhance their skills through distance learning courses. | 80 | 0 | 68 |
| Output 1.2: Output Enhanced Institutional Capacities for IWRM |  |  |  |
| 1 (one) fully functional Geospatial technology unit | 1 | 1 | 1 |
| 7 Sets (1 for MoEWR and 6 for relevant institution in FMS | 7 | 0 | 7 |
| Institutional Coordination System for IWRM formally adopted. (2 technical workshops held and a road map for improved water sector coordination piloted.) | 2 | 0 | 3 |
| COMPONENT 2: ENVIRONMENTAL GOVERNANCE |  |  |  |
| Output 2.1: Environmental management system strengthened at Federal and State level |  |  |  |
| 175 officials/staff trained including TOR for 30 official/staff on environmental governance and improved coordination | 175 | 0 | 129 (M:93; F:36) |
| One Environmental Adviser hired; 20 officials trained on capacity building to implement environmental strategy | 1 | 0 | 1 |
| 7 Training/workshop held to track progress on environmental SDGs | 7 | 0 | 7 |
| Output 2.2: Improved capacity for environmental monitoring and assessment |  |  |  |
| One GIS unit established, and 7 set equipment provided | 7 | 0 | 7 |
| One set of NEQS finalized | 1 | 0 | 1 |
| 20 Officials/staff (trained at Federal) and 60 Officials/staff trained at state levels on environmental monitoring and enforcement | 50 | 135 (M:77 F:58) | 205 (M:129; F:76) |
| 30 officials trained and one state of environment report finalized | 30 | 0 | 167 (M:106; F:61) |
| Output 2.3. Environmental awareness raised through education and advocacy at all level |  |  |  |
| 15 research studies undertaken | 15 | 0 | 10 |
| 30 Advocacy/campaigns held (30% women participants) | 30 | 6 | 20 |
| 1 IWSM policy developed, 50 officials trained, and 14 advocacy events held involving relevant authorities, municipalities and stakeholders | 50 | 0 | 55 (M:38; F:17) |
| COMPONENT 3: DISASTER RISK REDUCTION |  |  |  |
| Output 3.1: Somalia disaster risk management system strengthened at the federal, state and local levels |  |  |  |
| DRR Plan and DRR Strategy prepared following a gendered and multi-hazards’ approach | 2 | 0 | 2 |
| NEOC staffs trained and supported to develop and implement the operational plan | 30 | 0 | 185 (M: 113 F:72) |
| Total 7 DRM plans prepared following a gendered and multi-hazards approach | 7 | 0 | 7 |
| Output 3.2: Professional skill enhancement programme designed, instituted and implemented to drive the risk reduction paradigm in Somalia at all level |  |  |  |
| 1 DRR Learning and Advocacy Strategy prepared following a gendered approach at all levels | 1 | 0 | 1 |
| 9 DRR Training events (including TOT) organized at the Federal and States level | 9 | 0 | 12 |
| 6 nos. Communication pieces prepared and 6 DRR Advocacy events organized with 30% women participation | 6 | 0 | 6 |
| Output 3.3: Disaster risk reduction mainstreamed into the national planning and programming in Somalia |  |  |  |
| 6 DRR focal points designated with defined roles in 6 priority sector maintaining gender parity | 6 | 0 | 6 |
| Somalia DRR Mainstreaming tool incorporates women’s needs and special role | 1 | 0 | 1 |
| BBB for recovery of community infrastructure following a gendered approach | 1 | 0 | 2 |
| Output 3.4: Enhanced community preparedness through end-to-end early warning dissemination and instituting disaster volunteers’ network |  |  |  |
| EW needs assessment reflect special disaster warning messaging for the women in vulnerable communities | 1 | 0 | 1 |
| 18 Training courses conducted at various levels in a gender-balance way | 11 | 61 | 26 |
| 1 Guiding tool for mobile-bases EW dissemination developed for Somalia | 1 | 0 | 0 |
| Output 3.5: Capacity enhanced to promote urban resilience in Somalia |  |  |  |
| 16 DRR Training events with gender-balanced participation | 16 | 7 | 17 |
| 16 Urban DRR plans prepared following a gendered approach | 16 | 0 | 8 |
| Output 3.6: Local disaster resilience fund designed and operationalized to enhance community resilience to disaster/climate shocks |  |  |  |
| CRA Guidelines prepared following a gendered approach and incorporating special needs and vulnerabilities of the women | 1 | 0 | 1 |
| 30 LRRP prepared respecting the roles and special needs of the women | 30 | 0 | 24 |
| % of the delivered to implement LDRF at the local level | 80% | 0 | 100% |

Section 3: Narrative reporting on results

Progress towards outcomes OUTCOME STATEMENT The communities in Somalia are capacitated to become resilient with demonstrated ability to respond, recover and sustainably manage the shocks and stresses from water, environment, and disaster risks. COMPONENT 1: INTEGRATED WATER RESOURCE MANAGEMENT (IWRM) Brief Narrative Overview of Progress on Component 1: IWRM Somalia achieved a transformative milestone in developing its human capital for Integrated Water Resource Management (IWRM) through the successful establishment and institutionalization of the country's first MSc program in IWRM at Somali National University. As a result, 34 professionals (8 women), have acquired advanced expertise in sustainable water management. This well-trained cadre is now driving the country's efforts toward more effective and sustainable water resource utilization, contributing to resilience against climate-induced water challenges. Institutional capacities in Somalia have been transformed through strategic interventions. The establishment of the Geospatial Centre and national coordination platforms has strengthened the nation's ability to generate, analyze, and utilize data for informed decision-making. These enhanced capacities have enabled institutions to adopt a data-driven approach to water governance, fostering integration across sectors and levels of government. This foundational transformation has become a cornerstone for long-term water resource planning and management in Somalia. Advancements in gender equity and social inclusion within the water sector represent a notable achievement. Deliberate efforts to promote women’s participation have yielded a significant increase in their involvement, both in academic programs and capacity-building initiatives. This progress not only empowers women but also enriches the sector with diverse perspectives, ensuring more inclusive policies and practices in water governance. These achievements mark an important step toward addressing historical gender imbalances and enhancing social equity in Somalia’s water management sector. The project has delivered practical, on-the-ground impacts that are improving the livelihoods of communities across Somalia. Alumni of the training programs are now driving efforts in flood risk management, contributing to refined and actionable water policy frameworks, and implementing innovative approaches to climate-resilient water resource management. These tangible outcomes demonstrate the effectiveness of the project in creating solutions that directly address the pressing water challenges in Somalia, while also building a resilient and adaptive future for its agro-pastoral communities. Output 1.1: Enhanced Individuals Capacities for IWRM Establishment and Sustenance of Somalia’s First-Ever MSc Program in IWRM: The Master of Science in Integrated Water Resources Management (IWRM) was launched at Somali National University in partnership with the Ministry of Energy and Water Resources (MoEWR). The program successfully enrolled 35 students, and graduated 34 professionals, with 8 women earning their degrees. This innovative program integrates gender inclusivity and diverse academic disciplines such as GIS, hydrology, climate change, and water governance, equipping graduates with comprehensive skills essential for effective IWRM. Graduates have made substantial contributions to Somalia’s water governance institutions and the private sector, aligning their work with national priorities and supporting global Sustainable Development Goals (SDGs), particularly SDG 6 (Clean Water and Sanitation), SDG 11 (Sustainable Cities and Communities), and SDG 13 (Climate Action). Strengthened Technical Capacity for Integrated Water Resource Management (IWRM): Through a series of targeted training workshops conducted over the course of the project, a total of 448 individuals (307 men and 141 women), including senior government officials and key stakeholders, were equipped with advanced knowledge and practical skills in Integrated Water Resource Management (IWRM). These capacity-building efforts significantly enhanced technical expertise across federal and local institutions, fostering a deeper understanding of water governance, water quality management, and resource conservation. The trainings not only improved institutional readiness to implement IWRM principles but also promoted cross-sectoral collaboration and empowered participants to apply sustainable water management practices in policy, planning, and service delivery. As a result, Somalia now benefits from a more capable and coordinated workforce driving forward national water security and resilience objectives. Launch of a Postgraduate Internship Program: The launch of Somalia’s first postgraduate internship program in Integrated Water Resources Management (IWRM) in 2024 marked a transformative step toward embedding a new generation of water professionals into the country’s development agenda. This six-month structured program successfully bridged the gap between academic training and real-world application by placing MSc IWRM graduates in key government ministries, local organizations, international institutions, and UN agencies. Through hands-on engagement in policy development, water resource planning, and climate-resilient interventions, the interns applied their technical expertise to address pressing water security and governance challenges. As a result, Somalia now benefits from a growing pool of skilled, work-ready professionals contributing innovative, evidence-based solutions to strengthen national water governance, enhance institutional performance, and advance progress toward sustainable development and climate resilience. Advancing Research and Career Pathways in Water Resource Management: The MSc Programme in Integrated Water Resources Management (IWRM) at Somali National University significantly advanced Somalia’s research capacity and professional development in the water sector. A total of 34 research papers were produced by postgraduate students, addressing critical themes such as sustainable water management, climate change adaptation, water quality and pollution, governance and policy, and the socioeconomic impacts of water scarcity and flooding. These research outputs have contributed to national and global discourse, offering evidence-based insights to inform policy and practice. To complement academic achievement with professional integration, a dedicated career fair was organized, successfully connecting graduates with employment opportunities across government institutions, academia, and the private sector. This dual-track approach linking rigorous research with real-world career pathways has strengthened Somalia’s technical leadership in water governance and laid the foundation for a resilient, knowledge-driven water sector. Strengthening Professional Capacity and Partnerships in Somalia’s Water Sector: The MSc IWRM Internship Programme had demonstrably strengthened professional capacity in integrated water resources management in Somalia. A dedicated workshop brought together interns, Ministry of Energy and Water Resources (MoEWR) officials, and host institutions to exchange experiences, assess the programme’s impact, and chart future pathways. Interns reported enhanced technical competencies, improved problem-solving skills, and increased confidence in applying IWRM principles in real-world contexts. The event fostered stronger institutional linkages and partnerships, enabling sustained collaboration between academia, government, and industry. As a result, the internship programme not only accelerated the professional growth of participating graduates but also contributed to a pipeline of skilled water sector professionals ready to support national water governance and climate resilience goals. Output 1.2: Output Enhanced Institutional Capacities for IWRM Establishment of a National Geospatial Centre for Water Governance: As a cornerstone of Somalia’s transition toward data-driven water governance, the Ministry of Energy and Water Resources (MoEWR), in collaboration with IGAD/ICPAC, successfully established a state-of-the-art Geospatial Centre. This facility now serves as a national hub for real-time monitoring, analysis, and visualization of water resources using advanced Geographic Information System (GIS) technologies. The Centre has significantly enhanced institutional capabilities in environmental monitoring, disaster risk management, and evidence-based decision-making. A total of 20 professionals (M: 17, F: 3) from federal and state institutions were trained in geospatial technologies, equipping them with the skills to apply spatial data in planning, resource allocation, and climate resilience strategies. This achievement marks a transformative step in Somalia’s ability to manage its natural resources sustainably, respond to environmental risks proactively, and institutionalize geospatial intelligence as a core function of national water governance. Strengthened Institutional Coordination and Leadership for Sustainable Water Governance: Through strategic leadership and coordinated engagement, the Ministry of Energy and Water Resources (MoEWR) has established a robust governance framework that has transformed Somalia’s approach to sustainable water management. By fostering multi-stakeholder collaboration across federal and state levels, MoEWR facilitated the integration of global best practices, advanced knowledge sharing, and harmonized policy implementation. These efforts have significantly enhanced institutional capacity, secured long-term commitment to Integrated Water Resource Management (IWRM), and promoted unified action toward national water security and climate resilience. The outcomes of this initiative are reflected in improved coordination mechanisms, stronger stakeholder alignment, and measurable progress toward achieving Somalia’s Sustainable Development Goals (SDGs), particularly those related to clean water, climate action, and resilient communities. Strengthened GIS Infrastructure for Water and Environmental Governance: As part of its commitment to data-driven decision-making, the project successfully established a robust GIS infrastructure within the Ministry of Energy and Water Resources (MoEWR), significantly enhancing Somalia’s capacity for environmental monitoring and resource management. Through strategic collaboration with IGAD/ICPAC, essential hardware and software were procured to operationalize the Geospatial Unit, enabling real-time mapping and analysis of critical ecosystems—including rangelands, wetlands, and river basins. These high-resolution geospatial outputs have directly supported Integrated Water Resource Management (IWRM) planning and climate adaptation strategies. Additionally, 20 professionals (M: 17, F: 3) were trained in geospatial technologies, equipping institutions with the skills to apply spatial data for sustainable development, disaster risk reduction, and evidence-based policy formulation. This achievement marks a transformative step toward institutionalizing geospatial intelligence as a core pillar of Somalia’s environmental governance framework. COMPONENT 2: ENVIRONMENTAL GOVERNANCE Brief Narrative Overview of Progress on Component 2: Environmental Governance The project has successfully strengthened environmental governance at both federal and state levels, resulting in a significant enhancement of institutional capacities. A total of 219 officials, comprising 153 males and 66 females, participated in a tailored Training of Trainers (TOT) program, equipping them with the necessary skills and knowledge for effective environmental governance. This capacity-building initiative has empowered these officials to adapt and implement national environmental policies, which in turn has facilitated impactful climate change initiatives and advanced broader environmental conservation efforts across the nation. Moreover, the operationalization of the National Environmental Strategy and Action Plan (NESAP) has been a pivotal achievement. Through a series of consultation workshops, 216 officials (148 males, 68 females) identified critical actions and capacity needs vital for local-level environmental sustainability. This collaborative effort resulted in a strategic roadmap that lays the groundwork for coordinated nationwide implementation of NESAP, promoting sustainable development and ensuring the preservation of natural resources. The localization of environmental objectives aligned with the Sustainable Development Goals (SDGs) has also seen 277 individuals (175 males, 102 females) develop actionable strategies that resonate with local priorities, enhancing community engagement in environmental stewardship. In terms of monitoring and assessment, the project has significantly improved the capacity of environmental compliance mechanisms. Advanced training in Environmental Monitoring, Compliance, and Enforcement (EMCE) has equipped over 429 officials (262 males, 167 females) with essential skills for effective monitoring of environmental parameters. This enhancement has led to improved compliance with environmental regulations and a greater ability to tackle challenges related to ecological sustainability. Additionally, the development of National Environmental Quality Standards (NEQS) has aligned these standards with national policies and international benchmarks, establishing a robust framework that promotes environmental sustainability and public health. Moreover, the project has raised environmental awareness through extensive education and advocacy initiatives. A partnership with Somali National University resulted in research grants for graduate-level studies, fostering innovative solutions to critical environmental issues. Public awareness campaigns, including events on World Environment Day, engaged youth volunteers and catalyzed significant behavioral changes towards sustainable practices. Grassroots initiatives, particularly in marine conservation, mobilized over 400 youth volunteers, fostering community stewardship and enhancing local ecosystems. The development of the Integrated Solid Waste Management Strategy (ISWMS) involved 60 participants (41 males and 19 females) and has laid a comprehensive roadmap for improving waste management systems in Somalia, emphasizing sustainability and resource efficiency. Collectively, these outcomes underscore the project’s extensive impact on environmental governance, monitoring capacities, and community engagement. Output 2.1: Environmental management system strengthened at Federal and State level Enhanced Institutional Capacity for Environmental Governance: Through a tailored Training of Trainers (ToT) program, 219 officials, comprising 153 males and 66 females, across federal and state institutions significantly enhanced their knowledge and skills in sustainable environmental governance. This initiative empowered participants to effectively interpret, adapt, and implement national environmental policies, while integrating climate change considerations into planning and decision-making processes. The program fostered a network of trained facilitators capable of cascading knowledge within their respective institutions, thereby amplifying the reach and impact of environmental conservation efforts. As a result, Somalia now benefits from a more capable and responsive institutional framework, better equipped to lead climate initiatives, enforce environmental regulations, and advance national resilience and sustainability goals. Operationalization of the National Environmental Strategy and Action Plan (NESAP): The project successfully operationalized Somalia’s National Environmental Strategy and Action Plan (NESAP) through a participatory and inclusive process that engaged 216 government officials (148 males, 68 females) across federal and state levels. A series of national consultation workshops facilitated the identification of priority actions, institutional capacity needs, and localized implementation pathways for environmental sustainability. These efforts culminated in the development of a strategic roadmap that aligns national environmental objectives with local realities, enabling coordinated, effective, and accountable implementation of NESAP. The process strengthened institutional ownership, promoted cross-sectoral collaboration, and laid the groundwork for long-term environmental stewardship, contributing directly to Somalia’s sustainable development and natural resource preservation goals. Localization of Green SDGs for Community-Led Environmental Action: Through a series of participatory workshops, 277 individuals (175 males, 102 females) collaboratively localized the environmental dimensions of the Sustainable Development Goals (SDGs) at the municipal level, aligning global targets with Somalia’s local priorities. This inclusive process resulted in actionable strategies that integrate environmental sustainability into local governance, planning, and service delivery. By fostering community engagement and empowering local actors, the initiative strengthened ownership of environmental stewardship and promoted the adoption of sustainable practices. The outcome is a more grounded and responsive framework for advancing Green SDGs in Somalia, reinforcing national commitments to climate resilience, biodiversity protection, and sustainable resource management. Strengthened Local Environmental Governance: Through targeted capacity building initiatives, Ministries at the Federal Member State (FMS) level have significantly enhanced their capacity to lead and coordinate environmental governance. A total of 167 stakeholders (106 males, 61 females) were actively engaged in participatory processes that enabled the identification and prioritization of actionable strategies tailored to local environmental challenges. This inclusive and collaborative approach led to the development of comprehensive action plans that clearly define roles and responsibilities of key actors, promote transparency and accountability in decision-making, and foster inter-sectoral coordination and stakeholder ownership. As a result, local institutions are now better equipped to implement and monitor environmental policies, contributing to more resilient and sustainable environmental management systems across the FMS regions. Output 2.2: Improved capacity for environmental monitoring and assessment Strengthened Environmental Monitoring, Compliance, and Enforcement Mechanisms: Somalia’s Ministries of Environment and Climate Change at both federal and state levels significantly enhanced institutional capacity for environmental monitoring, compliance, and enforcement by training a total of 429 government officials (262 males, 167 females). These officials were equipped with advanced tools and methodologies aligned with international standards such as the Paris Agreement, enabling them to monitor key environmental indicators—including air and water quality, biodiversity, and resource use—and apply Monitoring, Reporting, and Verification (MRV) systems to track greenhouse gas emissions and climate actions. The initiative addressed systemic challenges such as governance fragility and infrastructure gaps by promoting decentralization of enforcement, strengthening federal-state coordination, and leveraging private sector partnerships. These efforts have resulted in a more inclusive, accountable, and resilient environmental governance framework that supports sustainable resource management and enhances Somalia’s climate resilience. Establishment of National Environmental Quality Standards (NEQS): The Ministry of Environment and Climate Change (MoECC) achieved a transformative milestone in environmental governance by developing, reviewing, and validating Somalia’s first-ever National Environmental Quality Standards (NEQS) through a collaborative, multi-stakeholder process. Aligned with national policies and international frameworks such as the Paris Agreement, the NEQS now serve as a foundational regulatory instrument for safeguarding environmental integrity, protecting public health, and guiding sustainable development. The process engaged technical experts from key institutions and emphasized inclusivity, institutional capacity-building, and policy coherence. It also addressed implementation challenges by recommending practical measures such as translating the standards into Somali, enhancing public awareness, and strengthening enforcement mechanisms. As a result, Somalia now possesses a robust, context-specific environmental regulatory framework that enhances accountability, promotes compliance, and supports long-term resilience to environmental and climate-related risks. Strengthened Institutional Capacity for Data-Driven Environmental Management: The project significantly enhanced Somalia’s institutional capacity for data-driven and evidence-based environmental governance by establishing and operationalizing fully functional Geographic Information Systems (GIS) units within key federal and state ministries. Through targeted training of 226 officials (140 men and 86 women), the initiative built advanced technical expertise in the application of GIS for environmental monitoring, planning, and decision-making. These strengthened GIS capabilities now enable systematic collection, analysis, and visualization of spatial and environmental data, improving the ministries’ ability to track trends, identify risks, and design responsive, sustainable interventions. This institutional transformation has resulted in more informed policy formulation, improved resource management, and enhanced capacity to implement sustainable environmental practices, laying the foundation for better long-term environmental outcomes and resilience in Somalia. Advancement of Somalia’s National Solid Waste Management Policy: The project significantly advanced the operationalization of Somalia's National Solid Waste Management Policy through a high-level national consultation with 60 representatives (41 males and 19 females) from key institutions. This inclusive dialogue fostered consensus on strategic priorities and actionable steps for effective waste management practices at the municipal level, strengthening institutional commitment to sustainable environmental management. The initiative empowered municipalities to develop tailored solutions for waste collection, disposal, and recycling, catalyzing momentum for policy-driven, locally adapted strategies. As a result, the project contributed to improved public health, environmental protection, and urban resilience, laying a strong foundation for long-term sustainability across the nation. Output 2.3. Environmental awareness raised through education and advocacy at all level Institutionalization of Graduate-Level Environmental Research: The project successfully institutionalized graduate-level environmental research in Somalia through a strategic partnership between the Ministry of Environment and Climate Change (MOECC) and Somali National University, leading to the establishment of dedicated research grants. This initiative has fostered a culture of innovation and academic inquiry, empowering graduate students to explore locally relevant environmental challenges. As a result, national research capacity has been strengthened, providing evidence to guide policy and support sustainable development. The partnership has improved collaboration among government, academia, and development partners, creating a foundation for long-term, research-driven environmental governance in Somalia. The project has also fostered community engagement and innovation on issues like resource management, climate resilience, and biodiversity conservation. Significant Enhancement of Public Awareness and Behavioral Change: The project successfully elevated public awareness and catalyzed behavioral change through targeted advocacy campaigns, including impactful World Environment Day events that engaged 120 participants (88 males, 32 females) from diverse stakeholder groups. Centered on the theme “Beat Plastic Pollution,” these initiatives effectively raised environmental consciousness, promoted sustainable practices, and mobilized community action against plastic waste. The initiative promoted responsible consumption and waste management through outreach efforts that included youth, women, and local shop owners. As a result, these campaigns led to observable changes in attitudes and practices, with communities increasingly adopting sustainable behaviors. This increased awareness supported local advocacy for environmental policies and contributed to greater community participation in conservation activities. The initiative provided a basis for ongoing environmental stewardship, aligning local actions with sustainability objectives at national and global levels, and supporting environmental health in the region. Community Engagement in Marine Conservation: Over 400 youth volunteers were mobilized through grassroots beach clean-ups and advocacy campaigns, fostering a strong sense of environmental stewardship and significantly reducing marine pollution, which contributed to the revitalization of coastal ecosystems and long-term environmental resilience. Strategic communication efforts across television, radio, and digital platforms amplified public awareness of the vital links between marine health, livelihoods, and regional stability, leading to multi-stakeholder consultations that produced actionable recommendations for sustainable marine practices. Simultaneously, advocacy campaigns addressing waste management and desertification enhanced public understanding of environmental health and its role in sustainable development, while targeted educational outreach and capacity-building initiatives empowered local communities with the knowledge and tools to combat environmental degradation and adopt resilience-oriented behaviors. Collectively, these integrated efforts advanced environmental sustainability and community development goals across the federal member states, laying a robust foundation for a more resilient and prosperous future. Integrated Solid Waste Management Strategy: Somalia successfully established its first Integrated Solid Waste Management Strategy (ISWMS), marking a transformative step toward sustainable urban development and environmental stewardship. Developed through a participatory process involving 60 stakeholders from federal and state institutions, the strategy now serves as a nationally endorsed framework guiding waste governance reforms. It has institutionalized sustainable practices, strengthened municipal capacities, and aligned national waste management with climate resilience and green growth objectives—laying the foundation for long-term public health protection, job creation, and environmental sustainability. COMPONENT 3: DISASTER RISK REDUCTION Brief Narrative Overview of Progress on Component 3: DRR The project has successfully established a robust National Disaster Risk Management (DRM) Framework, which has become a cornerstone of Somalia's disaster response strategy. The Ministry of Humanitarian Affairs and Disaster Management (MOHADM) developed a comprehensive, gender-responsive National DRM Plan that adopts a multi-hazard and multi-sectoral approach. This framework not only addresses priority risks and vulnerabilities in disaster-prone areas but also aligns seamlessly with the national DRR strategy, reflecting a collaborative effort among various stakeholders. As a result, Somalia has significantly enhanced its commitment to effective disaster preparedness, recovery, and sustainable development. A key achievement has been the operationalization of the National Emergency Operation Center (NEOC), which has transformed the coordination landscape among government agencies, UN entities, donors, and partner organizations. This enhanced collaboration has been crucial for mobilizing resources and actions to address the urgent humanitarian needs of drought-affected populations. Furthermore, the training of 185 local officials from disaster management institutions has fostered improved coordination and disaster preparedness across Federal Member States, ensuring that responses to emergencies are timely and effective. The project has also made substantial strides in developing and implementing local Disaster Risk Management (DRM) Plans, with six plans prepared and poised for finalization. These plans are specifically designed to mitigate disaster risks at the community level by incorporating tailored measures that address local vulnerabilities. Coupled with the establishment of a Disaster Volunteers’ Network, which includes 83 volunteers from high-risk districts, the local communities are now better equipped to respond to disasters. This network has not only empowered residents but also ensured that diverse community perspectives are integrated into disaster response strategies. Also, the integration of disaster risk reduction into national planning and programming marks a significant milestone. A coordination framework has been established with designated focal points for DRR across various sectoral ministries, facilitating the incorporation of disaster risk considerations into national policies. Training sessions for 202 officials (124 males, 78 females) have underscored the necessity of embedding DRR into planning processes, thereby laying a foundation for sustainable development and resilience. The development of a draft Building Back Better (BBB) strategy and the alignment of critical strategies with current risk profiles further exemplify Somalia's commitment to enhancing disaster management practices and building resilience within its communities. Output 3.1: Somalia disaster risk management system strengthened at the federal, state and local levels National Disaster Risk Management Framework Established: Somalia successfully institutionalized a comprehensive and gender-responsive National Disaster Risk Management (DRM) Framework, spearheaded by the Ministry of Humanitarian Affairs and Disaster Management (MOHADM). The finalized DRM Plan, grounded in a multi-hazard and multi-sectoral approach, now serves as the national blueprint for coordinated disaster risk reduction and resilience-building efforts. It has significantly enhanced the government's capacity to identify, prioritize, and mitigate disaster risks across vulnerable regions. The inclusive development process, involving diverse stakeholders, ensured alignment with the national DRR strategy and fostered national ownership and sustainability. This outcome has laid the foundation for more effective disaster preparedness, timely response, and long-term recovery, contributing to Somalia’s broader goals of resilience and sustainable development. Fully Operationalized NEOC Enhances National Disaster Coordination and Preparedness: The National Emergency Operations Center (NEOC) has been fully operationalized as a central coordination hub, significantly improving real-time collaboration among government institutions, UN agencies, donors, and humanitarian partners. This enhanced coordination has proven vital in mobilizing timely and effective responses to humanitarian crises, particularly in addressing the urgent needs of drought-affected populations. The project also strengthened institutional capacity by training 185 local officials (113 males, 72 females) from disaster management agencies across Federal Member States (FMS), equipping them with the skills and tools necessary for proactive disaster preparedness and response. As a result, Somalia now benefits from a more integrated, responsive, and resilient emergency management system that supports both immediate humanitarian action and long-term risk reduction Local DRM Plans Institutionalized for Community-Level Risk Reduction: Six localized Disaster Risk Management (DRM) Plans were developed and institutionalized, marking a significant step toward decentralized risk governance in Somalia. These plans, aligned with the national DRM framework, were tailored to the specific vulnerabilities, capacities, and risk profiles of each target community. Their development was grounded in inclusive, evidence-based processes that engaged local stakeholders and authorities, ensuring contextual relevance and ownership. As a result, communities are now better equipped with actionable, locally driven strategies to anticipate, mitigate, and respond to disaster risks. This outcome has strengthened the foundation for sustainable, community-centered resilience building and has enhanced the coherence between national and sub-national DRM efforts. Strengthened Localized DRR and CCA Prioritization Across FMS: Ministries of Humanitarian Affairs and Disaster Management (MoHADM) at the Federal Member State (FMS) level in Somalia significantly strengthened their institutional capacity to define and align localized Disaster Risk Reduction (DRR) and Climate Change Adaptation (CCA) priorities. Through a participatory and consultative process involving 330 community members and technical stakeholders (M:211, F:119), each FMS conducted structured baseline analyses that captured context-specific vulnerabilities and capacities. These efforts culminated in the development of updated, evidence-based DRR priorities that are now integrated into strategic planning processes, ensuring alignment with the national resilience agenda. The inclusive approach fostered local ownership, accountability, and sustainability, laying a solid foundation for adaptive, gender-responsive, and community-driven interventions that bridge the gap between policy and practice while enhancing Somalia’s long-term resilience to climate and disaster risks. Output 3.2: Professional skill enhancement programme designed, instituted and implemented to drive the risk reduction paradigm in Somalia at all level Strengthened Institutional and Community Capacities for Disaster Risk Reduction: Institutional and community capacities for disaster risk reduction (DRR) in Somalia were significantly enhanced through a series of targeted capacity-building initiatives. A total of 340 government officials benefited from tailored training programs that deepened their understanding of DRR principles, advocacy strategies, early warning systems, and the integration of DRR into planning processes. These trainings have contributed to more informed, coordinated, and proactive disaster management across all levels of government. Complementing this institutional strengthening, the establishment of a Disaster Volunteers’ Network comprising 83 trained individuals from high-risk districts has empowered local communities to take an active role in disaster preparedness and response. This dual approach has fostered inclusive participation, amplified local voices, and laid the groundwork for a more resilient and responsive disaster management ecosystem nationwide. Gender-Responsive DRR Institutionalized Across Policy and Practice: Somalia made significant strides in institutionalizing gender-responsive disaster risk reduction (DRR) through a combination of targeted training, advocacy, and policy engagement. Gender-sensitive DRR training modules were successfully implemented, enhancing the capacity of government officials and community actors to integrate gender considerations into all phases of disaster management. A landmark Gender-Responsive DRR workshop hosted by the Somali Disaster Management Agency (SODMA) in Mogadishu brought together 30 participants (M:13, F:17) from federal ministries and member states, equipping them with foundational knowledge on gender mainstreaming, intersectionality, and the use of gender-disaggregated data and analysis. These efforts fostered a deeper understanding of how to address systemic barriers and ensure inclusive disaster preparedness, response, recovery, and mitigation. DRR advocacy events further mobilized local communities and embedded gender equity into societal practices, reinforcing a culture of safety and protection. Collectively, these initiatives have strengthened national capacity to deliver equitable, effective, and inclusive DRR outcomes, contributing to Somalia’s broader goals of resilience and sustainable development. Output 3.3: Disaster risk reduction mainstreamed into the national planning and programming in Somalia. Institutionalization of Risk-Informed Planning Across Government Systems: Somalia’s institutional capacity for risk-informed development planning was significantly strengthened through the systematic integration of disaster risk reduction (DRR) into national and sectoral frameworks. A fully operational coordination mechanism was established, embedding DRR focal points across key ministries at both federal and state levels, which fostered cross-sectoral coherence and alignment in addressing disaster risks. Through targeted capacity-building initiatives, 202 government officials were equipped with practical skills in risk-sensitive planning tools and methodologies, resulting in enhanced technical competencies and stronger inter-ministerial collaboration. This institutional transformation has led to the routine inclusion of DRR measures in planning cycles, embedding a culture of risk-informed decision-making that underpins resilient governance and sustainable development outcomes across Somalia’s disaster-prone regions. Strengthened Community Resilience through Inclusive Recovery Strategies: A transformative outcome was achieved through the development and implementation of a comprehensive "Building Back Better and Greener" strategy, which significantly enhanced community resilience and disaster preparedness across Somalia. A collaboratively developed concept note laid the foundation for this strategy, engaging stakeholders through targeted consultation workshops and fostering inclusive recovery pathways. In partnership with the Ministries of Humanitarian Affairs and Disaster Management of Federal Member States, a series of capacity-building workshops equipped 157 participants (M:99, F:58)—with a strong emphasis on youth and marginalized women—with practical tools and knowledge to integrate environmental sustainability, social equity, and economic growth into recovery efforts. These workshops catalyzed community-driven advocacy, strengthened local capacities to address vulnerabilities across physical, social, environmental, and economic sectors, and promoted multi-sectoral collaboration among local governments, civil society, and the private sector. As a result, communities are now better positioned to transform post-crisis recovery into opportunities for long-term resilience, ensuring that future recovery processes not only rebuild but also improve societal and environmental systems against future shocks Enhanced Strategic Coherence for Disaster Risk Management and Humanitarian Response: Somalia achieved a significant milestone in strengthening its disaster risk management and humanitarian response frameworks through the comprehensive review and alignment of two critical national strategies. The National Humanitarian Strategy and the National Disaster Risk Reduction (DRR) Strategy were substantially revised to reflect the country’s evolving risk landscape, ensuring they are responsive to current and emerging vulnerabilities. This strategic realignment has enhanced coherence across policy instruments, improved operational effectiveness, and reinforced the government's commitment to building resilience in Somali communities. The updated strategies now provide a more integrated and forward-looking foundation for coordinated action among stakeholders, enabling more targeted interventions, efficient resource allocation, and sustainable recovery efforts that are better equipped to mitigate future shocks and disasters. Output 3.4: Enhanced community preparedness through end-to-end early warning dissemination and instituting disaster volunteers’ network. Operationalization of Multi-Hazard Early Warning Systems for Inclusive Risk Communication: Somalia successfully established a robust and inclusive multi-hazard early warning system, marking a critical advancement in disaster risk reduction and community resilience. Anchored in the principles of the Sendai Framework, a comprehensive end-to-end framework was developed to ensure timely generation, interpretation, and dissemination of early warning information. This system prioritizes accessibility and relevance, enabling vulnerable communities to receive life-saving alerts in formats tailored to their linguistic, cultural, and technological contexts. The initiative strengthened institutional capacities for risk monitoring and communication, fostered inter-agency coordination, and empowered local actors to act proactively in the face of hazards. As a result, communities are now better equipped to anticipate, prepare for, and respond to multiple risks, reducing disaster impacts and enhancing adaptive capacity across sectors. Strengthened Community Preparedness through Inclusive Capacity Building on Early Warning Systems: Local disaster preparedness was significantly enhanced through the training of 448 individuals (242 males and 206 females) in multi-hazard early warning systems (MHEWS), contributing to more resilient and responsive communities. The capacity-building initiative emphasized inclusive risk communication and community engagement, with a strong focus on the specific vulnerabilities and needs of women, girls, and the elderly. Participants were equipped with practical knowledge and tools to interpret and act on early warning information, enabling timely and informed decision-making at the community level. This training not only improved technical understanding of MHEWS but also fostered a culture of preparedness and proactive risk reduction. As a result, communities are now better positioned to anticipate, respond to, and recover from hazards, with enhanced local leadership and ownership of disaster risk management processes. Promoted Community-Based Disaster Response through Volunteer Networks: A robust and well-coordinated network of disaster volunteers was successfully established, significantly enhancing community-level emergency response and resilience. These trained volunteers now serve as frontline agents in disseminating early warning information, mobilizing rapid response efforts, and fostering a culture of preparedness across vulnerable communities. Their presence has improved the speed and effectiveness of local disaster response, ensuring timely action during emergencies. Moreover, the network has become a vital conduit for community engagement, promoting inclusive participation and empowering local actors—especially youth and women—to take active roles in risk reduction and recovery processes. This outcome has laid the groundwork for sustained community ownership of disaster preparedness, contributing to long-term resilience and adaptive capacity in the face of future hazards. Institutionalized Multi-Stakeholder Collaboration for Inclusive Early Warning Systems: Somalia had successfully institutionalized a multi-stakeholder coordination framework through the development and national endorsement of the Somalia Roadmap for the Implementation of the Early Warning for All (EW4ALL) Initiative (2024–2027). This roadmap, aligned with the Sendai Framework and the Paris Agreement, catalyzed a whole-of-society approach to disaster risk reduction by embedding local knowledge and community priorities into national early warning strategies. It established a structured platform for collaboration among government institutions, regional authorities, civil society, private sector actors, and international partners, ensuring that early warning systems are not only technically sound but also context-sensitive, inclusive, and actionable. The roadmap’s implementation has enhanced institutional accountability, streamlined coordination mechanisms, and fostered interjurisdictional integration of early warning services. As a result, Somalia is now better positioned to deliver timely, accessible, and equitable early warnings, particularly to its most vulnerable populations, thereby strengthening national resilience and adaptive capacity in the face of escalating climate and disaster risks Output 3.5: Capacity enhanced to promote urban resilience in Somalia Improved Urban Risk Governance through Targeted Capacity Building: Urban disaster risk governance was significantly enhanced through the successful training of 215 municipal officials (162 males and 53 females) across high-risk urban centers. These capacity-building initiatives equipped local authorities with critical competencies to systematically identify, prioritize, and mitigate urban disaster risks. The training emphasized participatory planning, risk-informed decision-making, and inclusive approaches that address the unique vulnerabilities of urban populations. As a direct result, trained officials led the formulation of actionable Urban Disaster Risk Reduction (DRR) plans tailored to their respective municipalities. These plans now serve as operational tools for integrating resilience into urban development processes, enabling cities to proactively manage risks and reduce the impact of future disasters. Institutionalization of Municipal Disaster Risk Reduction Planning in High-Risk Urban Areas: Disaster risk governance in Somalia’s urban centers was significantly strengthened through the development and implementation of Municipal Disaster Risk Reduction (DRR) Plans in four high-risk cities. A total of 344 municipal officials (232 males and 112 females) were actively engaged in participatory planning processes that identified localized vulnerabilities and formulated context-specific strategies for disaster preparedness, response, and recovery. These plans now serve as operational frameworks for integrating risk reduction into urban development, promoting proactive, inclusive, and evidence-based approaches to resilience. The initiative has fostered stronger coordination among municipal authorities, enhanced institutional ownership of DRR, and laid the foundation for sustained urban resilience through locally led action. Empowered Urban Youth as Agents of Resilient and Sustainable Development: 169 urban youth (83 males and 86 females) were equipped with practical livelihood and green recovery skills, enabling them to actively contribute to sustainable urban development and climate-resilient recovery efforts. These initiatives focused on building youth capacities in environmentally responsible practices, entrepreneurship, and community-based resilience, while also fostering leadership and innovation. The training emphasized inclusivity and social cohesion, ensuring that young people—particularly those from marginalized backgrounds—were empowered to become proactive agents of change in their communities. As a result, the initiative not only enhanced youth employability and income-generating potential but also strengthened local ownership of resilience-building processes, laying the groundwork for greener, more inclusive urban futures. Strategic Urban Resilience Planning Institutionalized in Mogadishu: Urban resilience planning in Somalia reached a significant milestone with the development of a comprehensive Urban Resilience Roadmap for Mogadishu. This strategic framework was tailored to the city’s unique risk landscape, integrating disaster risk reduction (DRR), climate adaptation, and sustainable urban development into a cohesive plan of action. The roadmap was developed through a participatory process involving municipal authorities, technical experts, and community stakeholders, ensuring that local knowledge and priorities were embedded in the planning process. It now serves as a guiding blueprint for ongoing and future resilience-building initiatives, providing clear pathways for risk-informed urban governance, infrastructure planning, and emergency preparedness. Moreover, the roadmap has catalyzed replication efforts across other Somali cities, positioning Mogadishu as a model for urban resilience and contributing to a broader national agenda for disaster risk management and sustainable urban transformation. Output 3.6: Local disaster resilience fund designed and operationalized to enhance community resilience to disaster/climate shocks Strengthened Community-Led Disaster Risk Governance through Local DRR Committees: Community-level disaster risk governance was significantly enhanced through the establishment of inclusive, community-managed Disaster Risk Reduction (DRR) Committees. These locally anchored structures have empowered communities to take ownership of their risk environments by identifying context-specific vulnerabilities and implementing tailored mitigation strategies. The committees serve as vital platforms for participatory decision-making, enabling diverse groups—including women, youth, and elders—to contribute meaningfully to disaster preparedness and response planning. Their active engagement has improved the timeliness and effectiveness of local emergency actions, facilitated rapid information dissemination, and fostered a culture of resilience and collective responsibility. As a result, communities are now better equipped to anticipate, manage, and recover from disasters, with strengthened social cohesion and institutional linkages that support long-term resilience. Enhanced Local Resilience through Participatory Disaster Risk Reduction Planning: Disaster preparedness and resilience at the local level were significantly boosted through the development and implementation of comprehensive Local Disaster Risk Reduction (DRR) Plans across 11 high-risk districts. A total of 155 individuals (91 males and 64 females) were actively engaged in inclusive, gender-responsive, and participatory planning processes that identified district-specific vulnerabilities and prioritized actionable risk reduction measures. These efforts culminated in the successful implementation of priority DRR interventions, directly benefiting 534 community members (224 males and 310 females). The initiative fostered local ownership, strengthened institutional and community capacities, and promoted equitable participation in disaster risk governance. As a result, communities are now better equipped to anticipate, mitigate, and respond to hazards, laying a sustainable foundation for long-term resilience and adaptive development. Improved Household Resilience through Distribution of Essential Resources: The living conditions and resilience of vulnerable households were significantly enhanced through the targeted distribution of essential resources. A total of 1,100 solar lanterns, 400 water tanks, and 1,600 plastic sheets were delivered to communities facing acute vulnerability to environmental and economic shocks. These resources addressed critical needs by providing reliable, renewable lighting solutions, improving access to safe water storage, and offering emergency shelter materials. The intervention not only improved daily well-being and safety—particularly for women, children, and the elderly—but also reduced reliance on harmful coping mechanisms. As a result, beneficiary households are now better equipped to withstand and recover from future disasters, contributing to broader community resilience and sustainable recovery outcomes. Informed Climate Action through Localized Vulnerability and Capacity Assessments in Puntland: Climate risk management in Puntland was significantly strengthened through the successful completion of an extensive Climate Vulnerability and Capacity Assessment (CVCA). This participatory assessment identified key climate hazards, exposure levels, and socio-economic vulnerabilities across diverse communities, with a strong emphasis on gender-responsive analysis and the inclusion of marginalized groups. The findings provided a robust evidence base that directly informed the design and implementation of targeted, community-driven interventions aimed at enhancing preparedness, adaptive capacity, and long-term resilience. Moreover, the CVCA process introduced innovative climate resilience practices tailored to local contexts, fostering greater community ownership and institutional alignment. As a result, stakeholders at both local and regional levels are now better equipped to anticipate climate-related risks and implement proactive, inclusive strategies that reduce vulnerability and strengthen resilience across Puntland States. COMPONENT 4: SOMALIA YOUTH CLIMATE PLATFORM (SYCP) The Somalia Youth Climate Platform (SYCP) successfully enhanced youth awareness, technical knowledge, and motivation regarding climate change and environmental sustainability. Through a series of workshops held in Garowe, Mogadishu, and Hargeisa, youth from over 40 organizations were engaged in discussions about Somalia's Nationally Determined Contributions (NDC), ensuring that their voices were heard in national climate dialogues. Gender inclusivity was a priority, with equal representation of female participants. Additionally, youth-led initiatives, such as beach clean-up campaigns, mobilized over 80 participants to address solid waste management in Mogadishu, fostering a sense of collective responsibility for environmental stewardship. Participation in international climate advocacy events, such as COP27 and COP28, further empowered Somali youth to represent their community on global platforms, showcasing their commitment to sustainable practices and climate action. The SYCP continued to build on these foundations by facilitating comprehensive youth consultations focused on the implementation of Somalia's NDC. These consultations emphasized the role of young people in driving innovation and resilience-building initiatives across key sectors, including energy, agriculture, and disaster management. The collaborative workshops successfully highlighted the importance of gender equity in climate action, resulting in actionable plans that called for capacity-building training and partnerships with government and private sector stakeholders. The SYCP's commitment to fostering dialogue between youth organizations and institutions culminated in significant contributions to national strategies, enhancing youth engagement in policy discussions and promoting environmental sustainability. The establishment of the SYCP's online database and interactive website has strengthened coordination and collaboration among youth groups and relevant institutions. This digital platform serves as a vital resource for youth organizations, enabling them to share best practices, access funding opportunities, and mobilize for climate action. By promoting joint initiatives and facilitating partnerships with stakeholders, the SYCP has created a robust network that empowers youth to take decisive action against climate challenges. Events such as the first Local Conference of Youth (LCOY) fostered a sense of unity among Somali youth, culminating in the creation of the Somali Youth National Statement on Climate Change, which was presented at COP29. Moreover, the SYCP has made significant strides in promoting youth employment and entrepreneurship, catalyzing initiatives that align with climate-resilient development. By organizing training sessions on disaster preparedness and early warning systems, the platform has equipped youth with essential skills to respond effectively to climate-related challenges. Strategic partnerships with various stakeholders have further mobilized resources and support for youth-led initiatives, including those focused on biodiversity conservation and sustainable use of marine resources. The SYCP's efforts in promoting gender equality have ensured that young women are actively involved in climate resilience initiatives, thereby contributing to a more inclusive approach to environmental sustainability in Somalia. Overall, the SYCP has laid the groundwork for a sustainable future, empowering Somali youth to play a pivotal role in addressing the urgent climate crisis. Output 4.1: Enhanced Youth Awareness and Engagement in Climate Action Improved Youth Engagement in Climate Policy and Gender-Inclusive Advocacy: Youth engagement in climate governance significantly enhanced across Somalia. A total of 80 young leaders (50% female) from over 40 organizations in Garowe, Mogadishu, and Hargeisa demonstrated increased climate literacy and advocacy capacity. Through a series of targeted workshops, participants gained a deeper understanding of Somalia’s Nationally Determined Contributions (NDCs) and actively contributed youth-driven perspectives to national climate policy dialogues. The initiative also fostered gender-responsive climate action by ensuring equal participation and integrating gender equality as a core theme throughout the training and policy discussions. Strengthened Community-Led Environmental Stewardship and Inclusive Waste Management Practices: Youth-led environmental action had become a visible and influential force in Mogadishu. Through a series of beach cleanup campaigns mobilized by trained youth leaders, public awareness of solid waste management significantly increased. These campaigns not only improved the physical environment but also fostered a culture of collective responsibility and environmental stewardship within local communities. Notably, the initiatives empowered women and Internally Displaced Persons (IDPs) to take active roles in environmental protection, promoting inclusive participation and social cohesion. Community members demonstrated greater ownership of local environmental challenges and began adopting more sustainable waste disposal practices. Elevated Somali Youth Representation in Global Climate Policy Dialogues: Somali youth had successfully positioned themselves as active contributors to international climate discourse. A total of eight youth delegates (equally split by gender) were sponsored to participate in COP27 and COP28, marking a historic milestone in amplifying Somali youth voices on the global stage. Their engagement in high-level negotiations and side events enabled them to share local climate realities and advocate for inclusive, youth-centered climate solutions. Upon returning, delegates translated global insights into actionable strategies, catalyzing local climate initiatives and strengthening national advocacy networks. This outcome fostered a new generation of climate leaders equipped with global perspectives and committed to driving transformative change in Somalia. Strengthened National Youth Climate Networks and Policy Engagement through Post-COP Knowledge Transfer: Following COP28, the project successfully facilitated a national youth workshop that enabled Somali youth delegates to disseminate key insights and strategies acquired from their participation in global climate negotiations. This initiative significantly enhanced the climate advocacy capacity of local youth organizations by translating international climate discourse into locally relevant action. The workshop fostered stronger collaboration between youth-led groups and government institutions, laying the groundwork for more structured and sustained youth engagement in national climate policy processes. Youth actors emerged better equipped to influence climate governance and contribute meaningfully to the implementation of Somalia’s climate commitments. Institutionalized Youth Engagement in Somalia’s NDC Implementation: Youth participation in Somalia’s climate governance was significantly institutionalized through a series of national consultations focused on the implementation of the country’s Nationally Determined Contributions (NDCs). These consultations brought together youth organizations, government institutions, and development partners to co-develop actionable plans that positioned youth as key stakeholders in advancing climate resilience. The process emphasized capacity building through tailored training on NDC priorities, climate-smart agriculture, and disaster risk management, while also equipping youth with advocacy skills to influence policy at national and sub-national levels. Youth-led initiatives were launched in alignment with NDC targets, and stronger partnerships were forged between youth networks and institutional actors, embedding youth roles within Somalia’s climate action frameworks. Strengthening Youth Leadership and Partnerships for Climate Action in Somalia: The SYCP had enhanced the leadership, visibility, and coordination of youth in advancing Somalia’s climate agenda. SYCP convened a high-impact post-COP29 follow-up workshop, bringing together 50 youth leaders (35 male, 17 female) from 25 youth organizations, alongside representatives from the Ministry of Environment and Climate Change, the Ministry of Youth and Sports, UN agencies, and the private sector. The workshop provided a strategic platform for youth delegates who participated in COP29 to share their experiences, lessons learned, and priority action points with fellow environmental champions. Discussions focused on translating COP29 outcomes into locally relevant initiatives, identifying opportunities for youth-led climate action, and refining advocacy and communication strategies for influencing climate policies at local, national, regional, and international levels. The active engagement of government institutions, development partners, and civil society in the workshop strengthened institutional linkages and broadened partnership networks. This resulted in improved coordination between youth organizations and government agencies, creating sustained avenues for youth participation in national climate policy processes and implementation. As a result, the initiative positioned young Somali leaders as credible actors in climate governance, equipped with stronger skills, networks, and platforms to drive climate resilience and sustainable development in Somalia. Output 4.2: Strengthened Coordination and Collaboration Among Youth Groups and Stakeholders Strengthened Strategic Coordination and Institutional Visibility of SYCP through Operational Roadmap: Somali Youth Climate Platform (SYCP) had transitioned into a nationally recognized coordination hub for youth-led climate action, guided by a finalized strategic operational roadmap. Developed through inclusive consultations with youth networks, federal and state institutions, UN agencies, and development partners, the roadmap outlined key milestones for a two-year implementation period. It enhanced SYCP’s capacity to mobilize youth participation, align with national climate priorities, and foster multi-stakeholder collaboration. The roadmap also supported the launch of SYCP’s digital platform, enabling real-time coordination, visibility, and knowledge sharing among youth organizations across Somalia. SYCP became a central mechanism for integrating youth voices into climate policy, facilitating joint initiatives, and scaling up climate resilience efforts nationwide. Digital Infrastructure Established to Strengthen Youth-Led Climate Action and Coordination: Somali Youth Climate Platform (SYCP) had successfully launched a dynamic and interactive online platform, transforming the digital landscape for youth-led climate action in Somalia. Developed through a comprehensive mapping of over 50 active youth organizations, the platform serves as a centralized hub for information sharing, networking, and collaboration. It empowers Somali youth by providing real-time access to climate resources, funding opportunities, and policy updates, while also promoting visibility for youth-led initiatives. The platform has significantly enhanced coordination among youth networks, government institutions, and development partners, enabling more inclusive and strategic engagement in national climate resilience efforts. SYCP website has become a vital tool for mobilizing youth participation, amplifying local solutions, and institutionalizing youth leadership in Somalia’s climate governance framework. Institutionalized Multi-Stakeholder Partnerships for Youth-Led Climate Action in Somalia: Somali Youth Climate Platform (SYCP) had successfully institutionalized strategic partnerships with the Ministry of Youth and Sports and the Ministry of Environment and Climate Change, significantly enhancing youth engagement in national climate governance. These partnerships enabled the co-design and implementation of inclusive climate initiatives, including youth participation in national events such as International Peace Day and biodiversity consultations. Through joint planning, policy dialogues, and co-hosted events, the SYCP facilitated structured collaboration between youth organizations and government institutions, fostering mutual accountability and shared ownership of Somalia’s climate resilience agenda. These partnerships also contributed to the development of youth-led policy recommendations, strengthened inter-ministerial coordination, and amplified youth visibility in national and global climate platforms. Somali youth emerged as recognized stakeholders in shaping climate and environmental policy, with sustained institutional support for their leadership and innovation. Strengthened Multi-Stakeholder Coordination for Youth-Led Climate Action in Somalia: Stakeholder engagement in Somalia’s climate governance had been significantly strengthened through the Somali Youth Climate Platform (SYCP), which successfully fostered coordination among youth organizations, government institutions, UN agencies, and international partners. This collaborative framework enabled the creation of a robust and inclusive network for climate action, facilitating joint planning, policy dialogue, and implementation of youth-led initiatives. Through co-hosted events, strategic consultations, and digital platforms, SYCP enhanced real-time communication and resource sharing, empowering youth to actively contribute to national climate resilience efforts. The platform’s inclusive approach also promoted gender equality and social cohesion, ensuring that women and marginalized groups were meaningfully represented in climate decision-making processes. Somalia now benefits from a more unified and responsive climate action ecosystem, with youth positioned as central actors in shaping sustainable development and environmental governance. Output 4.3: Increased Youth Participation in National Policy Dialogue Amplified Somali Youth Voice in Global Sustainable Development through Stockholm+50 Engagement: Somali youth had successfully positioned themselves as active contributors to global sustainable development discourse through their participation in the Stockholm+50 event. With support from the Somali Youth Climate Platform (SYCP), UNDP, Sida, and the Directorate of Environment and Climate Change under the Office of the Prime Minister, youth consultations were held in Mogadishu, engaging over 30 youth organizations from across Somalia. These consultations culminated in the articulation of Somali youth perspectives on climate resilience, environmental sustainability, and inclusive development, which were integrated into the global Stockholm+50 dialogue. The initiative not only strengthened youth representation at the international level but also catalyzed the formation of a national youth climate advocacy platform, empowering young leaders to influence policy and action both locally and globally. The event showcased Somali youth’s readiness to address the triple crises of conflict, climate change, and poverty, and laid the foundation for sustained youth engagement in future global forums. Youth-Informed Climate Policy through National Workshops on NDCs and COP Engagement: Somali youth had emerged as informed contributors to national climate policy through a series of strategic workshops focused on Somalia’s Nationally Determined Contributions (NDCs) and preparations for COP28. These workshops, organized by the Somali Youth Climate Platform (SYCP) in collaboration with the Ministry of Environment and Climate Change and the Ministry of Youth and Sports, brought together youth organizations, government institutions, private sector actors, and UN agencies. The sessions facilitated meaningful dialogue on climate priorities, resilience strategies, and the role of youth in advancing Somalia’s climate agenda. Participants developed actionable recommendations that were formally integrated into Somalia’s enhanced NDC under the cross-cutting section. The workshops also strengthened youth capacity in climate diplomacy, advocacy, and communication, equipping them to engage in global forums such as COP28. As a result, youth perspectives are now embedded in national climate strategies, and a foundation has been laid for sustained youth participation in climate governance and international negotiation. Institutionalized Gender-Responsive Access to Climate Opportunities and Youth Employment Pathways: Somali Youth Climate Platform (SYCP) had institutionalized a gender-responsive communication and engagement system that significantly expanded access to climate-related opportunities for young people across Somalia—particularly young women. Through the establishment of national email distribution lists and the launch of an interactive online platform, SYCP created a centralized hub for disseminating funding calls, grant opportunities, knowledge products, and best practices in climate resilience and sustainability. This proactive and inclusive outreach strategy ensured that over 46 youth organizations remained consistently informed and engaged in climate action initiatives. The platform’s commitment to gender equality was reflected in its balanced representation across all activities and its targeted efforts to empower young women through access to climate-focused employment, entrepreneurship, and leadership pathways. These efforts resulted that two young Somali environmental champions selected and sponsored under the Climate Mobility and Rising Nations Youth Delegates Program to participate in COP29, marking a significant milestone in elevating Somali youth—especially women—on the global climate stage. Youth Participation in Biodiversity and Blue Economy Policy Dialogues: Somali youth had become recognized contributors to national environmental governance through their active participation in biodiversity and blue economy consultations. The Somali Youth Climate Platform (SYCP), in collaboration with the Ministry of Environment and Climate Change and the Ministry of Youth and Sports, hosted a series of national consultations aligned with the International Day for Biodiversity 2024. These consultations brought together youth organizations, government institutions, private sector actors, and UN agencies to explore the roles, opportunities, and priorities for youth in advancing Somalia’s National Biodiversity Strategy and Action Plan (NBSAP) and the Global Biodiversity Framework (GBF). Participants engaged in in-depth discussions on marine biodiversity hotspots, ecosystem threats, and sustainable blue economy practices. The consultations culminated in a set of actionable recommendations, including youth-led conservation initiatives, policy advocacy, capacity building, and innovation in marine resource management. These recommendations received strong institutional backing and are now guiding youth engagement in national biodiversity and blue economy strategies. Somali youth are now positioned as key stakeholders in shaping and implementing environmental policies that protect the country’s unique ecosystems and promote sustainable livelihoods. Youth Leadership in Peace and Security through Somalia’s First YPS National Action Plan: Somalia achieved a historic milestone in youth inclusion by finalizing its first-ever Youth, Peace, and Security – National Action Plan (YPS-NAP), with technical and financial support from the platform in close collaboration with the Ministry of Youth and Sports. The process was anchored in inclusive, youth-led consultations held across four federal member states—Jubaland, South West, Hirshabelle, and Banaadir—engaging 298 youth (200 male, 98 female) from diverse backgrounds. These consultations surfaced critical insights on youth roles in peacebuilding, security, and community development, with strong emphasis on economic empowerment, digital advocacy, and gender equality. The YPS-NAP now serves as a nationally endorsed framework that institutionalizes youth as key stakeholders in Somalia’s peace and security architecture, fostering inter-ministerial coordination and laying the foundation for youth-led implementation and monitoring mechanisms. Institutionalized Youth Climate Leadership through Somalia’s First Local Conference of Youth (LCOY): Somalia had successfully institutionalized youth leadership in national and global climate advocacy through the organization of its first-ever Local Conference of Youth (LCOY), held in Mogadishu from 27–28 August 2024. This landmark event convened over 200 youth delegates from across the country, creating an inclusive platform for dialogue, knowledge exchange, and policy engagement. The conference culminated in the adoption of the Somali Youth National Statement on Climate Change—an unprecedented youth-led policy document articulating local climate priorities and solutions. To ensure continuity and ownership, a follow-up Post-LCOY workshop brought together 100 youth delegates to validate the statement and strategize for COP29. The finalized statement was officially launched as Somalia’s youth contribution to the Global Youth Statement at COP29 in Baku, Azerbaijan, where Somali youth delegates led side events and participated in high-level panels. This process not only amplified Somali youth voices on the international stage but also strengthened national youth networks, enhanced policy literacy, and positioned young people as key actors in shaping Somalia’s climate future. Output 4.4: Promotion of Youth Employment, Entrepreneurship, and Climate Resilience Enhanced Youth Capacity for Climate Resilience and Community-Based Disaster Preparedness: Somali youth had significantly strengthened their capacity to lead community-based climate resilience and disaster preparedness initiatives. Through a series of targeted training workshops organized by the Somali Youth Climate Platform (SYCP) in collaboration with national and sub-national institutions, 32 youth volunteers were equipped with practical skills in early warning systems, risk communication, and anticipatory action. These workshops emphasized inclusive approaches, integrating gender-responsive and locally contextualized strategies to address the unique vulnerabilities of Somali communities. The trained volunteers now serve as focal points for disaster risk reduction (DRR) in their respective districts, actively contributing to the development of local preparedness plans and awareness campaigns. This outcome not only enhanced grassroots resilience but also established a scalable model for youth-led DRR engagement across Somalia. Strengthened Youth-Led Disaster Preparedness and Community Resilience Across Somalia: Somali Youth Climate Platform (SYCP) had successfully established and trained a national network of youth disaster volunteers, significantly enhancing community resilience to climate-induced shocks. With support from UNDP, SIDA, and the Somali Disaster Management Agency (SODMA), targeted training sessions were conducted in Mogadishu and Galmudug, equipping youth with essential skills in early warning dissemination, disaster response coordination, and community mobilization. These sessions engaged over 60 youth volunteers, including women, and focused on practical preparedness strategies tailored to Somalia’s high-risk regions. The initiative also included the creation of a youth database and volunteer registry, enabling rapid deployment and coordination during emergencies. As a result, youth are now recognized as frontline responders and key stakeholders in Somalia’s disaster risk reduction framework, actively contributing to early warning systems and community-based resilience planning Advancing Youth-Led Green Entrepreneurship in Somalia: Youth engagement in Somalia’s green economy had been significantly strengthened through targeted skills development, enterprise creation, and network building. UNDP, under the Somalia Youth Climate Platform and in close collaboration with the Ministry of Youth and Sports and the Ministry of Environment and Climate Change, convened a Youth Consultation on Green Jobs and Entrepreneurship Skills in Mogadishu. The event brought together 65 young green entrepreneurs (40 male, 25 female) representing 30 youth organizations from across the country. The consultation focused on high-potential climate-smart sectors such as sustainable agriculture, renewable energy, waste management, and eco-construction. Participants mapped opportunities, shared innovative business ideas, and collectively identified key barriers to scaling green enterprises, including limited access to training, inadequate financing, and weak business networks. As a direct outcome, the event catalyzed the establishment of eight youth-led green micro, small, and medium-sized enterprises (MSMEs) and launched a dedicated Youth Green Entrepreneurship Network to foster peer learning, business collaboration, and advocacy for policy and financial support. This initiative has expanded the pipeline of viable youth-led green businesses, strengthened market linkages, and positioned young entrepreneurs as key drivers of Somalia’s transition to a climate-resilient and low-carbon economy. Building Youth Capacity for Climate-Smart Agriculture and Green Innovation: Youth-led contributions to Somalia’s climate-resilient agriculture sector had been strengthened through targeted technical training and practical skills development. UNDP’s Somalia Climate Platform, in partnership with the Ministry of Youth and Sport and the Ministry of Environment and Climate Change, and with support from Sida, delivered an intensive two-day training to 70 young green entrepreneurs (40 male, 30 female) from youth-led organizations. The training focused on climate-smart agriculture and hydroponic technologies, covering vertical, horizontal, and Mapal trough farming systems, sustainable pest and fertilizer management, and strategies to reduce post-harvest losses. Through hands-on sessions, participants assembled hydroponic units, prepared nutrient solutions, and applied eco-friendly farming practices, gaining both technical proficiency and entrepreneurial insights into emerging green job opportunities. As a direct outcome, participants graduated with recognized certificates, enhancing their credibility and employability in the green economy. The initiative created a pool of skilled young practitioners capable of introducing innovative, water-efficient farming methods in Somalia, supporting food security, promoting sustainable livelihoods, and contributing to the country’s transition toward a low-carbon, climate-resilient future.

Number of beneficiaries and feedback from beneficiaries Overall, the project has reached over a total of 10,103 individuals (including 3,866 women) benefited from a comprehensive suite of capacity-building initiatives, consultations, and awareness campaigns, ensuring broad and inclusive participation in critical areas focused on integrated water resource management, environmental governance, and disaster risk reduction (DRR). The project successfully engaged 17 government institutions across federal, federal member states, and local communities, leading to enhanced understanding and practical application of IWRM concepts, urban DRR strategies, and early warning systems. Feedback from beneficiaries consistently underscored the usefulness of the project’s technical assistance, particularly the blend of theoretical and practical training that empowered disaster management officials at all levels. Throughout the project’s duration, significant progress was made in aligning the focus and priorities of disaster management authorities with the national development plan of Somalia and the Sendai Framework for Disaster Risk Reduction. This alignment not only enriched the appreciation for disaster risk management but also resulted in the formulation of gender-responsive DRR plans targeting vulnerable populations, including women, youth, and persons with disabilities. The capacity-building support provided enabled these authorities to incorporate gender analysis into their strategies, ensuring that both men and women play active roles in DRR initiatives. The project fostered strong relationships with its beneficiaries, establishing effective disaster management institutions that are essential for enhancing community resilience in water-stressed and ecologically vulnerable areas. This collaborative approach has been highly valued, as it not only provided critical operational support but also enhanced the institutions' capability to fulfill their mandates. The positive rapport developed with national counterparts and other disaster management entities was frequently highlighted in project meetings, illustrating a shared commitment to sustainable disaster management practices. The project culminated in the establishment of Somalia's inaugural Youth Peace and Security agenda, demonstrating its commitment to inclusive development and community empowerment. The project’s emphasis on gender-balanced and youth-inclusive interventions facilitated the growth of local expertise in environmental monitoring and disaster preparedness. As a result, the initiative is well-positioned to provide enduring benefits, fostering long-term partnerships that will enhance environmental resilience and governance systems in Somalia. The positive feedback received from participants and stakeholders reinforces the project's effectiveness and solidifies its role as a catalyst for sustainable development and disaster risk reduction in the region.

Section 4: Project implementation

COVID 19 Response UNDP has adopted several measures to limit the spread of COVID-19 through social distancing and practicing hygiene measures in line with WHO guidelines. UNDP has developed operational guidelines based on relevant stakeholders, Somalia Government and WHO Guidance while mitigating COVID-19 risks and ensuring healthy and safe work environment. UNDP has also provided face masks, sanitizers and installed hand washing facilities as well as posters with COVID messages and importance of proper hygiene and social distancing.

Key constraints and challenges and associated corrective actions Security remains a formidable challenge for UNDP and its partners in Somalia, significantly impacting project implementation at both national and regional levels. This situation is exacerbated by intensified military operations against non-state armed groups (NSAGs) and the persistent effects of climate-related shocks, including recurrent droughts and floods. To address these challenges, the project has adopted a flexible and adaptive approach, emphasizing meticulous planning and effective risk management strategies. Close coordination with local stakeholders has been essential in ensuring continuity of activities, allowing the project to prioritize capacity-building efforts even in the face of persistent security threats. The ongoing governance and institutional gaps in Somalia further complicate the security landscape, enabling groups like Al-Shabaab to exploit vulnerabilities. Although there have been significant strides in counter-terrorism initiatives supported by international partners, the enduring threat of extremism remains a critical concern. The planned transition from the African Union Transition Mission in Somalia (ATMIS) to a Somali-led security framework presents both opportunities and risks. This transition could empower Somalia to exert greater control over its security, but it also necessitates the establishment of robust institutional frameworks to manage the change effectively. In response to these challenges, the project has focused on enhancing the resilience of Somali security institutions through targeted investments and international support. Ensuring that security gains are sustained during this transition requires that project implementation mechanisms remain flexible and responsive to the evolving environment. The commitment to capacity-building activities must be unwavering, even as resources are prioritized for addressing immediate security needs. During the implementation of the project, UNDP and its partners have demonstrated resilience and adaptability in navigating a complex operational landscape. They have maintained a steadfast commitment to project objectives by learning from past experiences and continuously refining their strategies. The focus on capacity building, stakeholder engagement, and adaptive planning has been crucial in overcoming these multifaceted challenges, enabling the project to make tangible progress despite the persistent security and governance issues in Somalia.

Risk Management Type of risk; Description of risk; Mitigating measures. Operational, Organizational; Limited/insufficient involvement of key stakeholders in implementation of project activities.; Regular consultative meetings held with national counterparts for planning and development approach. There was also close coordination with key national counterparts in federal member states for endorsements of AWP/LOAs by both UNDP and government counterparts. Risk mitigation plans developed and agreed project counterparts for effective implementation of activities in the LoAs.. Environmental, Security; Terrorist activities force UN / UNDP to significantly reduce its activities.; The project implementation is guided by the UN security plan and subject to strict compliance of UNDP security measures in place in Mogadishu. Access to security tools and support as well as close oversight by UNDP security team helps reduce and manage the security risks in project implementation.. Environmental, operational; COVID-19 pandemic may affect implementation of some activities.; Business continuity plan developed to ensure that the covid 19 compliant measures in place including avoiding exposure, rotational staff presence, the implementation, monitoring and oversight through zoom meetings, virtual consultations and using other digital platforms.. Environmental, operational; Institutional transition as result of new leadership in 2022; UNDP maintains strong vigilance and strategic foresight on contextual dynamics through close coordination, and regular communication with counterparts, partners, donors, and stakeholders. The project put the implementation of Comp3 (DRR) at the federal level on hold and informed the counterparts and Sida before the Government abolished the MOHADM. The project coordinated with the counterparts to ensure the timely return of the unspent balance to the UNDP account. In response to the institutional changes, the project re-calibrated the risk analysis and are executed through the revisions of the LOAs..

Partnerships Significant advancements in institutional partnerships and governance structures were realized across Federal and Federal Member States in Somalia. The Ministry of Energy and Water Resources (MoEWR) successfully collaborated with state-level water resource authorities and various international organizations, including IGAD/ICPAC and the Arab Water Council. This collaboration resulted in the establishment of a national water task force that effectively integrated UN agencies, donors, NGOs, and civil society organizations at both federal and state levels, ensuring broader stakeholder engagement in water resource management. The project also strengthened environmental governance through robust partnerships with the Ministry of Environment and Climate Change (MoECC) and environmental ministries across states. Collaborations with entities such as UNEP, FAO, and UNFPA facilitated the operationalization of the Somalia Environment Task Force. This initiative led to enhanced coordination among donors and UN agencies, significantly improving the response to environmental challenges and climate change. The participatory approach adopted by the project fostered a sense of ownership among local institutions, ensuring sustainability in environmental governance practices. In the realm of disaster risk reduction (DRR), partnerships with the Somali Disaster Management Agency (SODMA), state Ministries of Humanitarian Affairs and Disaster Management (MoHADM) were pivotal in building capacity within the National Emergency Operational Centre (NEOC). The project’s collaboration with UN DRR, UN OCHA, and various NGOs bolstered local disaster response capabilities. These partnerships not only facilitated the implementation of the Sendai Framework for Disaster Risk Reduction but also empowered local communities to mobilize resources for climate resilience and disaster preparedness, enhancing overall community ownership of DRR initiatives. Furthermore, the project achieved its goal of fostering inclusive, multi-stakeholder partnerships that championed climate resilience and sustainable development in Somalia. The establishment of the Somalia Youth Climate Platform (SYCP) exemplified this success, engaging youth as vital contributors to climate governance. Through strategic alliances with ministries, the private sector, and UN agencies, the platform mobilized young leaders to drive innovative solutions for climate challenges. The collective capacity built through these partnerships reflects a significant step towards a resilient and sustainable future for Somalia, with diverse voices actively participating in shaping the national agenda.

Learning impact - Somalia had institutionalized a comprehensive learning and coordination framework that significantly enhanced national and sub-national capacities in environmental governance, disaster risk reduction (DRR), and climate resilience. Through inclusive policy workshops and multi-sectoral dialogues, the project engaged all relevant stakeholders—government institutions, civil society, youth networks, and development partners—ensuring that environmental and DRR strategies were co-created, context-specific, and aligned with Somalia’s national development priorities - The project’s adaptive management approach allowed it to remain flexible and risk-responsive, adjusting to delays and evolving conditions. This responsiveness, combined with enhanced community engagement and scaled-up early warning systems, ensured that the project’s impact was both deep and durable. Ultimately, the initiative laid the foundation for a cohesive, inclusive, and sustainable resilience architecture in Somalia—anchored in local leadership, gender equity, and multi-stakeholder collaboration. - Training programs were tailored to local needs and institutionalized across federal and state levels, transitioning from one-off events to structured learning systems. These efforts prioritized gender equality and inclusivity, ensuring that women, youth, and marginalized groups were not only participants but also leaders in resilience-building initiatives. - The integration of local DRR and early warning systems into governance structures, supported by the establishment of DRR focal points and geospatial coordination units, enabled more responsive and data-driven planning across ministries. - The project also strengthened donor coordination and resource mobilization by fostering innovative partnerships and structured stakeholder engagement platforms at both national and federal member state levels. These platforms streamlined collaboration, reduced duplication, and aligned efforts with Somalia’s climate and development priorities. The Somalia Youth Climate Platform (SYCP) emerged as a key driver of innovation, showcasing the power of youth-led digital solutions and advocacy in addressing environmental challenges. - Community co-management frameworks were established to nurture local ownership and resilience, ensuring that interventions were grounded in local realities and sustained beyond the project’s lifecycle. Public awareness campaigns and advocacy messaging emphasized the interconnectedness of water, environment, and disaster risks, while promoting behavioral change and social transformation.

Coordination with other UN entities UNDP has made significant advances in collaboration with various UN agencies to enhance disaster risk reduction and environmental governance in Somalia. Notably, UNDP partnered with UNDRR and UNOCHA to develop the Somalia National Disaster Risk Reduction Strategy and operationalize the National Emergency Operation Centre (NEOC). Additionally, through close coordination with UNEP, UNDP supported national consultations to finalize the National Environmental Strategy and Action Plan (NESAP), laying the groundwork for improved environmental governance. Working in synergy with the Government of Sweden, UNDP has further strengthened its partnerships with other UN agencies, including projects like the Joint Programme on Local Governance and Decentralized Service Delivery (JPLG), to ensure coordinated efforts in Integrated Water Resources Management (IWRM), disaster risk reduction, and environmental governance. In expanding its partnerships, UNDP has engaged with key government ministries, particularly the Ministry of Youth and Sports (MoYS), to empower young people in addressing climate security and fostering inclusive participation at events like COP28. The Ministry of Environment and Climate Change (MOECC) has also cultivated a crucial partnership with Somali National University (SNU), focusing on advancing environmental research and sustainability at the graduate level. These collaborations not only generate valuable knowledge and innovative solutions for Somalia's environmental challenges but also enhance resource utilization and maximize the impact of collective actions among UNDP projects and other UN entities. Furthermore, UNDP, in partnership with UNDRR, has facilitated stakeholder consultations to develop Somalia's Roadmap for the Implementation of the Early Warning for All (EW4ALL) Initiative (2024–2027). This comprehensive framework aims to bolster early warning systems and promote multi-stakeholder engagement, ensuring accountability among early warning actors. The roadmap envisions a collaborative effort that integrates government institutions, regional authorities, and international partners to address both transboundary and localized risks effectively. Additionally, the Somali Youth Climate Platform, in collaboration with UNDP HQ, enabled a youth delegate's participation in the Climate, Peace, and Security Expert Academy in Nairobi, empowering the next generation of leaders to tackle climate challenges and contribute to sustainable peacebuilding efforts.

Monitoring and oversight activities Monitoring activity; Date; Description; Comments & Recommendations. Local Project Appraisal Committee (LPAC) Meeting; 24 March 2021; The objectives of the meeting were to review the project to suggest constructive improvements in the project document and endorse the project for final approval.; Agreed decisions and recommendations: - Realignment of the relevant gender project SDGs in the revised Prodoc. - The implementation of the project to be managed by a full-time International Project Manager / Chief Technical Specialist with support from full-time and short-term experts and consultants as well as support staff. - 30% gender representation is set as a benchmark for all the project outputs and activities. Also, the project team to follow-up discussion with the Gender Advisor, UNDP Somalia, and make project components, outputs, and activities more gender-focused - The UN coordination levy and the donor code to be adjusted accordingly in the multi - year work plan of the Prodoc. - Revisit the Project Results Framework in consultation with Project Manager and Programme Oversight and Quality Assurance Unit. - Established linkages and synergy with the relevant projects in other Portfolios. - The LPAC members approved the project subject to the additions and taking actions on points raised by the LPAC participants. Resilience and Climate Change Team of UNDP to to process approval and signing of the Project Document while arranging similar coordination with the government counterparts for countersigning.. Stakeholder Review Consultation Meeting; 19 May 2021; The objective of the consultation meeting was to brief and consult with the donors and other stakeholders on the DRR components which aims to strengthen the capacities of the relevant ministries/Institutions at federal and federal member states as well as community levels to respond to the quadruple threats in Somalia namely Climate Change, recurrent droughts, and locust invasion as well as health pandemic including the Global Covid-19. The meeting was attended by the Ministers and Senior Government Officials of FGS and FMS as well as SIDA Representative.; Agreed decisions and recommendations: - The project is vital and not to delay its implementation any further to minimize subsequent impacts to vulnerable communities across Somalia. - Discuss priorities and agree within the scope and strategic objectives of the project. - Agree on coordination and consultation platforms through the various existing/proposed structures in the project management during implementation. - Organize another consultation meeting between the federal and federal member states to clarify priorities, reach consensus around the roles, responsibilities, budget, and agree on the way forward. - Regularize the functions of the technical committees and project board committees i.e. holding quarterly and Bi-annual meetings while adjusting the frequency of the meetings on the needed basis. - Minutes of the meeting will be prepared and shared with the presentation to all the project stakeholders to provide necessary feedbacks. - The need to improve communication, coordination, and information sharing not only for finalizing the project document but increase the level of participation and ownership. - Relevance, ownership, and profile at federal and federal member states while reaching out to the communities at the local level. - Project budget distribution indicates more resources to federal member states at the second and third year while budget allocations to federal governments more in the first year because of the nature of the activities including the establishment of regularity frameworks, policies, and readiness and partnerships. - Question on MoHADM-FGS mandate is outside of the project and to be taken bilaterally by the Government counterparts at federal and federal member states. - Use the existing project implementation structures namely the technical committees and the Project Steering Committees / Project Board to improve the coordination and oversight functions of the project. Representatives of the Federal Government, federal member states, UNDP, and Donors should be represented equally in both the committees, and any grievances, and decision making should be directed to the existing coordination platforms.. Technical Working Group Meeting; 1 September 2021; The objectives of the Technical Advisory Group Meeting (TAGM) were; first to familiarize and understand the three strategically linked components namely Integrated Water Resource Management (IWRM), Environmental Governance, and Disaster Risk Reduction (DRR) and their interlinkages. Second to clarify the roles and collaborations around the project components. Third to present the project implementation principles, oversight, and individual responsibility towards successful delivery. Fourth to update each other on the progress regarding key planned milestones, input, and resources to determine the course to desired targets and outputs. Fifth to identify key issues and challenges that might require the board's attention. The meeting was participated by representatives of the federal and federal member states.; Agreed decisions and recommendations: - Project designs to be implemented in an integrated and interactive manner leaving no one behind - Strengthening consultations and communication among partners while keeping at one pace all components - Working in a coordinated manner and promoting synergies, address hurdles on time whilst UNDP support technically and operationally the government counterparts at federal and federal member states - Promote meaningfully the gender dimensions especially for women on issues of water management, environmental impacts, and disaster management - Arranging a meeting by mid-November 2021, to conclude collectively 2022 Letters of Agreements - Harmonize communication and information to meet the desired outcomes of the project - In-depth understanding of Letters of Agreements, keeping documentation in place to ease results-oriented reporting, joint monitoring, and oversights - Respect donors’ concerns. - Effective and efficient use of the project resources for the intended purpose.. Project Board Meeting; 28 November 2022; This project board meeting took place in Mogadishu and participated by Federal Government of Somalia - MOEWR, MOECC & SODMA, UNDP and donors. The objectives of this meeting was to discuss progress and achievements that UNDP and partners made during this reporting period and to seek guidance over challenges encountered during the period under consideration. The meeting was also an opportunity to discuss on the outcome technical review meetings organized with the partners in FMSs under component 2 (Environmental Governance) and component 3 (Disaster Risk Reduction), the institutional changes as a result of political transition in the Government and the impacts in the Project Implementation and the new initiative of establishing a National Climate Youth Platform supported by UNDP-Sida.; Agreed decisions and recommendations: - Support and continuation of the Master's degree program in integrated water resources management. - Establishment of workstations at the water mandated institutions GIS equipment (with satellite and resistivity equipment for surface and groundwater investigations). - Support the coordination of the water sector under the National Water Sector Coordination facility. - Support and strengthen the geospatial unit at FGS MOEWR and establish a state geospatial unit at FMS level. - Continue support for implementation of IWRM concepts and applications through comprehensive training workshops at national, state, and local levels. - Establishment of geospatial unit at FGS MOECC. - Continue discussion with Sida on how to enrich partnership with the Somali National University. - Bringing up the integrated aspects of the project and demonstrating how well Sida's funded project integrated with UN programmes with national processes in the National Development Plan (NDP). - Water priorities for each FMS to be included into the WED project, national development plan and national water strategy. - Coordinate a joint activity under the various outputs of the project, jointly implemented by SODMA, MOEWR & MOECC. - Continue support for the National Multi-Hazard Early Warning Center and GIS and remote sensing. - Develop communication strategies for WED project. - Speed up the processes for midterm review such as drafting of terms of reference (ToR) and procurement processes.. Monitoring Missions to Federal Member States; 18 August – 24 September 2022; The objective of the monitoring missions was to monitor the progress of the implementation of the FMS partner’s work, provide technical support to the ministries, identify issues that need to be addressed to ensure on-track implementation of the project work plan, and explore the challenges in implementation and probe possible solutions and recommendations on the way forward. The monitoring also assessed the level of satisfaction of technical/advisory/financial support received from the project by the partners.; Agreed decisions and recommendations: - The procedures for information sharing and coordination were agreed upon with the ministries and agencies, as well as the ministries of the environment, and the State level coordinators for both disaster and humanitarian management. - Requirements for quality assurance and reporting requirements were developed and made available. Counterparts were aware of the high quality standard of the work needed. - UNDP and project counterparts agreed on the intended results and milestones to be achieved across all the activities in the LOAs as well as how to ensure donor visibility and efforts to ensure gender balance when conducting activities. - Detailed action points agreed upon, and who to involve/focal points for each national counterpart to coordinate the implementation of the project activities at field level.. Project Board Meeting; 20 December 2023; This project board meeting took place in Mogadishu and participated by Federal Government of Somalia - MOEWR, MOECC & SODMA, UNDP and donors. The objectives of this meeting was to discuss progress and achievements that UNDP and partners made during this reporting period and to seek guidance over challenges encountered during the period under consideration. The meeting was also an opportunity to discuss on the outcome of recently conducted midterm evaluation of UNDP Sida funded project and approve the next year work plan.; Agreed decisions and recommendations: - The project Board endorses the implementation of the results under WED project in 2023 as well as the strategy to complete the remaining activities by June 2024. - The Project Board noted that the completion of few activities such as Master's programme under comp 1 and environmental studies under comp2 may go beyond June 2024. In such case, UNDP will send request to Sida to consider the extension of the project period until the end of December 2024. - Based on the presentation of positive MTR (Mid-Term Review) findings, the Board underscored the importance and urgency of a possible next phase of the programme, offering opportunities to scaling up successful pilots of the project. To ensure smooth transition, the Board advised to explore possibility of a transition phase of one year in consultation with Sida and the project counterparts. - Support and continuation of the Master's degree program in integrated water resources management. - •Strengthening of coordination in the water sector at the local level. - The Project Board emphasize the importance to finalize the implementation of the national environmental quality standards which will lay the foundation of the legal regime for addressing environmental pollution in the country. - Conclude that the final evaluation report would be with us 31 January 2024. - Prepare management response by 15 February 2024.. Monitoring Mission to Federal Member States – Baidoa, Southwest State of Somalia; 2-4 June 2024; UNDP Somalia’s Resilience and Climate Change Team, led by Tarik ul-Islam, traveled to Baidoa to meet with partners, review key results achieved under the SIDA-funded WED project and validate the next phase of a potential project. The mission aimed to discuss priorities in disaster risk management, environmental governance, and sustainable water management with partners, beneficiaries, women, and youth networks.; - Meeting with the Ministry of Humanitarian and Disaster Management Affairs - Key Points: - Early Warning Systems (EWS) need improvement in quality and integration of indigenous knowledge. - Priority for disaster resilience and preparedness, particularly for women, people with disabilities, and IDPs. - Supply routes for 650,000 IDPs must remain open during disasters. - Ministry has reduced disaster casualties significantly (e.g., 23 lives lost in 2023 floods). - Training committees and youth volunteer networks were identified as critical steps. - Meeting with the Ministry of Environment and Climate Change - Key Points: - Focus on biodiversity conservation, blue economy initiatives, solid waste management, and afforestation. - Need for federal-state coordination, green jobs for youth, journalist training, and capacity-building initiatives. - Emphasis on nature-based solutions and private sector engagement. - Women’s Groups (SUGE and others) - Key Points: - Activities include alternative livelihoods (e.g., nurseries, crafting from natural materials). - Additional training and skills development needed to expand their resilience-building initiatives. - Some groups have saved funds from grants and sought greener job opportunities. - Youth Groups - Key Points: - Active in emergency response, food distribution, and supporting vulnerable populations. - Request for training in emergency response, peacebuilding, skills development, and youth platforms (e.g., climate platforms). - Interest in cultural exchange programs and sports competitions. - Meeting with the Mayor - Key Points: - Challenges include water, waste, energy issues, and urban resilience. - Land department has resolved over 140 conflicts. - Formation of Disaster Risk Reduction (DRR) committees planned. - Solid waste department requires more resources. - Stakeholder Validation and Next Steps - Key Areas of Focus: - Continued capacity building for ministries and community-level engagement. - Developing roadmaps for DRR, environmental governance, and green jobs. - Skills training and youth engagement through programs and platforms. - Organizing joint events, including workshops with beneficiaries and DRR volunteers. Recommendations - Early Warning Systems (EWS) and Disaster Preparedness: - Improve EWS quality, integrating indigenous knowledge and building trust in the information provided. - Activate and train committees, including youth volunteer networks, for enhanced disaster response. - Capacity Building: - Strengthen ministries and coordinators through continuous training and capacity development. - Focus on peace-positive training, green jobs, and environmental governance linked to business and climate security. - Community-Level Engagement: - Expand resilience-building initiatives targeting women, youth, and vulnerable groups. - Establish organized platforms and training centers for women’s and youth groups. - Environmental and Urban Resilience: - Prioritize biodiversity conservation, solid waste management, afforestation, and nature-based solutions. - Improve urban services and infrastructure, including road reconstruction and energy systems for IDPs. - Youth and Women Empowerment: - Support alternative livelihoods, such as nurseries and natural material crafting. - Promote cultural exchange programs, skills training, and organized youth networks (e.g., youth climate platforms). - Joint Planning and Events: - Organize a consultation workshop in August 2024 to engage beneficiaries, youth groups, and DRR volunteers. - Align activities with ministries’ disaster and climate adaptation priorities. Follow up Actions to be Taken - Update the extension of the project following mission to Baidoa and consultations with SIDA - Organize consultation workshop with additional beneficiaries in Baidoa - SIDA to send letter on tentative cost extension, pending internal approval - Start draft of a new project document..

Communication activities Visibility and communication efforts had been significantly strengthened through the implementation of a comprehensive communication strategy aligned with UNDP and Sida guidelines. This strategy was embedded across all project components—Integrated Water Resources Management (IWRM), Environmental Governance, and Disaster Risk Reduction (DRR)—ensuring consistent branding, transparency, and stakeholder engagement. All project events, including workshops and consultations, adhered to a standardized visual identity featuring the logos of national counterparts, UNDP, and Sida. These efforts enhanced the project’s credibility and visibility, fostering stronger relationships with donors, government institutions, and community stakeholders. In addition, the project leveraged multiple communication channels—including the UNDP Somalia Country Office website and social media platforms (Facebook and Twitter)—to disseminate timely updates, success stories, and milestones. Regular email updates to Sida and other partners reinforced transparency and accountability, while high-quality visuals and storytelling amplified the project’s impact across digital platforms. These efforts not only increased public awareness of the project’s outcomes but also created a robust platform for ongoing engagement, positioning the project as a model for effective communication and stakeholder alignment in climate and resilience programming. https://twitter.com/mohadm_somalia https://fb.watch/7_Pw9cyH18/ https://www.facebook.com/Hirshabelle-TV-109245160998463/videos/576508340161474/?extid=WA-UNK-UNK-UNK-AN_GK0T-GK1C https://twitter.com/MoHADM_Somalia/status/1465190819850330114?t=WU5Wj9U8hFKBoPELDxnlLg&s=08 https://www.facebook.com/sntvnews/videos/216261797265368/?extid=WA-UNK-UNK-UNK-IOS_GK0T-GK1C&ref=sharing https://www.facebook.com/Puntlandstatetv/videos/587401659100139/?extid=NS-UNK-UNK-UNK-AN_GK0T-GK1C https://t.co/vr4h7Qt9eI https://t.co/y3bxxg0GOi https://t.co/yzxh35RvA4 https://twitter.com/MoEWRSo/status/1574048127677497344 https://fb.watch/gNSC3Qa6vD/ https://fb.watch/g7OQMiCVI0/ https://fb.watch/g7OSbAiDEC/ https://x.com/moysfgs/status/1850963827371757967?s=46&t=_Zz7FnzEGMGeKhRQfV1AeQ

Section 5: Project management

| Number of project board meetings held | 3 |
| --- | --- |
| Number of UN staff (international/national) funded by the project | 1 international staff and 4 national staff |
| Number of government personnel funded by the project? What are their functions and where do they work? | 17 national consultants/advisors - They support the implementation of project activities of the three components IWRM, Environmental governance and DRR at federal, state and local levels. |
| How has the project ensured the visibility of SJF donors during the reporting period? | The visibility is ensured as per the visibility and communication guidelines of UNDP and donor. Sida, UNDP and national counterparts logos and a notice on the Sida funding was put on each communication about the activities. In line with this, significant improvements have been made in terms of sharing information with donors, beneficiaries, and other stakeholders. Project information have been regularly provided on UNDP country office (CO) website and social media platforms (Facebook and Twitter). |

Section 6: Cross-cutting issues

Gender equality and women empowerment Over the course of four years, the project made significant progress in mainstreaming gender across Integrated Water Resource Management, Environmental Governance and Disaster Risk Reduction, in Somalia. These efforts have led to transformative outcomes that strengthened institutional capacities, empowered women and girls, and advanced inclusive resilience building at federal, state, and community levels. More than 4,000 women were directly engaged and empowered through targeted capacity building, livelihood support, and climate action interventions. These included extensive training on Integrated Water Resources Management (IWRM), environmental governance, and gender-responsive DRR. Women’s participation was prioritized in Local Disaster Resilience Fund (LDRF) initiatives, which piloted transparent and gender-sensitive funding mechanisms that enabled women to actively shape and implement local resilience solutions. To enhance women’s access to higher education in climate resilience fields, the project supported the launch of Somalia’s first-ever Master’s degree program in IWRM at the Somali National University. Between 2022 and 2024, a total of 35 students (30% women) were enrolled, with the program integrating climate change, natural resource management, and gender equality into its curriculum. The project delivered practical livelihood and resilience support to over 2,200 women-headed households, especially in drought-affected and disaster-prone communities. In Baidoa, 30 women received business start-up capital totaling $20,000 through a gender-responsive and transparent selection process. Additionally, 600 solar home systems and 1,600 high-quality plastic sheets were distributed to support women-led households in informal settlements. These interventions not only improved living conditions but also strengthened women’s income-generation capacities. Notably, 546 women were trained in solar gadget repair, providing them with marketable technical skills that contribute to long-term livelihood resilience. In Somaliland, the project targeted 500 women-headed households across drought-affected districts, distributing 300 solar lanterns and 200 water storage tanks (1,000-liter capacity each). These interventions had wide-ranging benefits, including enhanced safety for women and girls at night, improved educational outcomes for children through access to clean lighting, and reduced time burdens on women and girls who previously traveled long distances to fetch water. Efforts were further strengthened by engaging 810 women in community-based awareness campaigns, participatory consultations, and tailored training that promoted inclusive decision-making and built capacities in environmental governance. The project also expanded collaboration with the Somalia Youth Climate Platform (SYCP) to mainstream gender in climate advocacy. Women and girls participated equally in post-COP28 national consultations, where their leadership and perspectives on climate resilience were recognized and integrated into follow-up strategies. Through these sustained and targeted interventions, the project delivered tangible outcomes in advancing gender equality (SDG 5), building inclusive resilience (SDG 13), and promoting access to clean energy and water (SDGs 6 and 7). Women across Somalia are now better equipped with knowledge, tools, and voice to actively participate in climate action, disaster preparedness, and sustainable development processes at all levels. Proportion of gender specific outputs in the project; Total number of project outputs; Total number of gender specific outputs. 11; 4. Proportion of project staff with responsibility for gender issues; Total number of staff; Total number of staff with responsibility for gender issues. 4; 4.

Human-rights based approach The project achieved transformative results in advancing the human rights, resilience, and inclusion of marginalized and vulnerable communities in Somalia, particularly in chronically water-stressed and disaster-prone regions. Through a rights-based and gender-responsive approach, the initiative promoted equitable access to water and disaster risk management services, ensuring that women, children, persons with disabilities, and other underserved groups were not only protected but also empowered to influence and shape the systems that affect their lives. At the core of these achievements was the institutionalization of a gender-responsive National Disaster Risk Management Plan, which embedded key human rights principles—accountability, transparency, non-discrimination, and meaningful participation—into national and sub-national disaster preparedness and response frameworks. Developed through an inclusive, multi-stakeholder process, the plan prioritized the needs of the most vulnerable and integrated gender equity into Somalia’s national disaster risk governance, setting a precedent for inclusive policy reform across sectors. The project also played a pivotal role in strengthening institutional accountability and service delivery mechanisms, establishing robust systems that enhanced the responsiveness and transparency of duty bearers. These efforts led to more inclusive and equitable governance, particularly in the delivery of critical water, disaster response, and resilience-building services in fragile settings. In alignment with UNDP’s commitments to gender equality and inclusive development, over 2,000 women were empowered through a comprehensive suite of interventions, including gender-responsive funding schemes, capacity-building in Integrated Water Resources Management (IWRM), environmental governance, and disaster risk reduction (DRR), and leadership development programs. These initiatives not only enhanced women's technical and leadership skills but also enabled them to become active agents of change, shaping local solutions, influencing policy dialogues, and participating meaningfully in decision-making at the community and institutional levels. Importantly, the project dismantled systemic barriers that had long excluded women and marginalized populations from governance and planning processes. Through the creation of inclusive platforms and multi-stakeholder dialogues, communities were empowered to engage directly with policymakers, advocate for their rights, and drive development priorities that reflect their needs and aspirations. The project laid the foundation for climate-resilient and socially just development in Somalia by integrating human rights, gender equity, and environmental sustainability into a single coherent strategy. It contributed to tangible improvements in human dignity, social inclusion, and resilience to climate-induced shocks, particularly in regions facing acute water insecurity and disaster risk. These achievements directly advance multiple Sustainable Development Goals (SDGs)—notably SDG 5 (Gender Equality), SDG 6 (Clean Water and Sanitation), SDG 13 (Climate Action), and SDG 16 (Peace, Justice and Strong Institutions)—and provide a scalable model for rights-based resilience building in fragile contexts. Has the programme included a protection risk assessment in its context analysis, including on gender issues, and taken measures to mitigate these risks to ensure they are not exacerbated, or new risks created?; Result. Yes. Number of programme outputs specifically designed to address specific protection concerns; Result. 11. Number of programme outputs designed to build capacity of duty bearers to fulfil their human rights obligations towards rights holders.; Result. 4.

Humanitarian-development-peace nexus UNDP Somalia played a catalytic role in operationalizing the Humanitarian–Development–Peace (HDP) Nexus through a strategic shift from reactive crisis response to proactive disaster risk reduction (DRR), institutional resilience building, and inclusive, risk-informed recovery planning. UNDP spearheaded a national paradigm shift by embedding DRR into Somalia’s development planning. A key milestone was the institutionalization of Standard Operating Procedures (SOPs) for disaster management, which established a predictable and coordinated emergency response system. This initiative helped reduce recurring losses of life, livelihoods, and natural resources, thereby decreasing long-term humanitarian needs. A government-wide, multi-hazard risk management approach was promoted across federal and state institutions. UNDP's advocacy and technical assistance emphasized the importance of proactive risk mitigation, which was acknowledged by national counterparts and partners as a progressive departure from conventional, reactive disaster response frameworks. UNDP invested significantly in capacity-building initiatives to enhance the technical skills of federal and state disaster management institutions. Training covered DRR mainstreaming, early warning systems, and drought resilience. These efforts helped operationalize the HDP Nexus by fostering local ownership, sustainability, and institutional readiness for future shocks. Simultaneously, UNDP supported the alignment of the National DRR Plan with Somalia’s National DRR Strategy, fostering a unified and coherent national framework for addressing priority risks and vulnerabilities, particularly in disaster-prone regions. In response to Somalia’s protracted drought crisis, UNDP deployed Drought Response Coordinators across all Federal Member States (FMS) to strengthen real-time data collection, enhance coordination mechanisms, and support the Ministries of Humanitarian Affairs and Disaster Management (MOHADMs) in conducting rapid drought needs assessments, promoting gender-responsive interventions, and facilitating early recovery planning rooted in resilience. This integrated approach effectively bridged immediate humanitarian response with longer-term development and peacebuilding priorities. UNDP played a pivotal role in supporting evidence-based recovery planning in Somalia by co-leading major post-disaster needs assessments. In collaboration with the Federal Government of Somalia, the UN, World Bank, EU, and Asian Development Bank, UNDP contributed to the 2022 Rapid Post-Disaster Needs Assessment (R-PDNA) for Deyr Floods, which evaluated pre-crisis baselines, sectoral impacts, and recovery priorities, culminating in a government-led Recovery Framework to guide sustainable reconstruction and resilience investments. The devastating Deyr Floods—which affected 2.48 million people, displaced over 1.2 million, and caused 188 fatalities—UNDP supported the Government in conducting a Rapid Flood PDNA that estimated $176.1 million in damages and $230.61 million in recovery needs. This assessment prioritized investments in agriculture, transport, housing, and water, while integrating climate adaptation and resilience-building measures to ensure that recovery efforts also enhanced long-term adaptive capacity. UNDP’s support ensured that both drought and flood recovery efforts incorporated DRR principles, resilience-building, and climate adaptation strategies. These interventions helped shift the focus from short-term relief to risk-informed development, reinforcing the HDP nexus across planning, programming, and partnerships. Gender equity was a cross-cutting priority, with UNDP facilitating inclusive approaches to recovery that responded to the specific needs of women and marginalized groups. Drought response coordinators, for example, were instrumental in embedding gender-responsive planning within MOHADMs and local authorities.

Environment and climate security UNDP Somalia significantly advanced environmental governance and climate security by embedding the UNDP Social and Environmental Standards (SES) and accountability mechanisms across all project interventions. This approach ensured that sustainability, equity, and transparency were central to implementation, resulting in strengthened institutional resilience and improved environmental stewardship. National and sub-national authorities, including the Ministry of Environment and Climate Change (MoECC) and the Benadir Regional Authority (BRA), were empowered to adopt risk-informed planning and sustainable resource management practices, contributing to long-term resilience and inclusive development. Through targeted technical assistance and capacity-building, UNDP supported Somali institutions in implementing integrated water resources management (IWRM), disaster risk reduction (DRR), and environmental governance frameworks. These efforts enabled evidence-based policymaking and enhanced preparedness for climate-induced risks. A key milestone was the launch of a city pilot initiative under the UNDP-Sida-funded project, which catalyzed the development of a comprehensive Urban Resilience Framework in collaboration with UN-Habitat, DOECC, and BRA. This initiative laid the groundwork for resilient infrastructure, sustainable urban planning, and improved service delivery in Somalia’s rapidly urbanizing regions. UNDP’s support extended to the development of a National Strategy and Action Plan for Solid Waste Management, reinforcing Somalia’s urban resilience agenda. By mobilizing international expertise and facilitating multi-stakeholder engagement, UNDP helped define urban priorities and align them with national development goals. These efforts fostered a shared vision for climate-resilient cities and contributed to the institutionalization of environmental safeguards in urban governance. The integration of SES principles throughout project design and implementation ensured that environmental and social risks were systematically addressed. In coastal areas, UNDP championed marine conservation and climate security through innovative, youth-centered programming. Strategic partnerships with private sector actors enabled the delivery of training on sustainable materials, circular economy practices, and eco-innovation. These initiatives promoted green entrepreneurship, created alternative livelihoods, and supported ecological restoration, particularly in vulnerable coastal communities. By embedding sustainability, inclusivity, and accountability into its programming, UNDP Somalia played a pivotal role in building resilient communities and advancing a greener, more secure future for the country.

Prevention of corruption As part of its unwavering commitment to integrity and ethical conduct, UNDP enforced a zero-tolerance policy on fraud, corruption, and sexual exploitation and abuse throughout the implementation of the Sida-funded project. This principle was operationalized through the adoption of the Harmonized Approach to Cash Transfers (HACT), which served as the cornerstone of a comprehensive risk management framework. The project conducted rigorous HACT assessments that identified institutional and operational vulnerabilities by systematically engaging federal and state-level partners. These assessments informed the design and delivery of tailored capacity-building interventions, including structured training sessions, operational guidance, and targeted spot checks. As a result, implementing partners demonstrated measurable improvements in fiduciary compliance, internal controls, and ethical standards. The project’s integrated risk mitigation strategy led to strengthened institutional accountability and transparency, reducing the incidence and likelihood of financial mismanagement. These efforts not only safeguarded UNDP resources but also enhanced the credibility and operational readiness of national and subnational institutions. Moreover, the project catalyzed long-term institutional resilience by embedding risk-informed practices into partner workflows. Through sustained technical support and oversight, partners acquired the tools and competencies necessary to uphold international fiduciary standards beyond the project lifecycle. This has translated into improved service delivery, more responsive governance, and increased stakeholder trust in UNDP-supported initiatives. Ultimately, the project’s preventative and capacity-building measures contributed to a more robust and accountable implementation environment, laying the groundwork for sustainable development outcomes and reinforcing the governance architecture essential for future programming.

Project sustainability The project successfully embedded its interventions within national and local governance systems, ensuring sustainability through strong local ownership and alignment with Somalia’s development priorities. It strengthened accountability mechanisms and institutionalized practices that now guide coordinated action in disaster risk reduction, environmental governance, and sustainable water resource management by fostering active engagement of line ministries, relevant agencies, community representatives, and civil society. These efforts have enhanced institutional capacity, improved policy coherence, and established governance structures that continue to deliver results beyond the life of the project. Long-term capacity-building initiatives have equipped government institutions, technical agencies, and community structures with the skills and tools to independently manage, adapt, and scale resilience-focused interventions. As a result, stakeholders are now able to effectively plan, implement, and monitor risk reduction measures, enforce environmental management regulations, and optimize water resource use without reliance on external technical support. This shift has embedded resilience thinking into national and sub-national planning frameworks, making disaster preparedness, environmental sustainability, and equitable water governance integral to Somalia’s development agenda. The project’s participatory and inclusive management approach cultivated a culture of collaboration, innovation, and shared responsibility. This has encouraged stronger inter-agency coordination, enhanced stakeholder trust, and fostered meaningful community participation in decision-making. Communities now play a central role in leading and sustaining locally tailored solutions that address their unique environmental and climate risks. The integration of these inclusive practices into governance structures has ensured that resilience building remains community-driven and nationally supported. Sustainability has also been reinforced through the creation of self-sustaining mechanisms and the integration of best practices into national and sectoral development strategies. Somalia now benefits from scalable models that reduce dependency on external funding, promote environmentally sound livelihoods, and contribute directly to achieving national climate resilience and sustainable development goals. These enduring outcomes have positioned the country to better withstand future shocks, safeguard natural resources, and advance toward its long-term development vision. The following is a list of capacity-building training activities completed during the project period: #; Target group; Dates; Number of participants; Title of the training; Location of the training; Training provider. Ministry, District or UN staff; Others; M; F; Total. Ministry of Energy, Water & Resources - Senior officials and staff - Federal and State level; 25th - 29th September 2021; 41; 19; 60; Training on IWRM concepts, principles and practical tools to promote sustainable water resource management in Somalia.; Mogadishu - Somalia; IWRM Consultant - Abdullahi Hassan. Ministry of Energy, Minerals and Water Resources - Senior officials, staff -; 14th - 19th December 2021; 48; 17; 65; Training on practical tools on IWRM.; Garowe - Puntland; IWRM Consultant - Abdullahi Hassan. Ministries in Charge of Environment & Climate Change - Federal and State level; 21st -23rd November 2021; 34; 16; 50; Training of Trainers (ToT) on knowledge and understanding of the Sustainable Environmental Management.; Mogadishu, Benadir; DoECC Consultant - Abdikarim Hersi. Ministry of Humanitarian Affairs and Disaster Management (MoHADM) - FMS; Q3; 113; 72; 185; Preparedness training on emergency coordination and operations; Somaliland- Galmudug, Hirshabelle, Puntland, Jubaland, South West; FMS DRR consultants. Ministry of Humanitarian Affairs and Disaster Management (MoHADM) - FMS; Q3; 90; 50; 140; DRR training focusing institutional learning and development priorities.; Somaliland- Galmudug, Hirshabelle, Puntland, Jubaland, South West; FMS DRR consultants. Ministry of Humanitarian Affairs and Disaster Management (MoHADM) - FMS; Q3/Q4; 171; 83; 254; Training on End to End Early Warning training at FMS; Somaliland- Galmudug, Hirshabelle, Puntland, Jubaland, South West; FMS DRR consultants. Municipal Officials; Q3/Q4; 162; 53; 215; Training on urban Disaster Risk Reduction; Somaliland- Galmudug, Hirshabelle, Puntland, Jubaland, South West; FMS DRR consultants. Ministry of Humanitarian Affairs and Disaster Management (MoHADM) - FMS; Q3/Q4; 75; 28; 103; Stakeholder consultation on local DRR priorities; Somaliland- Galmudug, Hirshabelle, Puntland, Jubaland, South West; FMS DRR consultants. Public and Private Institutions of Federal Member States at Staff, Ministerial and Senior level; 02-06 April 2022; 38; 27; 65; Integrated Water Resources Management; Baidoa, South-West State of Somalia; IWRM Consultant – Abdullahi Hassan. Public and Private Institutions of Federal Member States at Staff, Ministerial and Senior level; 18-22 September 2022; 46; 26; 72; Integrated Water Resources Management; Kismayo, Jubaland State of Somalia; IWRM Consultant – Abdullahi Hassan. Federal and State Ministries of Energy and Water Resources; 24-25 September 2022; 43; 7; 50; IWRM Institutional Coordination and Leadership Engagement; Kismayo, Jubaland State of Somalia; IWRM Consultant – Abdullahi Hassan. Federal and State Ministries of Energy and Water Resources; Q4 - 2023; 42; 18; 60; Integrated Water Resources Management; Beledweyn, Hirshabelle State of Somalia; IWRM Consultant – Abdullahi Hassan. Ministries in Charge of Environment & Climate Change - Federal and State level; 28-30 June 2022; 31; 13; 44; TOT trainings on environmental governance for the federal and federal member state institutions; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. Ministries in Charge of Environment & Climate Change - Federal and State level; 19 June 2022; 60; 29; 89; Consultation workshop on accelerating and localization of the Green SDGs in Somalia.; Mogadishu, Somalia; MOEC Consultant – Mr. Ali A. Warsame. FGS Institutions and MEA Focal Points at FMS level; 25-26 July 2022; 36; 14; 50; Training workshop on Multilateral Environmental Agreements for the FGS Institutions and MEA Focal Points at FMS level.; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. FGS and FMS institutions and Banadir Region administration; 20-21 June 2022; 36; 14; 50; Training workshop on environmental monitoring compliance and enforcement; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. FGS and FMS institutions and private education umbrella, research institutions, local universities, CSOs; 23 June 2022; 29; 13; 42; Consultation workshop on the role of environmental education in environmental protection; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. Ministry of Environment and Climate and Change and CSOs; 8 December 2022; 54; 26; 80; Advocacy workshop on prevention of Environmental Management of Plastic Wastes for Prevention of Marine Litter; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. FGS and FMS institutions and private education umbrella, research institutions, local universities, civil societies, and National Museum of Somalia; 3-4 October 2022; 41; 17; 58; Technical consultation workshop for the selection of environmental research topics and necessary criteria for implementation; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. FMS MEA focal points and FGS relevant ministers; 10-11 November 2022; 32; 25; 57; Training workshop for financial mechanisms source for the implementation of multilateral environmental agreements; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. Ministries in Charge of Environment & Climate Change - Federal and State level and Somalia National Bureau of statistics; 11 December 2022; 26; 12; 38; Technical consultation workshop for the establishment of a Geospatial unit at MOECC; Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. Ministries in Charge of Environment & Climate Change - Federal and State level and Somalia National Bureau of statistics; 6 - 7 December 2022; 41; 19; 60; Validation workshop on Somalia integrated solid waste management strategy (SISWMS); Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. BRA and relevant institutions in Mogadishu including NGOs/CSOs; 21 - 23 November 2022; 21; 9; 30; Training on solid waste management; Mogadishu, Somalia; BRA Consultant – Abdikhafar Abubakar. Ministries in Charge of Environment & Climate Change - Federal and State level; 28-29 December 2022; 39; 18; 57; Validation workshop On National Environment Strategy Action Plan (2023-2027); Mogadishu, Somalia; MOEC Consultant – Abdikarim Hersi. Ministries in Charge of Environment & Climate Change - State level; Q1-Q4, 2022; 63; 33; 96; ToT trainings on Environmental Governance for federal member state institutions; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level; Q1-Q4, 2022; 66; 37; 103; Training on National environmental action plan; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level; Q1-Q4, 2022; 53; 36; 89; Local consultation workshop on green SDGs; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level; Q1-Q4, 2022; 32; 15; 47; Training on Geo-spatial services; Puntland, Galmudug, Hirshabelle, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level; Q1-Q4, 2022; 49; 24; 73; Training on environmental monitoring, compliance and enforcement; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level; Q1-Q4, 2022; 49; 15; 64; Training on Multilateral Environmental Agreements (MEA) compliance and reporting; Galmudug, Hirshabelle, and Southwest; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level; Q1-Q4, 2022; 203; 47; 250; Environmental advocacy and campaign; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS MOECC Consultants. Ministry of Humanitarian Affairs and Disaster Management - FGS; 30 May- 2 June 2022; 15; 5; 20; A technical workshop DRM management priorities across sectors in Somalia; Mogadishu, Somalia; FGS DRR Consultants. Ministry of Humanitarian Affairs and Disaster Management – FGS and BRA; Q2 2022; 25; 15; 40; Training on disaster risk reduction (DRR) approaches and principles and early warning services.; Mogadishu, Somalia; FGS DRR Consultants. Ministry of Humanitarian Affairs and Disaster Management – FGS; 4-8 June 2022; 14; 6; 20; First consultation workshop on Building Back Better (BBB); Mogadishu, Somalia; FGS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2022; 91; 64; 155; Validation workshop organized on local DRR plan; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management – FGS & FMS; Q1-Q4, 2022; 127; 64; 191; Gender-focused and Tailor-made DRR training; Mogadishu, Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FGS & FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management – FGS & FMS; Q1-Q4, 2022; 124; 78; 202; Training on DRR Mainstreaming; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FGS & FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2022; 93; 59; 152; Community based EW system; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management – FGS & FMS; Q1-Q4, 2022; 87; 61; 148; Training on End-to-End Early Warning services; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, BRA and Jubaland States; FGS & FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2022; 105; 52; 157; Training on Urban DRR; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, BRA and Jubaland States; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2022; 232; 112; 344; Training on Municipal DRR plan; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2022; 167; 205; 372; Training workshop on Local risks reduction plans (LRRP); Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2022; 224; 310; 534; Consultation workshop on Local Disaster Resilience Fund (LDRF); Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. Ministry of Energy and Water Resources (MOEWR); Public and private sectors, academia, civil society, women and Youth; 8-10 Oct 2023; 44; 14; 58; National IWRM Training Workshop in Mogadishu at Federal and State Institutions.; Mogadishu; MOEWR Consultants. Ministry of Energy and Water Resources (MOEWR); National and FMS institutions; 20-22 March 2023; 17; 3; 20; Geospatial Technology Training workshop at Federal and State Institutions.; Mogadishu; MOEWR Consultants. Ministry of Energy and Water Resources (MOEWR); Public and private sectors, academia, civil society, women and Youth; 14 – 18 May 2023; 48; 20; 68; FMS comprehensive IWRM workshop/training for Senior, staff and at Ministerial level district level in Galmudug State of Somalia.; Galmudug; MOEWR Consultants. Ministry of Energy and Water Resources (MOEWR); Federal and FMS institutions; 21 -22 June 2023; 21; 29; 50; Leadership and Coordination on IWRM; Mogadishu; MOEWR Consultants. Ministry of Energy and Water Resources (MOEWR); Public and Private sectors; 5 July 2023; 126; 44; 170; IWRM MSc Launching and Information sessions; Mogadishu; MOEWR Consultants. Ministry of Environment and Climate Change (MoECC); 20-23, August 2023; 59; 20; 79; Training on sustainable environmental management; Mogadishu; MOECC Consultants. Ministry of Environment and Climate Change (MoECC); 31 August, 2023; 43; 13; 56; Capacity building training for NESAP implementation at FGS and FMS levels.; Mogadishu; MOECC Consultants. Ministry of Environment and Climate Change (MoECC); 26 August, 2023; 20; 10; 30; Basic GIS training; Mogadishu; MOECC Consultants. Ministry of Environment and Climate Change (MoECC); 23-24 August, 2023; 52; 18; 70; Training on environmental monitoring, compliance and enforcement.; Mogadishu; MOECC Consultants. Ministry of Environment and Climate Change (MoECC); 27-29, August 2023; 61; 17; 78; Environmental advocacy and campaign events.; Mogadishu; MOECC Consultants. Ministry of Environment and Climate Change (MoECC); November 12, 2023; 34; 16; 50; Environmental advocacy and campaign events.; Mogadishu; MOECC Consultants. Ministry of Environment and Climate Change (MoECC); August 30, 2023; 38; 17; 55; National Solid Waste Management Policy; Mogadishu; MOECC Consultants. BRA - Deputy district commissioners on social affairs and district youth commissioners.; 34; 6; 40; Technical training on tackling plastic pollution; Mogadishu; BRA Consultant - Abdikhafar Abubakar – Senior Technical Advisor - Disaster Risk Reduction. BRA - Experts and Officials (FGS, Private Sector, Women and Youth Organizations); 21; 9; 30; Stakeholders’ Consultation Workshop to Develop Urban Resilience Roadmap and to Define Disaster Risk Reduction (DRR) Priorities In Mogadishu.; Mogadishu; BRA Consultant - Abdikhafar Abubakar – Senior Technical Advisor - Disaster Risk Reduction. Ministries in Charge of Environment & Climate Change - State level.; Q1-Q4, 2023; 106; 61; 167; Consultations workshop to identify specific Environmental governance, priorities, and actions at the FMS level.; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level.; Q1-Q4, 2023; 62; 37; 99; Workshop on the Implementation of environmental dimensions of SDGs at the FMS.; Somaliland, Puntland, Galmudug, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level.; Q1-Q4, 2023; 62; 49; 111; Training on Geospatial services at the local level.; Puntland, Galmudug, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level.; Q1-Q4, 2023; 48; 53; 101; Workshop on Environmental monitoring, compliance and enforcement.; Somaliland, Puntland, Galmudug, Southwest, and Jubaland States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level.; Q1-Q4, 2023; 50; 40; 90; Environmental Communication and advocacy events at FMS.; Puntland and Galmudug, States; FMS MOECC Consultants. Ministries in Charge of Environment & Climate Change - State level.; Q1-Q4, 2023; 10; 20; 30; Training on Solid waste management in Municipalities.; Puntland, Galmudug, Southwest, and Jubaland States; FMS MOECC Consultants. Somali Disaster Management Agency (SODMA); 11 -13 March, 2023; 17; 15; 32; Training Workshop on DRR Policy documents revisit to reflected institutional changes and renewed commitment and priorities.; Mogadishu; SODMA Consultants. Somali Disaster Management Agency (SODMA); 29 – 31 July 2023; 17; 15; 32; Training Workshop on Gender and Youth Mainstreaming in DRR; Mogadishu; SODMA Consultants. Somali Disaster Management Agency (SODMA); 7 – 9 August, 2023; 16; 7; 23; Training Workshop on Community Early Warning for Disaster Volunteers Network; Beledweyne; SODMA Consultants. Somali Disaster Management Agency (SODMA); 1 – 3 August, 2023; 19; 11; 30; National Consultation Workshop to finalize and validate the revised National Humanitarian Strategy; Mogadishu; SODMA Consultants. Ministries of Humanitarian Affairs and Disaster Management – FMS & NADFOR; Q1-Q4, 2023; 76; 84; 160; Training on Drought Recovery and DRR.; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management – FMS & NADFOR; Q1-Q4, 2023; 91; 77; 168; Community-based EW system.; Somaliland, Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. Ministry of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2023; 151; 129; 280; Capacity training on Early Warning; Puntland; FMS DRR Consultants. Ministry of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2023; 15; 10; 25; Training on setting up the system (Linking and connecting the EW to the dashboard systems); Puntland; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management – FMS & NADFOR; Q1-Q4, 2023; 83; 86; 169; Training on livelihood skills/green recovery for urban youth including IDPs in urban locations.; Somaliland, Puntland, Galmudug, Southwest, and Jubaland States; FMS DRR Consultants. Ministry of Humanitarian Affairs and Disaster Management – SWS & NADFOR; Q1-Q4, 2023; 13; 32; 45; Resilient micro-enterprise development in urban centers.; Somaliland, Southwest; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2023; 111; 51; 162; Consultation workshop on community based resilient recovery guidelines.; Puntland, Galmudug, Hirshabelle, Southwest, and Jubaland States; FMS DRR Consultants. NADFOR; Q1-Q4, 2023; 23; 12; 35; Consultation workshop on the review and amendment of NADFOR establishment act no 35.; Somaliland; NADFOR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2023; 18; 12; 30; Training on DRR mainstreaming into development sectors such as (Education, Water, Health, Livestock); Puntland; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2023; 42; 58; 100; Gender-responsive local DRR schemes.; Jubaland; FMS DRR Consultants. Ministries of Humanitarian Affairs and Disaster Management - FMS; Q1-Q4, 2023; 40; 50; 90; Community mobilization workshop on Community-based DRR schemes.; Galmudug, Hirshabelle,; FMS DRR Consultants. UNDP; Q2, 2023; 20; 17; 37; Youth engagement and awareness on Climate Security; Hargeisa; UNDP. UNDP Ministry of Youth and Sports; Q3 2023; 58; 22; 80; International Peace Day; Mogadishu; UNDP Ministry of Youth and Sports. UNDP; 12 October, 2023; 13; 9; 22; Youth Workshop on Somalia's Climate Commitments and COP28 Preparations; Mogadishu; UNDP Consultant. Ministries of Environment and Climate Change – Federal Member States; 23-24 Nov. 2024; 143; 72; 215; Training on environmental management system to address environmental challenges, including marine pollution, sustainable environmental economic practices and energy needs; Somaliland, Puntland, Galmudug, Hirshabelle, South West and Jubaland States; FMS MOECC National Consultants. Ministries of Environment and Climate Change – Federal Member States; 25 November 2024; 77; 58; 135; Training on environmental quality standards ensuring compliance and monitoring.; Somaliland, Puntland, Galmudug, Hirshabelle, South West and Jubaland States; FMS MOECC National Consultants. Ministries of Environment and Climate Change – Federal Member States; 08th December,2024; 84; 116; 200; Training on environmental advocacy event focusing on climate- security and waste management through youth networks, including district cleaning campaign.; Somaliland, Puntland, Galmudug, Hirshabelle, South West and Jubaland States; FMS MOECC National Consultants. Somali Disaster Management Agency; 8-9 May 2024; 13; 17; 30; Gender- Responsive Disaster Risk Reduction (DRR) workshop to enhance the integration of gender considerations into disaster management.; Mogadishu; SODMA Consultants. Somali Disaster Management Agency; 2-6 June 2024; 13; 17; 30; Training on Disaster Preparedness and Early Warning System for Volunteer’s Network; Mogadishu; SODMA Consultants. Ministries of Humanitarian Affairs and Disaster Management – Federal Member States; 3rd – 6th November 2024; 211; 119; 330; Training on Updating DRR Priorities at the Federal Member State (FMS) Level; Somaliland, Puntland, Galmudug, Hirshabelle, South West and Jubaland States; MOHADM Consultants. Ministries of Humanitarian Affairs and Disaster Management – Federal Member States; 9th – 11th November 2024; 99; 58; 157; Training on Building Back Better for Resilient Recovery at the Community; Somaliland, Puntland, Galmudug, Hirshabelle, South West and Jubaland States; MOHADM Consultants. Ministries of Humanitarian Affairs and Disaster Management – Federal Member States; 13th – 17th November 2024; 149; 88; 237; Training on Early Warning Systems and Community Preparedness; Somaliland, Puntland, Galmudug, Hirshabelle, South West and Jubaland States; MOHADM Consultants. Ministries of Humanitarian Affairs and Disaster Management – Federal Member States; 19th – 21st November 2024; 148; 73; 221; Training on preparing and Updating the Youth Database & Setting Up Youth Volunteer Networks under the Somali Youth Climate Platform (SYCP); Somaliland, Puntland, Galmudug, Hirshabelle, South West and Jubaland States; MOHADM Consultants. Youth Groups; Ministry of Youth and Sports, Ministry of Environment and Climate Change and Private Sectors.; 16th May 2024; 18; 18; 36; Youth Workshop on post COP28 follow-up; Mogadishu; UNDP. Youth groups; Government institutions and private sectors; 21st May 2024; 13; 13; 26; National Youth Consultations on Biodiversity and Blue Economy; Mogadishu; UNDP. Youth groups; Government institutions and private sector; Oct -Nov, 2024; 200; 98; 298; Youth, Peace and Security; Kismayo, Baidoa, Beledweyne, Mogadishu; Ministry of Youth and Sports. Youth groups; Government institutions and private sector; 27th to 28 August 2024; 140; 60; 200; Somalia’s Local Conference of Youth (LCOY); Mogadishu; UNDP. Youth groups; Government institutions and private sector; 15-17 Oct, 2024; 1; 1; 2; Climate, Peace & Security Experts Academy – Youth Iteration Conference; Nairobi; UNDP. Youth groups; Government institutions and private sector; 22 Oct – 11 Nov, 2024; 2; 2; 4; Youth Participation in Conference of Parties (COP29); Baku, Azerbaijan. Youth groups; Government institutions and private sector; 22 Oct -11 Nov, 2024; 1; 1; Youth Participation in the Regional Conference of Youth (RCOY); Rabat, Morocco. Youth groups; Government institutions and private sector; 23 June 2025; 40; 25; 65; Youth consultation workshop on Green Jobs and Entrepreneurship Skills; Mogadishu; UNDP. Youth groups; Government institutions and private sector; 24 and 25 June 2025; 40; 30; 70; Workshop on Climate-smart agriculture and hydroponic technologies for youth-led organizations.; Mogadishu; UNDP. Youth groups; Government institutions and private sector; 29th June 2025; 26; 8; 34; A reflection workshop for young professionals of the Master of Science (MSc) programme in Integrated Water Resources Management (IWRM).; Mogadishu; UNDP. Youth groups; Government institutions and private sector; 30th June 2025; 35; 17; 52; A youth workshop on the post-COP29 follow-up.; Mogadishu; UNDP. Total number of participants; 6400; 3946; 10,346.

Section 7: Human interest story: Voices from the field

My name is Hamza Mohamed Abdiwahab. I am 25. As a climate advocate and youth leader, I am dedicated to placing Somali youth at the heart of diplomacy, climate action, and national development. I serve as the Director of the Somalia Youth Hub under the Federal Government of Somalia, where I connect young people to policy platforms that shape our collective future. My journey began while I was still a student, working with NGOs and exploring the intersections of SDGs, diplomacy, and youth political participation. Over the years, I’ve founded youth initiatives like the Diplomacy Talk Series and Opportunity Hub Africa, and proudly represented Somalia at global forums: from ECOSOC in New York to the UN LDC5 Summit in Doha. I’m also the only youth voice on Somalia’s Climate Pillar for the National Transformation Plan 2024–2029. But my work goes beyond events and speeches. I led consultations for Somalia’s National Action Plan on Youth, Peace and Security. I help shape policy, train youth leaders, and advocate for climate finance that sincludes us. In the future, I want to grow as a strategic leader who bridges gaps: between generations, between policy and practice, and between local voices and international spaces. Hamza Mohamed Abdiwahab is a graduate of the UNDP Climate, Peace & Security Experts Academy and has closely collaborated with UNDP Somalia on youth engagement in peacebuilding and climate policy, including the ongoing process of formulating the Youth, Peace, and Security (YPS) National Action Plan.

Section 8: Looking ahead: Focus on the future

The Sida/UNDP-supported project has successfully established an effective partnership with the key institutions mandated to drive resilience action at national, local, and community levels. These partnerships—spanning government ministries, municipal authorities, academia, women and youth-led networks—have created a strong platform for coordinated climate adaptation, environmental governance, and disaster risk reduction. Building on this collaboration and in line with the recommendations of the mid-term review, there is an urgent need to formulate and design the next phase of the programme. To avoid losing the momentum achieved, UNDP is keen to explore opportunities to partner with Sida and other like-minded donors to initiate the design process as soon as possible. The next phase will consolidate and expand on the solid institutional, community, and policy foundations laid by this project, driving Somalia’s transition toward climate-resilient, peace-positive, and inclusive development. Building on strengthened national frameworks for IWRM, environmental governance, DRR, and youth-led climate action, the focus will shift from establishing systems to deepening their operational reach, ensuring that benefits are tangible, nationwide, and sustainable. A priority will be to strengthen Somalia’s nationwide disaster volunteer network, transforming it into a coordinated, well-trained, and gender-balanced force embedded in local governance structures. Linked with the operational hubs and early warning systems envisioned under the National Transformation Plan, these networks will serve as the backbone for community preparedness, rapid response, and recovery. This will go hand in hand with expanding end-to-end, people-centred early warning systems—integrated with the EW4ALL initiative—to ensure hazard information is accurate, accessible, and acted upon at all levels. Peace-positive adaptation will be embedded in all resilience programming, using environmental restoration, water governance, and DRR planning as entry points for dialogue, cooperation, and conflict-sensitive resource management. This approach will be especially critical in fragile regions, where climate stressors often intersect with local tensions. Youth empowerment will remain central, with the Somalia Youth Climate Platform evolving into a hub for green innovation, entrepreneurship, and policy advocacy. By linking young climate leaders with green economy value chains—such as renewable energy, sustainable agriculture, and circular waste management—the next phase will promote both environmental solutions and economic resilience. Institutional capacity building will extend beyond technical skills to include disaster and recovery financing. This will involve operationalizing Somalia’s National Disaster Management Fund, developing multi-hazard risk transfer mechanisms, and strengthening the financial literacy of DRR institutions to mobilize and manage both domestic and international resources. Finally, future investments will be guided by integrated, data-driven decision-making. Strengthened geospatial and environmental data systems will underpin anticipatory action, adaptive management, and transparent reporting against the SDGs, Sendai Framework, and NDC commitments. By pursuing these priorities, Somalia will be better equipped to withstand recurrent shocks, manage scarce natural resources equitably, and unlock the potential of its youth to lead in climate adaptation and green growth. The next phase will not only protect lives and livelihoods but also contribute to the long-term stability, prosperity, and dignity of communities across the country.