UNDSDCF Outcome: UNDAF/CPD, RPD or GPD

CPD Outcome: Output 4.1: Innovative and sustainable climate change adaptation and mitigation initiatives designed and implemented

UNDP Strategic Plan Outcome:

Total budget: EUR 4,150,000

Annual Budget: USD 842,533

Unfunded amount:

Donors: EU

IP:

RP:

Project Title: Supporting an inclusive transition to a “green” economy in the Agri-food

sector and development of a “climate-smart” Uzbek Agriculture Knowledge and Innovation

System (UAKIS)

Project Number: 00122914

Output Number:

Implementing Partner: UNDP

Start Date:		01.10.2021

End Date: 		30.09.2025

# Indicator Monitoring

| Indicator (Insert indicators from Prodoc RRF) | Baseline | Annual Target (as per AWP) | Previously Reported Value | Actual Value (for the reporting period) | Data Source | Output Achievement Progress (Provide brief narrative on output achievement progress) |
| --- | --- | --- | --- | --- | --- | --- |
| Output Indicator 1.1: Assessment of policy and regulatory barriers to scaled-up climate action and “green” transition | 0 | 1 | 0 | 1 | Action/Project reports, government reports | Supported policy dialogues and development of plans and regulatory framework at national and regional level for the alignment of agricultural policies and programmes to respond to climate change. |
| Output Indicator 1.2: Number of knowledge products elaborated per priority area, their status and availability | 0 | At least 20 | 19 | 30+1 CREA | Action/Project reports, government reports | Target exceeded; over 30 products developed, including technical briefs, policy papers, and CREA-supported outputs, widely disseminated to stakeholders. |
| Output Indicator 1.3: Number of policy makers informed by the Action about new knowledge products (O2.3) | 0 | At least 120 | 156 | 306 | Action/Project reports, Local surveys | More than doubled target; outreach achieved via dialogues, workshops, dissemination events. |
| Output Indicator 1.4: Number of professional staff and researchers trained (O3.1) | 0 | At least 100 | 229 | 249 | Project reports | Trainings exceeded target, covering climate-smart agriculture, digital tools, and innovation system strengthening. |
| Output Indicator 1.5: Number of professional organizations strengthened with research and training interventions (O3.2) | 0 | At least 10 | 18 | 18 | Training results | 18 organizations supported; capacity enhanced for research, advisory, and extension. |
| Output Indicator 1.6: Number of EU research organizations mobilized by the action (O4.1) | 0 | At least 3 | 13 | 13 | Cooperation agreements, Project reports | Target surpassed; strong partnerships with 13 EU institutions. |
| Output Indicator 1.7: Number of subject specific, evidence-based policy briefs prepared and supported to policy address constraints to the uptake of new innovations. | 0 | At least 5 | 5 | 5 | Action/Project reports | Achieved as planned; briefs informed policies on innovation, gender, and energy access. |
| Output Indicator 2.1: Number of new Agri-food Innovation Groups and Partnerships (operational groups) established with the project support | 0 | At least 12 | 18 | 18 | Government & Project reports | 18 IGs established and functional; piloting climate-smart solutions across regions. |
| Output Indicator 2.2: Number of food and agriculture value chains supported by the project on climate resilience and emission reduction | 0 | At least 20 | 17 | 23 | CCI, khokimiyats, Project reports | Target nearly met; 23 value chains improved in resilience and low-carbon practices. |
| Output Indicator 2.3: Agricultural/pastoral ecosystems with climate-relevant practices introduced (ha) | 0 | At least 200 | 193 | 285 | Local authorities, Project reports | Exceeded target; 285 ha under sustainable land management. |
| Output Indicator 2.4: Number of small-scale farmers adopting sustainable practices | 0 | At least 40 | 41 | 41 | Council of Farmers, Project reports | Target achieved; adoption includes women and youth-led groups. |
| Output Indicator 2.5: Number of smallholder farmers reached by R&D initiatives | 0 | At least 400 | 981 | 1004 | National & Council of Farmers reports | More than doubled target; over 1,000 farmers engaged with innovations and training. |

# Key Monitoring Activities

| Monitoring Activity (from M&E Plan) | Actual Date | Participants | Key Observations | Follow-Up Actions |
| --- | --- | --- | --- | --- |
| Monitoring Visits | April–July 2025 | UNDP, FAO, Ministry of Agriculture, Local authorities, Farmers | Farmers actively engaged; drip irrigation pilots improved water use efficiency; need for stronger IG–private sector linkages. | Strengthen private sector participation; organize additional farmer training on financial literacy. |
| Project Board Meeting | June 2025 | UNDP, EU Delegation, Ministry of Agriculture, Project partners | Strong national ownership; stakeholders requested scaling to other provinces. | Develop roadmap for replication of Innovation Group model at national level. |
| Audit | August 2025 | Independent auditors, UNDP Finance, Implementing Partner | No major irregularities; recommendation to improve procurement documentation. | Action plan prepared and procurement processes strengthened. |
| Evaluation | September 2025 (Final Evaluation) | Independent evaluators, UNDP, EU Delegation, Ministry of Agriculture, IG representatives | Project rated highly relevant, efficient, impactful; sustainability risks noted (financing, institutional anchoring). | Exit strategy developed; recommendations integrated into government’s agricultural innovation agenda. |

- Risk Log

Update Risk and Issue log

| Description | Date identified | Impact /Priority | Ountermeasure /MNGT Response | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| Limited farmer uptake of innovations due to financial constraints | 2024 | High | Introduced cost-sharing models; established demonstration plots to reduce risk for farmers | Implementing Partner (UNDP) | Mitigated |
| Institutional fragmentation between ministries slowing policy adoption | 2024 | Medium | Regular policy dialogues and establishment of inter-agency working groups | Ministry of Agriculture / UNDP | Ongoing |
| Climate variability affecting pilot results (drought, water shortages) | 2025 | High | Promoted climate-resilient crop varieties; scaled drip irrigation and efficient water management | Innovation Groups, Farmers | Under monitoring |
| Risk of insufficient financing to sustain Innovation Groups post-project | 2025 | High | Developed exit strategy; engaged with government and private sector for continued support | Ministry of Agriculture, EU Delegation | Partially mitigated |
| Weak private sector engagement in IG activities | 2025 | Medium | Facilitated business dialogues; linked farmers to input suppliers and processors | UNDP, Project Partners | Improving |

# Challenges/Issues  towards achieving results and actions taken

| Description | Impact | Actions Taken | Current Status |
| --- | --- | --- | --- |
| Delayed disbursement of funds in early 2025 | Slowed initial implementation of field activities | Adjusted work plan and intensified implementation mid-year | Resolved |
| Farmers hesitant to adopt new practices due to financial risks and lack of trust | Risk of low uptake of innovations | Established demonstration plots, farmer field schools, and peer-to-peer learning | Adoption improved; >40 farmers adopted practices |
| Weak private sector linkages in Innovation Groups | Limited commercialization of innovations | Facilitated dialogues with agri-input suppliers and processors; promoted IG–business partnerships | Improving |
| Sustainability concerns for Innovation Groups post-project | Risk of collapse without continued funding | Developed exit strategy, engaged government and private sector for long-term financing | Partially addressed; integration ongoing |

# Conclusions and Way Forward

- The EU-AGRIN project successfully achieved and, in several areas, exceeded its planned results. The establishment of 18 functional Innovation Groups, development of more than 30 knowledge products, and engagement of over 1,000 farmers demonstrate the project’s strong contribution to advancing climate-smart, innovation-driven agriculture in Uzbekistan. The project has proven effective in strengthening linkages between farmers, researchers, policymakers, and the private sector. It has also generated tangible policy inputs, supported institutional reforms, and enhanced the capacity of professional organizations and research institutions.

The project’s relevance and impact have been validated by the final evaluation, which recognized its role in piloting sustainable agricultural practices, influencing national strategies, and building capacity for innovation at multiple levels. However, sustainability challenges remain, particularly in securing long-term financing and institutional anchoring for the Innovation Group model.

Way Forward:
1. Institutionalization: Mainstream the Innovation Group (IG) model into the national agricultural extension and advisory system.
2. Scaling Up: Replicate successful practices and pilots beyond the three project regions, prioritizing climate-vulnerable areas.
3. Sustainability: Mobilize financing from public, private, and donor sources to sustain IG activities.
4. Climate Resilience: Further integrate climate adaptation and mitigation into agricultural strategies.
5. Knowledge Sharing: Expand dissemination of knowledge products at national and regional levels.
6. Capacity Building: Continue training with emphasis on digitalization, financial literacy, and gender inclusion.

The EU-AGRIN experience has demonstrated that innovation can be effectively driven from the ground up. Building on this momentum, Uzbekistan has the opportunity to consolidate gains, institutionalize systems, and become a regional leader in sustainable, climate-resilient, and innovation-led agriculture.

This narrative part of this section should focus on results backed by evidence of achievements.  It should make forceful arguments regarding the transformational change achieved, using quantitative and qualitative indicators.  It must include a review and assessment of the intended project outputs and output targets in accordance with the Annual Work Plan (AWP).  This section should also indicate any progress and achievements against the outcomes, outputs and indicators linked to of the Country Programme Document (CPD), UNDP Strategic Plan and Integrated Results and Resources Framework (IRRF).  Gender aspects should be incorporated in this section as well.

This section identifies and analyses project risks and issues that:

1) had an impact on project deliverables (quality, schedule, etc.) during the reporting period, or

2) were newly identified during the reporting period and are being addressed by the project (in the case of risks, “addressed” means to mitigate their effects or decrease the likelihood of impact, and in the case of issues, how to resolve them).