This project is funded by

the European Union

EU-AGRIN

Supporting an inclusive transition to a “green” economy in the Agri-food sector and development of a “climate-smart” Uzbek Agriculture Knowledge and Innovation System (UAKIS)

IMPLEMENTED BY UNDP

FINAL REPORT

October 2021 – September 2025

| Project Title: | Supporting an inclusive transition to a “green” economy in the Agri-food sector and development of a “climate-smart” Uzbek Agriculture Knowledge and Innovation System (UAKIS) |
| --- | --- |
| Contract Number: |  |
| Project Value: | EUR 4,150,000 |
| Starting Date: | 1 November 2021 |
| End Date: | 30 September 2025 |
| Duration: | 48 Months |
| Implementing agency Project Manager: Address: Telephone: e-mail: Project Office Address: Project Team Leader: Telephone: e-mail: |  |
|  | Annual Progress Report |
| Reporting period: | 01.10.2021 – 30.09.2025 |
| Report elaborated by: |  |
| Draft Interim Progress report submitted on: |  |

CONTENT

1.	GLOSSARY OF TERMS	5

2.	EXECUTIVE SUMMARY	6

3.	TECHNICAL PROGRESS IN THE REPORTING PERIOD	8

3.1	Output I: Establish Agri-food Innovation Support and Brokerage Services	8

Activity 1.1. Support and facilitate improvements in the policy and regulatory framework for effective implementation of the agri-food innovation support and brokerage services and for scaled-up climate action in the agri-food sector	8

Activity 1.2 Building institutional capacity and partnerships among UAKIS stakeholders to effectively deliver Agri-food Innovation Support and Brokerage Services	10

Activity 1.3 Participatory planning and identification of project portfolios	14

Activity 1.4 Establishing continuous feedback, learning and knowledge management system under UAKIS	15

3.2	Output II: Agri-food Innovation Groups and Partnerships	17

Activity 2.1	Establishing the Agri-food Innovation Groups and soliciting innovative proposals on climate-smart agriculture and transition to “green” agri-food value chains	17

Activity 2.2	Delivery of training, capacity building and technical advice to the members and partners of the Agri-food Innovation Operational Groups	19

Activity 2.3	Delivering targeted financial support and investments for innovative projects with climate change mitigation and adaptation benefits	21

Activity 2.4: Innovation Networking and Exchange Program	22

3.3	Project Board (Steering committee) meetings	24

3.4	Anticipated Problems, Planned Remedial Actions and Lessons Learned from Encountered Problems	24

4.	NEXT STEPS, SCALING-UP	26

4.1	Next Steps and Scaling Up: Building a Future-Ready Agri-Food System	26

5.	RISK MATRIX UPDATED	34

PROJECT WORK PLAN	36

6.	ANNEXES	37

GLOSSARY OF TERMS

| AKIS AAS | Agriculture Knowledge and Innovation System Agriculture Advisory Services |
| --- | --- |
| CREA | Consiglio per la Ricerca in Agricoltura e l'analisi dell'economia Agrarian Italy’s Council for Agricultural Research and Economics) |
| EU | European Union |
| EIP | European Innovation Partnership |
| IG | Innovation Group |
| GIZ | German International Cooperation Agency |
| MoA | Ministry of Agriculture |
| MoI | Ministry of Innovation |
| MoF | Ministry of Finance |
| ToT | Training of Trainers |
| TVET | Technical and Vocational Education and Training |
| UAKIS | Uzbekistan Agriculture Knowledge and Innovation System |
| WUR | Wageningen University and Research |

EXECUTIVE SUMMARY

The EU-AGRIN project, a flagship initiative of the UNDP Uzbekistan supported by EU, has successfully completed a transformative multi-year journey (2021–2024) to catalyze innovation, resilience, and sustainable growth across Uzbekistan’s agri-food sector. Guided by the principles of climate adaptation, knowledge-based development, and inclusive growth, EU-AGRIN has laid the foundations of a national innovation ecosystem—empowering researchers, farmers, entrepreneurs, and institutions to cooperate and co-create solutions for a green, climate-resilient future.

Over the four years, the project delivered remarkable breakthroughs across four interconnected pillars: participatory planning, innovation acceleration, capacity building, and knowledge networking. With deep engagement across Tashkent, Fergana, and Kashkadarya regions, EU-AGRIN has not only delivered on its objectives but also planted the seeds of a long-term transformation in Uzbekistan’s agricultural landscape.

Key achievements

- Innovation Groups (IGs): In a groundbreaking process, 18 Innovation Groups (innovation-based projects) were established through a transparent, two-phase selection mechanism involving over 200 applications. These IGs, composed of researchers, farmers, educational institutions, and private actors, implemented pilot projects addressing climate-smart agriculture, water efficiency, sustainable crop production, alternative energy use, and aquaculture.

- Demonstrable Impact on Climate Resilience: From solar-powered drip irrigation systems reducing energy and water use by 55% to climate-adapted plant varieties enhancing yield and reducing greenhouse gas emissions, IGs produced measurable results that directly address Uzbekistan’s climate vulnerabilities. Practices such as bioremediation, rotational grazing, and water recycling in aquaculture are now validated models for replication.

- Capacity Building and Technical Empowerment: More than 500 participants—including researchers, AKIS advisors, and farmers—benefited from intensive technical training, proposal development workshops, and practical modules delivered by the project key partner CREA (Italy’s premier agri-research institute). These programs aligned Uzbekistan’s research community with EU Horizon Europe standards, strengthening its integration into global research and funding frameworks.

- Youth and Gender Inclusion: Targeted initiatives such as the Women Students Innovation Challenge and the transformation of the Zangiota TVET center into an Innovation Lab have empowered women and youth to lead innovation in agriculture. Facilities were upgraded to serve as learning and demonstration spaces, bridging education with real-world application.

- Innovation Labs: A strategic innovation in 2024, the concept of Innovation Labs—a network of demonstration farms modeled on European best practices—was launched to institutionalize ongoing experimentation, peer learning, and technology transfer. These labs will serve as regional hubs for climate-smart agricultural practices and knowledge dissemination.

- Strategic Networking and International Exchange: Through study tours, on-site visits, and expert exchanges with the EU, Uzbekistan’s researchers and practitioners gained first-hand insights into EIP-AGRI and other European innovation mechanisms, creating pathways for ongoing international collaboration.

- Inclusive Grant Mechanism: A tailored financial support system, backed by clear guidelines and criteria, facilitated targeted investments in climate-resilient agricultural innovations. Over USD 755,000 in Low-Value Grants were distributed through IGs, reinforcing both equity and innovation.

- Policy Development and Institutional Recognition: A major policy breakthrough was achieved with the issuance of a Presidential Decree, formally endorsing the Innovation Partnership model and recognizing Innovation Groups as key instruments of agricultural modernization in Uzbekistan. This legislative act paves the way for long-term institutionalization and integration of the project’s approaches into national policy frameworks.

- Recognition and Awards: In 2023, the EU-AGRIN project was formally recognized as the Best UNDP Project in Uzbekistan, a testament to its innovation, inclusive design, and transformational impact across the agricultural sector.

A Foundation for the Future

The EU-AGRIN project has not merely introduced new tools or practices; it has cultivated a culture of innovation, built new institutional capacities, and inspired a new generation of agricultural thinkers and doers in Uzbekistan. The results are visible—in the fields where farmers now use less water and produce more, in laboratories where research aligns with global standards, and in classrooms where young people see agriculture as a career of purpose and promise.

As Uzbekistan continues to modernize its agriculture, EU-AGRIN leaves behind not only success stories but also a replicable model for innovation-driven rural development. The established networks, enhanced capacities, and demonstrated solutions provide a solid platform for future investments, national scaling, and international partnerships.

This report stands as a testament to what is possible when vision meets action, when local ingenuity is paired with global knowledge, and when inclusive partnerships pave the way for sustainable progress.

TECHNICAL PROGRESS IN THE REPORTING PERIOD

## Output I: Establish Agri-food Innovation Support and Brokerage Services

Activity 1.1. Support and facilitate improvements in the policy and regulatory framework for effective implementation of the agri-food innovation support and brokerage services and for scaled-up climate action in the agri-food sector

Under this activity the EU-AGRIN project has laid the groundwork for a more enabling policy environment in Uzbekistan’s agri-food sector by addressing systemic regulatory bottlenecks and introducing evidence-based policy tools to accelerate innovation and climate action. This work supports the operationalization of the Uzbekistan Agriculture Knowledge and Innovation System (UAKIS).

In 2022, the project initiated three pivotal studies to inform regulatory strengthening and policy development. A key initiative was the “Evidence-Based Study of the Policy and Regulatory Barriers for Innovation in Climate Action and Green Transition”, launched on 19 August 2022, aimed at identifying legal and institutional obstacles obstructing the development of innovative and climate-smart agricultural practices. The study was designed to support the Ministry of Agriculture (MoA) and other stakeholders in establishing a realistic and sustainable policy framework aligned with Uzbekistan’s green economy ambitions.

To complement this analysis, a Baseline Survey on Production Systems in Tashkent and Fergana regions was implemented as a comprehensive overview of agricultural production, transportation, storage, and marketing systems, as well as the profitability and feasibility of various subsectors including beekeeping, fish farming, animal husbandry, and sericulture. Importantly, it evaluated both quantitative and qualitative indicators, offering insights into financial, institutional, and socio-economic aspects of local production systems.

Simultaneously, a Capacity Needs Assessment of regional and sub-regional research organizations and agricultural colleges was conducted. This assessment provided an overview of institutional readiness to participate in innovation-driven activities, helping to identify tailored capacity development needs. The final drafts of all three studies were completed by the end of 2022, bringing a set of key baseline data about the project regions.

Progressing into 2023, policy and regulatory advancement took a significant leap with the issuing of the Presidential Decree No. PQ-225 dated 17 July 2023: “On Additional Measures to Improve Quality and Efficiency by Integrating Science, Education, and Production in the Agricultural Sector”. This landmark decree formalized and opened for scaling the Innovation Group (IG) mechanism developed under EU-AGRIN, integrating it into Uzbekistan’s national agricultural policy framework. It provided a legal and financial foundation for supporting and replicating the IG approach across the Republic, reinforcing the relevance of project-led principles such as bottom-up innovation, cross-sector partnerships, and demand-driven research.

In parallel, the project deepened its focus on gender-responsive policy development. A Gender Analysis Study, followed by a policy brief, identified barriers to women’s participation in climate-smart agriculture and proposed actionable recommendations for policy and programming. These findings were disseminated through targeted training sessions held in October and November 2023 across Tashkent, Fergana, and Kashkadarya, reaching 109 women farmers. The project also produced two knowledge products: “Barriers and Opportunities for Gender-Responsive Climate-Smart Agriculture Adoption in Uzbekistan” and “International Best Practices in Integrating Gender Equality and Women’s Empowerment in Climate-Smart Agriculture Programs”.

To further support policy development, preparatory work was launched in late 2023 for a new analytical activity focusing on key innovation bottlenecks. Through a series of policy dialogue workshops, co-organized with consultancy Civitta in Tashkent, Fergana, and Karshi, stakeholders explored three thematic areas:

- (a) Intellectual Property Rights (IPR) related to seed varieties and agri-technologies,

- (b) Access to Energy Markets for agri-food enterprises, and

- (c) Regulatory and Financial Incentives for Climate-Smart Agriculture.

These consultations enabled the development of a Policy Brief, finalized and disseminated in October 2024, with contributions from 41 national stakeholders representing government, academia, and the private sector. The brief presents a package of actionable policy recommendations, aligned with Uzbekistan’s climate and innovation goals.

In the area of Intellectual Property Rights, the brief proposes streamlining procedures for seed registration and patenting, establishing Regional Seed Production Centers, and introducing a National Seed Strategy. For improvement of the energy access, it advocates for the expansion of solar PV and biogas infrastructure, donor-supported clean energy investments, and financial incentives for agri-businesses adopting renewable technologies.

To accelerate the uptake of climate-smart agriculture, the brief recommends establishing a real-time agri-food supply monitoring system, increasing funding for climate-resilient technologies (e.g., drip irrigation, drought-tolerant crops), and enhancing export capacity through tailored VAT and subsidy mechanisms. It also highlights the importance of advisory services delivered through UAKIS to guide farmers in adopting sustainable practices.

A complementary achievement in 2024 was the Review of the Agrarian University Curricula conducted at the Tashkent State Agrarian University (TSAU). This effort, supported by a European academic expert, led to a detailed report and policy brief identifying strategic entry points for curricular reform. Recommendations focus on integrating climate change adaptation, renewable energy, biotechnology, and sustainable value chains into teaching programs, supported by faculty training, upgraded infrastructure, and stronger public-private collaboration.

Altogether, the EU-AGRIN project’s work under Activity 1.1 represents evidence-based response to Uzbekistan’s evolving agri-food policy needs. By interlinking legislative reform, institutional capacity building, gender responsiveness, and academic modernization, the project has fostered a robust enabling environment for inclusive, climate-resilient, and innovation-driven agricultural transformation.

Activity 1.2 Building institutional capacity and partnerships among UAKIS stakeholders to effectively deliver Agri-food Innovation Support and Brokerage Services

Starting in 2022, significant efforts were invested in raising awareness and preparing diverse stakeholders—research institutions, public and private advisory services, farmers, and entrepreneurs—for active participation in the innovation ecosystem. Multiple workshops and meetings were organized across Uzbekistan, engaging the Agriculture Knowledge and Innovation System (AKIS) centers and a broad network of agricultural actors.

Initial workshops took place in Tashkent and Fergana, where the EU-AGRIN project team, alongside international expert D. Kahan, introduced the core concepts of innovation support mechanisms, including the formation of Innovation Groups (IGs), the use of Support and Brokerage Services, and the development of project proposals. These sessions also highlighted the role of advisory services, regulatory reform, and climate-adaptive innovations tailored to smallholder and family farms.

In Fergana, a series of visits between May and July included institutions such as the Fergana Experimental Station of the Research Institute of Cereals and Legumes, Besharik vocational college, and the Fergana regional AKIS center. Discussions centered on linking research to practice, establishing Innovation Groups, and integrating technical vocational education (TVET) colleges to support innovation and demonstration trials.

Similar outreach was conducted in Jizzakh, Kashkadarya, and Samarkand, with cooperation from local branches of institutes like the Research Institute of Agriculture, the Research Institute of Vegetable-Melon Crops and Potato, and the Research Institute of Horticulture, Viniculture, and Wine-making named after Mahmud Mirzaev. These visits led to practical discussions on climate-smart farming, innovation diffusion, training needs, and cross-institutional collaboration.

Training seminars specifically designed for women farmers were held in collaboration with the Association "Women of the Agrarian Sphere", with a strong focus on milk hygiene, cooperative milk collection, food safety, and adaptation to climate-induced challenges in livestock production. This work culminated in the establishment of a women-led model for milk value chain development in the Ohangaron district.

In June 2022, the II National Agricultural and Food Research Forum was held in Tashkent, in cooperation with FAO and the EU ASK Facility project. It focused on three thematic areas: food security and nutrition, sustainable land and water management, and agri-food value chains. The forum brought together 174 participants in-person and 23 online, initiating the design of the National Agriculture and Food Research Program (NARP) and establishing a strategic framework for Uzbekistan’s long-term innovation agenda.

As part of infrastructure support, specialized laboratory and processing equipment was procured for various institutions, including the Research Institute for Livestock, State Committee of Veterinary and Livestock Development, and the Southern Agricultural Research Institute. Items such as milk coolers, ELISA analyzers, and pasta production lines were intended to foster applied research and improve links between science and production.

The momentum continued into 2023, with 47 training events reaching 1118 participants, including 87 members of Innovation Groups, 117 researchers, and a significant number of women and youth. The training program emphasized climate-resilient technologies, transitioning to green agriculture, and promoting inclusive innovation.

One of the highlights of 2023 was the International Forum on Women in Agriculture, held in Tashkent, focusing on gender equality, digital agriculture, and entrepreneurial success stories. This event strengthened women’s representation in innovation, policymaking, and agricultural leadership.

In 2024, a total of 60 capacity-building events reached 2,364 participants, with notable collaboration from institutes like the Scientific Research Institute of Irrigation and Water Problems, Research Institute of Plant Genetic Resources, and the Italian research network CREA. Topics ranged from crop breeding, agricultural technology, and water management, to gender inclusion.

The launch of the Tailored Capacity Building Programme for Service Providers in partnership with Civitta marked a major step forward in empowering AKIS advisors, TVET colleges, NGOs, and private entities. A comprehensive Needs Assessment was conducted across Tashkent, Fergana, and Kashkadarya to define training modules on climate-smart agriculture, renewable energy, gender-sensitive services, and financial and regulatory advisory skills.

Substantial equipment support continued in 2024, with laboratory tools allocated to the Scientific Research Institute of Plant Protection and Quarantine, Research Institute of Vegetable Crops, and the AKIS Services Center in Fergana, among others. Tools ranged from electrophoresis systems to drip irrigation kits, all strategically selected to enhance innovation group activities and regional research capacity.

The year 2025 opened with several key developments. In January, seven outstanding students from Karakalpakstan’s Nukus branch of Samarkand State University of Veterinary Medicine, Animal Husbandry, and Biotechnologywere awarded a study tour to Germany. Their eco-friendly innovation—biodegradable plant pots—won them access to Green Week Berlin, visits to the Leibniz Institute of Vegetable and Ornamental Crops (IGZ), and the Research Institute of Farm Animal Biology (FBN). There, they gained deep insight into precision farming, sustainable livestock management, and climate-resilient horticultural systems, returning inspired to lead local innovation.

In June 2025, a high-level delegation from the Ministry of Agriculture and partner institutions visited Italy. This study tour focused on smart farming, water-saving technologies, and crop resilience strategies, with discusions held with leading Italian agribusinesses and research centers. The exchange further strengthened cross-border innovation ties and adaptation of EU best practices.

In July 2025, the first district-level Youth HUB was launched at the Zangiota Agrotechnological College, serving as a platform for practical skills development, digital innovation, and youth-led agribusiness incubation. Equipped with co-working spaces, digital tools, and mentorship programs, the HUB aims to cultivate the next generation of agripreneurs and bridge the gap between education and practice.

Together, these efforts reflect a progressive and inclusive approach to building institutional capacity, fostering partnerships, and supporting Uzbekistan’s transition toward a resilient and innovative agri-food system.

Activity 1.3 Participatory planning and identification of project portfolios

The establishment of a sustainable and cyclical system for identifying and updating portfolios of agri-food innovation projects lies at the heart of Activity 1.3. This strategic approach ensures that innovations supported through the EU-AGRIN project are continually aligned with agricultural, environmental, and market priorities in Uzbekistan. From the outset, the focus was on mobilizing key stakeholders—research institutions, advisory service providers, educational institutions, and farmer organizations—through participatory planning processes, trainings, and technical consultations.

Initial capacity-building steps were taken in 2022 through a series of targeted training workshops aimed at strengthening institutional readiness for project development and portfolio planning. A key event was held on 19–20 August 2022, involving employees of regional research institutes and experimental stations from Fergana, Kashkadarya, and Tashkent. Organized in cooperation with the National Center for Agricultural Knowledge and Innovation, the sessions addressed core administrative competencies such as drafting project proposals and integrating international standards into food production systems. The discussions expanded into critical areas such as satellite-based land monitoring, climate adaptation, and enhancing the role of cooperative service providers, particularly youth and women, across agri-food value chains.

Another cornerstone event was the training conducted on 13 July 2022 in Tashkent, supported by international expert David Kahan. This session focused on the conceptual development of Innovation Groups (IGs) as a vehicle for identifying and resolving production-level challenges through collaborative research. Mr. Kahan underscored the need for agricultural enterprises to be managed as businesses and highlighted the critical role of partnerships with the private sector. His emphasis on innovation specialists—professionals capable of connecting research outputs with practical applications—set the tone for future IG planning and formation.

Further reinforcing the participatory dimension of project planning, a technical inception workshop took place on 14 July 2022. During this session, the EU-AGRIN team presented the first annual work plan of the project. This event served as a vital consultation forum, incorporating insights from earlier meetings with national and international partners. Representatives from ministries, international organizations, regional AKIS centers, research institutions, and vocational education providers contributed to refining the implementation strategy.

Collectively, these foundational events laid the groundwork for developing a dynamic and inclusive system for selecting innovation projects.

Activity 1.4 Establishing continuous feedback, learning and knowledge management system under UAKIS

The EU-AGRIN project placed strong emphasis on the creation of an evidence-based, responsive monitoring and knowledge management system to support effective decision-making and investment planning in Uzbekistan’s agricultural sector. Recognizing the transformative potential of digital tools and real-time data, this activity focused on adopting a culture of continuous learning, adaptive project management, and strategic knowledge sharing within the national Agriculture Knowledge and Innovation System (UAKIS).

Initial groundwork was laid in 2022, with the identification and piloting of the EOS Crop Monitoring System, a satellite-based application used globally to assess crop health, forecast plant diseases, and analyze soil conditions through multispectral imaging. The platform, which is accessible via PC and mobile devices, was introduced to Agricultural Advisory Services staff in Fergana, where advisors welcomed the potential to integrate real-time monitoring into their routine fieldwork. Plans were formulated for broader training and field testing among advisors, farmers, and agronomists to inform precision agriculture and tailored interventions.

By 2023, the project expanded its efforts through the development of practical training materials and a comprehensive M&E toolkit to support the 18 Innovation Groups (IGs). Regional M&E specialists were deployed across Tashkent, Fergana, and Kashkadarya, maintaining close communication with the IGs and submitting regular reports to guide adaptive management. Additionally, a dedicated Monitoring and Evaluation (M&E) expert was engaged, with a focus on data integration, and performance tracking.

This integrated platform enabled real-time tracking of IG activities, consolidated weekly reports, and generated visual dashboards to support evidence-based decision-making. Simultaneously, the system enhanced transparency, accelerated learning, and enabled the efficient delivery of advisory and technical support to stakeholders.

As a final activity, a long-term M&E framework for UAKIS has been finalized and proposed in 2025 with participation of the project partner CREA. This new system, led by the Ministry of Agriculture, will incorporate a context-specific set of indicators based on European best practices and stakeholder consultations. Workshops involving AKIS Centers, MoA staff, and other partners were organized to align monitoring criteria with local realities and strategic priorities. The resulting framework is intended to serve as a national tool for assessing innovation outcomes, guiding policy, and enabling responsive governance in agriculture.

During ECO EXPO 2024, the UNDP Uzbekistan stand showcased green technologies and digital tools from EU-AGRIN, attracting over 5,000 visitors. Two Innovation Groups were prominently featured: one in Kashkadarya presenting climate-resilient durum wheat cultivation, and another in Ferghana highlighting gains in cotton productivity through improved soil and irrigation practices. These demonstrations reinforced the value of applied research, peer learning, and sustainable solutions.

To enhance visibility and encourage cross-sectoral learning, the  EU-AGRIN project leveraged communication platforms and public engagement events throughout 2025. At the UNDP Talks, a dedicated new format that gives beneficiaries floor to speak about UNDP support, two project beneficiaries shared powerful stories—one from a dairy farm in Ohangaran, which improved production and inclusiveness through renewed milk systems and youth involvement; and another from Akkurgan, where a drip irrigation system significantly boosted efficiency and yield. These cases demonstrated how tailored support and innovation can improve productivity, sustainability, and community development.

Lastly, the release of

a beneficiary success video—which reached over 32,000 views—marked a major milestone in public engagement, illustrating the power of storytelling and multimedia outreach in adoption of best practices. This communication success has amplified project visibility and inspired broader uptake of climate-smart, inclusive agricultural innovation.

Together, these achievements under Activity 1.4 reflect the EU-AGRIN project’s commitment to dynamic knowledge systems, long-term institutional capacity building and constant sharing of experience and knowledge, set the foundation for a more resilient, data-driven, and inclusive agricultural future in Uzbekistan.

## Output II: Agri-food Innovation Groups and Partnerships

Activity 2.1	Establishing the Agri-food Innovation Groups and soliciting innovative proposals on climate-smart agriculture and transition to “green” agri-food value chains

To catalyze climate-smart agricultural practices and promote a transition to sustainable agri-food value chains, the EU-AGRIN project focused on the establishment of Agri-food Innovation Groups (IGs) – dedicated innovation testing projects - across Tashkent, Fergana, and Kashkadarya regions. These groups/projects were imagined as collaborative platforms bringing together research institutes, educational institutions, farmers, and private sector actors to co-create and implement innovative agricultural solutions tailored to local climatic and environmental conditions.

The initial phase, launched in 2022, involved a strategic process of partner identification in the three target regions. Meetings were held with institutions such as the Research Institute of Agrotechnologies of Cotton Growing, Research Institute of Horticulture, Viticulture and Winemaking, and AKIS Agricultural Services Centers, among others.

In parallel, the EU-AGRIN team developed a public call mechanism in coordination with the Ministry of Agriculture (MoA) and approved by the UNDP Deputy Resident Representative, ensuring a transparent selection process. The two-phase application system prioritized proposals based on their collaborative structure, innovation potential, and involvement of agricultural advisors. A wide communication campaign across digital platforms resulted in over 200 submissions, of which 18 Innovation Groups were selected following a rigorous technical evaluation process and field visits. These groups signed Low Value Grant Agreements in July 2023.

Each IG worked on project ideas aligned with EU-AGRIN’s priorities: sustainable agriculture, water conservation, soil health, and climate resilience. Examples of IGs established include:

- In Tashkent Region: Introduction of soybean varieties "Ehtiyoj" and "Xotira"; solar-powered drip irrigation systems; and in vitro vine graft cultivation, women led dairy production group and and Merino sheep breeding.

- In Fergana Region: Organic tomato drying technologies; sustainable aquaculture; and bioremediation of saline soils.

- In Kashkadarya Region: High-yield cotton and wheat varieties; pistachio cultivation using microclonal reproduction;

By late 2024, all 18 IGs had completed their work, delivering tangible results through field demonstrations, knowledge products, and public outreach. Impact assessments showcased excellent results in some of the IGs as:

- A 55% reduction in energy and water usage through solar-powered drip irrigation systems.

- 25% increase in cotton yields with improved seed varieties and efficient inputs.

- 80% reduction in GHG emissions in wheat cultivation.

- Bioremediation techniques reclaiming saline lands for agriculture in Fergana

- Income boosts of up to 300% for smallholder households working in milk production

Notably, the project launched key initiatives such as the Solar-powered Drip Irrigation System in Akkurgan District, significantly improving irrigation efficiency and livelihoods for local families. The cultivation of Ezoz wheat, a climate-adapted variety, demonstrated how innovation can bolster food security while mitigating environmental impacts.

The IGs also received high-level visibility. In 2024, the EU Delegation to Uzbekistan and UNDP leadership visited five IGs in Fergana region, underscoring the project’s success in addressing water scarcity, soil salinity, and climate resilience. These visits showcased the importance of collaborative innovation and fostered momentum for scaling best practices nationwide.

EU-AGRIN’s Innovation Groups have proven to be a dynamic and practical vehicle for fostering applied research, technology transfer, and inclusive development, practically serving as an functional AKIS mechanism, but developed bottom-up and keeping connection with real needs of farmers.

Activity 2.2	Delivery of training, capacity building and technical advice to the members and partners of the Agri-food Innovation Operational Groups

Over the course of the EU-AGRIN project, the delivery of training, capacity building, and technical advice has played a key role in empowering Innovation Group (IG) members, regional research institutes, and wider stakeholders in Uzbekistan’s agricultural sector. From 2022 to 2024, a series of comprehensive, tailored initiatives have been implemented to develop institutional capacity, foster innovation, and promote climate-smart, sustainable agriculture practices.

In 2022, the foundation was laid through a training seminar held in Tashkent on August 19–20. This event gathered representatives from agricultural research institutes, AKIS Agricultural Services Centers, secondary vocational institutions, and farms across Tashkent, Fergana, and Kashkadarya. The sessions focused on turning innovative ideas into actionable project proposals, the relevance of international food standards, and climate adaptation in agriculture. Participants received guidance on grant criteria and conditions under the EU-AGRIN framework and shared project ideas for 12 potential Innovation Groups. Constructive discussions followed, offering recommendations to overcome operational barriers.

The training approach expanded in 2023 with more specialized and high-level sessions. On January 31, a hybrid training was delivered in Tashkent in collaboration with Italy’s Research Center for Agriculture Economics (CREA), under the theme "Operational/Innovation Groups: An Overview of the European Union Experience." Participants, including researchers, farmers, NGOs, and education sector representatives, were introduced to the EIP-AGRI model and insights into co-creating agricultural innovations through collaborative models. CREA’s contributions strengthened understanding of successful European practices, enabling adaptation to the Uzbek context.

A key 2023 milestone was the organization of a study tour to Italy between May 20–28. Twelve Uzbek delegates visited several operational groups supported by CREA, gaining first-hand experience of innovative practices in areas such as aquaponics, irrigation, viticulture, and sheep farming. This study tour deepened practical knowledge and exposed stakeholders to collaborative, result-oriented innovation models in European rural development.

Gender inclusion and youth empowerment were emphasized through a student competition supporting green agriculture innovations. Endorsed by the UNDP and the EU Delegation, the competition engaged 2,703 women students. Finalists presented forward-looking ideas addressing climate change, and the top participants were awarded in a public ceremony. Additional training followed, linking the winners to CREA experts and promoting their continued participation in IG development.

CREA and UNDP advanced technical capacity-building efforts throughout 2024. A core element was the delivery of a targeted training program on project proposal development, benefiting 59 researchers from 12 regional institutes. These sessions, aligned with the Horizon Europe funding mechanisms, covered all components of competitive proposal design, from objectives and methodologies to budgeting and impact planning. The comprehensive training materials and a guidance report were finalized, marking the successful completion of this activity.

In parallel, a series of technical training modules were implemented for IG members. Covering topics like seed production, irrigation systems, food processing, and pest control, these sessions adopted a blended learning model. On-site practical demonstrations were combined with online consultations to ensure accessibility and relevance. Customization ensured that researchers received scientific insights, while farmers gained hands-on skills in applying new technologies. By August 2024, on-site sessions addressed animal health monitoring, aquaculture, and plant protection techniques. Technical guidelines and post-training reports offered strategic and operational recommendations tailored to each IG.

CREA also developed customized technical papers for IGs, detailing recommendations on pest control, water-saving practices, and soil management. These documents now serve as useful references, supporting long-term knowledge retention and skill development across the IG network.

A transformative addition in 2024 was the launch of Innovation Labs, envisioned as a network of demonstration farms across Uzbekistan. These labs aim to bridge the gap between academic research and agricultural practice. Conducted with CREA’s guidance, a thorough gap analysis of existing demo fields led to the preparation of a technical document recommending specific upgrades. Key goals include the promotion of climate-resilient farming, technology adoption, and collaborative learning, with a focus on inclusion of women and youth.

The Innovation Labs initiative culminated in a European best-practice training program for Uzbek stakeholders, enabling them to manage these labs effectively and replicate proven models from the EU Farm Demo Network. Through these Labs, a stronger international knowledge network is being cultivated, aligning Uzbekistan’s agricultural institutions with European innovation ecosystems.

Further promoting water-saving innovation, a major workshop was held on October 23, 2024, at the National Research University TIIAME, co-hosted by IFAD and EU-AGRIN. Over 40 participants from national and international organizations, including World Bank and ADB, participated. Technical presentations covered sustainable irrigation, legal frameworks, and organic farming practices. A practical field visit to TIIAME’s demonstration site provided real-world insights into smart water use technologies.

Across all these activities, the training and capacity-building strategy of EU-AGRIN has been instrumental in nurturing a technically equipped, innovation-driven, and collaborative agricultural community. By integrating research, education, and extension services, these initiatives have laid a strong foundation for sustainable agricultural development in Uzbekistan.

## Activity 2.3	Delivering targeted financial support and investments for innovative projects with climate change mitigation and adaptation benefits

In 2024, the EU-AGRIN project successfully completed its targeted financial support initiative, providing crucial funding to innovative projects aimed at climate change adaptation and mitigation in Uzbekistan’s agri-food sector. This initiative was instrumental in translating research and innovation into actionable, field-based practices with tangible environmental and socio-economic impacts.

The financial support was strategically aligned with the project’s broader goals of sustainability, inclusivity, and climate resilience. It was delivered through a structured and transparent mechanism that empowered Innovation Groups (IGs) and research institutions to pilot and scale climate-smart agricultural solutions.

- Development of a Comprehensive Grant Mechanism:

A grant framework was established, including customized regulations, evaluation criteria, and implementation guidelines. The mechanism was designed to prioritize high-impact, climate-focused innovations and ensure participation from underrepresented groups, particularly women and vulnerable communities.

- Transparent Public Call and Broad Outreach:

The grants were awarded through an open public call, widely promoted through available social media and groups under the AKIS network, and amplified by an extensive media campaign. This approach ensured widespread awareness and encouraged broad stakeholder engagement from across the agricultural value chain.

- Direct Support for Innovation Groups and Research Institutions:

The targeted financial support enabled selected IGs and research organizations to implement cutting-edge practices such as water-saving irrigation systems, climate-resilient crop varieties, and sustainable livestock and aquaculture innovations. These investments catalyzed knowledge transfer, increased productivity, and improved environmental outcomes in pilot regions.

This activity represents a key milestone for the EU-AGRIN project, reinforcing its role as a driver of sustainable agricultural transformation in Uzbekistan. The successful delivery of targeted financial support accelerated innovation but also laid the foundation for long-term resilience and adaptation within the country’s agricultural sector.

## Activity 2.4: Innovation Networking and Exchange Program

Innovation networking and knowledge exchange have been essential pillars of the EU-AGRIN project, fostering collaboration among farmers, researchers, educational institutions, and agricultural stakeholders across Uzbekistan. Throughout the project lifecycle, numerous training sessions, demonstration events, and technical workshops have served as key platforms for sharing expertise, promoting peer learning, and scaling up climate-smart agricultural solutions.

Building on these foundations, the project has laid the groundwork for a sustainable innovation ecosystem by launching several forward-looking initiatives:

To institutionalize knowledge exchange and accelerate adoption of sustainable practices, the EU-AGRIN project has initiated the formation of Innovation Labs—a national farm demonstration network inspired by successful European models. These labs will function as dynamic hubs where innovative techniques, technologies, and research-driven solutions can be tested, adapted, and disseminated. Designed to strengthen linkages between farmers, advisors, and researchers, Innovation Labs aim to bridge the gap between science and practice while facilitating region-wide learning and replication.

As part of the Innovation Lab network, a flagship initiative was launched to modernize the Technical and Vocational Education and Training (TVET) center in Zangiota, transforming it into a state-of-the-art facility for livestock training and innovation. The project undertook the refurbishment of outdated classrooms, equipping them with modern technologies, training equipment, and interactive learning tools. This center now serves as a model for climate-smart agricultural education, offering students hands-on experience in sustainable livestock practices, while promoting inclusivity and youth engagement in agriculture. It also serves as a collaborative platform connecting academia, private sector, and research institutions within the UAKIS Innovation Lab network.

To complement national networking efforts, the project has also implemented several study visits but also supported presence of key experts and European actors, to ensure connections and exposure to international best practices. By connecting Uzbek researchers, students, and farmers with their global counterparts, this exchange initiative contributed to a cross-border collaboration, capacity building, and awareness of globally tested methodologies and tools.

These efforts collectively strengthen the project’s goal of creating an inclusive, innovation-driven agricultural ecosystem, ensuring that knowledge and innovation continue to flow across regions and sectors.

## Project Board (Steering committee) meetings

1st Project Board Meeting minutes

2nd Project Board Meeting minutes

3rd Project Board Meeting minutes

## Anticipated Problems, Planned Remedial Actions and Lessons Learned from Encountered Problems

Throughout the EU-AGRIN project implementation several key challenges emerged that influenced the pace and structure of the project activities. However, each issue was met with practical remedial actions, ultimately contributing to stronger foundations and lessons for the future.

Delays in Contracting the International Lead Technical Specialist

In 2022 one of the most pressing challenges was the prolonged process of hiring the suitable international Lead Technical Specialist. Two initial public calls failed to identify a proper candidate. This delay temporarily constrained the full-scale launch of activities.

Remedial Action: To mitigate the gap, the project engaged short-term international experts. Their support was pivotal in developing the multi-year work plan and conducting initial stakeholder workshops. The successful appointment of the Lead Technical Specialist on October 23, 2022, restored continuity and expert leadership.

Lesson Learned: Building flexibility into recruitment plans and maintaining a roster of short-term experts are critical for ensuring momentum in project execution, especially when delays in key positions occur.

Confusion and Differences in Understanding the AKIS and Innovation Partnership and Innovation Groups

A significant and recurring challenge, particularly in the first two years, was the lack of a common understanding of the Agricultural Knowledge and Innovation System (AKIS) concept. This confusion was intensified by overlapping donor initiatives, often applying differing and non-aligned models, which led to uncertainty among stakeholders about the best direction for AKIS and Innovation Groups (IGs).

Remedial Action: The EU-AGRIN team responded proactively with awareness-raising activities, capacity building, and close collaboration with international partners. Training sessions, study tours, and hands-on implementation of Innovation Groups provided practical insights and unified understanding.

Lesson Learned: Real-world application and constant engagement with local actors are essential to clarify and consolidate new conceptual models, particularly when multiple frameworks are being introduced simultaneously by various donors.

Need for Project Design Adjustments and M&E Strengthening

Following the 2022 Results-Oriented Monitoring (ROM) mission, specific areas were identified for improvement: refining the project log-frame, establishing an internal Monitoring and Evaluation (M&E) system, and strengthening the connection to gender equality, inclusion, and sustainability strategies.

Remedial Action: These elements were incorporated into project planning in subsequent years. The establishment of a dedicated M&E expert in 2024 and the development of a tailored M&E framework significantly improved monitoring, accountability, and alignment with key thematic priorities.

Lesson Learned: External monitoring can offer valuable insights for realignment, and timely incorporation of their recommendations strengthens project responsiveness and impact.

Outcome

By 2024, the EU-AGRIN project had transformed initial challenges into strategic achievements. The successful rollout of Innovation Groups, widespread understanding of the AKIS model, and official endorsement through a 2023 Presidential Decree stand as a powerful example of how joint efforts can turn early obstacles into drivers of lasting impact.

NEXT STEPS, SCALING-UP

## Next Steps and Scaling Up: Building a Future-Ready Agri-Food System

The EU-AGRIN project has laid a solid foundation for agricultural innovation, resilience, and sustainability in Uzbekistan. Through an integrated approach involving Innovation Groups, capacity building, targeted financial support, and cross-sector collaboration, the project has demonstrated tangible paths for climate-smart, inclusive, and technology-driven development. Now, the momentum created should not only be sustained—but scaled.

Scaling up is not just about expanding the reach of current interventions. It is about institutionalizing innovation, fostering an ecosystem of collaboration, and aligning future investments with practical outcomes that matter for farmers, communities, and the national economy. This chapter outlines the key opportunities and dimensions of this scaling-up program.

1. Building Upon Achievements: From Pilots to Policy

EU-AGRIN’s success in fostering 18 Innovation Groups and engaging research institutes, educational institutions, and the private sector proves that Uzbekistan has the human capital and institutional capacity to lead agricultural transformation. However, to ensure long-term impact:

- The pilot results must be institutionalized through policy reform and integration into national agricultural development strategies.

- Demonstrated innovations—such as solar-powered drip irrigation, climate-resilient wheat, and aquaculture technologies—should become part of mainstream agricultural practices supported by public and private actors.

- A national repository of tested, scalable innovations should be created and continuously updated.

Scaling is not merely replication—it requires a systemic shift in how innovation is supported, rewarded, and embedded into everyday farming and policymaking.

2. A Modern Agricultural Advisory System: Catalyzing Farmer-Centered Change

To truly transform the agricultural landscape, Uzbekistan must modernize its farmer advisory system, mostly, non-existent at the moment. Traditional models of knowledge dissemination are no longer sufficient in the face of rapidly evolving challenges like climate change, market volatility, and labor migration.

A new generation of agricultural advisory services should be:

- Digital and data-driven, integrating remote sensing, AI, mobile platforms, and real-time agronomic recommendations.

- Decentralized and responsive, embedded within regions through Innovation Labs and connected to local value chains.

- Multi-actor oriented, involving not only agronomists but also environmental specialists, economists, and climate experts.

- Inclusive, targeting women and youth as both recipients and providers of advisory services.

These modern advisory services should act as innovation enablers - brokers, capable of guiding farmers through experimentation, scaling, and sustained adoption of new technologies.

3. Engaging All Actors Toward Common, Measurable Goals

Effective scaling requires alignment and synergy of effort. The future of Uzbekistan’s agri-food system depends on uniting actors—public institutions, research bodies, the private sector, academia, and civil society—under shared objectives that are measurable and result-oriented.

Key proposals include:

- Establishing a national innovation roadmap with clear performance indicators linked to adoption rates of new practices, productivity gains, and environmental outcomes.

- Mandating that all state-supported agricultural institutions align part of their mandates to national innovation and sustainability targets.

- Empowering regional governments and AKIS centers to tailor goals based on local contexts while contributing to national benchmarks.

Only through shared ownership of results will true systemic change take root.

4. Innovation-Linked Financing Models

One of the most critical enablers of long-term impact is the rethinking of how agricultural research, extension services, and development agencies are financed.

We recommend:

- Moving from input-based to performance-based funding, where institutions receive additional resources based on their contribution to measurable outcomes (e.g., improved yields, reduced water use, increased farmer income).

- Establishing innovation fund or blended finance mechanisms that encourage cross-sector collaboration and reward risk-taking

- Ensuring that financing structures support continuity beyond project cycles, allowing successful Innovation Groups to evolve into formal cooperatives, service providers, or knowledge hubs.

This model shifts the focus from spending to impact, ensuring public resources generate real value for farmers and the economy.

5. Towards a Resilient Innovation Ecosystem

Finally, scaling must be anchored in resilience. The future agricultural system must be able to adapt to shocks, seize new opportunities, and respond to emerging trends—whether from global markets or the climate front.

To that end, we propose:

- Expanding the Innovation Lab network, turning demonstration farms into living laboratories for testing, adapting, and transferring new practices.

- Institutionalizing regular innovation foresight exercises to anticipate changes in climate, technology, and food systems, and prepare appropriate responses.

- Strengthening partnerships with international research networks to keep Uzbekistan at the frontier of agricultural science and technology.

These steps will help ensure that innovation remains continuous, not episodic—and that Uzbekistan remains a leader in regional agricultural transformation.

Conclusion: A National Imperative

The EU-AGRIN experience has proven that Uzbekistan can foster innovation from the ground up—through clear objectives, straightforward rules, financial support, collaboration, capacity building, and commitment. What comes next must build on this momentum: scaling up through systems, not just projects.

With strategic investment, and continued international cooperation, Uzbekistan can become a model of sustainable, climate-resilient, and innovation-led agriculture in Central Asia and beyond.

| RESULTS FRAMEWORK Outcome as stated in the UNDAF/Country [or Global/Regional] Programme Results and Resource Framework: |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome indicators as stated in the Country Programme [or Global/Regional] Results and Resources Framework, including baseline and targets: |  |  |  |  |  |  |  |  |  |  |  |
| Applicable Output(s) from the UNDP Strategic Plan: |  |  |  |  |  |  |  |  |  |  |  |
| Project title and Atlas Project Number: |  |  |  |  |  |  |  |  |  |  |  |
| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | TARGETS (by frequency of data collection) |  |  |  |  |  | DATA COLLECTION METHODS & RISKS |
|  |  |  | Value | Year | Year 1 | Year 2 | Year 3 | Year 4 | Year … | FINAL |  |
| Output 1 Establish Agri-food Innovation Support and Brokerage Services | 1.1 Assessment of policy and regulatory barriers to scaled-up climate action and “green” transition. | Monitoring data and progress reports on the implementation of the Agri-food Strategy of the Ministry of Agriculture | UAKIS Strategy is adopted (Concept); Operationalization plan for CC mitigation and adaptation in the Agri-food sector not available for CC mitigation and adaptation in the Agri-food sector not available | 2021 | N/a | TBD | Done |  |  | Supported policy dialogues and development of plans and regulatory framework at national and regional level for the alignment of agricultural policies and programmes to respond to climate change. | Document review |
|  | 1.2 Number of knowledge products elaborated per priority area, their status and availability (O2.1, O2.2) | Action/Project reports, government reports | 0 | 0 | 5 | 19 | 29 | 30+1CREA |  | At least 20 | Document review |
|  | 1.3 Number of policy makers informed by the Action about the new knowledge products (O2.3) | Action/Project reports | 0 | 0 | 31 | 92 | 156 | 306 |  | At least 120 | Document review, local surveys |
|  | 1.4 Number of professional staff and researchers trained (O3.1) | Action/Project reports | 0 | 0 | 44 | 131 | 229 | 249 |  | At least 100 | Project report |
|  | 1.5 Number of professional organizations strengthened with research and training interventions (O3.2) | Results of the trainings | 0 | 0 | 5 | 18 | 18 | 18 |  | At least 10 | Project report |
|  | 1.6 Number of EU research organizations mobilized by the action (O4.1) | Cooperation agreement, project/Action reports | 0 | 0 | 1 | 13 | 13 | 13 |  | At least 3 | Project report |
|  | 1.7 Number of subject specific, evidence-based policy briefs prepared and supported to policy address constraints to the uptake of new innovations. | Action/Project reports | 0 | 0 | 1 | 2 | 3 | 4 |  | At least 5 | Document review |
| Output 2 Agri-food Innovation Operational Groups and Partnerships | 2.1 Number of new Agri-food Innovation Groups and Partnerships (operational groups) established with the project support | Government reports/report from partners/national registration data/mass media | 0 | 0 | 0 | 18 | 18 | 18 |  | At least 12 | Project report Risk: The failure of the national beneficiaries to meet their commitments for regulatory, institutional and financial sustainability of UAKIS network. |
|  | 2.2 Number of food and agriculture value chains supported by the project on climate resilience and emission reduction | Information from CCI and khokimiyats./ Action/project reports | 0 | 0 | 0 | 6 | 17 | 23 |  | At least 20 |  |
|  | 2.3 Agricultural and pastoral ecosystems where climate relevant management practices have been introduced with EU support, ha (SO1.3, EU RF 2.04) | Local khokimiyat/ Action/project reports | 0 | 0 | 0 | 92 | 193 | 285 |  | At least 200 |  |
|  | 2.4. Number of small-scale farmers adopting sustainable and resilient agriculture practices thanks to this action, disaggregated by sex (SO1.1, EU RF 2.03) | Council of Farmers reports/ Action/project reports | 0 | 0 | 0 | 38 | 41 | 41 |  | At least 40 | Project report |
|  | 2.5 Number of smallholder farmers reached by the R&D initiatives, disaggregated by sex and country (O1.1) | National reports/Council of Farmers Reports/ Action/project reports | 0 | 0 | 0 | 315 | 616 | 616 |  | At least 400 | Project report |

MATRIX UPDATED

| Risks | Risk level (H/M/L) | Mitigating measures |
| --- | --- | --- |
| Physical risks and force majeure. This includes national or man-made disasters, political disturbances, conflicts. | L | Contingency Plans and the extended climate resilience systems to minimize the impact of those risks on the operations. |
| Unintended, direct or indirect negative harms of human safety during the implementation of on-the-ground projects | L | The action will respect, protect and fulfil human safety standards. UNDP Social and Environmental Safeguards Policy will be applied to planning, implementation and oversight over the project implementation across all components. “Do not harm principle” will be applied during the implementation of the project, assessing and managing the possible intended/unintended, direct/indirect risk that could occur. |
| Lack of experience in the system innovation and participatory whole-of-government approaches. | M | The project will work closely and engage with national and local authorities as well as with local partners and stakeholders in an open dialogue that will help enhance awareness, set priorities, agree on results linked to performance, and measure progress. The project includes activities to strengthen enabling environment and capacities for system innovation and climate action across the food and agriculture sector stakeholders. |
| Project complexity and a broad scope related to the extended network of institutional partners, the geographical, social and economic diversity, and innovative nature of the project may affect the project implementation with respect to the adequacy of allocated resources, work plans and stakeholder engagement. | M | Development and implementation of the Action is based upon strong national ownership, a consensus regarding priorities, expected results and shared responsibilities, pro-active participation of all partners in the planning and implementation. The project will transfer successful innovative technologies, practices and advice, including from the EU, to facilitate transition to “green economy” in the Uzbekistan agri-food sector. |
| Risks related to the failure of the national beneficiaries to meet their commitments for regulatory, institutional and financial sustainability of UAKIS network. | M | The project is based on the extensive consultations with the Government of Uzbekistan on their long-term development priorities and commitments towards transition to “green economy” and scaling up innovation. Positive changes in the legal, regulatory and institutional framework conductive for the promotion of innovation and “green economy” strategy in agri-food sector have been demonstrated. |
| Failure to engage local private sector in the Agri-food Innovation Operational Groups and Partnerships | L | The project will be carrying out stakeholder consultations and participatory planning throughout the development and implementation of the Agri-food Innovation Support and Brokerage Services (Output 1) to make sure that the correct stakeholder engagement strategies are implemented and that adequate incentives are provided to the local private sector to engage. Through the implementation of Output 2, the project will demonstrate tangible benefits of participation to private sector and farming communities. |
| Risk of overlapping interventions of multiple donors causing distractions and changes in AKIS strategy and structure, which can slow down some of the activities of the EU-AGRIN | L | The project with liaise with key stakeholders, partners and donors to support open dialogue, sharing of information and common understanding of the AKIS concept and position of the IGs within. |
| Assumptions |  |  |
| ● Political willingness in the country to cooperate on transition to “green economy” and climate action, including timely adoption of the UAKIS regulatory framework ● Long-term commitment of the Government of Uzbekistan, non-governmental organizations and academia to facilitate and support the implementation of the UAKIS strategy and the EU Action by providing access to relevant information and contributions in the form of technical and human resources. ● A strong and sustainable network of institutional partners is established and maintained for the project implementation led by beneficiary governments. ● Clear lines and means of communication and dissemination of information are established ● Alignment with needs identified by the government translate into full support by the authorities, private sector and beneficiary farming communities in the implementation phase. ● Decision-making by recipient authorities is overall timely and coherent. ● Policy priorities do not suffer sudden and radical changes. ● Resources for implementation, including Government resources for the management and development of the UAKIS network are sufficient and available timely. |  |  |

- PROJECT WORK PLAN

The table is attached to this report as Annex 6.                                                                        Link to the document (EU-AGRIN workplan/timeline)

ANNEXES

# Annex 1:

# VISIBILITY ACTIVITIES:

# LIST OF POSTED ANNOUNCEMENTS

| # | Event | Links to publications |
| --- | --- | --- |
|  | The 2nd Agri-Food Forum aimed to set out the framework for the proposed National Agriculture and Food Research Program Date: 1-2 June 2022 | - https://twitter.com/UNDP_Uzbekistan/status/1531930773397221376?s=20&t=G1ayH2-tsSmN4LpG4PpZ1A - https://www.undp.org/uzbekistan/speeches/statement-ms-matilda-dimovska-undp-resident-representative-uzbekistan-2nd-national-agricultural-research-forum - https://daryo.uz/2022/06/05/sharlotta-adrian-ozbekistonda-qishloq-xojaligi-sohasi-bilan-ilmiy-tadqiqotlar-ortasidagi-bogliqlik-juda-zaif/ - https://www.agro.uz/ru/11-0173/ - https://www.agro.uz/11-0173/ - https://www.uzdaily.uz/en/post/73445 - http://ekolog.uz/?p=3657&lang=ru - https://t.me/uzagroministry/5909 - https://t.me/uzagroministry/5917 - https://t.me/uzagroministry/5960 TV reportages - https://t.me/mtrkuzofficial/97446 - https://t.me/mtrkuzofficial/97244 - https://t.me/mtrkuzofficial/96900 - https://t.me/mtrkuzofficial/96722 |
|  | 6 seminar-trainings for rural women on “Proper cow care in private farms, healthy breeding and increased productivity” in Ahangaran district of Tashkent region Date: 14-22 June 2022 | - https://telegra.ph/MORE-THAN-200-LOW-PROVIDED-WOMEN-WILL-INVOLVED-IN-AGROBUSINESS-IN-OHANGARON-DISTRICT-06-15 - https://t.me/agrowoman/1957 - https://t.me/agrowoman/1961 - https://m.facebook.com/story.php?story_fbid=pfbid024iW77zuGYFbv1WKHdMvSNmC762BcMkPypxGidaKT5wCmAXdsgFPfW9gYMxPDsYftl&id=157904747562748 - https://twitter.com/UNDP_Uzbekistan/status/1537026566063919104?s=20&t=KaJ-4H9mf5Qwgmq6hxZPIA - https://twitter.com/EU_Tashkent/status/1581838036488200194?s=20&t=dkwHKFi6lRNkf_4DQY2qMw - https://twitter.com/EU_Tashkent/status/1581132963990761472?s=20&t=dkwHKFi6lRNkf_4DQY2qMw TV reportage - https://t.me/mtrkuzofficial/99140 |
|  | Technical training workshop on Concept of Innovation Groups and Agri-smart Technologies by International Consultant. Date: 13th July 2022 | - https://www.eeas.europa.eu/delegations/uzbekistan/support-eu-uzbekistan-launch-innovative-groups-agriculture-development_en - https://e-cis.info/news/569/101816/ - https://uza.uz/uz/posts/qishloq-xozhaligini-rivozhlantirishda-innovacion-guruhlar-faoliyati-yolga-qoyiladi_389303 - https://www.agro.uz/11-0266/ - https://www.agro.uz/ru/11-0266-2/ - https://www.uzdaily.uz/ru/post/70296 - https://anhor.uz/news/innovation-groups/ - https://yuz.uz/ru/news/v-uzbekistane-budut-sozdan-innovatsionne-grupp-dlya-razvitiya-selskogo-xozyaystva - https://yuz.uz/news/qishloq-xojaligida-innovatsiyalarni-qollashga-doir-tadbir-tashkil-etildi - https://yuz.uz/news/ozbekistonda-qishloq-xojaligini-rivojlantirish-yolida-innovatsion-guruhlar-faoliyati-yolga-qoyiladi https://e-cis.info/news/569/101816/ - https://uza.uz/ru/posts/budut-sozdany-innovacionnye-gruppy-dlya-razvitiya-selskogo-xozyaystva_389390 - https://www.undp.org/uzbekistan/press-releases/uzbekistan-launch-innovative-groups-agriculture-development - https://www.undp.org/ru/uzbekistan/press-releases/v-uzbekistane-zapustyat-deyatelnost-innovacionnykh-grupp-dlya-razvitiya-selskogo-khozyaystva - https://dairynews.today/news/v-uzbekistane-sozdadut-innovatsionnye-gruppy-dlya-.html - https://www.uzdaily.uz/ru/post/70296 - https://aykan.uz/news/v-uzbekistane-zapustiat-deiatelnost-innovatsionnyh-grupp-dlia-razvitiia-selskogo-hoziaistva - https://twitter.com/UNDP_Uzbekistan/status/1548997169881006080 - https://invest.gov.uz/ru/mediacenter/news/russkij-v-uzbekistane-zapustyat-deyatelnost-innovatsionnyh-grupp-dlya-razvitiya-selskogo-hozyajstva/ - https://invest.gov.uz/uz/mediacenter/news/russkij-v-uzbekistane-zapustyat-deyatelnost-innovatsionnyh-grupp-dlya-razvitiya-selskogo-hozyajstva/ TV reportages - https://www.youtube.com/watch?v=EDmpmPV-gGo - https://t.me/mtrkuzofficial/102591 - https://t.me/markaziytv/10584 - https://drive.google.com/file/d/1yIn1Hk1e47NouaMWHhkDDxDr9d8lrzOz/view?usp=sharing |
|  | Training for the Innovation groups on: - International standards in the food production - Adaptation to climate change in agriculture - Effective using of Satellite-Based Monitoring in Agriculture - The project proposals development Date: 19-20 August 2022 | - https://www.eeas.europa.eu/delegations/uzbekistan/mutual-integration-science-research-service-system-and-production-will-help_en - https://www.undp.org/uzbekistan/press-releases/seminar-development-innovation-groups - https://www.undp.org/uz/uzbekistan/press-releases/innovatsion-guruhlarni-rivojlantirish-boyicha-seminar - https://www.agro.uz/11-0362/ - https://www.agro.uz/ru/11-0362/ - https://www.uzdaily.uz/ru/post/71174 - https://www.uzdaily.uz/en/post/75073 - https://www.uzdaily.uz/en/post/75052 - https://www.uzdaily.uz/en/post/75039 - https://www.uzdaily.uz/ru/post/71114 - https://www.uzdaily.uz/ru/post/71129 - https://www.uzdaily.uz/ru/post/71174 - https://t.me/AKIS_milliy_markaz/1177 - https://yuz.uz/ru/news/innovatsionne-grupp-ferganskoy-i-kashkadarinskoy-oblastey-budut-testirovat-nove-idei-v-selskom-xozyaystve |
|  | Inception workshop of EU-AGRIN project Date: 14th July 2022 | - https://www.agro.uz/11-02845/ - https://www.agro.uz/ru/11-02845/ - https://dairynews.today/news/v-uzbekistane-prezentovali-rabochiy-plan-po-razvit.html - https://www.undp.org/ru/uzbekistan/press-releases/programma-razvitiya-oon-pri-finansovoy-podderzhke-evropeyskogo-soyuza-predstavila-rabochiy-plan-napravlennyy-na-razvitie - https://www.undp.org/uz/uzbekistan/press-releases/bmt-taraqqiyot-dasturi-yevropa-ittifoqining-moliyaviy-komagi-ostida-ozbekiston-qishloq-xojaligida-innovatsion-tizimni - https://xs.uz/ru/post/v-tashkente-proshla-prezentatsiya-rabochego-plana-po-razvitiyu-innovatsionnoj-sistemy-v-selskom-khozyajstve |
|  | Meetings with research institutes in Tashkent, Fergana and Kashkadarya regions | - https://www.agro.uz/11-0336/ - https://www.agro.uz/ru/11-0336/ - https://www.agro.uz/11-0365/ - https://www.agro.uz/ru/11-0365/ - https://www.undp.org/uz/uzbekistan/press-releases/toshkent-viloyatida-qishloq-xojaligini-rivojlantirishga-qaratilgan-innovatsion-guruhlar-shakllantirilmoqda - https://www.facebook.com/UNDPUzbekistan/videos/1661910484187871 - https://t.me/ferganaakis/695 - https://t.me/ferganaakis/1193 |
|  | Workshop on the Efficient use of land and water resources In Agriculture | - https://www.undp.org/uzbekistan/press-releases/undp-hosts-workshop-efficient-use-land-and-water-resources-agriculture - https://www.undp.org/ru/uzbekistan/press-releases/sostoyalas-prezentaciya-metodov-effektivnogo-ispolzovaniya-zemelnykh-i-vodnykh-resursov-v-selskom-khozyaystve - https://www.undp.org/uz/uzbekistan/press-releases/qishloq-xojaligida-yer-va-suv-resurslaridan-samarali-foydalanish-usullari-taqdimoti-otkazildi - https://www.agro.uz/ru/11-045349/ - https://www.agro.uz/11-045349/ - https://www.yuz.uz/ru/news/sostoyalas-prezentatsiya-metodov-effektivnogo-ispolzovaniya-zemelnx-i-vodnx-resursov-v-selskom-xozyaystve |
|  | Contest for innovative ideas in agriculture | - https://www.undp.org/uz/uzbekistan/news/bmttd-innovatsion-qishloq-xojaligini-rivojlantirishga-qaratilgan-innovatsion-goyalar-tanlovini-elon-qiladi - https://www.undp.org/uzbekistan/news/undp-uzbekistan-announces-contest-innovative-ideas-agriculture - https://uza.uz/uz/posts/qishloq-xozhaligini-rivozhlantirishga-qaratilgan-innovacion-goyalar-tanlovi-elon-qilinadi_439919 - https://t.me/uzagroministry/9737 - https://www.uzdaily.uz/ru/post/74526 - https://www.uzdaily.uz/en/post/78266 - https://anhor.uz/news/innovative-ideas/ - https://anhor.uz/uz/news/bmttd-ishlo-h-zhaligini-rivozhlantirishga-aratilgan-innovacion-ojalar-tanlovini-jelon-iladi/ - https://www.spot.uz/ru/2022/12/28/undp-contest/ - https://www.spot.uz/oz/2022/12/28/tanlov/ - https://nuz.uz/nauka-i-tehnika/1264350-proon-i-minselhoz-uzbekistana-nachali-priem-zayavok-na-konkurs-innovaczij.html - https://grantgo.uz/grant/bmttd-innovatsion-qishloq-xojaligini-rivojlantirishga-qaratilgan-innovatsion-goyalar-tanlovi - https://t.me/grants4innovations/8 - https://t.me/uzagroministry/9733 - https://t.me/undpuzbekistan/628 - https://t.me/eu4uz/6190 |
|  | Leading Italian experts conducted training to the development of innovative groups for agriculture in Uzbekistan | - https://kknews.uz/132251.html - https://uza.uz/uz/posts/italiya-ekspertlari-ishtirokida-seminar-tashkil-etildi_450426 - https://uza.uz/ru/posts/veduschie-italyanskie-eksperty-proveli-seminar-v-oblasti-selskogo-xozyaystva_450280 - https://daryo.uz/en/2023/02/01/italy-aims-to-support-uzbekistans-transition-to-green-economy-and-this-is-how - https://www.uzdaily.com/en/post/78913 - https://www.uzdaily.com/ru/post/75199 - https://yuz.uz/ru/news/missiya-ekspertov-iz-italii-podderjka-inklyuzivnogo-perexoda-k-zelenoy-ekonomike - https://www.shirinmeva.uz/article/420 - https://yuz.uz/news/italiyalik-ekspertlar-ozbekistonda-yashil-iqtisodiyotga-otilishini-qollab-quvvatlaydi - https://yuz.uz/ru/news/missiya-ekspertov-iz-italii-podderjka-inklyuzivnogo-perexoda-k-zelenoy-ekonomike - https://uza.uz/uz/posts/italiya-ekspertlari-ishtirokida-seminar-tashkil-etildi_450426 - https://www.gov.uz/oz/news/view/36377 - https://www.gov.uz/ru/news/view/36377 - https://www.agro.uz/ru/11-04536141/ - https://www.agro.uz/11-04536141/ - https://anhor.uz/uz/news/bmttd-italija-ishlo-h-zhaligi-tad-i-otlari-b-jicha-kengash-delegacijasining-tashrifini-tashkil-ildi/ - https://anhor.uz/news/italian-council/ - https://anhor.uz/uz/news/bmttd-italija-ishlo-h-zhaligi-tad-i-otlari-b-jicha-kengash-delegacijasining-tashrifini-tashkil-ildi/ - https://www.eeas.europa.eu/delegations/uzbekistan/eu-and-undp-are-bringing-italian-expertise-development-innovative-groups_en?s=233 - https://www.eeas.europa.eu/delegations/uzbekistan/%D0%B5%D1%81-%D0%B8-%D0%BF%D1%80%D0%BE%D0%BE%D0%BD-%D0%BF%D1%80%D0%B8%D0%B2%D0%BB%D0%B5%D0%BA%D0%BB%D0%B8-%D0%B8%D1%82%D0%B0%D0%BB%D1%8C%D1%8F%D0%BD%D1%81%D0%BA%D0%B8%D1%85-%D1%8D%D0%BA%D1%81%D0%BF%D0%B5%D1%80%D1%82%D0%BE%D0%B2-%D0%B4%D0%BB%D1%8F-%D1%80%D0%B0%D0%B7%D0%B2%D0%B8%D1%82%D0%B8%D1%8F-%D0%B8%D0%BD%D0%BD%D0%BE%D0%B2%D0%B0%D1%86%D0%B8%D0%BE%D0%BD%D0%BD%D1%8B%D1%85-%D0%B3%D1%80%D1%83%D0%BF%D0%BF_ru?s=233 - https://www.eeas.europa.eu/delegations/uzbekistan/yevropa-ittifoqi-va-bmttd-ozbekistonda-qishloq-xo%E2%80%98jaligida-innovatsion_uz?s=233 - https://t.me/mtrkuzofficial/132954 |
|  | The project supported women students contest on promoting innovation and green transition in agriculture | - https://www.undp.org/uzbekistan/press-releases/women-students-promote-innovation-and-green-transition-agriculture-help-european-union-and-undp - https://www.undp.org/uz/uzbekistan/press-releases/talaba-qizlar-yevropa-ittifoqi-va-bmttd-komagida-qishloq-xojaligida-innovatsiyalar-va-yashil-otishni-targib-qilmoqda - https://www.eeas.europa.eu/delegations/uzbekistan/women-students-promote-innovation-and-green-transition-agriculture-help_en?s=233 - https://www.eeas.europa.eu/delegations/uzbekistan/talaba-ayollar-yevropa-ittifoqi-va-bmttd-yordamida-qishloq-xojaligida_uz?s=233 - https://www.eeas.europa.eu/delegations/uzbekistan/%D1%81-%D0%BF%D0%BE%D0%B4%D0%B4%D0%B5%D1%80%D0%B6%D0%BA%D0%BE%D0%B9-%D0%B5%D0%B2%D1%80%D0%BE%D0%BF%D0%B5%D0%B9%D1%81%D0%BA%D0%BE%D0%B3%D0%BE-%D1%81%D0%BE%D1%8E%D0%B7%D0%B0-%D0%B8-%D0%BF%D1%80%D0%BE%D0%BE%D0%BD-%D1%82%D0%B0%D0%BB%D0%B0%D0%BD%D1%82%D0%BB%D0%B8%D0%B2%D1%8B%D0%B5-%D1%81%D1%82%D1%83%D0%B4%D0%B5%D0%BD%D1%82%D0%BA%D0%B8-%D0%BF%D1%80%D0%BE%D0%B4%D0%B2%D0%B8%D0%B3%D0%B0%D1%8E%D1%82_ru?s=233 |
|  | Study tour to get Italian experience on Operational Groups | - https://dunyo.info/ru/site/inner/uzbekistan_i_italiya_narashtivayut_sotrudnichestvo_v_oblasti_znaniy_i_innovatsiy_v_selyskom_hozyaystve-K9z - https://dunyo.info/cyrl/site/inner/ozbekiston__italiya_bilan__qishloq_hozhaligida_bilim_va_innovatsiyalar_so%D2%B3asida_%D2%B3amkorlikni_kengaytiradi-sOj - https://www.agro.uz/02062023-3/ - https://www.agro.uz/ru/02062023-3/ - https://t.me/undpuzbekistan/1379 - https://twitter.com/UNDP_Uzbekistan/status/1663864707873140742?s=20 - https://www.facebook.com/UNDPUzbekistan/posts/pfbid02UYaqoNWUq2PJ52ZSFX1RPd81kS7CMxYwHP6pdx7BAzmCDGFzxmjQPw5ssVwz25rGl - https://www.undp.org/uz/uzbekistan/news/ozbekiston-delegatsiyasi-italiya-qishloq-xojaligi-tizimi-bilan-tanishdi - https://www.undp.org/ru/uzbekistan/news/delegaciya-uzbekistana-oznakomilas-s-uspeshnym-opytom-selskokhozyaystvennoy-sistemy-italii - https://www.undp.org/uzbekistan/news/delegation-uzbekistan-learns-best-practices-agricultural-system-italy - https://dairynews.today/uz/news/qishloq-xo-jaligi-mutasaddilari-italiyada-bo-ldilar.html |
|  | Exhibition of Innovation Group on cotton production in Kuva district | - https://t.me/undpuzbekistan/1463 - https://twitter.com/Ivana_Zivkovic_/status/1667830063704727552?s=20 - https://t.me/eu4uz/6746 |
|  | Festival of Life Science in Tashkent. | - https://twitter.com/UNDP_Uzbekistan/status/1669649504641904640?s=20 - https://www.eeas.europa.eu/delegations/uzbekistan/%D0%B4%D0%B5%D0%BD%D1%8C-%D0%B5%D0%B2%D1%80%D0%BE%D0%BF%D1%8B-%D1%84%D0%B5%D1%81%D1%82%D0%B8%D0%B2%D0%B0%D0%BB%D1%8C-%D0%BF%D0%BE-%D1%81%D0%BB%D1%83%D1%87%D0%B0%D1%8E-30-%D0%BB%D0%B5%D1%82%D0%B8%D1%8F-%D0%BF%D0%B0%D1%80%D1%82%D0%BD%D0%B5%D1%80%D1%81%D1%82%D0%B2%D0%B0-%D0%BC%D0%B5%D0%B6%D0%B4%D1%83-%D0%B5%D1%81-%D0%B8-%D1%83%D0%B7%D0%B1%D0%B5%D0%BA%D0%B8%D1%81%D1%82%D0%B0%D0%BD%D0%BE%D0%BC_ru?s=233#top - https://timesca.com/uzbekistan-and-the-eu-celebrate-30-years-of-mutually-beneficial-cooperation/ - https://daryo.uz/en/2024/05/10/eu-uzbekistan-to-mark-30-years-of-partnership-with-grand-festival-and-concert-in-tashkent - https://t.me/undpuzbekistan/1505 - https://www.facebook.com/UNDPUzbekistan/posts/pfbid04UZ5CFGQqTso5qtSxmQgemftSbAi3o93p14mcErtwDg59EhV6uQKMtNkPh5R1F6tl?__cft__[0]=AZV6aG0n5BVX-EtME6-elAAlVIrHlrFRVUSLmM85szIHwK9LD97ws8WhpUokXeZDNJ_8dLh_uG5YHityou_fvBu16mgGtFUVLcyuAf5ThJlT0SBLtEqMeK2HU8FE6hlN7ZOihofyFfHeazsYioxQWC_N7WOTNwVyYiAunxPHR4EX9yfLB7_604W_GjXFP0HS25v1-1Z057J_siTXUhmHHsXF&__tn__=%2CO%2CP-R - https://www.linkedin.com/posts/undp-uzbekistan_euagrin-agrinnovation-climatesmartagriculture-activity-7186369553398980609-XICB/?utm_source=share&utm_medium=member_desktop - https://x.com/UNDP_Uzbekistan/status/1780602594890760340 |
| 14. | Growing cotton in Fergana (12.09.2023) | - https://www.undp.org/ru/uzbekistan/news/fermery-ferganskoy-oblasti-osvaivayut-innovacionnye-metody-vyraschivaniya-ustoychivykh-k-vysokim-temperaturam-i-vodnomu-strescu - https://www.instagram.com/p/CxnNUF6tfgm/?img_index=1 - https://t.me/undpuzbekistan/2001 - https://bit.ly/3EUh6cB - https://bit.ly/456rHvu |
| 15. | Promoting climate-resilient agriculture in the Aral Sea region in the partnership with Japan (12.09.2023) | - https://www.undp.org/uzbekistan/press-releases/empowering-self-reliance-government-japan-provides-2-million-usd-promote-climate-resilient-agriculture-aral-sea-region - https://t.me/undpuzbekistan/1850 - https://bit.ly/48eGF5p - https://www.instagram.com/p/CxFertQopin/?img_index=2 - https://tashkenttimes.uz/national/11676-empowering-self-reliance-government-of-japan-provides-2-million-usd-to-promote-climate-resilient-agriculture-in-the-aral-sea-region - https://daryo.uz/en/2023/09/12/undp-and-japan-join-forces-to-revitalize-aral-sea-region-with-climate-resilient-agriculture-project - https://www.facebook.com/UNDPUzbekistan/posts/pfbid02XAAk1o5PVWrHxPRKbHxcDPZ1PkND7WTRZfvHPYLZDzrAh5TM1bzfs3bkcpuFVUfRl?__cft__[0]=AZW31v0VLXpJbSVIm0OgJtnvEM98e2nxyziADJeODHLG4c6XdbdcqL3xFpYUVLyHqPaPQPQ53h7LMouOcbL00gWuEnOLoJeMASrz6hUJhuqw3jtrOsOw4kZnI518vKv9EcqzYwvWyLcud2HFVVOX5sZYUTpLxXlcARV9Bezb6umnWNqV7AMHcDAnMdJehlvrtLueAEjgdmSFBF9FQlcV2Ev1&__tn__=%2CO%2CP-R |
| 16. | Forum empowering Rural Women in Agriculture (11.10.2023) | - https://www.undp.org/ru/uzbekistan/press-releases/proon-es-i-pravitelstvo-uzbekistana-provodyat-forum-po-rasshireniyu-prav-i-vozmozhnostey-selskikh-zhenschin-v-selskom - https://www.instagram.com/p/CyQjIXptYug/?img_index=7 - https://www.eeas.europa.eu/delegations/uzbekistan/eu-undp-and-government-uzbekistan-host-forum-empowering-rural-women-agriculture_en?page_lang=uz&s=233 - https://daryo.uz/en/2023/10/12/undp-eu-and-uzbekistan-convene-forum-for-empowering-rural-women-in-agriculture - https://www.facebook.com/UNDPUzbekistan/posts/pfbid0zWZDYCttFsxhxnMqbuhy2AoWC9pfgpZhBvsLNJvfaHgZiJ4LgsQ6vAD44sASYwMml?__cft__[0]=AZW0UngROdidzKX5H74fcu-4tiEXGdoV3VybAA1gGpsJR07tETOLVI-huvb6u_aKKJ42AJvb0pocqMDKtsM1wppXnAN4uwExv6qtAO5XvtBKp1uObfBePkancBgsUgIwQq9tUErLkePnsLIao2ZIIQX1Obq-ZYX5GdFwtuVyMIxRxAcMixXBqo091LaXizxvKT6tDbF2zJ86g5UDvotAkJGG&__tn__=%2CO%2CP-R - https://uza.uz/uz/posts/ayollarning-qishloq-xozhaligidagi-imkoniyati-kengaymoqda_530580 - https://www.gazeta.uz/ru/2023/10/13/agro/ - https://uza.uz/uz/posts/bugungi-qishloq-ayollarining-hikoyalari-elektron-kitobga-zhamlandi_528904 |
| 17. | World Food Forum on Science and Innovation (25.10.2023) | - https://www.undp.org/uzbekistan/press-releases/uzbek-students-participated-world-food-forum-science-and-innovation - https://t.me/undpuzbekistan/2323 - https://www.fao.org/countryprofiles/news-archive/detail-news/en/c/1654475/ - https://www.uzdaily.uz/en/post/84105 - https://www.instagram.com/p/Cy2jE8zIz8k/?img_index=1 - https://www.facebook.com/UNDPUzbekistan/posts/pfbid0iLDtUtDHhsTqTvsQYanFh1cmiR2Q3ybXYLsberzeD9L5rzzb4FYqhheGcZ3Xdvw5l?__cft__[0]=AZUL_czzH8TvCevkc9MGVNJVR4ZMCIUY_nt47OHJqqB8xmL7U7yAIlNtumLFIxoDXRMdp8GvKZAFspea4xCk6RQf1x7BOQn3J7QXLjJkD8CPohFmeevAgF5IzhZkBPrekQ-HoFNJLpAztD8Ff-mE6nQ3HYAXtqdV8ThZKMiQ3T0oRxBLFbn1dKNvUzBqyYhDQep9zhrmCyo1Z28ksLARxcph&__tn__=%2CO%2CP-R |
| 18. | Wheat verities launched by Innovation group in Kashkaradya (23.11.2023) | - https://www.undp.org/uzbekistan/press-releases/first-pasta-made-climate-resilient-and-water-saving-durum-wheat-varieties-launched-innovation-group-kashkadarya - https://t.me/undpuzbekistan/2582 - https://www.facebook.com/UNDPUzbekistan/posts/pfbid02XsERPEVkPvvFjy1FTZeDWBXkzNMcCVRrBRi4MfWBfPe6TfnutQpqvEikifDXmK9cl?__cft__[0]=AZV558eNoLfVBG0ncShf8zYeAWOiNanXeFkEYcKvc71N43Z0vzV5tNV6vk6Iv-QGMY5gbdta1ZHDzivIWbcEuW5UePLV41pTdG5cRDytWK6SQVzJ84BgGRcaSZVKHzQNTUKfBK1KBnAOpe8D947BfHN2iT_U2ooywSei_HQL0yt8NJIKhGAoGsihVjzNp7S4vtCpNCXCl4r-XGmrvuWGPrcy&__tn__=%2CO%2CP-R - https://www.instagram.com/p/Cz_V4dbtaNC/?img_index=1 - https://www.eeas.europa.eu/delegations/uzbekistan/first-pasta-made-climate-resilient-and-water-saving-durum-wheat-varieties-launched-innovation-group_en?s=233 |
|  | CREA visiting to research institutes | - https://t.me/AKIS_milliy_markaz/4914 |
| 19. | Supporting sustainable fisheries production (05.03.2024) | - https://www.undp.org/uzbekistan/press-releases/european-union-and-undp-handover-fish-laboratory-and-farm-equipment-support-sustainable-fisheries-production - https://t.me/undpuzbekistan/3115 - https://www.facebook.com/UNDPUzbekistan/posts/pfbid02r2TLazoMSA8eDzjhgzxNALzL3Z9SUrCF6AF9Rut9MWf3x9JxqEGAsbewoB7sRgakl?__cft__[0]=AZWNGeEgFCfkvtkj8I3cRCeud2p7JD6YsNqdm3WgWPAYfHbtUc3CicTbVCiiTlpIPln1vSeDVWBRbAxg0yjQyfr-Jnr5TO2y6OtQwAHLVGOlKvFQgkAH_tIWDA7F1viqAIRz4M5O67ZXAYs9hoSUkxCDxvaQe4vP__F9QZagK539XF1aRMgYFB3HxPLj0WEHc6i9tx1N4yWwVzjGbx8Kq_jI&__tn__=%2CO%2CP-R - https://www.eeas.europa.eu/delegations/uzbekistan/european-union-and-undp-handover-fish-laboratory-and-farm-equipment-support-sustainable-fisheries_en - http://tashkenttimes.uz/national/12590-eu-and-undp-handover-of-fish-laboratory-and-farm-equipment-to-support-sustainable-fisheries-production - https://uza.uz/uz/posts/baliqchilikka-grant-mablagi-zhalb-etildi_576637 - http://www.fis-net.com/fis/worldnews/search_brief.asp?l=e&id=128763&ndb=1&monthyear=&day=&country=0&df=1 - https://www.publicnow.com/view/1B9450348A2C40FCA77800F686F5883D099FE7F5 - https://www.uzdaily.uz/ru/post/84121 - https://www.agro.uz/baliqchilik-ilmiy-tadqiqot-institutiga-barqaror-baliqchilikni-qo-llab-quvvatlashga-xizmat-qiluvchi-zamonaviy-uskunalar-topshirildi/ - https://x.com/EU_Tashkent/status/1764971712712425542 - https://t.me/uzagroministry/19159 - https://www.gazeta.uz/oz/2024/03/06/fish-farming/ - https://flic.kr/s/aHBqjBgxju |
| 20. | EU and UNDP Support Sustainable Pasture Management (26.04.2024) | - https://www.undp.org/uzbekistan/press-releases/european-union-and-undp-handover-fish-laboratory-and-farm-equipment-support-sustainable-fisheries-production - https://www.linkedin.com/posts/nripankadas_eu-and-undp-support-sustainable-pasture-management-activity-7189839282423902209-P6LP - https://t.me/undpuzbekistan/3336 - https://www.facebook.com/UNDPUzbekistan/posts/pfbid0QxKgaTmFnLFi3r5PPpNbTgryMQGiyctw8sfwg1xhkeyuqNy8aaeeVTcyuTpML1MKl?__cft__[0]=AZXhgsXe9Hb1TfOagKKS8kC00uciZS31dM8ulFPIGLB8-Ufqx2urYOb8FUl0lhJvEtfSCQzz7p-6IIVfTJpgUx3MXDM4qu38ehXYw3QaUhXTXqNh5oyPlpe-4Pc7hbBTehqyVjAIbcRZSUvLTjAXsFgABzJ5bhnhOqa4ZheAD0J4nbasdaGfSHtjKcxR8u8N4rn2EdCuvmeW5wSB_P9S71s3&__tn__=%2CO%2CP-R - https://www.instagram.com/p/C6N5yGutIgI/ |
| 21 | Activities of IG on drip irrigation | - https://t.me/TGminwater/28047 - https://t.me/TGminwater/27501 - https://t.me/TGminwater/26550 - https://t.me/TGminwater/21946 |
| 22. | Insights from a Study Tour to Italy (19.06.2024) | - https://www.undp.org/uzbekistan/blog/exposure-future-agriculture-insights-study-tour-italy - https://www.facebook.com/UNDPUzbekistan/posts/pfbid0JYu7fBukQB9PhGBphZpYTUrA8DWn8jVWPi4vFZzUnycqs8ktPyXfi4ED6bderEw9l?__cft__[0]=AZVZq_LyMmUOop4UlOVwaMEsnYpkRqbfSCmzW3-VxlrnCTyIQrpFOPbLJT8zcL6ii0iLCCq7jOtwBbX_1H16OZ4Hjom1b09MJSizyHxfzq4VpzfKWz2DMKohxiudquG5yuac6XWZIEdVQdoefedf3kOGLpkrTxh90j9mJm0GwvRdOPEVw_uS33Bp-eUu50psGT4chZKtHsjqC5507OCxov7H&__tn__=%2CO%2CP-R - https://www.google.com/url?sa=i&url=https%3A%2F%2Fwww.undp.org%2Fuzbekistan%2Fblog%2Fexposure-future-agriculture-insights-study-tour-italy&psig=AOvVaw36C-GHNH0uagKNJmrT-IkQ&ust=1720691223141000&source=images&cd=vfe&opi=89978449&ved=0CBQQjhxqFwoTCOCQmMCYnIcDFQAAAAAdAAAAABAR - https://www.google.com/search?sca_esv=951454d4e44807ae&rlz=1C5CHFA_enUZ1041UZ1041&sxsrf=ADLYWIIxEdfkZGHLAYK8rKW5-UJxrUcAaA:1720604671746&q=Exposure+to+the+Future+of+Agriculture:+Insights+from+a+Study+Tour+to+Italy&udm=2&fbs=AEQNm0BcPEQzCJo6339NzIm4bfyT-yKz0qpF1PY0VZZiwpyc5Fy2x_WiIIRkUdPozKzPOJ86E6XEWUtcSaBtuXM_5Q9walHpq9P0ZqMirV8RvuucPJ1aJd9aniea4nSbm4Ud66VL-nKlz6Qt_T9QLxXoelG_ogYwl68LLvOVIF63yqmAuyX8nri5zM7NqGjpwyX4x4VKqeAp8vv_hwfpZD_Sa9y9clUZpJ79TS7cnsk2OSwXzmsVSj0&sa=X&ved=2ahUKEwiek4jyl5yHAxWPCBAIHWHmCOMQtKgLegQIDxAB&biw=1440&bih=788&dpr=2#vhid=65AVQCg72QgO4M&vssid=mosaic:~:text=%D0%9F%D0%BE%D0%B8%D1%81%D0%BA%20%D0%BD%D0%B0%20%D0%B8%D0%B7%D0%BE%D0%B1%D1%80%D0%B0%D0%B6%D0%B5%D0%BD%D0%B8%D0%B8-,Exposure%20to%20the%20Future%20of%20Agriculture%3A%20Insights%20from%20a%20Study%20Tour%20to%20Italy%20%7C%20United%20Nations%20Development%20Programme,-%D0%9F%D0%B5%D1%80%D0%B5%D0%B9%D1%82%D0%B8 - https://www.instagram.com/p/C8Yu3IZsmEf/?img_index=5 |
| 23. | CREA experts visiting fields | - https://t.me/AKIS_milliy_markaz/6936c - https://t.me/AKIS_milliy_markaz/5055 |
| 24. | Trainings conducted at Southern Agriculture Institute | - https://t.me/AKIS_milliy_markaz/6206 - https://t.me/uzagroministry/22020 - https://t.me/AKIS_milliy_markaz/6191 |
| 25. | Support for young innovators in agriculture (14.06.2024) | - https://www.undp.org/uzbekistan/press-releases/european-union-and-undp-support-young-innovators-agriculture-0 - https://daryo.uz/en/2024/06/15/eu-undp-backing-empowers-uzbekistans-youth-innovators-in-agriculture - https://t.me/undpuzbekistan/3592 - https://www.facebook.com/UNDPUzbekistan/posts/pfbid0EtNnioCKnxdseuMRjoKxHezxSrgPJEEZrZcoPCTU8bLUEPCPdDuQryZtSkED5QrHl?__cft__[0]=AZWTIh5VO-0IFYqBqaVNw3RpFBihXjqO9M70AFBC1xIWU-Fz-oZGF5HaWA-nDwPQcEU5NqHL5EgZKLix3wmTigyHpsemFuaLhLiuyOrO7oV_N-8nfUFTa9aNSaDYRccS3lZJSEdqdsOpLIOXUfdQ3RbPSUiVcnO4ZNamNw20viYKJ9kVARBwLcUVqQYSweRIwZ-qh7iihNwVyVFiOm1unTlQkjr4mQvTxJ3wf2X3ZItDXQ&__tn__=%2CO%2CP-R - https://www.instagram.com/p/C8NGP2UKyeR/ - https://www.eeas.europa.eu/delegations/uzbekistan/european-union-and-undp-support-young-innovators-agriculture_en?s=233 - https://t.me/uzagroministry/23082 - https://uza.uz/uz/posts/yoshlar-va-innovacion-qishloq-xozhaligi-korik-tanlovi-goliblari-aniqlandi_607482 |
| 26. | Could UNDP's Innovation Groups Set a New Standard for Speeding Up Climate Change Response? (blog) (17.07.2024) | - https://www.facebook.com/share/p/18H9hMJGEC/?mibextid=VhDh1V - https://www.undp.org/uzbekistan/blog/could-undps-innovation-groups-set-new-standard-speeding-climate-change-response - https://www.undp.org/uz/uzbekistan/blog/bmttdning-innovatsion-guruhlari-iqlim-ozgarishiga-qarshi-choralarda-yangi-usullarni-joriy-etishi-mumkinmi - https://www.undp.org/ru/uzbekistan/blog/mogut-li-innovacionnye-gruppy-proon-ustanovit-novyy-standart-dlya-uskoreniya-mer-reagirovaniya-na-izmenenie-klimata |
| 27. | Filed visits by international evaluator | - https://t.me/TGminwater/28050 |
| 28. | Activities of IG on bioremediation salinity soils | - https://academy.uz/uz/news/mikrobiologiya-instituti-olimlaridan-innovatsion-guruh-tuzildi-ularning-izlanishlari-va-harakatlari-natijalari-bilan-tanishtiramiz - https://t.me/ANRUz/19524 - http://www.youtube.com/@BiosalRemedy - http://www.instagram.com/biosalremedy - https://t.me/biosalremedy - https://microbio.uz/index.php/vse-novosti/158-zr-fa-mikrobiologiya-instituti-tomonidan-2023-jil-9-sentyabr-kuni |
| 29. | Launching of Drip Irrigation IG (08.08.24) | - https://t.me/c/1821407615/3988 - https://x.com/undp_uzbekistan/status/1821541115381899557?s=52&t=vokxLlm9ZBQ11wynPTR8Dw - https://x.com/eu_tashkent/status/1821543782262976761?s=46&t=vokxLlm9ZBQ11wynPTR8Dw - https://t.me/c/1821407615/3992 - https://t.me/c/1821407615/4003 - https://t.me/c/1821407615/4004 - https://www.gazeta.uz/ru/2024/08/08/drip-irrigation/ - https://t.me/c/1821407615/4013 - https://uza.uz/posts/623379 - https://uza.uz/uz/posts/tomorqa-erlar-uchun-quyosh-energiyasidan-quvvat-oladigan-tomchilatib-sugorish-tizimi-ishga-tushirildi_623378 - https://uzreport.news/society/tomorqa-yerlar-uchun-quyosh-energiyasidan-quvvat-oladigan-tomchilatib-sug-orish-tizimi-ish - https://www.uzdaily.uz/ru/post/88312 - https://podrobno.uz/cat/obchestvo/es-i-proon-zapustili-sistemu-kapelnogo-orosheniya-na-solnechnykh-batareyakh-dlya-domokhozyaystv-akku/ - https://tafsilar.info/obshhestvo/es-i-proon-zapustili-sistemu-kapelnogo-oroshenija-na-solnechnyh-batarejah-v-tashkentskoj-oblasti/ - https://uz.kursiv.media/2024-08-09/es-i-proon-zapustili-sistemu-orosheniya-v-tashkentskoj-oblasti/ - https://akipress.com/news:790024:EU,_UNDP_launch_solar-powered_drip_irrigation_system_for_local_households_in_Uzbekistan/ - https://tashkenttimes.uz/national/13498-eu-and-undp-launch-solar-powered-drip-irrigation-system-for-local-households - https://glosema.group/news/eu-and-undp-have-jointly-introduced-a-solar-powered-drip-irrigation-system-to-support-local-households-in-uzbekistan/ - https://agroworld.uz/en/news/eu-and-undp-launch-solar-powered-drip-irrigation-system-in-tashkent-region - https://gov.uz/oz/agro/news/view/18373 - https://www.eeas.europa.eu/delegations/uzbekistan/eu-and-undp-launched-solar-powered-drip-irrigation-system-local-households-1_en#:~:text=The%20new%20drip%20irrigation%20system,the%20support%20of%20solar%20panels |
| 30. | Advantages of innovation approaches against whitefly (encarsia) | - https://t.me/mtrkuzofficial/193275 |
| 31. | Introducing of green economy by Innovation groups | - https://tiiame.uz/news?id=6939 |
| 32. | Presentation of the results of cooperation between EU-AGRIN and SRI | - https://t.me/AKIS_milliy_markaz/8310 |
| 33. | Trainings conducted by Civitta | - https://t.me/qashqadaryo_trk/39406 - https://t.me/qashqadaryo_trk/39394 |
| 34. | Blog about EU-AGRIN project by EUD Key challenges that the project helps to address | - https://www.eeas.europa.eu/delegations/uzbekistan/eu-agrin-supporting-inclusive-transition-%E2%80%9Cgreen%E2%80%9D-economy-agri-food-sector-and-developing-%E2%80%9Cclimate_en?s=233 - https://www.eeas.europa.eu/delegations/uzbekistan/eu-agrin-%D0%BF%D0%BE%D0%B4%D0%B4%D0%B5%D1%80%D0%B6%D0%BA%D0%B0-%D0%B8%D0%BD%D0%BA%D0%BB%D1%8E%D0%B7%D0%B8%D0%B2%D0%BD%D0%BE%D0%B3%D0%BE-%D0%BF%D0%B5%D1%80%D0%B5%D1%85%D0%BE%D0%B4%D0%B0-%D0%BA-%C2%AB%D0%B7%D0%B5%D0%BB%D0%B5%D0%BD%D0%BE%D0%B9%C2%BB-%D1%8D%D0%BA%D0%BE%D0%BD%D0%BE%D0%BC%D0%B8%D0%BA%D0%B5-%D0%B2-%D0%B0%D0%B3%D1%80%D0%BE%D0%BF%D1%80%D0%BE%D0%B4%D0%BE%D0%B2%D0%BE%D0%BB%D1%8C%D1%81%D1%82%D0%B2%D0%B5%D0%BD%D0%BD%D0%BE%D0%BC-%D1%81%D0%B5%D0%BA%D1%82%D0%BE%D1%80%D0%B5-%D0%B8_ru?s=233 - https://www.eeas.europa.eu/delegations/uzbekistan/eu-agrin-qishloq-xo%E2%80%98jaligi-va-oziq-ovqat-sektorining-%E2%80%9Cyashil-iqtisodiyot%E2%80%9Dga-inklyuziv-o%E2%80%98tishini-qo_uz?s=233 |
| 35. | Visit of our UN country team to wheat & pistachio projects 06.09.2024 | - https://x.com/SabineMachl/status/1831977068650987733 - https://t.me/c/1821407615/4838 - https://uza.uz/uz/posts/bmt-delegaciya-qashqadaryoda_633147 - https://t.me/c/1821407615/4919 |
| 36. | Presentation of Fiber cotton in Kashkadarya region | - https://t.me/qashqadaryo_trk/40240 |
| 37. | The European Union and UNDP Visit Innovation Groups Dedicated to Agricultural Development In The Fergana Region 16.10.2024 | - https://www.undp.org/uzbekistan/press-releases/european-union-and-undp-visit-innovation-groups-dedicated-agricultural-development-fergana-region - https://www.eeas.europa.eu/delegations/uzbekistan/european-union-and-undp-visit-innovation-groups-dedicated-agricultural-development-fergana-region_en?s=233 - https://x.com/ToivoKlaar/status/1846534808681189490 - https://x.com/ToivoKlaar/status/1846238946851791011https://x.com/UNDP_Uzbekistan/status/1846513481618481387 - https://tashkenttimes.uz/national/13875-eu-and-undp-officials-visit-innovation-groups-dedicated-to-agricultural-development-in-fergana-province - https://newslineuz.com/article/1178107/ - https://t.me/eu4uz/8191 - https://t.me/undpuzbekistan/4290 - https://www.uzdaily.uz/en/the-eu-and-undp-visit-innovation-groups-dedicated-to-agricultural-development-in-the-ferghana-region/ https://x.com/UNDP_Uzbekistan/status/1846410167883022650 - https://x.com/UNDP_Uzbekistan/status/1846457443595047297 - https://www.instagram.com/eudeluzb/reel/DBMGe48KAYu/ - https://www.instagram.com/eudeluzb/reel/DBJbBE2KgOL/ - https://www.facebook.com/photo/?fbid=966638152173430&set=a.307582398079012 - https://t.me/Fargona_trk/20358 - https://t.me/Fargona_trk/20370 |
| 38. | Training-workshop on water usage efficiency in Agriculture 23.10.2024 | - https://t.me/uzagroministry/30546 |
| 39. | Professional Awareness Session on Practical Project Implementation and Execution Monitoring 26.10.2024 | - https://t.me/uzagroministry/30769 |
| 40. | UzAgroExpo – International Agro-Industrial Exhibition 27.11.24 | - https://t.me/undpuzbekistan/4702 - https://t.me/AgroOlamUz/44706 - https://www.instagram.com/p/DC4FrEPKl80/?utm_source=ig_web_copy_link - https://www.linkedin.com/posts/undp-uzbekistan_euagrin-ugcPost-7268257107555069953-fZKq?utm_medium=ios_app&rcm=ACoAADZHO-sBhEULNOL7jn-FmKRVSYk6vDg9Rt0&utm_source=social_share_send&utm_campaign=copy_link - https://x.com/undp_uzbekistan/status/1861764126026105066?s=46&t=vokxLlm9ZBQ11wynPTR8Dwhttps://x.com/undp_uzbekistan/status/1861764126026105066?s=46&t=vokxLlm9ZBQ11wynPTR8Dw - https://t.me/undpuzbekistan/4734 - https://t.me/AgroOlamUz/44778 - https://t.me/uzagroministry/32189 |
| 41. | Project board meeting and Project results 17.12.2024 | - https://x.com/UNDP_Uzbekistan/status/1869020972038385939 - https://www.linkedin.com/posts/undp-uzbekistan_results-of-the-euagrin-project-in-2024-activity-7274785914617221121-iDp-?utm_source=share&utm_medium=member_ios - https://www.facebook.com/share/p/1DYnaM2Udh/ - https://t.me/undpuzbekistan/4973 - https://youtu.be/fnYE-aJcffI |
| 42. | Study Tour to Germany 18.01.2025 | - https://t.me/undpuzbekistan/5114 - https://www.facebook.com/story.php?story_fbid=1021610383326860&id=100064337243345 - https://www.instagram.com/reel/DE63jaSqSqv/?igsh=MXYxejhnZjRnY25lZw== - https://uza.uz/uz/posts/katta-taassurotlarga-boy-safar_684682 - https://kknews.uz/uz/231439.html - https://t.me/SamVMINukusfilial/19261 - https://t.me/SamVMINukusfilial/18704 - https://www.youtube.com/watch?v=iXSXLO06Ylg |
| 43. | Agro-Zamin Stars Student Competition 03.03.2025 | - https://t.me/undpuzbekistan/5424 - https://www.facebook.com/100064337243345/posts/1055681513253080/?_rdr - https://www.instagram.com/p/DGu5iItqvA2/ |
| 44. | UNDP Talks: Inspiring Stories of Resilience and Poverty Reduction 19.03.2035 | - https://www.undp.org/uzbekistan/press-releases/undp-talks-inspiring-stories-resilience-and-poverty-reduction - https://t.me/undpuzbekistan/5520 - https://t.me/gazetauz/53122 - https://www.gazeta.uz/ru/2025/03/25/undp-takls/ - https://www.uzdaily.uz/en/undp-in-uzbekistan-launches-a-unique-platform-for-sharing-success-xtories-in-the-fight-against-poverty/ - https://www.linkedin.com/posts/undp-uzbekistan_undptalks-activity-7308464934059659264-_CnE - https://www.linkedin.com/posts/xadicha-suyarova_yesterday-i-had-the-honor-of-attending-undp-activity-7308363226369458176-vgJW |
| 45. | Meeting between UNDP Regional Director Ivana Živković and Agriculture Minister Ibrokhim Abdurakhmonov 08.04.2025 | - https://t.me/undpuzbekistan/5648 - https://uza.uz/en/posts/a-new-step-toward-food-security_707415 - https://t.me/uzagroministry/36174 - https://gov.uz/oz/agro/news/view/44385 |
| 46. | Italian experts meeting on AKIS Monitoring and Evaluation in Uzbekistan 10.04.2025 | - https://t.me/info_uzfk/39640 |
| 47. | Life Sciences Festival in Tashkent 24.04.2025 | - https://www.linkedin.com/posts/hrvojehorvat_the-15c-generation-and-why-they-give-activity-7323634349877153792-MG8d?utm_medium=ios_app&rcm=ACoAADZHO-sBhEULNOL7jn-FmKRVSYk6vDg9Rt0&utm_source=social_share_send&utm_campaign=copy_link - https://iau.uz/life-science-festival-2025/ |
| 48. | Study tour to Italy 08.06.2025 | - https://t.me/uzagroministry/36926 - https://gov.uz/ru/agro/news/view/60482 - https://t.me/undpuzbekistan/6148 - https://agroworld.uz/ru/novosti/delegaciq-uzbekistana-izuchaet-peredovoj-opt-zhivotnovodstva-v-italii - https://www.facebook.com/UNDPUzbekistan/posts/-ozbekiston-delegatsiyasi-italiyada-chorvachilikning-ilgor-tajribasini-organmoqd/1137767871711110/ - https://www.instagram.com/p/DKzCFUCq3zQ/ - https://t.me/UzstandardChannel/12227 |
| 49. | Eco Expo Central Asia 19.06.2025 | - https://t.me/undpuzbekistan/6176 - https://www.uzdaily.uz/en/international-exhibition-eco-expo-central-asia-2025-opens-in-tashkent/ - https://t.me/ecogovuz/46929 - https://gov.uz/oz/eco/news/view/62424 - https://t.me/ecogovuz/46938 - https://gov.uz/oz/eco/news/view/62503 - https://t.me/ecogovuz/46943 - https://gov.uz/oz/eco/news/view/62613 |
| 50. | 100th of the Irrigation and Water problems Scientific Research Institute 20.06.2025 | - https://t.me/TGminwater/37934 - https://t.me/TGminwater/37935 - https://youtu.be/BF1BKUDLuhc?si=vUwE8Oe3-8oJiwLv - https://t.me/undpuzbekistan/6190 - https://t.me/joyida_informatsion/6937 |
| 51. | Launching of Youth Innovation Hub at Zangiota 26.06.2025 | - https://go.undp.org/UDB - https://t.me/undpuzbekistan/6237 - https://www.tvsspo.uz/zangiota-tumani-agrotexnologiyalar-texnikumida-eu-agrib-loyihasi-doirasida-yoshlar-innovatsion-markazi-ochildi/ - https://xs.uz/uz/post/bmt-taraqqiyot-dasturi-va-evropa-ittifoqi-tomonidan-zangiota-agrotekhnologiyalar-tekhnikumida-yoshlar-innovatsion-markazi-ochildi - https://uza.uz/oz/posts/bmttd-va-yevropa-ittifoqi-tomonidan-zangiota-agrotexnika-texnikumida-yoshlar-innovatsion-markazi-ochildi_734587 - https://gov.uz/oz/agro/news/view/64129 - https://t.me/uzagroministry/37158 - https://gov.uz/ru/agro/news/view/64129 - https://t.me/Zangiotatumanihokimligi/51902 |

Publications could be found through below link

https://drive.google.com/drive/folders/1m9TUVzO_306vlucV69LlRmHhnZT6MUXY?usp=sharing

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.