| EXPECTED OUTPUTS | OUTPUT INDICATORS | BASELINE |  | ## Implementation of targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value | Year 2021 | Year 2022 | Fact 2022 | Year 2023 | Fact 2023 | Up to date | Remarks |
| Output 1. Capacities of targeted local communities increased to identify local needs and to develop plans of actions, i.e., Community Development Plans (CDP), by identifying priority infrastructures for investments that have optimum and long-term benefits through an inclusive community engagement (including women and youth) and consultation with sub-regional and local authorities. | 1.1 Number of target communities for development of CDPs identified in Karakalpakstan, Khorezm, Bukhara and Navoi regions | 0 | 0 | 170 | 170 | 0 | 0 | 170 | 170 communities were identified by the Ministry of Economy and Finance in four pilot regions. The initial list of the communities has been revised by the PIU and submitted to the UNDP only in late 2022. |
|  | 1.2 Number of community members and representatives of local authorities trained on CDP process and community needs assessment, disaggregated by gender, as well as on improving rural economy, such as knowledge sharing on agriculture & new farming methodologies, irrigation technologies, and strengthening home industries related to women empowerment. | No capacity in target communities to identify priorities for community development | 0 | 2000 | 4005 | 1800 | 3303 | 7308 | In 57 communities conducted community mobilization trainings for 3303 rural population (1219 women and 2084 men): - Karakalpakstan – 925 people trained (230 women and 695 men) - Khorezm region - 1208 people trained (418 women and 790 men) - Bukhara region - 698 people trained (355 women and 343 men) - Navoi region - 472 people trained (216 women and 256 men) In total 7308 people trained (2736 women and 4572 men) in community mobilization trainings in 2021-2023 years. |
|  | 1.3 Number of CDPs developed and implemented. | No CDPs in targeted communities | 0 | 12 | 113 | 55 | 57 | 170 | 1. 40 Cluster CDP for 170 communities developed: - Karakalpakstan – 12 Cluster CDPs - Khorezm region - 12 Cluster CDPs - Bukhara region - 10 Cluster CDPs - Navoi region - 6 Cluster CDPs 2. Integrated Community Development Plan Manual developed. 3. CDP presentations for 170 communities and 20 working groups |
|  | 1.4 Number of sub-national plans that reflect CDPs | No explicit links of sub-national development plans/budget and CDPs | 0 | 0 | 0 | 0 | 0 | 0 | The consulting company ERGO ANALYTICS recruited to develop 15 socio-economic and environmental maps of the 4 selected pilot districts and developed methodology with questionaries. o Tahyatash district, Karakalpakstan o Urgench district, Khorezm region o Vobkent district, Bukhara region o Karmana district, Navoi region |
|  | 1.5 Number of target communities for development of CDPs for second phase identified in Samarkand, Kashkadarya, and Surkhandarya regions |  | 0 | 0 | 0 | 200 | 157 | 157 | Validation assessment of 157 communities in Samarqand, Kashkadarya and Surkhandarya regions conducted by M-Vector company and presented its results on November 29, 2023, to the Ministry of Economy and Finance, IsDB, UNDP and regional authorities. 38 communities recommended to be changed out of 157 communities |
|  | 1.6.1 Number of community members and representatives of local authorities trained on CDP Organization of workshops with community participation (around 1500) and development of 200 cluster based CDPs. 1.6.2. Number of CDPs developed and implemented | No capacity in target communities to identify priorities for community development | 0 0 | 0 0 | 0 0 | 1500 200 | 0 0 | 0 0 | The Sustainable Rural Development Project Phase II's project documentation has been completed and received approval from both the Ministry of Economy and Finance and the Islamic Development Bank (IsDB). The consulting firm conducted validation assessment of 157 communities and presented to the IsDB, Ministry of Economy and Finance and UNDP its results. |
| Output 2: Capacities of local architecture-design institutions and regional departments of architecture and construction are enhanced for development of improved engineering designs and master plans that are responsive to the sustainability aspects (economic, operational, and environment sustainability), innovative energy and water efficient, low carbon technology, climate resilient and gender responsive, and promoting local resources. | 2.1 Number of assessment reports of the impact of the ecological disaster on agriculture and local social infrastructure, including recommendations on strategies and architectural methods and other innovative approaches. | No research on adverse impact of the ecological disaster on social infrastructure and identification of locally relevant sustainable environmentally friendly solutions. | 0 | 0 | 0 | 1 | 2 | 2 | 2 researches conducted, and 1 guidance developed: - Analytical report on analysis on adverse impact of the ecological disaster and environment degradation on agriculture and rural population developed. - Methodological guidance “Application of the best foreign practices to overcome the consequences of environmental degradation on the agricultural sector and rural population” developed. - Report Capacity assessment of the local architectural-construction environment (e.g., regulations, technical capacities of architects/engineers) regarding adopting and implementing climate resilient solution developed. |
|  | 2.2 Number of beneficiaries of trainings on energy efficient construction materials and low carbon technology, economic and agriculture infrastructure, men/women breakdown % of trainees incorporate energy efficient construction materials and low carbon technology in developing plans for constructing social, economic and agriculture infrastructure in rural areas | 0 of relevant professionals trained on energy efficient construction materials and low carbon technology | 0 0 | 150 0 | 0 0 | 150 0 | 655 0 | 655 0 | In total 655 local specialists (143 women and 512 men) were trained in four pilot regions: - Training "Modern approaches in the development of master plans" - 118 participants (13 women and 105 men) - Training "Use of energy-efficient and low-carbon technologies in construction" - 120 participants (13 women and 107 men) - Training "Agroecological" - 219 participants (65 women and 154 men) - Training "Modern Low Carbon Air Conditioning. Design. Installation and maintenance" - 102 participants (32 women and 70 men) - Training "Use of "AutoCAD" and "3DMAX" engineering software” - 96 participants (20 women and 76 men) |
|  | 2.3 Number of piloted energy-efficient and water efficient, new agriculture & farming technologies, ozone-friendly and low GWP (global-warming potential) based technologies | Limited number of energy and water efficient, new agriculture and farming technologies -efficient, ozone-friendly and low GWP based technologies available in supported communities | 0 | 0 | 0 | 1 | 1 | 1 | 4 agro-meteostations delivered and installed in four regions: - Kipchoq mahalla, Amudarya district, Karakalpakstan - Gayrat mahalla, Honka district, Khorezm region - Katta karvonboshi mahalla, Shofrikon district, Bukhara region - Arabhona mahalla, Navbahor district, Navoi region |
| Output 3: Capacities of construction, architecture-design and public service delivery sector are increased on the local governance and community participatory mechanism in the planning and implementation of rural development programs and initiatives by using digital transformation, gender-sensitive approaches, innovative IT solutions, including development of digital infrastructure and information systems to ensure better access to social facilities and services in rural areas, including green redevelopment/regeneration and increasing resilience in post-disaster situations (such as COVID-19 and other pandemics). | 3.1 Status of the assessment report of local capacities to implement government digitalization agenda | Limited evidence on local capacity to implement government digitalization agenda | 0 | Assessment methodology developed | 0 | Process started | 3 reports | 3 reports | 3 reports and 3 concept notes developed: - Analytical report on assessment of the existing information technology infrastructure and plans for their development in rural areas developed. - Report on capacity assessment of the rural government institutions and digital literacy of the rural civil servants - Report on capacity assessment of the rural schools and digital literacy of the school students and teachers - Concept note for pilot implementation of a wireless intelligent automation system for precision irrigation based on the internet of platform in agriculture developed. - Concept note for pilot implementation of flagship Li-Fi technology to expand Internet connectivity in schools developed. - Concept note on Community Resource center developed and approved. |
|  | 3.2 Number of trainings on digital literacy/skills completed, gender disaggregated number of beneficiaries trained (e.g., # of doctors in rural areas trained on using telemedicine solutions to treat and advise patients | Limited local knowledge of local professionals on digital solutions | 0 | 50 | 0 | 75 | 96 | 96 | 96 rural specialists were trained in four pilot regions, whereas 26 women and 70 men |
|  | 3.3 Number of community members and youth trained on rural areas relevant ICT and digital solutions disaggregated by gender, age and location. Number of public schools modernized using ICT and digital solutions. | limited youth and community members ICT and digital literacy | 0 0 | 200 0 | 0 0 | 400 0 | 2098 4 | 2098 4 | In total 2098 community center’s members and rural population trained: - 1755 rural population were trained in four regions, whereas 1059 women and 696 men. - 343 community specialists (khokim’s assistant and youth leaders) were trained whereas 70 women and 273 men. 4 schools modernized and equipped with 60 computers, 4 smart boards and LAN equipment |
|  | 3.4 Number of ICT/digital solutions developed by the Project. Number of beneficiaries in targeted communities who were supported through ICT/digital solutions | no ICT/digital solutions addressing needs of targeting communities, including access to public/social services. no model of a smart community | 0 0 | 0 0 | 0 0 | 0 0 | 2 3425 | 2 3425 | 4 ICT/digital solutions developed and will be implemented in 2024-2025 years: - Community resource center - Smart board and computer classes - Li-Fi technology - Smart irrigation system Number of school students who will benefit from project support |
| Output 4 Local communities are strengthened (including women, youth, elderly, people with disabilities) and national/sub-regional/local government capacities and institutionalization in operation and maintenance of the infrastructure to ensure sustainable functioning. Base line: 0 mechanisms of the project proposed for replication Target: 10 mechanisms of the project proposed for replication | 4.1 # of mechanisms of the project proposed for replication | no well elaborated mechanisms in place supporting Project sustainability | 0 | 0 | 0 | 2 | 4 | 4 | Analytical report on baseline assessment in four pilot regions conducted. 4 mechanisms proposed for replication by the project: - Community mobilization training - CDP development - Community specialists teach population to take public service online. - Community Resource Center |
|  | 4.2 Share of resources mobilized to support replication of Project results and innovations (breakdown down by source, national/international) | No resource mobilization strategy/actions | 0 | 0 | 0 | 0 | 0 | 0 | 2 replications of the project implemented within the project: - Agrometeostations - O Smart boards |
|  | 4.3 Number of people reached through the Project PR campaign % of target communities people covered by the PR and outreach campaign of the project | Limited awareness of targeted communities in support Project results | 0 0 | 0 0 | 0 0 | 3000 25% | 50000 100% | 50000 100% | Project gender-sensitive communication strategy developed and more than 50000 people reached through project PR campaign. 100% of the 170 communities covered by project PR and outreach campaign. |
|  | 4.4 Number of PR/Outreach events promoting the project results and raising awareness among communities | 0 | 0 | 5 | 5 | 25 | 221 | 226 | 221 conducted PR/outreach events (project presentations, trainings, CDP presentations, study tours, quiz, and contest). |
|  | 4.5 Number of publications/articles issued and disseminated widely among partners and mass media | 0 | 0 | 5 | 15 | 15 | 284 | 299 | 284 press-release and publication in national and international mass media prepared and posted |