United Nations Development Programme

Project Document for projects

financed by the various GEF Trust Funds

| Project title: Enhanced Water Security and Community Resilience in the Adjacent Cuvelai and Kunene Transboundary River Basins (PIMS 4756) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country(ies): Angola and Namibia | Implementing Partner (GEF Executing Entity): Global Water Partnership Southern Africa (GWP-SA) |  |  | Execution Modality IGO Execution |  |
| Contributing Outcome (UNDAF/CPD, RPD, GPD): N/A |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Substantial |  |  | UNDP Gender Marker: GEN2 |  |  |
| Quantum Award ID: 1249833 |  |  | Quantum Project ID: 01002406 |  |  |
| UNDP-GEF PIMS ID number: 4756 |  |  | GEF Project ID number: 10565 |  |  |
| LPAC meeting date: 22 March 2022 |  |  |  |  |  |
| Last possible date to submit to GEF: 31 March 2022 |  |  |  |  |  |
| CEO Re-endorsed: 16 April 2024 |  |  |  |  |  |
| Resubmission date: 28 February 2024 |  |  |  |  |  |
| Project duration in months: 66 |  |  |  |  |  |
| Planned start date: 13th May 2024 |  |  | Planned completion date: 12th November 2029 |  |  |
| Expected date of Mid-Term Review (MTR) submission to the GEF: February 2027 |  |  | Expected date of Terminal evaluation (TE) submission to the GEF: February 2030 |  |  |
| Expected Operational Closure Date: 12th August 2030 |  |  | Expected Financial Closure Date: 13th February 2031 |  |  |
| Brief project description: Improved management of water resources, especially the extremes of flood and drought are key elements of the project, which covers the adjacent but quite different transboundary Kunene and Cuvelai basin shared by Angola and Namibia. For the Kunene River Basin, the focus will be on the groundwork required for the sustainable development of the Kunene River which has significant potential for hydropower and irrigation development. This will be achieved through a basin-wide e-flows assessment, the modelling of water resources development and management, a detailed TDA and a long-term IWRM Plan. The IWRM plan will be informed by preliminary results from pilot demonstration projects. For the ephemeral Cuvelai River basin, which is beset by extreme drought and flood, the focus will be on an assessment of groundwater potential, flood management through food risk mapping and the development of a flood early warning systems, and water harvesting. Both aspects will also feature in the proposed pilot demonstration projects. As with the Kunene River basin, a detailed TDA will be developed and used to update the existing preliminary IWRM Plan. Five-year Investment programmes for both basins will be drawn up. The proposed project will undertake a suite of other activities designed to strengthen joint management and planning capacity and practices at the transboundary basin level. These activities include strengthening of CUVECOM and the Kunene PJTC, strengthening of the CUVECOM and eventual joint basin Secretariat to support IWRM implementation at the basin level; addressing critical information gaps that prevent effective IWRM implementation; developing information management tools to consolidate information and present it to policy makers and other audiences to raise awareness of issues critical to the sustainable management of the two basins. |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| GEF Trust Fund grant |  |  | USD 11,167,890 |  |  |
| - Total Budget administered by UNDP |  |  | USD 11,167,890 |  |  |
| - Total confirmed co-financing to this project not administered by UNDP |  |  | USD 165,450,801 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | USD 176,618,691 |  |  |
| Signatures: |  |  |  |  |  |
| Signature: print name below |  | Agreed by Government Development Coordination Authority - Namibia |  |  | Date/Month/Year: |
| Signature: print name below |  | Agreed by Government Development Coordination Authority - Angola |  |  | Date/Month/Year: |
| Signature: print name below |  | Agreed by UNDP |  |  | Date/Month/Year: |

# I	Table of Contents

I	Table of Contents	3

II	Development Challenge	6

III	Strategy	11

IV	Results and Partnerships	15

V	Project Results Framework	38

VI	Monitoring and Evaluation (M&E) Plan	45

VII	Governance and Management Arrangements	48

VIII	 Financial Planning and Management	54

IX	Total Budget and Work Plan	60

X	Legal Context	72

XI	Risk Management	72

XII	Mandatory Annexes	76

Annex 1: GEF Budget Template	72

Annex 2: Project map and Geospatial Coordinates of project sites	73

Annex 3: Multi Year Work Plan	77

Annex 4: UNDP Social and Environmental Screening Procedure (SESP)	81

Annex 5: UNDP Risk Register	101

Annex 6:  Overview of Project Staff and Technical Consultancies	106

List of Table and Figures

Table 1: Project Risk Management Matrix	24

Table 2: Gender Action Plan	32

Table 3: Summary of Co-financing	51

Figure 1: Summary of Theory of Change for the Overall Project	11

Figure 2: Project Organisation Structure	46

Acronyms

| BGR | Bundesanstalt für Geowissenschaften und Rohstoffe (Federal Institute for Geosciences and Natural Resourceschanges) |
| --- | --- |
| CEO | Chief Executive Officer |
| CNA | Central North Area |
| CO2 | Carbon dioxide |
| FFEWS | Flash Flood early Warning System |
| CO2 | Carbon dioxide |
| DSS | Decision support system(s) |
| EWS | Early warning system |
| FFEWS | Flash Flood early Warning System |
| FSP | Full Sized Project |
| GABHIC | Gabinete Para a Administração da Bacia Hidroeléctrica do Cunene |
| GAP | Gender Action Plan |
| GEF | Global Environment Facility |
| GEFSEC | Global Environment Facility Secretariat |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit (German Society for International Cooperation) |
| GWP-SA | Global Water Partnership Southern Africa |
| HR | Human Resources |
| IW | International Waters |
| IWRM | Integrated Water Resources Management |
| LDCF | Least Developed Countries Fund |
| MSP | Medium Sized Project |
| MW | Megawatt(s) |
| MAWLR | Ministry of Water, Livestock and Rural Development |
| MTR | Mid-term review |
| MWE | Ministry of Water and Environment |
| NAP | National Action Plan |
| NBI | Nile Basin Initiative |
| NGO | Non-governmental Organisation |
| OKACOM | Okavango River Basin Commission |
| ORASECOM | Orange-Senqu River Basin Commission |
| PJTC | Permanent Joint Technical Commission |
| PIF | Project Identification Form |
| PIR | GEF Project Implementation Report |
| PCU | Project Coordination Unit |
| POPP | Programme and Operations Policies and Procedures |
| ProDoc | Project Document |
| PPG | Project Preparation Grant |
| RBO | River Basin Organisation |
| SADC | Southern Africa Development Commission |
| SAP | Strategic Action Plan |
| SDG | Strategic Development Goal |
| SESP | Social and Environmental Screening Procedure |
| SGP | Small Grants Programme |
| SLM | Sustainable land management |
| STAP | GEF Scientific Technical Advisory Panel |
| TB | Transboundary |
| TDA | Transboundary Diagnostic Analysis |
| TE | Terminal Evaluation |
| TOR | Terms of Reference |
| BPPS NCE | Bureau for Policy and Programme Support, Nature, Climate and Energy |
| UNAM | University of Namibia |
| UNDP | United Nations Develop Programme |
| USGS | United States Geological Services |

# II	Development Challenge

The Cuvelai River takes its source in the hills of the northern part of the catchment at over 1100 masl, and more than 400 metres above the rest of the basin, which is otherwise extremely flat. The limits of the basin to the north are clear due to the relatively steep slopes. Demarcation in other parts of the basin is less clear.

The Kunene River rises in the central highlands of Angola at elevations of up to 2000m masl near the town of Huambo. This area, the “planalto”, receives relatively high amounts of rainfall (1000 to 1500 mm), and is one of the continent’s “water towers”, hosting the headwaters of other important rivers such as the Kuanza, Queve and Kubango. The area has become a densely populated agricultural area. The Upper Kunene is characterised by highlands with gentle rolling hills separated by broad shallow valleys in the central Angolan highlands. The Middle Kunene consists of rolling hills, whilst the Lower Kunene exhibits mountainous topography and semi-arid to arid conditions. Near the river mouth, the river crosses the Namib desert.

The Cuvelai basin is the most densely populated part of Namibia. This is a product of soils that are comparatively fertile and the ready availability of freshwater in shallow wells. While alluvial sediments make up substantial areas of the Central Drainage, Cuvelai Delta and the western Shana sub-basin zones, these are really only concentrated within the drainage channels themselves. These areas are very important to most people in the Cuvelai in providing fertile soils for crops. Together with fresh water in shallow wells, it is these soils that attracted people to settle and farm here 500 to 600 years ago. Rainfed farming predominates with pearl millet (mohangu) the main subsistence cereal crop. Irrigation is limited to alongside the Kunene Transboundary Water Transfer Scheme canal between Olushanja Dam and Oshakati and the Etunda Agricultural project near Ruacana. Cattle are moved between dry winter season grazing grounds and wet season areas around the homes of their owners. The winter grazing grounds were always in areas where few people lived but this system is increasingly under threat because wintering grounds have been lost, or the grazing available per unit animal has been severely reduced (Mendelsohn, 2015). Many of the grazing areas have been expropriated by fenced farms for the exclusive use of individual cattle owners.

In the Upper Kunene, the dominant crops are maize and beans and to a lesser extent sweet potato, with livestock playing a complementary role in local farming systems, being used for animal traction and as a source of milk. In the Middle Kunene, which is mostly semi-arid, farming systems are generally based on livestock as well as crops with a greater range of crops (maize, manioc, sorghum, millet and cowpea being grown. The semi-arid and arid lower section of the Kunene is dominated by subsistence pastoralism, supplemented by crop cultivation on the Kunene Riverbank and around springs during the rainy season. Subsistence livelihoods are complemented by the collection of firewood, the production and sale of charcoal, the gathering, consumption and sale of natural food and medicinal plants, the hunting of wild animals, as well as artisanal inland fisheries in rivers and lakes.

Namibia's Etosha National Park centred around the vast Etosha salt Pan and designated as a game reserve in 1907, is one of Africa's major wildlife sanctuaries. Large floods only reach the pan every 7 to 10 years and the biodiversity of the park is entirely dependent on seasonal flooding events. The park is home to abundant wildlife, making it Namibia’s number one tourist attraction. The Lower and Middle Kunene basin is home to various existing or emerging national parks, communal-area conservancies and community forests that offer significant ecotourism attractions and services within and near conservation areas.

During wet years in the Cuvelai basin fisheries are important. Tens of thousands of fish belonging to about 45 species are to be found in the various channels in years of high rainfall (Mendelsohn, Fish in the Cuvelai Basin, 2018). By contrast, fish are effectively absent during dry years. A high proportion of the fish biomass is harvested by people in the Cuvelai, thus providing food to several. What happens in the dry season is not well understood. Fisheries is an important activity along the entire length of the perennial Kunene River. In both countries, fish farming is viewed as an important contributing sector to food security. Pilot aquaculture projects have been initiated, some of them within the basin in the Omusati, Oshana and Omaheke regions. In Namibia, The Aquaculture Act 18 of 2002 came into effect in 2003 followed by the quick implementation of aquaculture government farms, offices, and community projects in almost every corner of the country. Initially uptake was poor, but more recently a move towards a bottom-up community-based approach is proving more successful. Aquaculture production has increased from less than 100 tonnes in 2000 to more than 600 tonnes today. The technical expertise is available but there are significant challenges in management, provision of capacity-building and uptake by some communities. In general, interest is greater in the Cuvelai basin than in the Kunene.

- Production levels were similar in Angola but are growing. The 2012-17 NDP predicted production of 60,000 tonnes from the country’s aquaculture programme.  There is significant private sector in the sector aimed at higher levels of commercialization. Although this activity is currently outside of the basin, there is no reason why the experience gained could be replicated in the basin.

- Hydropower is generated along the course of the Kunene River, with a current total installed capacity along the river of around 350 MW, and a potential capacity of over 2 300 MW. All of the major hydraulic structures in the basin are in Angola, with the exception of the Ruacana Plant, which straddles the border with Namibia. Many sites for large hydropower schemes have been identified and studied both in Angola and especially along the joint border where the river slope is at its steepest.

Current demands on the surface water resources of the Kunene River are relatively limited. Within Angola there are long-standing plans for the development of both hydropower and irrigation but very little of this has materialised. The main consumptive demands on the surface waters of the Kunene River are for municipal water supply (in both countries) and some very limited irrigation. The majority of the municipal demand is in Namibia (in the Cuvelai Basin). The existing agreement between the governments of Angola and Namibia allows for an annual abstraction of 180 Mm3/annum (3% of the mean annual runoff), but less than a third of this is currently utilized. More significant is the non-consumptive demand of hydropower. Partial regulation of flows (and some generation of hydro-electricity) is currently carried out at the Gove Dam in the upper reaches of the catchment and to a much lesser extent at the Matala Weir further downstream (where hydroelectricity is generated (installed capacity of 40MW). Additional electricity is generated at the Calueque weir and Ruacana scheme on the border (240MW). Further development of hydropower is likely to create a more regulated flow, which means increased opportunities for irrigation development and water supply. The impact on environmental flows is less clear since in its natural state the Kunene River is highly variable and nearly stops flowing in its lower reaches during the dry season. Evaluating the potential impact on ecological flow requirements will need to take into account the impacts of increased regulation, increased evaporation, a reduction in the mean annual runoff, bearing in mind that these may not be cumulative. In terms of the water-food-energy-environment nexus, it is clear that the development of hydropower can bring significant improvements in water, food and energy security and that minimizing negative environmental impacts will depend on the overall design of developments basinwide and then way in which they are operated. Transboundary cooperation and coordination will be critical.

The situation in the Cuvelai basin is very different. There are no significant surface water abstraction schemes for municipal water supply since flows are ephemeral and unpredictable.  The option of creating large-scale intra or inter-seasonal storage is limited by a lack of suitable dam sites in the generally very flat terrain. In both countries floodwater harvesting has been practised for decades, in Angola generally at the very localised level, in Namibia at a slightly larger scale. Given the highly variable nature of the Cuvelai hydrology there is no significant impact on the overall flow regime of the river, but the contribution to water and food security can be significant. Developments in the Cuvelai Basin are not anticipated to have negative environmental impacts and no significant impact on the hydrological regime.

- The global environmental and/or adaptation problems, root causes and barriers that need to be addressed (systems description)

- Global Environmental (and Transboundary) Problems and their Immediate Causes

- Increasing water scarcity and hydrological variability, exacerbated by climate change

This is a critical issue for both basins but with quite different impacts. The Cuvelai River basin is very dry, prone to both floods and droughts.  The basin supports a large rural population whose livelihoods are, in most cases, directly dependent on agriculture and the availability of water. This means that the basin population is particularly vulnerable to the highly variable nature of the hydrological patterns of the Basin.

Rainfall in the Cuvelai basin varies in many ways: across the Basin, from north to south in volume and reliability, within the season and from season to season. The Variability increases southwards as the average annual precipitation decreases so this adverse combination of low but highly variable precipitation makes water scarcity a particularly serious challenge in the southern part of the basin. In some years, including the 2018/19 season, the rains have completely failed resulting in almost zero crop production.

In the Kunene basin, variability increases even more rapidly southwards and westwards. In addition to its impacts on the livelihoods of subsistence farmers, as well as wildlife within the Skeleton Coast Park (Namibia) and the Parque Naçional de Iona (Angola), water scarcity has significant impacts on hydropower generation in the Kunene basin. The Kunene River mouth supports a small wetland area that is important for migrating birds.

Immediate causes

The natural variability in precipitation, combined with lack of intra-and inter-seasonal storage, under-utilization of groundwater (combined with insignificant conjunctive use of surface and ground water), are the immediate causes of water scarcity in in the Cuvelai basin. This is offset by water transfers from the Kunene basin, but many settlements and rural inhabitants are not covered by the distribution systems.

In contract, there is significant water storage infrastructure in the Kunene basin but the focus of this storage has been in support of hydropower generation rather than water supply for the basin’s population. Population density in the Kunene basin is lower than in many parts of the Cuvelai, but water scarcity is an issue for those that don’t live close to the river. There is a large level of dependence on groundwater in these areas.

The need for the comprehensive monitoring of climate and water resources and the sharing of information has never been greater, as also the need to improve systems that can provide early warning of climate-related disasters. Other measures and interventions such as rainfall and flood water harvesting, and more and better planned groundwater abstraction are required to fill the increasing gap between water demands and water availability. All of these require a coordinated, integrated and sustainable approach to planning and implementation at a transboundary basin scale.

- Land degradation

Land degradation has led to reduced ecosystem productivity, contributing to widespread poverty, poor health and increase of the highly vulnerable population in many parts of the two basins. It is important to stress the very strong dependence of the population on the available natural resources. When these resources become degraded as a result of over-exploitation, there is a tendency to try and exploit the resources even further beyond the limits of sustainability, supporting a vicious cycle that becomes increasingly challenging to break out of. Climate change will add additional pressure to the land resources.

Immediate causes

While there is insufficient data on land degradation and desertification, in particular on spatial distribution, it is clear that the most serious land degradation occurs in the hilly headwaters of both basins in Angola where poor farming practices and deforestation result in increased erosion. The loss of vegetation in the headwaters increases sediment load (impacting on reservoir storage) and leads to reduced base flows and higher flood peaks. Climate variability and changes also have a profound effect on accelerating erosion and land degradation. The immediate causes are, to a large extent, related to agriculture and livestock farming and deforestation. Deforestation is generally as a result of sourcing of fuelwood. This is a particular issue in the northern parts of both basins. Bush encroachment is also an issue in some parts of both basins, in particular in the southernmost parts of the Cuvelai Basin.

The loss of Oshimolo as the last major grazing area for cattle owned by Oshiwambo people may have significant consequences. Pressures on grazing in national parks, commonages and perhaps on freehold land are likely to increase in Namibia and local conflicts may arise, including tensions between Namibia and Angola.

- Water quality degradation

The quality of the Kunene River from source to mouth is relatively unpolluted and is considered to be good. There are areas of the Cuvelai Basin where water quality is naturally poor as a result of salinity and fluoride. Measurements are lacking, so it is not possible to say whether either of these are deteriorating.

Immediate causes:

The immediate causes of water quality degradation are the erosion which contributes to high sediment loads in both the Kunene and Cuvelai Rivers and the discharge of untreated wastewater/sludge directly into the river systems. A major source of pollution is the lack of sanitation and efficient wastewater treatment facilities. While the larger settlements such as Oshakati, Ongwedive and Ondangwa have wastewater treatment facilities, there is a challenge with the disposal of waste from septic tanks and pit latrines.

- Root causes:

Climate variability and water scarcity in both basins is being amplified by increasing population pressures and climate change.

While land degradation, can be addressed to a large extent through addressing some of the immediate causes, it is clear that there are root causes lying behind the increasing number of farmers and livestock in the basins. A combination of poor farming practices, lack of i) access to credit, ii) markets, iii) opportunities for commercialization, iv) adding of value through agro-processing, together with v) a lack of alternative (off-farm) livelihoods is some of the root causes that need to be addressed in a holistic manner. Experience has shown that the planning, design and implementation of complex community-based interventions, can best be achieved through a bottom-up approach supporting small-scale (across a limited number of communities and a manageable area), but holistic, pilot demonstration projects which yield both environmental and livelihood benefits, and which can easily be scaled up. Local Government and/or CUVECOM, Gabhic and the PJTC will have a key role to play in terms of technical support, contract management, organising experience-sharing and peer-to-peer networking in support of scaling up.

Security, or lack thereof, of land tenure is also considered in general as a root cause for land degradation.  When farmers or land-users do not have a long-term tenure over the land they utilize, their willingness and motivation to invest in long-term, sustainable land management practice is low.

- Barriers to be addressed:

The following five limitations that are currently prevalent in one or both of the two basins are identified as barriers to be addressed through this project in order to promote and strengthen the basin-wide cooperation between the two basin states, with a particular focus on the joint planning capacity of the basin by both the PJTC and CUVECOM for their sustainable future:

- Limited institutional, technical, financial capacity for joint planning and management at the transboundary basin level.

- Limited data, information, and knowledge of the resources and ecosystems in the basin shared at the basin level.

- Lack of a long-term strategy and policy planning efforts at the basin levels, knowledge-based and supported by strong political commitment.

- Limited engagement of various stakeholders and resources users in the planning and implementation of the IWRM in the basin in order to address global and local challenges the basin is facing.

- Linked to 4 above, there is inadequate cross-sectoral participation in the planning and implementation of interventions. It is a fact that both the PJTC and CUVECOM have their roots in the water ministries but many of the key required actions are concerned with agriculture, energy and the environment.

It is important to stress the dire consequences of the continued baseline, bearing in mind that business as usual does not mean that no actions are being taken, only that these actions are not adequate to address the issues and challenges and to remove the barriers. Looking in a bit more at these barriers:

- Lack of knowledge (limited data and analysis), especially for i) the critical headwaters (part of the Angolan central highlands water tower), where there is a need to have an economic evaluation/accounting of ecosystem services and ii) the potential for increased groundwater use (as standalone and as part of conjunctive use with surface water).

There is an ever-narrowing gap between the water available and the demand imposed. This is a result of an increasing population, increasing per capita demand, climate change and land degradation induced increased variability of water resources including longer drought periods and increased flood peaks.

Without a better knowledge of both the surface and groundwater resources (in space and time), it is not possible to plan for this demand to be met. Without a much-improved understanding of the groundwater potential (and hence also the potential for conjunctive use), the only way to meet demands in the Cuvelai basin will be through ever-greater transfers from the Kunene. Not only is the infrastructure for these transfers very expensive compared to the localised development of groundwater, they take away from the water in the Kunene River available for hydropower generation.

Environmental degradation, in particular land degradation in the headwater areas and pollution especially in densely populated areas

Degradation of the upper parts of the catchments, in particular the Kunene, has been exacerbated by a rapid increase in the population over the last two decades. Without the rapid and widespread uptake of improved farming and watershed management practices catchment degradation will result in the erosion of valuable topsoil and reduced crop yields, increased flooding, reduced baseflows and lowering groundwater levels. This degradation can take on an exponential form under the baseline scenario.

Weak governance at both the national levels (especially in the Angolan portions of the basins where there is both weak technical and institutional capacity), and at the transboundary levels where the Cuvelai Watercourse Commission is relatively new and the proposed Kunene Commission not yet in place.

Flooding in both catchments will continue to increase under the baseline scenario. The increased magnitude of floods is driven by both climate change and land degradation.

Without adequately addressing land degradation and implementing knowledge-based climate change adaptation strategies, the frequency and magnitude of extreme floods will continue to rise with both an economic cost and loss of life.

- Limited stakeholder participation at the community level,

Although there is transboundary cooperation already in place, without strengthening, the management of the basin’s water and natural resources will not be adequately catchment-based. Without a fully integrated basin wide approach, management will be inefficient, and development limited.

Transboundary cooperation in the Kunene, through the PJTC (and earlier versions of this body) has been in existence for several decades and has contributed to the development of large-scale infrastructure on the Cuvelai River. However, there is a need to extend the scope of this cooperation beyond the development of water transfers and hydropower schemes.

Transboundary management in the Cuvelai basin is relatively new yet movement of the local populations across the border occurs on a continuous basis. Without the improved collection, sharing and combined analysis of data and a combined effort to address the barriers to development the challenges of the energy-food-water-environment nexus will become increasingly difficult to address.

# III	Strategy

- Theory of Change

The theory of change starts from an analysis of key barriers to strengthening cooperation between the two countries across both countries and proposes an intervention strategy to be followed in order to reach the proposed project outcomes, which in turn will contribute to long-term impacts beyond the direct influence of the project. The theory of change for the project is summarised in Figure 3.

- Barriers

The headline barriers were indicated in the previous section of the report. They are further broken down and indicated in the first column of Figure 3.

- Actions and Outcomes

- To achieve a situation of improved water security and a strong water-energy-food nexus, the following actions are required and proposed:

Building a substantial and solid knowledgebase, critical in contributing to the removal of Barrier #2.   Achieving robust IWRM Plans for both basins is dependent on adequate knowledge.

Developing stakeholder-driven and bilaterally endorsed IWRM Plans for both basins which provide clear and agreed actions that address the root causes constraining water (and associated food and energy) security (Components 1 and 2). This will contribute to the removal of Barrier #3.

Building strong governance (Component 3 and Component 4, which is specific to Angola) to ensure the effective implementation of the IWRM plans. The effective implementation of the IWRM Plans will require coordination capacity (vertical, horizontal and transboundary), financial resources, a good monitoring system and reporting mechanism on progress made.  The project aims to support CUVECOM and PJTC to build these capacities in their Secretariat. This will contribute to addressing Barrier #1.

Implementing community-based pilot projects for key intervention areas in order to facilitate stakeholder support and scaling up (Component 5), which will contribute to addressing Barrier #4.

Intermediate States and Impacts

- As indicated in Figure 3, three main overarching impacts are identified.

Impact 1: Improved Water for livelihood and sustainable socio-economic development across the two basin states, balancing resource demands and protection of freshwater ecosystems.

Impact 2: Confidence amongst stakeholders and their support for sustainable development including contributing to SDGs 1, 2, 6 ,7, 8, 13, 15, as well as to enhanced water security in freshwater systems.

Impact 3: Sustainable transboundary partnerships and cooperation, including progress towards SDG 5 (Achievement of gender equality and empowerment of all women & girls)

Alignment with GEF Focal Areas / Impact Programs

- The project is fully aligned with Objective 3 of the International Waters Focal Area: Enhance water security in freshwater ecosystems in the GEF-7 Programming Directions.  The proposed project interventions will be relevant to all three areas of strategic actions under this objective.  Angola and Namibia have demonstrated their firm commitment to the transboundary cooperation through the establishment of the Cuvelai Watercourse Commission (CUVECOM) and the PJTC for the Kunene River Basin.  Through the proposed project interventions, the countries will aim to enhance water security in freshwater ecosystems through advance information exchange (IW 3-5) and through regional and national cooperation on shared freshwater resources (IW 3-6).  While investments in water, food, energy and environmental security (IW 3-7) are limited at this foundational phase of the GEF support, the investments made during this foundational phase are expected to generate knowledge and the required enabling environment in terms of a strengthened transboundary water governance institution with adequate capacity for joint planning, development, management and implementation of its mandate, including effective replication and upscaling in the future of accumulated best practices from the current phase.

D1-D4: Driver to support transition from outputs to direct outcome: Strong ownership at local, national & transboundary levels for integration of findings into consolidated Plan, including scaling up of pilots. D5,D6: Strong desire at national (D5) & transboundary (D6) levels, including political buy-in to support cooperation between states

Figure 1: Summary of Theory of Change for the Overall Project

A1: Good buy-in by local stakeholders of IWRM practices & mechanisms;  A2: Willingness of both countries & institutions to contribute to data collection & sharing of data;  A3: Governments male provisions for support to CUVECOM & PJTC (RBOs); A4: High level of political will to support IWRM practices ; Willingness to invest in monitoring & stakeholder consultation

Project Objective: To enhance water security in the adjacent transboundary Cuvelai and Kunene river basins through planning and actions based on an improved knowledge base and transboundary cooperation together with interventions on the ground

Changes to Incremental Reasoning

Incremental Cost Reasoning and Expected Contributions from the baseline investments

The proposed regional project, to be financed by GEF, would not be successful without the baseline investments and political commitments made by the countries.  These have successfully established both the PJTC for the Kunene River basin and CUVECOM for the Cuvelai River basin. The PJTC has been running since 1990 (when the agreement was renewed between Angola and Namibia), and before. While CUVECOM Agreement was signed only in 2014, an interim secretariat was established with the support of GIZ for some years.  The CUVECOM secretariat is now supported through contributions from both countries.

Building upon the baseline investments from the member states, GEF support will enhance the institutional, operational and technical capacity of the CUVECOM and PJTC/eventual KUNENE Commission and ensure its/their sustainability. This will contribute to the long-lasting transboundary benefits.  GEF support will also result in a long-term strategic document (IWRM Plan) for the PJTC and the Kunene River basin and a new, improved IWRM Plan for the Cuvelai basin, which will include a focus on the second 5 years of the plan (2025-2029). These plans will guide any future investments.  by the national governments, by international cooperating partners, and/or by the private sector in the basins so that they will be aligned with strategic priorities agreed for the basins.

Building upon the rapid assessment carried out in 2015 with GIZ support, together with other work, a first IWRM Plan for the Cuvelai Basin was finalized in 2019, with detailed interventions outlined for 2020-2024. This Plan acknowledged the many gaps that need to be filled and included actions for filling them. CUVECOM requested GEF support through UNDP to develop the TDA. The TDA will not only fill some key knowledge gaps identified during the drawing up of the first IWRM Plan, but also include the Causal Chain Analysis and the future development scenario analysis.

There is currently no transboundary IWRM Plan for the Kunene basin. The rapid assessment and preliminary work on an IWRM plan currently being carried out with support from GIZ, will provide a basis for the TDA requested by the PJTC. As with the TDA for the Cuvelai basin, the TDA will include the Causal Chain Analysis and, using an updated version of the existing basin wide water resources model, investigate a range of future development scenarios.  GEF support will fill priority knowledge gaps at the basin level (mostly through the activities under Comp 2) to collect key data to be included in the TDA.  Just like for the Cuvelai basin, the TDA for the Kunene transboundary river basin would not be completed without the baseline investments made by the countries.

Strategy / Approach

Improved water resources (including flood) management, including the equitable allocation of water between upstream and downstream areas and among urban and rural users, is a fundamental goal for the future water management of both the Kunene and Cuvelai Basins.  For sustainable economic growth to take place, it is important that there is a stable and secure water supply for all those across the two basins. Interventions proposed to be financed by the GEF will cover the incremental costs of the actions required to foster transboundary IWRM through stronger basin-wide cooperation in both basins, and are targeted to realize various transboundary benefits, building upon the baseline activities to be carried out by basin states individually or sometimes collectively, or through initiatives financed by other partners supporting the CUVECOM and the PJTC.

To complement the TDA-SAP process, the proposed project will undertake a suite of other activities designed to support the delivery of transboundary benefits and contribute to strengthening joint management and planning capacity and practices at the transboundary basin level, facilitated by CUVECOM and the PJTC, and others. These activities include: strengthening the capacities of both countries and the CUVECOM (eventual Joint) Secretariat to support IWRM implementation at the basin level; addressing critical information gaps that prevent effective IWRM implementation; developing information management tools to consolidate information and present it to policy makers and other targeted audiences to raise understanding and awareness of issues critical to the sustainable management of the two basins; implementing sustainable land management activities at a pilot scale with the goal of reducing land degradation at the pilot sites and demonstrating the link between SLM activities and reduced sedimentation, as well as promoting the replication and up-scaling of land degradation control activities in the basin; and supporting knowledge exchange and information sharing with other RBOs in the region to support the effective and efficient delivery of project results.

Benefits.

The project will directly address the need for multinational cooperation supported by CUVECOM and the PJTC. The project, together with co-financing partners, will strengthen CUVECOM and the PJTC’s institutional, technical and coordination capacity so that they can jointly function effectively as a hub for harnessing, coordinating and channelling political and economic interests from both public and private sectors in the basin.  In addition, both countries will significantly benefit from capacity building activities planned at both regional and national levels.

The project will promote effective IWRM (SDG 6, target 6.5) at the transboundary, national and local levels.  It will ensure the inclusion of the improved knowledge of the transboundary aquifers across both basins, and particularly in the Cuvelai basin, and climate information, produced by the co-financing activities, into the TDAs for both basins. This will support the promotion of the conjunctive management of surface and groundwater resources as well as climate-resilient basin planning in both basins. The project also will support the participating countries to carry out informed policy dialogue at the basin level to address increasing water, energy, food demands in the future and how these needs can be met in an environmentally sustainable and socially inclusive manner for the basin’s population.  The tangible contributions to be made by GEF investment to this policy dialogue are the development of the future water resources development scenarios and the inclusion of the findings from the future development scenarios in the Kunene and Cuvelai TDAs.  The project also will support the countries to establish the ecological flow of the Kunene River basin, understanding of which can provide environmental safeguards to the riverine ecosystems (another GEB expected from the project) as well as social safeguards to those populations whose livelihoods depend on the healthy and productive ecosystems in the basin.

Other benefits expected to accrue to the basins’ population include: reduced fish morbidity and spread of disease due to improved water quality monitoring, which will improve livelihoods and food security; benefits for downstream agriculture and fisheries, as well as water storage and hydroelectric infrastructure, from reduced levels of sedimentation; increased levels of fisheries production through management of e-flows; and finally, increased financing of priority interventions in the Basin based on the SAP and its associated financing strategy, which will result in increased availability of water for that is essential for economic development and livelihoods improvements in the basin over the long term.

Covid Analysis / Strategy

The COVID-19 pandemic may impose restrictions on working arrangement, movements, procurement, supply chains, local market, etc., which will all impact operational efficiency of the project.  It may have impacts on security stability in rural areas or in fragile states where there existed limited resilience to absorb such unpredicted and unprecedented external shocks. The level and type of risks will change as the COVID-19 pandemic situations change in particular location in the basin as well as in two countries.  The project will regularly screen or COVID-19 risks through available tools and mechanisms (e.g. Social and Environmental Safeguards, Stakeholder Engagement and M&E Plans implementation) and update Quantum Project Risk Register to develop and adjust mitigation actions to deal with changing risks.

# IV	Results and Partnerships

- Expected Results

Project Objective: To strengthen the water security and resilient livelihoods of the populations in the adjacent Kunene and Cuvelai river basins through improved transboundary and conjunctive water resources management.

Component 1: Strengthening the transboundary and conjunctive water resources management in the Cuvelai River basin

This Component aims at strengthening transboundary and conjunctive water resources management mainly through the strengthening of the knowledge base. Updating the “preliminary” TDA and the existing Cuvelai Basin IWRM Plan will be the main tools used to achieve this.

Outcome 1.1 - Two countries committed to the joint management of the transboundary Cuvelai River basin with a focus on the improved resilient community livelihoods, based on the best available science and knowledge

Despite major knowledge gaps, both countries decided to proceed with the development of a first transboundary IWRM Plan for the next 20 years (2020-2039).  An investment plan for the first five years (up to 2024) was developed in the full knowledge that the plan would need to have considerable flexibility and to be reviewed, revised and updated as the knowledge base is improved. In fact, the plan included several actions specifically aimed at collecting the data for filling gaps, with actions over the first five years focusing on actions of no regret. The proposed TDA production will fill most gaps so that the plan can be updated and revised in 2024 on a much firmer knowledge base. The improved knowledge base in particular with respect to climate, hydrology, water quality, degradation hotspots, socio-economic factors and future development trajectories), will result not only from interventions under this component but also from other ongoing studies.

Output 1.1.1 - Groundwater quality and availability assessed in both countries: A much-improved assessment of groundwater basin-wide is intended to fill a major gap. Knowledge on the quantity, accessibility and quality of groundwater resources is limited.

- Under this output, the project will undertake the following activities:

The assessment will make use of ongoing work and monitoring records in both countries as well as research carried out through the University of Lubango in Angola and the proposed major transboundary study to be carried out by BGR, and collect all the available into a consolidated georeferenced database.

Conduct an initial analysis based on the available mapped data and identify areas for field reconnaissance.

Carry out preliminary field reconnaissance aimed at i) collecting water level and samples from existing boreholes and wells, and preliminary planning geophysical investigations.

Map all new water level and quality data and finalise plan for first round of geophysical investigations.

Carry out geophysical investigation, build and refine models with further geophysical investigations and drilling as may be required.

Output 1.1.2 - Operational water resources model for quantity and flood routing/mapping covering the entire basin: There is a lack of an adequate cross-border understanding of the hydrology, both in terms of surface water resources and flood assessment and risk. As part of the TDA, the knowledge base will be extended to cover the whole basin using the new data collected under the UNDP-LDCF project combined with datasets available in the Namibian part of the basin. The proposed data collection actions in Angola under Component 4 will provide vital inputs in this respect. Activities include:

Better quantifying the surface transboundary water resources of the Cuvelai basin in space and time. This will use all available existing datasets and any new ones collected during the course of the project and will take into account existing and emerging knowledge on climate change.

Setting up the framework for a transboundary flood early warning system (to be detailed for selected communities as a pilot project). This will bring together knowledge and experience on these systems in Namibia and new real-time data collected in Angola.

Output 1.1.3: Revised TDA (existing rapid assessments (equivalent to preliminary TDA) updated, including the Causal Chain analyses (CCA), and emphasis on conjunctive ground/surface water management). All of this work will contribute to the updating of the TDA and IWRM Plan and National Action plans.

- In summary, the TDA will be based on a number of focused activities including:

The assessment of groundwater aimed at:

Consolidating existing knowledge on both sides of the border and any new investigatory work, (Support from Germany/BGR has been secured for further study on the Ohangwena II/Cuvelai aquifer.

Improving existing knowledge through limited field investigations and modelling work

Surface water resources modelling work

Assessment of flood water harvesting in the basin. This will be based on both:

Improving the existing knowledge base, making and inventory of the current state of flood water harvesting from upstream to downstream.

Recommendations for floodwater harvesting approaches at different scales.

Assessment of opportunities for conjunctive use of surface and groundwater. This will include:

  - Assessment of flood water harvesting in the basin. This will be based on both:

Improving the existing knowledge base, making and inventory of the current state of flood water harvesting from upstream to downstream. This should include an assessment of existing approaches used in the two countries (Namibia used artificial recharge for the wellfield that contributes to Windhoek conjunctive use water supply scheme, and has also developed the OMDEL recharge enhancement scheme), elsewhere in the region, and further afield.

  - Recommendations for floodwater harvesting approaches at different scales, taking into account experiences in other basins (via IW Learn for example)

Output 1.1.4:  Operational (development and testing complete) real-time transboundary flood early warning system.

The model will provide preliminary early warning based on forecasts of rainfall. This could result in the issuing of a preliminary early warning aimed at moving communities into a preliminary level of alert.

Preliminary early warnings would be updated and refined using real-time information on actual rainfall falling in the upper parts of the catchment where runoff is generated.

In the event of heavy flood-generating rainfall, real-time notification of rising water levels at the most upstream river gauging stations would be run through the model (automatically and in real-time) to start generating predicted flood levels downstream.

Flood warning messages would be relayed to the flood warning committees at the community level (and the relevant government departments) in the form of text and e-mail messages. It is important that the composition of flood-warning communities is representative of women, the elderly and the youth in order that their concerns and needs are fully taken into account.

Output 1.1.5: The long-term Cuvelai IWRM Plan (2020-2039) endorsed at the ministerial level, the 2nd 5-year IWRM Plan and Investment Plan (2025-2029) developed together with National Action Plans (NAPs).

Based on the completed TDA, the preliminary results of the IWRM demonstrations/community-based projects under Component 5, the project will support CUVECOM in the revision the IWRM Plan.

The updated Plan and associated investment plan will be the focus of a well-organized and publicized roundtable with potential investors and development partners

Identification of potential cooperating partners and donors

Circulation of communication materials including the new IWRM Plan, TDA and results from Pilot demonstration projects

Organisation of Roundtable (Windhoek and Luanda potentially) and issuing of invitations well in advance

Component 2: Strengthening transboundary water resources management with future development scenario analysis in the Kunene River basin

This will be achieved mainly through the strengthening of the knowledge base, and then using it to examine suitable development scenarios which could potentially underpin the IWRM Plan to be developed for the basin.

Outcome 2.1: Two countries committed to the joint management and sustainable development of the transboundary Kunene river basin, based on the best available science and knowledge

While there is no formal transboundary rapid assessment or preliminary TDA of the Kunene basin conducted in the past, the hydrology of the basin as a whole, has been studied and updated on a number of occasions.

Output 2.1.1 - Ecological water requirements at +/- 10 key locations along the river system are investigated and established: The ecological water requirements will be an important to the water resources modelling that will contribute to Output 2.1.1.

- Under this output, the project will undertake the following activities:

Assess and agree on the ecological water requirements methodology that will be used.

Make a rapid assessment from source to sea with the aim of identifying how the river will be broken up in to representative reaches.

Select and agree on the representative reaches to be surveyed and monitored.

Instrument reaches and carry out assessments.

Evaluate the ecological water requirements.

Output 2.1.2 - Future water resources development scenario analyses for planning and establishment of DSS (including linked hydromet) for operations management This will entail the development of an updated basin-wide water resources model for the integrated evaluation of future development scenarios, aimed at identifying the most sustainable development options going forward. This analysis will be updated and combined with a multi-criteria analysis to take into account socio-economic and environmental aspects. An operational decision-support system will be set up and recommendations made for improving the hydroclimatic monitoring network.

- Under this output, the project will undertake the following activities:

Final choice of water resource model to be utilised.

Set up the model topology and hydrological inputs based on improved data sets and data sets based on climate change considerations.

Compile details of all sectoral demands around the basin, existing and potential, including the newly available ecological flow requirements

Populate the model with details of all possible infrastructure developments.

Devise scenarios in terms of combinations of infrastructure and climate change

Run scenarios and analyse results.

Apply multicriteria analysis and compile report.

At all stages consult with stakeholders

Output 2.1.3 – TDA produced (including the future development scenario analysis and causal chain analysis)

- Under this output, the project will undertake the following activities:

Based on all the existing studies and the new work carried out to achieve outputs 2.1.1 to 2.1.3, the TDA will be drawn up. It will clearly identify the baseline situation, the issues and challenges that present the barriers, together with the opportunities available for sustainable development of the basin.

Output 2.1.4 - A long-term IWRM Plan (2025-2040) and 2 NAPs negotiated and endorsed at the ministerial level.

- Under this output, the project will undertake the following activities:

Working with the PJTC, (or new Kunene River Commission), the project will develop a IWRM Plan (2025-2040) for the Kunene basin, setting out the vision and long-term strategic priorities for the basin.

The design and timeline will be coherent with the Cuvelai Basin IWRM Plan to ensure compatibility, bearing in mind the close ties between these two basins. This will be accompanied by a 5-year Investment Plan covering the period 2025-2029 and nationally endorsed National Actions Plans (NAPs).

The project will support securing the ministerial endorsement on the IWRM Plan from the two countries to signify a high political commitment of the two countries to manage the transboundary basin jointly.

Once endorsed at the ministerial level, the IWRM Plan and associated investment plan will be the focus of a well-organized and publicized roundtable with potential investors and development partners.

Output 2.1.5 - 5-year investment plan developed and a roundtable with potential investors and partners (aimed at resource mobilization for implementation of the IWRM Plan.

- Under this output, the project will undertake the following activities:

A five-year investment plan covering all aspects of the IWRM Plan covering both enabling and infrastructure investments, will be drafted to include costed actions with associated timelines

An implementation framework including institutional responsibilities and a monitoring and a results-based monitoring and evaluation system

Financing plan

Component 3: Strengthening the governance of the Cuvelai and Kunene River Basins to foster joint management by the two countries in the most cost-effective manner

Historically the two countries have cooperated closely in the management of these two basins, in particular for the Kunene Basin, largely as a result of its evident hydropower potential. There are proposals to transform the PJTC into a river basin commission similar in nature to other River Basin Organizations (RBOs) in the region, such as CUVECOM on the Cuvelai River basin.  The countries are well on the way to adopting similar provisions as those in place for CUVECOM (Cuvelai Basin). This has been discussed by the Kunene PJTC, as has the solution of a joint (Cuvelai and Kunene) Secretariat.

Cooperation on the Cuvelai is more recent but has moved forward rapidly since signing of the CUVECOM Agreement in 2014. A Secretariat was established in 2016 and a preliminary transboundary IWRM Plan published in 2019 following a rapid assessment and series of stakeholder’s discussions.

.

Outcome 3.1: Intergovernmental institutional structures set up in a financially sustainable manner to foster joint management of the Cuvelai and Kunene basins by the two countries

Output 3.1.1 - Transboundary governance structures developed and functioning.

- Under this output, the project will undertake the following activities:

For both CUVECOM and the PJTC a rapid institutional assessment will be carried out examining how the institutions have functioned in terms of activities, achievements, participation of Commissioners and other stakeholders, interactions with other institutions and international cooperating partners and sustainability aspects, including financial resources.

For the Cuvelai Watercourse Commission (CUVECOM), the aim will be move from the current financially dependent commission to one that is fully functional and self-financing based on only country contributions and any other earnings or levies that it may be due in the future.

For the PJTC, the aim is to transform the organisation into a financially sustainable River Basin Organisation, probably similar in structure and mandate to CUVECOM.

Output 3.1.2 Joint Secretariat for the CUVECOM and Kunene Commission formed and strengthened. While the plan is to have separate commissions for each river basin, the current proposal is to have a joint Secretariat.

- In order to achieve this output, the project will undertake the following activities:

Institutional Functional Analysis for CUVECOM and Kunene Commission to suggest a sustainable structure for the Joint Secretariat

In order to be functional as rapidly as possible, it is proposed to set up an interim joint structure to:

Establish an Operational and Financial Management Structure (Accounting Systems, Procurement Systems, Financial Management Systems, Human Resources Policies and Manuals, Host Country Agreement, etc.)

Ensure an adequate internet connection and establish a suite of virtual tools and digital solutions that allow the current CUVECOM Secretariat in Namibia and its satellite offices in Angola (which would jointly serve as an interim joint Secretariat until permanent arrangements are agreed) are fully capable of remote working relationship with Commissioners and focal ministries in Luanda and Windhoek.

Development of a costed, detailed proposal Sustainability Plan for the Joint Secretariat.

Output 3.1.3. Assessment of national legislation, policies, strategies and plans and assessment of transboundary harmonization needs

- In order to achieve this output, the project will undertake the following activities:

Proposals for policy strengthening and/or policy harmonization will then be made.  The assessment will be included in TDAs.

An area of particular importance is legislation relating to the treatment of wastewater, industrial and other waste. As part of the TDA work, the policies, legislation and enforcement systems will be reviewed and experience in both countries analysed followed by proposals for inclusion in the TDAs and Investment Plans.

Output 3.1.4. Information Management Systems established

- Under this output, the project will undertake the following activities

- Information Management Systems will be established.

- The information management system will support the dissemination of newly acquired information and knowledge about the two basins through the basin TDAs and policy briefs.

Output 3.1.5 - Effective and productive cooperation between universities and with CUVECOM and PJTC/Kunene Commission

- Under this output, the project will undertake the following activities

- This activity will build recent initiatives supported by CUVECOM which has seen the development of cooperation between University of Namibia and University of Agostino Neto in Angola.

- It is envisaged that the universities can provide assistance through research work carried out by students.

- Mutual benefits can be accrued through internships within CUVECOM and PJTC/Kunene Commission. .

Output 3.1.6 - Gender equality and women empowerment efforts mainstreamed into all CUVECOM and Kunene Commission policies and practices through the development and implementation of the Gender Strategy.  Gender mainstreaming strategy is developed and implemented as integral part of the IWRM Plans. The importance of gender mainstreaming is heavily emphasized in the IWRM Plan for the Cuvelai Basin, but as yet little progress has been made in terms of implementation.

- Under this output, the project will undertake the following activities

- The Gender Strategy for the two basins IWRM plans will be (further) developed with support from the project and adopted by the CUVECOM and the PJTC.

- The strategy will make sure that the gender considerations are incorporated throughout the IWRM plan development and implementation process, leading to the women empowerment results in the basin.

Component 4: Strengthening institutional, technical and operational capacity in Angola to sustainably develop and manage the sub-region’s water tower located in southern Angola

The source areas of both rivers lie in areas that were devastated during the Angolan Civil War. The concerned provinces (Cunene, Huila and Huambo) are development priorities for the Angolan Government. Considering that the Angolan Central Highlands form the water tower for the Kunene, Cubango, Cuito, Cuvo and Cuanza rivers, their management is absolutely critical, not only for Angola but also for Namibia and other neighbouring countries, which are water-stressed and facing the impacts of climate change. While economic activity in the central highlands is dominated by agriculture, forestry (inlcuding logging) and mining are important economic activities and must be taken into account. Involvement of stakeholders from these sectors is critical.

Outcome 4.1: Capacity in water resources and environmental management in Angola strengthened

Output 4.1.1 - Ecosystem-based approach to protect water towers in southern Angola (through awareness raising & strengthened institutional capacity) successfully promoted.

- Under this output, the project will undertake the following activities

Institutional strengthening within the basins, to be provide to GABHIC, the Provincial Environmental Offices and the National Directorate for the Environment.

Strengthening of the CUVECOM satellite office in Ondjiva and to create “focal points” in the office of the provincial administrations of Huambo and Huila provinces (in Huambo and Lubango).

In order to support awareness raising and institutional capacity, Information Management Systems will be established in order to support coordination and communications

The Ondjiva satellite office and key relevant offices (e.g. GABHIC, provincial offices) will be capacitated for remote conferencing, regular online communications, and sharing documents to work together remotely.

Output 4.1.2 - Technical capacity strengthened through training in GIS, flood risk mapping and flood management, hydrological monitoring and water resources modelling. This capacity strengthening is important in supporting the technical work under Components 1,2 and 4.

- Under this output, the project will undertake the following activities

Training of up to 4 participants (from Angola) in GIS

Training of 4 participants from each country in flood risk mapping and management

Training of up to 4 participants (from Angola) in hydrological monitoring

Training of 4 participants from each country in water resources modelling and scenario analysis

The selection of trainees should be such that at least haf of the trainees are women.

Output 4.1.3 - Data collection and analysis capacity strengthened. Strengthening the data availability in the Angolan Central Highlands will also support the economic valuation of the ecosystem goods and services from this important ecosystem.

- Under this output, the project will undertake the following activities

Provision of equipment for climate and hydrological monitoring so as to bring the density of coverage up to WMO standard (1 station/1875km2 of catchment), prioritising rehabilitation of existing sites.

Provision of equipment for water quality sampling and analysis.

Provision of equipment for sediment sampling and analysis and one sediment sampling station.

Provision of software (licenses) for water resource and flood line modelling (min of 2 licences per country)

Output 4.1.4 - Economic Valuation of the ecosystem goods and services provided by the Angolan Highlands ecosystem

Conservation of the Benefits of addressing environmental degradation on the Central plateau will ultimately go beyond the two basins concerned by this project.

- Under this output, the project will undertake the following activities

- Establish the environmental baseline. While this will only be a first estimate based partly on a short hydroclimatic data series, it will be adequate for a first estimate.

- Analysis of the current use of natural resources, for agriculture, livestock, forestry (including logging) and mining and the impacts of these activities

- Identify and provide qualitative assessment of the potential impacts of policy options on ecosystem services. Decide resources quality objectives.

- Quantify the impacts of policy options on specific ecosystem services.

- Assess the effects on human welfare.

- Value the changes in ecosystem services related to the different policy directions

Component 5: Enhancing the community participation in IWRM to build resilience in their livelihoods

Ensuring sustainable and resilient livelihoods for the basin communities will be at the centre of the proposed interventions. Improved livelihoods and increased resilience and adaptive capacity to climate change and variability are critical to both poverty alleviation and sustainable development.

Outcome 5.1: Livelihoods enhanced and community resilience improved through community-driven activities

Experience has shown that the planning, design and implementation of complex community-based interventions, can best be achieved through a bottom-up approach supporting small-scale (across a limited number of communities and a manageable area), but holistic, pilot demonstration projects which yield both environmental and livelihood benefits, and which can easily be scaled up. Local Government and/or CUVECOM, Gabhic and the PJTC will have a key role to play in terms of technical support, contract management, organising experience-sharing and peer-to-peer networking in support of scaling up. Implementing community-based pilot projects for key intervention areas in order to facilitate stakeholder support and scaling up will contribute to addressing Barrier #4.

Output 5.1.1 – Gender-responsive Community-driven interventions to improve their resilience and livelihoods identified and implemented that are in line with the implementation of the IWRM Plans for CUVECOM and Kunene PJTC, in close coordination and planning with local authorities/line ministries. The following preliminary conclusions on project content and localisation were reached following consultation with community representatives in the two basins. The preliminary location of project sites is provided in Annex 2 together with further detail on project design. The precise localisation at the village level was not possible to achieve at this stage due to travel constraints related to the COVID-19 Pandemic.

- Water (rainwater and/or flood water) harvesting: These pilot projects should incorporate community-based aquaculture with the central water-harvesting component. It is assumed that there will be 1 site in Angola and 3 in Namibia, all in the Cuvelai basin.

- Livelihood-based watershed management: Six sites are proposed, four in Angola and two in Namibia. These pilot projects should incorporate the following elements into single integrated benefits:

Conservation agriculture including no-tillage practices

Livelihood-based watershed management and

community-based aquaculture

Siting of the projects is in the rainfed farming areas of the middle to upper parts of the Kunene basin in Angola and within an arable/mixed farming area of the Cuvelai basin (north-easter part) within Namibia. The community level committees that will be set up at during project inception must include adequate representation of the elderly and the youth and include equal membership of women.

Output 5.1.2 - Capacity strengthened in the Secretariat to ensure the sustainability of basin community engagement and community-driven activities to implement the IWRM Plan: This component will be CUVECOM/PJTC driven, coordinating and planning together with NGOs, local authorities and line ministries and working with the communities. In terms of implementation, it is proposed that the CUVECOM/Joint Secretariat is given responsibility via a grant agreement with GWP-SA. The Secretariat will work closely with local administrations in both countries.

Output 5.1.3 - Piloting of gender-responsive and inclusive flood early warning system for communities in selected hotspot settlements with the system operational for at least 4 hotspots basin wide. A minimum of four sites are proposed, all in the Cuvelai basin and two in each country.   Some preliminary flood-risk maps (see of the Cuvelai basin do exist and these will be used as a basis of discussion with the authorities and community representatives to finalize the localization of the pilot communities. For more details, see Annex 2. This ties in with the work to be carried out under Component 1 (Setting up the framework for a transboundary flood early warning system). It will bring together knowledge and experience on these systems in Namibia and new real-time data collected in Angola.

- Under this output, the project will undertake the following activities

Based on the preliminary identification of sites (see Annex 2) the following activities are foreseen:

Discussions with the authorities in both countries to finalise a shortlist of target communities in each country

Carry out site visit to each shortlisted community to assess risk and collect information on previous flood events and associated loss of life and damage, and to ensure high level of gender-responsiveness and inclusion.

Compile assessment report with recommendations, preliminary project design and budget for the pilot demonstration projects to be implemented at the selected sites

Develop and implement early warning system in close cooperation with the target communities. Representation of the target communities should include adequate representation of women, the elderly and youth to ensure that their specific concerns and needs are fully taken into account.

Component 6: Outreach and Knowledge Management for replication, upscaling and stakeholder engagement

Component 6 will support knowledge exchange and information sharing with other RBOs in the region to support the effective and efficient delivery of project results.  It will also support dialogue between CUVECOM and the new RBO for the Kunene and other RBOs in the region and further afield.

Outcome 6.1: Stakeholder engagement strengthened through targeted communication and Replication and upscaling supported through exchange of knowledge, best practices and lessons learned

Output 6.1.1 - Stakeholder Engagement Strategy and Communication Strategy developed (based on the Stakeholder Engagement Plan and Gender Action Plan) developed during PPG) with participation of women and gender experts.

- Under this output, the project will undertake the following activities:

- Participate in the SADC RBO Dialogue and SACD Multi-Stakeholder Dialogues

- Participate in regional meetings of RBOs (workshops and technical events organized by SADC Water Div)

- Participate in and provide information to digital platforms on transboundary river management

- Carry out exchange visits with other River Basin Organizations on technical issues around transboundary river management, including the “source-to-sea” approach

Output 6.1.2 - Targeted policy briefs and communication products produced.  The aim will be to consolidate project knowledge products in formats suitable for sharing with national, regional and international partners and audiences.

- Under this output, the project will undertake the following activities

- Produce policy briefs to connect science to management and policy discussions

- Other knowledge products on key scientific outputs such as E-Flows in Kunene, Flood early Warning system in Cuvelai, the groundwater assessment of the transboundary Cuvelai basin and on the Kune River Basin Scenario Analysis and development proposals

- Communicate materials developed for targeted audience via various media, in local languages

Output 6.1.3 - Exchanges with other RBOs and relevant regional institutions, in particular with RBOs in SADC region, SADC Groundwater Institute, and other TB river basins with headwaters in Angola.

- Under this output, the project will undertake the following activities

- Make contacts with all RBOs in the region

- Carry out exchanges with RBOs, such as OKACOM, aimed at experience sharing and learning lessons.

- Work closely with OKACOM, particularly in Angola with respect to Component 4.

Output 6.1.4 - Active contribution to the learning and knowledge sharing activities and events organized by the GEF IW: LEARN, including the GEF IWC (at least 1% of the project budget. The use of the GEF IW: LEARN network, IW Experience Notes, and IW: LEARN website/database will underpin the knowledge management strategy of this project.  Maintaining linkages with IW: LEARN activities enables projects to share challenges and benefits and improve governance at the local, regional, and international levels.

Output 6.1.5 - Timely Project M&E to inform adaptive management for successful delivery of project results, including MTR and TE. System in place. A participatory Monitoring and Evaluation and learning framework will be developed and implemented for the project, following standard UNDP and GEF procedures.

- Under this output, the project will undertake the following activities

- Development and implementation of the project M&E framework, including tracking of GEF Core Indicators and other indicators in the Project Results Framework; monitoring of Social and Environmental Safeguards; and an independent Mid-Term Review and Terminal Evaluation of the project

Partnerships

Partnerships - Baseline Initiatives

National Investments in River Basin Management

Hydrological monitoring: In the Kunene basin in Angola there are 5 stations and 3 hydro-climatological stations in the Cuvelai, with more than 10-gauge plates (for water levels) having been recently installed. In Namibia there are a total of 27 gauging stations in the Cuvelai Basin, of which 10 are operational. There are plans to review the network and add up to 10 new stations. In the Namibian portion of the Kunene basin there are 8 stations of which 5 are operational.

Water quality monitoring: The Namibian authorities continue work on initiatives related to water quality monitoring in the basin, pollution control, monitoring, extraction permitting and management activities and both countries have agreed to invest on an ongoing basis in initiatives related to:

- water quality monitoring in the basin, pollution control, monitoring and management activities;

- water resources monitoring (both surface and ground water) and modelling in the basin;

- water abstraction permitting and management activities; and

- ensuring security of water supply and environmental management

NamWater has a number of projects underway or due to start in the near future (projects with external financing are summarised under Paragraphs 82 onwards.). All of them concern improving the supply of potable water to both large and small settlements. Interventions included rehabilitation of canals and conversion to pipeline to reduce losses and improve conveyance, addition of pumping stations and expansion of water treatment works.

- Calueque Pumping Station. The completion and commissioning of the permanent pumping system forming part of the Calueque dam with agreement on and appointment of an Angolan/Namibian authority to operate and maintain the system.

- Omahanene to Olushandja Canal Refurbishment. The replacement and repair of the 10 km long concrete lined canal running from the Namibian border with Angola to the Olushandja balancing dam

- Olushandja Pump Station and Siphon Refurbishment. Investigation of the condition of the Olushandja pumping station and siphon, and its upgrade to meet expected pumping volumes, after the duplication of the Oshakati purification works becomes operational.

- Olushandja to Ogongo Canal Refurbishment. Investigation of the condition of the Olushandja pumping station and siphon, and its upgrade to meet expected pumping volumes, after the duplication of the Oshakati purification works becomes operative.

- Ogongo to Oshakati Canal Rehabilitation. A reinvestigation of the capacity and upgrading of the 54-km-long concrete canal between Ogongo and Oshakati, together with replacement of a 10-km section in the vicinity of Oshikuku with a pipeline/pumping system

- Ohangwena II Phase 1: Omafo – Eenhana Extension, first phase development of Ohangwena II aquifer system to cater mainly for the demand in an area between and including Oshandi and Eenhana. Financing is provided through the AfDB

- Oshakati Water Purification Plant (Cuvelai Basin) will be extended in order to increase the availability of potable water in the Central North of Namibia. The treatment plant is currently exceeding its design capacity of (40,556 m3/day) during high demand months. Capacity will be doubled through construction of a second plant. Efforts are also being made to improve the treatment of wastewater. Financing is provided through the AfDB

Following the devasting 2018/19 drought, which hit both basins in both countries, efforts to improve water security have been accelerated. In Angola, a number of water transfers are being studied in detail including:

- Cunene River Water Transfer System from the town of Cafu to Shana zone – Towns of Cuamato and Namacunde. This is part of a set of proposed Infrastructure projects in southern Angola to combat drought.

Design and Construction of intake on the Cunene River, Pumping System, Pressurized Pipeline, Open Channel from Cafu to Cuamato and 10 Chimpacas;

Design and Construction of Pipeline from Cuamato to Dombendola, Pipeline from Cuamato to Namacunde and 20 Chimpacas; This would involve the construction of a new intake on the Cunene River, a pipeline, canal and reservoirs.

- Calucuve Dam and canal. This would involve the construction of a dam, a canal from Mupa to Ondjiva and reservoirs.

Design and construction of Dam 128 (Caculuve);

Project and Construction of the Adductor Canal from Mupa to Ondjiva and 44 Chimpacas;

- Ndúe Dam and canal. This would involve the construction of a dam, a canal from Ndúe to Embundo and reservoirs. Part of Infrastructure projects in southern Angola to combat drought.

Project and Construction of Dam 71 (Ndué);

Project and Construction of the Adductor Canal associated with Dam 71 (Ndué) from Ndué to Embundo and 15 Chimpacas

- Pilot Groundwater abtsraction schemes for communities on right bank of Cunene

- Construction of the Cova do Leão Dam and Emergency Actions for Desassoreamento in the Municipality of Curoca. This is part of Emergency Programme to combat dought in Kunene to expand the area of influence and populations benefiting from the “CUNENE 8 Programme”, through the rehabilitation and reconstruction of existing structures

- Water Supply System for Cahama, Otchinjau and Óncocua and water supply system to Chitado ll under CUNENE 8 programme

- Programme for strengthening resilience and food and nutritional security in Angola. To contribute to the reduction of hunger, poverty and vulnerability to food and nutritional insecurity in the Southern Provinces most affected by climate change - Cunene, Huila and Namibe.

- Climate resilience and water security programme in Angola to improve water supply and sanitation services and strengthen water resource management in specific areas for climate resilience.

Baseline Programs supported by International Cooperating Partners

NamWater has a number of urban water supply projects underway or due to start in the near future with external support. They include:

- Central Norther Area (CNA) Master Water Plan Study. A comprehensive revision of the water masterplan of the central northern area, including full utilisation of Namibia’s specified share of water from the Kunene River and the development of the Ohangwena II aquifer"

- Omundaungilo – Omutsegwonime Bulk Pipeline Scheme. A bulk pipeline with secondary branch-lines to cater for the rural communities that drink unhygienic water from traditional wells, brackish water.  Construction of a Pump station, reservoirs, and associated facilities.

A wastewater treatment plant is under construction in Oshikango in Namibia and the Nordic Development Fund is supporting the development of a biogas plant in Ondangwa that will produce 3.4 GWh of carbon-neutral electricity annually, (mitigating 2,330 tons of CO2e). The project is the first of its kind in Namibia that will process city sewage water and produce low-cost organic fertilizers to local farmers.

Replacement of Olushandja-Oshakati Canal. KfW have made funding available (Euro 2.1 million) for feasibility study into replacement of existing Olushandja-Oshakati canal (transferring water from Kunene-Cuvelai) with a pipeline, in order to reduce evaporation and damage (from cross-drainage flooding and vandalism

Although the World Bank Board of Directors approved a $300 million loan to support the Government of Angola to improve water supply and strengthen water resource management for greater climate resilience in Angola, the funding has not yet been finalised.  If the support comes into fruition, there will be significant synergies with the project through physical investments in urban and rural areas as well as institutional development activities to increase water security and help manage climate extremes, from the national and basin levels to the municipal level. The majority of support will be in the south of the country and will include the provinces of Huila and Cunene. Three components are envisaged:

- Component 1 is aimed at strengthening Water Services for Water Security in Urban and Rural Areas. These works will contribute to water security (I-W3.7), strengthening water supply and sanitation service provision in urban and rural areas of selected provinces, including rehabilitation and expansion of water supply services in urban and peri-urban areas, maintenance and repairs of rural water supply systems. A major sub-component is focused on strengthening of rural water services to build drought resilience in the South of Angola. The envisaged work on groundwater assessment under this project can enhance the knowledge base for the planning and design of rural water supply infrastructure.

- Component 2 concerns Strengthening Water Resources Management for Climate Resilience. A key part of the proposed works includes community-level infrastructure investments to increase reliable access to water resources. There are significant synergies with Component 5 of this project and the World Bank project could support the process of taking to scale. Component 2 will also provide institutional support for water resources management. The support will include capacity building and support to improving monitoring of climate hydrology, groundwater. The creation of basin councils is also foreseen, echoing the approach in Namibia.

- Component 3 is focused on project management and inter-institutional coordination.

Partnerships - Coordination with other relevant GEF-financed projects and other initiatives

National Projects

The FAO/GEF supported Sustainable Land Management in target landscapes in Angola’s southwestern region project should start in the near future. This is a highly relevant project with the objective of “reversing negative land degradation trends in selected landscapes in southwestern Angola by combining sustainable and rational approaches to planning, decision-making and land-use stabilization with participatory approaches to capacity building of local stakeholders”. Interventions are planned in both the Cuvelai and Kunene River basins. Component 1 comprises an agro-ecological zoning and integrated planning exercise to be followed by Component 2 which would see at least 80,000ha of target landscapes, where land-use will be stabilized and monitored (locations in the provinces of Cunene, Namibe, Huila and Benguela, with exact municipalities to be confirmed during PPG). Interventions will focus on different goals depending on the landscape and will include the intensification of agriculture, intensification of agro-pastoral agriculture and rangeland degradation prevention measures. A new protected area in the Cuvelai Basin on the border with Namibia is also proposed.

The ongoing GEF/LDCF supported project Promoting Climate-resilient Development and Enhanced Adaptive Capacity to Withstand Disaster Risks in Angola’s Cuvelai River Basin is also highly relevant. The project objective is that the climate-related vulnerabilities facing the inhabitants of Angola’s Cuvelai River Basin are reduced through targeted investments and capacity building. The outcomes are highly relevant. Component 1 includes actions in hydro-climatic monitoring and establishment of a famine and flood early warning system. Component 2 is focused on institutional capacity-building and capacity-building in vulnerable communities. The livelihoods assessment work under this component will provide useful information.

- UNESCO has had recent experience in the region in both groundwater resources governance and in planning for flood and drought management:

- The UNESCO Groundwater Resources Governance in Transboundary Aquifers (GGRETA) Project, funded by the Swiss Agency for Development and Cooperation, aims to strengthen the transboundary groundwater governance through the establishment of cooperative frameworks for transboundary groundwater governance in River Basin Organizations. In particular, the Stampriet Transboundary Aquifer System (Namibia, Botswana and South Africa) was the one of pilot transboundary aquifers. Based on the successful example from the Stampriet Transboundary Aquifer, several lessons learnt can be identified to strengthen the transboundary and conjunctive water resource management in the Cuvelai River Basin and Kunene River Basin:

The Multi-Country Cooperation Mechanisms (MCCM) for the Stampriet Aquifer system (STAS) was established and nested in ORASECOM in 2017 through the GGRETA Project and is a first example of a mechanism for a transboundary aquifer to be nested within a river basin organization (ORASECOM), capturing IWRM and surface water groundwater conjunctive management approaches.

The GGRETA project made a direct response/contribution to the regional water mandate, as expressed in the SADC Regional Strategic Action Plan, phase 4, which is very explicit on the need for financial support to transboundary aquifer management through Transboundary Diagnostic Analysis (TDAs) and Strategic Action Plans (SAPs).

Groundwater modelling as a powerful tool for management in TBAs should be promoted, taking cognisance of the data challenges with decisions having to be made on whether to build regional models or a suite of models. The GGRETA project has developed numerical models as management tools, also be able to open new development perspectives and present attractive opportunities for coping with the looming threats of climate variability and change.

Information or data sharing/exchange protocols are critical for continued sharing of data and these need to be co-developed. Information systems have become central to the Transboundary Aquifers projects. The use of free and open-source software increases access to data, e.g. the new platform of the SADC Groundwater Information Portal (SADC-GIP).

- The Strategic Action Plan for Flood and Drought Management for Namibia was developed by UNESCO and University of Princeton (USA) for the long-term proactive disaster risk reduction in Namibia. Several key messages can be identified:

Through consultation with key stakeholders from different backgrounds, a clear need was identified to strengthen early warning and monitoring systems instead of disaster response, supporting communities to move ‘beyond short term relief’.

High resolution (30 m) flood hazard maps are required.

Early warning communication and dissemination is critical for the real-time flood early warning. In particular, the community-based flood early communication should include the multiple communication channels, including SMS, social media, and radio, to disseminate the flood forecasting.

Citizen Science data sources can complement national observational networks and ensure engagement from local communities to increase data availability for flood risk management.

There is a general acceptance that there is a need to integrate climate change into medium to long-term water resources planning, which is being hampered by the large uncertainty associated to climate change projections. UNESCO launched the ‘Climate Risk Informed Decision Analysis (CRIDA): Collaborative Water Resources Planning for an Uncertain Future’ as a response to this gap. CRIDA aims to integrate climate change uncertainty, including the hydromet services, into the identification of ecosystem-based adaptation strategies and to enable flexible decision- making processes.

- During the project initiation phase, CUVECOM, PJTC and GWP-SAS will have further consultations with UNESCO on possible synergies and collaboration especially on Component 1, Outputs 1.1.1, 1.1.2 and 1.1.4.

Risks

The following risks to successful project implementation have been identified and risk mitigation strategies have been developed for each risk.  The risks to project implementation listed below are also provided in the UNDP Quantum Risk Register (Annex 5), along with risks that might result from project implementation as identified in the Social and Environmental Risk Screening Checklist.

Table 1: Project Risk Management Matrix

| Risk | Rating | Risk Mitigation Strategy |
| --- | --- | --- |
| Political commitment on the long-term IWRM Plan, developed based on the TDA, will not be secured (in the form of the ministerial endorsement) | Low | Both countries are committed to the joint management of the basin, not only at the technical level but also at the political level, as manifested through the establishment of the CUVECOM and through their ongoing discussion to transform the PJTC into the Kunene Commission. Both countries have gone through the process of securing the ministerial endorsement on the Cubango-Okavango River Strategic Action Programme (SAP) in the past; thus, they are experienced to show their political commitment through the ministerial endorsement. Also, they are aware that the strong commitment is needed for them to attract any external resources from their partners to implement the SAP or the IWRM Plan. Therefore, the risk is considered low. Nonetheless, the project is designed to produce a series of policy briefs to facilitate linking of scientific knowledge to management and policy decisions. By keeping the senior policy makers as well as politicians closely informed of the new knowledge and information will further reduce the risk of inadequate political commitment to the IWRM Plan. |
| Basin states will not be willing to release their data for use by CUVECOM or PJTC. This will pose a significant risk to the achievement of the project outcomes, as TDA, Information Management Systems and joint basin planning activities in general will all depend on data from basin states. | Low | Both governments have signed the SADC revised shared watercourse protocol, which provide the legal basis for the member states to cooperate for joint management of the shared watercourse, such as the Cuvelai or Kunene River basin. Further, CUVECOM and PJTC have been discussing the importance of data collection and sharing as well as strengthened monitoring activities to collect real-time data for management decisions. It is considered as one of their priorities; hence, GEF support is requested to address. Hence, the risk is considered low. |
| Lack of inter-sectoral coordination and consultation at local, sub-national and national levels will hamper the effective IWRM implementation in the basins. | Moderate | The TDA-SAP (IWRM Plan)-NAP development process requires a strong inter-sectoral, multi-country consultation process. The project will support the two countries to establish inter-sectoral committees to support this process. Multi-sectoral coordination at the technical level will be strengthened through the TDA development process, while multi-sectoral coordination at the policy and political levels will be strongly promoted through the SAP (IWRM Plan) and NAP negotiation process. Strong engagement of communities and local stakeholders in the IWRM implementation will be ensured not only through the implementation of the Stakeholder Engagement Plan and the Communication Plan but also through the implementation of the SAP demonstration projects. For Angola, the project will provide focused interventions to strengthen inter-sectoral coordination at national and sub-national levels under Component 4 to further mitigate this risk. This will include the logging and mining sectors, whose activities, of not well-mitigated, have negative impacts on the ecoservices provided by the water tower. |
| Poor coordination among various projects supporting CUVECOM and PJTC, funded by different entities, leading to sub-optimal results delivery or duplication or work. | Low | The countries are highly willing to coordinate activities through CUVECOM and PJTC for their respective basins in order to maximize their cumulative impacts as well as achieve resource efficiencies in their own investments towards the joint management. Required level of coordination efforts are currently not overwhelming since both CUVECOM and PJTC currently have limited number of partner-funded initiatives that they need to coordinate. In addition, the project supports the capacity strengthening of the Secretariat, which will provide valuable support to the two governments to coordinate various projects and initiatives as a coherent programme. |
| Poor coordination among various existing and upcoming projects that are relevant to the ecosystem-based approach to the Angola’s water tower protection leading to the suboptimal results delivery and/or policy or management recommendations with conflicting messages | Moderate | Coordination of various existing and upcoming projects and initiatives in the headwater regions of the two basins is not a simple task. Angola will be supported to do the mapping of relevant initiatives in the targeted geographical areas during the project development phase to identify the potential projects and initiatives that the project should aim to coordinate and collaborate. The information gathered through the mapping exercise will influence the details of the project interventions, in particular under Comp 4, to medicate and manage this risk. |
| Further ecosystem and water quality degradation in the basins due to the development pressure and uncoordinated development activities across the basin. Development pressure is high in the basins, especially in Angola, and some major development decisions are made outside of CUVECOM or PJTC discussions or mandates. | Moderate/ High | The project will support CUVECOM and PJTC in the development of future water resources development scenarios, taking into account e-flow requirements, potential impacts from climate change and variability. This exercise, to be included in the TDA, will inform policy makers beyond the water sector about potential positive and negative impacts from different water resources development scenarios and help establish common knowledge base across the member states. Further, the project will strengthen the engagement of regional/provincial government stakeholders in the management and policy discussions of CUVECOM and PJTC as part of the efforts to raise awareness among the regional/provincial government stakeholders of the importance of water resources and the basin ecosystem integrity. With this approach, the project will support policy makers directly involved in CUVECOM and/or PJTC as well as those who are not to make more informed decisions about potential future development options that are supported by the basin resources and that would affect the basin resources at the same time. |
| The project activities will worsen, instead of improving, the livelihoods of basin communities even unintentionally in the name of conservation | Low | Realizing sustainable and resilient livelihood improvement of the basin community is one of the overarching objectives of the proposed project. Thus, due consideration is given to the potential impacts of the proposed project interventions on the livelihoods of basin communities. Through the application of Social and Environmental Safeguard Procedures during the project development phase, details of this risk will be identified, and appropriate risk mitigation measures developed and incorporated into the project design. |
| Financial, operational and/or safety challenges emerged due to COVID-19 in the countries (not necessarily in the basin areas) imposing risks on the timely and effective implementation of the project activities | Moderate | COVID-19 pandemic may impose restrictions on working arrangement, movements, procurement, supply chains, local market, etc., which will all impact operational efficiency of the project. It may have impacts on security stability in rural areas or in fragile states where there existed limited resilience to absorb such unpredicted and unprecedented external shocks. The level and type of risks will change as the COVID-19 pandemic situations change in particular location in the basin as well as in two countries. The project will regularly screen or COVID-19 risks through available tools and mechanisms (e.g. Social and Environmental Safeguards, Stakeholder Engagement and M&E Plans implementation) and update Quantum Project Risk Register to develop and adjust mitigation actions to deal with changing risks. The project will build the CUVECOM and the Kunene PJTC’s capacity to continue operating and coordinating closely with their member states and stakeholders remotely even without face-to-face consultations. These measures will build the operational resilience in the CUVECOM and the Kunene PJTC against shocks that were caused by COVID-19. These are reflecting the lessons learned and good practices from other River Basin Organizations in southern Africa which had to make some quick adjustment to their modus operandi when hit hard by COVID-19 earlier in 2020. |
| Government (and partner) priorities (and resultant financial resources) shifted to COVID-19 response, recovery and preparedness operations, leaving less attention to the joint management of the Cuvelai and Kunene River basin resources. | Low | During the project development phase, the details of the project design and interventions will be developed carefully, taking into account the governments’ and basin communities’ needs in the context of COVID-19 pandemic, especially their recovery efforts. Life in both countries is gradually returning to normal and while a return to some level of pandemic conditions cannot be ruled out, the assumption is that consultations will take place on a face-to-face basis and that there will be no significant restrictions on movement. It is also worth noting that the project – and the Governments’ efforts to strengthen the joint management of water resources in the Cuvelai and Kunene River basins in general – will build resilience of the basin communities against the impacts of any possible resurgence of the pandemic and other challenges. |
| Risk of other priorities drawing attention away from the IWRM Plans | Low | Sufficient attention has been drawn to the Cuvelai IWRM Plan through its development and approval processes in the recent past. The project will support the CUVECOM and Kunene PJTC to organize a ministerial endorsement of their respective IWRM Plans. The Cuvelai and Cunene basins in Angola and Namibia are among the high priority provinces/regions for development by the national governments. The Cuvelai basin in Namibia is one of the most densely populated areas in the country and one which suffers cycles of flooding and drought events, especially in recent years. The Cuvelai basin is seen as one with significant economic development potential. Given all of these drawcards combined, the risk of attention being diverted elsewhere is low. |
| Risk to stability and local conflict potential | Low | There is no obvious reason why the project should have a negative impact on stability and the potential conflict. Components 1 and 2 are aimed at building plans that are based on both enhance knowledge and a high level of stakeholder engagement. The implementation of such plans is much less susceptible to conflict than an adhoc or non-integrated development approach. This holds true for the potential for conflict at all levels from the most localized through to transboundary. |
| Risk of mobilizing resources required for IWRM Implementation | Moderate | Securing sufficient financial resources to initiate and continue with the IWRM Plan implementation has been a significant challenge for many river basins, transboundary or otherwise. The Cuvelai and Kunene River basins will not be an exception. However, for Cuvelai, high priority is given from both Angola and Namibia on Disaster Risk Reduction after a series of flooding and drought events in the basin, which caused significant damages to their development and the livelihoods of the basin communities. With the high priority, national budget and international aid has been channelled to the region. The project will support both Angola and Namibia to place the Cuvelai IWRM Plan and its implementation in the strategic place in the context of the DRR efforts so that the IWRM Plan implementation can be supported by DRR-related investment as well. Further, the project will support the donor roundtable to attract financial support to the IWRM Plan implementation. |
| Increased climate variability and change (see section on climate risk screening below table) | Moderate to high | The basins are situated in southern Africa, where many global circulation models indicates that the climate will be drier, flood and droughts will be more frequent and more intense. Thus, this risk is high. That is why it is even more critical to have the long-term, basin-wide IWRM Plans as a long-term strategic document for each basin, complemented by a 5-yearly investment plans and National Action Plans. To manage adverse impacts of increased climate variability and change, we need to apply inter-sectoral, holistic, and stakeholder-driven approaches, guided by long-term vision. The project will mitigate risks associated with the increased climate variability and change through the development and implementation of selected priority activities in the IWRM Plans. |
|  | Low |  |
| Project delays, constraints, or capacity-related risks related to the COVID-19 global pandemic –short-medium-term | Low | Project implementation could start in early 2023, with the first field activities starting by the second quarter. Although business has largely returned to normal in both countries, it is clear that there remain a significant risk of COVID resurgence waves. In the event that either country re-introduces measures that restrict the extent of stakeholder consultation (either through restrictions in the numbers of stakeholders congregating or travel restrictions), the team will revert to virtual workshopping. Stakeholders have experience in virtual meetings and workshops, so the risk of significant impact is considered low. The role that the project potentially plays in promoting and supporting stakeholder engagement during COVID restrictions can be significant in supporting stakeholders during future pandemics and/or the recovery efforts following pandemics and other disasters (flood and drought etc). |

Stakeholder engagement

The stakeholder engagement plan, which is included as Annex 7, is summarised in the following paragraphs. In Namibia there are a number of emerging Issues pertaining to Stakeholder Participation in the Cuvelai and Kunene River Basins that have been identified.

Key barriers to gender responsive and inclusive engagement of stakeholders in planning and decision making of water resources include

The major bottleneck to effective stakeholder participation in the planning and management of water resources in the two basins is the limited awareness of the multi-stakeholder platforms (Basin Management Committees) in the case of the Cuvelai basin, and the absence of the Basin Management Committees in the Kunene River basin.

Water sector policies and strategies recognise the need for inter-sectoral coordination between key line ministries but collaboration between authorities with the responsibility for environmental management, public health, agriculture, land-use planning and land management, urban and rural water supply is weak and undermines efforts for comprehensive planning and management of water resources and ecosystem services alike.

The Cuvelai basin has well-established structures such as water committees and sub-committees, but ineffective communication channels remain a bottleneck. Lack of internet access is a limiting factor and there is a need to use traditional media.

To enhance dialogue, the use of smaller group discussions, visual aids, and translators is needed to improve dialogue between and amongst stakeholders attending meetings in the two adjacent basins, being mindful of the asymmetrical power relations emanating from cultural, legal, and gender dynamics in the two sub-basins.

Representation of stakeholders at Basin Management Committee meetings and forums will remain elusive to the most marginalised stakeholder groups in the absence of adequate budget.

Consultations with basin stakeholders revealed that stakeholders have varying technical capacities, and one way to bridge this gap will be to undertake exchange visits amongst basin stakeholders. Experience has shown that exchange visits amongst stakeholders, where persons interested in the same challenges can speak on a one-to-one basis, are a powerful mechanism for enhancing capacity and information exchange.

Stakeholders also proposed the implementation of targeted on-going training covering both technical issues relating to the sustainable planning, utilisation, and management of water and other basin resources.

Key Consideration for Strengthening Stakeholder Engagement for the CUVKUN Project include:

Ensuring that existing multi-stakeholder platforms such as the basin management committees in the Cuvelai are strengthened and establishing new ones in the Kunene River basin would be important for the sustainability of the project. There is also a need to tap into the existing relations between Angola and Namibia such as the PJTC.

CUVECOM, PJTC, can draw lessons from other established RBOs such as ORASECOM and ZAMCOM in terms of models for effective stakeholder engagement in the planning and management of water resources and ecosystems.

Participation for activities targeting grassroot level stakeholders should be fostered. This participation should take cognizance of the underserved population groups in the Kunene regions and specific needs of the huge population in the Cuvelai basin. The current project focuses on empowering local institutions to develop and implement resource management decisions. Thus, in establishing and strengthening the NASC, Joint basin Forum, and Basin Management Committees, careful consideration shall be made to ensure these multi-stakeholder platforms have broad representation of key stakeholders. In addition, effort shall be made to ensure that the underserved population groups such as the indigenous populations, elderly, people living with disability and unemployed are represented.

It has been argued that capacitating stakeholders is key to progressive and meaningful stakeholder dialogues to take place in transboundary basins. If well-structured and executed, capacity building initiatives can transform top-down approaches to the planning and management of water resources and ecosystem services in the Basin.

Creating a platform where stakeholders meet and voice their opinions not only enriches the quality of discussions held but also enables authorities to make well informed decisions that will not face a hostile community. This approach will also benefit those community members with low literacy levels. This action will in the long term contribute to the successful operationalisation of the subsidiarity principle.

Gender equality and social inclusion principles must also be integrated in the development of the SAP, NAP and IWRM Plan and this can be done through the involvement of gender experts in the development of such policy documents.

Platforms for Information Disclosure

Platforms Inception Phase

A regional project inception meeting shall be convened: This meeting will be a strategic platform to update project partners and stakeholders on the project scope including concept, objectives, components, and outputs. The meeting can be used to endorse any changes to project annexes if any. This meeting will also serve to ensure stakeholders have a common understanding of the project delivery structure, the linkages, and the roles and responsibilities of each partner including reporting requirements. The meeting will be used to finalize detailed project work plans, budgets, and quarterly forecasts for the first year of the project. Lastly, the inception meeting will discuss the communication and visibility plan as well as the knowledge management approach for project partners and executing agency.

In-country inception meeting: An inception workshop shall be convened to update country- level stakeholders on the scope of the project including its goals, objectives, and planned activities. Efforts shall be made to convene these meetings in the basin to ensure basin-level stakeholders are appropriately informed of the project.

Implementation Phase

Stakeholder Engagement Training Targeting the NASC: Targeting training on stakeholder analysis and stakeholder engagement will be conducted targeting the NASC, and the governance structures of CUVECOM, the JPTC, and the PCU.

Development of an Interactive Online Platform: A dedicated webpage /shall be developed for the CUVKUN project to enable users to find all the information about the project in a central place. The online platform will serve a dual purpose of sharing information about the project, as well as provide a platform for stakeholder feedback on the various activities undertaken by the project. This includes a platform to lodge grievances. All project data, decision-support tools and training materials will be made available through a project web platform to provide a single go-to reference point for the project. In addition, the project website will be linked to the websites of the Ministries responsible for water resources management in Kunene and Cuvelai River Basins.

Project Board Meetings: The Project Board shall convene meetings on a quarterly basis to approve work plans submitted by the PCU, as well as to take stock of progress made towards set targets. The Project Board shall provide strategic directions aimed at ensuring the project results are achieved in a timeous manner, and to recommend remediation actions where necessary.

Quarterly NASC Meetings: The Project Coordination Unit under the overall guidance of the Project Board and the Joint Basin Secretariat shall convene quarterly NASC meetings. The NASC meetings shall be used to guide processes as well as to validate project outputs.

Basin-wide Stakeholder Forum: The PCU under the overall guidance of the Project Board and the Joint Basin Secretariat shall convene bi-annual basin-wide stakeholders’ meetings. This Basin-wide stakeholder platform shall enable knowledge sharing across the basin.

SADC RBO Workshops: To strengthen South-South cooperation, CUVECOM, KUNENECOM, the Project Board, and the PCU will strengthen technical cooperation by attending SADC RBO workshops. Learning visits will also be convened where appropriate to collaborate and share knowledge, skills, and successful transboundary initiatives.

Project Closeout Phase

A regional project reflection meeting shall be convened: This meeting will be a strategic platform to reflect on the outputs, outcomes, and lessons learned. The findings of this workshop will inform any follow up work planned, as well as provide input into a project sustainability plan.

Project sustainability plan: The end of the GEF funding should not mark the end of the interventions. Thus, a Project Sustainability Plan shall be developed to ensure continuity of the project as well to ensure sustainability of results over a longer period.

Basin-level closeout meeting: A basin-level closeout workshop shall be convened. The purpose of project closeout workshop will be jointly assessed with the basin-level project the extent to which the project activities, outputs and results were realized, as well as to discuss any lessons learned and best practices to be applied to future projects.

The stakeholder engagement plan in Angola, promotes an inclusive and participatory engagement through project design and implementation. Stakeholder mapping and consultations were conducted at national level (Luanda), as well as in the Cuvelai and Kunene basins (Angola) in order to identify stakeholders and define their engagement within the CUVKUN project. The Stakeholder Engagement Plan identifies three different levels of engagement, as follows:

- Co-decision making engagement within the CUVKUN project

- Participation engagement within the CUVKUN project

- Consultation level engagement within the CUVKUN project

Key stakeholders’ groups identified include: i) potential beneficiaries, ii) key line ministries and local government, iii) traditional authorities and representatives of indigenous groups in the basins, iv) academia, v) CSO, women's groups as well as vi) development partners. The following groups are to be highlighted due to their potential high level of engagement:

Potential beneficiaries - The Permanent Joint Technical Commission (PJTC) for the Kunene River basin - The Cabinet for hydric Administration of Cunene, Cubango and Cuvelai rivers (GABHIC) - Institute for Agricultural Development / Instituto de Desenvolvimento Agrario (IDA) - Community-based water management Committees, including Consultative Community Councils or Conselhos de Auscultação das Comunidades (CACs)”, Civil Protection local response committees or “Comité Gestao de desastres"; Community Committees on Water and Sanitation / Community Management Model (MoGeCa) - Rural women organizations and rural cooperatives

Key line ministries and local government - The Ministry of Energy and Water (MINEA) - The Ministry of Agriculture and Fisheries - The Ministry of Women, Social Action and Family (MASFAMU) - Provincial Government Cunene - Provincial Government Huila - Provincial Cabinets for the environment and solid waste in Cunene and Huila - Provincial Cabinets for fisheries and Agriculture in Cunene and Huila - Municipality of Namacunde (Cuvelai basin) - Municipality of Ombadja (Kunene basin)

South-south cooperation

The proposed project is based on south-south cooperation and expresses the interests of both states to coordinate on and develop joint strategies to address common problems and pursue common approaches to opportunities. This interest is long-standing, especially in the case of the Kunene basin where close technical cooperation goes back more than 50 years.  The backbone of the project is the preparation of the Transboundary Diagnostic Analyses (TDA) and the IWRM Plan for the Cuvelai and Kunene River basins.  The project also includes a series of actions for the exchange of knowledge, experience and lessons among authorities and key stakeholders, and UNDP will catalyse this process by facilitating access to global experiences and motivating alliances among project participants. The use of the GEF IW: LEARN network, IW Experience Notes, and IW: LEARN website/database will underpin the knowledge management strategy of this project and support the TDA process.  The GEF International Waters Learning Exchange and Resource Network (IW: LEARN) provides critical support to International Waters projects through trainings, conferences, and information exchange opportunities.  In addition, in order to bring the voices of Angola and Namibia to global and regional fora, the project will explore opportunities for meaningful participation in specific events where UNDP could support engagement with the global development discourse on management of transboundary river basins.

Gender equality and Women’s Empowerment

Gender, inequality, land management, water resources management and sustainable environmental conservation are closely interrelated as women, men, the youth and people living with disability have unique dependencies and expertise regarding their environment in both basins. Women in particular play a significant role in providing, managing and safeguarding land, water and environmental resources. It is thus essential for any planned projects and programmes implemented in either basin to identify solutions aimed at enhancing the participation of women, youth and other disadvantaged groups in the planning and management of water and other natural resources in the Basin.  Annex 9 provides has the Gender Equity and Social Inclusion Reports as well as the Gender Action Plans for the project.

Summary of Gender Equity and Social Inclusion Report

In the Angolan portion of the basins the following key gender gaps have been identified through the Gender Analysis Angola:

Even if Angola has ratified most of international and regional instruments to promote gender equality and women’s empowerment and is adapting its national legal framework in line with SADC’s Gender Protocol and CEDAW’s recommendations, the status of women in the Kunene and Cuvelai basins is mainly regulated and influenced by Customary Law.

Customary Law is not always aligned with the Angolan Constitution, or international and regional standards.

The ambiguous customary practices, and the fact that rural women do not have knowledge or access to formal law and justice, promotes gender discrimination in the basins. Gender discriminatory practices are mainly related to family and property rights, equality and equity principles, access to services.

The climate emergency that is currently affecting Southern Angola (Cunene and Huila provinces) due to the severe drought (Seca) is hitting vulnerable population, and women are in the front line.

In 2012, a GIZ report indicated that 4 km was the maximum distance that women and girls walked in the Angolan Cuvelai basin to reach water points. The drought affecting the Cunene and Huila provinces (Seca) has increased water scarcity and has reduced the number of water points with clean water available.

Women are responsible to provide water to families, but their engagement in community committees on water management and sanitation, and early warning systems is very low.

Rural women in the basins do not access to property rights. In fact, “women in Cunene comprise 54% of the agriculture labour force”, but they are not landowners at the same rate. In Huila province: 40% of women cultivate land that does not belong to them, and 70% of men versus 40% of women cultivate land obtained through inheritance.

Summary of Gender Action Plan

For the Angolan portion of the basins the Gender Action Plan (GAP) can be summarised as follows:

The project will contribute to gender mainstreaming efforts in the basins, through the development of two tailored Gender Strategies, one for CUVECOM and one for KUNENECOM.

The Gender Analysis completed during the project preparation phase has informed the Gender Action Plan Results Framework.

The Results Framework includes effective gender-sensitive indicators, and project interventions include gender-responsive measures to address gender gaps identified through the Gender Analysis and to promote gender equality and women’s empowerment in the Cuvelai and Kunene basins.

The project will include gender-responsive measures to address gender gaps and promote gender equality and women’s empowerment, including improving women’s participation and decision making.

The proposed project will focus on strengthening the role of women in IWRM in the Kunene and Cuvelai basins, with emphasis on their role on governance and decision making of future projects and investments in the basin. It will collect gender-sensitive data, and will build gender equality capacities of IWRM institutions to promote gender equality through project implementation

The project will strengthen women’s beneficiaries’ capacities to ensure meaningful participation, leadership and engagement through project implementation.

A number of activities were identified in the Gender Action Plan (GAP), in line with Project’s components as provide below:

Summary of Activities under the Gender Action Plan (GAP) for Angola

Develop a gender-transformative “Flood early warning system (EWS)”.

Conduct training on “sex disaggregated data-collection, gender-sensitive data-gathering, gender analysis and gender transformative planning” for personnel in the Angolan water management institutions.

Develop and implement Gender Mainstreaming Strategies for CUVECOM and KUNENECOM.

Conduct a Gender Equality Capacity Needs Assessment (CNA) to personnel at the Angolan institutional structures (CUVECOM, KUNENECOM, GABHIC).

Develop a Gender Equality Capacity Development Plan to personnel at the Angolan institutional structures (CUVECOM, KUNENECOM, GABHIC)

Conduct a tailored training on Gender Equality to personnel at the Angolan institutional structures (CUVECOM, KUNENECOM, GABHIC), in line with capacity gaps identified.

Develop and conduct tailored training on gender equality and women’s rights to participants at the sustainable land management activities at pilot sites in Angola.

- Subject areas include Access to rights, services, and assets (civil registry, land, livestock and water), gender discriminatory practices in the Angolan basins.

Conduct tailored training and promote discussions on gender equality and women’s rights to 20 selected Angolan traditional leaders (Sobas) at the pilot sites.

- Subject areas include Access to rights, services, and assets (civil registry, land, livestock and water), and gender discriminatory practices in the Angolan basins (identified at the Gender Analysis Angola)

Conduct a Capacity Needs Assessment (CNA) to all women participants at the sustainable land management activities at the pilot sites, to identify critical capacity gaps that can jeopardize female participation and leadership in project activities.

Develop gender-sensitive Policy briefs and Communication products, to sensitize stakeholders on Gender Equality, women’s rights, and empowerment

- Namibia has made significant progress towards gender equality and the empowerment of women and the girl child in the last two decades. The country progressed in the gender equality agenda as demonstrated by the establishment of gender-sensitive policies and programmes, ratification of international, continental, and regional frameworks, as well as the establishment of a gender machinery which has, among other things, spearheaded the reform of various laws to make them gender-sensitive (GRN, 2022).

Time Use and the Gendered Division of Labour

The Gender and Social Inclusion Analysis done for the CUVKUN project revealed that gender inequality in the Cuvelai and the Kunene River Basins in Namibia are rooted in the injustices preceding the country’s independence, where women did not have the same rights in decision making or hold equal access to financial, material and information resources a position that was affirmed in studies by Angula (2010).

Most of the Kunene and Cuvelai basins are rural areas, with livelihoods dependent mainly on the available natural resources.  Women are traditionally responsible for taking care of the family household and are the primary users of environmental resources. Men on the other hand mostly engage with livestock farming related activities. Women and girls have the traditional responsibility of water collection and in areas with water scarcity, often travel long distances to get to the nearest source for domestic purposes.

Gendered Access to and Control of Resources in the Cuvelai and Kunene River Basins

For agriculture, women have relatively less access to productive resources and opportunities in the regions covering both Cuvelai and the Kunene River basins. Despite distinct and progressive policies, legislation, and programmes to promote gender equality in the household, in communities, and society at large, women, the youth, children, and people living with disability are predominantly ascribed lower positions in family set ups and public settings alike.

For participation of women and men in productive work, limited mobility impacts women’s participation in productive activities. Women, and people with disability tend to take up economic opportunities closer to their homes, whilst men in general, and the Kunene region are known to take up employment opportunities in urban areas. Thus, limited mobility of women and people with disability makes such groups more vulnerable, and less able to adapt in the face of extended droughts or other natural disasters.

Gender Equality and Social Inclusion Mainstreaming in Water Resources Planning & Management at Basin Scale

- The Cuvelai Watercourse Commission and the Permanent Joint Technical Commission (PJTC) have not developed Gender Equality and Social Inclusion (GESI) strategies to guide GESI mainstreaming in the planning and management of water resources. The Water Resources Management Act of 2013 places emphasis on the need to employ participatory approaches when establishing Basin Management Committees (BMCs). However, in practice, no special efforts have been made to ensure gender equality and social inclusion when convening BMC meetings, and in the broader planning and management of water resources in the Cuvelai basin. The situation is worse in the Kunene River Basin, where Basin Management Committees have not been established as yet.

Table 2: Gender Action Plan

| Strengthening the water security and resilient livelihoods of the populations in the adjacent Kunene and Cuvelai river basins through improved transboundary and conjunctive water resources management | Establish a high-level GESI committee/ task team to guide GESI policy formulation, programming, and implementation thereof for the CUVKUN project, CUVECOM, and KUNENECOM.[1] |
| --- | --- |
|  | Establish GESI responsive National Steering Committees and Basin Steering Committees to guide the updating of the TDA and IWRM Plan for Cuvelai Basin, as well as the development of the TDA and SAP and IWRM Plan for the Kunene River basin. |
|  | Strengthen inclusive management of transboundary water resources through the establishment of GESI responsive Basin Management Committees in the Kunene River basin. |
|  | Strengthen capacity of vulnerable women, men, the youth, and people with disability to meaningfully participate in multi-stakeholder platforms through participatory training. |
|  | Conduct a GESI responsive assessment of opportunities for conjunctive and ground water use for domestic and productive purposes. |
| Strengthening the transboundary water resources management with future development scenario analysis in the Kunene River basin | Map the GESI impacts of floods, and existing early warning systems. |
|  | Ensure representation of socio-economic and GESI expertise in the development of the TDA, NAPs, and IWRM Plan for the Kunene Basin. This includes a detailed socio-economic and GESI assessment to better understand the GESI impacts of sedimentation and increased dissolved minerals in the Kunene River. |
|  | Conduct consultations with vulnerable women, men, youth, and people with disability in the in undertaking of water resources development scenario analyses in the Kunene river basin. |

Innovativeness, Sustainability and Potential for Scaling Up

Innovation

Pre-emptive engagement to sustain one of Africa’s water towers: A key area of effort is focused on preventing further degradation and promoting conservation in the source areas of the two rivers in Angola. These areas form part of the central plateau water tower in Angola. This provides a win-win in several respects. From as transboundary perspective the improved health of the catchment in the headwaters translated into reduced floods and increased baseflow downstream in Namibia (or on the joint border). The reduced levels of erosion in Angola also translated into reduced sedimentation downstream, an advantage especially in the Kunene River. Within the upland areas the win-win is between the environment and livelihoods with an improved status of the natural resource base supporting improved levels of productivity for farmers.

Positive community engagement and support through action on the ground: Considerable attention has been paid to relating the TDA work and strategic IWRM thinking to action on the ground. Beneficiary stakeholders, the communities, have in many cases been exposed to consultative sessions aimed at ensuring that their concerns and interests are taken into account in the planning process but they are now becoming impatient and want to see that these processes are able to bring progress and action. The proposed programme includes a significant component of community level pilot demonstration projects aimed at improving livelihoods and water security (better access to safe water and better protection from floods). The actions are related to the work of the TDAs and will be scaled up as part of the IWRM plans.

Heightened visibility for greater support - Emphasis on CUVECOM and PJTC as coordination bodies and drivers of action at the local level: It is proposed that CUVECOM will be the key coordinating body for the promotion and implementation of the Community-based projects and that they will play an important role in ensuring that national and regional reference groups are active in the support of the Component 5 actions. It is proposed to have a community liaison officer within the CUVECOM Secretariat for the course of the programme, whose job will be to drive the consultation around, and the implementation of the Component 5 projects. Achieving improvements for the communities will be effective in rapidly increasing the visibility and credibility of CUVECOM and the PJTC and this will, in turn, support the sustainability of these institutions.

Communications Technology. The proposed early warning system for flooding will make use of mobile phone technology to support both real-time data collection and the provision of real-time early warning to communities.

Sustainability

The firm commitments of both governments in the recent establishment of CUVECOM and the long history of the PJTC for the Kunene basin provides a strong basis for the sustainability of impacts, in particular transboundary benefits, delivered by this project.  Therefore, the project interventions will be designed to support and catalyse the Governments’ various efforts to strengthen CUVECOM and the PJTC’s institutional, technical and operational capacity.  For each intervention proposed in this project, how the expected results delivered by the intervention will be sustained beyond the project duration has been considered, which will contribute to the Sustainability Strategy of the project when that is developed during the project preparatory phase.   During the project preparatory phase, these considerations will be expanded in more details through discussions with the governments and stakeholders.

Some outputs proposed in this project will directly contribute to the sustainability of the two RBOs. The relatively weak institutional and development status of the Angolan portion of both basins is recognized by the project and also by the Angolan Government which has defined the concerned provinces as priorities for development. This will greatly enhance the sustainability of development and management efforts. The two IWRM plans will provide long-term strategies that will guide future investments in the basin by the governments, private sector, and international cooperation partners so that these investments will collectively contribute to the achievement of the Vision for the basin.  Future development scenario analysis, to be included in the TDA, will also influence the policy discussions and decisions on the future development trajectory and strategy at the basin level, which will have a long-lasting impact.

A strong focus on management of the Bie Plateau water tower in Angola is critical in supporting the sustainable development of water resources in the two basins, especially the Kunene River basin.

Potential for scaling up:

All the proposed IWRM Plan demonstration activities under Component 5 are designed with the replicability and scalability in mind. Each of the proposed IWRM demonstration activities (livelihood-based watershed management, floodwater harvesting, aquaculture and flood early warning) will address targeted priority issues for the two basins (land degradation in the Kunene and lack of water and food security in the dry season and flood early warning in the wet season in the Cuvelai), identified during the scoping studies for the first Cuvelai IWRM Plan and through various studies in the Kunene basin. The demonstration, with its limited investment scale and limited geographical scope, will not be expected to yield significant stress reduction results at the basin scale, but it will be expected to present quantifiable evidence to support potential environmental and transboundary benefits from these investments, if replicated and upscaled across the basin at a scale that matters.  It will also aim to demonstrate how various stakeholders in the basin can actively take part in the IWRM implementation in practice in general, and in stress reduction activities in particular.  They will also reinforce the visibility of CUVECOM and the PJTC in the basin and among the basin populations, which will in turn facilitate the role of these institutions in supporting the scale-up efforts.  The best practices and lessons learned from the demonstration projects will be codified and disseminated to further promote the replication potential.

The use of pilot demonstration projects and their scaling up is a thread running through the recently published first Cuvelai IWRM Plan. The concept has already been discussed and agreed with stakeholders during meetings in 2018, 2019 (and earlier).

# V	Project Results Framework

|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target |
| --- | --- | --- | --- | --- |
| Project Objective: To strengthen the water security and resilient livelihoods of the populations in the adjacent Kunene and Cuvelai river basins through improved transboundary and conjunctive water resources management | Indicator 1 (GEF7 core indicator 11): # of direct project beneficiaries disaggregated by gender (individual people) | 0 persons directly benefitting from project activities | 9,500 persons directly benefitting from project activities (10 x 150 for pilot demonstration projects and 4 x 2,000 for community flood warning (50:50 gender split) | 19,000 persons directly benefitting from project activities replication at 10 sites + 4 more communities fir flood warning (50:50 gender split) |
|  | Indicator 2 (GEF7 core indicator 11): # of indirect project beneficiaries disaggregated by gender (individual people) | 0 persons indirectly benefitting from project activities | 47,500 | 85,000 |
|  | Indicator 3 (GEF7 Core Indicator 4): Area of land restored (Hectares) | 0 hectares of land restored at project pilot sites | Land restoration plans finalized for at least 6 pilot sites (note: sites for water harvesting may do limited restoration). Estimate of 1,000 ha woodland/forest per site + 500 ha pasture/agricultural land per site = Total of 9000 ha | Mid-term land restoration plans implemented Land restoration plans finalized for at least 6 additional sites; 18,000 ha in total |
|  | Indicator 4 (GEF7 Core Indicator 5): Area of landscapes under improved practices (excluding protected areas) (Hectares) | 0 hectares of land under improved practices at project pilot sites | Land under improved practices for at least 6 pilot sites (note: sites for water harvesting may do more limited areas of improved practices). Est. of 1,500 ha per site = 9,000 ha + 4 x 500 ha = 2,000ha (total= 11,000ha) | Land under improved practices for at least 12 pilot sites (note: sites for water harvesting may do more limited areas of improved practices). Est. of 750ha per site = 18,000 ha + 8 x 500ha km2 = 4,000 ha (total=22,000ha) |
|  | Indicator 5 (GEF7 Core Indicator 7): Number of shared water ecosystems under new or improved cooperative management (7.1 Level of Transboundary Diagnostic Analysis and Strategic Action Program (TDA/SAP) | Preliminary TDA and IWM Plan exists for Cuvelai Basin | TDA finalized; IWRM plans submitted for review for both basins | Full IWRM Plans completed and endorsed at the Ministerial level |
| Project Component 1 | Strengthening the transboundary and conjunctive water resources management in the Cuvelai River |  |  |  |
| Outcome 1.1: Two countries committed to the joint management of the transboundary Cuvelai River basin with a focus on the improved resilient community livelihoods, based on the best available science and knowledge | Indicator 9: Critical knowledge gaps filled in the following areas to support joint planning and analysis of the Cuvelai River Basin: - Transboundary groundwater assessed and mapped. - Opportunities for conjunctive use identified and planned - Flood risk mapping and early warning system in place and operational | - Groundwater in both countries has been partially assessed (BGR Phase 1 study in Namibia, various scattered investigations in Angola) +/- 25% of sustainable potential identified with confidence - Significant knowledge gaps - Some flood mapping exists but accuracy affected by poor knowledge of the hydrology. Lack of gauging sites, especially in Angolan portion - No transboundary flood warning system | - BGR Phase 2 study completed and results available for analysis - Improved and complete flood risk mapping based on improved but far from perfect hydrological records. - Flood early warning system set up in Beta mode for further testing and calibration. - Most knowledge gaps filled | - Improved knowledge of groundwater in both countries following BGR Phase 2 study 60% of sustainable potential identified with confidence - Flood risk mapping established - Transboundary Flood early warning system fully functional - All significant knowledge gaps filled - IWRM plan revised and updated - 5 Year Investment plan (2025-29) finalised and endorsed |
| Outputs to achieve Outcome 1.1 | 1.1.1 Groundwater quality and availability assessed in both countries 1.1.2 Operational water resources model for quantity and flood routing/mapping covering the entire basin 1.1.3 Revised TDA (existing rapid assessments (equivalent to preliminary TDA)) updated, including the Causal Chain analyses (CCA), and emphasis on conjunctive ground/surface water management) 1.1.4 Operational (development and testing complete) real-time transboundary flood early warning system in place 1.1.5 The long-term Cuvelai IWRM Plan (2020-2039) endorsed at the ministerial level; National Action Plans (NAPs), the 2nd 5-year IWRM Plan and Investment Plan (2025-2029) developed (updated (including an investment plan). Roundtable with potential investors and partners organized |  |  |  |
| Project Component 2 | Strengthening the transboundary water resources management with future development scenario analysis in the Kunene River basin |  |  |  |
| Outcome 2.1: Two countries committed for the joint management and sustainable development of the transboundary Kunene river basin, based on the best available science and knowledge | Indicator 9: Critical knowledge gaps filled in the following areas to support joint planning and analysis of the Kunene River Basin: - Ecological water requirements - Sediment transport - Future water resources development - Hydropower development | - Ecological flow requirements not evaluated or only partially identified - Very limited data on sediment transport - Other Significant knowledge gaps - Water resources development plans exist and some systems analysis has been carried out at national levels. - Lack of up-to-date transboundary hydropower development plan - Preliminary stakeholder mapping and consultation (incl. under GIZ support) - Rapid analysis and identification of gaps completed under GIZ support (2022/23) - Preliminary IWRM Plan developed under GIZ support (2022/23) | - Site for ecological flow requirements selected and assessed, and preliminary results available - 2 seasons of sediment transport data collected - Most knowledge gaps filled - Water resources management scenarios have been run and assessed and fed into draft transboundary hydropower development and management plan - Most knowledge gaps filled - At least 50% of planning team for EWS are women | - Improved knowledge of groundwater in both countries following BGR Phase 2 study 60% of sustainable potential identified with confidence - Flood risk mapping established - Transboundary Flood early warning system fully functional - 50% of those managing EWS are women - All significant knowledge gaps filled - Preliminary IWRM Plan (GIZ supported), revised and updated - Investment Plan (2025-29) agreed and endorsed |
| Outputs to achieve Outcome 2.1 | 2.1.1 Ecological water requirements at +/- 10 key locations along the river system are investigated and established 2.1.2 Future water resources development scenario analyses for planning and establishment of DSS (including linked hydromet) for operations management completed 2.1.3 TDA produced (including the future development scenario analysis and causal chain analysis). 2.1.4 A long-term IWRM Plan (2025-2040) and 2 NAPs negotiated and endorsed at the ministerial level 2.1.5 5-year investment plan developed and a roundtable with potential investors and partners (aimed at resource mobilization for implementation of the IWRM Plan) organized |  |  |  |
| Project Component 3 | Strengthening the governance of the Cuvelai and Kunene River Basins to foster joint management by the two countries in the most cost-effective manner |  |  |  |
| Project Outcome 3.1 Intergovernmental institutional structure set up in a financially sustainable manner to foster joint management of the Cuvelai and Kunene basins by the two countries | Indicator 6: A fully operational CUVECOM and “Kunene Commission joint secretariat that is able to coordinate initiatives, institutions and International Cooperating Partners (ICPs) in a harmonized manner and promote IWRM principles in the Cuvelai and Kunene River Basins. | - CUVECOM has established a Secretariat with 5 full-time staff, Head office in Oshakati and a satellite office in Ondjiva. The CUVECOM Council and Technical Task Team (TTT) both meet on a regular basis. CUVECOM has a website and accessible resources but there is no information management system to share available data and information - Kunene Basin has no Commission or Secretariat, the transboundary PJTC meets regularly. | - Institutional Functional Analysis for CUVECOM and Kunene Commission to suggest a sustainable structure for the Joint Secretariat complete - an adequate internet connection and a suite of virtual tools and digital solutions for communication and coordination between all offices - Joint Secretariat for the CUVECOM and Kunene Commission formed and strengthened with the establishment of the Operational and Financial Management Structure (Accounting Systems, Procurement Systems, Financial Management Systems, HR Policies & Manuals, Host Country Agreement, etc - All preparatory work for the transformation of the PJTC into a river basin commission for Kunene Basin is complete - At least 50 % of personnel within Intergovernmental institutional structure trained in Gender Equality Capacity needs | - Cuvelai Watercourse Commission (CUVECOM) fully capacitated and sustainable - Permanent Joint Technical Commission (PJTC) transformed into Kunene Commission and sustainable - Joint secretariat fully functional and sustainable - 100 % of personnel within Intergovernmental institutional structure trained in Gender Equality Capacity needs |
|  | Indicator 7: Data sharing protocol to support joint planning and management and address three core challenges for the Cuvelai River Basin (disasters; water quality problems; water scarcity) | - There is no established mechanism for sharing information throughout the basin and across sectors, or for analysing data in an integrated manner. - Data sharing is adhoc on by request basis | - Information Management Systems established - Data sharing protocol to support joint planning and management in both basins drafted and agreed | - Data sharing protocol to support joint planning and management in both basins formally endorsed |
|  | Indicator 8: National Stakeholder Coordination Committees (NASCs) in each Member State, and a Basin-wide Stakeholder Committee (BASC), established to guide SAP and NAP development and negotiation and to make basin management decisions based on those documents | - No formal transboundary national or regional structures exist to coordinate multi-sectorial stakeholders on issues specific to the two basins - National and Regional working groups established for inouts to project Document - Basin management committees (BMCs) in place in Namibia in portions of Cuvelai River basin - Cooperation between UNAM and Universidade Agostinho Neto established for Cuvelai Basin - Gender Analysis undertaken and Gender Action Plan developed | - National Stakeholder Coordination Committees (NASCs) established in each Member State - Basin-wide Stakeholder Committee (BASC), established to guide IWRM Plans and NAPs development and negotiation and to make basin management decisions based on those documents - NASCs to comprise at least 50% women - BASC to comprise at least 50% women - Cooperation between UNAM and Universidade Agostinho Neto established for Cuvelai Basin and CUVECOM and PJTC formalised through MoU - Gender equality and women empowerment efforts mainstreamed into all CUVECOM and Kunene Commission policies and practices through the development and implementation of the Gender Strategy | - Universities and CUVECOM and Kunene Commission carrying out joint research work - At least 4 student interns working in Joint Secretariat |
| Outputs to achieve Outcome 3.1 | 3.1.1 Transboundary governance structures developed and functioning 3.1.2 Joint Secretariat for the CUVECOM and Kunene Commission formed and strengthened with the establishment of the Operational and Financial Management Structure (Accounting Systems, Procurement Systems, Financial Management Systems, HR Policies & Manuals, Host Country Agreement, etc). 3.1.3 Assessment of national legislation, policies, strategies and plans and assessment of transboundary harmonization needs 3.1.4 Information Management Systems established 3.1.5 Effective and productive cooperation between universities and with CUVECOM and PJTC/Kunene Commission 3.1.6 Gender equality and women empowerment efforts mainstreamed into all CUVECOM and Kunene Commission policies and practices through the development and implementation of the Gender Strategy |  |  |  |
| Project Component 4 | Strengthening institutional, technical and operational capacity in Angola to sustainably develop and manage the sub-region’s water tower located in southern Angola |  |  |  |
| Outcome 4.1: Capacity in water resources and environmental management in Angola strengthened | Indicator 9: Critical knowledge gaps filled in the following areas to support joint planning and analysis of the Kunene River Basin in Angola: - Hydrology, climate and water quality of source areas in both basins, especially Kunene - Changes in land use and land cover in source areas in both basins, especially Kunene, - Detailed information on livelihoods and economic activities insource areas of Kunene - Limited technical capacity in data collection and analysis, GIS and water resources modelling - No systematic economic Valuation of the ecosystem goods and services provided by the Angolan Highlands ecosystem | - Very limited hydrological and water quality data collection in Kunene headwaters - Land use and land cover in Upper Kunene not systematically mapped - Detailed information on livelihoods and economic activities insource areas of Kunene not systematically mapped | - Additions to hydrology, climate and water quality of source areas in both basins, especially Kunene designed and implemented - Historic changes in land use and land cover in source areas in both basins, especially Kunene mapped - Detailed information on livelihoods and economic activities insource areas of Kunene mapped Training in data collection and analysis, GIS and water resources modelling provided to 4 participants - Work on valuation of the ecosystem goods and services provided by the Angolan Highlands ecosystem underway | - At least 3 years of hydrological, water quality and climate data collected and analysed for Kunene water tower - Valuation of the ecosystem goods and services provided by the Angolan Highlands ecosystem complete, approved and published |
| Outputs to achieve Outcome 4.1 | 4.1.1 Ecosystem-based approach to protect water towers in southern Angola (through awareness raising & strengthened institutional capacity) successfully promoted 4.1.2. Technical capacity in GIS, water resources modelling, and E-Flow assessment strengthened 4.1.3 Data collection and analysis capacity strengthened 4.1.4 Economic Valuation of the ecosystem goods and services provided by the Angolan Highlands ecosystem |  |  |  |
| Project Component 5 | Enhancing the community participation in IWRM to build resilience in their livelihoods |  |  |  |
| Outcome 5.1: Livelihoods enhanced, and community resilience improved through community-driven activities | Indicator 14: Percentage of women participating in sustainable land management activities at the pilot sites | 0 at start of project | - 30% women participating | - 50% women participating |
|  | Indicator 15: Number of farms with improved conditions due to the adoption of sustainable land management practices | 0 at start of project | - 30 household level small farms for each pilot demonstration x 6 = 180 small farms as part of livelihood-based watershed management projects - 4 communities participating in Water (rainwater and/or flood water) harvesting incorporating community-based aquaculture | - Doubled to 360 small farms as part of livelihood-based watershed management projects - 8 communities participating in Water (rainwater and/or flood water) harvesting incorporating community-based aquaculture |
| Outputs to achieve Outcome 5.1 | 5.1.1 Gender-responsive Community-driven interventions to improve their resilience and livelihoods (especially those of women) identified and implemented 5.1.2 - Capacity strengthened in the Secretariat to ensure the sustainability of basin community engagement and community-driven activities to implement the IWRM Plan 5.1.3 - Piloting of gender-responsive and inclusive flood early warning system for communities in selected hotspot settlements with the system operational for at least 4 hotspots basinwide. |  |  |  |
| Project Component 6 | Outreach and Knowledge Management for replication, upscaling and stakeholder engagement |  |  |  |
| Outcome 6.1: Stakeholder engagement strengthened through targeted communication and Replication and upscaling supported through exchange of knowledge, best practices and lessons learned | Indicator 16: Formal exchange visits by CUVECOM and new commission for Kunene representatives to other River Basin Organizations and regional institutions in southern Africa to share knowledge and facilitate replication of project lesson learnt | River Basin Organizations and regional institutions in southern Africa hold a bi-annual RBO workshop and participate in SADC Water Resources Technical Committee (WRTC) meetings and SADC Water Dialogue meetings; some also participate in annual Stockholm World Water Week (SWWW) | - Stakeholder Engagement Strategy and Communication Strategy (fully incorporating gender-related recommendations) published - At least 2 official exchange visits with other RBOs and relevant regional institutions undertaken - Participation by CUVECOM and new commission for Kunene representatives in at least 2 regional and global events (e.g. SWWW; GEF IW Conference) | - Stakeholder Engagement Strategy and Communication Strategy reviewed (with inputs from gender experts) and updated edition published. - At least 4 additional official exchange visits with other RBOs and relevant regional institutions - Participation by CUVECOM and KUNUNECOM representatives in at least 2 additional regional and global events |
|  | Indicator 17: # of knowledge products disseminated to relevant national, regional and global stakeholders | Brochures dealing with floods in the Cuvelai River Basin have been developed and disseminated | - At least 5 knowledge products produced and shared. These should include 3 targeted policy briefs connecting science to management and policy discussions. Other knowledge products on key scientific outputs such as E-Flows in Kunene, Flood early Warning system in Cuvelai, - 45 % of Policy B2iefs and Communications Products include sensitization messages on gender equality, women’s rights and empowerment | - At least 10 additional knowledge products produced and shared. These should include 4 targeted policy briefs connecting science to management and policy discussions. Other knowledge products in addition to mid-term targets, to include report on scenario analysis and development choices and groundwater assessment of the transboundary Cuvelai basin. - 65 % of Policy Briefs and Communications Products include sensitization messages on gender equality, women’s rights and empowerment |
| Outputs to achieve Outcome 6.1 | 6.1.1 Stakeholder Engagement Strategy and Communication Strategy developed (based on the Stakeholder Engagement Plan and Gender Action Plan developed during PPG), with participation of women and gender experts; SESP strengthened. 6.1.2. Targeted policy briefs and communication products produced. 6.1.3 Exchanges with other RBOs and relevant regional institutions, in particular with RBOs in SADC region, SADC Groundwater Institute, and other TB river basins with headwaters in Angola. Communications with all parties up and running. 6.1.4 Active contribution to the learning and knowledge sharing activities and events organized by the GEF IW: LEARN, including the GEF IWC (at least 1% of the project budget) 6.1.5 Timely Project M&E to inform adaptive management for successful delivery of project results, including MTR and TE. Monthly Project results and knowledge products developed and disseminated nationally, regionally and globally |  |  |  |

# VI	Monitoring and Evaluation (M&E) Plan

The project results, corresponding indicators and mid-term and end-of-project targets in the project results framework will be    monitored annually and evaluated periodically during project implementation. If baseline data for some of the results indicators are not yet available, they will be collected during the first year of project implementation as part of the work being carried out to prepare the TDAs in each basin. The Monitoring Plan included below details the roles, responsibilities, and frequency of monitoring project results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office is responsible for ensuring full compliance with all UNDP project monitoring, quality assurance, risk management, and evaluation requirements.

Additional mandatory GEF-specific M&E requirements will be undertaken in accordance with the GEF Monitoring Policy and the GEF Evaluation Policy and other relevant GEF policies. The costed M&E plan included below, will guide the GEF-specific M&E activities to be undertaken by this project.

In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report.

Additional GEF monitoring and reporting requirements:

Inception Workshop and Report:  The Project Inception Report will be made available in both English and Portuguese languages.  A project inception workshop will be held within 60 days of project CEO endorsement, with the aim to:

- Familiarize key stakeholders with the detailed project strategy and discuss any changes that may have taken place in the overall context since the project idea was initially conceptualized that may influence its strategy and implementation.

- Discuss the roles and responsibilities of the project team, including reporting lines, stakeholder engagement strategies and conflict resolution mechanisms.

- Review the results framework and monitoring plan.

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP and other stakeholders in project-level M&E.

- Update and review responsibilities for monitoring project strategies, including the risk log; SESP report, Social and Environmental Management Framework and other safeguard requirements; project grievance mechanisms; gender strategy; knowledge management strategy, and other relevant management strategies.

- Review financial reporting procedures and budget monitoring and other mandatory requirements and agree on the arrangements for the annual audit.

- Plan and schedule Project Board meetings and finalize the first-year annual work plan.  Finalize the TOR of the Project Board.

- Formally launch the Project.

GEF Project Implementation Report (PIR): The annual GEF PIR covering the reporting period July (previous year) to June (current year) will be completed for each year of project implementation. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR. The PIR submitted to the GEF will be shared with the Project Board. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

GEF Core Indicators: The GEF Core indicators included as Annex will be used to monitor global environmental benefits and will be updated for reporting to the GEF prior to MTR and TE. It should be stressed that the project team will be responsible for updating the indicator status. The updated monitoring data should be shared with MTR/TE consultants prior to the evaluation missions, so these can be used for subsequent verification. The methodologies to be used in data collection have been defined by the GEF and are available on the GEF website.

Independent Mid-term Review (MTR): The terms of reference, the review process and the final MTR report will follow the standard templates and guidance for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). The evaluation will be ‘independent, impartial and rigorous. The evaluators that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project under review. The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the evaluation process. Additional quality assurance support is available from the BPPS/GEF Directorate. The final MTR report and MTR TOR will be publicly available in English and will be posted on the UNDP ERC in June 2027. It will also be translated into Portuguese language. A management response to MTR recommendations will be posted in the ERC within six weeks of the MTR report’s completion.

Terminal Evaluation (TE): An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance for GEF-financed projects available on the UNDP Evaluation Resource Center. The evaluation will be ‘independent, impartial and rigorous. The evaluators that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. Equally, the evaluators should not be in a position where there may be the possibility of future contracts regarding the project being evaluated. The GEF Operational Focal Point and other stakeholders will be actively involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the BPPS/GEF Directorate. The final TE report and TE TOR will be publicly available in English and posted on the UNDP ERC by April 2029.  It will also be translated into Portuguese language. A management response to the TE recommendations will be posted to the ERC within six weeks of the TE report’s completion.

Final Report: The project’s terminal GEF PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

| GEF M&E requirements | Indicative costs (US$) | Timeframe | Responsible Entity |
| --- | --- | --- | --- |
| Inception Workshop | 10,000 | Within 60 days of CEO re-endorsement of this project | PMU |
| Inception Report | None | Within 90 days of CEO re-endorsement of this project | PMU |
| M&E of GEF core indicators and project results framework | 45,000 | Annually and at mid-point and closure | PMU, UNDP |
| GEF Project Implementation Report (PIR) | None | Annually typically between June-August | PMU, UNDP |
| Monitoring all risks (UNDP risk register) | None | On-going | PMU, UNDP |
| Monitoring of Social and Environmental Safeguards | 10,000 | On-going | Environmental and Social Safeguards Specialist in PMU |
| Supervision missions | None | Annually | PMU, IP, RP |
| Oversight/troubleshooting missions | None | Troubleshooting as needed | UNDP |
| Mid-term GEF Core indicators | 7,000 | Before mid-term review mission takes place. | M&E Specialist in PMU |
| Independent Mid-term Review (MTR) | 70,000 | June 2027 | UNDP |
| Terminal GEF Core indicators | 5,000 | Before terminal evaluation mission takes place | PMU |
| Independent Terminal Evaluation (TE) | 70,000 | April 2029 (At least three months before completion date) | UNDP |
| Translation of Mid-Term Review and Terminal Evaluation | 3,000 |  | PMU |
| TOTAL indicative COST | 220,000 |  |  |

# VII	Governance and Management Arrangements

- Roles and responsibilities of the project’s governance mechanism

- Implementing Partner

The Implementing Partner (IP) for this project is GWP-SA. The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

Global Water Partnership (GWP) is a well-established inter-governmental organisation, headquartered in Sweden. Formed in 2002, it links agencies of the United Nations, government institutions, bi- and multi-lateral development banks, professional associations, research institutions, non-governmental organisations, and the private sector. An MOU exists between UNDP and GWP (signed in 2014). GWP’s Southern Africa branch (GWP_SA) has a strong system of policies and procedures, including internal operational controls for project management, governance, reporting and budget management and administration. It maintains yearly audited accounts of its financial performance and position. The UNDP South Africa Country Office conducted a HACT-based micro assessment for GWP Southern Africa in Q3 2020 with no concerns and completed a PCAT for GWP Southern Africa in December 2020. GWP-SA is currently implementing UNDP-GEF financed project on Integrated Transboundary River Basin Management for the sustainable development of the Limpopo River Basin.

The Implementing Partner is responsible for executing this project. Specific tasks include:

Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

Overseeing the management of project risks as included in this project document and new risks that may emerge during project implementation.

Procurement of goods and services, including human resources.

Financial management, including overseeing financial expenditures against project budgets.

Approving and signing the multiyear workplan.

Approving and signing the combined delivery report at the end of the year; and,

Signing the financial report or the funding authorization and certificate of expenditures.

- Responsible Parties

Due to its current limited capacity and limited track record on financial management, neither CUVECOM nor the PJTC is yet eligible to be selected as an Implementing Partner (IP) by UNDP.  Subsequently, GWP-SA will perform as the UNDP IP (= GEF Executing Agency or EA) for this project and execute the project on behalf of CUVECOM and the PJTC, and the member states of Angola and Namibia. GWP-SA as the Implementing Partner will support the implementation of the programme through providing quality assurance and supporting financial and administrative functions for the project.  Based on consultations with GEFSEC during the development of the ProDoc, GWP-SA will build the CUVECOM and eventual joint Secretariat (for both basins) execution capacity throughout the project implementation period so that by the time the project is completed, the joint CUVECOM/Kunene Secretariat’s capacity will be sufficient to start executing donor-funded projects directly without the involvement of a third party as Executing Agency.

The Cuvelai Watercourse Commission (CUVECOM) was established by the Republics of Angola and Namibia on 16th September 2014. CUVECOM shall serve as an Advisor to the Parties on matters relating to Equitable & reasonable utilization,  sustainable development, and Efficient management of water resources of the Cuvelai Watercourse. The Kunene River basin does not have a commission but the  Permanent Joint Technical Commission (PJTC) was established in 1969 as an advisory body to consult the respective governments on the development of the Kunene River. Both CUVECOM and the PJTC have council with three commissioners from each country. CUVECOM has a Secretariat, established in 2015, led by an Executive Secretary. The Secretariat is based in Oshakati, Namibia but has a satellite office in Ondjiva, Angola within the offices of GABHIC.

CUVECOM and the PJTC will be key drivers in the implementation of the project, as it is the originator and focal custodian of the project on behalf of the two countries with the convening power to bring together all key stakeholders in both basins. Many of the outputs proposed under Component 3 are aimed at strengthening the capacities of both CUVECOM and the PJTC and creating a joint Secretariat. The project will support CUVECOM and the PJTC in potentially establishing new governance bodies, such as the proposed joint Secretariat. There will also be a need to create various technical task teams, a legal task team and an economic task team.

The CUVECOM Secretariat is a relatively new organization but has built significant institutional capacity and human resources. It played a leading role in the development of the preliminary IWRM Plan for the Cuvelai Basin. The proposed GEF investment will put a strong focus in strengthening the institutional, and individual capacities of both the proposed joint secretariat. The CUVECOM Secretariat staff currently number four (Cuvelai Programme Manager/Acting Executive Secretary, Finance & Administration, Technical support officer and cleaner. The project will support the filling of three vacant posts, Procurement Officer, Communications Officer and Translator/editor/interpreter. The Secretariat (CUVECOM and future Joint) will take responsibility for the overall management of some assignments through a grant mechanism from GWPSA. This should include (but not be limited to) the overall management of the Pilot Demonstration Projects. For some activities in Angola, it is envisage that Gabhic will play a role as a responsible party as well as the PJTC, while in Namibia there will be a role for MAWLR.

Project organisation structure:

UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes overseeing project execution undertaken by the Implementing Partner to ensure that the project is being carried out in accordance with UNDP and GEF policies and procedures and the standards and provisions outlined in the Delegation of Authority (DOA) letter for this project. The UNDP GEF Executive Coordinator, in consultation with UNDP Bureaus and the Implementing Partner, retains the right to revoke the project DOA, suspend or cancel this GEF project. UNDP is responsible for the Project Assurance function in the project governance structure and presents to the Project Board and attends Project Board meetings as a non-voting member.

Notes

1. CUVECOM Secretariat staff currently number 4 (Cuvelai Programme Manager/Acting ES, Finance and Admin, Technical Support Officer, and Cleaner). The Secretariat will take the responsibility for the overall management of some assignment through a grant mechanism from GWP-SA.

2. Position to be covered by the project under Component 3 in CUVECOM Secretariat and then in Joint Secretariat. If sustainable, these positions will be covered by the two Governments after end of the project.

3. PCU to be provided with office space within CUVECOM Secretariat in Oshakati, Satellite Office in Ondjiva and subsequently within the Joint Secretariat.

4. Environment Specialist will be a part-time position (individual consultant) with input within the basins and home office.

5. Full-time for much of the project duration, positions are 1 hydrologist+1 geohydrologist for 50 months each covering both basins. Main task is to provide supervision of specialist consultancies

6. This position will be part-time and workload shared with Communications and Outreach Officer within CUVECOM Secretariat

7. Component 4 requires 3 technical officers to be stationed in GABHIC offices in Ondjiva, Huambo and Lubango, full-time for 4 years.

8. Commissions of these two River Basins have specific Committees/Task Teams, which carry out tasks related to the subjects/areas mentioned in the Task Teams

UNDP BPPS NCE assumes full responsibility and accountability for oversight and quality assurance of this Project and ensures its timely implementation in compliance with the GEF-specific requirements and UNDP’s Programme and Operations Policies and Procedures (POPP), its Financial Regulations and Rules and Internal Control Framework. A UNDP BPPS NCE representative will assume the assurance role and will present assurance findings to the Project Board, and therefore attends Project Board meetings as a non-voting member.

Segregation of duties and firewalls vis-à-vis UNDP representation on the project board:

As noted in the Minimum Fiduciary Standards for GEF Partner Agencies, in cases where a GEF Partner Agency (i.e. UNDP) carries out both implementation oversight and execution of a project, the GEF Partner Agency (i.e. UNDP) must separate its project implementation oversight and execution duties, and describe in the relevant project document a: 1) Satisfactory institutional arrangement for the separation of implementation oversight and executing functions in different departments of the GEF Partner Agency; and 2) Clear lines of responsibility, reporting and accountability within the GEF Partner Agency between the project implementation oversight and execution functions.

If the implementing partner is not UNDP and if UNDP is not performing ANY support to execution for the implementing partner: In this case, UNDP is only performing an implementation oversight role in the project vis-à-vis our role in the project board and in the project assurance function and therefore a full separation of project implementation oversight and execution duties has been assured.

Roles and Responsibilities of the Project Organisation Structure

Project Board: All UNDP projects must be governed by a multi-stakeholder board or committee established to review performance based on monitoring and evaluation, and implementation issues to ensure quality delivery of results. The Project Board (also called the Project Steering Committee) is the most senior, dedicated oversight body for a project.

The two main (mandatory) roles of the project board are as follows:

- High-level oversight of the execution of the project by the Implementing Partner (as explained in the “Provide Oversight” section of the POPP). This is the primary function of the project board and includes annual (and as-needed) assessments of any major risks to the project, and decisions/agreements on any management actions or remedial measures to address them effectively. The Project Board reviews evidence of project performance based on monitoring, evaluation and reporting, including progress reports, evaluations, risk logs and the combined delivery report. The Project Board is responsible for taking corrective action as needed to ensure the project achieves the desired results.

- Approval of strategic project execution decisions of the Implementing Partner with a view to assess and manage risks, monitor and ensure the overall achievement of projected results and impacts and ensure long term sustainability of project execution decisions of the Implementing Partner (as explained in the “Manage Change” section of the POPP).

The composition of the Project Steering Committee will be determined at the LPAC meeting, but will include representation of the PJTC and CUVECOM through the Chairs, one of whom will be chair of the PSC), two representative from each member state. Representation should take into account the need for gender equality as laid out in Section 3.1 of the Gender Action Plan. The ES of the Joint Secretariat will act as the Secretary of the PSC), UNDP, and GWP-SA.

Requirements to serve on the Project Board: to be included in the TOR of the Project Board

- Agree to the Terms of Reference of the Board and the rules on protocols, quorum and minuting.

- Meet annually; at least once.

- Disclose any conflict of interest in performing the functions of a Project Board member and take all measures to avoid any real or perceived conflicts of interest. This disclosure must be documented and kept on record by UNDP.

- Discharge the functions of the Project Board in accordance with UNDP policies and procedures.

- Ensure highest levels of transparency and ensure Project Board meeting minutes are recorded and shared with project stakeholders.

Responsibilities of the Project Board include:

- Consensus decision making:

  - The project board provides overall guidance and direction to the project, ensuring it remains within any specified constraints, and providing overall oversight of the project implementation.

  - Review project performance based on monitoring, evaluation and reporting, including progress reports, risk logs and the combined delivery report;

  - The project board is responsible for making management decisions by consensus.

  - In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

  - In case consensus cannot be reached within the Board, the UNDP representative on the board will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed

- Oversee project execution:

  - Agree on project manager’s tolerances as required, within the parameters outlined in the project document, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded.

  - Appraise annual work plans prepared by the Implementing Partner for the Project; review combined delivery reports prior to certification by the implementing partner.

  - Address any high-level project issues as raised by the project manager and project assurance;

  - Advise on major and minor amendments to the project within the parameters set by UNDP and the donor and refer such proposed major and minor amendments to the UNDP BPPS Nature, Climate and Energy Executive Coordinator (and the GEF, as required by GEF policies);

  - Provide high-level direction and recommendations to the project management unit to ensure that the agreed deliverables are produced satisfactorily and according to plans.

  - Track and monitor co-financed activities and realization of co-financing amounts of this project.

  - Approve the Inception Report, GEF annual project implementation reports, mid-term review and terminal evaluation reports.

  - Ensure commitment of human resources to support project implementation, arbitrating any issues within the project.

- Risk Management:

  - Provide guidance on evolving or materialized project risks and agree on possible mitigation and management actions to address specific risks.

  - Review and update the project risk register and associated management plans based on the information prepared by the Implementing Partner. This includes risks related that can be directly managed by this project, as well as contextual risks that may affect project delivery or continued UNDP compliance and reputation but are outside of the control of the project. For example, social and environmental risks associated with co-financed activities or activities taking place in the project’s area of influence that have implications for the project.

  - Address project-level grievances.

- Coordination:

  - Ensure coordination between various donor and government-funded projects and programmes.

- Ensure coordination with various government agencies and their participation in project activities

- Provide overall strategic guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the project manager;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on project Coordinators’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the project coordinatorsr’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

- Ensure highest levels of transparency and take all measures to avoid any real or perceived conflicts of interest.

- The PSC will meet at least twice per year to monitor the project’s implementation progress and progress towards the expected results.  When possible, PSC meeting will be held back-to-back with CUVECOM/PJTC statutory meetings.

The composition of the Project Board must include the following roles:

- Project Executive: Is an individual who represents ownership of the project and chairs the Project Board. The Executive is normally the national counterpart for nationally implemented projects. The Project Executive is the Chair of either CUVECOM or the PJTC (alternating).

- Beneficiary Representative(s): Individuals or groups representing the interests of those who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. Often civil society representative(s) can fulfil this role. The Beneficiary representatives will be two representative from each Member State.

- Development Partner(s): Individuals or groups representing the interests of the parties concerned that provide funding and/or technical expertise to the project. The Development Partner(s) is/are: United Nations Development Programme; GWP-SA, key co-financing and other partners (to be determined at LPAC)

Project Assurance: Project assurance is the responsibility of each project board member; however, UNDP has a distinct assurance role for all UNDP projects in carrying out objective and independent project oversight and monitoring functions. UNDP performs quality assurance and supports the Project Board (and Project Management Unit) by carrying out objective and independent project oversight and monitoring functions, including compliance with the risk management and social and environmental standards of UNDP. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager. Project assurance is totally independent of project execution.

A designated representative of UNDP playing the project assurance role is expected to attend all board meetings and support board processes as a non-voting representative. It should be noted that while in certain cases UNDP’s project assurance role across the project may encompass activities happening at several levels (e.g. global, regional), at least one UNDP representative playing that function must, as part of their duties, specifically attend board meeting and provide board members with the required documentation required to perform their duties.

Project Management – Execution of the Project: The Project Manager (PM) (also called project coordinator) is the senior most representative of the Project Management Unit (PMU) and is responsible for the overall day-to-day management of the project on behalf of the Implementing Partner, including the mobilization of all project inputs, supervision over project staff, responsible parties, consultants and sub-contractors. The project manager typically presents key deliverables and documents to the board for their review and approval, including progress reports, annual work plans, adjustments to tolerance levels and risk registers.

Proposed Support for Project Implementation (additional details on roles and responsibilities are provided in the Overview of Project Staff and Technical Consultancies in Annex 6 of the UNDP Project Document)

- a) The position of (Acting) Executive Secretary (ES) of CUVECOM is already funded by Member State contributions. There are currently only four staff (Cuvelai Programme Manager/Acting ES, Finance and Administration, Technical support officer and cleaner. The structure makes allowance for Procurement Officer, a Communications and Outreach Expert and a bilingual editor/translator and an additional technical support officer). The project will cover the cost of a Procurement Officer, a Communications and Outreach Expert and a bilingual editor/translator under Component 3 in the CUVECOM Secretariat initially and then in Joint Secretariat. For sustainability, it is proposed that these positions be covered by the two Governments after end of project.

- b) The Executive Secretary (ES) (and ultimately of the Joint Secretariat), who has overall responsibility for the programs of the CUVECOM Secretariat, will oversee the work of the CUVECOM (and ultimately Joint) Secretariat and PCU staff, and will be responsible for overall liaison with the Member States who are the proponents and key beneficiaries of the project.  The ES will be responsible for facilitating collaborative efforts between project partners, and for ensuring that the activities of the project are responding to the requirements, needs, and priorities of the project’s beneficiaries.  The Executive Secretary will be responsible for overseeing and supporting all project Components as well as project management.

- Project Coordination Unit: The Coordination Unit (PCU), headed by the Project Coordinator/IWRM Expert, will be responsible for the development and timely implementation of work plans approved by the PSC and for the day-to-day activities of the project.  PCU staff will be paid using GEF project funds throughout the project implementation period, and they will be contracted by the project Implementing Partner (GWP-SA). The PCU staff will be located at the offices of the CUVECOM Secretariat in Oshakati (or at one of the satellite offices), (through a hosting agreement between GWP-SA and CUVECOM).  All positions will be filled by contracted individuals.  The PCU staff will comprise:

Project Coordinator / IWRM expert;

Environment Specialist (part-time)

Hydrologist/geohydrologist(s)

M & E, Gender and Safeguard Specialist

Communications & Knowledge Management Officer (part-time)6

Administrative, Finance & Procurement Officer

3 x technical officers, Angola (Component 4)7

The selection and appointment process should take into account the need for gender equality as laid out in Section 3.1 of the Gender Action Plan, so that the PCU has a high level of gender equality.

- Project Coordinator (PC)/IWRM Expert (55 months, full-time): The PC will be responsible for the day-to-day management of the project and the regular monitoring of project outcomes and risks, including social and environmental risks.  The PC will ensure that all project staff maintain a high level of transparency, responsibility and accountability in monitoring and evaluating and reporting on project outcomes. The PC will inform the Project Board, the UNDP country offices, and the UNDP-GEF Regional Technical Advisor (RTA) of any delays or difficulties encountered during implementation so that appropriate support and remedial action can be taken.  The PC will develop annual workplans based on the multi-year workplan included in Annex 3, which will include annual performance targets to support efficient project implementation. Most importantly, the PC will work very closely with the ES of the Joint Secretariat.

- Monitoring and Evaluation, Gender and Safeguards Specialist (48 months: 75% of full-time): The M & E specialist will ensure that the standard M&E requirements of UNDP and GEF are met with the highest quality standards. This includes but is not limited to: 1) ensuring that results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR; 2) monitoring of the project implementation progress, and ensuring its close link to implementation of the IWRM Plan and eventually the SAP; and 3) expanded tracking of co-financing and complementary initiatives at national and regional levels.

- Finance / Administration / Procurement Officer (40 months): This officer will support the Project Coordinator in managing the budget, administration, and procurement tasks associated with the project.  In addition, he/she will provide technical guidance and support to activities under Component 3 to strengthen the Operational Capacity of the Joint Secretariat and put in place a financial system that enables The Joint Secretariat to be eligible to receive direct funding from the GEF and other partners, including training of the Administrative and Financial Assistant to manage this system over the long-term. He/she will work closely with both the Procurement officer within the Secretariat so that this person can play this role during periods of absence.

- Communications and Knowledge Management Officer: will lead all communications and knowledge management activities for the project (primarily under Component 3 and 6) as well as supporting activities in those areas on a broader scale for CUVECOM/PJTC. He/she will work closely with both the Communications and Outreach Officer within the Secretariat who will dedicate at least 50% of his/her time on this project.

- Environment specialist (36 months 60% of time): This specialist will focus much of his/her effort on Components 1 and 2 (ecological flow requirements, groundwater assessments and scenario analysis), specifically in the preparation of the TDAs and IWRM Plans. He/she will also provide expert support in the design of the pilot demonstration projects (Component 5, and in support of the evaluation of ecosystem services of the water tower in Angola (unit Component 4).

- Hydrologist/geohydrologist (s): (66 months x 2 or 33 months x 4): The main role of the hydrologist and geohydrologist will to be to supervise the work of consultants carrying out assignments under Components 1 and 2 and subsequently in compiling the TDA and the IWRM Plans. They will also have inputs under Components 4 and 5. It is envisaged that both posts will be filled by experts from the two countries, secondment from Government ministries could be considered.

- 3 x Technical Officers, Angola These technical officers will be posted to three sentries, Ondjiva, Lubango and Huambo for a duration of 60 months each, starting from Month 4. Their work will be principally under Component 4 which is in support of improved management of the water tower in Angola, but they will play an important support role in other components as well, in particular under Component 5 which deals with the pilot demonstration projects. They will be professionally qualified with joint expertise covering (as far as possible), agriculture, forestry, fisheries (aquaculture), the environment and rural development.

- Project stakeholders and target groups: In order to ensure stakeholder participation is structured at the local level, it is proposed that the Joint Secretariat establishes National Stakeholder Coordination Committees (NASCs); and a Basin-wide Stakeholder Committee (BASC), which will convene regularly to address issues relevant to the implementation of the proposed project.

# VIII	 Financial Planning and Management

The total cost of the project is USD 176,618,691.  This is financed through a GEF grant of USD 11,167,890 administered by UNDP, USD  165,450,801 in cash co-financing to be administered by UNDP. UNDP, as the GEF Implementing Agency, is responsible for the oversight of the GEF resources and the cash co-financing transferred to UNDP bank account only.

Co-financing: The actual realization of project co-financing amounts will be monitored by the UNDP Country Office and the PMU on an annual basis in the GEF PIF and will be reported to the GEF during the mid-term review and terminal evaluation process as follows:

Table 3: Summary of Co-financing

| Co-Financing Source | Co-financing type |  | Co-financing amount (USD) | LOCATION | BRIEF PROJECT DESCRIPTION | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NamWater/KfW |  | Public investment | Included in total below | Cuvelai & Kunene | CNA Master Water Plan Study A comprehensive revision of the water masterplan of the central northern area, including full utilisation of Namibia’s specified share of water from the Kunene River and the development of the Ohangwena II aquifer | Very low | UNDP Namibia will keep in close contact with KfW (project about to start) |
| Gov. of Namibia and Angola |  | Public investment | Included in total below | Kunene | Calueque Pumping Station The completion and commissioning of the permanent pumping system forming part of the Calueque dam with agreement on and appointment of an authority with Angola to operate and maintain the system. | Very low | UNDP and PCU to work closely with PJTC and Gabhic to address any potential issues |
| NamWater |  | Public investment | Included in total below | Cuvelai | Omahanene to Olushandja Canal Refurbishment The replacement and repair of the 10 km long concrete lined canal running from the Namibian border with Angola to the Olushandja balancing dam | Very low | UNDP and PCU to work closely with NamWater to address any potential issues |
| NamWater |  | Public investment | Included in total below | Cuvelai | Olushandja Pump Station and Siphon Refurbishment Investigation of the condition of the Olushandja pumping station and siphon, and its upgrade to meet expected pumping volumes, after the duplication of the Oshakati purification works becomes operative. | Very low | UNDP and PCU to work closely with NamWater to address any potential issues |
| NamWater |  | Public investment | Included in total below | Cuvelai | Olushandja to Ogongo Canal Refurbishment Escalated cleaning, maintenance and repairs of the 70-km-long concrete canal between Olushandja and Ogongo. Also included in the project is the replacement of the end section at Ogongo. | Very low | UNDP and PCU to work closely with NamWater to address any potential issues |
| NamWater |  | Public investment | Included in total below | Cuvelai | Ogongo End section The scope of works for this project entails the detail design and construction for replacing the last section (±700 m long) of the canal at Ogongo | Very low | UNDP and PCU to work closely with NamWater to address any potential issues |
| NamWater |  | Public investment | Included in total below | Cuvelai | Ogongo-Oshakati Canal Rehabilitation: Oshikuku Section (Cuvelai) This project focusses on the Oshikuku Canal section, the accepted proposal entails replacing this section of the canal with a pumped pipeline via an approximately 8 km direct route. | Very low | UNDP and PCU to work closely with NamWater to address any potential issues |
| NamWater |  | Public investment | Included in total below | Cuvelai | Ogongo to Oshakati Canal Refurbishment In the vicinity of Oshikuku with a pipeline/pumping system | Very low | UNDP and PCU to work closely with NamWater to address any potential issues |
| NamWater/AfDB |  | Public investment | Included in total below | Cuvelai | Oshakati purification plant extension Duplication of capacity of the existing purification plant at Oshakati to cater for growing and expected future demand for water in the region, which has already outstripped the existing capacity of that plant. | Very low | UNDP and PCU to work closely with NamWater and AfDB to address any potential issues |
| NamWater/AfDB |  | Public investment | Included in total below | Cuvelai | Ohangwena II Wellfield Development of Ohangwena II aquifer to provide water supply infrastructure to improve and increase the bulk water supply capacity of the Omafo-Eenhana and Omakango-Onambutu-Eenhana Schemes to meet the 2037 water demand. | Very low | UNDP and PCU to work closely with NamWater and AfDB to address any potential issues |
| NamWater & a donor |  | Public investment | Included in total below | Cuvelai | Omundaungilo – Omutsegwonime Bulk Pipeline Scheme A bulk pipeline with secondary branch-lines to cater for the rural communities that drink unhygienic water from traditional wells, brackish water. Construction of a Pump station, reservoirs and associated facilities. Propose year of project year, financial year of 2025. | Very low | UNDP and PCU to work closely with NamWater and donor to address any potential issues |
|  |  | Total | 110,354,627 |  |  |  |  |
| GIZ |  | Grant | 109,847 | Kunene | Rapid Assessment of the state of the Kunene Watercourse in order to map out and give recommendations for the development of an IWRM plan for the management of the basin | Very low | UNDP Namibia to continue working closely with GIZ and CUVECOM |
| SADC Groundwater Management Institute (GMI) |  | Grant | 150,000 |  | In-kind support to the sustainable development and management of conjunctive surface and groundwater resources | Low | UNDP Namibia to keep close contact with SADC Water Division |
| Southern African Science Services Centre for Climate Change and Adaptive land management (SASSCAL) |  | Grant | 131,817 |  | In-kind support through provision of expertise | Low | UNDP Namibia and CUVECOM to keep close contact with SASSCAL |
| BMZ, Germany | In-Kind |  | 100,000 |  | In-kind support through participation of BGR staff in in support of the project activities; supporting and organizing meetings or workshops and further measures in line with a jointly developed working plan of CUVECOM and BGR. | Low | CUVECOM to work closely with BGR |
| MINEA (Government of Angola) | Public Investment |  | 54,304,510 |  | Emergency drought fighting program in Kunene basin including Water Transfer System of the Kunene River from the Cafu Locality to the Shana Zone at communal headquarters of Chitado and in localities of Cuamato and Namacunde in two lots. |  | PJTC and CUVECOM to work closely with Gabhic |
| UNDP, Namibia | In-kind |  | 100,000 |  | General programme support | Very low | GWP-SA to work closely with UNDP |
| UNDP, Angola | In-kind |  | 200,000 |  | Strategic support to demonstration activities under Components 4 and 5 | Very low | GWP-SA to work closely with UNDP |
|  |  | TOTAL co-financing | 165,450,801 |  |  |  |  |

Budget Revision and Tolerance: As per UNDP POPP, the project board may agree with the project manager on a tolerance level for each detailed plan under the overall multi-year workplan. The agreed tolerance should be written in the project document or approved project board meeting minutes. It should normally not exceed 10 percent of the agreed annual budget at the activity level, but within the overall approved multi-year workplan at the activity level. Within the agreed tolerances, the project manager can operate without intervention from the project board. Restrictions apply as follows:

Should the following deviations occur, the Project Manager/IP through UNDP Country Office will seek the approval of the BPPS/NCE-VF team to ensure accurate reporting to the GEF.  It is strongly encouraged to maintain the expenditures within the approved budget at the budgetary account and at the component level:

- Budget reallocations must prove that the suggested changes in the budget will not lead to material changes in the results to be achieved by the project. A strong justification is required and will be approved on an exceptional basis.  Budget re-allocations among the components (including PMC) of the approved Total Budget and Work Plans (TBWP) that represent a value greater than 10% of the total GEF grant.

- Introduction of new outputs/activities (i.e. budget items) that were not part of the agreed project document and TBWP that represent a value greater than 5% of the total GEF grant. The new budget items must be eligible as per the GEF and UNDP  policies.

- Project management cost (PMC): budget under PMC component is capped and cannot be increased.

UNDP is not in a position to increase the total budget above the amount approved by the donor, therefore any over-expenditure would have to be absorbed from non-GEF resources by the Implementing Partner (GEF Executing Entity)

Project extensions: The UNDP-BPPS-NCE team Executive Coordinator must approve all requests for extension of the Project Completion Date and for other milestone extensions with hard deadlines. All extensions impose additional time and cost burdens at all levels and the GEF project budget cannot be increased beyond its originally approved amount. A single extension may be granted on an exceptional basis and subject to the conditions and maximum durations set out in the UNDP POPP. The project management costs during the extension period must remain within the originally approved amount, and any increase in PMC costs shall be covered by non-GEF resources; the additional UNDP oversight costs during the extension period must be covered by non-GEF resources, in accordance with UNDP’s policy as set out in UNDP POPP.

For any extension request, UNDP CO and IP will consult and jointly present a clear plan indicating how and from which specific sources the additional oversight costs that will be incurred by UNDP will be covered during the extended period. The BPPS-NCE Executive Coordinator will consult the Regional Bureaux (RBX) and may reject the extension request if no (external co-financing by the IP or internal UNDP CO resources) can be identified.

All extension requests, along with all supporting documentation, shall be submitted by the IP to the UNDP CO in line with the requirements and within the deadlines set out in the UNDP SOPs and policies in UNDP POPP.

Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies. Audit cycle and process must be discussed during the Inception workshop. If the Implementing Partner is an UN Agency, the project will be audited according to that Agencies applicable audit policies. The costs for audit cannot be included under M&E component and budget and must be included under PMC. Do not remove any text from this audit section.

Transfer or disposal of assets: In consultation with the Implementing Partner and other parties of the project, UNDP is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project, however, must be done before the operational closure date. In all cases of transfer, a transfer document must be prepared and kept on file. The transfer should be done before Project Management Unit complete their assignments.

Completion Date: The project completion date is the date of Project Document Signature plus project duration. This date can only be extended through a formal extension request. Prior to completion date, all UNDP-financed inputs must be provided and related activities for the Project completed. No activities, except for the final clearance of the Terminal Evaluation Report and the corresponding management response and the end-of-project review Project Board Meeting should take place after the Completion Date.

Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. All costs incurred to close the project must be included in the project closure budget and reported as final project commitments presented to the Project Board during the final project review. The only costs a project may incur following the final project review are those included in the project closure budget.

Operational Closure: Operational closure must happen within 9 months from project completion date. Prior to operational closure, the Terminal Evaluation must have been submitted and the corresponding TE management response and the end-of-project review Project Board meeting must have been completed. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. Before Operational Closure, the project must have completed the transfer or disposal of any equipment that is still the property of UNDP.

Financial Closure: Financial closure must happen within 6 months of operational closure or after the date of cancellation. The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to BPPS/NCE for confirmation before the project will be financially closed in Quantum by the UNDP Country Office.

Cancellation and Suspension: All projects considering going through cancellation or suspension must follow UNDP and GEF requirements. Guidance can be found in the UNDP POPP (SOPs for management actions of Vertical Fund projects escalated to the Executive Coordinator and Guidance for GEF project revisions).

Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the BPPS/NCE-VF Directorate in New York. No action is required by the UNDP Country Office on the actual refund from UNDP project to the GEF Trustee. Unspent project balance is not permitted to be transferred to any other projects.

# IX	Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Quantum Award ID: | 1220489 | Quantum Output Project ID: | 01001714 |
| Quantum Proposal or Award Title: | Enhanced Water Security and Community Resilience in the Adjacent Cuvelai and Kunene Transboundary River Basins |  |  |
| Quantum Business Unit | NAM10 |  |  |
| Quantum Primary Output Project Title | CUVKUN Water Security & Community Resilience Building |  |  |
| UNDP-GEF PIMS No. | 4756 |  |  |
| Implementing Partner | GWP-SA |  |  |

| Quantum Activity (GEF Component) | Project Outcomes | Quantum Implementing Agent (Responsible Party/[1] , IP, or UNDP) | Quantum Fund ID | Donor Name | Quantum Budgetary Account Code | Quantum Budget Account Description | Amount Year {2024} (USD) | Amount Year {2025} (USD) | Amount Year {2026} (USD) | Amount Year {2027} (USD) | Amount Year {2028} (USD) | Amount Year {2029} (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Strengthening the transboundary and conjunctive water resources management in the Cuvelai River Basin | 1.1 - Two countries committed to the joint management of the transboundary Cuvelai River basin with a focus on the improved resilient community livelihoods, based on the best available science and knowledge | GWP-SA | 62000 | GEF | 71200 | International Consultants | 100,000 | 200,000 | 160,000 | 55,000 | 25,000 | 0 | 540,000 | 1 |
|  |  |  |  |  | 71300 | Local Consultants | 100,000 | 150,000 | 210,000 | 65,000 | 25,000 | 0 | 550,000 | 2 |
|  |  |  |  |  | 71800 | Contractual Services-Imp Partn | 200,000 | 200,000 | 200,000 | 200,000 | 200,000 | 82,500 | 1,082,500 | 3 |
|  |  |  |  |  | 71600 | Travel | 60,000 | 30,000 | 30,000 | 40,000 | 65,000 | 25,000 | 250,000 | 4 |
|  |  |  |  |  | 72100 | Contractual services - Companies | 50,000 | 200,000 | 25,000 | 25,000 | 0 | 0 | 300,000 | 5 |
|  |  |  |  |  | 72200 | Equipment and Furniture | 10,000 | 7,500 | 1,500 | 0 | 0 |  | 19,000 | 6 |
|  |  |  |  |  | 72300 | Materials and Goods | 5,000 | 5,000 | 5,000 | 2,500 | 0 | 0 | 17,500 | 7 |
|  |  |  |  |  | 72800 | Information Technology Equipment | 0 | 0 | 10,000 | 10,000 | 0 | 0 | 20,000 | 8 |
|  |  |  |  |  | 74200 | Audio Visual & Print production costs | 0 | 2,500 | 2,500 | 15,000 | 20,000 | 0 | 40,000 | 9 |
|  |  |  |  |  | 74500 | Miscellaneous | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 | 0 | 15,000 | 10 |
|  |  |  |  |  | 74700 | Transport, shipping and handling | 1,500 | 3,000 | 1,500 | 0 | 0 | 0 | 6,000 | 11 |
|  |  |  |  |  | 75700 | Training, workshops and conference | 35,000 | 20,000 | 30,000 | 40,000 | 35,000 | 0 | 160,000 | 12 |
|  |  |  |  |  |  | Sub-total GEF | 564,500 | 821,000 | 678,500 | 455,500 | 373,000 | 107,500 | 3,000,000 |  |
|  |  |  |  |  |  | Sub-total component 1 | 564,500 | 821,000 | 678,500 | 455,500 | 373,000 | 107,500 | 3,000,000 |  |
| Component 2: Strengthening the transboundary water resources management with future development scenario analysis in the Kunene River basin |  | GWP-SA | 62000 | GEF | 71200 | International Consultants | 150000 | 240000 | 200000 | 50000 | 30000 | 5000 | 675000 | 13 |
|  | 2.1: Two countries committed for the joint management and sustainable development of the transboundary Kunene River basin, based on the best available science and knowledge |  |  |  | 71300 | Local Consultants | 200,000 | 340,000 | 340,000 | 65,000 | 15,000 | 0 | 960,000 | 14 |
|  |  |  |  |  | 71800 | Contractual Services-Imp Partn | 160,000 | 160,000 | 175,000 | 130,000 | 134,500 | 75,000 | 834,500 | 15 |
|  |  |  |  |  | 71600 | Travel | 60,000 | 40,000 | 40,000 | 60,000 | 65,000 | 25,000 | 290,000 | 16 |
|  |  |  |  |  | 72100 | Contractual services - Companies | 10,000 | 30,000 | 30,000 | 0 | 0 | 0 | 70,000 | 17 |
|  |  |  |  |  | 72200 | Equipment and Furniture | 10,000 | 7,500 | 0 | 0 | 0 |  | 17,500 | 18 |
|  |  |  |  |  | 72300 | Materials and Goods | 5,000 | 5,000 | 5,000 | 2,500 | 0 | 0 | 17,500 | 19 |
|  |  |  |  |  | 72800 | Information Technology Equipment | 0 | 0 | 15,000 | 15,000 | 0 | 0 | 30,000 | 20 |
|  |  |  |  |  | 74200 | Audio Visual & Print production costs | 0 | 2,500 | 2,500 | 15,000 | 20,000 | 0 | 40,000 | 21 |
|  |  |  |  |  | 74500 | Miscellaneous | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 | 0 | 15,000 | 22 |
|  |  |  |  |  | 74700 | Transport, shipping and handling | 1,500 | 3,000 | 1,500 | 0 | 0 | 0 | 6,000 | 23 |
|  |  |  |  |  | 75700 | Training, workshops and conference | 35,000 | 30,000 | 30,000 | 50,000 | 49,500 | 0 | 194,500 | 24 |
|  |  |  |  |  |  | Sub-total GEF | 634,500 | 861,000 | 842,000 | 390,500 | 317,000 | 105,000 | 3,150,000 |  |
|  |  |  |  |  |  | Sub-total Component 2 | 634,500 | 861,000 | 842,000 | 390,500 | 317,000 | 105,000 | 3,150,000 |  |
| Component 3: Strengthening the governance of the Cuvelai and Kunene River Basins to foster joint management by the two countries in the most cost-effective manner | 3.1: Intergovernmental institutional structures set up in a financially sustainable manner to foster joint management of the Cuvelai and Kunene basins by the two countries | GWP-SA | 62000 | GEF | 71200 | International Consultants | 10,000 | 10,000 | 20,000 | 5,000 | 0 | 0 | 45,000 | 25 |
|  |  |  |  |  | 71300 | Local Consultants | 10,000 | 15,000 | 25,000 | 15,000 | 0 | 0 | 65,000 | 26 |
|  |  |  |  |  | 71800 | Contractual Services-Imp Partn | 100,000 | 150,000 | 160,000 | 160,000 | 140,000 | 123,500 | 833,500 | 27 |
|  |  |  |  |  | 71600 | Travel | 5,000 | 10,000 | 10,000 | 10,000 | 5,000 | 5,000 | 45,000 | 28 |
|  |  |  |  |  | 72100 | Contractual services - Companies | 25,000 | 40,000 | 40,000 | 10,000 | 0 | 0 | 115,000 | 29 |
|  |  |  |  |  | 72200 | Equipment and Furniture | 5,000 | 10,000 | 10,000 | 500 | 500 | 0 | 26,000 | 30 |
|  |  |  |  |  | 72300 | Materials and Goods | 2,000 | 5,000 | 5,000 | 2,000 | 2,000 | 0 | 16,000 | 31 |
|  |  |  |  |  | 72400 | Communication & Audio Visual Equip | 5,000 | 15,000 | 12,500 | 2,500 | 0 | 0 | 35,000 | 32 |
|  |  |  |  |  | 72800 | Information Technology Equipment | 5,000 | 20,000 | 40,000 | 2,500 | 2,500 | 0 | 70,000 | 33 |
|  |  |  |  |  | 74200 | Audio Visual & Print production costs | 2,500 | 5,000 | 2,500 | 2,000 | 2,000 | 1,000 | 15,000 | 34 |
|  |  |  |  |  | 74500 | Miscellaneous | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 | 1,950 | 11,950 | 35 |
|  |  |  |  |  | 75700 | Training, workshops and conference | 10,000 | 30,000 | 30,000 | 20,000 | 20,000 | 12,550 | 122,550 | 36 |
|  |  |  |  |  |  | Sub-total GEF | 181,500 | 312,000 | 357,000 | 231,500 | 174,000 | 144,000 | 1,400,000 |  |
|  |  |  |  |  |  | Total Component 3 | 181,500 | 312,000 | 357,000 | 231,500 | 174,000 | 144,000 | 1,400,000 |  |
| Component 4: Strengthening institutional, technical and operational capacity in Angola to sustainably develop and manage the sub-region’s water tower located in southern Angola | 4.1: Capacity in water resources and environmental management in Angola strengthened | GWP-SA | 62000 | GEF | 71200 | International Consultants | 30,000 | 70,000 | 50,000 | 30,000 | 0 | 0 | 180,000 | 37 |
|  |  |  |  |  | 71300 | Local Consultants | 40,000 | 100,000 | 120,000 | 85,000 | 0 | 0 | 345,000 | 38 |
|  |  |  |  |  | 71800 | Contractual Services-Imp Partn | 100,000 | 190,000 | 190,000 | 180,000 | 140,000 | 49,144 | 849,144 | 39 |
|  |  |  |  |  | 71600 | Travel | 25,000 | 40,000 | 50,000 | 30,000 | 25,000 | 10,000 | 180,000 | 40 |
|  |  |  |  |  | 72100 | Contractual services - Companies | 10,000 | 10,000 | 2,500 | 2,500 | 0 | 0 | 25,000 | 41 |
|  |  |  |  |  | 72200 | Equipment and Furniture | 20,000 | 10,000 | 5,000 | 5,000 | 0 | 0 | 40,000 | 42 |
|  |  |  |  |  | 72400 | Communication & Audio Visual Equip | 7,500 | 2,500 | 0 | 0 | 0 | 0 | 10,000 | 43 |
|  |  |  |  |  | 72800 | Information Technology Equipment | 10,000 | 5,000 | 9,442 | 0 | 0 | 0 | 24,442 | 44 |
|  |  |  |  |  | 74500 | Miscellaneous | 4,000 | 4,000 | 4,000 | 4,000 | 3,000 | 1,000 | 20,000 | 45 |
|  |  |  |  |  | 75700 | Training, workshops and conference | 15,000 | 25,000 | 35,000 | 35,000 | 22,500 | 0 | 132,500 | 46 |
|  |  |  |  |  |  | Sub-total GEF | 261,500 | 456,500 | 465,942 | 371,500 | 190,500 | 60,144 | 1,806,086 |  |
|  |  |  |  |  |  | Sub-total Component 4 | 261,500 | 456,500 | 465,942 | 371,500 | 188,000 | 60,144 | 1,806,086 |  |
| Component 5: Enhancing the community participation in IWRM to build resilience in their livelihoods | 5.1: Livelihoods enhanced, and community resilience improved through community-driven activities | GWP-SA | 62000 | GEF | 71200 | International Consultants | 5,000 | 10,000 | 5,000 |  |  |  | 20,000 | 47 |
|  |  |  |  |  | 71300 | Local Consultants | 30,000 | 30,000 | 47,500 |  |  |  | 107,500 | 48 |
|  |  |  |  |  | 71800 | Contractual Services-Imp Partn | 20,000 | 20,000 | 15,000 | 15,000 | 7,500 | 2,500 | 80,000 | 49 |
|  |  |  |  |  | 71600 | Travel | 15,000 | 10,000 | 10,000 | 2,500 | 1,500 | 1,000 | 40,000 | 50 |
|  |  |  |  |  | 72100 | Contractual services - Companies | 50,000 | 75,000 | 50,000 | 10,000 | 0 | 0 | 185,000 | 51 |
|  |  |  |  |  | 72200 | Equipment and Furniture | 10,000 | 30,000 | 20,000 | 0 | 0 | 0 | 60,000 | 52 |
|  |  |  |  |  | 72300 | Materials and Goods | 50,000 | 150,000 | 82,000 |  |  |  | 282,000 | 53 |
|  |  |  |  |  | 72400 | Communication & Audio Visual Equip | 1,000 | 3,000 | 3,000 | 1,000 | 1,000 |  | 9,000 | 54 |
|  |  |  |  |  | 72800 | Information Technology Equipment | 2,500 | 7,500 | 7,500 | 2,500 |  |  | 20,000 | 55 |
|  |  |  |  |  | 74200 | Audio Visual & Print production costs |  | 5,000 | 10,000 | 10,000 | 2,500 | 2,500 | 30,000 | 56 |
|  |  |  |  |  | 74500 | Miscellaneous | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 | 1,500 | 16,500 | 57 |
|  |  |  |  |  | 75700 | Training, workshops and conference | 5,000 | 10,000 | 7,500 | 5,000 | 2,500 |  | 30,000 | 58 |
|  |  |  |  |  |  | Sub-total GEF | 191,500 | 353,500 | 260,500 | 49,000 | 18,000 | 7,500 | 880,000 |  |
|  |  |  |  |  |  | Sub-total Component 5 | 191,500 | 353,500 | 260,500 | 49,000 | 18,000 | 7,500 | 880,000 |  |
| Component 6: Outreach and Knowledge Management for replication, upscaling and stakeholder engagement | 6.1: Stakeholder engagement strengthened through targeted communication and Replication and upscaling supported through exchange of knowledge, best practices and lessons learned | GWP-SA | 62000 | GEF | 71800 | Contractual Services-Imp Partn | 20,000 | 15,000 | 15,000 | 15,000 | 15,000 | 13,600 | 93,600 | 59 |
|  |  |  |  |  | 71600 | Travel | 7,000 | 7,000 | 7,000 | 7,000 | 7,000 | 2,900 | 37,900 | 60 |
|  |  |  |  |  | 72400 | Communication & audiovisual Equipment | 2,500 | 2,500 | 1,500 | 1,000 | 1,000 |  | 8,500 | 61 |
|  |  |  |  |  | 74200 | Audio Visual & Print production costs | 5,000 | 5,000 | 5,000 | 3,500 | 3,500 | 3,000 | 25,000 | 62 |
|  |  |  |  |  | 75700 | Training, workshops and conference | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 15,000 | 63 |
|  |  |  |  |  |  | Sub-total GEF | 37,000 | 32,000 | 31,000 | 29,000 | 29,000 | 22,000 | 180,000 |  |
|  |  |  |  |  |  | Sub-total Component6 | 37,000 | 32,000 | 31,000 | 29,000 | 29,000 | 22,000 | 180,000 |  |
| Monitoring and Evaluation |  | UNDP | 62000 | GEF | 71200 | International Consultants | 4,000 | 4,000 | 44,000 | 3,000 | 3,000 | 35,000 | 93,000 | 64a |
|  |  | UNDP |  |  | 71300 | Local Consultants | 3,000 | 3,000 | 25,000 | 3,000 | 3,000 | 29,000 | 66,000 | 64b |
|  |  | GWP-SA |  |  | 71800 | Contractual Services-Imp Partn | 6,000 | 6,000 | 9,000 | 6,000 | 6,000 | 3,000 | 36,000 | 64c |
|  |  | UNDP |  |  | 71600 | Travel | 1,000 | 1,000 | 5,000 | 1,000 | 1,000 | 3,000 | 12,000 | 64d |
|  |  | GWP-SA |  |  | 74100 | Professional Services | 800 | 200 | 800 | 200 | 200 | 800 | 3,000 | 64e |
|  |  | GWP-SA |  |  | 75700 | Training, workshops and conference | 10,000 | 0 | 0 | 0 | 0 | 0 | 10,000 | 64f |
|  |  |  |  |  |  | Sub-total GEF | 24,800 | 14,200 | 83,800 | 13,200 | 13,200 | 70,800 | 220,000 |  |
|  |  |  |  |  |  | Sub-total M & E | 24,800 | 14,200 | 83,800 | 13,200 | 13,200 | 70,800 | 220,000 |  |
| PROJECT MANAGEMENT COSTS |  | GWP-SA | 6200 | GEF | 71800 | Contractual Services-Imp Partn | 94,500 | 94,500 | 76,500 | 74,000 | 74,000 | 30,500 | 444,000 | 65 |
|  |  |  |  |  | 71600 | Travel | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 24,000 | 66 |
|  |  |  |  |  | 72200 | Equipment and Furniture | 3,000 | 1,500 | 1,000 | 250 | 250 | 0 | 6,000 | 67 |
|  |  |  |  |  | 72800 | Information Technology Equipment | 2,000 | 1,500 | 1,030 | 524 | 500 | 250 | 5,804 | 68 |
|  |  |  |  |  | 74500 | Miscellaneous Expenses | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 | 1,000 | 11,000 | 69 |
|  |  | UNDP |  |  | 74100 | Professional Services | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 24,000 | 70 |
|  |  | GWP-SA |  |  | 75700 | Training, workshops and conference | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 | 2,000 | 17,000 | 71 |
|  |  |  |  |  |  | Sub-total GEF | 112,500 | 110,500 | 91,530 | 87,774 | 87,750 | 41,750 | 531,804 |  |
|  |  |  |  |  |  | Sub-total Project Management Costs | 112,500 | 110,500 | 91,530 | 87,774 | 87,750 | 41,750 | 531,804 |  |
|  |  |  |  |  | Total GEF |  | 2,007,800 | 2,960,700 | 2,810,272 | 1,627,974 | 1,202,450 | 558,694 | 11,167,890 |  |
|  |  |  |  |  | Project Total |  | 2,007,800 | 2,960,700 | 2,810,272 | 1,627,974 | 1,202,450 | 558,694 | 11,167,890 |  |

Budget Notes

| Budget notes | Subtotal USD | Quantum Category | Detail |
| --- | --- | --- | --- |
| 1 | 540,000 | International Consultants | The work on groundwater assessment (output 1.1.1) ($300,000) on the water resources and flood risk mapping and warning system (1.1.2 and 1.1.4 ($200,000+$40,000) will be contracted out to a consulting company(ies) – consortium with international and local membership |
| 2 | 550,000 | Local consultants | The local consultant input on groundwater assessment (output 1.1.1) ($350,000) on the water resources and flood risk mapping and warning system (1.1.2 and 1.1.4 ($150,000+$50,000) (see note 1) |
| 3 | 1,082,500 | Contractual Services-Imp Partn | - Inputs of the Hydrologist and geohydrologist (part of PCU team of experts) with main task being supervision of groundwater assessments, water resources and flood risk mapping and warning system, include testing ($345,000). Inputs on TDA and IWRM Plan ($225,000). - Inputs of the Agriculture, livestock and fisheries specialists (local and international) into TDA and IWRM Plan ($200,000) - Inputs of Environment Expert into TDA ($168,750) and IWRM Plan ($56,250) - M & E, Gender and Safeguards Specialist ($37,500) - Other expertise ($50,000) |
| 4 | 250,000 | Travel | Travel for individual experts associated with groundwater assessment, on the water resources and flood risk mapping and warning system, TDA and training and workshops (average of 45,000 per year for years 1-5 (=225,000) with 25,000 for final 6 months (total of 250,000). Higher travel costs associated with Year 1 and Year 5). |
| 5 | 300,000 | Contractual services - Companies | - Drilling and geophysics associated with groundwater assessment ($200,000) - Imagery, surveys, ($100,000) |
| 6 | 19,000 | Equipment and furniture | Mainly equipment associated with fieldwork |
| 7 | 17,500 | Materials and Goods | Allowance has been made for $5,000 per year for years 1 to 3 and $2,500 for year 4 for (mainly) materials and goods that maybe required to support the work of PMU geohydrologist(s) in carrying out their supervisory roles. |
| 8 | 20,000 | Information Technology Equipment | Equipment for stakeholder consultation (tablets), for computer equipment for analysis of satellite imagery, GPS, communication equipment. |
| 9 | 40,000 | Audio Visual & Print production costs | Communication materials associated with TDA and IWR Plan |
| 10 | 15,000 | Miscellaneous | For Activities under component 1 |
| 11 | 6,000 | Transport, shipping and handling | Important of specialised equipment for groundwater assessment and flood warning |
| 12 | 160,000 | Training, workshops and conference | Stakeholder workshops, technical meetings and workshops. |
| 13 | 675,000 | International Consultants | The work on ecological water requirements ($350,000) and Water resources modelling and futures scenarios ($260,000), IWRM Plan ($65,000) – consortium with international and local membership |
| 14 | 960,000 | Local consultants | The work on ecological water requirements ($600,000) and Water resources modelling and futures scenarios ($300,000), IWRM Plan ($60,000) – consortium with international and local membership |
| 15 | 834,500 | Contractual Services-Imp Partn | - Inputs of the Hydrologist and geohydrologist (part of PCU team of experts) on Output 2.1.1 ($36,000+$18,000), on Output 2.1.2 ($36,000+$18,000), on Output 2.1.3 ($63,000+$22,500), on Output 2.1.4 ($27,000+$18,000) and Output 4.1.5 ($9,000+$4,500) - Inputs of Livestock, Agriculture and livestock specialist (international) on TDA (output 2.1.3) ($67,500) and IWRM Plan (Output 2.1.5) ($22,500) - Inputs of Livestock, Agriculture and livestock specialist (local) on TDA (output 2.1.3) ($135,000) and IWRM Plan (Output 2.1.5) ($45,000) - Inputs of Environmental Specialist on TDA (output 2.1.3) ($168,750) and IWRM Plan (Output 2.1.5) ($56,250) - Inputs of M & E, Gender and Safeguards Specialist on all outputs ($37,500) - Inputs of other expertise over all outputs ($50,000) |
| 16 | 290,000 | Travel | Travel for individual experts associated with ecological flows assessment, and water resources modelling, and TDA, and training and workshops. |
| 17 | 70,000 | Contractual services - Companies | Laboratory and other analyses associated with Ecological flow requirements ($70,000) |
| 18 | 17,500 | Equipment and furniture | Mainly equipment associated with fieldwork |
| 19 | 17,500 | Materials and Goods | Materials and goods mainly for fieldwork and investigations |
| 20 | 30,000 | Information Technology Equipment | Equipment for stakeholder consultation (tablets), for computer equipment for analysis of satellite imagery, GPS, communication equipment. |
| 21 | 40,000 | Audio Visual & Print production costs | Communication materials associated with TDA and IWR Plan |
| 22 | 15,000 | Miscellaneous | For Activities under component 2 |
| 23 | 6,000 | Transport, shipping and handling | Important of specialised equipment for ecological flows, ecosystem services |
| 24 | 194,500 | Training, workshops and conference | Stakeholder workshops, technical meetings and workshops. |
| 25 | 45,000 | International Consultants | Working with a local partner on the establishment, testing (and training on) an information system covering both basins |
| 26 | 65,000 | Local consultants | Working with an international partner on the establishment, testing (and training on) an information system covering both basins |
| 27 | 833,500 | Contractual Services-Imp Partn | - Inputs of international ($90,000) and locally based ($75,000) institutional and governance experts - Inputs of other experts ($87,500) - M& E, gender, and Safeguards specialist ($67,500) - Salaries for 66 months of Procurement Officer, Bilingual editor/translator and Communications and Outreach Officer ($313,500) within CUVECOM/Joint Secretariat - $100.000 for internships within CUVECOM/PJTC + $100,000 for implementation of studies through universities |
| 28 | 45,000 | Travel | Travel for individual experts associated with institutional studies and all other tasks ($45,000) |
| 29 | 115,000 | Contractual services - Companies | Supply Of digital solutions for video conferencing, virtual communications etc at CUVECOM/Joint Commission offices and Commissioners in Luanda and Windhoek, systems for accounting, procurement, financial management etc |
| 30 | 26,000 | Equipment and furniture | Equipment and furniture within Secretariat and satellite offices, Commission offices |
| 31 | 16,000 | Materials and Goods | For CUVECOM/Joint Secretariat and satellite offices |
| 32 | 35,000 | Communication & Audio Visual Equip | In support of video conferencing, conference and workshop facilities etc |
| 33 | 70,000 | Information Technology Equipment | Equipment for stakeholder consultation (tablets), for computer equipment for analysis of satellite imagery, GPS, communication equipment. |
| 34 | 15,000 | Audio Visual & Print production costs | Especially communication and publication materials (leaflets, booklets banners, documents etc., for CUVECOM, new Kunene Commission and Joint Secretariat |
| 35 | 11,950 | Miscellaneous | For Activities under component 3 |
| 36 | 122,550 | Training, workshops and conference | Training of CUVECOM/Joint Secretariat staff including satellite offices, Commission staff in Luanda, Windhoek and elsewhere |
| 37 | 180,000 | International Consultants | - Working with local partners to provide capacity building on i) water resources modelling (including scenario analysis) and GIS ($15,000), ii) flood risk mapping and management ($15,000), iii) hydrological monitoring ($15,000) - Working with local partners on the economic valuation of the ecosystem goods and services provided by the Angolan Highlands ecosystem ($135,000) |
| 38 | 345,000 | Local consultants | - Working with international partner to provide capacity building on i) water resources modelling (including scenario analysis) and GIS ($30,000), ii) flood risk mapping and management ($30,000), iii) hydrological monitoring ($30,000) - Working with international partners on the economic valuation of the ecosystem goods and services provided by the Angolan Highlands ecosystem ($165,000) - Design and installation of hydro-climatic data collection and processing systems ($70,000) - Support to Inter-sectoral coordination across ministries in charge of water, energy, agriculture, land, and rural development for sustainable development of water resources at both national and provincial levels (20,000) |
| 39 | 849,144 | Contractual services – imp part | - Salaries (60 months) for 3 x technical officers at Onfdjiva, Lubango and Huambo ($546,144) - Inputs of the Hydrologist ($60,000) on several outputs - Inputs of Environmental expert, especially on ecosystem services ($108,000) - Inputs of the M & E, Gender and Safeguards specialist $90,000) - Inputs f Communications and Outreach specialist ($45,000) |
| 40 | 180,000 | Travel | Travel especially for work of the 3 x technical officers based in Lubango, Ondjiva and Huambo, operation of hydroclimatic network (average of $30,000/yr) |
| 41 | 25,000 | Contractual services - Companies | Installation of remote conferencing facilities etc at offices for technical officers, CUVECOM satellite offices etc |
| 42 | 40,000 | Equipment and furniture | Mainly equipment associated with fieldwork |
| 43 | 10,000 | Communication & Audio Visual Equip | For offices of technical officers |
| 44 | 24,442 | Information Technology Equipment | Equipment for stakeholder consultation (tablets), for computer equipment for technical officers and other stakeholders |
| 45 | 20,000 | Miscellaneous | For Activities under component 4 |
| 46 | 132,500 | Training, workshops and conference | Associated with training (and workshops) of technical officers and technical personnel in GHABIC; associated with hydroclimatic systems and ecosystem services |
| 47 | 20,000 | International Consultants | Support to capacity strengthening of the Secretariat to ensure community engagement and community-driven activities |
| 48 | 107,500 | Local consultants | Support in the design and construction supervision of the pilot projects (10x$7,500); Support to capacity strengthening of the Secretariat to ensure community engagement and community-driven activities ($32,500) |
| 49 | 80,000 | Contractual Services-Imp Partn | - Inputs of the Hydrologist and Geohydrologist ($10,000) - Inputs of the Agriculture, livestock and fisheries specialists (local and international) into TDA and IWRM Plan ($20,000) - Inputs of Environment Expert ($20,000) - M & E, gender and Safeguards Specialist ($30,000) |
| 50 | 40,000 | Travel | Travel especially associated with the pilot projects (10 IWRM projects + 4 early warning sites). |
| 51 | 185,000 | Contractual services - Companies | Installation and construction work at pilot projects ($12,500 per project x 10) + $15,000 per EWS project x 4) |
| 52 | 60,000 | Equipment and furniture | $4,000 per pilot project x 10. $5,000 per EWS project site x 4 |
| 53 | 282,000 | Materials and Goods | $20,000 per pilot project x 10. $20,500 per EWS x 4. |
| 54 | 9,000 | Communication & Audio Visual Equip | In order to support capacity-building and communications with the beneficiary communities, as well as record keeping (audi and video) $500 has been allowed for each pilot project x 10 (total of $5,000) + $1000 per EWS x 4 (Total of $4,000) for each target Early Warning System (EWS) community |
| 55 | 20,000 | Information Technology Equipment | Innovation with information technology to be part of pilot projects where possible and appropriate. $1,000 pr pilot project x 10 + $2,500 per EWS pilot project x 4 |
| 56 | 30,000 | Audio Visual & Print Production Costs | Especially for monthly reporting and publicity (videos etc) of progress with pilot projects |
| 57 | 16,500 | Miscellaneous | For Activities under component 5 |
| 58 | 30,000 | Training, workshops and conference | Especially as associated with pilot demonstration projects: $1000 per pilot project x 10 + $2,500 x 4 for EWS sites |
| 59 | 93,600 | Contractual Services-Imp Partn | - Inputs of the stakeholder engagement and communications Specialists on 6.1.1 ($18,600) - Inputs of the Communications & Knowledge Management Officer on Output 6.1.1 ($15,000), on Output 6.1.2 ($15,000) - Inputs of the M & E, Gender and Safeguard specialist on Output 6.1.2 ($15,000), on Output 6.1.3 ($15,000) and 0n Output 6.1.4 ($15,000) |
| 60 | 37,900 | Travel | Travel for individual experts associated with all outputs and general gravel associated with workshops/conferences and capacity building. |
| 61 | 8,500 | Communication & audiovisual Equipment | $2,500 for the first years, $1,500 for Year 3 and $1,000 for Years 4 and 5 have been allowed for the purchase or rental of equipment for communications (projector(s), cameras, microphones/interpreter equipment, TV screen (s0 etc) so as to facilitate communications |
| 62 | 25,000 | Audio Visual & Print production costs | +/- $5,000/year across all outputs. This is to cover cost associated with presentation of outputs (both audio-visual and hard copy) and will include short videos, brochures, leaflets, reports etc |
| 63 | 15,000 | Training, workshops and conference | +/- $3,000/year across Outputs 6.1.1, 6.1.3. |
| 64a | 93,000 | International Consultants | Inception Report, mid-term and terminal review to be handled by UNDP. |
| 64b | 66,000 | Local Consultants | Inception Report, mid-term and terminal review to be handled by UNDP |
| 64c | 36,000 | Contractual Services-Imp Partns | M and E Expert |
| 64d | 12,000 | Travel | Travel budget allocated for M&E activities whereby the main costs will be related to mid-term and terminal evaluations. |
| 64e | 3.000 | Professional Services | Translation of reports |
| 64f | 10,000 | Training, workshops and conference | Mainly Inception Report |
| 65 | 444,000 | Contractual Services-Imp Partn | - Project Coordinator / IWRM Expert ($324,000) - Project Finance Specialist to manage project budgets, hiring, procurement, etc. ($60,000). NB task will be shared with Finance / Administration officer in CUVEKOM/Joint Secretariat - Admin/Fin. Assistant (PCU) to support management of project budgets, hiring, procurement, etc. ($60,000). NB task will be shared with procurement officer in CUVEKOM/Joint Secretariat) |
| 66 | 24,000 | Travel | Travel costs associated with project |
| 67 | 6,000 | Equipment and Furniture | Office furniture. This is for additional requirements above what may be provided by CUVECOM |
| 68 | 5,804 | Information Technology Equipment | 2 computers (2,804); 2 additional screens (400) software (400); 2 printers (1,000); hard drives (700); power stabilizers (500); total = 5,804 |
| 69 | 11,000 | Miscellaneous Expenses | Unforeseen miscellaneous expenses |
| 70 | 24,000 | Professional Services | Professional audit services (4,000 year X 6 years = (24,000) to be handled by UNDP. |
| 71 | 17,000 | Training, workshops and conference | Two Project Steering Committee meeting per year |

# X	Legal Context

Legal Context for Global and Regional Projects

- This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions to the Project Document attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be implemented by GWP-SA (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# XI	Risk Management

Risk Management for CSO/NGO/Non-UN or other IGO with no signed SBEAA with UNDP

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document and the Project Cooperation Agreement between UNDP and the Implementing Partner.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will, and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4, have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and such sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP is committed to the highest ethical standards and will not tolerate the diversion of the resources entrusted to it through Money Laundering or Terrorist Financing and will not partner with entities that tolerate the diversion of resources through Money Laundering or Terrorist Financing. To that effect, the Implementing Partner represents and warrants that it has not, and it shall not, at any time in the implementation of the Project engage in Terrorism Financing or Money Laundering. The Implementing Partner shall communicate the restriction of this paragraph to its and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Documents and shall take all reasonable measures to ensure that such persons do not engage in Terrorism Financing or Money Laundering.

- The Implementing Partner shall immediately disclose to UNDP any actual, apparent, potential or attempted Terrorism Financing or Money Laundering activity that it becomes aware of. The Implementing Partner shall fully cooperate with any investigation or review of Terrorism Financing or Money Laundering activity by UNDP.

- The Implementing Partner acknowledges and agrees that Terrorism Financing or Money Laundering constitute financial irregularities and that if the Implementing Partner or any of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document engages in Terrorism Financing or Money Laundering activity that would constitute a material breach of this Project Document, which entitles UNDP to immediately terminate the Project without incurring any liability or penalty.

- Furthermore, the Implementing Partner expressly acknowledges and agrees that, in the event that UNDP were to determine through an investigation or otherwise that Terrorism Financing or Money Laundering occurred, UNDP shall have, in addition to its right to immediately terminate the Project, the rights to:

i) apply and enforce the relevant sanctions in accordance with UNDP internal regulations, rules, procedures, practices, policies and guidelines, including referral of the matter to national authorities when appropriate; and

ii) recover all losses, financial or otherwise, suffered by UNDP in connection with such Terrorism Financing or Money Laundering activity.

- For the purpose of this Project Document the following terms shall have the definition ascribed to the below:

i) “Money Laundering” is generally considered as concealment of the origins of money obtained illegally, typically by passing it through a complex sequence of financial or commercial transactions. ML usually involves three stages: (i) introducing the proceeds of crime into the financial system (placement); (ii) transactions to convert or transfer the funds to other locations or financial institutions (layering); and (iii) reintroducing the funds into the legitimate economy as "clean" money and investing it in various assets or business ventures (reintegration) appearing to have been legally obtained. The FATF recommends that ML be criminalized by every country on the basis of article 3(1)(b) and (c) of the Vienna Convention and article 6(1) of the Palermo Convention.

ii) “Terrorist Financing” means providing support to individuals or entities that appear on the United Nations Security Council Consolidated Sanctions List accessible at https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using the UNDP funds. The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti-money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP programmes and projects in accordance with UNDP regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The Implementing Partner will promptly inform UNDP in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of this Project Document. Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement. Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note: The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with the Implementing Partner, responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# XII	Mandatory Annexes

- GEF Budget Template (available from BPPS NCE-VF)

- Project Map and geospatial coordinates of the project area

- Multiyear Workplan

- Social and Environmental Screening Procedure (SESP)

- UNDP Quantum Risk Register

- Overview of technical consultancies/subcontracts

- Stakeholder Analysis and Stakeholder Engagement Plan (separate document)

- Environmental Social Management Framework and Indigenous Peoples Planning Framework (separate document)

- Gender Analysis and Gender Action Plan (separate document)

- Procurement Plan for first year of implementation (separate document)

- GEF focal area specific annexes: Baseline study (separate document)

- Co-financing Letters (separate document)

- GEF Core indicators (separate document)

- GEF Taxonomy (separate document)

Annex 1: GEF Budget Template

To be provided by MPSU after TBWP clearance.

Annex 2: Project map and Geospatial Coordinates of project sites

Type 1: Water (rainwater and/or flood water) harvesting

Map 1: Site in Angola to be located between Mupa and Evale

| Settlement | Latitude (South) in decimal degrees | Longitude (East) in decimal degrees |
| --- | --- | --- |
| Evale, Angola | 16.543 | 15.744 |
| Mupa, Angola | 16.187 | 15.679 |
| Othika, Namibia | 17.796 | 15.436 |
| Likango, Namibia | 17.862 | 15.218 |

Oshakati

Map 2: 3 Sites in Namibia to be located between Othika and Likango

Likango

Othika

Type 2: Livelihood-based watershed management

Map 3: 3 Sites in Angola to be located in the marked area (see overleaf)

Cambembua

Cabembua (12.977 N, 15.51 E) in the map above, top.

Piloting of flood early warning system for communities 2

Nehone ( 16.64N, 16.03E)

Namacunde (17.31 N, 15.85E)

Annex 3: Multi Year Work Plan

Annex 4: UNDP Social and Environmental Screening Procedure (SESP)

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Enhanced water security and community resilience in the adjacent Cuvelai and Kunene transboundary river basins |
| - Project Number (i.e. Quantum project ID, PIMS+) | PIMS 4736; GEF ID 10565 |
| - Location (Global/Region/Country) | Regional (Angola and Namibia) |
| - Project stage (Design or Implementation) | Design |
| - Date | 10th December 2021 |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the project mainstreams the human rights-based approach

Human-rights based approach (HRBA) seeks to promote and protect human rights by strengthening and building capacities in rights-holders in order to empower them to claim their rights and valid entitlements, and in duty-bearers in order to enable them to meet their obligations to respect, protect and fulfil all human rights. The project will respect and support Human Rights in the project target areas (Cuvelai and Kunene River basins) through the development and implementation of the Integrated Water Resources Management (IWRM) Plans. IWRM, from the perspective of HRBA, can be seen as a planning and implementation tool to realize the HRBA. IWRM Plan development and implementation helps identify tangible indicators and targets for the duty-bearers to meet gradually in time, which measures clearly how much they meet their obligations, and it helps strengthening capacities in rights-holders so that they will be made aware of and empowered to claim their rights and valid entitlements during the development and the implementation of the IWRM Plans. The project will strengthen water governance in and for the two basins, through the maintenance and reinforcement of the national and regional stakeholder working groups (these exist already for the Cuvelai basin), which will function in a similar way to the catchment management committees that already exist in Namibia and which are planned under new legislation in Angola. Strengthened water governance through catchment management committees and water associations help reinforce the most respected procedural human rights principles: Participation, Accountability, Non-discrimination and Transparency.

Briefly describe in the space below how the project is likely to improve gender equality and women’s empowerment

Equal representation of gender is already realized currently in CUVECOM at its highest decision-making body (i.e. two female and one male commissioner in Namibia and two male and one female in Angola). The same is true for the Kunene PJTC. Gender equality achieved at the highest decision-making level ensures that the proposed gender mainstreaming measures are not sidelined. The Project also focuses on “Gender equality and women empowerment” in Outcome 3. The efforts will be mainstreamed into all CUVECOM and Kunene Commission policies and practices through the development and implementation of the Gender Action Plan. Its implementation will contribute to the improvement of gender equality and women’s empowerment in the basins. Although gender mainstreaming has been relatively successful at the senior levels within CUVECOM and the PJTC, major efforts are still required at the community leadership level. The mainstreaming of gender aspects is heavily emphasized in the IWRM Plan for the Cuvelai Basin, yet little progress has been made in terms of implementation. Representation of community-level stakeholders is still largely male. There are several areas where the programme will support gender mainstreaming throughout the project implementation. The project developed a Gender Analysis and Action Plan during the preparatory phase, which will help identify specific gaps and priority areas in the basins and a set of specific actions that the project will take to fill these gaps and address priorities. The Project will: - Sensitize stakeholders on the relevance of gender mainstreaming and gauge their interest or willingness - Promote the dialogue and collaboration of gender experts in the basins, supporting activities on an ongoing basis - Train all CUVECOM and PJTC technical task teams and other relevant project steering committees on the value of gender mainstreaming and provide concrete support.

Briefly describe in the space below how the project mainstreams sustainability and resilience

The overall objective of the Project is to move towards the agreed vision for the two basins that is oriented towards sustainability. Environmental sustainability is at the heart of the proposed project and one of the most important results to be delivered by projects financed by the Global Environment Facility. It is also one of the principles of an IWRM Plan, which aims to strike balance between the development needs and conservation, and applies the precautionary approach. Further, specific to the project sites, the basins’ population depends heavily on natural resources for their livelihoods, for their health, for their resilience to climate change, and their well-being. It is both clear and accepted by stakeholders that improved livelihoods can only be achieved through an approach that is environmentally sustainable. The main steps that will be followed by the Project to ensure environmental sustainability can be summarized as follows: - Building a much stronger knowledge base of the basin ecosystems through the TDAs - Improving stakeholder involvement across both basins through strengthening water governance, with special attention to reinforcing the process in Angola, and implementing the IWRM approach. - Improving technical and institutional capacity at all levels and with a special emphasis in Angola - Development of IWRM Plans that are based on sound knowledge bases (especially with respect to naturals resources) and input from the appropriate stakeholders from multiple sectors with various interests. - Implementation of pilot demonstration projects that tackle the key environmental-livelihood issues (community-based ecosystem management approach) and which can be taken to scale - A robust monitoring and evaluation system

Briefly describe in the space below how the project strengthens accountability to stakeholders

The project design aims to ensure full accountability for project activities by local stakeholders. The project puts a strong focus on community engagement throughout project design and this will continue throughout implementation. Engagement with project stakeholders in both countries commenced during the project development phase. These activities were led by Stakeholder Engagement professional who also has good understanding of local contexts. In addition to these consultations, meaningful, effective and informed consultations will be conducted across the project landscape during the implementation phase. Consultations will follow FPIC approach whenever Indigenous People are involved. The Project developed Stakeholder Engagement Plans and will implement them. A grievance redress mechanism will also be developed and established early in the project and communicated to all stakeholders. Access to these mechanisms will be ensured, with special attention to the specific challenges and obstacles faced by Indigenous People and Local Communities (IPLC). Consultations and participation of stakeholders, including both women and men in local communities, is not only a component of project design but will be implemented as a guiding principle throughout the project’s implementation and mainstreamed into governance principles promoted by the project. Consultations will seek to ensure that both women and men are able to fully participate, with ability to safely voice their own particular needs, concerns and interests. This may require the hosting of separate consultations for women and girls using different methodologies and outreach approaches.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Complete SESP Attachment 1 before responding to Question 2. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5below before proceeding to Question 5 |  |  |  | QUESTION 6: Describe the assessment and management measures for each risk rated Moderate, Substantial or High |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Description (broken down by event, cause, impact) | Impact and Likelihood (1-5) | Significance (Low, Moderate Substantial, High) | Comments (optional) |  | Description of assessment and management measures for risks rated as Moderate, Substantial or High |  |  |
| Risk 01 – Issues related to access to water resources Project could potentially require some adjustments or alterations to traditional or conventional ways of access to water practiced by water users, if those practices are found to be contributing to inefficient water utilization, environmental degradation, water quality degradation, etc., in order to achieve a long-term water use efficiency, environment sustainability, and fair distribution of water resources. If not designed or implemented well, such changes could cause harm to indigenous peoples and local communities (IPLC) or increase their vulnerability, especially if changes are administered top-down without adequate participation and inclusion of communities concerned. Principle 1: Leave No One Behind Principle 2: Human Rights Principle 5: Accountability Standard 6: Indigenous Peoples Standard 8: Pollution Prevention and Resource Efficiency | I = 3 L = 3 | Moderate | The objectives of Outcome 1 and 2 are to improve water resources management in the project landscape, achieve the long-term water use efficiency, environment sustainability, stronger resilience of communities to climate change, and improved water quality in the basins. In this quest, there are chances that traditionally or commonly practiced practices, which are found to be environmentally unsustainable and/or leading to inefficient water use, etc., may need to be altered during the project implementation period, which could potentially restrict the water access which has been traditionally practiced. However, new approaches to supplying water are not being proposed. |  | An Environmental & Social Management Framework (ESMF) has been developed during the PPG phase to guide risk management steps required during project implementation. During the implementation phase, the Project will undertake a Strategic Environmental and Social Assessment (SESA) for upstream activities (Outcomes 1, 2, and 3). Appropriately scoped Environmental and Social Impact Assessments (ESIAs) will be completed for downstream activities (Outcomes 4 and 5) in each country (Namibia and Angola). In each country, the ESIAs will assess potential social and environmental impacts (both short-term and long-term) of any restriction or altered access to water resources by any water users, with a particular focus on marginalized individuals or groups prior to any of such restrictions or alterations occur, to develop and implement management measures, and to monitor the implementation of such measures and their effectiveness. But before the ESIAs, additional screenings will be completed for activities definition and site selection, that will have minimal environmental and social impacts. Along with each ESIA, an Environmental & Social Impact Management Plan (ESMP) will be prepared. The ESMP will include plan that promotes the sustainable use of water resources. The Project will specifically implement: - measures to enhance natural recharge of aquifers where possible, and - an agreed governance system to allocate water resources to users - ecological water requirements at several locations across the project landscape - a long-term Integrated Water Resource Management (IWRM) Plan that will be negotiated and endorsed at the ministerial level. Consultations during the ESIAs will be meaningful and comprehensive and will follow FPIC approach when Indigenous Peoples are involved (see risk 6 below). The ESIAs and ESMPs will be completed during the first year of project implementation to further refine risk identification, mitigation and management strategies, as well as to establish a system for monitoring risks. Stakeholder consultations took place during project design. Stakeholder Engagement Plans (SEP) were also developed (one for each country) and these SEPs will be implemented during the full project, aimed at actively involving all relevant groups through targeted communication and outreach efforts. Following the ESIA/ESMP, a Grievance Redress Mechanism (GRM) will be developed and will be country specific. These GRMs will be activated in case any concerns are raised by partners or beneficiaries about human rights infringements, adverse socio-economic or environmental impacts directly or indirectly attributed to project implementation. The GRMs will also include a section dealing with potential complaints by water users and/or downstream communities who might experience or perceive negative impacts on their resource supply. All concerns will be assessed, documented, and followed up with appropriate responses in order to address the issue. |  |  |
| Risk 02 – Perpetuation of discriminations against women The project (especially for Component 5) might perpetuate existing or lead to new discriminations against women in their access to project benefit. The low knowledge of the formal law within rural communities, and the ambiguous customary practices, promote gender discrimination on accessing and controlling land. High number of women in both basins lack ID Card. This lack of a formal ID Card promotes the violation of an infinite list of rights, including civil, political, economic, cultural, and social rights. There is also a risk that women will be under-represented in pilot project activities. Principle 2: Human Rights Principle 3: Gender Equality and Women's Empowerment | I = 3 L = 3 | Moderate | This risk is prevalent given the baseline situation in the project landscape (including gender-based violence, under-representation in stakeholder groups). The practice of polygamy in rural areas, promotes land disputes over inheritance, if women become widows. |  | During the PPG, the project ensured women’s full participation in the discussions and decisions about project activities. A Gender Expert, member of the PPG Team, developed a Gender Analysis and Action Plan during the PPG phase. The Plan will ensure that women are adequately represented in the stakeholder groups to be set up to avoid under representation of women. This Plan will be regularly updated, implemented, and monitored during the full project. The ESIAs/ESMPs will review the impacts specifically associated with women During the implementation phase, in advance of undertaking consultations, steps will be taken to gather information about obstacles faced by women, their preferred approaches for consultation, and how to provide and share information with them. |  |  |
| Risk 03 – Limited institutional capacity towards Safeguards standards Project implementation partners (e.g. Government ministries, agencies, NGOs, private sector partners, as well as community associations) in both countries may not have all the capacity and tools needed to meet their obligations in the project, especially those related to their roles and responsibilities in the project cycle, as well as the social and environmental safeguarding. There is limited institutional, technical, financial capacity for joint planning and management at the transboundary basin level. Principle 1: Leave No One Behind Principle 2: Human Rights Principle 5: Accountability | I = 2 L = 4 | Moderate | The project will involve personnel from several parties for its implementation (various Government ministries, NGOs, community associations, and other third-party institutions) to implement activities on the ground. At the time of project implementation, all these partners will not necessarily be aware of UNDP technical and safeguarding requirements. Capacity gaps are also expected to have a gender and Indigenous Peoples dimension. |  | The SESA and ESIAs will conduct further assessment on risks associated with partnering with Third Parties. Specific procedures will be integrated into the ESMPs to address the risks and gaps identified. At a minimum, these procedures will include requirements for partners to: - adhere to the UNDP social and environmental standards (SES). - subject all on-the-ground activities to screening, using the SESP. - clear the on-the-ground interventions with the Project Safeguards expert - ensure that gender and Indigenous Peoples considerations are fully integrated into all activities, and that activities proactively promote women’s empowerment and human rights. - prepare bi-annual reports on progress, including status of their compliance with UNDP environment and social policies When necessary, the Project will organize trainings and/or workshops to build the capacity of key project implementation partners and equip them with necessary knowledge and tools needed to achieve the objectives of the Project effectively and efficiently. This is key to ensuring continued success over the course of the project implementation, and beyond. Such capacity building activities will start before the implementation of the first activity and will include a combination of the following topics : - UNDP Social and Environmental Standards (SES) - Stakeholder Engagement and FPIC (Free Prior and Informed Consent), - UNDP Accountability Mechanism (Grievance Redress Mechanism, SRM, SECU), - Understanding UNDP Project Cycle, - Monitoring and Evaluation of UNDP Projects, - Gender Equality and Women’s Empowerment, - Human Rights Overall, the project will have a strong focus on enhancing capacity of relevant authorities and targeted communities to ensure that they have the required knowledge and skills to actively participate in project interventions, incorporate lessons learned, and uptake good practices. |  |  |
| Risk 04 – Consultations may not be comprehensive Full participation of potentially affected stakeholders in the design and implementation of the Project is critical. However, because of logistical and/or cultural barriers, there is a risk that consultations with indigenous people, as well as local women and men (incl. FPIC process) may not be comprehensive. Principle 1: No One Left behind Principle 2: Human Rights Principle 3: Gender Equality and Women’s Empowerment Principle 5: Accountability Standard 6: Indigenous Peoples | I = 3 L = 3 | Moderate | All the project outcomes require consultation and/or engagement with stakeholders. If the stakeholder engagement is not properly designed and managed including by ensuring the full and equitable participation of various ethnic groups, women and the most vulnerable, there is a risk that women, minorities and other marginalized groups (including persons with disabilities) could be discriminated, sidelined, and not effectively involved during the different project phases resulting in them being negatively impacted by the project or in not benefiting from positive project results. |  | During the PPG, consultations with stakeholder and communities were conducted in the project landscape. These activities were led by experienced Stakeholder Engagement professionals who also has good understanding of local contexts and profound knowledge of consultation with local communities, to both gather views and concerns of stakeholders and facilitate their full contribution to project design. The Project will continue to adhere with those principles during the implementation phase. The Project will put measures in place to ensure that local people are inclusively consulted and provided with regular feedback on how their input is taken into consideration and to address any additional concerns that may be identified as the project moves forward. This engagement process will include disclosure of information in appropriate format that is understandable and relevant to local women and men and consultation in a culturally appropriate manner. Moreover, the Project will maintain a clear and transparent communication channel with the communities by presenting the activities and objectives of the project, and what are being done with the Project. The Stakeholder Engagement Plans (SEPs) developed during the PPG phase will guide the consultation and engagement activities. FPIC will be followed for consultation at every single intervention site that involves Indigenous Peoples. The country-specific Grievance Redress Mechanisms (GRMs) will also play a key role in addressing in a timely manner any concerns or grievance from affected the community. |  |  |
| Risk 05 – Impacts of climate change. The project outcomes could be compromised by the impacts of climate change. The Project will carry out activities under Output 5.1 and 4.3 that could be subject to hazards such as severe winds, storms and floods, etc. The interventions of the Project could also be impacted by disasters. This could have negative impact on both the communities, the environment and jeopardize the project objectives Principle 4: Sustainability and Resilience Standard 2: Climate Change Mitigation and Adaptation | I = 3 L = 2 | Moderate | Project activities could be affected by droughts or floods, occurring more frequently and with greater intensity with climate change. For example, the community-driven interventions to improve resilience and livelihoods that the Project will implement under Output 5.1 and 4.3 might be affected by a prolonged dry spell, floods or extreme weather events. |  | Per the project’s ESMF (ProDoc Annex 8), the Project will assess, during ESIAs, the climate risks related to the activities, and consider the measures that will need to be put in place to minimize the risks to project activities. The Project will also ensure, as part of the early warning system (Output 5.3), that beneficiaries have access to timely climate information to take measures in case of climate hazard. |  |  |
| Risk 06 – Presence of various Indigenous People in the project landscape There is a presence of various Indigenous communities in the project area. The Project’s SLM and SFM practices to be implemented in targeted landscapes, will impact (positively or negatively) the human rights, lands, natural resources, territories, and traditional livelihoods of these Indigenous People. While the project has an explicit focus on strengthening the human rights, participation, and self-determined development of local and forest dependent communities, there is the risk that the Project could face grievances or concerns about project activities affecting the rights of Indigenous People. There is also a risk that project activities can conflict with the development priorities of those Indigenous Communities, as defined by them. Principle 1: Leave No One Behind Principle 2: Human Rights Principle 5: Accountability Standard 6: Indigenous Peoples. | I = 4 L = 3 | Substantial | During PPG phase, the Project identified various Indigenous communities. The San, the Himba and their related groups constitute the indigenous peoples of Angola. In Namibia, the indigenous peoples of include the San, the Ovatue and Ovatjimba. The Ovatjimba and Ovatue (Ovatwa) are largely pastoral people, formerly also relying on hunting and gathering, residing in the semi-arid and mountainous north-west (Kunene Region) and across the border in southern Angola. These communities have strong links with the land, water resources and other surrounding natural resources. The community-driven interventions to be implemented under Outcome 5 will involve significant interactions with Indigenous Communities. |  | The consultations that were conducted during PPG phase did not follow FPIC approach. However, the project engaged with stakeholders in a way that ensured that they are fully aware of the Project and able to provide meaningful input. FPIC consultations will be undertaken during the implementation phase, before the commencement of activities involving Indigenous People. The ESMF/IPPF specifies the activities that will require FPIC. The engagement process in implementation phase will take into consideration the rights of Indigenous People and the disadvantages faced by them, linked to vulnerabilities, such as limited access to education, low literacy levels, negative stereo-typing and inadequate understanding of national or project-specific processes. Where necessary, civil society organizations representing and deemed acceptable by Indigenous communities will also be engaged to provide additional support. During the PPG phase, the Project developed an Indigenous People Planning Framework (IPPF) in addition to the ESMF. During implementation phase, the Project will develop an Indigenous People Plan (IPP), one for each country, and all the relevant consultations with be carried following FPIC principles. FPIC training will be delivered to Project Team and relevant stakeholders in Namibia and Angola. Applicable rights and claims to natural resources will be respected while working closely together with targeted communities to implement SLM/SFM practices and strengthen livelihoods. The Project will also establish a Grievance Redress Mechanism (GRM) to handle in an appropriate and timely manner grievances from the Indigenous People. |  |  |
| Risk 07 – Concerns or grievances raised by communities/stakeholders not being properly addressed. Project-affected people (PAP), including Indigenous Peoples, might not be able to effectively claim their rights, raise their concerns or file grievances, due to limiting factors and barriers. Such barriers include, but are not limited to, awareness, logistics, language, culture, literacy, and technology. If the questions, concerns, grievances and/or objections raised by the PAPs are not properly addressed, the achievement of the Project’s objectives could be jeopardized. Principle 1: Leave No One Behind Principle 2: Human Rights Principle 5: Accountability Standard 6: Indigenous Peoples | I = 3 L = 3 | Moderate | Ensuring that all Project-affected people (PAP), including Indigenous Peoples, can communicate their concerns and have access to a rights-compatible grievance redress mechanism is key to the local buy-in and to the success of the Project. |  | Communities were consulted during the PPG phase. These comprehensive, gender-responsive consultations with local communities allowed them to raise concerns and/or to request additional information. The Project accommodated their expressed interest and concerns in the project design. The engagement process will continue in the implementation phase and will take into consideration the rights Project-affected people (PAP), including Indigenous Peoples, and the disadvantages and vulnerabilities faced by them. The Project will develop a project-level Grievance Redress Mechanism (GRM) that is proportional, culturally appropriate, accessible, and transparent, and that ensures appropriate protection for claimants, and the Project also will inform the stakeholders about the existence of the mechanism and how to use it. The GRM will include an early warning system, helping to identify problems and close gaps in a timely and cost-effective manner, avoiding escalation into more entrenched or complex disputes. The GRM will be executed through the implementing partner. As needed or as requested, UNDP will be available to help the implementing partner to address project-related grievances as part of its oversight and assurance roles. |  |  |
| Risk 08 – Child Labour Project intervention under Outcome 5 (e.g. agriculture, aquaculture, agroforestry, construction, SLM and SFM activities) could potentially involve child labour. Additional hazards to children could include disrupted physical, mental, moral and social development, exposure to extreme weather conditions, injuries, infections, and diseases, etc. Principle 2: Human Rights Standard 3: Community Health, Safety and Security Standard 7: Labour and Working Conditions | I = 4 L = 4 | Substantial | US Department of Labor reports issued in 2020 indicated that Child labour continues to be prevalent in Namibia (agriculture, fishing, domestic work, each sometimes as a result of human trafficking) and in Angola (agriculture, construction, artisanal diamond mining, domestic work, each sometimes as a result of human trafficking). Project interventions intersect these high risks sectors. |  | Risks associated with child labour were assessed during the project development phase. Relevant procedures are described in the ESMF annexed to the ProDoc. Risks associated with child labour will be further assessed during the implementation phase through the ESIAs and subsequent specific mitigation/management measures will be included in the ESMPs as appropriate. |  |  |
| Risk 09 – Non-compliance with labour and safety standards Project activities Project intervention under Outcome 5 and field activities under Outcome 4 could potentially involve practices that fail to comply with national and/or international labour standards and/or occupational health and safety standards. Project staff, third-party workers and/or communities could be exposed to those risks. Principle 2: Human Rights Standard 7: Labour and Working Conditions | I = 3 L = 3 | Moderate | Unsafe work practices are poor labour practices also prevalent in the country. |  | Risks associated with occupational health and safety, working conditions and labour practices will be further assessed during the implementation phase as part of the ESIAs. The mitigation/management measures will be included in the ESMPs as appropriate. The Project will develop Labour Management Procedures as part of the ESIA/ESMP. The procedures will set out the conditions in which project workers will be employed or engaged and managed, in accordance with the requirements of the SES and applicable labour laws, rules and regulations. |  |  |
| Risk 10 – Impact on Key Biodiversity Areas and potential critical habitats. The Project will carry out activities within or near potential Key Biodiversity Areas (KBA) that are present in the project landscape. When project activities, especially ‘hard interventions’ such as water dams, concrete structure, borehole drilling, canal construction, etc.) under Outcome 4 and 5 are carried out in these areas, there could be adverse impacts to the fauna and/or flora species living in these KBAs and the ecosystems that support them. Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management. | I = 4 L = 3 | Substantial | The project landscape (adjacent Cuvelai and Kunene basins) overlaps with internationally recognized protected areas, including Iona National Park, Bicuare National Park, and Mupa National Park in Angola, and Etosha National Park in Namibia. These national parks are Key Biodiversity Areas (KBA) and could qualify for Critical Habitats. Careful planning and monitoring of activities in these areas is needed. |  | Further screening will be completed before the ESIAs.This will allow the Project to make decision on the best course of action with regards to siting the planned activities. Then the Project will conduct the ESIAs, including specialist biodiversity studies to confirm level of risk to biodiversity and ecosystem services. The ESIAs could confirm whether Endangered, Vulnerable or Critically Endangered species are found at the project’s intervention sites, as well as the ecosystem services that could be impacted. The ESMPs will address the biodiversity risks identified in or near the protected areas and other critical habitats, and management actions will be designed to achieve net gains of those biodiversity values that might be impacted within the Protected Areas. Existing Protected Area Management Plans will be reviewed to ensure alignment with this requirement. |  |  |
| Risk 11 – Exposing communities to COVID-19 and other disease outbreaks The COVID-19 and other potential disease outbreaks could pose serious difficulties for effective project implementation and benefit sharing. The project activities (e.g. frequent meetings, field visits, travelling, etc.) could inadvertently cause significant spread of the COVID-19 virus. Standard 3: Community Health, Safety and Security | I = 4 L = 2 | Moderate | As a consequence, it would affect the ability of vulnerable people to get back into economic activities as any lingering or new zoonotic disease outbreaks can affect vulnerable groups in the project area the most and leave them out from participating and accruing benefits from the project in particular from the livelihood activities. |  | The Covid-19 prevention protocols in effect in respective countries were adopted during the meetings and consultation events. To manage potential risks and vulnerabilities related to Covid-19, during the implementation, the project team will continue to strictly applying the Covid-19 prevention protocols in effect in respective countries. In addition, awareness will be promoted to ensure that people (project staff and stakeholders) are aware of the risks and undertake mitigation measures. |  |  |
| Risk 12 – Use of chemicals and pesticides The community-driven interventions to improve resilience and livelihoods (Outcome 5) supported by the Project could be using pesticides or other chemicals that may have a negative effect on the environment or human health. These interventions could also generate waste (e.g. human waste, metal scraps, plastic, batteries, chemicals, etc.). Any poor waste management at these places could cause environmental pollution and pose a threat to the health of the community and eventual workers. Standard 3: Community Health, Safety and Security Standard 7: Labour and Working Conditions Standard 8: Pollution Prevention and Resource Efficiency | I = 3 L = 3 | Moderate | Activities such as agriculture, aquaculture, fodder production, poultry, piggery, etc., presented in Outcome 5 will make use of chemicals and generate waste to some extent. |  | The Project will promote organic practices that avoid the use of pesticides and other harmful chemicals on the initiatives it supports and to encourage proper handling of wastes generated at those sites. The project will include environmental awareness activities with local communities on how to avoid issues related to waste management and environmental pollution. These issues will nonetheless be addressed in the ESMPs. |  |  |
| Risk 13 – Risk of drowning in water reservoirs (dams, rainwater retention infrastructure). The rainwater retention infrastructure (water reservoirs) built by the Project may pose risks of drowning to communities and/or livestock. Standard 3: Community Health, Safety and Security | I = 4 L = 2 | Moderate | Outcome 5 |  | The Project will ensure that stormwater retention infrastructure is constructed in a way that reduces the risk of drowning for communities and / or livestock. Solutions to manage these risks will have to be decided by mutual agreement with the communities concerned. Some solutions may consist of: - Community awareness of the dangers associated with these infrastructures, and accident prevention measures - The installation of exit ramps for animals, etc. The ESIAs will further investigate this risk and appropriate mitigation and management measures will be indicated in the ESMPs. |  |  |
| Risk 14 – Risk of water-borne diseases The rainwater retention/harvesting infrastructure (water reservoirs) to be built by the Project can be contaminated and/or be the source of waterborne diseases, such as malaria or schistosomiasis, and thus affect the health of surrounding communities. Standard 3: Community Health, Safety and Security Standard 8: Pollution prevention and resource efficiency | I = 3 L = 3 | Moderate | Outcome 5 |  | Safety measures (anti-drowning pictograms and signs and / or prohibiting access) will be put in place around the water reservoirs and beneficiaries will be made aware of the measures to be taken to avoid cases of drowning and disease. The Project will strengthen this action through health watch activities in collaboration with the health authorities of the intervention communities. This health watch will make it possible to monitor the evolution of water-related diseases in the intervention communities, and possibly help local authorities in the management of cases of water-related diseases related to the rainwater retention infrastructure of the Project. The ESIAs will further investigate this risk and appropriate mitigation and management measures will be indicated in the ESMPs. |  |  |
| Risk 15 – Environmental and Physical Hazards during construction activities During the construction activities supported by the Project, there is a risk of air pollution, water pollution, noise pollution, vibration, erosion, river dredging, physical hazards, accidents, unexploded ordnance (UXO), etc. that could affect the workers, environment and the communities around the intervention sites. Standard 3: Community Health, Safety and Security Standard 7: Labour and Working Conditions Standard 8: Pollution Prevention and Resource Efficiency | I = 3 L = 3 | Moderate | Outcome 5 |  | Per the ESMF, the Contractors involved in the construction activities will be required to submit their Construction Environmental and Social Management Plan (C-ESMP) to the Project for review and approval prior to commencing work on the ground. The purpose of the C-ESMP is to outline how their construction activities will avoid, minimize or mitigate effects on the environment, the communities and workers. The commitments in the C-ESMP should be aligned with: - The Project’s Environmental and Social Management Framework. - The UNDP Social and Environmental Standards - Relevant Social and Environmental requirements and laws of the respective countries. To that end, the Project should preferentially hire Contractors that effectively demonstrate that they can appropriately address the impacts and risks related to occupational health and safety. environment, and community. The ESIAs will further investigate this risk and appropriate mitigation and management measures will be indicated in the ESMPs. |  |  |
| Risk 16 – Introduction of invasive alien fish species Fish farming activities could inadvertently enable the introduction of invasive alien fish species into the waterbodies, leading to adverse effects on freshwater ecology and native species. Principle 4: Sustainability and Resilience Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management | I = 4 L = 3 | Substantial | Although the project is designed around the best practice in integrated fish farming, it is possible that project participants could fail to use these best practice techniques and instead introduce inappropriate exotic fish species. These could escape from aquaculture ponds into river tributaries, leading to these fish preying on small indigenous fish species. Such exotic species are often fast-breeding, voracious omnivores that eat plants and animal matter, living or dead, and can therefore be high-impact invaders that alter the structure and function of ecosystems. |  | The Project has developed an ESMF during PPG phase. Scoped ESIAs will be completed during the implementation phase. The ESIAs will assess the level and extent of the eventual impacts related to fisheries. The project will develop ESMPs that will layout the measures to prevent the introduction of invasive alien fish species. The project will promote best practice in fish farming using indigenous and/or non-invasive fish species. |  |  |
| Risk 17 - Human-wildlife conflict (HWC) Project-sponsored activities could increase the frequency of interactions between humans and wildlife, consequently increasing the likelihood of conflicts between people and animals. The conflicts will be mainly associated with droughts and water scarcity in the two basins. Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management | I = 3 L = 3 | Moderate | There are immense challenges in addressing HWC, in particular because underlying cultural, political and economic aspects that shape these conflicts are often very complex and poorly understood |  | The Project will develop and implement a human-wildlife conflict mitigation program, following widely-recognized IUCN Best Practices guidelines or similar, to ensure that efforts to manage human–wildlife conflicts are pursued through well-informed, holistic and collaborative processes that take into account underlying social, cultural and economic contexts. The ESIAs will further investigate this risk and appropriate mitigation and management measures will be indicated in the ESMPs. |  |  |
| Risk 18 – Impact on cultural resources The Project activities, especially those involving construction or excavation, could lead to unintentional impact on cultural resources. Standard 4: Cultural Heritage Standard 6: Indigenous Peoples | I = 3 L = 3 | Moderate | Cultural resources can be in urban or rural contexts and can be underground or underwater. Their cultural interest may be local, provincial or national, or within the international community. |  | Per the ESMF, the Project will carry out a screening to identify all cultural heritage assets in the project intervention areas, so that those sites can be avoided where possible The ESIAs and ESMPs will ensure that: - Full and effective community participation, stakeholder consultations and use of experts when dealing with cultural heritage properties. - Development and implementation of a chance finds procedure during all the work of the Project. - Immediately reporting to local authorities all discoveries and any archaeological sites discovered. |  |  |
| Risk 18 – Possible economic displacement The Project activities, especially those under Component 5, could lead to economic displacement. Standard 5: Displacement and Resettlement | I = 3 L = 3 | Moderate | With the Project activities under Component 5, there is a possibility of temporary restriction to access some areas, etc.). |  | The ESIAs will further investigate this risk and appropriate mitigation and management measures will be indicated in the ESMPs. The ESMPs will include a Livelihoods Action Plan where there is a need to address the impact of economic displacements. All consultation during implementation phase will adopt a Free, Prior and Informed Consent (FPIC) process when engaging with Indigenous Peoples. |  |  |
|  | QUESTION 4: What is the overall project risk categorization? |  |  |  |  |  |  |
|  | Low Risk |  |  | ☐ |  |  |  |
|  | Moderate Risk |  |  | ☐ |  |  |  |
|  | Substantial Risk |  |  | ☑ | A few Substantial Risks and multiple Moderate Risks |  |  |
|  | High Risk |  |  | ☐ |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are triggered? (check all that apply) |  |  |  |  |  |  |
|  | Question only required for Moderate, Substantial and High Risk projects |  |  |  |  |  |  |
|  | Is assessment required? (check if “yes”) |  |  | ☑ |  |  | Status? (completed, planned) |
|  | if yes, indicate overall type and status |  |  |  | ☑ | Targeted assessment(s) | Planned |
|  |  |  |  |  | ☑ | ESIA (Environmental and Social Impact Assessment) | Planned |
|  |  |  |  |  | ☑ | SESA (Strategic Environmental and Social Assessment) | Planned |
|  | Are management plans required? (check if “yes) |  |  | ☑ |  |  |  |
|  | If yes, indicate overall type |  |  |  | ☑ | Targeted management plans | Planned |
|  |  |  |  |  | ☑ | ESMP (Environmental and Social Management Plan which may include range of targeted plans) (e.g. Gender Action Plan, Indigenous People Plan, Grievance Redress Mechanism, Livelihood Action Plan.) | Planned |
|  |  |  |  |  | ☑ | ESMF (Environmental and Social Management Framework) | Completed (with IPPF) |
|  | Based on identified risks, which Principles/Project-level Standards triggered? |  |  |  | Comments (not required) |  |  |
|  | Overarching Principle: Leave No One Behind |  |  |  |  |  |  |
|  | Human Rights |  |  | ☑ |  |  |  |
|  | Gender Equality and Women’s Empowerment |  |  | ☑ |  |  |  |
|  | Accountability |  |  | ☑ |  |  |  |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management |  |  | ☑ |  |  |  |
|  | 2. Climate Change and Disaster Risks |  |  | ☑ |  |  |  |
|  | 3. Community Health, Safety and Security |  |  | ☑ |  |  |  |
|  | 4. Cultural Heritage |  |  | ☑ |  |  |  |
|  | 5. Displacement and Resettlement |  |  | ☑ |  |  |  |
|  | 6. Indigenous Peoples |  |  | ☑ |  |  |  |
|  | 7. Labour and Working Conditions |  |  | ☑ |  |  |  |
|  | 8. Pollution Prevention and Resource Efficiency |  |  | ☑ |  |  |  |

Final Sign Off

Final Screening at the design-stage is not complete until the following signatures are included

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases, PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| INSTRUCTIONS: The risk screening checklist will assist in answering Questions 2-6 of the Screening Template. Answers to the checklist questions help to (1) identify potential risks, (2) determine the overall risk categorization of the project, and (3) determine required level of assessment and management measures. Refer to the SES toolkit for further guidance on addressing screening questions. |  |
| Overarching Principle: Leave No One Behind Human Rights | Answer (Yes/No) |
| P.1 Have local communities or individuals raised human rights concerns regarding the project (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 Is there a risk that duty-bearers (e.g. government agencies) do not have the capacity to meet their obligations in the project? | Yes |
| P.3 Is there a risk that rights-holders (e.g. project-affected persons) do not have the capacity to claim their rights? | Yes |
| Would the project potentially involve or lead to: |  |
| P.4 adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | Yes |
| P.5 inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? | Yes |
| P.6 restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? | Yes |
| P.7 exacerbation of conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Gender Equality and Women’s Empowerment |  |
| P.8 Have women’s groups/leaders raised gender equality concerns regarding the project, (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| Would the project potentially involve or lead to: |  |
| P.9 adverse impacts on gender equality and/or the situation of women and girls? | Yes |
| P.10 reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | Yes |
| P.11 limitations on women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | Yes |
| P.12 exacerbation of risks of gender-based violence? For example, through the influx of workers to a community, changes in community and household power dynamics, increased exposure to unsafe public places and/or transport, etc. | Yes |
| Sustainability and Resilience: Screening questions regarding risks associated with sustainability and resilience are encompassed by the Standard-specific questions below |  |
| Accountability |  |
| Would the project potentially involve or lead to: |  |
| P.13 exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them? | Yes |
| P.14 grievances or objections from potentially affected stakeholders? | Yes |
| P.15 risks of retaliation or reprisals against stakeholders who express concerns or grievances, or who seek to participate in or to obtain information on the project? | No |
| Project-Level Standards |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| Would the project potentially involve or lead to: |  |
| 1.1 adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | Yes |
| 1.2 activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | Yes |
| 1.3 changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 risks to endangered species (e.g. reduction, encroachment on habitat)? | Yes |
| 1.5 exacerbation of illegal wildlife trade? | No |
| 1.6 introduction of invasive alien species? | Yes |
| 1.7 adverse impacts on soils? | Yes |
| 1.8 harvesting of natural forests, plantation development, or reforestation? | No |
| 1.9 significant agricultural production? | Yes |
| 1.10 animal husbandry or harvesting of fish populations or other aquatic species? | Yes |
| 1.11 significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | Yes |
| 1.12 handling or utilization of genetically modified organisms/living modified organisms? | No |
| 1.13 utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | Yes |
| 1.14 adverse transboundary or global environmental concerns? | Yes |
| Standard 2: Climate Change and Disaster Risks |  |
| Would the project potentially involve or lead to: |  |
| 2.1 areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? | Yes |
| 2.2 outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters? For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes | Yes |
| 2.3 increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| 2.4 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | No |
| Standard 3: Community Health, Safety and Security |  |
| Would the project potentially involve or lead to: |  |
| 3.1 construction and/or infrastructure development (e.g. roads, buildings, dams)? (Note: the GEF does not finance projects that would involve the construction or rehabilitation of large or complex dams) | Yes |
| 3.2 air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? | Yes |
| 3.3 harm or losses due to failure of structural elements of the project (e.g. collapse of buildings or infrastructure)? | Yes |
| 3.4 risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | Yes |
| 3.5 transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.6 adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g. food, surface water purification, natural buffers from flooding)? | Yes |
| 3.7 influx of project workers to project areas? | No |
| 3.8 engagement of security personnel to protect facilities and property or to support project activities? | No |
| Standard 4: Cultural Heritage |  |
| Would the project potentially involve or lead to: |  |
| 4.1 activities adjacent to or within a Cultural Heritage site? | No |
| 4.2 significant excavations, demolitions, movement of earth, flooding or other environmental changes? | Yes |
| 4.3 adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.4 alterations to landscapes and natural features with cultural significance? | No |
| 4.5 utilization of tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| Would the project potentially involve or lead to: |  |
| 5.1 temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |
| 5.2 economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | Yes |
| 5.3 risk of forced evictions? |  |
| 5.4 impacts on or changes to land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| Would the project potentially involve or lead to: |  |
| 6.1 areas where indigenous peoples are present (including project area of influence)? | Yes |
| 6.2 activities located on lands and territories claimed by indigenous peoples? | Yes |
| 6.3 impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to screening question 6.3 is “yes”, then the potential risk impacts are considered significant and the project would be categorized as either Substantial Risk or High Risk | Yes |
| 6.4 the absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | Yes |
| 6.5 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | Yes |
| 6.6 forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? Consider, and where appropriate ensure, consistency with the answers under Standard 5 above | No |
| 6.7 adverse impacts on the development priorities of indigenous peoples as defined by them? | Yes |
| 6.8 risks to the physical and cultural survival of indigenous peoples? | No |
| 6.9 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? Consider, and where appropriate ensure, consistency with the answers under Standard 4 above. | No |
| Standard 7: Labour and Working Conditions |  |
| Would the project potentially involve or lead to: (note: applies to project and contractor workers) |  |
| 7.1 working conditions that do not meet national labour laws and international commitments? | Yes |
| 7.2 working conditions that may deny freedom of association and collective bargaining? | Yes |
| 7.3 use of child labour? | Yes |
| 7.4 use of forced labour? | No |
| 7.5 discriminatory working conditions and/or lack of equal opportunity? | Yes |
| 7.6 occupational health and safety risks due to physical, chemical, biological and psychosocial hazards (including violence and harassment) throughout the project life-cycle? | Yes |
| Standard 8: Pollution Prevention and Resource Efficiency |  |
| Would the project potentially involve or lead to: |  |
| 8.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | Yes |
| 8.2 the generation of waste (both hazardous and non-hazardous)? | Yes |
| 8.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | Yes |
| 8.4 the use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention | No |
| 8.5 the application of pesticides that may have a negative effect on the environment or human health? | Yes |
| 8.6 significant consumption of raw materials, energy, and/or water? | Yes |

Annex 5: UNDP Risk Register

| Project Title: Enhanced Water Security and Community Resilience in the Adjacent Cuvelai and Kunene Transboundary River Basins | Project Number: 10565 | Date: 7/03/2022 |
| --- | --- | --- |

| # | Description | Risk Category | Impact & Probability | Risk Treatment / Management Measures | Risk Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Political commitment on the long-term IWRM Plan, developed based on the TDA, will not be secured (in the form of the ministerial endorsement) | Political | Low (Likelihood: 1; Impact: 4) | Both countries are committed to the joint management of the basin, not only at the technical level but also at the political level, as manifested through the establishment of the CUVECOM and through their ongoing discussion to transform the PJTC (established under a different name in 1969) into the Kunene Commission. Both countries have gone through the process of securing the ministerial endorsement on the Cubango-Okavango River Strategic Action Programme (SAP) in the past; thus, they are experienced in demonstrating their political commitment through the ministerial endorsement. Also, they are aware that the strong commitment is needed for them to attract any external resources from their partners to implement the SAP or the IWRM Plan. Therefore, the risk is considered low. Nonetheless, the project is designed to produce a series of policy briefs to facilitate linking of scientific knowledge to management and policy decisions. By keeping the senior policy makers as well as politicians closely informed of the new knowledge and information will further reduce the risk of inadequate political commitment to the IWRM Plan. | Project Coordinator, CUVECOM, PJTC |
| 2 | Basin states will not be willing to release their data for use by CUVECOM or PJTC. This will pose a significant risk to the achievement of the project outcomes, as TDA, Information Management Systems and joint basin planning activities in general will all depend on data from basin states | Political | Low (Likelihood: 1; Impact: 4) | Both governments have signed the SADC revised shared watercourse protocol, which provides the legal basis for the member states to cooperate for joint management of shared watercourses, such as the Cuvelai or Kunene River basin. Further, CUVECOM and PJTC have been discussing the importance of data collection and sharing as well as strengthened monitoring activities to collect real-time data for management decisions. It is considered as one of their priorities; hence, GEF support is requested to address this. Hence, the risk is considered low. There is no history of reticence in sharing data between the two countries | Project Coordinator, CUVECOM, PJTC |
| 3 | Lack of inter-sectoral coordination and consultation at local, sub-national and national levels will hamper the effective IWRM implementation in the basins. | Operational Organizational | Low (Likelihood: 1; Impact: 3) | The TDA-SAP (IWRM Plan)-NAP development process requires a strong inter-sectoral, multi-country consultation process. The project will support the two countries to establish inter-sectoral committees to support this process. Multi-sectoral coordination at the technical level will be strengthened through the TDA development process, while multi-sectoral coordination at the policy and political levels will be strongly promoted through the IWRM Plan and NAP negotiation process. Strong engagement of communities and local stakeholders in the IWRM implementation will be ensured not only through the implementation of the Stakeholder Engagement Plan and the Communication Plan but also through the implementation of the IWRM demonstration projects. For Angola, especially within the critical water tower area, the project will provide focused interventions to strengthen inter-sectoral coordination at national and sub-national levels under Component 4 to further mitigate this risk. This will include the logging and mining sectors, whose activities, of not well-mitigated, have negative impacts on the ecoservices provided by the water tower. | Project Coordinator, CUVECOM, PJTC |
| 4 | Poor coordination among various projects supporting CUVECOM and PJTC, funded by different entities, leading to sub-optimal results delivery or duplication or work. | Operational Organizational | Low (Likelihood: 1; Impact: 3) | The countries are highly willing to coordinate activities through CUVECOM and PJTC for their respective basins in order to maximize their cumulative impacts as well as achieve resource efficiencies in their own investments towards the joint management. Required level of coordination efforts are currently not overwhelming since both CUVECOM and PJTC currently have a limited number of partner-funded initiatives that they need to coordinate. In addition, the project supports the capacity strengthening of the Secretariat, which will provide valuable support to the two governments to coordinate various projects and initiatives as a coherent programme | Project Coordinator, CUVECOM, PJTC |
| 5 | Poor coordination among various existing and upcoming projects that are relevant to the ecosystem-based approach to the Angola’s water tower protection leading to the suboptimal results delivery and/or policy or management recommendations with conflicting messages | Moderate | Low (Likelihood: 1; Impact: 3) | Coordination of various existing and upcoming projects and initiatives in the headwater regions of the two basins is not a simple task. Angola will be supported to do the mapping of relevant initiatives in the targeted geographical areas during the project development phase to identify the potential projects and initiatives that the project should aim to coordinate and collaborate. The information gathered through the mapping exercise will influence the details of the project interventions, in particular under Component 4, to medicate and manage this risk. | Project Coordinator, Gabhic, PJTC |
| 6 | Further ecosystem and water quality degradation in the basins due to the development pressure and uncoordinated development activities across the basin. Development pressure is high in the basins, especially in Angola, and some major development decisions are made outside of CUVECOM or PJTC discussions or mandates. | Moderate/ High | Moderate (Likelihood: 2; Impact: 3) | The project will support CUVECOM and PJTC in the development of future water resources development scenarios, taking into account e-flow requirements, potential impacts from climate change and variability. This exercise, to be included in the TDA, will inform policy makers beyond the water sector about potential positive and negative impacts from different water resources development scenarios and help establish common knowledge base across the member states. Further, the project will strengthen the engagement of regional/provincial government stakeholders in the management and policy discussions of CUVECOM and PJTC as part of the efforts to raise awareness among the regional/provincial government stakeholders of the importance of water resources and the basin ecosystem integrity. With this approach, the project will support policy makers directly involved in CUVECOM and/or PJTC as well as those who are not to make more informed decisions about potential future development options that are supported by the basin resources and that would affect the basin resources at the same time. | Project Coordinator, CUVECOM, PJTC |
| 7 | The project activities will worsen, instead of improving, the livelihoods of basin communities even unintentionally in the name of conservation | Financial Social and environmental | Low (Likelihood: 1; Impact: 4) | Realizing sustainable and resilient livelihood improvement of the basin community is one of the overarching objectives of the proposed project. Thus, due consideration is given to the potential impacts of the proposed project interventions on the livelihoods of basin communities. Through the application of Social and Environmental Safeguard Procedures during the project development phase, details of this risk will be identified, and appropriate risk mitigation measures developed and incorporated into the project design. It should be stressed that the IWRM Plans to be produced will be focused on promoting sustainable development driven by the knowledge-based use of natural resources | Project Coordinator, CUVECOM, PJTC |
| 8 | Financial, operational and/or safety challenges emerged due to COVID-19 in the countries (not necessarily in the basin areas) imposing risks on the timely and effective implementation of the project activities | Financial, Operational, organizational | Low (Likelihood: 1; Impact: 4) | COVID-19 pandemic may impose restrictions on working arrangement, movements, procurement, supply chains, local market, etc., which will all impact operational efficiency of the project. It may have impacts on security stability in rural areas or in fragile states where there existed limited resilience to absorb such unpredicted and unprecedented external shocks. The level and type of risks will change as the COVID-19 pandemic situations change in particular location in the basin as well as in two countries. The project will regularly screen or COVID-19 risks through available tools and mechanisms (e.g. Social and Environmental Safeguards, Stakeholder Engagement and M&E Plans implementation) and update Quantum Project Risk Register to develop and adjust mitigation actions to deal with changing risks. The project will build the CUVECOM and the Kunene PJTC’s capacity to continue operating and coordinating closely with their member states and stakeholders remotely even without face-to-face consultations. These measures will build the operational resilience in the CUVECOM and the Kunene PJTC against shocks that were caused by COVID-19. During the development of this ProDoc, key stakeholder has adapted well to the use of remote/virtual conferencing and the continued use of this option remains an option if required during any future peaks of COVID-19. | Project Coordinator,Govt of Namibia, Govt of Angola |
| 9 | Government (and partner) priorities (and resultant financial resources) shifted to COVID-19 response, recovery and preparedness operations, leaving less attention to the joint management of the Cuvelai and Kunene River basin resources. | Financial, Political | Low (Likelihood: 1; Impact: 4) | During the project development phase, the details of the project design and interventions were developed carefully, taking into account the governments’ and basin communities’ needs in the context of COVID-19 pandemic, especially their recovery efforts. Life in both countries is gradually returning to normal and while a return to some level of pandemic conditions cannot be ruled out, the assumption is that consultations will take place on a face-to-face basis and that there will be no significant restrictions on movement. It is also worth noting that the project – and the Governments’ efforts to strengthen the joint management of water resources in the Cuvelai and Kunene River basins in general – will build resilience of the basin communities against the impacts of any possible resurgence of the pandemic and other challenges. | Project Coordinator, Govt of Namibia, Govt of Angola |
| 10 | Risk of other priorities drawing attention away from the IWRM Plans | Political | Low (Likelihood: 1; Impact: 4) | Sufficient attention has been drawn to the Cuvelai IWRM Plan through its development and approval processes in the recent past. The project will support the CUVECOM and Kunene PJTC to organize a ministerial endorsement of their respective IWRM Plans. The Cuvelai and Cunene basins in Angola and Namibia are among the high priority provinces/regions for development by the national governments. The Cuvelai basin in Namibia is one of the most densely populated areas in the country and one which suffers cycles of flooding and drought events, especially in recent years. The Cuvelai basin is seen as one with significant economic development potential. Given all of these drawcards combined, the risk of attention being diverted elsewhere is low. | Project Coordinator, CUVECOM, PJTC |
| 11 | Risk of mobilizing resources required for IWRM Implementation | Financial, Political | Low (Likelihood: 2; Impact: 4) | Securing sufficient financial resources to initiate and continue with the IWRM Plan implementation has been a significant challenge for many river basins, transboundary or otherwise. The Cuvelai and Kunene River basins may not be exceptions. However, for Cuvelai, high priority is given from both Angola and Namibia on Disaster Risk Reduction after a series of flooding and drought events in the basin, which caused significant damages to their development and the livelihoods of the basin communities. With the high priority, national budget and international aid has been channelled to the region. The project will support both Angola and Namibia to place the Cuvelai IWRM Plan and its implementation in the strategic place in the context of the DRR efforts so that the IWRM Plan implementation can be supported by DRR-related investment as well. Further, the project will support the donor roundtable to attract financial support to the IWRM Plan implementation. | Project Coordinator, CUVECOM, PJTC |
| 12 | Increased climate variability and change (see section on climate risk screening below table) | Environmental and social | Low (Likelihood: 1; Impact: 4) | The basins are situated in southern Africa, where many global circulation models indicates that the climate will be drier, flood and droughts will be more frequent and more intense. Thus, this risk is high. That is why it is even more critical to have the long-term, basin-wide IWRM Plans as a long-term strategic document for each basin, complemented by a 5-yearly investment plans and National Action Plans. To manage adverse impacts of increased climate variability and change, we need to apply inter-sectoral, holistic, and stakeholder-driven approaches, guided by long-term vision. The project will mitigate risks associated with the increased climate variability and change through the development and implementation of selected priority activities in the IWRM Plans. | Project Coordinator, CUVECOM, PJTC |
| 13 | Reduced stability and/or potential for local conflict | Environmental, social, political | Low (Likelihood: 1; Impact: 3) | There is no obvious reason why the project should have a negative impact on stability and the potential conflict. Components 1 and 2 are aimed at building plans that are based on both enhance knowledge and a high level of stakeholder engagement. The implementation of such plans is much less susceptible to conflict than an adhoc or non-integrated development approach. This holds true for the potential for conflict at all levels from the most localized through to transboundary |  |
| 1 | Project delays, constraints, or capacity-related risks related to the COVID-19 global pandemic – Short-medium-term | Political | Low (Likelihood: 1; Impact: 2) | Project implementation could start in early 2023, with the first field activities starting by the second quarter. Although unlikely, there may still be some risks associated with COIVD-19, so implementation of the various components will have to be planned taking into account COVID-19 related risks, as well any still existing constraints on international, regional and local travel. | Project Coordinator, Govt of Namibia, Govt of Angola |

Annex 6:  Overview of Project Staff and Technical Consultancies

| Consultant | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| For Project Management |  |  |
| International / Reginal / National contracting |  |  |
| Project Coordinator / IWRM Expert | 55 months | The Project Manager (PM)/IWRM Expert will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. He/She will work closely with the CUVECOM/Joint Secretariat who will have significant project implementation responsibilities under a grant agreement with GWP-SA. Duties and Responsibilities - Manage the overall conduct of the project. - Plan the activities of the project and monitor progress against the approved workplan. - Execute activities by managing personnel, goods and services, training and low-value grants, including drafting terms of reference and work specifications, and overseeing all contractors’ work. - Supervise grant agreements with the CUVECOM/PJTC Secretariat for the implementation of specific sub-Components as may be agreed. - Monitor events as determined in the project monitoring plan, and update the plan as required. - Provide support for completion of assessments required by UNDP, spot checks and audits. - Manage requests for the provision of UNDP financial resources through funding advances, direct payments or reimbursement using the FACE form. - Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports. - Monitor progress, watch for plan deviations and make course corrections when needed within project board-agreed tolerances to achieve results. - Ensure that changes are controlled, and problems addressed. - Perform regular progress reporting to the project board as agreed with the board, including measures to address challenges and opportunities. - Prepare and submit financial reports to UNDP on a quarterly basis. - Manage and monitor the project risks – including social and environmental risks – initially identified and submit new risks to the Project Board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log; - Capture lessons learned during project implementation. - Prepare revisions to the multi-year workplan, as needed, as well as annual and quarterly plans if required. - Prepare the inception report no later than one month after the inception workshop. - Ensure that the indicators included in the project results framework are monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR. - Prepare the GEF PIR; - Assess major and minor amendments to the project within the parameters set by UNDP-GEF; - Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans; - Monitor and track progress against the GEF Core indicators. - Support the Mid-term review and Terminal Evaluation process. - Act as Team technical Leader for all water resources related components including groundwater assessments, Flood risk mapping and early warning systems, water resources modelling and scenario analysis and environmental flows assessments. - Supervise technical inputs of Hydrologist, geohydrologists, environmental expert, and inputs by consultants - Ensure overall supervision of 3 x technical officers in Angola, through Gabhic office heads. |
| Monitoring & Evaluation, Gender, and Safeguards Specialist | 40 months | Duties and Responsibilities Monitoring & Evaluation aspect - Ensure project’s M&E meets the requirements of the Government, the UNDP Country Office, and UNDP-GEF; develop project-specific M&E tools as necessary. - Oversee and ensure the implementation of the project’s M&E plan, including periodic appraisal of the Project’s Theory of Change and Results Framework with reference to actual and potential project progress and results. - Monitor project progress and participate in the production of progress reports ensuring that they meet the necessary reporting requirements and standards. - Oversee/develop/coordinate the implementation of the stakeholder engagement plan. - Provide feedback to the Project Manager on project strategies and activities. - Oversee and guide the design of surveys/ assessments commissioned for monitoring and evaluating project results. - Facilitate mid-term and terminal evaluations of the project, including management responses. - Visit project sites as and when required to appraise project progress on the ground and validate written progress reports. - Suggest strategies to the Project Management for improving the efficiency and effectiveness of the project by identifying bottlenecks in completing project activities and developing plans to minimize or eliminate such bottlenecks. Safeguards aspect - Monitor progress in implementation of the project ESMP/ESMF ensuring that UNDPs SES policy is fully met and the reporting requirements are fulfilled; - Oversee/develop/coordinate implementation of all safeguards related plans. - Ensure environmental and social risks are identified, avoided, mitigated and managed throughout project implementation. - Ensuring social and environmental screening, scoping and assessment for subproject/activities when required. - Review the SESP annually, and update and revise corresponding risk log; mitigation/management plans as necessary. - Ensure social and environmental grievances are managed effectively and transparently and ensure full disclosure with concerned stakeholders. - Prepare information, communication, and awareness strategy on social and environmental management to enable proper implementation of project. Gender aspect - Monitor progress in implementation of the project Gender Action Plan ensuring that targets are fully met, and the reporting requirements are fulfilled. - Provide technical leadership to ensure integration of gender and the aim for gender equality throughout the project implementation, including development of tools, frameworks and resources. - Review the Gender Action Plan annually, and update and revise corresponding management plans as necessary. - Collect and analyze information on how gender is integrated in workshops and trainings and advise on course correction where necessary - Advise Project team on opportunities to strengthen and improve the project engagement and activities concerning gender equality and women’s empowerment, and proactively make recommendations on gender sensitive approaches, realistic and adaptive gender strategies and programming interventions that will lead to positive gender equality outcomes. - Integrate gender equality considerations in monitoring and reporting methods. - Facilitate training/workshops for relevant stakeholders and staff to promote the adoption of gender mainstreaming mechanism for all project components. - Prepare communications materials that highlight the Project’s gender equality programming, successes and lessons learnt. |
| Local / National contracting |  |  |
| Finance / Administrative / Procurement Officer | 40 months | The Finance / Administration / Procurement (FAP) Officer will support the Project Coordinator in managing the budget, administration, and procurement tasks associated with the project. In addition, this person will provide technical guidance and support to activities under Component 3 to strengthen the Operational Capacity of the CUVECOM/Joint Secretariat, working closely with the Secretariat’s Procurement officer, and put in place a financial system that enables the Secretariat to be eligible to receive direct funding from the GEF and other partners, including training of the Administrative and Financial Assistant to manage this system over the long-term. Duties and Responsibilities: - Keep records of project funds and expenditures, and ensure all project-related financial documentation are well maintained and readily available when required by the Project Coordinator; - Review project expenditures and ensure that project funds are used in compliance with the Project Document and government financial rules and procedures; - Validate and certify FACE forms before submission to UNDP; - Provide necessary financial information as and when required for project management decisions; - Provide necessary financial information during project audit(s); - Review annual budgets and project expenditure reports, and notify the Project Coordinator if there are any discrepancies or issues; - Consolidate financial progress reports submitted by the responsible parties for implementation of project activities; - Liaise and follow up with the responsible parties for implementation of project activities in matters related to project funds and financial progress reports. |
| For Technical Assistance |  |  |
| Local / National contracting |  |  |
| Hydrologists x 2 | Part-time (33 months), but mainly focussed on the first 4 years of the project. | The hydrologists, one from each country, will be national appointments, potentially secondments from the hydrological divisions in each country. They should have a minimum of five years’ experience, ideally including experience in managing the work of consultants. Duties and Responsibilities: - Inputs of the technical evaluation of consultant proposals for work on flood mapping and early warning system and water resources assessments for the Cuvelai Basin - Inputs of the technical evaluation of consultant proposals for work on environmental flows assessment and water resources/s scenarios modelling in the Kunene Basin - Drawing up of specifications for all hydroclimatic equipment, including siting of stations - Supervision of installation of hydroclimatic stations - Technical Inputs go the TDAs for each basin - Technical inputs to the IWRM Plans for each basin in line with guidance from the Project Coordinator / IWRM Expert - Assistance in provision of capacity building in hydrometry and other areas as required - Other duties that may be assigned by the Project coordinator |
| Geohydrologists x 2 | Part-time (33 months), but mainly focussed on the first 4 years of the project. | The geohydrologists, one from each country, will be national appointments, potentially secondments from the hydrological divisions in each country. They should have a minimum of five years’ experience, ideally including experience in managing the work of consultants. Duties and Responsibilities: - Inputs of the technical evaluation of consultant proposals for work on flood mapping and early warning system and water resources assessments for the Cuvelai Basin - Inputs of the technical evaluation of consultant proposals for work on environmental flows assessment and water resources/s scenarios modelling in the Kunene Basin - Drawing up of specifications for all hydroclimatic equipment, inlcuding siting of stations - Supervision of installation of hydroclimatic stations - Technical Inputs go the TDAs for each basin - Technical inputs to the IWRM Plans for each basin in line with guidance from the Project Coordinator / IWRM Expert - Assistance in provision of capacity building in hydrometry and other areas as required - Other duties that may be assigned by the Project coordinator |
| 3 x Technical Officers, Angola |  | The three technical officers will be employed under Component 4 and will be stationed in the Gabhic offices in Ondjiva, Huambo and Lubango on a full-time basis. They will provide additional capacity within Angola. The CUVECOM/Joint Secretariat will have overall responsibility for the work to be carried out by the technical officers full-time for geohydrologists, but it is anticipated that it will work through the Gabhic chain of command. Their work will be principally under Component 4 (in support of improved management of the water tower in Angola) and Component 5 (pilot demonstration projects). They will also assist in both Components 1 and 2 in Angola. , They will be professionally qualified with joint expertise covering (as far as possible), agriculture, forestry, fisheries (aquaculture), the environment and rural development Duties and Responsibilities: - Provision of support to the consultants working on flood mapping and early warning system and water resources assessments for the Cuvelai Basin - Provision of support to the consultants working on environmental flows assessment and water resources/s scenarios modelling in the Kunene Basin - Provision of support during the installation and subsequent operation of hydroclimatic stations - Technical inputs on the assessment of environmental flows in the Cunene River in Angola - Technical Inputs go the TDAs for each basin - Technical inputs to the IWRM Plans for each basin in line with guidance from the Project Coordinator / IWRM Expert - Assistance in provision of capacity building in hydrometry and other areas as required - Other duties that may be assigned by the Project coordinator |
| Procurement Officer (Secretariat) |  | The procurement officer will be recruited by the Secretariat under a grant agreement with GWP-SA for the duration of the project. This is a position on the draft post structure of the Secretariat and if so decided at the end of the project, the cost associated with the position will be taken over by the countries. Duties will be split between working on the GEF Project and other CUVECOM/PJTC projects. Salary will be in-line with civil service salaries. Duties and Responsibilities: - Keep records of project funds and expenditures, especially for activities with responsibility delegated to the CUVECOM/Joint Secretariat, and ensure all project-related financial documentation are well maintained and readily available when required by the Project Coordinator; - Work closely with the PCU Finance / Administrative / Procurement Officer - Review project expenditures and ensure that project funds are used in compliance with the Project Document and government financial rules and procedures; - Validate and certify FACE forms before submission to GWP-SA; - Provide necessary financial information as and when required for project management decisions; - Provide necessary financial information during project audit(s); - Review annual budgets and project expenditure reports, and notify the Project Coordinator if there are any discrepancies or issues; - Consolidate financial progress reports submitted by the responsible parties for implementation of project activities; - Liaise and follow up with the responsible parties for implementation of project activities in matters related to project funds and financial progress reports |
| Communications Officer (Secretariat) |  | The Communications and Outreach officer will be recruited by the Secretariat under a grant agreement with GWP-SA for the duration of the project. This is a position on the draft post structure of the Secretariat and if so, decided at the end of the project, the cost associated with the position will be taken over by the countries. Duties will be split between working on the GEF Project and other CUVECOM/PJTC projects. Salary will be in-line with civil service salaries. Duties and Responsibilities: - Support the Communications and Knowledge management Officer (in PCU) under Component 6 for developing and implementing CUVECOM and PJTC Communications Plans, including technical information on best practices developed by the project; research results associated with project activities; policy briefs; newsletters, results of Commission meetings and decisions, coordinating joint data use, etc. - Support the Communications and Knowledge management Officer (in PCU) for the development of policy briefs, in collaboration with Member States, to provide guidance on priority issues within the two basins. - Take lead responsibility for exchanges with stakeholders for communications related to Component 5 (pilot Demonstration Projects). - Take lead responsibility in keeping the CUVECOM (and PJTC) website up-to-date. - Support the Communications and Knowledge management Officer (in PCU for development and dissemination of project results and knowledge products in formats for sharing with stakeholders; developing and implementing a strategy to disseminate project knowledge products through SADC, UNDP and other partners. - Support the Communications and Knowledge management Officer (in PCU) for the project’s active contribution to learning and knowledge sharing activities and events organized by the GEF IW:LEARN program, including: participation of the project team and national focal points in IW:LEARN activities, including the GEF International Waters Conference held every two years; production of at least 2 GEF IW Experience Notes for IW:LEARN covering project activities and lessons learnt; and establishment of a project website, linked to the IW:LEARN site - Ensure that lessons learned are captured by project staff during project implementation |
| Translator/ editor/ interpreter (Secretariat) |  | The Translator/Editor/Interpreter will be recruited by the Secretariat under a grant agreement with GWP-SA for the duration of the project. This is a position on the draft post structure of the Secretariat and if so decided at the end of the project, the cost associated with the position will be taken over by the countries. Duties will be split between working on the GEF Project and other CUVECOM/PJTC projects. Salary will be in-line with civil service salaries. Duties and Responsibilities: - Translate and edit project documentation into Portuguese (and vice versa) - Translate PowerPoint presentations into Portuguese (and vice versa) - Translation of letters and e-mails as required - Provide interpretation at meetings - Keep the Secretariat website up-to-date in both languages |
| International / Regional Contracting |  |  |
| Environmental Specialist | 30 months | The Environment Specialist (based at the PCU on part-time basis) will be generally responsible for aspects related to the biophysical environment in the TDAs and IWRM Plans for both basins, and in particular in supervision of the work carried out to determine environmental flows in the Kunene River and in the evaluation of ecoservices provided by the Angolan water tower. Duties and Responsibilities - Drafting of terms of reference for the work to be carried to determine environmental flow requirements (EFR) in the Kunene River. - Work closely with water resources modellers in order to estimate potential resource quality objectives to underpin setting of EFRs in the Kunene River - Support national government partners under Component 2 in identifying sites to establish additional e-flow assessment and monitoring in the basin; agreeing on key e-flow parameters to be measured; and conducting e-flow assessments at sites. - Drafting of section relating to the biophysical environment in the TDAs for both basins, based on literature, field visits and interaction with stakeholders. Inputs ti all key elements, including causal chain analysis - Support strengthening the technical capacity of CUVECOM/PJTC and the Member States (through existing and new task teams) - Support contracted experts under Component 2 in developing future water resources development scenarios - Support national government partners in developing a strategy for joint monitoring frameworks - Provide oversight to contracted NGOs and/or other partners responsible for the sustainable land management pilot projects under Component 5, including linking the pilot site activities on sustainable land management with the sedimentation modelling and monitoring carried out under Components 1,2 and 4. - Take lead responsibility under for monitoring & evaluation of the GEF-supported project including: - Monitor ecosystem and/or socioeconomic changes targeted in the project’s Results Framework (i.e. tracking progress on stress reduction indicators and socioeconomic and environmental status indicators) and otherwise support the monitoring of ecosystem and socioeconomic status changes that result from the implementation of the LIMCOM IWRM plan and other various relevant activities in the basin at national, local levels - Contribution to ensuring project’s M&E meets the requirements of the Government, the UNDP Country Office, and UNDP-GEF; - Oversee and guide the design of surveys/ assessments commissioned for monitoring and evaluating project results with respect to ecosystems, biodiversity and other environmental aspects - Support facilitation of mid-term and terminal evaluations of the project; including management responses - Support project site M&E and learning missions - Visit project sites as and when required to appraise project progress on the ground and validate written progress reports. |
| Communications & Knowledge Management Officer (part-time) | 24 months | The Communications and Knowledge Management Officer (based at the PCU) will, working closely with the Communications and Outreach Officer in the CUVECOM/Joint Secretariat, lead all communications and knowledge management activities for the project (primarily under `Component 6) as well as supporting activities in those areas on a broader scale for CUVECOM and the PJTC. Duties and Responsibilities - Take lead responsibility under Component 6 for developing and implementing CUVECOM and PJTC Communications Plans, including technical information on best practices developed by the project; research results associated with project activities; policy briefs; newsletters, results of Commission meetings and decisions, coordinating joint data use, etc. - Take lead responsibility for the development of policy briefs, in collaboration with Member States, to provide guidance on priority issues within the two basins. - Take lead responsibility for exchanges with other RBOs and relevant regional institutions, including participation in SADC RBO Dialogue and SADC Multi-Stakeholder Dialogues; participation in regional meetings of RBOs; participation in and provide information to digital platforms on transboundary river management; and exchange visits with other RBOs on technical issues around transboundary river management - Take lead responsibility for development and dissemination of project results and knowledge products in formats for sharing with stakeholders; developing and implementing a strategy to disseminate project knowledge products through SADC, UNDP and other partners. - Take lead responsibility for the project’s active contribution to learning and knowledge sharing activities and events organized by the GEF IW:LEARN program, including: participation of the project team and national focal points in IW:LEARN activities, including the GEF International Waters Conference held every two years; production of at least 2 GEF IW Experience Notes for IW:LEARN covering project activities and lessons learnt; and establishment of a project website, linked to the IW:LEARN site - Ensure that lessons learned are captured by project staff during project implementation |

Annexes provided as separate documents

Annex 7. Stakeholder Analysis and Stakeholder Engagement Plan

Annex 8. Environmental Social Management Framework and Indigenous Peoples Planning Framework

Annex 9. Gender Analysis and Gender Action Plan

Annex 10. Procurement Plan for first year of implementation

Annex 11. GEF focal area specific annexes: Baseline study

Annex 12. Co-financing Letters

Annex 13. GEF Core indicators

Annex 14. GEF Taxonomy

The First Investment Plan was put in place to cover 2019-2024 at the same time as the first and preliminary IWRM Plan was drafted (2018/9)

The footnote mentions the 1969 agreement in which the PJTC was established (an agreement between South Africa and Portugal). However, this was updated in 1990 soon after Namibia’s independence in the Agreement of Co-operation between the two countries and the Angolan-Namibian Border Security Agreement in 1990. One of the first concrete steps following this agreement was the creation of Permanent Joint Technical Commission on the Kunene River (PJTC) that was created in the same year

Chimpacas are artificial storage reservoirs

See https://www.thegef.org/gef/policies_guidelines

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

GABHIC provides support for this satellite office including provision of office space and funding of staff

The proposal is to have 1 hydrologist and 1 geohydrologist for a total of 120 months. An alternative would be to have 4 positions with one from each country assigned to each basin.

The concept of the NASCs and the BASC is adopted from lessons learned in the Zambezi River Basin. ZAMCOM has established the NASC and BASC to facilitate dialogue and consensus building on issues pertaining to the planning, development and management of water and related resources in the Zambezi Basin.

See https://popp.undp.org/ https://popp-prod.acquia.undp.org/policy-page/close-and-transition.

Use bracketed text only when IP is an NGO/IGO

Prohibited grounds of discrimination include race, ethnicity, sex, age, language, disability, sexual orientation, gender identity, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender and transsexual people.

See the Convention on Biological Diversity and its Cartagena Protocol on Biosafety.

See the Convention on Biological Diversity and its Nagoya Protocol on access and benefit sharing from use of genetic resources.

Forced eviction is defined here as the permanent or temporary removal against their will of individuals, families or communities from the homes and/or land which they occupy, without the provision of, and access to, appropriate forms of legal or other protection. Forced evictions constitute gross violations of a range of internationally recognized human rights.