## Fund distribution summary
Fund distribution summary
Fund code | Donor Name | Donor Code | Available Resources | Receivable | Total AWP current 2023 Budget | Total AWP future year Budget (s) | Un-Programmed
|  |  | A | B | C | D | E = (A + B)-(C +D)
30000 | NETHERLANDS | 00182 | 30482.53 |  | #REF! |  | #REF!
30000 | SIDA | 00555 | 532622.68 |  | 437531.46 |  | 95091.22
30000 | USAID | 10480 | 2309334.37 | 4651973.54 | 2282073.04 |  | 4679234.87
30000 | NORWAY | 10503 | 60486.57 |  | 61030.026 |  | -543.456
30079 | EU | 10159 | 405570.53 |  | 320656.39 |  | 84914.14
30000 | FRANCE | 00112 | 5094.65 |  | 11535.3618 |  | -6440.7118
32045 | JAPAN | 00141 | 430577.11 |  | 426904.88 |  | 3672.23
| Total |  | 3774168.44 | 4651973.54 | #REF! | 0 | #REF!
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The milestone was due 31 Dec 2022

## AWP_2023
Annual Work Plan 2023
Atlas PROJECT ID: | 00131655
Atlas OUTPUT ID: | 00124641
ATLAS Project/Programme Title: | Support to Iraq´s Electoral Process – Capacity Development
Atlas OUTPUT Name | Elections Capacity Development
UNSDCF/CPD Outcome (2020-2024): | 3.1. Strengthened institutions and systems deliver people-centred, evidence and needs-based equitable and inclusive gender and age-responsive services, especially for the most vulnerable populations, with particular focus on advocating for women’s leadership in decision-making processes.
Applicable Key Result Area/Output (from 2018-2021 Strategic Plan): | Output 2.2.2 Constitution-making, electoral and parliamentary processes and institutions strengthened to promote inclusion, transparency and accountability. Output Indicator 2.2.2.1. Number of Electoral Management Bodies (EMBs) with strengthened capacity to conduct inclusive and credible elections
Applicable Key Result Area/Output (from 2022-2025 Strategic Plan):
CPD Output (s) 2020-2024: | Output 3.3: National institutions and mechanisms dedicated to promoting social cohesion and prevention of violent extremism strengthened
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount (USD) | Notes
Output 1: Strengthened technical capacities of IHEC to deliver elections in a credible, professional manner.
Output1.1: Operational and administrative capacities of IHEC to deliver CoR elections are improved. Indicators: 1.1.1- % of trained IHEC staff who feel that they are more effective in their jobs because of training and capacity development opportunities. 1.1.2-# of induction trainings held 1.1.3-# of fully functional tele-conferencing facilities established 1.1.4 - # of lessons learning exercises held at IHEC HQ and field offices Baselines (2020): 1.1.1 - 0% 1.1.2 - 0 1.1.3 - 0 1.1.4 - 0 Annual Target: 1.1.1-40% of senior managers trained 1.1.2-50% of IHEC aware of gender mainstreaining provisions 1.1.3 - 0 1.1.4 - 0 | 1.1.1: Support to electoral preparations through capacity-building programmes for staff that instill values and principles underpinning transparent elections. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 10000
| 1.1.2: Development and delivery of operations planning and management training for IHEC senior management. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 20000
| 1.1.3: Technical support on gender mainstreaming on election management, including developing and designing IHEC’s internal gender policy. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 50000
| 1.1.4: Gender mainstream training for IHEC operations staff in Baghdad and governorate offices. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 84000
|  | X | X | X | X | UNAMI/ UNDP | 30079 | EU | 10159 | 71400 | Contractual Services - Individ | 0
| 1.1.5: UN support for electoral security planning through participation in the High Election Security Council meetings. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 70000
| 1.1.6: Procurement and installation of conferencing capacities to facilitate management of meetings and trainings in IHEC HQ and GEOs during COVID-19 emergency. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 40000
| 1.1.7: A lessons-learned workshop (facilitated by international experts) to identify challenges encountered along the electoral process and recommend solutions. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 40000
| 1.1.8: Support to IHEC in Upgrading the Capacities of its Central Servers for Biometric Voter Registration |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
| 1.1.9: Establishing In-House Biometric Voter Card Printing Capacity |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
| 1.1.10: Package of Upgrade for IHEC GEO and HQ Network Capacities | X | X | X | X | UNAMI/ UNDP | 32045 | Japan | 141 | 72800 | Information Technology Equipment | 395282.2963
| 1.1.11: Support with E-Day COVID-19 Mitigation Measures for Polling Staff | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Materials & Supplies
| Monitoring Costs | X | X | X | X | UNAMI/ UNDP
| GMS (8%) | X | X | X | X | UNDP | 30079 | EU | 10159 | 75100 | Facilities & Administration | 0
| GMS (8%) | X | X | X | X | UNDP | 32045 | Japan | 141 | 75100 | Facilities & Administration | 31622.5837
| GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 25120
[11 empty] | SUB-TOTAL (OUTPUT 1.1) | 766024.88
Output1.2: The technical capacity of IHEC staff at HQ and governorates offices is developed through a comprehensive capacity development strategy Indicators: 1.2.1- % of IHEC staff (HQ and governorate offices) aware of gender mainstreaming provisions relevant to their respective areas/departments 1.2.2 # of master trainers trained (gender disaggregated) 1.2.3 # of thematic trainings held at HQ and field offices (result to be reported disaggregated by theme) 1.2.4 # of comprehensive capacity development strategy and action plan developed by IHEC 1.2.5 # of IHEC staff trained at HQ and field offices (gender disaggregated) Baselines (2020): 1.2.1 - 0% 1.2.2 - 0 1.2.3 - 0 1.2.4 - 0 1.2.5 - 0 Annual Target: 1.2.1- 50% 1.2.2 - 10 (25% women) 1.2.3 - 2 1.2.4 - 0 1.2.5- 200 | 1.2.1: Design of a comprehensive capacity development strategy and action plan and monitoring and evaluation activities to assess its effectiveness. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 10000
| 1.2.2: Design of an induction package and delivery of induction training for newly recruited GEO staff. Gender-responsive electoral processes will be integrated in the induction. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 40000
| 1.2.3: Training for master trainers at IHEC HQ and governorate level, including on gender perspectives. | X | X | X | X | UNAMI/ UNDP | 30079 | EU | 10159 | 61300 | Salary & Post Adj Cst-IP Staff | 0
|  | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 81000
| 1.2.4: Training on devolved results management, and specialized training in Information and Communication technology (ICT). | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference and Travel
| 1.2.5: Training on electoral operations and procedures. COVID-19 Trainings | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference and Travel
|  | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/local consultants
| 1.2.6: Training on reporting and monitoring, using gender indicators on elections management. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference and Travel
| 1.2.7: Procurement and installation of conferencing facilities to supporting GEO remote training and meetings during COVID-19 emergency. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
Monitoring Costs
| GMS (8%) | X | X | X | X | UNDP | 30079 | EU | 10159 | 75100 | Facilities & Administration | 0
| GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 10480 | Not correctly included in the final budget approved by donor
[11 empty] | SUB-TOTAL (OUTPUT 1.2) | 141480
Output 1.3
Output1.3: The electoral legal framework is strengthened Indicators: 1.3.1 # of legal provisions/policy measures amended to be more inclusive 1.3.2 # of awareness raising interventions conducted on enhanced inclusivity and participation Baselines (2020) 1.3.1 - 0 1.3.2 - 0 Annual Target: 1.3.1 - 2 1.3.2 - 3 | 1.3.1: Review of existing IHEC regulations and instructions to align with international best practices. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/national Advisers
| 1.3.2: Advocacy and support and provision of technical advice in designing legislation and/or policy measures to promote the political participation and representation of women, youth and marginalized groups. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/national Advisers
| 1.3.3: Provision of technical advice and assistance on monitoring and enforcement of existing electoral legislation; provide support in awareness raising of special measures to increase political participation of women, youth, the displaced and other marginalized groups. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/national Advisers
Monitoring Costs
| GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration
[11 empty] | SUB-TOTAL (OUTPUT 1.3) | 0
[11 empty] | SUB-TOTAL (OUTPUT 1) | 907504.88
Output 2: The conduct of key electoral operations for Council of Representatives elections is improved.
Output 2.1: IHEC acts in a transparent manner through improved communication Indicators: 2.1.1- # of Comprehensive communication and media strategy for elections in place 2.1.2 # of viewers/users of IHEC’s website and other social media platforms 2.1.3 # of staff using project supported institutional email system and operational guidelines for field offices in place Baselines (2020): 2.1.1 - 0 2.1.2 - 0 2.1.3 - 0 Annual Target: 2.1.1 - 0 2.1.2 - 1,000,000 2.1.3 - 800 | 2.1.1: Support to the development of IHEC’s comprehensive communication and media strategy for elections. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
|  | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
| 2.1.2: Provision of technical advice and support on IHEC’s website and social media strategy to disseminate information relevant to the electoral process. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
| 2.1.3: Provision of technical advice to create a systematic and effective internal communications system (including setting up a corporate IHEC emailing system and improve connectivity between HQ and GEOs). | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
Monitoring Costs
| GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration
[11 empty] | SUB-TOTAL (OUTPUT 2.1) | 0
Output 2.2: IHEC promotes inclusiveness in all phases of the electoral process and in its working environment, with a special focus on the participation of women, first-time voters and marginalized groups Indicators: 2.2.1 # of IHEC policies and procedures that were gender mainstreamed 2.2.2 # of trainings held on importance of women and youth participation Baselines (2020): 2.2.1 - 0 2.2.2 - 0 Annual Target: 2.2.1 - 4 2.2.2 - 4 | 2.2.1: Conduct an internal assessment of IHEC’s gender policies, to identify gaps in existing practices and identify opportunities for gender mainstreaming. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 89810
| 2.2.2: Provide guidance and support to development of an internal gender policy which defines IHEC´s operational objectives, responsibilities and targets on gender equality - on human resources, operations and staff capacity development. | X | X | X | X | UNAMI/ UNDP | 30079 | EU | 10159 | 61300 | Salary & Post Adj Cst-IP Staff | 0
|  | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 75000
| 2.2.3: Provision of training on gender responsive electoral processes. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 80000
| 2.2.4: Provision of guidance and support to the IHEC’s gender unit/focal point | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 70000
| 2.2.5: Provision of training and support for awareness-raising strategies to help IHEC promote youth and marginalized groups’ participation and representation in electoral processes. | X | X | X | X | UNAMI/ UNDP
| Monitoring Costs | X | X | X | X | UNAMI
| GMS (8%) |  |  |  |  | UNDP | 30079 | EU | 10159 | 75100 | Facilities & Administration | 0
| GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 25184.8
[11 empty] | SUB-TOTAL (OUTPUT 2.2) | 339994.8
[11 empty] | SUB-TOTAL (OUTPUT 2) | 339994.8
Output 3 The conduct of key electoral operations for the Council of Representatives elections is improved.
Output 3.1: Support to IHEC’s operational and administrative preparations at the central and field offices. Indicators: 3.1.1 Assessment of application of new technologies in Voter Registration processes, with actionable recommendations, produced 3.1.2 # of trainings conducted on use of new technologies 3.1.3 # of operational trainings on procedures and rules of VR 3.1.4 # of advisories provided to IHEC in procuring and overseeing an independent audit of the election results management system 3.1.5 # of IDPs registered as voters (gender disaggregated) 3.1.6 Gender disaggregated voter registration data available Baselines (2020): 3.1.1 - 0 3.1.2 - 0 3.1.3 - 0 3.1.4 -0 3.1.5 - 0 Annual Target: 3.1.1 - 0 3.1.2 - 0 3.1.3 - 0 3.1.4 -0 3.1.5 - 0 | 3.1.1 'Support to the voter registration process for more accurate voters´ lists | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.1.2 'Development of D-day procedures and training manuals, including production of innovative training tools | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.1.3 'Assisting in the formulation and implementation of cascade training plan | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.1.4 'Support for the preparation and management of a Results Management System (RMS) | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
|  | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.1.5 'Training and ongoing support to IHEC staff on Results Management, seats allocation and Information and Communication Technology (ICT) | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| Monitoring Costs | X | X | X | X | UNAMI
| GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
[11 empty] | SUB-TOTAL (OUTPUT 3.1) | 0
Output 3.2: Support to civic and voter education initiatives Indicators: 3.2.1: # of calls for proposal completed to administer small grants to civil society groups to implement countrywide voter education campaigns 3.2.2 # of voter education materials produced 3.2.3 # of comprehensive youth motivational campaign using social media developed, with a specific focus on young people (first time voters) 3.2.4 # of grants issued to civil society organizations to support the work of CSOs and national media Baselines (2020): 3.2.1 - 0 3.2.2 - 0 3.2.3 - 0 3.2.4 - 0 Annual Target: 3.2.1- 0 call for proposals in 2022 3.2.2 - 0 documents produced 3.2.3 - 0 campaigns 3.2.4 - 0 grants | 3.2.1 'Administer a small grants programme to support civil society groups in the implementation of countrywide voter education campaigns: The provision of small targeted grants will enable the involvement of youth groups in a voter participation campaign specifically targeting youth; groups representing people with disabilities, to reach out to disabled voters; and the dissemination of civic and voter education to IDPs and minority communities. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.2.2 'Support for the production of voter education materials | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.2.3 'Support for a youth motivational campaign using social media | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| Monitoring Costs |  |  |  |  | UNAMI
| GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
[11 empty] | SUB-TOTAL (OUTPUT 3.2) | 0
Output 3.3: Improvement of IHEC’s structured engagement with stakeholders Indicators: 3.3.1 # of information working groups/meetings with key stakeholders in electoral processes 3.3.2 A fully functional IHEC Media Centre is established 3.3.3 19 Governorate Electoral Offices (GEOs) and 1 national results acceleration center established Baselines (2020): 3.3.1 - 0 3.3.2 - 0 3.3.3 - 0 Annual Target: 3.3.1 - 0 3.3.2 - 0 3.3.3 - 0 | 3.3.1 'Support for regular IHEC briefing of electoral stakeholders, such as political parties, media and civil society groups | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.3.2 'Support for the establishment of a well-equipped, fully functional IHEC Media Centre | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
|  | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
| 3.3.3 Support for the establishment of IHEC Governorate Results Announcement Centers (GEO RAC) complementary to National Results Announcement Center (NRAC) in Baghdad' | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment + Assessment
|  | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment + Assessment
Monitoring Costs
| GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
[11 empty] | SUB-TOTAL (OUTPUT 3.3) | 0
Output 3.4: 'IHEC promotes inclusiveness in all phases of the electoral process for a conducive electoral environment Indicators: 3.4.1 # of trainings provided to women candidates 3.4.2 Electoral Code of Conduct is developed for 2021 3.4.3 # of specialized trainings to counter hate speech delivered to political actors and media Baselines (2020): 3.4.1 - 0 3.4.2 - 0 3.4.3 - 0 Annual Target: 3.4.1 - 0 3.4.2 - 0 3.4.3 - 0 | 3.4.1 Training for female candidates | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.4.2 Support to IHEC in developing an electoral Code of Conduct (in collaboration with UNAMI´s Office of Political Affairs) | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.4.3 Delivery of specialized training to counter hate speech | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs
| GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
[11 empty] | SUB-TOTAL (OUTPUT 3.1) | 0
Output 3.5: Strengthen IHEC’s electoral adjudication mechanism and appeals process Indicators: 3.5.1: # of reviews of IHEC complaints adjudication system completed 3.5.2: # of framework for the appeals process established 3.5.3: # of specialized trainings on the complaints adjudication system and appeals system delilvered 3.5.4: # of Public information campaigns for electoral stakeholders and electorate is designed and delivered Baselines (2020): 3.5.1 - 0 3.5.2 - 0 3.5.3 - 0 3.5.4 - 0 Annual Target: 3.5.1 - 0 3.5.2 - 0 3.5.3 - 0 3.5.4 - 0 | 3.5.1 'Review of IHEC complaints adjudication system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.5.2 Support to development of appeals regulation | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
| 3.5.3 'Specialised training on the complaints adjudication system and appeals system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
| 3.5.4'Public information campaign for electoral stakeholders and electorate |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs
| 3.5.1 'Review of IHEC complaints adjudication system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.5.2 Support to development of appeals regulation | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
| 3.5.3 'Specialised training on the complaints adjudication system and appeals system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
| 3.5.4'Public information campaign for electoral stakeholders and electorate |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs
| GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
[11 empty] | SUB-TOTAL (OUTPUT 3.1) | 0
Output 3.6: The project is effectively and sustainably managed and implemented, under national ownership Indicators: 3.6.1 # of staff in place to enable implementation of the project (disaggregated by technical and management roles) 3.6.2 % of completion for Procurement of equipment, transport and communication means. 3.6.3: A substantive project monitoring, evaluation and reporting mechanism is in place. Baselines (2020): 3.6.1 - 0 3.6.2 - 0 3.6.3 - No Annual Target: 3.6.1 - 25 (85% technical and 15% management) 3.6.2 - 50% 3.6.3 - Yes | 3.6.1 'Recruitment of top quality, experienced project personnel. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 1076213.193
|  | X | X | X | X | UNAMI/ UNDP | 30000 | SIDA | 00555 | 61300 | Salary & Post Adj Cst-IP Staff | 341121.7222
|  | X | X | X | X | UNAMI/ UNDP | 30079 | EU | 10159 | 61300 | Salary & Post Adj Cst-IP Staff | 232904.0648
|  | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Salary & Post Adj Cst-IP Staff | 173007.3996
| 3.6.2 'Oversight of, and close engagement with, the project by UNAMI senior leadership and OEA. | X | X | X | X | UNAMI/ UNDP | 30000 | Norway | 10503 | 71200 | International Consultant | 56509.2833
| 3.6.3 'Procurement of equipment, transport and communication means; COVID-19 protective equipment and preparedness; security for staff deployment. | X | X | X | X | UNAMI/ UNDP | 30000 | France | 112 | 74000 | Miscellaneous Operating Expens | 9192.0222
| 3.6.4 'A substantive project monitoring, evaluation and reporting mechanism is put in place. Conduct a Project Evaluation’ | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71200 | International Consultant | 40000
| 3.6.5 Full collaboration and co-operation with IHEC staff, its leadership | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| 3.6.6: Programmatic contingency funding to be used only for programmatic activities | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
|  | X | X | X | X | UNAMI/ UNDP | 30000 | France | 112 | 74000 | Miscellaneous Operating Expens | 10000
| GMS (8%) | X | X | X | X | UNDP | 30000 | Norway | 10503 | 75100 | Facilities & Administration | 4520.7427
| GMS (8%) | X | X | X | X | UNDP | 30079 | EU | 10159 | 75100 | Facilities & Administration | 18632.3252
| GMS (8%) | X | X | X | X | UNDP | 30000 | SIDA | 00555 | 75100 | Facilities & Administration | 27289.7378
| GMS (8%) | X | X | X | X | UNDP | 30000 | France | 112 | 75100 | Facilities & Administration | 1535.3618
| GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 103137.6474
[11 empty] | SUB-TOTAL (OUTPUT 3.1) | 2094063.5
[11 empty] | SUB-TOTAL (OUTPUT 3) | 2094063.5
DPC for Country Office Support Services | DPC for Country Office Support Services | X | X | X | X | UNDP | 30079 | EU | 10159 | 74500 | Staff Mgmt Costs - IP Staff (Services to Projects) | 64000
| DPC for Country Office Support Services | X | X | X | X | UNDP | 30000 | USAID | 10480 | 74500 | Staff Mgmt Costs - IP Staff (Services to Projects) | 64000
| DPC for Country Office Support Services | X | X | X | X | UNDP | 30000 | SIDA | 00555 | 74500 | Staff Mgmt Costs - IP Staff (Services to Projects) | 64000
| GMS (8%) | X | X | X | X | UNDP | 30079 | EU | 10159 | 75100 | Facilities & Administration | 5120
| GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 5120
| GMS (8%) | X | X | X | X | UNDP | 30000 | SIDA | 00555 | 75100 | Facilities & Administration | 5120
[11 empty] | SUB-TOTAL (DPC) | 207360
Total Project Budget for 2023 | [11 empty] | 3548923.18
Programme/Project Manager Name & Signature |  | Resident Representative/ Deputy Resident Representative: Name & Signature
Date: |  | Date:

## Note on the Budget
The key role of the project staff is building the capacity of IHEC through the provision of technical advice and guidance to the IHEC staff.
Therefore, in the 2023 AWP, the salary of the project staff is allocated 50:50 to program activities under Activity 1.1, 1.2 and 2.2 and project management under Activity 3.6 respectively.

## HR Plan
UNDP Iraq
Human Resource Plan 20xx
Project/Programme Title:
Project ID: 00131655
Output ID: 00
No. | Post Title (As per Approved Project Organogram) | Status (Vacant/Filled) | Name (for positions already Filled) | Number of Posts | Type of Contract | Category (National/ International) | Grade | Pro Forma | Estimated Budget | COA |  |  |  | Funds Available in Work Plan (Yes/No) | Expected or actual End of Contract | Required period of extension | Project end date |  | Remarks
[10 empty] | Project | Donor | Fund Code | Activity |  |  |  |  | Expection completion date of HR process
1 | Project Manager | Filled | Sammy Alfandika | 1 | FTA | International | P4 | 282925.982 | 282925.982 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
2 | Finance Specialist | Filled | Worknesh KETEMA | 1 | FTA | International | P3 | 245998.351 | 245998.351 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
3 | Legal Advisor | Filled | Josepf Tummers | 1 | FTA | International | P4 | 282925.982 | 212194.4865 | 00124641 | 10480 | 30000 | 1.1 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
4 | ICT Officer | Filled | Ammar SAEEDI | 1 | SC | National | SB5 | 75249.024 | 75249.024 | 00124641 | 10480 | 30000 | 1.1 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
5 | Programme Support | Filled | Firas AL-KARKHI | 1 | SC | Natioal | SB-5 | 75249.024 | 75249.024 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
6 | Electoral Support | Filled | Ali Ehsan Naser AL-KHAFAJI | 1 | SC | National | SB-4 | 56277.504 | 56277.504 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
7 | Communication Officer | Filled | Aous Youns | 1 | SC | National | SB5 | 75249.024 | 75249.024 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
8 | Driver | Filled | Mohanad Ali Najm | 1 | SC | National | SB-2 | 41481.0716 | 41481.0716 | 00124641 | 10480 | 30000 | 1.1 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
9 | Financial Mgmt Support | Vacant | To be filled | 1 | SC | National | SB5 | 75106.8864 | 59459.6184 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
10 | Operations Officer | Vacant | To be filled | 1 | SC | National | SB4 | 75106.8864 | 59459.6184 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
11 | Asset/Administration Officer | Vacant | To be filled | 1 | SC | National | SB5 | 75106.8864 | 59459.6184 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
12 | Operations Adviser | Vacant | To be filled | 1 | TA | International | P4 | 246953.3865 | 185215.0399 | 00124641 | 555 | 30000 | 1.2 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
13 | Field Coordination Adviser | Vacant | To be filled | 1 | TA | International | P4 | 246953.3865 | 185215.0399 | 00124641 | 555 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
14 | ICT Specialist | Vacant | To be filled | 1 | TA | International | P4 | 246953.3865 | 185215.0399 | 00124641 | 10159 | 30079 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
15 | Communication Adviser | Vacant | To be filled | 1 | TA | International | P4 | 246953.3865 | 185215.0399 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
16 | Legal Officer | Vacant | To be filled | 1 | SC | National | SB5 | 75106.8864 | 59459.6184 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
17 | Security Adviser | Vacant | To be filled | 1 | TA | International | P4 | 246953.3865 | 185215.0399 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
18 | Transportation Support | Vacant | To be filled | 1 | SC | National | SB2 | 23362.56 | 18495.36 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
19 | Electoral Support | Vacant | To be filled | 1 | SC | National | SB5 | 75106.8864 | 59459.6184 | 00124641 | 10480 | 30000 | 1.2 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
20 | KRG Electoral Adviser | Vacant | To be filled | 1 | TA | International | P4 | 246953.3865 | 185215.0399 | 00124641 | 10480 | 30000 | 2.2 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
21 | ICT Specialist | Vacant | To be filled | 1 | TA | International | P4 | 246953.3865 | 185215.0399 | 00124641 | 10480 | 30000 | 2.2 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
22 | Legal Specialist | Vacant | To be filled | 1 | TA | International | P3 | 214379.1051 | 160784.3288 | 00124641 | 10159 | 30079 | 1.1 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
23 | Liaison and Reporting Officer | Vacant | To be filled | 1 | IUNV | International | IUNV | 47595 | 35696.25 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
24 | Planning Specialist | Vacant | To be filled | 1 | IUNV | International | IUNV | 47595 | 35696.25 | 00124641 | 10159 | 30079 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
25 | Security Officer | Vacant | To be filled | 1 | SC | National | SB3 | 49880.1888 | 39488.4828 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
26 | Security Officer | Vacant | To be filled | 1 | SC | National | SB3 | 49880.1888 | 39488.4828 | 00124641 | 10480 | 30000 | 3.6 | Yes | 2023-12-31 | 2023-12-31 | 2023-12-31
[8 empty] | 3572495.765 | 2909100.0269
GMS
Total

## Sheet6
Sum of Amount (USD) |  | Donor Name
Account Code | Budget Description | EU | France | Japan | Norway | SIDA | USAID | Grand Total | Description
61300 | Salary & Post Adj Cst-IP Staff | 232904.0648 |  |  |  | 341121.7222 | 1522023.193 | 2096048.98 | staff salary | 2583056.3796
71200 | International Consultant |  |  |  | 56509.2833 |  | 40000 | 96509.2833 | consultant and operating costs
71400 | Contractual Services - Individ | [5 empty] | 314000 | 314000 | staff salary
| Salary & Post Adj Cst-IP Staff | [5 empty] | 173007.3996 | 173007.3996 | staff salary
72800 | Information Technology Equipment |  |  | 395282.2963 |  |  |  | 395282.2963 | IT Equipments
74000 | Miscellaneous Operating Expens |  | 19192.0222 |  |  |  |  | 19192.0222 | Monitoring and operating costs
74500 | Staff Mgmt Costs - IP Staff (Services to Projects) | 64000 |  |  |  | 64000 | 64000 | 192000 | DPC
75100 | Facilities & Administration | 23752.3252 | 1535.3618 | 31622.5837 | 4520.7427 | 32409.7378 | 169042.4474 | 262883.1985 | GMS
Grand Total |  | 320656.39 | 20727.384 | 426904.88 | 61030.026 | 437531.46 | 2282073.04 | 3548923.18

## AWP_2023 (4)
List activity results and associated actions | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE PARTY | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount (USD) | Notes
1.1.1: Support to electoral preparations through capacity-building programmes for staff that instill values and principles underpinning transparent elections. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 10000
1.1.2: Development and delivery of operations planning and management training for IHEC senior management. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 20000
1.1.3: Technical support on gender mainstreaming on election management, including developing and designing IHEC’s internal gender policy. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 50000
1.1.4: Gender mainstream training for IHEC operations staff in Baghdad and governorate offices. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 84000
1.1.5: UN support for electoral security planning through participation in the High Election Security Council meetings. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 70000
1.1.6: Procurement and installation of conferencing capacities to facilitate management of meetings and trainings in IHEC HQ and GEOs during COVID-19 emergency. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 40000
1.1.7: A lessons-learned workshop (facilitated by international experts) to identify challenges encountered along the electoral process and recommend solutions. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Contractual Services - Individ | 40000
1.1.8: Support to IHEC in Upgrading the Capacities of its Central Servers for Biometric Voter Registration |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
1.1.9: Establishing In-House Biometric Voter Card Printing Capacity |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
1.1.10: Package of Upgrade for IHEC GEO and HQ Network Capacities | X | X | X | X | UNAMI/ UNDP | 32045 | Japan | 141 | 72800 | Information Technology Equipment | 395282.2963
1.1.11: Support with E-Day COVID-19 Mitigation Measures for Polling Staff | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Materials & Supplies
Monitoring Costs | X | X | X | X | UNAMI/ UNDP
GMS (8%) | X | X | X | X | UNDP | 32045 | Japan | 141 | 75100 | Facilities & Administration | 31622.5837
GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 25120
1.2.1: Design of a comprehensive capacity development strategy and action plan and monitoring and evaluation activities to assess its effectiveness. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 10000
1.2.2: Design of an induction package and delivery of induction training for newly recruited GEO staff. Gender-responsive electoral processes will be integrated in the induction. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 40000
1.2.3: Training for master trainers at IHEC HQ and governorate level, including on gender perspectives. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 81000
1.2.4: Training on devolved results management, and specialized training in Information and Communication technology (ICT). | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference and Travel
1.2.5: Training on electoral operations and procedures. COVID-19 Trainings | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference and Travel
| X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/local consultants
1.2.6: Training on reporting and monitoring, using gender indicators on elections management. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference and Travel
1.2.7: Procurement and installation of conferencing facilities to supporting GEO remote training and meetings during COVID-19 emergency. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
Monitoring Costs
GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 10480 | Not correctly included in the final budget approved by donor
1.3.1: Review of existing IHEC regulations and instructions to align with international best practices. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/national Advisers
1.3.2: Advocacy and support and provision of technical advice in designing legislation and/or policy measures to promote the political participation and representation of women, youth and marginalized groups. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/national Advisers
1.3.3: Provision of technical advice and assistance on monitoring and enforcement of existing electoral legislation; provide support in awareness raising of special measures to increase political participation of women, youth, the displaced and other marginalized groups. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/national Advisers
Monitoring Costs
GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration
2.1.1: Support to the development of IHEC’s comprehensive communication and media strategy for elections. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
| X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
2.1.2: Provision of technical advice and support on IHEC’s website and social media strategy to disseminate information relevant to the electoral process. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
2.1.3: Provision of technical advice to create a systematic and effective internal communications system (including setting up a corporate IHEC emailing system and improve connectivity between HQ and GEOs). | X | X | X | X | UNAMI/ UNDP |  |  |  |  | International/ National Advisers
Monitoring Costs
GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration
2.2.1: Conduct an internal assessment of IHEC’s gender policies, to identify gaps in existing practices and identify opportunities for gender mainstreaming. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 89810
2.2.2: Provide guidance and support to development of an internal gender policy which defines IHEC´s operational objectives, responsibilities and targets on gender equality - on human resources, operations and staff capacity development. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 75000
2.2.3: Provision of training on gender responsive electoral processes. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 80000
2.2.4: Provision of guidance and support to the IHEC’s gender unit/focal point | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 70000
2.2.5: Provision of training and support for awareness-raising strategies to help IHEC promote youth and marginalized groups’ participation and representation in electoral processes. | X | X | X | X | UNAMI/ UNDP
Monitoring Costs | X | X | X | X | UNAMI
GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 25184.8
3.1.1 'Support to the voter registration process for more accurate voters´ lists | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.1.2 'Development of D-day procedures and training manuals, including production of innovative training tools | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.1.3 'Assisting in the formulation and implementation of cascade training plan | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.1.4 'Support for the preparation and management of a Results Management System (RMS) | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
| X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.1.5 'Training and ongoing support to IHEC staff on Results Management, seats allocation and Information and Communication Technology (ICT) | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs | X | X | X | X | UNAMI
GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
3.2.1 'Administer a small grants programme to support civil society groups in the implementation of countrywide voter education campaigns: The provision of small targeted grants will enable the involvement of youth groups in a voter participation campaign specifically targeting youth; groups representing people with disabilities, to reach out to disabled voters; and the dissemination of civic and voter education to IDPs and minority communities. | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.2.2 'Support for the production of voter education materials | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.2.3 'Support for a youth motivational campaign using social media | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs |  |  |  |  | UNAMI
GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
3.3.1 'Support for regular IHEC briefing of electoral stakeholders, such as political parties, media and civil society groups | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.3.2 'Support for the establishment of a well-equipped, fully functional IHEC Media Centre | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
| X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment
3.3.3 Support for the establishment of IHEC Governorate Results Announcement Centers (GEO RAC) complementary to National Results Announcement Center (NRAC) in Baghdad' | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment + Assessment
| X | X | X | X | UNAMI/ UNDP |  |  |  |  | Information Technology Equipment + Assessment
Monitoring Costs
GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
3.4.1 Training for female candidates | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.4.2 Support to IHEC in developing an electoral Code of Conduct (in collaboration with UNAMI´s Office of Political Affairs) | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.4.3 Delivery of specialized training to counter hate speech | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs
GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
3.5.1 'Review of IHEC complaints adjudication system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.5.2 Support to development of appeals regulation | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
3.5.3 'Specialised training on the complaints adjudication system and appeals system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
3.5.4'Public information campaign for electoral stakeholders and electorate |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs
3.5.1 'Review of IHEC complaints adjudication system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.5.2 Support to development of appeals regulation | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
3.5.3 'Specialised training on the complaints adjudication system and appeals system | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops and Confer
3.5.4'Public information campaign for electoral stakeholders and electorate |  |  |  |  | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs
GMS (8%) | X | X | X | X | UNDP |  |  |  | 75100 | Facilities & Administration | 0
3.6.1 'Recruitment of top quality, experienced project personnel. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 61300 | Salary & Post Adj Cst-IP Staff | 1076213.193
3.6.1 'Recruitment of top quality, experienced project personnel. | X | X | X | X | UNAMI/ UNDP | 30000 | SIDA | 00555 | 61300 | Salary & Post Adj Cst-IP Staff | 341121.7222
3.6.1 'Recruitment of top quality, experienced project personnel. | X | X | X | X | UNAMI/ UNDP | 30079 | EU | 10159 | 61300 | Salary & Post Adj Cst-IP Staff | 232904.0648
3.6.1 'Recruitment of top quality, experienced project personnel. | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71400 | Salary & Post Adj Cst-IP Staff | 173007.3996
3.6.2 'Oversight of, and close engagement with, the project by UNAMI senior leadership and OEA. | X | X | X | X | UNAMI/ UNDP | 30000 | Norway | 10503 | 71200 | International Consultant | 56509.2833
3.6.3 'Procurement of equipment, transport and communication means; COVID-19 protective equipment and preparedness; security for staff deployment. | X | X | X | X | UNAMI/ UNDP | 30000 | France | 112 | 74000 | Miscellaneous Operating Expens | 9192.0222
3.6.4 'A substantive project monitoring, evaluation and reporting mechanism is put in place. Conduct a Project Evaluation’ | X | X | X | X | UNAMI/ UNDP | 30000 | USAID | 10480 | 71200 | International Consultant | 40000
3.6.5 Full collaboration and co-operation with IHEC staff, its leadership | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
3.6.6: Programmatic contingency funding to be used only for programmatic activities | X | X | X | X | UNAMI/ UNDP |  |  |  |  | Training, Workshops & Conference + Travel
Monitoring Costs | X | X | X | X | UNAMI/ UNDP | 30000 | France | 112 | 74000 | Miscellaneous Operating Expens | 10000
GMS (8%) | X | X | X | X | UNDP | 30000 | Norway | 10503 | 75100 | Facilities & Administration | 4520.7427
GMS (8%) | X | X | X | X | UNDP | 30079 | EU | 10159 | 75100 | Facilities & Administration | 18632.3252
GMS (8%) | X | X | X | X | UNDP | 30000 | SIDA | 00555 | 75100 | Facilities & Administration | 27289.7378
GMS (8%) | X | X | X | X | UNDP | 30000 | France | 112 | 75100 | Facilities & Administration | 1535.3618
GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 103137.6474
DPC for Country Office Support Services | X | X | X | X | UNDP | 30079 | EU | 10159 | 74500 | Staff Mgmt Costs - IP Staff (Services to Projects) | 64000
DPC for Country Office Support Services | X | X | X | X | UNDP | 30000 | USAID | 10480 | 74500 | Staff Mgmt Costs - IP Staff (Services to Projects) | 64000
DPC for Country Office Support Services | X | X | X | X | UNDP | 30000 | SIDA | 00555 | 74500 | Staff Mgmt Costs - IP Staff (Services to Projects) | 64000
GMS (8%) | X | X | X | X | UNDP | 30079 | EU | 10159 | 75100 | Facilities & Administration | 5120
GMS (8%) | X | X | X | X | UNDP | 30000 | USAID | 10480 | 75100 | Facilities & Administration | 5120
GMS (8%) | X | X | X | X | UNDP | 30000 | SIDA | 00555 | 75100 | Facilities & Administration | 5120
Resident Representative/ Deputy Resident Representative: Name & Signature
Date:

## Procurement Plan
Procurement Plan 2023
Country Office |  | UNDP Iraq
Submitted By Project: |  | 2260-06-15
Year |  | 2023
Updated on: |  | 2023-01-20
Requesting Unit (Project Name) | ATLAS Project Number | ATLAS Output Number | Procurement Year | Type of Procurement Action (Civil Work, Goods, Services or ICs) | Procurement Category (Refer next Sheet) | Title of Procurement Action | Number of Units | Is this Request an Amendment? | Amendment value (USD) | Proposed date of Submission of Documents to Procurement | Planned Start Date | Estimated Contract Duration ( #of Days, Weeks, Months, Years) | Estimated Contract Value (USD) | Delivery Location | Comments | Expection completion date | Primary Focal Point | Alternate Focal Point | Status (Cancelled/ CO_PO Issued/Work Completed/Close PO)
Suport to Iraq Elections _ Capacity Development | 131655 | 124641 | 2023 | ICs | International Consultancy | External Evaluation Consultant | 1 | No | N/A | 2023-06-01 | 2023-09-01 | 40 days | 40000 | Baghdad |  | 2023-12-31 | Sammy Alfandika | Worknesh Katema
| Type |  | Procurement Category
| Civil Works |  | Contruction -Horizontal
| Goods |  | Construction- Vertical
| Individual Contracts |  | Rehabilization Infrastructure
| Services |  | Armored Vechiles
Computer Software
Contraceptives
Drugs and Pharmaceuticals
Election Items
Furniture and Fixtures
Generators
ICT Equipment
Medical and Laboratory Equipment/Supplies
Meteorological Equipment
Motor Vehicles and Parts
Pesticides/Herbicides
Phone/VHF/HF Equipment
Pre-Fabricated buildings
Printers and copiers
Renewable Energy Equipment
Rent/Lease of Copiers of ICT equipment
Safety and Security Equipment
Other Goods
International Consultants
National Consultants
Audit Services
Cleaning Services
Communication/Advocacy
Consultancy Services-Firms
NGO/CSO Engagement
Office/Warehouse Lease Agreements
Port/Custom Clearing Services
Printing/Publishing and Design
Rent/Lease of Vehicles
Security Services
Shipping and Warehousing
Software Development
Translation Services (companies)
Vehicle Maintenance
Workshop/Seminar Cost
Other services

## Programmatic Selection Plan
Programmatic Selection Processes for Responsible Parties & Low Value Grant Recipients
Country Office |  | UNDP Iraq
Submitted By Project: |  | Support to Iraq Electoral Process- Capacity Development
Year |  | 2020-2023
Updated on: |  | 2023-01-20
Requesting Unit (Project Name) | ATLAS Project Number | ATLAS Output Number | Selection Year | Type of Institution (NGO/ Government) | Type of Selection (Responsible Party or Grant Recipient) | Selection Process (Collaborative Advantage Analysis for RP / Call for Proposal for LVG Recipient) | Agreement Type (Responsible Party Agreement or Letter of Agreement or LVGA) | Type of Actvities/Deliverables | Proposed date of Submission of TOR to PMSU | Proposed date to start Selection Process | Contract Start Date | Estimated Agreement(s) Value (USD) | Comments | Primary Focal Point | Alternate Focal Point | HACT Applicability- YES or NO
Support to Iraq Electoral Process- Capacity Development | 131655 | 124641 | 2020 | Government (IHEC) | Responsible Party (UNDP/UNAMI) | Collaborative Advantage Analysis for RP | Responsible Party Agreement | Institutional capacity building activities | N/A | N/A | N/A | N/A |  | Sammy Alfandika | Worknesh Katema
| Type |  | Procurement Category
| Civil Works |  | Contruction -Horizontal
| Goods |  | Construction- Vertical
| Individual Contracts |  | Rehabilization Infrastructure
| Services |  | Armored Vechiles
Computer Software
Contraceptives
Drugs and Pharmaceuticals
Election Items
Furniture and Fixtures
Generators
ICT Equipment
Medical and Laboratory Equipment/Supplies
Meteorological Equipment
Motor Vehicles and Parts
Pesticides/Herbicides
Phone/VHF/HF Equipment
Pre-Fabricated buildings
Printers and copiers
Renewable Energy Equipment
Rent/Lease of Copiers of ICT equipment
Safety and Security Equipment
Other Goods
International Consultants
National Consultants
Audit Services
Cleaning Services
Communication/Advocacy
Consultancy Services-Firms
NGO/CSO Engagement
Office/Warehouse Lease Agreements
Port/Custom Clearing Services
Printing/Publishing and Design
Rent/Lease of Vehicles
Security Services
Shipping and Warehousing
Software Development
Translation Services (companies)
Vehicle Maintenance
Workshop/Seminar Cost
Other services

## Costed Monitoring Plan
Costed Annual Monitoring & Evaluation Plan 20xx
Project/Programme Title:
Project ID:
Output ID:
Monitoring Activity | Purpose | Frequency | Estimated Dates | Expected Action | Partners (if Joint) | Cost (USD) - Should Link to Allocations in the Work Plan
Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly on in the frequency required by each indicator | April, July, October and December | Slower than expected progress will be addressed by project management. | UNAMI/UNDP | 1000
Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | April, July, October and December | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | UNAMI/UNDP | 2000
Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At the end of the project | 2023-12-31 | Relevant lessons are captured by the project team and used to inform management decisions. | UNAMI/UNDP | 1000
Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | 2023-12-31 | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | UNAMI/UNDP | 1000
Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At six months | 2023-07-01 | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | UNAMI/UNDP | 2000
Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annual report and final progress report | Proposed Date for 2022 Report: March 2023 Proposed Date for 2023 Report: March 2024 |  | UNAMI/UNDP | 2000
Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Atleast annually | 2023-09-01 | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | UNAMI/UNDP/IHEC | 1000
Project (DIM) Audit | Audit Commissioned by the Office of Audit an investigation for Directly Implementatiom Modality in keeping with UNDP's Rules and Regulations. | Annually | 410412 |  | UNAMI/UNDP | 10000
Spot-Checks for Responsible Parties | Within the Harmonized Approach to Cash Transfer (HACT) framework, spot-checks conducted by a Third-Party Service Provider on Responsible Party Expenditure. Spot-checks to be completed in accordance with the Assurance Plan developed for each Responsible Party.
Audits for Responsible Parties | Within the Harmonized Approach to Cash Transfer (HACT) framework, annual audit of Responsible Party Expenditure.
Evaluation Title | Related Strategic Plan Output | UNDAF/CPD Outcome |  | Planned Start & Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding
Final Independent external evaluation | Output 2.2.2 Constitution-making, electoral and parliamentary processes and institutions strengthened to promote inclusion, transparency and accountability. | UNSDCF 2020-2024 OUTCOME INVOLVING UNDP 3.2 |  | September to December 2023 | UNAMI/UNDP/IHEC | 40000