HCFC phase-out management plan

TRANCHE REQUEST AND IMPLEMENTATION REPORT FORMAT

FOR THE 93rd MEETING OF THE EXECUTIVE COMMITTEE

PROJECT COVER SHEET

| Fill in the drop-down menus below, entering additional text only if required to specify. See section on project cover sheet on page 3 of the accompanying Guide for further information. |  |  |
| --- | --- | --- |
| # HPMP stage: | Stage II |  |
| Tranche(s) of implementation report: | # First tranche | # 209,900 UNDP |
| # Next tranche being requested | # Second tranche | # 293,513 UNDP |
| # Country: | # Sri Lanka |  |
| # Lead implementing agency (IA): | # UNDP | # Click or tap here to enter text. |
| # Cooperating implementing/bilateral agency (1): | # UNEP |  |
| # Cooperating agency (2): | # (select) | # Click or tap here to enter text. |
| # Cooperating agency (3): | # (select) | # Click or tap here to enter text. |
| # Cooperating agency (4): | # (select) | # Click or tap here to enter text. |
| # Meeting of current stage approval | # 86th |  |
| # Tranche implementation report |  |  |
| # Meeting where the tranche being reported on was approved | # 86th |  |
| # Implementation period of the tranche being reported on: (specify month and year: e.g., January 2020 to December 2023) | # January 2021 to December 2024 |  |
| # Are there relevant decisions/special reporting requirements related to the implementation of the tranche being reported on, or conditions for the consideration of the tranche requested? YES NO ☐ ☒ # If yes, please specify on the right. | # Click or tap here to enter text. |  |
| # Requested tranche |  |  |
| # Implementation period: (specify month and year: e.g., January 2024 to December 2026) | # July 2024 to December 2026 |  |
| # Funding requested: |  |  |
| # Agency | # Project funding requested (excluding support costs) (US $) |  |
| # UNDP | 293,513 |  |
| # UNEP | # 85.800 |  |
| # (select) |  |  |
| # (select) |  |  |
| # Total |  |  |
| # If there are any discrepancy between the amounts or the agencies approved in principal and the information provided above, please provide an explanation here. Click or tap here to enter text. |  |  |

* Note that details should be consistent with information provided in the relevant sections below.

CHECKLIST OF PREREQUISITES FOR SUBMISSION

| Select Yes or No below; entering additional text only if required to explain. See section on Checklist of prerequisites for submission on page 3-4 of the accompanying Guide for further information. |  |  |  |
| --- | --- | --- | --- |
| Components of the submission |  |  |  |
| Required for all projects | YES included | NO not included | If NO, please explain |
| - Official endorsement letter from Government specifying roles (lead/cooperating) of respective agencies (where more than one IA is involved) | ☒ | ☐ |  |
| - Progress and financial report from previous tranche (>20% disbursement from the previously approved tranche) | ☒ | ☐ |  |
| - Next tranche implementation plan | ☒ | ☐ |  |
| - Consideration of the Multilateral Fund gender policy and completed section 1.4.5 below using the guide for the HPMP tranche request and progress report format for guidance | ☒ | ☐ |  |
| - Completed section 1.4.6 on sustainability of the HCFC phase-out and assessment of risks using the guide for the HPMP tranche request and progress report format for guidance (decision 89/1(c)(iii)) | ☒ | ☐ |  |
| - Submission of CP data for the previous year eight weeks prior to the first meeting of the year and no later than 1 May | ☒ | ☐ | Submitted on 13.10.2023 |
| - Submission of A7 data for the previous year by 30 June, and no later than 30 September | ☒ | ☐ | Submitted on 13.10.2023 |
| - Comparison of CP and A7 data | ☒ | ☐ |  |
| - Completed all other applicable sections of this format | ☒ | ☐ |  |
| Required where applicable | YES included | N/A not applicable | Applicable but not included (please explain) |
| - Inventory of enterprises | ☐ | ☒ |  |
| - Verification report | ☐ | ☒ |  |
| - Revised Agreement (in a separate Word document) | ☐ | ☒ |  |
| - Submission of a project completion report for the previous stage where due | ☐ | ☒ |  |
| - Submission of a final report of completed end-user projects approved as part of decision 84/84 under this HPMP | ☐ | ☒ |  |

ADDITIONAL REQUESTS INCLUDED WITH SUBMISSION

Select Yes or No below; entering additional text only if an explanation is required. See section III of the Guide for further information.

| Additional request | YES included | NO not included | Comment |
| --- | --- | --- | --- |
| - Request for funding additional activities to maintain energy efficiency in line with decision 89/6 (for low-volume-consuming countries only) | ☒ | ☐ |  |
| - Request for activities related to environmentally sound management of used or unwanted controlled substances, including disposal (under decision 90/49(b) | ☐ | ☒ |  |

I.	PROGRESS REPORT ON THE FIRST TRANCHE IMPLEMENTATION

| I.1 Background |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Montreal Protocol compliance target to be met in stage II of the HPMP |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase-out commitment (%) |  | 100% |  |  | Year when target will be met |  |  |  |  |  | December 2030 |  |
| ☒ Servicing sector |  |  |  |  | ☐ Manufacturing sector |  |  |  |  |  |  |  |
| In the box below, provide a brief background (one to four paragraphs maximum) on the tranche of the HPMP being reported. See section I.1 of the Guide for guidance on what information to include. |  |  |  |  |  |  |  |  |  |  |  |  |
| HCFC Phase-out Management Plan of Sri Lanka for Stage II (HPMP of Sri Lanka-Stage II) for achieving targets from 2021 to 2030 was approved at the 86th Meeting of the Executive Committee held from 16 November – 3 December 2020, at a funding level of US $1,137,700, consisting of US $625,000 plus agency support costs of US $43,750 for UNDP, and US $415,000 plus agency support costs of US $53,950 for UNEP. To implement this, the Executive Committee entered into a Multi-year Performance Based Agreement spread over 10 years, 2021 to 2030, with the Government of Sri Lanka. With this funding level, the Government of Sri Lanka agreed to phase-out 9.38 ODP tons constituting (65% of the baseline) by the year 2025 and 13.9 ODP tons constituting (100%) by the end of 2030. The first tranche of stage II of the HPMP for Sri Lanka, and the corresponding tranche implementation plans, were approved in the amount of US $458,238, consisting of US $216,200 plus agency support costs of US $15,134 for UNDP, and US $200,800 plus agency support costs of US $26,104 for UNEP. However, as per decision of the extended meeting of the 86th Executive Committee meeting to apply a reduction in funding as per paragraph 11 and Appendix 7-A of the Agreement between the Government of Sri Lanka and the Executive Committee for stage I of the HPMP, calculated at US $2,500 for each metric tonne of HCFC consumption over the maximum allowable consumption limit, resulting in a penalty of US $11,463, consisting of US $6,270, plus agency support costs of US $470 for UNDP, and US $4,180, plus agency support costs of US $543 for UNEP, to the first tranche of stage II of the HPMP. Thus, the first tranche for UNDP is US$ 209,929 and for UNEP is US$ 196,620 |  |  |  |  |  |  |  |  |  |  |  |  |
| I.2 ODS policy/legislative/regulatory and institutional framework |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicate which regulatory/legislative measures in place by selecting Yes or No and where yes is indicated fill in the additional information requested in the space provided. See section I.2 of the Guide for further guidance. |  |  |  |  |  |  |  |  |  |  |  |  |
| HCFC-related legislation/regulations in place |  |  |  |  |  |  |  |  |  |  |  |  |
| Legislation/Regulation |  |  | Yes | No |  | Legislation/regulation number, year of adoption and other comments |  |  |  |  |  |  |  |
| HCFC licensing system (operational) |  |  | ☒ | ☐ |  | Click or tap here to enter text. |  |  |  |  |  |  |  |
| HCFC quota system (operational) |  |  | ☒ | ☐ |  | Click or tap here to enter text. |  |  |  |  |  |  |  |
| HCFC national import (and where relevant export and production) quotas issued for the year of tranche request and next year |  |  | ☒ | ☐ |  | 2023 Total HCFC quota: NOU to provide input |  |  |  |  |  |  |  |
| Technician certification program in place |  |  | ☒ | ☐ |  | If YES, please clarify whether the certification programme is competency-based and/or mandatory NOU to provide input |  |  |  |  |  |  |  |
| HFC licensing system |  |  | ☒ | ☐ |  | If NO, please explain Click or tap here to enter text. |  |  |  |  |  |  |  |
| HFC quota system |  |  | ☐ | ☒ |  | If NO, please explain Planned to be implemented w.e.f. Jan 2024 |  |  |  |  |  |  |  |
| In the box below provide a brief description (one to five paragraphs) of any relevant institutional changes and new or revised legislation/regulations related to HCFCs introduced since the previous tranche or stage report was submitted. (See section I.2 of the Guide for further guidance.) |  |  |  |  |  |  |  |  |  |  |  |  |
| No (NOU Please confirm) |  |  |  |  |  |  |  |  |  |  |  |  |
| I.3 HCFC consumption |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicate when the most recent country programme and Article 7 (A7) data have been submitted and provide the expected date of submission in the comments box as necessary; if there are discrepancies between the two reports provide a brief explanation (one paragraph) in the space provided. Provide A7 consumption data (in metric tonnes (mt) and ODP tonnes) from the last five years for each substance consumed in the country, deleting unnecessary rows and provide a short (one to two paragraphs) explanation of the recent consumption trends. For countries exporting HCFC-141b contained in pre-blended polyols fill in the additional row for it and see section I.3 of the Guide for further guidance on filling in this part of the format. |  |  |  |  |  |  |  |  |  |  |  |  |
| Submission of latest ODS data Reports |  |  |  |  |  |  |  |  |  |  |  |  |
| Report |  |  | Submission of data for the previous year |  |  |  |  | Most recent year submitted |  | Comments |  |  |
|  |  |  | Yes |  |  |  | No |  |  |  |  |  |
| Country programme |  |  | ☒ |  |  |  | ☐ | 2022 |  | Submitted on 13.10.2023 |  |  |
| Article 7 data |  |  | ☒ |  |  |  | ☐ | 2022 |  | Submitted on 13.10.2023 |  |  |
| Explain any data discrepancies: Click or tap here to enter text. |  |  |  |  |  |  |  |  |  |  |  |  |
| Overview of current HCFC consumption: NOTE: Rows with substances which are not applicable can be deleted. See section I.3 of the Guide for further guidance on filling in this part of the format. |  |  |  |  |  |  |  |  |  |  |  |  |
| Metric tonnes (mt) by substance (last five years) |  |  |  |  |  |  |  |  |  |  |  |  |
| Substance | 2018 |  | 2019 |  |  |  |  | 2020 |  | 2021 |  | 2022 |
| HCFC-22 | 187.47 |  | 180.18 |  |  |  |  | 155.82 |  | 155.98 |  | 139.14 |
| HCFC-123 | 0.00 |  | 0.00 |  |  |  |  | 0.00 |  | 0.00 |  | 0.00 |
| HCFC -141b | 0.00 |  | 0.00 |  |  |  |  | 0.00 |  | 0.00 |  | 0.00 |
| Total | 187.47 |  | 180.18 |  |  |  |  | 155.82 |  | 155.98 |  | 139.14 |
| ODP tonnes by substance (last five years) |  |  |  |  |  |  |  |  |  |  |  |  |
| Substance | 2018 |  | 2019 |  |  |  |  | 2020 | 2021 |  |  | 2022 |
| HCFC-22 | 10.31 |  | 9.91 |  |  |  |  | 8.57 | 8.58 |  |  | 7.65 |
| HCFC-123 | 0.00 |  | 0.00 |  |  |  |  | 0.00 | 0.00 |  |  | 0.00 |
| HCFC -141b | 0.00 |  | 0.00 |  |  |  |  | 0.00 | 0.00 |  |  | 0.00 |
| Total | 10.31 |  | 9.91 |  |  |  |  | 8.57 | 8.58 |  |  | 7.65 |
| Based on the consumption data given above: Provide a description of the sector(s) and sub-sector(s) that use HCFCs in the country, including a short analysis and explanation of the consumption trends (i.e., increasing or decreasing). In addition, describe the use of HCFC-alternatives in the sectors and sub-sectors indicated. |  |  |  |  |  |  |  |  |  |  |  |  |
| The HCFC consumption is only for servicing of RAC equipment. The main sub sectors using HCFC includes residential air conditioning and commercial air conditionings. The consumption in refrigeration sub sector is almost nil. In case of residential air conditioning, demand of HCFC 22 based AC is decreasing due to efforts made during stage I. Thus, R22 which was preferred choice of users till 2017, is now replaced with alternative technologies like R 410A. R-32 has entered the market in early 2016. However, it was not a preferred choice of the customers due to the higher unit cost despite environment friendly and energy saving benefits . Under commercial air conditioning, chillers & water cooled or air-cooled packaged type large air-conditioners operating on HCFC-22 had been imported prior to 2017. However, trend in importing VRF system operating on R-410A system has been increased. The commercial refrigerators such as display cabinets, serve-over cabinets and standalone freezer operating with HCFC-22 are found in some supermarkets, groceries, and food outlets. However, with penetration of R-404A, R-134a and R-600a technologies, numbers of HCFC based equipment is very minimal. The HCFC-22 based industrial refrigeration systems in food industry and ice plants were gradually replaced with Ammonia driven systems. |  |  |  |  |  |  |  |  |  |  |  |  |
| For countries exporting HCFC-141b contained in pre-blended polyols, insert a table below showing the amounts of HCFC-141b exported in pre-blended polyols and their destination countries and indicate whether an export ban will be issued. |  |  |  |  |  |  |  |  |  |  |  |  |
| Not applicable |  |  |  |  |  |  |  |  |  |  |  |  |

[Insert table as needed]

I.4 HCFC phase-out activities

Fill out section I.4.1 for servicing sector activities by providing a brief overview of activities and filling in the tables indicated below. Information should be focused on the activities and outcomes during the implementation of the tranche being reported on and should be clearly tied to the agreed activities when the tranche was approved. For those countries with investment projects fill out the details in section I.4.2 by providing a brief overview of activities and filling out the tables provided. Note that the tables in this format should be used and rows may be deleted or added; additional tables can be inserted only if necessary. Further guidance on completing these parts of the format can be found in sections I.4.1 and I.4.2 of the accompanying Guide.

Delayed tranche request: If this tranche request is being submitted late provide explanation of the reasons and actions taken for the delayed submission below.

The tranche was due to the 93rd ExCom. However due to slow disbursement rate of first tranche, it is being submitted to the 94th ExCom. The main reason for the delay is due to the Economic crisis that badly affected the country in 2022. The COVID impact in 2020 and 2021, followed by this economic crisis in 2022, slowed down the activities in the sector. For e.g. there was ban on import of certain items hence procurement could not be completed. Hence tranche was deferred for submission to next excom

I.4.1 Servicing sector activities

Narrative summary: In the section below provide a brief narrative (one to two pages maximum) of continued or new activities implemented during the tranche for the servicing sector. See section I.4.1 of the accompanying Guide for further guidance.

1. Policy, regulations and enforcement 1.1 Policy review and amendments of the existing regulations (UNDP) Two meetings were held with stakeholders (including importers) during tranche 1 to discuss license and quota system. Meetings were held with customs and I&E for review of existing license and quota system. Some amendments are being discussed to strengthen the license & quota system for better coordination. The NOU established a system for checking online approvals with I&E. Also NOU was given access to the ACYCUDA system of customs. (NOU to elaborate) 1.2 Training for customs and enforcement officers (UNEP to add) 1.3 Strengthening customs operations to control import/export (UNEP to add) 2. Capacity building of RAC sector 2.1 Procurement of training equipment for training centers (UNDP to add) Procurement of training tools and equipment for eight Technical and Vocational Training Institutes under Tertiary Vocational Education and Training Authority(TVETA) is under final stage. By procuring and supplying these tools and equipment to training centers will enhance the facilities in conducting trainings programmes for Master trainers as well as technicians on new generation refrigerants and technologies. The following 8 training centres have been selected with the recommendations of Technical Evaluation Committee appointed jointly by the NOU and TVETA. 1. National Vocational Training Institute – Mirijjawila 2. National Vocational Training Institute – Batticaloa 3. National Vocational Training Institute – Rathmalana 4. District Vocational Training Center – Ballapana, Kegalle 5. District Vocational Training Center – Anuradhapura 6. District Vocational Training Center – Veyangoda 7. National Youth Services Council – Elpitiya 8. Lalith Athulathmudali Vocational Training Institute – Rathmalana 2.2 Training of technician on good servicing practices and handling of flammable refrigerants (UNEP to add) 2.3 Integration of code of good practices into TVET system and certification of technicians (UNEP to add) 2.4 Strengthening of existing reclamation centres by providing technical assistance (UNDP) Establishment of nine Refrigerant Reclaim Centres to reduce usage of virgin HCFCs was completed in 2018. The centres indicated that refrigerants had been collected and processed refrigerant recovered and reclaimed. Training, awareness and monitoring for recovery/reclamation programme were continued during Tranche 1 of HPMP Stage II. Meetings/workshops were held to create awareness and encourage RAC workshops/ technicians to recover HCFC and reclaim the same using the nine facilities established. (NOU to add detail) 2.5 Technical assistance for feasibility study on use of HCFC chillers (UNDP) Feasibility study on HCFC chillers in Sri Lanka is being carried out by Sri Lanka Sustainable Energy Authority in collaboration with the Ministry of Environment and the Industrial Services Bureau (ISB) in close coordination with the NOU. Initial Data collection has been completed and inception report and Pilot Study Report have are being reviewed by Sri Lanka Sustainable Energy Authority. (to be elaborated by nou) 2.6 Revive RAC Association to support HPMP implementation (UNEP) 3. Public awareness and Outreach (UNEP) 4. Project Implementation, coordination and Monitoring (UNDP) A project team was set up under the NOU consisting of one Project Associate and one Technical Consultant. The team provides support to the NOU for coordination and implementation of project activities as per target. One PSC meeting was held on 27th June 2023.

Quantitative summary: For training and equipment components (as applicable): Please list in the table below the specific targets (as relevant) achieved during the implementation of the tranche being reported on (rows can be added or deleted as necessary). See section I.4.1 of the accompanying Guide for further guidance.

| Activity | Total (tranche) | Cumulative total (stage) | Target (stage) | Male (tranche) | Female (tranche) | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Number of customs officers trained |  |  |  |  |  |  |
| Number of brokers/importers trained |  |  |  |  |  |  |
| Number of other stakeholders trained (specify which stakeholders in comments box) |  |  |  |  |  |  |
| Number of technicians certified |  |  |  |  |  |  |
| Number of technicians trained on good servicing practices for refrigeration and air-conditioning equipment |  |  |  |  |  |  |
| Number of trainers trained on good servicing practices for refrigeration and air-conditioning equipment |  |  |  |  |  |  |
| Number of technicians trained on other specialized subjects (specify which topic(s) in comments box) |  |  |  |  |  |  |
| Number of trainers trained on other specialized subjects (specify which topics in comments box) |  |  |  |  |  |  |
| Number of tool kits and equipment distributed to refrigeration and air-conditioning technicians | 0 | Na | Na | Na | Na |  |
| Number of recycling reuse and reclamation centres equipped and/or renovated | 0 | Na | Na | Na | Na |  |
| Number of national technical institutions equipped and/or renovated | 8 | 8 | 8 | Na | na |  |
| Number of other stakeholder/ organizations that received tools/equipment (specify stakeholder/organization in comment box) | 0 | Na | Na | Na | na |  |

List any other quantifiable results achieved under the tranche and cumulatively under the stage below. For activities related to end-user-related projects implemented as part of decision 84/84, provide a summary of the project(s) as approved (including funding and targets), activities implemented during the tranche, challenges encountered, and any adjustments that have been made to the approved activities.

Not applicable

Fund disbursement and progress on activity implementation (see section I.4.1 of the accompanying Guide for instructions to fill out the table below).

| Agency (1) | Project component (2) | Activities and targets planned for the tranche (3) | Activities and targets completed for the tranche (4) | Activities remaining to be implemented during the next tranche (5) | Funding originally planned (US$) (6) | Funds disbursed (US$) (7) | Balance of funds to be disbursed (US$)* (8) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP | Policy, regulations and enforcement | Annual meeting with stakeholders, workshop for policy makers and online license and quota system | Two meeting were held with stakeholders, one meeting with policy makers and system established for Nou to coordinate online with I&E. NOU can also access ACYCUDA system. | Full implementation of online system | 11,200 | 7,189.62 | 4,010.38 |
| UNDP | Capacity building of RAC servicing sector | *Procurement of training equipment for training institutions *Technical assistance for reclaim centers *Feasibility study for chillers | *Equipment/tools procurement finalised for eight training centers *Technical assistance provided to reclaim centers and activities conducted to promote reclamation * Feasibility study for chillers initiated | *Delivery of tools/equipment and handing over to the training centres *Workshops to promote reclamation will continue *Final report to be received | 157,064 | 132,897.40 | 24,166.64 |
| UNDP | Project management, coordination and monitoring | Setting up of project team and support to project implementation | Project team was set up and coordination and monitoring activities initiated | Project coordination and monitoring will continue during entire life cycle of the project | 41,636 | 20,424.29 | 21,211.71 |

*Includes funds committed

Remarks or additional comments: These may be included here as necessary, including challenges in implementation, please specify if any.

Click or tap here to enter text.

I.4.2 Progress on implementation of investment projects

Narrative summary: In the section below provide a brief narrative (one page maximum) of the investment project components implemented during the tranche. See section I.4.2 of the accompanying Guide for further guidance.

Not applicable

For tranches with investment components please fill out the table below. See section I.4.2 of the accompanying Guide for further guidance.

Fund disbursement and progress on project milestones (add or delete rows as needed)

| Overall funds approved | HCFC substance to be phased-out | Alternative to be phased in | Total HCFC to be phased out (mt) | Overall funds approved in stage (US $) | Funds allocated for this tranche (US $) | Funds disbursed in this tranche (US $) | Balance of funds to be disbursed (US$) * | Project milestone reached for each enterprise | Expected date of project completion (mm/yy) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To enter subsector name, click here |  |  |  |  |  |  |  |  |  |
| To enter enterprise name, click here. | (select) |  |  |  |  |  |  | Select milestone |  |
| To enter enterprise name, click here. | (select) |  |  |  |  |  |  | Select milestone |  |
| To enter enterprise name, click here | (select) |  |  |  |  |  |  | Select milestone |  |
| To enter enterprise name, click here | (select) |  |  |  |  |  |  | Select milestone |  |
| To enter enterprise name, click here. | (select) |  |  |  |  |  |  | Select milestone |  |
| Sub-total | n/a |  |  |  |  |  |  | n/a |  |
| To enter subsector name click here. |  |  |  |  |  |  |  |  |  |
| To enter enterprise name, click here. | (select) |  |  |  |  |  |  | Select milestone |  |
| To enter enterprise name, click here | (select) |  |  |  |  |  |  | Select milestone |  |
| To enter enterprise name, click here | (select) |  |  |  |  |  |  | Select milestone |  |
| Sub-total | n/a |  |  |  |  |  |  | n/a |  |
| Total | n/a |  |  |  |  |  |  | n/a |  |

*Includes funds committed

Remarks or additional comments: Include here as necessary remarks or additional information on contingencies encountered, reasons for delays, where applicable, pictures, changes to the original plan (e.g., enterprises found ineligible or that will not participate, new eligible enterprises identified, needed changes to the originally approved technology).

Click or tap here to enter text.

| I.4.3 Other impacts on the environment including on the climate |  |  |
| --- | --- | --- |
| In the box below describe (up to one page) the activities initiated to reduce potential impact to the environment with emphasis on the climate impact associated with the phase-out of HCFCs (i.e., use of low-GWP substances, energy efficiency, etc.). See section I.4.3 of the accompanying Guide for further guidance. |  |  |
| The activities proposed in HPMP for the servicing sector, which include better containment of refrigerants through policy measures, training, provision of equipment/tools, recovery, reclaim and reuse programme, ban on import of HCFC based equipment is gradually reducing the amount of HCFC-22 used for RAC servicing sector. Each Kg of HCFC-22 reduced, is resulting in avoiding emission of approx. 1.8 tons of CO2 equivalent. Thus, through the implementation of Stage I of HPMP for Sri Lanka, a total of 4.76 ODP tones of HCFCs was phased out, resulting to net direct emission reductions of 124,691 CO2 equivalent tons. HPMP Stage II aims to complete phase-out of remaining 9.14 ODP tons ( which is equal to 300,789 CO2 equivalent tons. Efforts to promote low-GWP will reduce global warming through the emission of refrigerants into the atmosphere, resulting in climate benefits |  |  |
| I.4.4 Consideration of the Multilateral Fund gender policy in HPMP implementation |  |  |
| In the box below describe (up to one page) the activities initiated to implement the gender policy of the Multilateral Fund into activities of the HPMP. See section I.4.4 of the accompanying Guide for further guidance. |  |  |
| Click or tap here to enter text. |  |  |
| 1.4.5 Sustainability of the HCFC phase-out and assessment of risks |  |  |
| Include information on how the long-term sustainability of the HCFC phase-out and the activities will be assured and a discussion on identified risks to project implementation or sustainability and how they will be mitigated. See section I.4.5 of the accompanying Guide for further guidance. |  |  |
| Qualitative discussion of the risks to the successful implementation of the project and its sustainability, includes possible challenges in the market uptake of new technologies, assessment of the implementation timeline, readiness of the sector to convert to new technologies, and other challenges. The risks were discussed and addressed during the implementation of HPMP right from stage I. With various policy measures like establishment of licence and quota system, ban on import of HCFC based equipment, ban on import of 141 b etc the reduction in HCFC consumption was ensured. Also, various activities were implemented to create enabling environment in the market for penetration of non ODS technologies. This includes replacement programme for end users, training of master trainers and technicians, awareness programme and more. In addition to reduce the consumption of HCFC, nine reclamation centres were established in the country. However, there was delay in implementation due to unavoidable situation like covid (2020,2021) and economic crisis in the country (2022). The PSC will monitor and review the progress and risks related to sustainability annually and mitigation plan will be developed and implemented. |  |  |
| I.4.6 Co-financing U(where applicable) |  |  |
| If applicable describe financial incentives and opportunities for co-financing that were identified and implemented during the tranche under review. See section I.4.6 of the accompanying Guide for further guidance. |  |  |
| Not applicable |  |  |
| I.4.7 Project management and monitoring |  |  |
| Brief description (one to four paragraphs) of roles and responsibilities of key stakeholders in the implementation of the tranche (government departments, the National Ozone Unit, project management unit (PMU), and non-governmental organizations, other). |  |  |
| *The National Ozone Unit (NOU) of Sri Lanka is responsible for the planning, implementation and monitoring of all the approved activities under HPMP Stage II. *The project management and monitoring component is to support NOU in successful implementation of HPMP II, through a project management unit. other key stakeholders role is as below: * Department of Import and Export Control (DIEC) as the regulatory body issuing import licenses on the recommendations of NOU and monitoring the importation process through coordination with Sri Lanka Customs (SLC) when required to ensure the imports are legitimate *Sri Lanka Customs (SLC) as the agency physically monitoring the importation for right substance from the right source in right quantities and right channel linking with respective agencies to confirm the legitimacy of the imports *Importers as the approved agencies to import HCFC products *Consumer Protection Authority as the government entity enforcing laws in protecting consumers from abused trading practices by traders |  |  |
| Breakdown of project monitoring activities and disbursements |  |  |
| Responsible entity select |  |  |
| Activity (add/delete rows as needed) | Amount allocated for tranche (US $) | Amount disbursedot (US $) |
| Staff/consultants | 31,953 | 15,022.85 |
| Travel, communication etc | 6,600 | 939.99 |
| Total | 38,553 | 15,962.84 |
| I.4.8 Other information |  |  |
| Provide a short summary (half a page maximum) comparing the overall progress of the tranche implementation with the information provided in the remark’s column of the most recent Annual Progress and Financial Report and explain the difference. |  |  |
| UNDP UNEP |  |  |
| I.5 Financial report |  |  |
| In the two tables below please fill in disbursement amounts for each agency, add or delete column/row as necessary depending on number of implementing agencies and number of tranches. See section I.5 of the accompanying Guide for further guidance. |  |  |

Table 1. Disbursement by agency and by tranche

| Tranche | Agency | UNDP | UNEP | (select cooperating agency) | Total | Disbursement rate |
| --- | --- | --- | --- | --- | --- | --- |
|  | Amount | (US $) | (US $) | (US $) | (US $) | (%) |
| First | Approved | 209,900 | 200,800 | -- | 417,000 |  |
|  | Disbursed | 160,511.31 |  |  |  |  |
| Second | Approved |  |  |  |  |  |
|  | Disbursed |  |  |  |  |  |
| Third | Approved |  |  |  |  |  |
|  | Disbursed |  |  |  |  |  |
| Fourth | Approved |  |  |  |  |  |
|  | Disbursed |  |  |  |  |  |
| Total | Approved | 209900 |  |  |  |  |
|  | Disbursed | 160511.31 |  |  |  |  |
|  | Balance | 49,388.69 |  |  |  |  |

Table 2. Disbursement by agency and component in current tranche

| Agency | Component | Total for stage (US $) | Total for tranche (US $) | Disbursed for tranche (US $) | Committed* (US $) | Balance (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| *Please clarify and include relevant information on any funding that has been committed but not yet disbursed. |  |  |  |  |  |  |
| Click or tap here to enter text. |  |  |  |  |  |  |

II.	Verification report

| If a verification report was required, include it in a separate file attachment following the guidelines for verification reports contained in Annex II to the accompanying Guide and specify the years covered below. |  |
| --- | --- |
| From select year | To select year |

III.	Requested tranche implementation plan

Tranche implementation plan narrative summary: In the section below provide a detailed narrative (one to three page maximum) of the activities and targets in the implementation plan for the requested tranche. See section III of the accompanying Guide for further guidance.

1. Policy, regulations and enforcement 1.1 Policy review and amendments of the existing regulations (UNDP) Strengthening the application of the licensing and quota system for HCFCs and products and equipment based on those controlled substances. Developing, adopting, or revising standards, codes and norms that could facilitate the adoption, operation and servicing of refrigeration technologies based on low-GWP refrigerants, including a national code of practice for hydrocarbon (HC), ammonia (NH3) and carbon dioxide (CO2) use. 1.2 Training for customs and enforcement officers (UNEP) 1.3 Strengthening customs operations to control import/export (UNDP) To strengthen the Customs operation in identifying refrigerants, Sri Lanka Customs will be provided five (5) new refrigerant identifiers would be needed in next 8 years to fulfil the requirement. 2. Capacity building of RAC sector (UNEP)s 2.1 Training of technician on good servicing practices and handling of flammable refrigerants (UNEP) 2.2 Strengthening of existing reclamation centres by providing technical assistance (UNDP) Under the second tranche of HPMP, the NOU will continue working closely with UNDP to further promote refrigerant recovery and reclamation by providing additional training to the operators of existing R&R centres; monitoring centre operations; and assessing the data reporting issues in relation to reclaimed quantities. 2.3 Technical assistance for feasibility study on use of HCFC chillers (UNDP) The ongoing work of development of feasibility study will be finalised. A workshop will be organised with relevant stakeholders to discuss the findings and way forward. 3. Public awareness and Outreach (UNEP) 4. Project Implementation, coordination and Monitoring (UNDP) Project team will continue to support the project implementation.

New investment component for implementation: If an investment component was approved in principle to commence in the requested tranche, details of that component should be provided in the space below or insert table(s) below. See section III of the accompanying Guide for further guidance.

Not applicable

[Insert table(s) as needed]

Tranche implementation plan activities, targets and funding

| Agency (1) | Project/component (2) | Specific activities (3) | Targets and outcomes (4) | Funds requested for the next tranche (US $) (5) | Balance of funds remaining to be disbursed from previous tranche (US $)* (6) | Total budget for the planned implementation period (US $) (7) |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | Policy, regulations and enforcement | Policy review and amendment of regulations |  | 5,200 |  |  |
| UNEP | Policy, regulations and enforcement | Training of custom and enforcement officers |  | 7,000 |  |  |
| UNDP | Policy, regulations and enforcement | Strengthening customs operation to control import/export |  | 25,000 |  |  |
| UNEP | Capacity building of RAC servicing sector | Training of RAC technician on good practice and handling of flammable refrigerant |  | 38,800 |  |  |
| UNDP | Capacity building of RAC servicing sector | Procurement of tools for Servicing workshops |  | 215,000 |  |  |
| UNDP | Capacity building of RAC servicing sector | Technical assistance for Chillers |  | 2,000 |  |  |
| UNEP | Capacity building of RAC servicing sector | Integration of code of good practices into TVET system and certification of RAC technician |  | 15,000 |  |  |
| UNEP | Public awareness and outreach |  |  | 25,000 |  |  |
| UNDP | Project Management, coordination and monitoring |  |  | 46,000 |  |  |
|  |  |  | Totals | 379,000 |  |  |

*Amount from column (8) of the table on Fund disbursement and progress on activity implementation in section I.4.1 above

Remarks or additional comments: Include as necessary and if there are any changes to the projects approved in principle.

Click or tap here to enter text.

For LVC countries requesting additional funding for activities to introduce alternatives to HCFCs with low or zero GWP and for maintaining energy efficiency in the refrigeration servicing sector (decision 89/6) complete the following:

Justification for activity requested:

Funding requested (US $):

Project description:

Project activities and budget, including performance indicators per activity (fill in here or insert table below).

[Insert table as needed]

For countries requesting funding for activities related to environmentally sound management of used or unwanted controlled substances, including disposal (decision 90/49(b)), complete the following:

Justification for activity requested:

Funding requested (US $):

Project description:

Project activities and budget, including performance indicators per activity (fill in here or insert table below).

[Insert table as needed]