## AOP
PIMS No: | 6653
Award ID: | 00126368.1
Award Title: | GOLD+ ECUADOR
Project ID: | 00126368
Project Title: | GOLD+ ECUADOR
Executing Agency: | UNDP-ECU
POA ORIGINAL PRODOC
GCF Outcome/Atlas Activity | Fund ID | Donor Name | Implementing agent | Atlas Budgetary Account Code | ATLAS Budget Description | Amount (USD) Year 2024 | Amount (USD) Year 2025 | Amount (USD) Year 2026 | Amount (USD) Year 2027 | Amount (USD) Year 2028 | Total PRODOC (USD) | Ejecución Previa | Disbursement till December 2023 (cummulative years until last official CDR) | % Delivery per item | A Approved budget revision 2024 | B Proposed budget revision (2024) | C Difference (B-A) | Amount (USD) Year 2025 | Amount (USD) Year 2026 | Amount (USD) Year 2027 | Amount (USD) Year 2028 | Total (USD) expenditure by end of project | Deviation from budget approved in Prodoc (Total ProDoc-Total Expenditure by end of project) | Budget revision explanation for changes +/- 5,000 USD | Budget Note
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 20000 | 20000 | 20000 | 20000 | 20000 | 100000 | 0 | 0 | 0% | 20000 | 0 | -20000 | 40000 | 20000 | 20000 | 20000 | 100000 | 0 | 1 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 20000 | 40000 | 40000 | 40000 | 40000 | 180000 |  |  | 0% | 20000 | 0 | -20000 | 60000 | 40000 | 40000 | 40000 | 180000 | 0 | 2 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 53580 | 53580 | 53580 | 53580 | 53580 | 267900 |  |  | 0% | 53580 | 22509.94 | -31070.06 | 55978.84 | 47653.88 | 49068.55 | 92688.79 | 267900 | 0 | 3 | El presupuesto total se mantiene, se redistribuye el monto entre los años 2024 y 2028
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 15000 | 15000 | 17000 | 19500 | 20000 | 86500 |  |  | 0% | 15000 | 26748.8 | 11748.8 | 9400 | 16451.2 | 13900 | 20000 | 86500 | 0 | 4 | Se utilizará mayor presupuesto del establecido inicialmente en el PRODOC para el 2024 ya que es necesario realizar viajes a Nambija, Zamora y la Maná para levantar información de manera conjunta con los técnicos del IIEGE/MAATE que posteriormente servirá de insumos para el plantamiento de consultorías
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 72100 | Servicios contractuales - Empresas | 10000 | 42980 | 50000 | 50000 | 50000 | 202980 |  |  | 0% | 10000 | 0 | -10000 | 52980 | 50000 | 50000 | 50000 | 202980 | 0 | 5 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 5000 | 10000 | 10000 | 10000 | 10000 | 45000 |  |  | 0% | 5000 | 0 | -5000 | 15000 | 10000 | 10000 | 10000 | 45000 | 0 | 6 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 10000 | 15000 | 15000 | 15000 | 15000 | 70000 |  |  | 0% | 10000 | 12809.75 | 2809.75 | 18241.45 | 8948.8 | 15000 | 15000 | 70000 | 0 | 7 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
TOTAL COMPONENTE 1 | [5 empty] | 133580 | 196560 | 205580 | 208080 | 208580 | 952380 | 0 | 0 | 0 | 133580 | 62068.49 | -71511.51 | 251600.29 | 193053.88 | 197968.55 | 247688.79 | 952380 | 0
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 5450 | 10000 | 10000 | 10000 | 10000 | 45450 |  |  | 0% | 5450 | 0 | -5450 | 15450 | 10000 | 10000 | 10000 | 45450 | 0 | 8 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 15000 | 15000 | 15000 | 15000 | 18250 | 78250 |  |  | 0% | 15000 | 5404 | -9596 | 24596 | 15000 | 15000 | 18250 | 78250 | 0 | 9 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 49360 | 49360 | 49360 | 49360 | 49360 | 246800 |  |  | 0% | 49360 | 10208.11 | -39151.89 | 51640.98 | 52481.88 | 53385.54 | 79083.49 | 246800 | 0 | 10 | El presupuesto total se mantiene, se redistribuye el monto entre los años 2024 y 2028
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 15000 | 20000 | 20000 | 20000 | 20000 | 95000 |  |  | 0% | 15000 | 0 | -15000 | 35000 | 20000 | 20000 | 20000 | 95000 | 0 | 11 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 72100 | Servicios contractuales - Empresas | 0 | 103500 | 135000 | 165000 | 115000 | 518500 |  |  | 0% | 0 | 0 | 0 | 103500 | 135000 | 165000 | 115000 | 518500 | 0
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 7500 | 7500 | 7500 | 7500 | 7500 | 37500 |  |  | 0% | 7500 | 0 | -7500 | 15000 | 7500 | 7500 | 7500 | 37500 | 0 | 12 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 8000 | 8000 | 8000 | 10000 | 11170 | 45170 |  |  | 0% | 8000 | 0 | -8000 | 16000 | 8000 | 10000 | 11170 | 45170 | 0 | 13 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
TOTAL COMPONENTE 2 | [5 empty] | 100310 | 213360 | 244860 | 276860 | 231280 | 1066670 | 0 | 0 | 0% | 100310 | 15612.11 | -84697.89 | 261186.98 | 247981.88 | 280885.54 | 261003.49 | 1066670 | 0
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 15000 | 15000 | 15000 | 15000 | 15000 | 75000 |  |  | 0% | 15000 | 0 | -15000 | 30000 | 15000 | 15000 | 15000 | 75000 | 0 | 14 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 0 | 0 | 5000 | 5000 | 5000 | 15000 |  |  | 0% | 0 | 8608.4952 | 8608.4952 | 0 | 5000 | 260.1 | 1131.4 | 14999.9952 | 0.0047826 | 15 | Se redistribuyó el presupuesto de los años 2025 al 2028 para asignar el monto necesario en el 2024 para la contratación de un consultor individual MAPE mientras se culmina la contratación del especialista
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 49360 | 49360 | 49360 | 49360 | 49360 | 246800 | 0 |  | 0% | 49360 | 14372.73 | -34987.27 | 46698.05 | 48024.11 | 49450.95 | 88254.16 | 246800 | 0 | 16 | El presupuesto total se mantiene, se redistribuye el monto entre los años 2024 y 2028
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 0 |  | 0% | 10000 | 11200 | 1200 | 8800 | 10000 | 10000 | 10000 | 50000 | 0 | 17 | Se redistribuyó el presupuesto de los años 2025 al 2028 para asignar un monto mayor al 2024 dado que se requiere realizar viajes a Nambija, Zamora y la Maná para levantar información de manera conjunta con los técnicos del IIEGE/MAATE que servirá de insumo para el planteamiento de consultorías
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 72100 | Servicios contractuales - Empresas | 10000 | 65000 | 90500 | 92000 | 56500 | 314000 | 0 |  | 0% | 10000 | 0 | -10000 | 75000 | 90500 | 92000 | 56500 | 314000 | 0 | 18 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 72200 | Equipo y Mobiliario | 0 | 0 | 200000 | 222722 | 200000 | 622722 | 0 |  | 0% | 0 | 0 | 0 | 0 | 200000 | 222722 | 200000 | 622722 | 0
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 6000 | 7500 | 7500 | 7500 | 7500 | 36000 | 0 |  | 0% | 6000 | 0 | -6000 | 13500 | 7500 | 7500 | 7500 | 36000 | 0 | 19 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 0 |  | 0% | 10000 | 0 | -10000 | 20000 | 10000 | 10000 | 10000 | 50000 | 0 | 20 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
TOTAL COMPONENTE 3 | [5 empty] | 100360 | 156860 | 387360 | 411582 | 353360 | 1409522 | 0 | 0 | 0% | 100360 | 34181.2252 | -66178.7748 | 193998.05 | 386024.11 | 406933.05 | 388385.56 | 1409521.9952 | 0.0047826
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 0 | 3000 | 3000 | 3000 | 1952 | 10952 |  |  | 0% | 0 | 0 | 0 | 3000 | 3000 | 3000 | 1952 | 10952 | 0
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 14500 | 14500 | 14500 | 14500 | 14500 | 72500 |  |  | 0% | 14500 | 4485.8459 | -10014.1541 | 14107.7881 | 14502.5277 | 14932.2095 | 24471.63 | 72500.0012 | -0.0012262 | 21 | El presupuesto total se mantiene, se redistribuye el monto entre los años 2024 y 2028
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 |  |  | 0% | 5000 | 6716.4 | 1716.4 | 3283.6 | 5000 | 5000 | 5000 | 25000 | 0 | 22 | Se redistribuyó el presupuesto de los años 2025 al 2028 para asignar un monto mayor al 2024. Este valor se utilizó para la participación de delegados en el taller de PLANET GOLD en Filipinas
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 7500 | 10000 | 10000 | 10000 | 10000 | 47500 |  |  | 0% | 7500 | 15750.33 | 8250.33 | 10000 | 10000 | 10000 | 1749.67 | 47500 | 0 | 23 | Se redistribuyó el presupuesto de los años 2025 al 2028 para asignar un monto mayor al 2024. Este valor se utilizó para la realización de material promocional del proyecto que fue utilizado en el taller de arranque
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 |  |  | 0% | 5000 | 1777.78 | -3222.22 | 8222.22 | 5000 | 5000 | 5000 | 25000 | 0 | 24 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028. Se utilizó menor presupuesto del establecido en el PRODOC para el taller de arranque
TOTAL COMPONENTE 4 | [5 empty] | 32000 | 37500 | 37500 | 37500 | 36452 | 180952 | 0 | 0 | 0% | 32000 | 28730.3559 | -3269.6441 | 38613.6081 | 37502.5277 | 37932.2095 | 38173.3 | 180952.0012 | -0.0012262
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 0 | 0 | 27500 | 0 | 27500 | 55000 |  |  |  | 0 | 0 | 0 | 0 | 27500 | 0 | 27500 | 55000 | 0
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 0 | 0 | 17500 | 0 | 17500 | 35000 |  |  |  | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 35000 | 0
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 14000 | 14000 | 14000 | 14000 | 14000 | 70000 |  |  |  | 14000 | 8305.2112 | -5694.7888 | 18158.6699 | 18675.548 | 19230.3124 | 5630.26 | 70000.0014 | -0.0014482 | 25 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 2500 | 2500 | 5000 | 5000 | 5000 | 20000 |  |  |  | 2500 | 143.31 | -2356.69 | 4856.69 | 5000 | 5000 | 5000 | 20000 | 0 | 26 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 73100 | Alquiler y mantenimiento de locales | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 3300 | 3706 | 0 | 0 | 7006 | -7006 | 27 | $ 7006 vienen de la cuenta 75700, este monto no fue utilizado en el taller de arranque del proyecto y se utlizará para cubrir parte del gasto de arriendo de la oficina
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 0 | 0 | 5000 | 0 | 5000 | 10000 |  |  |  | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 10000 | 0
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 10000 | 0 | 0 | 0 | 0 | 10000 |  |  |  | 10000 | 2994 | -7006 | 0 | 0 | 0 | 0 | 2994 | 7006 | 28 | $ 7006,00 movidos a la cuenta 73100, este monto no se utilizó en el taller de arranque
TOTAL COMPONENTE 5 | [5 empty] | 26500 | 16500 | 69000 | 19000 | 69000 | 200000 | 0 | 0 | 0% | 26500 | 11442.5212 | -15057.4788 | 26315.3599 | 77381.548 | 24230.3124 | 60630.26 | 200000.0014 | -0.0026744
PMC | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuale | 8000 | 8000 | 8000 | 8000 | 8000 | 40000 |  |  | 0% | 8000 | 5647.78 | -2352.22 | 13161.5133 | 13529.3947 | 7661.31 | 0 | 39999.9981 | 0.0019495 | 29 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
PMC | 62000 | GEF | 001981-PNUD | 72200 | Equipo y Mobiliario | 100 | 100 | 100 | 100 | 100 | 500 |  |  | 0% | 100 | 0 | -100 | 150 | 150 | 100 | 100 | 500 | 0 | 30 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
PMC | 62000 | GEF | 001981-PNUD | 72500 | Suministros | 100 | 100 | 100 | 100 | 100 | 500 |  |  | 0% | 100 | 249 | 149 | 100 | 100 | 25.5 | 25.5 | 500 | 0 | 31 | Se redistribuyó el presupuesto de los años 2025 al 2028 para asignar un monto mayor al 2024. Este valor se utilizó para adquirir suministros de oficina para iniciar la implemetación del proyecto
PMC | 62000 | GEF | 001981-PNUD | 72800 | Equipo informático | 5661 | 0 | 0 | 0 | 0 | 5661 |  |  | 0% | 5661 | 5661 | 0 | 0 | 0 | 0 | 0 | 5661 | 0
PMC | 62000 | GEF | 001981-PNUD | 73100 | Alquiler y mantenimiento de locales | 2500 | 2500 | 2500 | 2500 | 2500 | 12500 |  |  | 0% | 2500 | 4000 | 1500 | 8500 | 0 | 0 | 0 | 12500 | 0 | 32 | Se redistribuyó el presupuesto de los años 2025 al 2028 para asignar un monto mayor al 2024 dado que el valor asignado no cubre el costo del arriendo.
PMC | 62000 | GEF | 001981-PNUD | 74100 | Servicios Profesionales | 0 | 2500 | 2500 | 2500 | 2500 | 10000 |  |  | 0% | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 10000 | 0
PMC | 62000 | GEF | 001981-PNUD | 74500 | Gastos Misceláneos | 10555 | 22856 | 21011 | 20089 | 44804 | 119315 |  |  | 0% | 10555 | 3500 | -7055 | 30911 | 20011 | 20089 | 44804 | 119315 | 0 | 33 | El presupuesto total se mantiene, el monto no utilizado en el año 2024 se redistribuye entre los años 2025 al 2028
PMC | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 0 | 500 | 500 | 500 | 500 | 2000 |  |  | 0% | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 2000 | 0
TOTAL PMC | [5 empty] | 26916 | 36556 | 34711 | 33789 | 58504 | 190476 | 0 | 0 | 0% | 26916 | 19057.78 | -7858.22 | 55822.5133 | 36790.3947 | 30875.81 | 47929.5 | 190475.9981 | 0.0019495
[5 empty] | TOTAL GENERAL | 419666 | 657336 | 979011 | 986811 | 957176 | 4000000 | 0 | 0 | 0% | 419666 | 171092.4824 | -248573.5176 | 827536.8012 | 978734.3404 | 978825.4719 | 1043810.9 | 3999999.9959 | 0.0028315

## comprobacion
Etiquetas de fila | Suma de Total PRODOC (USD) | Suma de B Proposed budget revision (2024) | Suma de Amount (USD) Year 2025 | Suma de Amount (USD) Year 2026 | Suma de Amount (USD) Year 2027 | Suma de Amount (USD) Year 2028
TOTAL COMPONENTE 1 | 952380 | 62068.49 | 251600.29 | 193053.88 | 197968.55 | 247688.79 | 952380
TOTAL COMPONENTE 2 | 1066670 | 15612.11 | 261186.98 | 247981.88 | 280885.54 | 261003.49 | 1066670
TOTAL COMPONENTE 3 | 1409522 | 34181.2252 | 193998.05 | 386024.11 | 406933.05 | 388385.56 | 1409521.9952
TOTAL COMPONENTE 4 | 180952 | 28730.3559 | 38613.6081 | 37502.5277 | 37932.2095 | 38173.3 | 180952.0012
TOTAL COMPONENTE 5 | 200000 | 11442.5212 | 26315.3599 | 77381.548 | 24230.3124 | 60630.26 | 200000.0014
TOTAL PMC | 190476 | 19057.78 | 54822.5133 | 37790.3947 | 30875.81 | 47929.5 | 190475.9981
Total general | 4000000 | 171092.4824 | 826536.8012 | 979734.3404 | 978825.4719 | 1043810.9 | 3999999.9959

## base_comprobacion
POA ORIGINAL PRODOC
GCF Outcome/Atlas Activity | Fund ID | Donor Name | Implementing agent | Atlas Budgetary Account Code | ATLAS Budget Description | Total PRODOC (USD) | B Proposed budget revision (2024) | Amount (USD) Year 2025 | Amount (USD) Year 2026 | Amount (USD) Year 2027 | Amount (USD) Year 2028 | Total (USD) expenditure by end of project
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 100000 | 0 | 40000 | 20000 | 20000 | 20000 | 100000
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 180000 | 0 | 60000 | 40000 | 40000 | 40000 | 180000
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 267900 | 22509.94 | 55978.84 | 47653.88 | 49068.55 | 92688.79 | 267900
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 86500 | 26748.8 | 9400 | 16451.2 | 13900 | 20000 | 86500
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 72100 | Servicios contractuales - Empresas | 202980 | 0 | 52980 | 50000 | 50000 | 50000 | 202980
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 45000 | 0 | 15000 | 10000 | 10000 | 10000 | 45000
COMPONENTE 1 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 70000 | 12809.75 | 18241.45 | 8948.8 | 15000 | 15000 | 70000
TOTAL COMPONENTE 1 | [5 empty] | 952380 | 62068.49 | 251600.29 | 193053.88 | 197968.55 | 247688.79 | 952380
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 45450 | 0 | 15450 | 10000 | 10000 | 10000 | 45450
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 78250 | 5404 | 24596 | 15000 | 15000 | 18250 | 78250
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 246800 | 10208.11 | 51640.98 | 52481.88 | 53385.54 | 79083.49 | 246800
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 95000 | 0 | 35000 | 20000 | 20000 | 20000 | 95000
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 72100 | Servicios contractuales - Empresas | 518500 | 0 | 103500 | 135000 | 165000 | 115000 | 518500
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 37500 | 0 | 15000 | 7500 | 7500 | 7500 | 37500
COMPONENTE 2 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 45170 | 0 | 16000 | 8000 | 10000 | 11170 | 45170
TOTAL COMPONENTE 2 | [5 empty] | 1066670 | 15612.11 | 261186.98 | 247981.88 | 280885.54 | 261003.49 | 1066670
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 75000 | 0 | 30000 | 15000 | 15000 | 15000 | 75000
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 15000 | 8608.4952 | 0 | 5000 | 260.1 | 1131.4 | 14999.9952
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 246800 | 14372.73 | 46698.05 | 48024.11 | 49450.95 | 88254.16 | 246800
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 50000 | 11200 | 8800 | 10000 | 10000 | 10000 | 50000
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 72100 | Servicios contractuales - Empresas | 314000 | 0 | 75000 | 90500 | 92000 | 56500 | 314000
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 72200 | Equipo y Mobiliario | 622722 | 0 | 0 | 200000 | 222722 | 200000 | 622722
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 36000 | 0 | 13500 | 7500 | 7500 | 7500 | 36000
COMPONENTE 3 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 50000 | 0 | 20000 | 10000 | 10000 | 10000 | 50000
TOTAL COMPONENTE 3 | [5 empty] | 1409522 | 34181.2252 | 193998.05 | 386024.11 | 406933.05 | 388385.56 | 1409521.9952
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 10952 | 0 | 3000 | 3000 | 3000 | 1952 | 10952
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 72500 | 4485.8459 | 14107.7881 | 14502.5277 | 14932.2095 | 24471.63 | 72500.0012
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 25000 | 6716.4 | 3283.6 | 5000 | 5000 | 5000 | 25000
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 47500 | 15750.33 | 10000 | 10000 | 10000 | 1749.67 | 47500
COMPONENTE 4 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 25000 | 1777.78 | 8222.22 | 5000 | 5000 | 5000 | 25000
TOTAL COMPONENTE 4 | [5 empty] | 180952 | 28730.3559 | 38613.6081 | 37502.5277 | 37932.2095 | 38173.3 | 180952.0012
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71200 | Consultores Internacionales | 55000 | 0 | 0 | 27500 | 0 | 27500 | 55000
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71300 | Consultores locales | 35000 | 0 | 0 | 17500 | 0 | 17500 | 35000
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuales | 70000 | 8305.2112 | 18158.6699 | 18675.548 | 19230.3124 | 5630.26 | 70000.0014
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 71600 | Viajes | 20000 | 143.31 | 4856.69 | 5000 | 5000 | 5000 | 20000
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 73100 | Alquiler y mantenimiento de locales | 0 | 0 | 3300 | 3706 | 0 | 0 | 7006
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 74200 | Costos audiovisuales y de impresión | 10000 | 0 | 0 | 5000 | 0 | 5000 | 10000
COMPONENTE 5 | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 10000 | 2994 | 0 | 0 | 0 | 0 | 2994
TOTAL COMPONENTE 5 | [5 empty] | 200000 | 11442.5212 | 26315.3599 | 77381.548 | 24230.3124 | 60630.26 | 200000.0014
PMC | 62000 | GEF | 001981-PNUD | 71400 | Servicios contractuales - Individuale | 40000 | 5647.78 | 13161.5133 | 13529.3947 | 7661.31 | 0 | 39999.9981
PMC | 62000 | GEF | 001981-PNUD | 72200 | Equipo y Mobiliario | 500 | 0 | 150 | 150 | 100 | 100 | 500
PMC | 62000 | GEF | 001981-PNUD | 72500 | Suministros | 500 | 249 | 100 | 100 | 25.5 | 25.5 | 500
PMC | 62000 | GEF | 001981-PNUD | 72800 | Equipo informático | 5661 | 5661 | 0 | 0 | 0 | 0 | 5661
PMC | 62000 | GEF | 001981-PNUD | 73100 | Alquiler y mantenimiento de locales | 12500 | 5000 | 7500 | 0 | 0 | 0 | 12500
PMC | 62000 | GEF | 001981-PNUD | 74100 | Servicios Profesionales | 10000 | 0 | 2500 | 2500 | 2500 | 2500 | 10000
PMC | 62000 | GEF | 001981-PNUD | 74500 | Gastos Misceláneos | 119315 | 2500 | 30911 | 21011 | 20089 | 44804 | 119315
PMC | 62000 | GEF | 001981-PNUD | 75700 | Capacitación, Talleres, Reuniones | 2000 | 0 | 500 | 500 | 500 | 500 | 2000
TOTAL PMC | [5 empty] | 190476 | 19057.78 | 54822.5133 | 37790.3947 | 30875.81 | 47929.5 | 190475.9981
[5 empty] | TOTAL GENERAL | 4000000 | 171092.4824 | 826536.8012 | 979734.3404 | 978825.4719 | 1043810.9 | 3999999.9959

## account details
Budgetary Account | Budgetary Acct Description | Budgetary Acct Short Descr | Expense Account | Expense Acct Description | Expense Acct Short Descr
71100 | Employee Costs
71100 | ALD Employee Costs | ALDEmplCst | 71105 | Salaries - ALD | Sal-ALD
71100 | ALD Employee Costs | ALDEmplCst | 71110 | Medical Insurance - ALD | MedIns-ALD
71100 | ALD Employee Costs | ALDEmplCst | 71115 | Contr to Jt Staff Pens Fd-ALD | Pens-ALD
71100 | ALD Employee Costs | ALDEmplCst | 71120 | Reimb of Income Tax-ALD | Rmb Inc Tx
71100 | ALD Employee Costs | ALDEmplCst | 71125 | Special Oper Living Allow-ALD | Sp Oper
71100 | ALD Employee Costs | ALDEmplCst | 71130 | Mission Allowance - ALD | Missn-ALD
71100 | ALD Employee Costs | ALDEmplCst | 71135 | Appoint/Sep Cost Incl Trvl-ALD | App/Sp-ALD
71100 | ALD Employee Costs | ALDEmplCst | 71140 | Hazard Duty Station Allow-ALD | Hazard Dut
71100 | ALD Employee Costs | ALDEmplCst | 71145 | Security Evacuation (ALD) | ALD
71100 | ALD Employee Costs | ALDEmplCst | 71150 | Medical Evacuation (ALD) | ALD
71100 | ALD Employee Costs | ALDEmplCst | 71160 | Other Personnel costs ALD(A&T) | ALD(A & T)
71100 | ALD Employee Costs | ALDEmplCst | 71165 | MIP Conts UN agy NOT adm UNDP | MIP notAdm
71100 | ALD Employee Costs | ALDEmplCst | 71166 | Life Ins UN agy not adm UNDP | Life Insur
71100 | ALD Employee Costs | ALDEmplCst | 71167 | Pen Fund Cont UN Ag Not UNDP | Pen Fund
71100 | ALD Employee Costs | ALDEmplCst | 71168 | Other Expenses UN Agy Pers Rel | Othr EXP
71200 | International Consultants
71200 | International Consultants | Intl Cnslt | 71205 | Intl Consultants-Sht Term-Tech | IntlConST
71200 | International Consultants | Intl Cnslt | 71210 | Intl Consultants-Sht Term-Supp | IntlCons-S
71200 | International Consultants | Intl Cnslt | 71211 | Intl Consult Security Charge | INCSECURTY
71200 | International Consultants | Intl Cnslt | 71212 | UNFPA International IC - Trav | FPAIntTR
71200 | International Consultants | Intl Cnslt | 71215 | IICA Partner personnel | IICApartne
71200 | International Consultants | Intl Cnslt | 71225 | UNOPS CMDC_Partnr Supervd IICA | CMDCIICPA
71200 | International Consultants | Intl Cnslt | 71230 | UNOPS CMDC_Supervised IICA | CMDCIICUN
71200 | International Consultants | Intl Cnslt | 71235 | UNOPS LMDC_Partnr Supervd IICA | LMDCIICPA
71200 | International Consultants | Intl Cnslt | 71240 | UNOPS LMDC_Supervised IICA | LMDCIICUN
71300 | Local Consultants
71300 | Local Consultants | Lcl Cnslts | 71305 | Local Consult.-Sht Term-Tech | LclCons-T
71300 | Local Consultants | Lcl Cnslts | 71306 | UNOPS LICA PF Cont Tech - 15% | LICAPFOPST
71300 | Local Consultants | Lcl Cnslts | 71307 | UNOPS LICA PF PersTechCont 7.5 | LICAPFPETM
71300 | Local Consultants | Lcl Cnslts | 71308 | UNOPS LICA PF PerTech Cont-Vol | LICAPFPETV
71300 | Local Consultants | Lcl Cnslts | 71310 | Local Consult.-Short Term-Supp | LclCons-Sp
71300 | Local Consultants | Lcl Cnslts | 71311 | UNOPS LICA PF Cont Supp 15% | LICAPFOPSS
71300 | Local Consultants | Lcl Cnslts | 71312 | UNOPS LICA PF PersSuppCont 7.5 | LICAPFPESM
71300 | Local Consultants | Lcl Cnslts | 71313 | UNOPS LICA PF Pers SuppContVol | LICAPFPeSv
71300 | Local Consultants | Lcl Cnslts | 71315 | LICA Partner personel | LLICApartn
71300 | Local Consultants | Lcl Cnslts | 71316 | UNFPA Local IC - Travel | FPALocICTr
71300 | Local Consultants | Lcl Cnslts | 71325 | UNOPS CMDC_Partnr Suprvsd LICA | CMDCLICPA
71300 | Local Consultants | Lcl Cnslts | 71330 | UNOPS CMDC_Supervised LICA | CMDCLICUN
71300 | Local Consultants | Lcl Cnslts | 71335 | UNOPS LMDC_Partnr Suprvsd LICA | LMDCLICPA
71300 | Local Consultants | Lcl Cnslts | 71340 | UNOPS LMDC_Supervised LICA | LMDCLICUN
71300 | Local Consultants | Lcl Cnslts | 71350 | Internship stipend | INTERNSTIP
71300 | Local Consultants | Lcl Cnslts | 71351 | UNWomen Internship Stipend | INTERNSTIP
71300 | Local Consultants | Lcl Cnslts | 71360 | Local Consult-Security | LoCsecurit
71400 | Contractual Services - Individ
71400 | Contractual Services - Individ | CntractSrv | 71405 | Service Contracts-Individuals | ServCon-In
71400 | Contractual Services - Individ | CntractSrv | 71410 | MAIP Premium SC | MAIPpreSC
71400 | Contractual Services - Individ | CntractSrv | 71415 | Contribution to Security SC | SecuritySC
71400 | Contractual Services - Individ | CntractSrv | 71420 | Payroll Mgt Cost Recovery SC | PMCR SC
71400 | Contractual Services - Individ | CntractSrv | 71440 | Appendix D SC | AppendDsc
71400 | Contractual Services - Individ | CntractSrv | 71450 | UNFPA-Salaries-ImpPrtn prnl | FPASALMPP
71400 | Contractual Services - Individ | CntractSrv | 71455 | Innovation Prizes Individuals | InnPrizInd
71400 | Contractual Services - Individ | CntractSrv | 71460 | Int Personnel Srvcs Agreement | IPSA
71400 | Contractual Services - Individ | CntractSrv | 71470 | Natl Personnel Srvcs Agreement | NPSA
71500 | UN Volunteers
71500 | UN Volunteers | Un Vol | 71505 | UN Volunteers-Stipend & Allow | UNV-Stp&Al
71500 | UN Volunteers | Un Vol | 71510 | UNV Settling-In-Grant | UNV-S in G
71500 | UN Volunteers | Un Vol | 71511 | UNV_Entry_Lump_Sum | UNV_EntLS
71500 | UN Volunteers | Un Vol | 71515 | UNV-Security Allowance | UNV-SecAll
71500 | UN Volunteers | Un Vol | 71520 | UNV_Volunteer_Learning | UNV_VolLrn
71500 | UN Volunteers | Un Vol | 71525 | UNV-Hazard Pay | UNV-Hazard
71500 | UN Volunteers | Un Vol | 71526 | UNV Well being differential | UNV WellBe
71500 | UN Volunteers | Un Vol | 71530 | UNV-Rest and Recuperation | UNV-R&R
71500 | UN Volunteers | Un Vol | 71535 | UNV-Medical Insurance | UNV-MedIns
71500 | UN Volunteers | Un Vol | 71536 | UNVs - Medical Evacuation | UNV-MedEva
71500 | UN Volunteers | Un Vol | 71537 | UNVs Security Evacuation | UNV SecEva
71500 | UN Volunteers | Un Vol | 71540 | UNV-Global Charges | UNV-Global
71500 | UN Volunteers | Un Vol | 71541 | UNVs-Contribution to security | UNVSECCTRL
71500 | UN Volunteers | Un Vol | 71545 | UNV-Home Leave Travel & Allowa | UNV-HomeLe
71500 | UN Volunteers | Un Vol | 71550 | UNV RSA / Exit Allowance | UNV_RSAExL
71500 | UN Volunteers | Un Vol | 71560 | UNV-Intl Appoint/Sep incl Trvl | UNV-IASIT
71500 | UN Volunteers | Un Vol | 71565 | UNV-Natl Appoint/Sep incl Trvl | UNV-NASIT
71500 | UN Volunteers | Un Vol | 71581 | UNV Housing UN Mission | UNV HouMsn
71500 | UN Volunteers | Un Vol | 71582 | UNV Liberty Mileage UN Misson | UNV LM Msn
71500 | UN Volunteers | Un Vol | 71583 | UNV Telephone UN Mission | UNVTPH msn
71500 | UN Volunteers | Un Vol | 71584 | UNV Medical Exp. UN Mission | UNVMedExp
71500 | UN Volunteers | Un Vol | 71585 | UNV Lost/Damged Prop UN Missio | UNVLOSTDAM
71500 | UN Volunteers | Un Vol | 71586 | UNV Ration DD UN Mission | UNVRations
71500 | UN Volunteers | Un Vol | 71590 | UNV Development Effectiveness | UNVDevEffv
71500 | UN Volunteers | Un Vol | 71591 | UNV_Cost_Recovery_Deployment | UNV_CR_DEP
71500 | UN Volunteers | Un Vol | 71592 | UNV_COST_RECOVERY_RECURRING | UNV_CR_REC
71600 | Travel
71600 | Travel | Travel | 71605 | Travel Tickets-International | TrvlTixInt
71600 | Travel | Travel | 71610 | Travel Tickets-Local | TrvlTixLcl
71600 | Travel | Travel | 71615 | Daily Subsistence Allow-Intl | DSA-Intl
71600 | Travel | Travel | 71620 | Daily Subsistence Allow-Local | DSA-Local
71600 | Travel | Travel | 71625 | Daily Subsist Allow-Mtg Partic | DSA-MtgPrt
71600 | Travel | Travel | 71630 | Shipment | Shipment
71600 | Travel | Travel | 71635 | Travel - Other | Trvl-Other
71600 | Travel | Travel | 71640 | Prepaid Travel Advance | PrepdTrave
71800 | Contractual Services-Imp Partn
71800 | Contractual Services-Imp Partn | SC-IMP PR | 71810 | Contractual Svcs-indiv ImpPtnr | CtrInvImpP
72100 | Contractual Services-Companies
72100 | Contractual Services-Companies | Contr-Cmpy | 72105 | Svc Co-Construction & Engineer | SrcCo-C&E
72100 | Contractual Services-Companies | Contr-Cmpy | 72110 | Svc Co-Agricultural Management | SvcCo-Agri
72100 | Contractual Services-Companies | Contr-Cmpy | 72115 | Svc Co-Natural Resources & Env | SvcCo-Natl
72100 | Contractual Services-Companies | Contr-Cmpy | 72120 | Svc Co-Trade and Business Serv | SvcCo-Trad
72100 | Contractual Services-Companies | Contr-Cmpy | 72125 | Svc Co-Studies & Research Serv | SvcCo-Stud
72100 | Contractual Services-Companies | Contr-Cmpy | 72126 | Svc Co-Security blast assessme | SRC CO SEC
72100 | Contractual Services-Companies | Contr-Cmpy | 72130 | Svc Co-Transportation Services | SvcCo-Tran
72100 | Contractual Services-Companies | Contr-Cmpy | 72135 | Svc Co-Communications Service | SvcCo-Comm
72100 | Contractual Services-Companies | Contr-Cmpy | 72136 | ServiceCo-Systems Development | FPACoSyDel
72100 | Contractual Services-Companies | Contr-Cmpy | 72137 | ServiceCo-HlpdskDskSuprtTrng | FPACOHDST
72100 | Contractual Services-Companies | Contr-Cmpy | 72138 | Service Co - Business Analysis | FPASERCOBA
72100 | Contractual Services-Companies | Contr-Cmpy | 72140 | Svc Co-Information Technology | SvcCo-Info
72100 | Contractual Services-Companies | Contr-Cmpy | 72145 | Svc Co-Training and Educ Serv | SvcCo-Trai
72100 | Contractual Services-Companies | Contr-Cmpy | 72150 | Svc Co-Manufacturing Services | SvcCo-Manu
72100 | Contractual Services-Companies | Contr-Cmpy | 72155 | Svc Co-Public Admin, Politics | SvcCo-Publ
72100 | Contractual Services-Companies | Contr-Cmpy | 72160 | Svc Co-Education & Health Serv | SvcCo-Educ
72100 | Contractual Services-Companies | Contr-Cmpy | 72165 | Svc Co-Social Svcs, Social Sci | Svc Co-Soc
72100 | Contractual Services-Companies | Contr-Cmpy | 72170 | Svc Co-Humanitarian Aid & Relf | Svc Co-Hum
72100 | Contractual Services-Companies | Contr-Cmpy | 72175 | Svc Co-Urban, Rural & Regional | Svc Co-Urb
72100 | Contractual Services-Companies | Contr-Cmpy | 72180 | Innovation Prizes Companies | InnovPriCo
72200 | Equipment and Furniture
72200 | Equipment and Furniture | Equip&Furn | 72205 | Office Machinery | Office Mch
72200 | Equipment and Furniture | Equip&Furn | 72210 | Machinery and Equipment | Mac & Eqpt
72200 | Equipment and Furniture | Equip&Furn | 72215 | Transporation Equipment | Tran Equip
72200 | Equipment and Furniture | Equip&Furn | 72216 | Spec purp transp Armored&Mine | ArmoreMine
72200 | Equipment and Furniture | Equip&Furn | 72220 | Furniture | Furniture
72200 | Equipment and Furniture | Equip&Furn | 72225 | Sale of Equip & Furniture | SaleEq&Frn
72300 | Materials & Goods
72300 | Materials & Goods | Matl&Goods | 72305 | Agri & Forestry Products | Ag&FrPrds
72300 | Materials & Goods | Matl&Goods | 72310 | Minerals,Mining & Metal Prdcts | MM&MPrds
72300 | Materials & Goods | Matl&Goods | 72311 | Fuel, petroleum and other oils | Fuel/Oils
72300 | Materials & Goods | Matl&Goods | 72315 | Food & Textile Products | Fd&TxtlPrd
72300 | Materials & Goods | Matl&Goods | 72320 | Wood & Paper Products | Wd&PprPrds
72300 | Materials & Goods | Matl&Goods | 72325 | Chemical,Glass,NonMetallic Prd | ChemGlass
72300 | Materials & Goods | Matl&Goods | 72330 | Medical Products | MedicalPrd
72300 | Materials & Goods | Matl&Goods | 72335 | Pharmaceutical Products | PharmPrds
72300 | Materials & Goods | Matl&Goods | 72340 | Contraceptive Pills | Ctrc Pills
72300 | Materials & Goods | Matl&Goods | 72341 | Contraceptive-IUDs | Ctrc-IUDs
72300 | Materials & Goods | Matl&Goods | 72342 | Contraceptives-Condoms | C-Condoms
72300 | Materials & Goods | Matl&Goods | 72343 | Contraceptives-Injectables | Injectable
72300 | Materials & Goods | Matl&Goods | 72344 | Contraceptives-Implants | C-Implants
72300 | Materials & Goods | Matl&Goods | 72345 | Contraceptives-Spermicides | Spermicide
72300 | Materials & Goods | Matl&Goods | 72350 | Medical Kits | Med_Kits
72300 | Materials & Goods | Matl&Goods | 72351 | CD4 analyser/accessories | CD4 analys
72300 | Materials & Goods | Matl&Goods | 72352 | HIV Viral Load analyser/access | HIV VL ana
72300 | Materials & Goods | Matl&Goods | 72353 | Mircoscopes | Mircoscope
72300 | Materials & Goods | Matl&Goods | 72354 | TB Molecular Test Equipment | TB MT equi
72300 | Materials & Goods | Matl&Goods | 72355 | Bednets, Anti-malarial | Bednets
72300 | Materials & Goods | Matl&Goods | 72360 | Anti-retroviral drugs (ARV) | ARV Drugs
72300 | Materials & Goods | Matl&Goods | 72361 | Antimalarial medicines | Antimalari
72300 | Materials & Goods | Matl&Goods | 72362 | Opioid substitutes medicines | Opsubmedic
72300 | Materials & Goods | Matl&Goods | 72363 | Opport, infections & STI medic | OI&STImed
72300 | Materials & Goods | Matl&Goods | 72364 | Anti-tuberculosis medicines | AnitTB med
72300 | Materials & Goods | Matl&Goods | 72365 | Laboratory reagents | Lab Reagen
72300 | Materials & Goods | Matl&Goods | 72366 | Dignity & hygiene kits | Dig Hyg Kt
72300 | Materials & Goods | Matl&Goods | 72367 | Personal Protective Equipment | PrsProtEq
72300 | Materials & Goods | Matl&Goods | 72370 | Security related goods and mat | Sec Goods
72300 | Materials & Goods | Matl&Goods | 72399 | Other Materials and Goods | OtherM&G
72400 | Communic & Audio Visual Equip
72400 | Communic & Audio Visual Equip | Comm&AV | 72401 | Prefab structure/other buildin | Prefab-
72400 | Communic & Audio Visual Equip | Comm&AV | 72402 | Building Maintenance | BuildMant
72400 | Communic & Audio Visual Equip | Comm&AV | 72405 | Acquisition of Communic Equip | ExpCommEq
72400 | Communic & Audio Visual Equip | Comm&AV | 72406 | Security communication equipme | Sec Comm
72400 | Communic & Audio Visual Equip | Comm&AV | 72410 | Acquisition of Audio Visual Eq | AcqAVEqu
72400 | Communic & Audio Visual Equip | Comm&AV | 72415 | Courier Charges | Corier Chg
72400 | Communic & Audio Visual Equip | Comm&AV | 72420 | Land Telephone Charges | LndTeleChg
72400 | Communic & Audio Visual Equip | Comm&AV | 72425 | Mobile Telephone Charges | MblTeleChg
72400 | Communic & Audio Visual Equip | Comm&AV | 72430 | Postage and Pouch | Post&Pouch
72400 | Communic & Audio Visual Equip | Comm&AV | 72435 | E-mail-Subscription | E-mailSubs
72400 | Communic & Audio Visual Equip | Comm&AV | 72440 | Connectivity Charges | ConnectChg
72400 | Communic & Audio Visual Equip | Comm&AV | 72445 | Common Services-Communications | CommServ
72500 | Supplies
72500 | Supplies | Supplies | 72505 | Stationery & other Office Supp | Stationery
72500 | Supplies | Supplies | 72510 | Publications | Publicatin
72500 | Supplies | Supplies | 72515 | Print Media | PrintMedia
72500 | Supplies | Supplies | 72520 | Electronic Media | Elec Media
72600 | Grants
72600 | Grants | Grants | 72605 | Grants to Instit & other Benef | Grants
72600 | Grants | Grants | 72610 | Micro Capital Grants-Credit | Micro-Crdt
72600 | Grants | Grants | 72615 | Micro Capital Grants-Other | Micro-Othr
72600 | Grants | Grants | 72620 | Joint Programming Expenditure | JointProg
72600 | Grants | Grants | 72625 | Capital Grants - Financial Ser | GrantsFinS
72600 | Grants | Grants | 72630 | Capital Grants - Local GOVT | Grants-LG
72600 | Grants | Grants | 72635 | Grant by IP toSubGrantee | GrantByIP
72600 | Grants | Grants | 72640 | Performance Based Payments PBP | PerfBasePy
72600 | Grants | Grants | 72645 | Low Value Perfor based payment | LowValuPBP
72600 | Grants | Grants | 72650 | Inc Conting Repay Clause_Payt | IncCotREpP
72700 | Hospitality/Catering
72700 | Hospitality/Catering | Hospitalty | 72705 | Hospitality-Special Events | Hsp-SpEvts
72700 | Hospitality/Catering | Hospitalty | 72710 | Hospitality-Vouchered Expenses | Hsp-Vchred
72700 | Hospitality/Catering | Hospitalty | 72715 | Hospitality Catering | Hospitalit
72800 | Information Technology Equipmt
72800 | Information Technology Equipmt | InfoTechEq | 72805 | Acquis of Computer Hardware | CompHrdwre
72800 | Information Technology Equipmt | InfoTechEq | 72810 | Acquis of Computer Software | CompSftwre
72800 | Information Technology Equipmt | InfoTechEq | 72815 | Inform Technology Supplies | InfoTchSup
72900 | MDTF & DBS Reporting
72900 | MDTF & DBS Reporting | MDTF-DBS | 72915 | DirectPassThrough_IndirectCost | DirPasThIC
72900 | MDTF & DBS Reporting | MDTF-DBS | 72920 | UNDG-Joint Prog Expend-Transf | UNDG-TRNFR
72900 | MDTF & DBS Reporting | MDTF-DBS | 72921 | UNDG-1.1 Supplies, com, equip | UNDG-1.1
72900 | MDTF & DBS Reporting | MDTF-DBS | 72922 | UNDG-1.2 Personnel | UNDG-1.2
72900 | MDTF & DBS Reporting | MDTF-DBS | 72923 | UNDG-1.3 Training of counter | UNDG-1.3
72900 | MDTF & DBS Reporting | MDTF-DBS | 72924 | UNDG-1.4 Contracts | UNDG-1.4
72900 | MDTF & DBS Reporting | MDTF-DBS | 72925 | UNDG-1.5 Other direct costs | UNDG-1.5
72900 | MDTF & DBS Reporting | MDTF-DBS | 72926 | UNDG-2.0 Indirect costs | UNDG-2.0
72900 | MDTF & DBS Reporting | MDTF-DBS | 72928 | UNDG MPTF to MPTF | MPTFtoMPTF
72900 | MDTF & DBS Reporting | MDTF-DBS | 72929 | UNDG-Agency Return of Transfer | UNDG-AGRET
72900 | MDTF & DBS Reporting | MDTF-DBS | 72935 | UNDG-JP - UNEX Submitted | UNDG SUBM
72900 | MDTF & DBS Reporting | MDTF-DBS | 72940 | UNDG-JP Exp Transfer from Inte | UNDG-JPTRN
72900 | MDTF & DBS Reporting | MDTF-DBS | 72941 | UNDG3.1 Staff & Personnel Cost | UNDG 3.1
72900 | MDTF & DBS Reporting | MDTF-DBS | 72942 | UNDG3.2 Suppl, Comm, Materials | UNDG 3.2
72900 | MDTF & DBS Reporting | MDTF-DBS | 72943 | UNDG3.3 Equip, Veh, Furn, Depn | UNDG 3.3
72900 | MDTF & DBS Reporting | MDTF-DBS | 72944 | UNDG 3.4 Contratual Services | UNDG 3.4
72900 | MDTF & DBS Reporting | MDTF-DBS | 72945 | UNDG 3.5 TRAVEL | UNDG 3.5
72900 | MDTF & DBS Reporting | MDTF-DBS | 72946 | UNDG 3.6 Transfer and Grants | UNDG 3.6
72900 | MDTF & DBS Reporting | MDTF-DBS | 72947 | UNDG 3.7 General Operating | UNDG 3.7
72900 | MDTF & DBS Reporting | MDTF-DBS | 72949 | MDTF National Expenses | MPTFONATE
72900 | MDTF & DBS Reporting | MDTF-DBS | 72950 | DBS Expenditure | DBS EXP
72900 | MDTF & DBS Reporting | MDTF-DBS | 72962 | Software-internally developed | SoftIntDev
72900 | MDTF & DBS Reporting | MDTF-DBS | 72963 | Copyrights | Copyrights
72900 | MDTF & DBS Reporting | MDTF-DBS | 72964 | Patent Rights | Patents
72900 | MDTF & DBS Reporting | MDTF-DBS | 72965 | Trade Marks | Trade Mark
72900 | MDTF & DBS Reporting | MDTF-DBS | 72966 | Licenses and other | License
73100 | Rental & Maintenance-Premises
73100 | Rental & Maintenance-Premises | Rent&Maint | 73101 | Leased/rented land | LeaseLand
73100 | Rental & Maintenance-Premises | Rent&Maint | 73104 | Leased Building | LeaseBuild
73100 | Rental & Maintenance-Premises | Rent&Maint | 73105 | Rent | Rent
73100 | Rental & Maintenance-Premises | Rent&Maint | 73106 | Leased premises alterations | Leasealter
73100 | Rental & Maintenance-Premises | Rent&Maint | 73107 | Rent - Meeting Rooms | MeetingRm
73100 | Rental & Maintenance-Premises | Rent&Maint | 73108 | Leased office equip and furnit | LeaseOffeq
73100 | Rental & Maintenance-Premises | Rent&Maint | 73110 | Custodial & Cleaning Services | Cust&Clng
73100 | Rental & Maintenance-Premises | Rent&Maint | 73115 | Moving Expenses | Moving Exp
73100 | Rental & Maintenance-Premises | Rent&Maint | 73120 | Utilities | Utilities
73100 | Rental & Maintenance-Premises | Rent&Maint | 73125 | Common Services-Premises | CmnServPrm
73200 | Premises Alternations
73200 | Premises Alternations | PremAlter | 73201 | Land | Land
73200 | Premises Alternations | PremAlter | 73204 | Building | Building
73200 | Premises Alternations | PremAlter | 73205 | Premises Alternations | Prms Alter
73200 | Premises Alternations | PremAlter | 73210 | Reinforcement of premises | Reinforcem
73200 | Premises Alternations | PremAlter | 73216 | Construction Cost | Constructi
73300 | Rental & Maint of Info Tech Eq
73300 | Rental & Maint of Info Tech Eq | Rnt&Maint | 73305 | Maint & Licensing of Hardware | MaintHdwre
73300 | Rental & Maint of Info Tech Eq | Rnt&Maint | 73310 | Maint & Licencing of Software | MaintSftwr
73300 | Rental & Maint of Info Tech Eq | Rnt&Maint | 73315 | Leasing of Hardware | LsgHrdware
73400 | Rental & Maint of Other Equip | Rntl&Maint | 73405 | Rental & Maint-Other Office Eq | RntlOthrEq
73400 | Rental & Maint of Other Equip | Rntl&Maint | 73406 | Maintenance of Equipment | MaintEq
73400 | Rental & Maint of Other Equip | Rntl&Maint | 73410 | Maint, Oper of Transport Equip | MaintTrnsp
73400 | Rental & Maint of Other Equip | Rntl&Maint | 73420 | Leased Vehicles | LeasedVehi
73400 | Rental & Maint of Other Equip | Rntl&Maint | 73440 | Lease Heavy equip/other equip | LeaseHvyEq
73500 | Reimbursement Costs
73500 | Reimbursement Costs | Reimb Csts | 73505 | Reimb to UNDP for Supp Srvs | Rmb UNDP
73500 | Reimbursement Costs | Reimb Csts | 73510 | Reimb to UN for Supp Srvs | Rmb UN
73500 | Reimbursement Costs | Reimb Csts | 73515 | Reimb to UN for Ext Audit Srvs | Rmb UN Aud
73500 | Reimbursement Costs | Reimb Csts | 73520 | Reimb UN Sys Entity Supp Srvs | Rmb UN Sys
73600 | UNOPS Non Pers Direct Costs
73600 | UNOPS Non Pers Direct Costs | DCNONPER | 73610 | UNOPS CMDC_non-person related | CMDCNONPER
73600 | UNOPS Non Pers Direct Costs | DCNONPER | 73620 | UNOPS LMDC_non-person related | LMDCNONPER
74100 | Professional Services
74100 | Professional Services | Prof Srvcs | 74105 | Management and Reporting Srvs | MgmtRptSrv
74100 | Professional Services | Prof Srvcs | 74110 | Audit Fees | Audit Fees
74100 | Professional Services | Prof Srvcs | 74112 | Accounting related Fees | AcctingFee
74100 | Professional Services | Prof Srvcs | 74115 | Legal Fees | Legal Fees
74100 | Professional Services | Prof Srvcs | 74120 | Capacity Assessment | Cap Assess
74100 | Professional Services | Prof Srvcs | 74125 | Investment Management Fees | Inv MgtFee
74200 | Audio Visual&Print Prod Costs
74200 | Audio Visual&Print Prod Costs | AudioVisl | 74205 | Audio Visual Productions | AudioVisua
74200 | Audio Visual&Print Prod Costs | AudioVisl | 74210 | Printing and Publications | PrintPubs
74200 | Audio Visual&Print Prod Costs | AudioVisl | 74215 | Promotional Materials and Dist | PromoDist
74200 | Audio Visual&Print Prod Costs | AudioVisl | 74220 | Translation Costs | TransCsts
74200 | Audio Visual&Print Prod Costs | AudioVisl | 74225 | Other Media Costs | OtherMedia
74200 | Audio Visual&Print Prod Costs | AudioVisl | 74230 | Audio & Visual Equipment | AudioVisua
74300 | Contributions
74300 | Contributions | Contribut | 74305 | Contributions to CCAQ | Contr CCAQ
74300 | Contributions | Contribut | 74310 | Contributions to JIU | Contr JIU
74300 | Contributions | Contribut | 74315 | Contributions to ICSC | Contr ICSC
74300 | Contributions | Contribut | 74320 | Contributions to CEB Activity | Contr CEB
74300 | Contributions | Contribut | 74325 | Contrib.To CO Common Security | Security
74300 | Contributions | Contribut | 74330 | UNFPA-ContributionsTORCsystems | FPACONTRCS
74300 | Contributions | Contribut | 74335 | Contributions to RC System | Contrib RC
74300 | Contributions | Contribut | 74340 | Contributions to GEI | IEO2GEI
74400 | Provisions & Write-offs
74400 | Provisions & Write-offs | Prov&WrtOf | 74401 | Provision for Write-Off | ProvW/0
74400 | Provisions & Write-offs | Prov&WrtOf | 74405 | Charge for Doubtful Accounts | DbtfulAcct
74400 | Provisions & Write-offs | Prov&WrtOf | 74410 | Charges on Fin Completed Projs | ChgFinCmpl
74400 | Provisions & Write-offs | Prov&WrtOf | 74415 | Investments Compensation Pymts | Comp Pymt
74400 | Provisions & Write-offs | Prov&WrtOf | 74420 | Exch Loss ExecutingAgt HQ only | AgyExcLoss
74400 | Provisions & Write-offs | Prov&WrtOf | 74425 | Provision for ASHI | Prov. ASHI
74400 | Provisions & Write-offs | Prov&WrtOf | 74430 | CDF Account Provisions & WO | CDF Accoun
74500 | Miscellaneous Expenses
74500 | Miscellaneous Expenses | MiscExp | 74505 | Insurance | Insurance
74500 | Miscellaneous Expenses | MiscExp | 74507 | Warranty Expense | Warrantyex
74500 | Miscellaneous Expenses | MiscExp | 74510 | Bank Charges | Bank Chgs
74500 | Miscellaneous Expenses | MiscExp | 74511 | Bank Compensation Expense | BankComExp
74500 | Miscellaneous Expenses | MiscExp | 74513 | Lease Interest Expense | LeaseINT
74500 | Miscellaneous Expenses | MiscExp | 74515 | Claims and Adjustments | Clms & Adj
74500 | Miscellaneous Expenses | MiscExp | 74516 | UNFPA_Non-recoverable VAT | Nonrec VAT
74500 | Miscellaneous Expenses | MiscExp | 74520 | Storage | Storage
74500 | Miscellaneous Expenses | MiscExp | 74525 | Sundry | Sundry
74500 | Miscellaneous Expenses | MiscExp | 74530 | Staff Welfare | Staff Welf
74500 | Miscellaneous Expenses | MiscExp | 74540 | Ex-Gratia Payments non staff | Ex-gratia
74500 | Miscellaneous Expenses | MiscExp | 74550 | MSA EXPENSE | MSA EXP
74500 | Miscellaneous Expenses | MiscExp | 74551 | MSA_Employee benefits | MSAempBen
74500 | Miscellaneous Expenses | MiscExp | 74552 | MSA_Contractual services | MSAConSer
74500 | Miscellaneous Expenses | MiscExp | 74553 | MSA_Grantsand other transfers | MSAGrantTr
74500 | Miscellaneous Expenses | MiscExp | 74554 | MSA_Supplies&consumables used | MSAsuppCon
74500 | Miscellaneous Expenses | MiscExp | 74555 | MSA_Management Fee | MSAmgmtFee
74500 | Miscellaneous Expenses | MiscExp | 74557 | MSA_Finance Costs | MSAFinanCo
74500 | Miscellaneous Expenses | MiscExp | 74558 | MSA_Other expenses | MSAOtherEx
74500 | Miscellaneous Expenses | MiscExp | 74559 | PDR AOS Fees UNOPS | PDR AOS
74500 | Miscellaneous Expenses | MiscExp | 74560 | UNFPA-Catering non hospitality | FPACATNOHO
74500 | Miscellaneous Expenses | MiscExp | 74570 | UNFPA_Incentv-indvd w/t contrt | IncentNonC
74500 | Miscellaneous Expenses | MiscExp | 74595 | UNCDF Appraisal and De-Risking | Derisk
74500 | Miscellaneous Expenses | MiscExp | 74596 | Services to projects -GOE | PrjSrv-GOE
74500 | Miscellaneous Expenses | MiscExp | 74597 | DPC to recover waived GMS | DPCWAIGMS
74500 | Miscellaneous Expenses | MiscExp | 74598 | Direct Project Costs - GOE | DPC-GOE
74500 | Miscellaneous Expenses | MiscExp | 74599 | UNDP cost recovery chrgs-Bills | UNDP Cost
74600 | Prepaid Project Expenses
74600 | Prepaid Project Expenses | PrPaidExp | 74605 | Prepaid Project Expenses | PrepdPrjEx
74600 | Prepaid Project Expenses | PrPaidExp | 74610 | UNOPS Prepaid Operational Exp | Prepd misc
74600 | Prepaid Project Expenses | PrPaidExp | 74615 | Prepaid Miscellaneous Expense | Prepd Misc
74600 | Prepaid Project Expenses | PrPaidExp | 74696 | PP&E Expensed Items | RIE PPE
74700 | Transport, Shipping and handle
74700 | Transport, Shipping and handle | TransShip | 74705 | Port Operation | Port Oper
74700 | Transport, Shipping and handle | TransShip | 74710 | Land Transport | Land Trans
74700 | Transport, Shipping and handle | TransShip | 74715 | EDP Operations | EDP Operat
74700 | Transport, Shipping and handle | TransShip | 74720 | Distribution Cost | Distribut
74700 | Transport, Shipping and handle | TransShip | 74725 | Other L.T.S.H. | Other LTSH
75700 | Training, Workshops and Confer
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75705 | Learning costs | LearnCost
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75706 | Learning - ticket costs | LEARN_TKT
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75707 | Learning – subsistence allowan | LEARN_SUBS
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75708 | Learning - subcontracts | LEARN_SUBC
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75709 | Learning - training of counter | LEARN_CNTR
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75710 | Participation of counterparts | ParticpCpt
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75711 | TrnWrkshp&Conf - Stipends | TWCStipend
75700 | Training, Workshops and Confer | TR,WKSP,CF | 75712 | TrnWrkshp&Conf - Honorariums | TWCHonorar

## Hoja1
Renta/Mes | Meses |  | Años | Total
750 | 12 | 9000 | 4 | 36000
PPCF | Meses |  | Años | Total
150 | 12 | 1800 | 4 | 7200
10800
43200