“National Child Project Under GEF Africa Minigrids Program – Somalia”

UNDP-GEF PIMS+ ID number: 6328

GEF Project ID number: 10470

Country:; Somalia. Region:; Africa. Focal Area/Strategic Program:; Climate change. GEF Implementing Agency:; United Nations Development Programme (UNDP). Implementing Partner/Executing Agency:; UNDP Somalia Country Office. Project Timeframe:; December 13, 2022 – December 13, 2026. Timeframe of MTR; August 2025 – October 2025. Report version #; 2.0. Evaluation Team. Name:; Kevin Enongene. Role:; International Evaluator. E-Mail:; kenongene@fokabs.com. Name:; Leyla Jeyte. Role:; National Evaluator. E-Mail:; leylajt@gmail.com. December 2025.

# ACKNOWLEDGEMENTS

The evaluators wish to express their sincere gratitude to all project participants and stakeholders for their time and effort during the midterm review interviews. Your valuable insights, candid perspectives, and constructive contributions significantly informed the evaluation findings.

Special thanks go to United Nations Development Programme (UNDP) Somalia Country Office (CO), particularly Mr. Hassan Abdirizak Ahmed, Mr. Salah Dahir and Mr. Mohamed Adan for their consistent logistical support and guidance, which were instrumental in the successful completion of the review. The evaluators are thankful to the UNDP Regional Technical Adviser (Dr. Amal Aldababseh) for her guidance provided during the mid-term review (MTR) process. The evaluators also extend their appreciation to all interviewed stakeholders including the Ministry of Energy and Water Resources (MoEWR), the Ministry of Education and the Ministry of Energy of Somaliland among others for the information and assistance provided throughout the review process. Your willingness to share experiences and highlight key facts was essential in establishing a solid factual foundation for this review. All remaining errors are our own.

We trust that the findings and recommendations presented in this report will support the effective implementation of the second half of the project.

# TABLE OF CONTENT

ACKNOWLEDGEMENTS	ii

TABLE OF CONTENTS	iii

List of Tables	v

ACRONYMS AND ABBREVIATIONS	vi

GLOSSARY	vii

1	EXECUTIVE SUMMARY	ix

2	INTRODUCTION	1

2.1	Purpose and objective of the Mid-term Review	1

2.2	Scope and Methodology	1

2.2.1	Scope of the MTR	1

2.2.2	Methodology	1

2.3	Limitations to the MTR	2

2.4	Structure of the MTR Report	3

3	PROJECT DESCRIPTION AND BACKGROUND	3

3.1	Project start and duration, including milestones	3

3.2	Development context: environmental, socio-economic, institutional, and policy factors relevant to the project objectives and scope	3

3.2.1	Environment, and Socio-Economic context	3

3.2.2	Institutional and policy factors	6

3.3	Problems that the project seeks to address: threats and barriers targeted	7

3.4	Project Description and Strategy	9

3.4.1	Project objective, outcomes and expected results	9

3.4.2	Description of field sites	12

3.5	Project Implementation Arrangements	13

3.6	Total resources for the project	15

3.7	Main stakeholders	16

4	FINDINGS	17

4.1	Project Strategy	17

4.1.1	Project Design	17

4.1.2	Results Framework	22

4.2	Progress towards Results	28

4.2.1	Progress towards outcomes analysis	28

4.3	Project Implementation and Adaptive Management	30

4.3.1	Management Arrangements	30

4.3.2	Work planning	33

4.3.3	Finance and co-finance	34

4.3.4	Project level monitoring and evaluation systems	36

4.3.5	Stakeholder engagement	37

4.3.6	Social and Environmental Standards (Safeguards)	39

4.3.7	Reporting	40

4.3.8	Communications & Knowledge Management	41

4.4	Sustainability	43

4.4.1	Financial risks to sustainability	44

4.4.2	Socio-economic to sustainability	46

4.4.3	Environmental risks to sustainability	46

5	CONCLUSIONS AND RECOMMENDATIONS	48

5.1	Conclusions	48

5.2	Recommendations	48

ANNEX. LIST OF ANNEXES	51

Annex I.	Terms of Reference of the MTR	52

Annex II.	Evaluative Matrix	68

Annex III.	Questionnaire used for Data Collection	82

Annex IV.	MTR Rating Scales	84

Annex V.	MTR Itinerary	87

Annex VI.	Stakeholders Consulted	90

Annex VII.	List of Documents Reviewed	92

Annex VIII.	GEF Core Indicators	93

Annex IX.	Signed UNEG Code of Conduct Form	94

Annex X.	Signed MTR Clearance Form	96

Annex XI.	Audit Trail_(attached as a separate file)	97

Annex XII.	Risks to achieving outcomes (attached as a separate file)	98

Annex XIII.	Progress towards outcomes analysis	99

# List of Tables

Table 1: Project timeline and key milestones	3

Table 2: Total project budget (ProDoc)	15

Table 3 Categories of project stakeholders and institutions	16

Table 4: Review of non-SMART project indicators	23

Table 5: Proposition of new gender-sensitive indicators	27

Table 6: Progress Towards Results Matrix (Achievement of outcomes against End-of-project Targets)	99

# ACRONYMS AND ABBREVIATIONS

| ADRA AfDB | Adventist Development and Relief Agency African Development Bank |
| --- | --- |
| AMP BECO | Africa Minigrids Program Benadir Energy Company |
| CBO | Community-Based Organization |
| CO CoP | Country Office Communities of Practice |
| CSO DRA | Civil Society Organization Digital Readiness Assessment |
| DREI | Derisking Renewable Energy Investment |
| ESMF ESPs ESRES GAP GEEL GEF GHG GoS HECO IFC KM LoA MoECC MoEM MTR MoERD MoEWR MPP M&E NEA PIR PSC PMU ProDoc PSAWEN RESA SBS SMART SNEC SOMRENA SQCC UNDP USAID USD QA QAMF | Environmental and Social Management Framework Energy Service Providers Energy Security and Resource Efficiency in Somaliland Gender Action Plan Growth, Enterprise, Employment and Livelihoods Global Environment Facility Greenhouse gas Government of Somalia Horn Electricity Company International Finance Corporation Knowledge Management Letter of Agreement Ministry of Environment and Climate Change Ministry of Energy and Minerals Midterm Review Ministry of Environment and Rural Development Ministry of Energy and Water Resources Mini-grid Pilot Plan Monitoring and Evaluation National Electricity Authority Project Implementation Report Project Steering Committee Project Management Unit Project Document Puntland State Authority for Water, Energy and Natural Resources Renewable Energy Sector Association Somali Bureau of Standards Specific, Measurable, Achievable, Reliable and Time-bound Somaliland National Energy Commission Somaliland Renewable Energy Association Somaliland Quality Control Commission United Nations Development Programme United States Agency for International Development United States Dollar Quality Assurance Quality Assurance and Monitoring Framework |

# GLOSSARY

| Baseline data | Data that describe the situation to be addressed by an intervention and serve as the starting point for measuring the performance of the intervention |
| --- | --- |
| Beneficiaries | The specific individuals or organizations for whose benefit an intervention is undertaken |
| Capacity development | The process by which individuals, organizations, institutions, and societies develop their abilities individually and collectively to perform functions, solve problems, and set and achieve objectives |
| Conclusion | A reasoned judgement based on a synthesis of empirical findings or factual statements corresponding to a specific circumstance |
| Effect | Intended or unintended change due directly or indirectly to an intervention |
| Effectiveness | The extent to which the development intervention’s objectives were achieved, or are expected to be achieved |
| Efficiency | A measure of how economically resources/inputs (funds, expertise, time, etc) are converted to results |
| Finding | A factual statement about the programme or project based on empirical evidence gathered through monitoring and evaluation activities |
| Impact | Positive and negative, intended and non-intended, directly and indirectly, long-term effects produced by a development intervention |
| Indicator | Quantitative or qualitative factors that provide a means to measure the changes caused by an intervention |
| Lessons learned | Generalizations based on evaluation experiences that abstract from specific circumstances to broader situations |
| Logframe (logical framework approach) | Management tool used to facilitate the planning, implementation and evaluation of an intervention. It involves identifying strategic elements (activities, outputs, outcomes, impact) and their causal relationships, indicators, and assumptions that may affect success or failure. Based on RBM (results-based management) principles |
| Outcome | The likely or achieved (short-term and/or medium-term) effects of an intervention’s outputs |
| Output | The product, capital goods, and/or service that results from an intervention; may also include a change resulting from the intervention which is relevant to the achievement of an outcome |
| Rating | An instrument for forming and validating a judgement on the relevance, performance, and success of a programme or project through the use of a scale with numeric, alphabetic, and/or descriptive codes |
| Recommendation | A proposal for action to be taken in a specific circumstance, including the parties responsible for that action |
| Relevance | The extent to which the objectives of an intervention are consistent with beneficiaries’ requirements, country needs, global priorities, and partners’ and donors’ policies |
| Risk | Factor, normally outside the scope of an intervention, which may affect the achievement of an intervention’s objectives |
| Sustainability | The continuation of benefits from an intervention, after the development assistance has been completed |
| Stakeholders | The specific individuals or organizations that have a role and interest in the objectives and implementation of a programme or project |

# EXECUTIVE SUMMARY

Project Information Table

| Project Details |  | Project Milestones | Dates |
| --- | --- | --- | --- |
| Project Title | Promoting access to modern energy services and better livelihoods in Somalia - National child project under the GEF Africa Minigrids Program – Somalia | PIF Approval Date: | Dec 19, 2019 |
| UNDP Project ID (PIMS #): | 6328 | CEO Approval date (MSP): | Dec 14, 2021 |
| GEF Project ID: | 10413 | ProDoc Signature Date: | Jul 12, 2022 |
| UNDP Quantum Award ID: Project ID: | n/a n/a | Date Project Manager hired: | n/a |
| Country/Countries: | Somalia | Inception Workshop Date: | Feb 13, 2023 , |
| Region: | Arab States | Mid-Term Review Completion Date: | 12.08.2025 |
| Focal Area: | Climate Change Mitigation | Terminal Evaluation Completion date: | Oct 30, 2026 |
| GEF Operational Programme or Strategic Priorities/Objectives: |  | Planned Operational Closure Date: | Nov 30, 2026 |
| Trust Fund: | GEF Trust Fund |  |  |
| Implementing Partner (GEF Executing Entity): | Ministry of Energy and Water Resources (MoEWR) of the Federal Government of Somalia |  |  |
| NGOs/CBOs involvement: | - Adventist Development and Relief Agency (ADRA). - SHURAAKO - Hayle Barise Technical College - Women and Child Care Association in Somalia. - Nagaad Network in Somaliland. |  |  |
| Private sector involvement: | Associations Somaliland Electricity Association (SEA) Somaliland Renewable Energy Association (SOMRENA) Renewable Energy private companies and organizations - Gollis Energy: - Kaafi Energy - Solar Land Africa: - Cadceed Maal. - SomEnergy Research & Consultancy. |  |  |
| Geospatial coordinates of project sites: |  |  |  |
| Financial Information |  |  |  |
| Project | at CEO Endorsement (US$) | at MTR (US$) |  |
| [1] UNDP | USD 750,000 | 112,007.6 |  |
| [2] MoEWR | USD 3,500,000 | 1,750.000 |  |
| [3] World Bank | USD 157,200,000 | 87,200.000 |  |
| [4]GEF Trust Fund grant | USD 3,276,147 | 342,870 |  |
| [5] SIDA | USD 10,000,000 | 8,500.000 |  |
| [Total] | USD 174,726,147 | 97,904,877.6 |  |

Project Description

The GEF-funded African Minigrids Program (AMP) National Child Project in Somalia is a medium-sized project (FSP) implemented by UNDP under the Direct Implementation Modality (DIM), with the Ministry of Energy and Water Resources (MoEWR) as the main executing partner. The Somalia project is part of the AMP as a programmatic approach and receives technical assistance from the AMP regional project, enhancing experience sharing among the different AMP national projects. Somalia has a high electricity tariff (estimated at USD 1/kWh) and a national electrification rate of 50.3% in 2023 which is low when compared to countries like Kenya and Ethiopia. The project aims to support access to clean energy by increasing the financial viability and promoting scaled-up commercial investment in minigrids in Somalia. It runs from November 2022 to November 2026, with a GEF grant of USD 3,276,147, UNDP TRAC resources of USD 750,000, and planned co-financing of USD 170,700,000. Key national partners include the Ministry of Energy and Water Resources (MoEWR), the National Energy Authority, Federal Government of Somalia, Electricity Service Providers (ESPs), the Renewable Energy Sector Association, private sector developers, Federal Member States and local communities, the Somali Bureau of Standards (SBS), Somaliland Quality Control Commission (SQCC), as well as universities, higher learning institutions and vocational training programs. The project is aligned with Somalia’s national development strategies and energy policies, emphasizing the country’s strong commitment to rapidly expand energy access, particularly in rural and underserved areas of the country. It is also aligned with Somalia’s national development strategies and energy policies, such as the National Transformation Plan with focus on expanding Somalia’s renewable energy sector, key strategic documents like the Optimized Cost Electricity Generation and Transmission Development Plan which is a 20-year roadmap to support long-term investment planning and donor coordination.

The project is structured into four components:

Component 1: Policy and regulation - improving the enabling environment for minigrids through the operationalization of national mini-grid policies, and regulation. This component also involves conducting techno-economic analyses, designing tools for tariff calculation, and strengthening the institutional capacity of the public sector. The key outputs of this component include the development of the national mini-grid policy and regulations covering tariff and licensing, consensus-building through broad stakeholder consultations on an economically or commercially viable mini-grid model of delivery. An analysis on De-Risking Renewable Energy Investment (DREI) and the formulation of a national digital strategy for mini-grids as well as the development of sector-wide regulations, technical codes and standards are also expected from the first component of the AMP Somalia project.

Component 2: Relates to Business Model Innovation which involves piloting innovative business models with key outputs such as the drafting of a Mini-grid Pilot Plan, the development of a comprehensive curriculum for solar and hybrid mini-grids and the establishment of a governance structure and operational guidelines for the Renewable Energy Sector Association to enhance coordination among private operators and developers.

Component 3: Scaled-Up Financing: This component aims to enhance the readiness of financial sector actors to invest in low-carbon mini-grid development. It also involves assessing planned and existing financial schemes, developing operational guidance, and offering training support to domestic financial sector stakeholders. Key outputs for Component 3 include: the initiation of financing mechanisms for mini-grid development, comprehensive mapping of funding opportunities, an analysis of current financing mechanisms and capacity building trainings for public and private sector stakeholders on mini-grid technologies, financing structures and financial modelling.

Component 4: Digital Transformation and Knowledge Management – this focuses on enhancing digitalization, monitoring, knowledge sharing and stakeholder networking in a bid to scale up mini-grid solutions. The outputs expected from this component comprise running an effective system of Monitoring and Evaluation (M & E), Quality Assurance (QA) and Knowledge Management (KM) building on the Digital Readiness Assessment and national digital strategy for minigrids. This will also involve cross-cutting activities like knowledge exchange, stakeholder capacity building and the reinforcement of linkages with international best practices to foster a sustainable and inclusive mini-grid market.

Overall, key outputs of the AMP Somalia project include delivery model development, DREI analyses, Digital Readiness Assessments, capacity building for institutional and private sector stakeholders, mini-grid pilot plans, curriculum development for solar and hybrid mini-grids, establishment of a renewable energy sector association, development of financing mechanisms, and robust monitoring and knowledge sharing systems.

Project Progress Summary

Government ownership of the project is assessed as strong, as it is anchored primarily through the active participation of the Ministry of Energy and Water Resources (MoEWR) which is the executing partner of the project, responsible for project implementation. The participation of some of the ministry’s staff as members of the Project Board, in strong cooperation with the UNDP representative also indicate a strong commitment to the transformation of the energy sector and rural electrification in general, and sense of ownership in the project. The National Electricity Authority (NEA) of the Government of Somalia is also actively engaged in the elaboration and development of energy sector regulations, technical codes and standards, as well as Electricity Service Providers (ESPs).  The AMP project has contributed to advancing national understanding of both the benefits and the limitations of minigrids by supporting access to clean energy, focusing on the digital transformation and institutionalization of ongoing initiatives, with a focus on expanding the adoption of photovoltaic energy technologies within Somalia.

Key early achievements highlighted in relevant documents from the project include the elaboration of the national Minigrid Policy and Regulations under Component 1 which established standards for tariff and licensing as well as the facilitation of broad stakeholder consultations. A DREI analysis and DRA were conducted as planned. To help facilitate capacity building within the context of Component 1 activities, an assessment on the institutional setup for rural electrification was conducted, which resulted in the identification of capacity building needs both technical, managerial and regulatory. Component two initiated the drafting of the Minigrid Pilot Plan and succeeded in carrying out a mapping exercise for the energy sector. The operationalization of the Pilot Plan and piloting of innovative business models to attract private investments in minigrids were both planned for 2025. Some progress has been made in identifying potential minigrid locations for the completion of feasibility studies. The project has so far initiated the analysis and development of financing mechanisms, and delivered capacity building activities to stakeholders from both public and private sectors (Component 3).

Stakeholder engagement has been frequently highlighted as necessary for the successful implementation of the project, and this has been so far ensured through consultations, stakeholder engagement activities and capacity building trainings and workshops throughout the implementation this far. This strong sense of engagement from stakeholders contributed in some of the success that the project has so far realized such as the development of the Minigrid Policy and Regulations, where through stakeholder consultations, a consensus could be reached on a commercially viable delivery model. Similarly, continuous stakeholder engagement was fundamental in the establishment of the governance structure and operational guidelines for the Renewable Energy Sector Association (RESA) under the project. The AMP Somalia project maintained external communication and visibility through social media outlets (including Facebook, Twitter and LinkedIn managed by the regional AMP project) and participation at the United Nations Framework Convention on Climate Change (UNFCCC) 29th session of the Conference of Parties (COP29) and at the AMP regional project-managed Community of Practice (CoP).

However, the project faced delays in its early days due to institutional conflicts between the Ministry of Environment and Climate Change (MoECC) and MoEWR, and leadership changes within the MoEWR soon after the inception of the project. As a result of this, the workplan for the first, second, and third quarters only got approved at the end of 2023 (during quarter 4) almost a year after its inception.  The project equally recorded delays in the pre-selection of the sites for the minigrid pilots.

Institutional and technical capacities have been strengthened commencing with a capacity needs and institutional setup assessment that permitted the project to identify the needs of the various stakeholders involved in rural electrification in Somalia, therefore guiding the capacity building process by ensuring that the activities are directly targeted to the identified technical, managerial and regulatory gaps. Capacity building has also been strengthened through the recruitment of national consultants to support the implementation of key activities such as the DREI analysis and DRA assessment, as well as the development of a comprehensive curriculum for solar and hybrid minigrid to be used for public educational purposes within university programs to help boost the labour market and support an effective management of minigrids in the country. However, there is a need for continuous capacity building throughout the project, as government officials need to be able to carry the project to its end. Equally, the project is required to enhance its gender-responsiveness by integrating specific and measurable targets into a gender action plan (GAP) which should be subject to tracking and reporting.

The GAP, developed at the preparatory phase of the project identified the key gaps in the status of men, women, boys and girls in terms of energy access as well as their roles and contributions in both the production and distribution of electricity. Gender considerations were therefore incorporated into the project document and activities designed to mainstream gender into the implementation of the project. However, there is still a need for more effort to be put to encourage women’s involvement and participation in decision-making and implementation of minigrid development activities.

Private sector engagement remains unclear at the time of this MTR, though steps have been taken to engage actors from the private sector. Such steps such as consultations with stakeholders leading to the establishment of a governance structure and operational guidelines for the Renewable Energy Sector Association (RESA) were expected to support private sector engagement in minigrid development and energy access expansion in general. Given that the private sector plays a pivotal role in rural electrification and minigrid development and expansion, its engagement will need to expand even beyond the project lifespan, hence continuous de-risking of this sector is encouraged.

In summary, the project has acted as a foundation putting in place the necessary policies, standards and regulations necessary to support financial viability and scaled-up investments in low-carbon minigrid, through successfully implemented activities such as the DREI analysis. The project experienced significant delays during its inception phase, though activities finally kicked off and are ongoing. The project will be a major addition to already existing initiatives to rural electrification, private sector engagement and technical and institutional capacity building in Somalia. At the time of this MTR, there is a need to accelerate project delivery so as to catch up with the implementation time lost due to delays. The priorities for the rest of the project include strengthening coordination and communication between the government, local communities and among relevant institutions, finalizing and adopting the policies and regulations already developed, continuous gender mainstreaming into project implementation, implementation of the minigrid pilots and support to private sector engagement, continuous capacity building for local operators and service providers and financial de-risking.

MTR Ratings & Achievement Summary Table

| Measure | MTR Rating | Achievement Description |
| --- | --- | --- |
| Project Strategy | N/A |  |
| Progress towards results | Objective Achievement Rating: Satisfactory (S) | The achievement of the objective is measured with the GEF mandatory core indicators. For indicator 1 (Greenhouse gas emissions mitigated), indicator 2 (Number of direct beneficiaries) and indicator 3 (Increase in installed solar PV capacity (MW) and battery storage (MWh), nine sites have been preselected by the government from which three sites will be selected through a competitive bidding process for the installation and construction of minigrids. The minigrid pilot plan is under finalization and procurement for service providers for the installation and construction of minigrid is planned towards the end of 2025. Indicators 1, 2 and 3 are each rated Satisfactory - their mid-term targets were set at zero. Indicator 4 (Number of local residents trained in different aspects of mini-grid development and operation disaggregated by gender (number of people) is rated Moderately Unsatisfactory as no household members have been trained on minigrid development and operation. |
|  | Outcome 1 Achievement Rating: Satisfactory (S) | Outcome 1 is rated as satisfactory as the achievement rating for indicator 5 (A minigrid delivery model to enable minigrid development is endorsed/adopted by the national government through a consultative process involving key stakeholders) and 6 (Number of policy derisking instruments for minigrid investments - whose development has been supported by the project - are endorsed/adopted by the national government) are rated as satisfactory, while the achievement of indicator 7 (Online tools for digital transformation of the mini-grid sector are selected and adopted through a consultative process involving key stakeholders) is achieved and rated as highly satisfactory. |
|  | Outcome 2 Achievement Rating: Satisfactory (S) | Outcome 2 is delayed and rated as satisfactory as indicator 7 (Number of minigrid pilots implemented that demonstrate a delivery model, cost-reduction measure(s) and/or productive use of electricity) is not at all implemented and the elaboration of the minigrid pilot plan is under finalization – the indicator is rated as moderately satisfactory, and the achievement of indicator 8 (Capacity of minigrid developers and/or operators is enhanced to implement innovative business models and incorporate cost-reduction levers in minigrid projects) is rated as satisfactory. |
|  | Outcome 3 Achievement Rating: Moderately Satisfactory (MS) | Outcome 3 is delayed overall and rated moderately satisfactory. The achievement of indicator 9 (Capacity of financial institutions is enhanced through training, knowledge sharing, and/or awareness raising events aimed at increasing the financial sector’s capacity to evaluate investments in minigrids) is rated Satisfactory while indicator 10 (Number of government or impact investor-supported financing mechanisms offering concessional finance for low-carbon mini-grids) is rated moderately unsatisfactory as no complementary funding instrument had been designed at MTR. |
|  | Outcome 4 Achievement Rating: Satisfactory (S) | Outcome 4 is satisfactory. The achievement of indicator 11 (A project digital strategy for the project is prepared and implemented by the PMU to contribute to project implementation and local minigrid market development) is rated highly satisfactory and 12 (Number of mini-grid pilot(s) sharing data on mini-grid performance with the regional project and other stakeholders following best practices and guidance provided by the AMP Regional Project) is lagging behind since the minigrids are yet to be constructed and commissioned – the indicator is rated as moderately satisfactory. |
| Project Implementation and Adaptive Management | Moderately Satisfactory (MS) | The project is implemented by UNDP in collaboration with MoEWR that supports project implementation through established annual letters of agreements (LoA). At the inception of the project, an institutional mandate conflict existed MoECC) and MoEWR which delayed the start of the project and establishment of the first loA. The project demonstrates a strong and weak gender balance across staff and governance structures (Project Board) respectively. Work planning is done in a manner consistent with project results, involving the establishment of annual workplans from the project’s multiannual workplan linked to the results framework. Relating to co-financing, the project exhibits gaps in the tracking of parallel co-financing from other donors, with a co-financing materialization rate at midterm of 57%. The project’s monitoring and evaluation system was found to be functioning well, and the M&E budget was assessed to be adequate. The Social and Environmental Prescreening Procedure (SESP) conducted for the project was assessed to be adequate with most targeted assessments and management plans to be conducted, elaborated and implemented during the construction of the minigrids. However, limited stakeholders were aware of the Grievance Redress Mechanism (GRM) of the project. The project’s reporting was aligned with the requirements of the Global Environment Facility (GEF) and external and internal communication of the project were assessed to be adequate. |
| Sustainability | Financial Risks to Sustainability Rating: Moderately Likely (ML) | A key project result with long-term financial considerations is the commissioning of the mini-grid pilots, which will need to remain economically sustainable beyond the life of the project. The AMP Somalia model builds on the country’s predominantly private-sector energy landscape, with mini-grids owned and operated by ESPs. Under the project, ESPs will receive results-based grant support to enhance their ability to operate profitably in peri-urban and rural areas. Working together, the selected ESPs and the NEA will establish cost-reflective tariffs that support financial viability. The pilot’s subsidy framework sets a target tariff of USD 0.35/kWh, and ESPs must demonstrate that their proposed business model can feasibly achieve this rate. To further enhance affordability and stabilize revenue flows, the project will promote productive uses of energy (PUE), enabling households and small businesses to generate additional income. Although the pilot shows promising potential to reduce tariffs from roughly USD 1/kWh to USD 0.35/kWh, it remains uncertain whether this reduced rate will be affordable for all consumers, particularly those not engaged in PUE. Overall, the financial risk to sustainability is assessed as Moderately Likely. |
|  | Socio-economic Risks to Sustainability Rating: Moderately Likely (ML) | The pre-selection of the sites for the pilots took into consideration security conditions, ensuring that pre-selected sites are secured. However, the volatility of the country continues to present a political risk to project implementation. Socio-economic risks to sustainability of the AMP project in Somalia identified by the MTR includes community perceptions and security-related challenges that may weaken trust, ownership, and long-term operational stability. Persistent misconceptions associating solar installations with fire hazards and livestock electrocution could hinder community acceptance and participation. To mitigate these risks, the effective implementation of the developed minigrid training curriculum offers an opportunity to strengthen local capacity, foster collaboration with academic institutions, and ensure that technical skills and knowledge are retained and applied beyond the project’s duration. |
|  | Institutional Framework and Governance Risks to Sustainability Rating: Moderately Likely (ML) | The project supported the development of minigrid policies for both Somalia and Somaliland, establishing a foundation for improved regulation and governance within the electricity sector. The project has also strengthened institutional capacity within Somalia’s energy sector. Its support led to the establishment of a dedicated Rural Electrification Unit within the Ministry of Energy, enhancing the government’s ability to address rural energy access and electrification challenges. In addition, the regulatory guidance provided through the AMP helped NEA to design and operationalize a licensing fee structure, marking progress toward a more formalized and regulated sector. Capacity development was further reinforced through specialized training for staff from both government institutions and private Energy Service Providers, with these skills expected to contribute to sector development beyond the project’s duration. However, high staff turnover within public institutions remains a concern, as skills and knowledge gained through the AMP may be lost if trained personnel move to other organizations. Given these dynamics, the institutional framework and governance risk to sustainability is assessed as Moderately Likely. |
|  | Environmental Risks to Sustainability Rating: Moderately Unlikely (MU) | The environmental risks to sustainability of the AMP Somalia relates to increasingly frequent extreme weather events, particularly flooding, which is projected to worsen under climate change. Flooding could damage key infrastructure such as generation units, distribution networks, and control systems—resulting in costly repairs, operational disruptions, and extended service outages. In addition, high wind conditions common in parts of Somalia pose further threats, including potential damage to mounting structures, reduced solar panel efficiency, and accelerated dust accumulation that increases maintenance demands. Unless climate adaptation and resilience measures are integrated into the design and installation of the minigrids, these risks could undermine community confidence in the system’s reliability and weaken prospects for future investment in productive energy use. |
|  | Overall likelihood of Sustainability: Moderately Likely (ML) | Overall, the sustainability of the AMP project in Somalia is rated as moderately likely, based on the ratings of environmental, financial, socio-economic, and institutional framework and governance risks to sustainability. |

Concise summary of conclusions

At mid-term, the AMP Somalia project is making reasonable progress toward sustainable rural electrification, putting the groundwork for minigrid expansion and rural electrification in general, by establishing policies and regulations, building capacity as well as strong partnerships and coordination between stakeholders from the government, public and private sector service providers. However, overlaps in the roles and mandates between two main ministries (MoEWR and MoECC) caused almost a year-long delay, coupled with prolonged consultations and procurement delays, which have slowed down project implementation and affected the level of achievement of some project outcomes. The need for private sector engagement cannot be over-emphasized. However, the low demand for electricity especially in rural and underserved areas of Somalia, coupled with the high level of poverty and high tariffs demanded by energy service providers (ESPs) resulting in a high level of risk associated with energy services and consequently limited access to financing for service providers have made it even more difficult to achieve a high level of engagement from the private sector.

Results and strengths: At mid-term, the AMP Somalia project has made meaningful progress in strengthening the enabling environment for renewable energy and preparing the groundwork for pilot mini-grid deployment. Key achievements include the development of core regulatory tools such as the mini-grid policy, licensing and tariff regulations, and the DREI techno-economic analysis along with substantial capacity building for public institutions and private Energy Service Providers. The establishment of the Rural Electrification Unit and the national mini-grid training curriculum further demonstrate strong institutional progress. At the time of the MTR, the projects minigrid pilot plan was being finalized which will pave the way for procuring the service providers who will be charged with the construction of minigrids within three locations out of the nine preselected sites.

Weaknesses: implementation has been slowed by early institutional conflicts that arose between MoECC and MoEWR over the entity to assume the role of the government counterpart for the implementation of the project. Delays equally stemmed from the preselection of the pilot sites for the minigrid pilots as the approach employed by MoEWR in the selection three sites was contested by UNDP based on the need to have more sites from which three sites will be selected through the competitive bidding process. While a gender analysis was conducted for the project and a gender action plan developed during the project preparatory phase, the document was lacking targets for the identified indicators, posing the tracking of the extent to which gender mainstreaming was achieved in the project challenging. At mid-term, the project team could provide figures of the amount of co-financing materialized from the different co-financiers, but the figures were lacking co-financing letters from the different co-financiers attesting to the materialized co-financing amount report – co-financing tracking represents an area of the project that will benefit from improvement.

Overall, the project is moderately on track, with strong foundational results but requiring accelerated implementation. A 12-month no-cost extension is recommended to ensure completion of the pilot mini-grids, consolidation of policy gains, and full realization of expected outcomes.

Recommendation Summary Table

| No. | Recommendation | Responsibility |
| --- | --- | --- |
| Corrective actions for the design, implementation, monitoring, and evaluation of the project |  |  |
| 1. | Organize more frequent board meetings to monitor progress and make any updates to the project workplans as needed. Coordination meetings should be organized more frequently to discuss any issues affecting the project and address them in a timely manner | PMU and MoEWR |
| 2. | Enhance gender responsiveness during the second half of project implementation: The GAP should be updated to include specific, measurable targets and baselines aligned with existing indicators. These targets should capture both quantitative and qualitative dimensions of gender equality—such as the number and proportion of women participating in training, consultations, employment opportunities, and decision-making processes related to minigrid development and management | PMU |
| 3. | Strengthen application of the Grievance Redress Mechanism: To enhance accountability and ensure effective stakeholder engagement, the GRM should be actively publicized and mainstreamed across all project activities during the second half of implementation. | UNDP, PMU |
| Actions to follow up or reinforce initial benefits from the project |  |  |
| 4. | Strengthen Institutional Capacity for Delivery of the Minigrid Curriculum through Strategic Partnership: it is recommended that the project establish a partnership with the Res4Africa Foundation to support the implementation of the curriculum. Res4Africa has demonstrated experience in developing and delivering renewable energy and minigrid training programs in countries such as Eritrea and Mozambique, providing both technical content and instructor training. Through this collaboration, Res4Africa could assist in training trainers, and building institutional competence within targeted vocational and higher education institutions. | PMU, UNDP, MoEWR |
| 5. | Strengthen Tracking and Reporting of Co-Financing Contributions: It is recommended that the project establish a systematic mechanism for tracking and reporting on co-financing commitments made by development partners and other contributors during the design phase. While several donors and stakeholders had pledged financial and in-kind support to complement GEF resources, there is currently no structured process to monitor, verify, and document the actual realization of these contributions. | UNDP and PMU |
| 6. | Request a 12-Month No-Cost Extension to Ensure Timely and Effective Delivery: It is recommended that the project formally request a 12-month no-cost extension to compensate for the implementation delays experienced during the inception and early operational phases | PMU and UNDP |
| Proposals for future directions |  |  |
| 7. | Organize pre-bidding meetings to attract qualified bidders: To broaden participation and attract capable bidders, the project should consider organizing a roadshow and a pre-bidding meeting (either virtual or in-person) during the procurement stage. These outreach efforts would help publicize opportunities, clarify eligibility and technical criteria, and encourage competitive, well-prepared proposals—thereby reducing procurement delays and enhancing the quality of submissions | UNDP |
| 8 | Enhance Community Awareness and Sensitization on Minigrid Safety and Benefits: it is recommended that the project implement a structured community sensitization and outreach program in all pilot sites. This program should aim to build understanding and trust around minigrid technologies by providing clear information on system safety features, proper installation standards, and operational protocols. Sensitization activities should be participatory and culturally appropriate, involving community leaders, elders, women’s groups, and youth representatives to ensure inclusivity and local ownership. | UNDP and PMU |
| 9 | Strengthen Climate and Environmental Resilience of Minigrid Infrastructure: it is recommended that the project integrate climate-resilient design and environmental risk management measures into the construction and operation phases of all installations. | UNDP and PMU |
| 10. | Expedite the Procurement Process for Minigrid Implementation: To ensure timely delivery of outputs in the second half of the project, it is recommended that UNDP expedite the procurement process for selecting qualified service providers for the design, construction, and installation of the three-pilot solar minigrids. | UNDP |

# INTRODUCTION

## Purpose and objective of the Mid-term Review

The midterm review (MTR) is a critical independent review to assess the project’s advancement toward its defined objectives and outcomes. Its purpose is to detect early indicators of success or challenges, recommend necessary adjustments, and ensure the project remains aligned with its strategic goals given current circumstances. As a mandatory process for medium-sized projects (MSPs) financed by the Global Environment Facility (GEF), with a budget over USD 2milion, the MTR primarily monitors obstacles hindering progress toward the targeted higher-level impacts outlined in the Project Document. By focusing on forward-looking, solution-driven analysis, the MTR helps guide corrective measures that support the project’s trajectory toward achieving its intended and sustainable results. Moreover, a comprehensive MTR provides a valuable foundation for the subsequent Terminal Evaluation (TE), enhancing the overall project appraisal process.

## Scope and Methodology

### Scope of the MTR

The MTR aims to provide an independent external assessment of the project’s progress at its midpoint, offering feedback and recommendations to the Government, UNDP, and other stakeholders. The review evaluates the extent to which the project’s planned outcomes align with actual achievements and examines the contribution of these results to the overarching project objectives. It also assesses the efficiency and effectiveness of project management, considering quality, timeliness, cost-effectiveness, and the processes involved in delivering outputs and impacts. The review addresses challenges and underlying causes for any shortfalls in target achievements. Key aspects covered include project design and development, stakeholder engagement and ownership, implementation arrangements, financial management and co-financing, gender mainstreaming, sustainability, and adaptive management to provide a comprehensive appraisal of the project.

### Methodology

The methodology for the MTR was designed in accordance with the terms of reference  (Annex I) and follows the guidance provided by the UNDP Handbook on Planning, Monitoring, and Evaluating for Development Results, as well as the UNDP/GEF Guidance for Conducting Midterm Reviews of UNDP-supported, GEF-financed projects. An evaluative matrix (Annex II) was developed to structure the review process by defining key evaluation questions related to the project’s strategy, progress toward results, implementation arrangements, sustainability, and other relevant thematic areas. A participatory approach was employed for the MTR, involving the project stakeholders in all stages of the evaluation – inception (inception meeting and review of the inception report), primary data collection (stakeholder consultation) and reporting (presentation of preliminary findings and review of the draft MTR report).

Data collection was conducted through a mixed-methods approach, combining the following main elements:

- Desk Review: A comprehensive review of project documentation was conducted, including the Project Document, results frameworks, progress reports, minutes from project meetings, and other relevant materials. The complete list of reviewed documents is provided in Annex III.

- Stakeholder Consultations: Semi-structured interviews and consultations were carried out with key informants, including members of the project management unit (PMU), government counterparts, partner organizations, beneficiaries, and other stakeholders. The list of interviewees, the MTR itinerary and the data collection tools are presented in Annex IV, Annex V and Annex VI respectively.

- Data Triangulation: Findings from different data sources were cross-checked to ensure the validity and reliability of conclusions. The evaluators also used researcher triangulation, discussing each finding among them to ensure a balanced and well-rounded analysis.

Given the targeted nature of the AMP Somalia project, a purposive sampling approach was applied to ensure that the evaluation engaged stakeholders directly involved in, or significantly affected by, project implementation. The evaluation team relied on the official stakeholder list provided by the Project Management Unit (PMU), which included representatives from government institutions, Energy Service Providers (ESPs), private-sector partners, and UNDP personnel. Stakeholders were selected based on their roles, responsibilities, and expected contributions to project outcomes, ensuring that information was gathered from individuals with firsthand knowledge of project activities, achievements, and challenges. This approach allowed the evaluation to capture a diverse set of perspectives that are most relevant to understanding project performance, implementation dynamics, and emerging results at mid-term.

The review period covered activities from the project starting through the end of June 2025. The evaluation process involved consultation with key stakeholders for feedback, debriefing, and finalization of the MTR report, incorporating provided comments (as per the audit trail presented as a separate document - Annex XI) to ensure a participatory and transparent review.

A gender-sensitive approach was integrated throughout the evaluation process in line with GEF and UNDP evaluation guidelines. The methodology ensured that gender considerations were systematically incorporated into data collection, analysis, and validation. During stakeholder consultations and interviews, efforts were made to include both women and men representatives from project beneficiaries, government counterparts, and implementing partners to capture diverse perspectives and experiences. Where available, gender-disaggregated data were reviewed to assess participation, benefits, and impacts for women and men within project activities. The evaluation also examined the implementation of the project’s Gender Action Plan, including progress toward gender indicators and the extent to which gender equality and women’s empowerment were mainstreamed into project design, decision-making, and outcomes – recommendations were provided to address identified gaps. This approach enabled the evaluation to provide balanced, inclusive, and evidence-based findings on gender responsiveness and effectiveness.

Data analysis

Data collected through document review and key informant interviews (KIIs) were systematically analyzed using a mixed-methods approach combining qualitative and quantitative techniques.

1. Qualitative Data Analysis:

- Interview transcripts were analyzed using thematic content analysis.

- Responses were coded and grouped according to the evaluation criteria (relevance, effectiveness, efficiency, sustainability, and adaptive management) and key evaluation questions outlined in the MTR Terms of Reference using a data matrix template.

- Emerging themes, patterns, and divergences were triangulated across stakeholder groups (government, private sector, beneficiaries, project team, and project partners) to ensure consistency and validity of findings.

2. Quantitative Data Analysis:

- Quantitative information (e.g., outputs achieved, financial data, and indicator progress) was extracted from project monitoring reports, the Project Implementation Reports (PIR)s, and progress updates.

- Data were processed and analyzed using Microsoft Excel, generating simple statistics (percentages) to assess performance against project targets and timelines.

- Indicator-level analysis was conducted to measure progress toward outcome and output targets, as defined in the project’s Results Framework.

3. Triangulation and Validation:

- Evidence from different data sources and methods was triangulated to validate findings and ensure robustness of conclusions.

- Preliminary findings were validated with project stakeholders during debriefing sessions to verify accuracy and contextual relevance before finalization of the draft MTR report.

## Limitations to the MTR

The selection of interviewees was coordinated by the project management unit and depended on stakeholders’ availability and willingness to participate, which may have resulted in some key individuals being unavailable for consultation despite repeated requests. This dependency may have implications for the completeness of stakeholder perspectives captured. Some stakeholders (e.g. National Electricity Authority, Ministry of Energy of Somaliland, Somali Green Energy Association, Somaliland Electricity Association and financial institutions – Shurako, Kube Energy and Dahabshil Bank) were not responsive to the evaluators request for interviews during the in-country mission.

While the project team provided details on the amount of co-financing materialized, co-financing letters confirming the level of materialization of co-financing from co-financiers was not shared with the evaluators. While the co-financing amount materialized shared by the project team was used in the assessment, the lack of the letters rendered it challenging for the evaluators to verify the level of materialization of co-financing reported. Project documents reviewed for this MTR include: project document (ProDoc); project financing reports; Stakeholder Engagement Plan; Project delivery reports; Project Implementation Reports; indicator progress reports; de-risking renewable energy investment (DREI) analysis reports; DREI workshop reports; financing workshop reports; pilot study reports; minigrid curriculum reports; workshop reports; terms of references; inception workshop report; capacity building training reports; stakeholder consultation reports; and LoA among others.

Despite these limitations, the MTR team mitigated challenges through constant follow-ups with stakeholders with whom interviews could not be secured during the in-country mission and virtual interviews were secured for some of the stakeholders who were non-responsive at the time of the mission. Equally, the evaluators used extensive triangulation of the available data sources, including documents, interviews, and supplementary internet research to mitigate the limitations. The inclusion of a national consultant with in-depth contextual knowledge further enhanced the reliability and validity of the findings.

## Structure of the MTR Report

The report is structured as follows: Section 1 presents the Executive Summary of the evaluation report followed by Section 2 which is the Introduction.  Section 3 offers background information and essential description of the project, including the targeted barriers and strategies, project arrangements, key stakeholders, and an overview of the resources utilized. Section 4 presents the main findings of the midterm review, organized by project strategy, progress toward results, project implementation and adaptive management, and sustainability. Finally, Section 5 provides the conclusions and recommendations.

# PROJECT DESCRIPTION AND BACKGROUND

## Development context: environmental, socio-economic, institutional, and policy factors relevant to the project objectives and scope

This section contains a brief description of the project development context. It draws from the project document, which contains more extensive and detailed information.

### Environment, and Socio-Economic context

Somalia is located in the eastern part of Africa with a population of approximately 19 million inhabitants as of 2024, most of which are nomadic and semi-nomadic pastoralists. This population is projected to be double or more by the year 2050. The country’s economy is affected by the pressure on natural resources caused by widespread land degradation from deforestation, soil erosion, overgrazing, over-exploitation among others as well as the obvious impacts of climate change such as flooding, droughts and cyclones, to which Somalia is prone. The level of greenhouse gas (GHG) emissions is currently low, estimated at about 53 MtCO2eq, accounting for less than 0.03% of the world’s GHG emissions. These emissions emanate mostly from the Agriculture, Forestry and Land-use sectors, worsened by the high level of poverty affecting most of the population, who rely on the exploitation of natural resources for their livelihood.

Access to services among the Somalia population is limited, as much of the energy infrastructure had been destroyed back in the 1990s when the country experienced a collapse of their government and ensuing conflicts. This resulted in electrification rates varying widely between the urban dwellers and the rural dwellers. It is estimated that in 2023, about 50.3% of the population of Somalia have access to electricity with 79% and 23.9% of the urban and rural population respectively having access to electricity. Though the government is making efforts at increasing its electricity supply and expanding access to energy for all, it had been reported that a sizeable portion of the population of the country had access to electricity in 2020. Some progress has been recorded as the rate has now increased to approximately 49%, showing progress on the country’s goal of expansion of electricity services. However, reliability and affordability are major concerns when it comes to electrification in the Somalian context, with unit prices for electricity reportedly among the highest among its neighbours and Africa in general (ranging from 50 to 125 cents per kWh) and inefficient and low-quality supply due to the use of old electricity equipment and reliance on conventional energy sources such as diesel, charcoal and firewood which are the primary source of electricity.

Somalia lacks a national transmission and distribution network hence the private sector plays a major role in the supply of electricity mainly from ESPs whose supply come mainly from diesel generators. One of such ESPs is the Benadir Energy Company (BECO), which is the largest electricity utility company supplying the country’s capital Mogadishu. It has been reported that there are no national grids in the whole country, and this therefore highlights the importance of the private sector in the development of a more reliable and sustainable energy supply. The ESPs face the challenge of limited access to financial resources from both government and commercial banks, especially as minigrid development is often seen as uncertain in terms of its commercial viability. Photovoltaic solar minigrid deployment remains an issue given the risks of its return on investment and uncertainty attached to it. Foreign manufacturers think of Somalia as a risky milieu for business given the level of political instability and conflict there. This scares investments from both public and private sector companies coupled with the fact that the majority of the population already face challenges paying for the high cost of energy that is common in Somalia.  Electrification challenges include the lack of comprehensive regulations, standards and adequate quality controls, worsened by weak enforcement and regulation from the government, insufficient technical skills and workforce for an improved generation, transmission and distribution of electrical power.

### Institutional and policy factors

The Federal Government of Somalia is making continuous effort to expand the energy sector by outing in place relevant policies and regulations to guide the planning and development of minigrids and their delivery. The National Energy Policy of 2018 and the Energy Act of 2023 stand as the main document governing the energy sector, focusing on a transition from conventional or dirty sources of energy to renewable energy, while building on the abundant solar and wind energy resources that Somalia possesses. The emphasis of the policy was also on increasing or expanding access to electricity for Somalian households and businesses in both rural and remote areas and establish a legal and regulatory foundation for the energy sector on licensing, tariff setting and compliance with the standards. Having an enabling environment will help in attracting private sector engagement as well as foreign and local investments.

Somalia’s National Transformation Plan (NTP) 2025-2029 sets out a transformative agenda across four strategic pillars: (1) Transformational Governance; (2) Sustainable Economic Transformation; (3) Social and Human Capital Transformation; and (4) Environment and Climate Resilience. Under Pillar 4: Environment and Climate Resilience, the plan emphasizes sustainable management of natural resources, climate-resilient infrastructure, and the promotion of renewable energy and expanded access to electricity. Specifically, the NTP includes a target to increase national electricity coverage from about 69.1% to approximately 80% by 2029.

The Somaliland Energy Policy of 2010 and the Somaliland Electrical Energy Act (2016) developed by the Ministry of Energy and Minerals (MoEM) aimed at meeting the energy needs of the people in a cost-effective manner while promoting sustainable and renewable energy sources and supporting economic development. Their goal is to create a legal and regulatory framework for the country.

Somalia’s third Nationally Determined Contributions (NDC 3.0), submitted in June 2025, places strong emphasis on both mitigation and adaptation across sectors including energy, land use and forestry, transport, waste and agriculture. Under the Energy sector, while the document identifies that the current share of emissions from energy is relatively low compared with agriculture and land use, the proposed emission cut of 50% (3.24 MtCO₂e) in the sector is proportionately the highest of all sectors. Targeted mitigation initiatives in the energy sector includes: development of solar and wind energy; sustainable charcoal production with improved kiln technology; promotion of improved cookstoves and energy-efficient appliances; small scale solar lighting solutions; promoting clean cooking including use of liquified petroleum gas (LPG) to replace biomass in domestic energy; increasing access to modern energy systems and enhancing energy efficiency; and solar powered irrigation systems.

As of 2023, the national electrification rate of Somalia was estimated at 50.3%, lower when compared to other African countries especially its neighboring countries Kenya (76.2%) and Ethiopia (55.4%), with the main source being diesel-generators. To be able to achieve the government’s commitment of 80% electrification by 2029 as per the NTP 2025-2029, an energy sector development partners coordination platform was established of which UNDP/PMU is a member and the platform brings together development partners financing and implementing several projects and initiatives, including:

- Somalia Energy Sector Recovery Project (ESRP) (US$150 million) – 2022-2026

- Accelerating Sustainable and Clean Energy Access Transformation (ASCENT) in Somalia (US$100.0 million), financed by the World Bank (2023-2028)

- Horn of Africa Regional Power System Transformation Project (HoA RPSTP) (US$250.0 million) – 2024-2028

- Households’ Access to Renewable Energy and Advanced Cooking Technologies- HAREACT (USD 7.65 million) – 2022-2026

- Repair/Expansion of Bosaso Power Grid and Strengthening Institutions in-charge of Energy (USD 22 million)

- Next Generation of the UN Joint Program on Charcoal Reduction and Alternative livelihoods (PROSCAL) “Building Climate Resilient Communities and Sustainable Ecosystems in Somalia

Before the inception of the AMP project in Somalia, the country was served by privately owned and operated diesel-powered minigrids for all its electricity needs, especially in the urban areas. The project therefore plays a fundamental role in expanding energy access especially for underserved rural areas, while supporting the transition to renewable energy sources of energy and economic growth in general. This will be a significant add-on to the existing initiatives the government is implementing through the MoEWR with the support of other international development partners.

## Problems that the project seeks to address: threats and barriers targeted

Somalia aims to achieve 80% electricity access by 2029, building on continuous progress already made in ongoing projects and initiatives geared towards minigrid development and national electrification in general which has improved the electrification rate from 35% to about 50%. This success has also been realized thanks to the coordination of the MoEWR who has the mandate to manage minigrids licensing and regulations until the Energy Regulatory Commission goes fully operational. Equally, the NEA established under the Energy Act is now operational although not at full capacity and has been leading the development of key regulatory instruments, including tariff and licensing frameworks, with technical support from the AMP project. The project is making progress by increasing access to energy for some areas that were underserved before now, yet electrification rates are still not even between the urban and rural areas, due to high rates charged for electricity by the private providers, in addition to poverty. It is however expected that by the end of the project, this disparity would have been closed to a larger extent.

Minigrids are therefore a more viable option for electricity expansion in Somalia, to help bridge the gap in terms of access between the urban and rural areas, particularly areas that are inaccessible. The AMP project seeks to increase the financial viability of the minigrid sector, thus making electricity more sustainable, reliable and affordable to all, especially in areas that face economic barriers to energy access. Given the efforts and initiatives that the Somalian government in collaboration with other development partners have in place as policy and regulation to guide minigrid expansion, its development has been noticeable and continues to improve. The regulatory framework and standards have advanced and are making progress through consultations and national dialogues with relevant partners and stakeholders from the public and private sectors.

Barriers to scaling and sustainability of minigrids include:

Financial viability: The commercial viability of minigrids faces the challenge of high poverty level in rural areas and the consequent inability of consumers to pay for the high cost of electricity that service providers offer driven largely by reliance on diesel-based generation, which results in elevated tariffs due to fuel and maintenance costs. The introduction of solar minigrids and hybrid systems presents a significant opportunity to reduce diesel consumption, lower generation costs, and ultimately make electricity more affordable. However, the key bottleneck lies in the high upfront capital investment required to establish solar or hybridized systems, coupled with limited access to long-term financing and credit guarantees for private developers.

Private sector participation: Private sector involvement in Somalia’s energy sector is extensive, with local ESPs driving most electricity generation, distribution, and retail operations in the absence of a national grid. Many of these private actors are vertically integrated and maintain close linkages with local financial institutions, which has supported the rapid, market-driven expansion of electricity access in urban and peri-urban areas. However, despite this strong domestic presence, the sector continues to face significant barriers to scaling, including limited access to international finance, regulatory uncertainties, and high perceived investment risks. These factors constrain the ability of local ESPs to attract external capital, modernize infrastructure, and expand services to underserved and rural communities.

Institutional coordination: The institutional coordination of minigrid development is led by the Ministry of Energy and Water Resources and the NEA. MoEWR ensures that supportive policies are formulated to guide the process of minigrid development, supports collaboration among institutions and stakeholders and supports national planning while the NEA oversees the electricity sector by ensuring that ESPs are in compliance and operate efficiently. Private sector engagement, and the lack of a clear institutional setup with clearly defined roles between the government and other actors remains a challenge in meeting the intended targets of the minigrid sector.

Limited access of ESPs to financial incentives: The ESPs in Somalia’s minigrid sector find it hard to access funding, as minigrid investment is perceived to be risky. Given the high cost of electricity, consumers find it hard to pay and therefore minigrids are not a very profitable venture to investors.

Limited capacity on government and institutions: The government and other institutions involved lack the capacity to operationalize and enforce the policies, standards and regulations established.

## Project Description and Strategy

### Project objective, outcomes and expected results

The AMP national child project in Somalia is a GEF-funded  MSP project. The project is executed under UNDP’s Direct Implementation Modality (DIM), with the MoEWR serving as the main executing partner. UNDP is the implementing agency responsible for supporting implementation, ensuring financial oversight, delivering outputs as per the work plan, and ensuring cost-effectiveness. The Project Board provides strategic guidance and oversees the project's alignment with national priorities and GEF objectives. As stated in the ProDoc, the project objective is to: "Support access to clean energy by increasing the financial viability and promoting scaled-up commercial investment in low-carbon minigrids in Somalia with a focus on cost-reduction levers and innovative business models."

The project has four main sets of expected results. Under the first component, the project focuses on establishing an enabling environment for minigrid development by operationalizing the existing minigrid policies and regulations and conducting techno-economic analyses as well as supporting the institutional capacity of the minigrid public sector. The second component will carry out piloting of minigrid projects, explore innovative business delivery models, and build capacity for minigrid industry associations and private operators and developers. The third component will develop operational guidelines for existing financing mechanisms and training for the local financial sector actors. Lastly, the fourth component will ensure effective Monitoring and Evaluation, Quality Assurance and Knowledge Management systems.

The project is structured in four components, consisting of the following outputs:

Component 1: Policy and Regulation

Outcome 1: Stakeholder ownership in a national minigrid delivery model is advanced, and appropriate policies and regulations are adopted to facilitate investment in low-carbon minigrids.

- Output 1.1: An inclusive national dialogue to identify mini-grid delivery models is facilitated, clarifying priority interventions for an integrated approach to off-grid electrification.

- Output 1.2: Mini-grid DREI techno-economic analyses carried out to propose most cost-effective basket of policy and financial de-risking instruments and contribute to AMP Flagship Report on cost reduction.

- Output 1.3: Mini-grid policies and regulations, including tariff model and incentives, are operationalized through digital transformation support, in collaboration with the authorities and other development partners.

- Output 1.4: Institutional setup for rural electrification assessed and supported, and institutional capacity building provided on technical, managerial, and regulatory issue.

- Output 1.5: Quality standards for solar and hybrid mini-grid components domesticated, and institutional capacity of Somali Bureau of Standards (SBS) and Somaliland Quality Control Commission (SQCC) strengthened.

Component 2: Business Model Innovation with private sector engagement

Outcome 2: Innovative business models based on cost reduction operationalized, with strengthened private sector participation in low-carbon minigrid development.

- Output 2.1: Pilot(s) developed using innovative business models through calls for proposals based on lessons learned from the operationalization of the SREF under ESRES2 and the results of the geospatial mapping under SEAP.

- Output 2.2: Public programmes (apprenticeships, certificates, university programs) to develop competitive, skilled labor market in the design, O&M, and management of solar and hybrid mini-grids, including technical training on the utilization of online tools for performance monitoring, consumption tracking and billing.

- Output 2.3: Support provided to establish, grow and capacitate national industry associations for private sector developers and ESPs.

Component 3: Scaled-Up Financing

Outcome 3: Financial sector actors are ready to invest in a pipeline of low-carbon mini-grids and concessional financial mechanisms are in place to incentivize scaled-up investment.

- Output 3.1: Design support, including development of operational guidance, for a complementary funding instrument through which the diaspora and small investors can participate in existing financing mechanisms that have been introduced by other development partners to facilitate finance for vetted mini-grid projects.

- Output 3.2: Domestic financial sector capacity building on business and financing models for mini-grids.

Component 4: Digital, Knowledge Management (KM) and Monitoring and Evaluation (M&E)

Outcome 4: Digital and data are mainstreamed, across stakeholders, into local mini-grid market development. Increased knowledge, awareness and network opportunities in the mini-grid market and among stakeholders, including benefitting from linkages to international good practice.

- Output 4.1:  A Project Digital Strategy is developed and implemented, including linkages to and following guidance from, the AMP Regional Project.

- Output 4.2: A ‘Mini-grids Digital Platform’ implemented to run tenders and manage data from pilot(s), and to support mini-grids scale-up and cost-reduction.

- Output 4.3: A Quality Assurance and Monitoring Framework (QAMF) for measuring, reporting and verification of the sustainable development impacts of all mini-grid pilot(s) supported, including GHG emission reductions, is adopted and operationalized based on standardized guidance from the AMP Regional Project.

- Output 4.4:  M&E and Reporting, including (i) Conducting inception workshop and preparing report, (ii) Ongoing M&E, (iii) Mid Term Evaluation and (iv) Terminal Evaluation

- Output 4.5: Engage with the AMP Regional Project, including, but not limited to, via (i) Participating in Communities of Practice (CoPs), and (ii) Capturing and sharing lessons learnt.

The project officially commenced on 13 December 2022 with the signature of the Project Document, and implementation began with the inception workshop held on February 12th - 13th 2023. The project is scheduled for completion by 30 November 2026. It is a climate change mitigation project under the GEF Africa Minigrids Program, with GEF grant funding of USD 3,276,147 and UNDP TRAC resources of USD 750,000. Additionally, USD 170,700,000 in co-financing is planned to be provided by the MoEWR  and other development partners, bringing the total project cost to USD 174,726,147.

### Description of field sites

The field sites for the AMP national project in Somalia came from the three geographic zones including Jubaland, Galmudug and Northeast states each of which had three selected field sites, shortlisted by the government of Somalia.  Within each geographical zone, three towns from each state are for electrification. These states are shown below:

- Jubaland State: 1. Dhobley; 2. Afmadow; 3. Diif

- Northeast  State: 1. Buhoodle; 2. Lascanood; 3. Xudun

- Galmudug State: 1. Hobyo; 2. Adado; 3. Guriceel

The selection of pilot sites for the Somalia AMP mini-grid project will follow a competitive, ESP-led approach. The Government of the Federal Republic of Somalia requested UNDP to distribute the funds to three geographic areas equally. These three areas have been selected by the government, considering the political stability of the country in a politically sensitive environment. As UNDP can only allocate budget under a competitive procedure, and as any existing ESP on site has an advantage over third-party ESPs, the competitive component will be introduced through the selection of three sites per geographic area. Each geographic area with its three sites is therefore forming a LOT. Only one of these three sites per geographic area will benefit from the UNDP AMP grant funding.

An ESP or consortium of ESPs may select sites from the list of three sites per LOT. There are three LOTs with $665,032 grant allocated to each LOT. Only one site out of the three sites per LOT will be supported with the allocated funds. ESPs are to select their preferred site out of the list of sites to ensure site selection aligns with ESPs’ operational capacity, market intelligence, and strategic business interests, leveraging existing infrastructure and synergies. Therefore, at least three bidders are expected to bid per LOT. This is considered sufficient competition to achieve minimum concessionality.

UNDP AMP was informed that most of the pre-selected sites have several smaller ESPs. Each of these ESPs may bid on its own, but a consortium of ESPs working together to achieve economies of scale have higher chances to be selected as the winning bidder. This is in alignment with the policy of the Federal Government of Somalia which encourages ESPs to merge, achieve economies of scale, reduce their ongoing cost and eventually reduce tariffs while increasing reliability of supply.

## Project Implementation Arrangements

Key government institutions engaged in the project include the MoEWR as the lead entity, the Ministry of Energy and Minerals (MoEM in Hargeisa), MoECC, Puntland State Authority for Water, Energy and Natural Resources (PSAWEN), Somali Bureau of Standards (SBS) and Somaliland Quality Control Commission (SQCC), as well as the regulators NEA and the Energy Regulatory Commission (ERC) for Somaliland. Additional engagement includes civil society organizations, private sector developers, academic institutions, and local authorities.

The Project Board, or Project Steering Committee (PSC) includes the UNDP Somalia Resident Representative (also known as the Project Executive), GEF Operational Focal Point and MoEWR. The Project Board was established during the project’s inception phase with the role of overseeing project development, governance and Monitoring and Evaluation throughout the project’s implementation. Its first board meeting was held in June 2025, during which the annual workplan for 2025 and the revised timeline for the Minigrid Pilot Plan were both approved.

A Project Technical Committee (TC) has been established to provide strategic technical oversight and ensure alignment of project activities with national policies and priorities. The Lead Technical Advisor is responsible for providing overall technical guidance and management support to the project, ensuring compliance  with equipment procurement, and deliverables are aligned with the standard procedures. As per the ProDoc, the PMU was meant to include the following: Project Manager, Finance Officer,  and a Monitoring and Evaluation (M&E) Officer and Lead Technical Advisor. However, at MTR, engagement with the project team at UNDP revealed that the PMU is composed of a Project Manager and Project Associate with support provided by other portfolios within the UNDP CO such M&E and finance. The Technical Committee meets more frequently and has the responsibility of looking into the technical aspects of project implementation.

The day-to-day implementation of the project is managed by a PMU under the supervision of a Project Manager based within the UNDP Somalia Country Office who ensures that the project is well managed, including supervision of project staff, consultants and sub-contractors and the mobilization of all project inputs.  The Project Manager is responsible for planning project activities, monitoring progress against approved workplans, coordination of project events, elaboration of terms of references for contractors, monitoring project financial resources, conduct progress reporting, submit financial reports, manage and monitor any project risks, perform work plan revisions, monitor results framework, prepare PIRs and track progress among others. He is supported by a Project Accountant or Finance Officer.

The UNDP Country Office in Somalia, provides ongoing project management support, quality assurance, risk management and compliance support throughout the project cycle. This multi-level governance structure is designed to foster national ownership, ensure inclusive stakeholder inclusiveness, and enable adaptive management throughout the project implementation period. Further quality assurance and oversight is provided by the Regional Technical Advisor in the UNDP Regional Hub while the Regional AMP project provides technical support in the implementation of the Somalia AMP project.

## Project timing, milestones and total resources

Table 1: Project timeline and key milestones

| Timeline | December 19, 2019 | January 19, 2022 | December 13, 2022 | February 13, 2023 | March 22, 2023 | October, 2025 | December 13, 2026 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Milestones | PIF and PPG approved | Full project approved (CEO approval) | ProDoc signed; Official project start | Inception workshop | Date of first disbursement | MTR report | Expected date of operational closure |

The total financial resource for the project is USD 174,726,147 including USD 4,026,147 of UNDP and GEF resources administered by UNDP. A disaggregation of the budget administered by UNDP across the PMU and the project components is presented in Table 2.

Table 2: Total project budget (ProDoc)

| Project Component | Budget (USD) |
| --- | --- |
| Component 1: Policy and Regulation | 614,425 |
| Component 2 : Business Model Innovation with Private Sector Engagement | 1,978,340 |
| Component 3: Scaled-up Financing | 266,378 |
| Component 4: Digital, Knowledge Management and Monitoring and Evaluation | 502,497 |
| Project Management | 176,007 |
| Total | 4,026,147 |

## Main stakeholders

Table 3 Categories of project stakeholders and institutions

| Stakeholder category | Institutions |
| --- | --- |
| Implementation partner | UNDP Country Office |
| GEF Operational Focal Point | Ministry of Environment and Climate Change |
| Government | Directorate of Environment and Climate Change, Office of the Prime Minister, Government of Somalia Ministry of Energy, and Water Resources Ministry of Environment and Climate Change National Electricity Authority Ministry of National Education Puntland State Authority for Water, Energy and Natural Resources (PSAWEN) Ministry of Energy & Minerals (MOEM) Ministry of Environment and Rural Development (MOERD) Somaliland National Energy Commission (SNEC) Somaliland Ministry of Trade, Industries and Tourism Local Governments |
| Private sector | Blue Sky – Mogadishu Muqdisho Power – Mogadishu Badhan Electricity Company (BECO) – Somalia – Mogadishu Delta Engineering – Mogadishu Dayax Electric – Beledwyne, Hirshabelle Galgaduud Electric Company – Dhusamareeb, Galmudug JESCO – Kismayo, Jubaland NECSOM – Garowe Tesco – Garowe Sunway Som Power Company – Bosaso Beco-Baydhabo – Baidoa, South West Somaliland Electricity Association (SEA) Somaliland Renewable Energy Association (SOMRENA) |
| Mini-grid ESPs | SomPower – Hargeisa, Gebiley and Wajale Horn Electricity Company (HECO) – Burao Telesom Electric Company (TEC) – Hargeisa, Borama, Odweiyne, Gebiley, and Buhodle Aloog – Borama LESCO – Las’anod SEPCO – Erigabo BEDER – Sheikh, Ainabo, and OOG TAYO electric – Berbera Badhan Electric Company – Badhan Abdaal Electric – Abdaal Salaxley Power Station – Salaxley Iftin Electric Company Baligubadle Electric – Baligubadle Gafane Electric – Hargeysa National Electric Company (NEC) – Hargaysa Mohamed Ali EC – Dilla Liban Group – Dacarbudhuq |
| Renewable Energy private companies/organizations | Gollis Energy Kaafi Energy Solar Land Africa Cadceed Maal SomEnergy Research and Consultancy |
| Financing (e.g., private or development banks, investors) | World Bank (WB) and the International Finance Corporation (IFC) Foreign, Commonwealth & Development Office of the United Kingdom (FCDO) United States Agency for International Development (USAID) African Development Bank (AfDB) |
| Academia | Necsom technical institute Garowe vocational training centre Hargeisa Technical Institute Havoyoco VTC Pharo VTC Kuwait VTC University of Hargeisa Horn Technology Institute |
| Local communities | Engagement with local communities will happen during the implementation of the pilots |
| NGOs | Adventist Development and Relief Agency (ADRA) SHURAAKO: A program of One Earth Future (OEF) Hayle Barise Technical College Women and Child Care Association in Somalia Nagaad Network in Somaliland |

# FINDINGS

## Project Strategy

### Project Design

#### Problem statement

The Somalia AMP project addresses the critical challenge of electrifying the remaining approximately 60% of the rural population, particularly those in remote areas where grid extension is not feasible or economically viable and 20% of urban dwellers. It aims at increasing the market competitiveness of solar photovoltaic minigrid systems while reducing the associated costs. It will also mitigate the various barriers to the adoption of renewable energy based minigrids such as limited access to financial schemes and incentives for service providers, limited policy enforcement, lack of quality standards, lack of viable business delivery models and perceived high investment risks.  The core assumptions of the project include that inability to pay for electricity, limited access to finance, low electricity demand are the key drivers of high minigrid costs and low uptake, and proposes that these barriers can be mitigated through interventions such as policy reforms, business model innovation, digitalization and capacity building,  and ensuring financial and commercial viability.

In summary, these assumptions are true in real life as witnessed within local communities especially peri-urban and rural underserved areas in Somalia. The country stands a chance of transitioning to renewable minigrids, given the high renewable energy potential in Somalia as a result of diversified energy sources by a few private companies such as Benadir Energy Company (BECO). However, given the political instability, weak institutional coordination, and low socio-economic status of a major part of the Somalian population, the project’s ability to fully achieve its intended results may be impacted negatively.

#### Project strategy

The AMP Somalia project seeks to contribute to the national goal of expanding energy access by mitigating the identified barriers to rural electrification, especially for remote and underserved communities. It targets key barriers such as limited policy implementation, lack of viable business models, and high investment risks, through interventions focused on regulatory reform, capacity building, and business model development.

Overall, while the AMP Somalia project is making progress towards addressing the barriers and is aligned to national policies and initiatives, the impact of the project is still to be felt in the project areas. This is because these areas stretch between urban and peri-urban areas, facing varying types of barriers in terms of socio-economic status and the demand for electricity, let alone the ability to pay. The project’s potential impact would be enhanced by adopting a more flexible, differentiated approach, focusing on the most appropriate electrification solutions for each community type, taking into account their ability and willingness to pay for minigrid use and ensuring better alignment between readiness activities and implementation priorities.

Stakeholder consultations confirmed that the overall project context has remained largely consistent between the preparation and implementation phases and is expected to do so unless major structural changes occur. Somalia still lacks a national electricity grid, and although efforts were made to establish a regional interconnection with Ethiopia, these have not yet materialized. Consequently, the assumptions and context that informed the AMP project design remain valid at mid-term. A minor change occurred during implementation with the transition from the National Development Plan which guided the project’s preparatory phase to the National Transformation Plan; however, both maintain a similar emphasis on expanding electrification in rural and peri-urban areas. Notably, the project has contributed to shaping new policy directions within the Ministry, including the development of a Digital Strategy and a Mini-Grid Policy, which did not exist prior to the project’s intervention.

#### Relevance for country priorities

The AMP Somalia is well aligned with national policies and priorities to expand rural energy access, particularly for communities unlikely to be reached by the national grid due to cost or geographic challenges. A significant majority of Somalia’s population is not connected to the diesel-operated minigrids operated by ESPs, particularly rural areas as those minigrids are mainly located in urban areas where the demand for electricity is higher. This is worsened by the lack of sufficient minigrid infrastructure and inaccessibility of some areas, implying that grid expansion remains a major hassle. For such regions, solar mini-grids are vital, especially as electricity tariffs are expected to rise and decentralized solutions become more attractive. AMP complements other major projects, notably the World Bank-funded “Accelerating Sustainable and Clean Energy Access Transformation (ASCENT)” initiative, which aims at increasing access to renewable energy through increased private sector participation in Somalia (World Bank 2025).

The AMP is building pathways for private investment in mini-grids by developing commercially viable delivery models and a national platform, strengthening the environment for private sector participation. It also seeks to address critical capacity gaps within institutions and service providers through the mini-grid curriculum that has been developed and will aid in establishing local expertise in renewable energy.

The AMP in Somalia aligns very well with the alignment with national electrification goals and energy sector development needs. It directly corresponds to the unique structure of the energy sector in Somalia which is characterized by the absence of public grid infrastructure and a high reliance on private-owned diesel mini-grids charging remarkably high tariffs, making affordability a challenge. It complements existing government initiatives, addresses structural weaknesses through targeted capacity building, and strengthens economic sustainability through its productive use strategy.

The project is closely aligned with Somalia’s National Transformation Plan (NTP), particularly Strategic Objective 1 on Energy, which aims to increase electricity access from 61.9% to 80% of the population by 2029. This objective emphasizes expanding rural electrification through investments in diversified and alternative energy sources. It seeks to extend electricity supply to hard-to-reach areas and underserved communities in both rural and peri-urban locations, including settlements of internally displaced persons near major cities. The AMP directly supports this national priority by promoting access to clean and reliable energy through the development of three pilot minigrids. Furthermore, the project complements the geospatial mapping initiative undertaken by the Government of Somalia with World Bank support, which identifies optimal locations for electrification investments. Equally, Somalia’s NDC 3.0 seeks to achieve an emission reduction of 35% by 2035 relative to the BAU. In the energy sector, the targeted emission reduction by 2035 relative to the BAU scenario is 50% to be achieved through development of solar and wind energy among other initiatives. Hence, AMP Somalia supports the mitigation targets in the energy sector

Several stakeholders noted that the AMP project demonstrated strong alignment with national priorities and needs, which was further reinforced through its adaptive approach during implementation. For example, while the original Project Document proposed conducting an institutional assessment, MoEWR later requested support for the development of a Rural Electrification Strategy. In response, the project reallocated efforts within the same budget line to accommodate this national priority. A Terms of Reference (ToR) has already been prepared and shared with the Ministry for review and feedback, and the recruitment of an international consultant will follow to undertake the assignment.

#### Decision making

The MTR is asked to review decision-making processes under the following aspects: were perspectives of those who would be affected by project decisions, those who could affect the outcomes, and those who could contribute information or other resources to the process, taken into account during project design processes? The ProDoc identifies affected stakeholders, influential stakeholders, and resource persons.

In this case, the affected stakeholders are those directly impacted by the project, including local communities in pilot areas, direct beneficiaries such as training recipients and productive energy users, as well as women. Influential stakeholders are actors with the capacity to shape project outcomes. These include government institutions  (e.g., MoEWR, MoECC, NEA, Ministry of Energy and Minerals in Somaliland, Puntland Energy Authority, Hirshabelle Ministry of Energy, National Energy Commission of Somaliland ), regulatory bodies (Somaliland Quality Control Commission - SQCC, SBS), international organizations (African Development Bank, World Bank, Foreign Commonwealth Development Office), private sector actors and associations and academic institutions contributing to policy and technical guidance. And lastly, resource persons are those who provide technical expertise, data, or operational support. This group comprises academic partners, NGOs, and potential private minigrid developers or financiers.

In Annex 9, the ProDoc documents extensive stakeholder consultations during the Project preparation with the groups mentioned above. International organizations, donors, national ministries, national agencies, local level government, minigrid developers and NGOs were involved in the consultation meetings. According to the ProDoc, the comments and recommendations from participants in the consultation meetings and workshops and the UNDP review team shaped the project strategy which has been subsequently presented to stakeholders at end of the PPG phase, to obtain final comments on the design and validate the overall project strategy. Due to the COVID-19 pandemic, the international consultants could not travel to meet with national stakeholders in-person and so most engagements were done online or in hybrid approaches. Communities were not consulted during the PPG phase as the sites for the pilots  were unknown at the time.

Pertaining to Stakeholder consultations during project implementation, this began at inception, with key partners participating in the project launch and inception workshop. Engagement continued throughout implementation, involving civil society organizations, private sector representatives, relevant government ministries at both federal and federal member state levels, and ESPs—particularly in relation to the project’s policy and regulatory components. However, community-level engagement had not yet taken place at the time of the Mid-Term Review, as the selection of the three pilot sites for minigrid installation was still underway. It is anticipated that once these sites are confirmed, community consultations will be carried out in each locality, focusing on areas such as energy literacy, social cohesion, and gender inclusion to ensure local ownership and sustainability of the interventions.

#### Gender

The evaluation assessed the extent to which gender issues were addressed in the project design. The project was found to be compliant with applicable gender policies. Gender considerations are integrated into project design particularly through, for example: Output 1.1 where national dialogues include a gender-sensitive component on women’s participation in the design of tariff models, delivery models and licensing procedures; Output 2.2 emphasizes the need for integrating gender-sensitive content and considerations into the public programmes for technical and vocational training and education that would be developed; capacity building for financial sector actors under Output 3.2. ensures a gender-sensitive focus in terms of women’s participation and lastly Output 4.1 includes the inclusion in the development of digital tools and strategy.  These design elements reflect a commitment to inclusive energy access and gender-responsive rural electrification and development.

In addition, gender issues such as improving women’s access to clean energy, addressing gender-specific barriers, and promoting women's economic empowerment are explicitly addressed in the extensive Gender Analysis and Action Plan in the ProDoc, as required by UNDP/GEF procedures. This plan served as a foundation for gender mainstreaming across the project and informed the annual work plans. The project later engaged a project gender consultant to review the gender action plan for the project,  including research on the ground on gender disaggregated data collection on economic activities and literature review. The gender officer’s involvement in the project also included overseeing and coordinating all gender-related work, review of the GAP, ensuring that targets of the GAP are fully met and any gender issues addressed accordingly.

### Results Framework

#### Logframe – Indicators and Targets

The project’s logframe indicators and targets were critically reviewed for the SMARTness of its criteria. The indicators were assessed as mostly SMART (Specific, Measurable, Achievable, Relevant, and Time-bound). Indicator 11, however, is in its current form difficult to measure while indicator 6 is not very specific in its targets (see Table 4). The indicator 11 aims at “the strategy is implemented and staff members in public authorities, including women, are capacitated to utilize the associating tools and reporting procedure ”. To meet this indicator, the project team would need to develop a monitoring approach to measure how the capacities have evolved. Furthermore, there seems to be an output missing  directly linked to Indicator 11.

The GEF core indicator sheet was reviewed at MTR. The indicator targets were not assessed at mid-term since the minigrid pilot sites have not yet been constructed or commissioned. As a result, no greenhouse gas (GHG) emission reductions or avoidance have occurred, and rural households have not yet been connected to the minigrids. The evaluation team observed that data were provided for direct and indirect carbon sequestration or emission reductions within the Agriculture, Forestry, and Other Land Use (AFOLU) sector (Indicators 6.5 and 6.6). However, no data were reported for emission reductions outside the AFOLU sector—specifically, those expected from the displacement of diesel generators or other fossil fuel sources such as kerosene traditionally used for lighting in rural households.

Table 4: Review of non-SMART project indicators

| Description of indicator | Baseline level | Midterm target level | End of project target level |
| --- | --- | --- | --- |
| Project Outcome 1 Stakeholder ownership in a national mini-grid delivery model is advanced, and appropriate policies and regulations are adopted to facilitate investment in low-carbon mini-grids. |  |  |  |
| Indicator 6 Number of policy derisking instruments for minigrid investments - whose development has been supported by the project - are endorsed/adopted by the national government (number of policy derisking instruments) | Zero, since the project has not yet started | [x] policy derisking Suggestion: It would have been worthwhile for the actual targeted number of policies derisking instruments to be specified. This will render the target more specific | [x] policy derisking Suggestion: It would have been worthwhile for the actual targeted number of policy derisking instruments to be specified. This will render the target more specific |
| Project Outcome 4 Digital and data are mainstreamed, across stakeholders, into local mini-grid market development. Increased knowledge, awareness and network opportunities in the mini-grid market and among stakeholders, including benefitting from linkages to international good practice. |  |  |  |
| Indicator 11 : A project digital strategy for the project is prepared and implemented by the PMU to contribute to project implementation and local minigrid market development. | No progress, since the project has not yet started. . | Digital strategy is prepared, in consultation with public and private parties and close collaboration with the CoPs led by the AMP Regional Project. | The strategy is implemented and staff members in public authorities, including women are capacitated to utilize the associating tools and reporting procedure. Suggestion: The following could be added for more clarity: Following the implementation of the project’s digital strategy, capacity of targeted individuals trained on the utilization of the digital strategy is assessed by survey. On a scale of 1 to 5, an average score of at least 4 is achieved (1 represents a low level of capacity and 5 represents a strong capacity to utilize the strategy. |

#### Logframe – Outcomes

The clarity, practicality, and feasibility of the project's objectives and outcomes were reviewed in relation to the overall time frame. The targets were assessed as mostly SMART. Stakeholders expressed differing opinions regarding the likelihood of completing all project activities by the scheduled closure in November 2026. Initial delays stemmed from institutional mandate overlaps between the Ministry of Energy and the Ministry of Environment, as well as from the extended process of project site preselection. Despite these setbacks, activities related to capacity building and improvement of the enabling environment are expected to be finalized within the remaining implementation period. The construction of the minigrid pilot sites could also be achieved before project closure, provided that procurement proceeds without further delays. However, post-construction monitoring of minigrid operations and the documentation of lessons learned will likely extend beyond the project’s current timeframe. Additionally, the 2026 national elections pose a potential risk, as any outbreak of violence or unrest—identified by the International Crisis Group as a plausible scenario could disrupt implementation. It is therefore recommended that the project seek a one-year no-cost extension to recover lost time, ensure adequate post-commissioning monitoring, and mitigate risks associated with potential procurement delays or election-related instability.

#### Logframe – Development Outcomes

Progress to date was examined to determine whether it has already contributed to, or is likely to catalyze, beneficial development outcomes such as income generation, gender equality, women's empowerment, or improved governance. The energy sector in Somalia has historically operated without formal regulation. The Somalia Minigrid  Project seeks to introduce market-friendly regulatory frameworks in coordination with complementary initiatives supported by the World Bank and the African Development Bank. Through its enabling environment interventions, the AMP aims to strengthen the capacity of the MoEWR and NEA to effectively oversee and regulate the sector. Under Component 3, the project plans to develop and pilot a financing framework and business model designed to attract private investment and mobilize international funding, including contributions from the Somali diaspora. If successful, this will expand financial flows for future minigrid development in the country.

Upon completion and commissioning of the pilot minigrids, the project is expected to deliver significant social and economic co-benefits, including increased income-generating opportunities from the productive use of energy, enhanced gender equality as electricity will facilitate women’s household chores such as cooking, and improved educational outcomes for students benefiting from extended study hours under better lighting conditions. In addition, the technical and vocational education and training (TVET) curriculum developed on solar and hybrid minigrids is intended to address existing skills gaps in the renewable energy sector. However, the mid-term review identified concerns regarding the limited availability of qualified academic staff to deliver the curriculum effectively. Some stakeholders also raised issues of inclusivity, noting that many technicians currently working in existing minigrids possess limited formal education and may face difficulties participating in the TVET courses, particularly because they will be delivered in English, posing a potential language barrier.

#### Logframe – Measuring Gender

The evaluation reviewed whether broader development and gender-related aspects of the project are being effectively monitored. The project has taken tangible steps to address broader development and gender aspects, as demonstrated through a comprehensive Gender Action Plan. A gender specialist played a key role providing support to the AMP Somalia project, revising the GAP for the project in 2024. The GAP has indicators, but these are lacking targets, rendering it challenging to track and determine how well the project is progressing towards integrating gender in its delivery. The results framework of the project or the GAP could include additional indicators as suggested in Table 5 which should be integrated into the project’s monitoring and evaluation system. The gender targets should be tracked systematically and reported in the project’s monitoring reports such as the PIRs.

Table 5: Proposition of new gender-sensitive indicators

| Outcome | Proposed gender-sensitive indicators | End of project target level |
| --- | --- | --- |
| Outcome 1 | Indicator 1: Number and percentage of women of the total stakeholders consulted for the elaboration and endorsement of a minigrid delivery model (Unit of Measure: Number of women trained) | At least 25% of stakeholders consulted for the elaboration and adoption process of a minigrid delivery model are women |
|  | Indicator 2: Number and percentage of women trained in the utilization of online tools for digital transformation of the minigrid sector (Unit of Measure: Number of women trained) | At least 25% of the stakeholders trained on the utilization of online tools for digital transformation of the minigrid sector are women |
| Outcome 2 | Indicator 3: Number and percentage of women-led businesses established or expanded using minigrid electricity within 12 months of grid installation. (Unit of Measure: Number of businesses owned by women) | At least 40% of new or expanded businesses using minigrid power are women-led by the end of Year 1 after PUE installation. |
|  | Indicator 4: Number and percentage of women trained on the implementation of innovative business models and integration of cost-reduction levers in mini-grid projects (Unit of Measure: Number of women trained) | At least 25% of the stakeholders trained on the implementation of innovative business models and integration of cost-reduction levers in mini-grid projects are women |
|  | Indicator 5: Number and percentage of women and girls trained in technical, business, or energy management skills under the project (Unit of Measure: Number of women) | At least 30% of women and girls in the community trained, making up 50% of all training participants by project end. |
|  | Indicator 6: Number and percentage of women participating in minigrid management committees or decision-making (Unit of Measure: Number of women) | Women hold at least 25% of committee positions by project completion. |
| Outcome 3 | Indicator 7: Number and percentage of women participating in training, knowledge sharing and awareness raising events aimed at increasing financial sector’s capacity to evaluate investment in minigrids (Unit of Measure: Number of women) | At least 25% of the participants from financial institutions participating in training, knowledge sharing and awareness raising events aimed at increasing financial sector’s capacity to evaluate investment in minigrids are women. |

## Progress towards Results

### Rating of Progress towards Results

Progress made by the project to date was assessed against the originally defined expectations (Table 6). The current status of implementation was judged as moderately satisfactory, based on the comparison between planned outputs and actual results achieved up to this point. Overall, the project is on track for most of its outcomes.

Under Component 1, the project organized national dialogues and delivered training sessions for representatives of the MoEWR, the energy regulator, and the private sector on developing mini-grid regulations and applying tariff calculation models using the AFUR template tool. It also supported the translation of licensing and tariff regulations from Somali into English and engaged consultants to assist in establishing institutional structures for rural electrification and formulating policies and regulatory frameworks for mini-grids. By the time of the Mid-Term Review (MTR), the project had successfully completed the DREI and Digital Readiness Assessments, as well as the national mini-grid policy and regulations, thereby providing a solid analytical and policy foundation for sector reform. However, the digital strategy and accompanying regulatory tools were still pending formal government approval, delaying their full implementation. During the MTR, it was confirmed that the project team was actively collaborating with government counterparts to expedite the endorsement process and initiate rollout. Outcome 1 comprises of three indicators (5, 6 and 7). Of these, the MTR rated progress achieved for two indicators (5 and 6) as Satisfactory and one indicator (7) as Highly Satisfactory. The overall progress rating for outcome 1 is therefore computed as Satisfactory.

Under Component 2, a one-year academic curriculum for certification or diploma in solar and hybrid mini-grid systems has been developed, and several training sessions and stakeholder consultations have taken place. However, delays in securing accreditation have postponed its finalization and implementation. The project also initiated the preparation of the Mini-grid Pilot Plan (MPP), which proposed two key approaches: (i) expanding the operations of ESPs into rural areas through solar mini-grids, and (ii) launching an innovation competition to promote rural industrialization using solar mini-grid solutions. Progress on the MPP has been slowed by the government’s lengthy internal approval process for confirming the initial three pilot sites, as well as extensive consultations needed to finalize the longlist list of nine locations to enable a competitive process of site selection. These delays have consequently impacted the launching of the innovation competition, commissioning schedule and achievement of results under this component. The project had elaborated an advanced draft of the MPP as of end of October 2025 and aims to begin pilot delivery of the curriculum in the last quarter of the year. Outcome 2 has two indicators (7 and 8). The progress achieved for indicators 7 and 8 were rated as Moderately Satisfactory and Satisfactory respectively. The overall progress rating for Outcome 2 was rated Satisfactory.

Under Component 3, the project initiated a comprehensive techno-economic analysis for minigrids using the De-risking Renewable Energy Investment (DREI) framework. To support this process, a DREI Technical Working Group was established and trained in March 2024 to facilitate the application of DREI recommendations. The group identified the appropriate project types for Levelized Cost of Energy (LCOE) modeling, based on market characteristics assessed during the field mission. An international financial market and mechanisms expert was engaged to design a dedicated financing facility for minigrids in Somalia. By the time of the mid-term review, the consultant had produced a detailed mapping report outlining existing and planned funding opportunities, an analysis of current financing mechanisms, and an overview of the political and institutional landscape influencing minigrid development. However, the absence of key government counterparts caused a slight delay in conducting the consultant’s in-country mission for stakeholder consultations, which was rescheduled for August 2025. At mid-term, it was confirmed that the project is accelerating recruitment processes and preparing to initiate structured engagement with local financial institutions and diaspora investment platforms to collaboratively design blended finance instruments supporting minigrid expansion in Somalia. Outcome 3 comprises of two indicators (9 and 10). Progress achieved for indicator 9 was rated Satisfactory while that for indicator 10 was Moderately Unsatisfactory. The overall rating for Outcome 3 was computed as Moderately Satisfactory.

Under Component 4, the project successfully developed a digital strategy, and Somalia’s experience has been showcased at the UNFCCC COP29 and during global AMP webinars. However, the strategy is yet to be formally endorsed, and the procurement of the Prospect platform remains in progress. The project team is collaborating closely with the AMP Regional Project to complete the procurement process being handled at the regional level and commence capacity-building activities focused on data collection and utilization. Outcome 4 has 2 indicators (11 and 12). While progress achieved for indicator 11 is rated as Highly Satisfactory, that for indicator 12 is rated Moderately Satisfactory. The overall progress rating for Outcome 4 has been computed as Satisfactory.

Table 6: Progress Towards Results Matrix (Achievement of outcomes against End-of-project Targets)

| Project Strategy | Indicator | Baseline Level | Level in 1st PIR (self- reported) | Midterm Target | End-of-project Target | Midterm Level & Assessment | Achievement Rating | Justification for Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Supporting access to clean energy by increasing the financial viability, and promoting scaled-up commercial investment, in low-carbon mini-grids in Somalia, with a focus on cost-reduction levers and innovative business models. | Mandatory indicator 1: GEF Core indicator 6 GHG emissions mitigated (Metric tons of carbon dioxide equivalent (tCO2e)) | Zero, since the project has not yet started | National dialogue and DREI joint mission was conducted from 3rd to the 7th of March 2024 in Mogadishu to identify the most suitable minigrid delivery model, provide training to representatives from MoEWR, NEA and private sector on minigrid policy and regulation. Business model chosen was the expansion of existing minigrids into less profitable semi-urben areas by incentivizing ESPs with grad funding, this model was to be presented to MoEWR for final approval before the development of pilot plans. | Zero, since the project is not yet commissioned | Direct: 29,577 tCO2eq Indirect: 594,000 tCO2eq (90% of the total estimation for this project) |  | S | Partly achieved Pilot plants yet to be commissioned, training provided to stakeholders during national dialogue workshop, expansion of existing mini-grids into less profitable semi-urban areas using grant incentives selected as the delivery model. A delivery model and DREI analysis reports have been finalized, to inform financing strategies, derisking policy instruments and investment prioritization. 9 pilot sites identified during Project Board meeting in June 2025. Site selection process delayed. MPP under finalization |
|  | Mandatory Indicator 2: GEF Core indicator 11: Number of direct beneficiaries benefitting from clean, affordable and sustainable energy access via mini-grids, disaggregated by gender and by customer segment (residential, social, commercial/productive use) (number of people) | Zero, since the project has not yet started | Following the national dialogue, a concept note was drafted to serve as the foundation for discussions with the government on the development of minigrid pilot plans. 2 delivery models identified: Comtinuous Expansion Model (service extension to less profitable semi-urban areas) and Rural Industrilization Model (assessing deep-rural natural resources that could attract industrial investment requiring electricity and ESPs electrify them. | Zero, since the pilot project(s) is not yet commissioned. | 66,670 people (of which 50% women) 65,570 people (residential) 210 people (social) 710 people (commercial/PUE) 66,670 people (total) |  | S | On track 0, project yet to be commissioned. Pilot minigrid project still under planning following elaboration of the concept note. Government proposed three self-selected sites, causing delays in finalizing the MPP. However 9 sites have been identified. Training provided to 36 stakeholders from MoEWR, NEA and private sector. |
|  | Indicator 3: GEF Core indicator 6.4 Increase in installed solar PV capacity (MW) and battery storage (MWh) | Zero, since the project has not yet started | National dialogue workshops conducted, trainings provided to MoEWR, NEA and private sector representatives | Zero, since the pilot project(s) is not yet commissioned | Solar PV: 2.116 MW Battery storage: 3.300 MWh |  | S | On track 0 since pilot project is not yet commissioned. National dialogue workshops held in March 2024. Two delivery models proposed – CEM and RIM. Concept note drafted to guide MPP. Capacity building with training delivered to 36 stakeholders (20 males, 16 females). 9 pilot sites identified |
|  | Indicator 4: Number of local residents trained in different aspects of mini-grid development and operation (e.g. sales, distribution, operations, management) disaggregated by gender (number of people) | Zero, since the project has not yet started | Affected by the nearly year-long delay in approving work plans, to be achieved during the commissioning of pilot projects. | Female: 60 Male: 90 Total: 150 persons | Female: 120 people Male: 180 people Total: 300 people |  | MU | Partly achieved Yet to be realized. Groundwork however has been done such as trainings organized for government and private sector stakeholders, to train them on policy regulation and tariff modelling. Further trainings on enhancing institutional, technical and financial capacity held in Mogadishu, involving 20 participants (7 females and 13 males) from government, private sector, academia and civil society. Capacity gaps and sectoral challenges identified and addressed. Project supported training in Somaliland for 22 ministry staff (2 females and 10 males) , on minigrid system design. MoEM organized GIS training for 22 staff members (9 females and 13 males) to build capacity on spatial data analysis and mapping. Refresher training on DREI methodology provided to 33 participants. Project supported development of a curriculum for academic and vocational institutions |
| Outcome 1: Policy and Regulation | Indicator 5: A minigrid delivery model to enable minigrid development is endorsed/adopted by the national government through a consultative process involving key stakeholders (e.g. relevant ministries, local authorities, rural populations, private sector, media, etc.) (binary (1/0)) | Zero, since the project has not yet started. | As of June 30, 2024, joint mission on national dialogue and DREI conducted in March 2024. MoEWR, NEA and private sector representatives trained on minigrid regulations that incentivize investments and electrification using the AFUR minigrid regulation template creation tool and also trained on tariff calculation model. 2 delivery models identified – CEM and RIM. A consultant has been engaged under an LOA with the MoEWR, for capacity assessment and building on technical, managerial and regulatory issues on the institutional setup for rural electrification. | One Multi-stakeholder national dialogue platform on minigrid delivery models established and active. | At least one minigrid delivery model is identified and endorsed by the government through the work of the multi-stakeholder platform and dialogue. |  | S | Partly achieved National dialogue report delivery model available, waiting for validation by MoEWR-FGS. Institutional assessment for rural electrification completed. National dialogue consultation and DREI workshops held in Mogadishu in March 2024. Participants were trained on minigrid regulation and tariff modelling. 2 delivery models proposed – CEM and RIM. Institutional assessment for Rural Electrification completed. . |
|  | Indicator 6: Number of policy derisking instruments for minigrid investments - whose development has been supported by the project - are endorsed/adopted by the national government (number of policy derisking instruments) | Zero, since the project has not yet started | As of June 30, 2024, a comprehensive mini-grid techno-economic analyses on DREI has been launched. A DREI technical working group to support the implementation of DREI recommendations has been established and trained on the DREI methodology. International and national DREI consultants have conducted structured interviews with both government and private sector stakeholders, pending modeling phase. | [x] policy derisking instruments. | [x] policy derisking instruments. |  | S | Partly achieved 3 policy derisking instruments adopted . DREI analysis report completed. Minigrid Policy drafted. Project has made significant progress made in the development and adoption of derisking policy instruments in Somalia. Techno-economic analysis launched in 2024 and a DREI Technical Working Group set up. Second round of DREI workshops were organized in February 2025 with significant outcomes. DREI analysis identified major risks – security and political instability as critical investment risks, financial risks-limited financial products and high collateral demands, energy market risk (lack of structured rural electrification strategy and regulatory clarity), and end-user credit risk (low ability to pay and affordability issues). |
|  | Indicator 7: Online tools for digital transformation of the mini-grid sector are selected and adopted through a consultative process involving key stakeholders (e.g. relevant ministries, local authorities, rural populations, private sector, media, etc.) | Limited capacity for monitoring and regulation | A national consultant has been recruited to assist in the review and operationalization of mini-grid policies and regulations through digital transformation support, while the recruitment of an international consultant is in progress. Recently developed licensing and tariff regulations successfully translated from Somali to English for international consultants and partners. | Online tools are selected and consensus among public and private parties is achieved on their adoption as part of the proposed digital transformation activities. | The selected online tools are adopted and staff members in public authorities, including women, are capacitated to utilize them for sector monitoring. |  | HS | Achieved Project made significant progress : Digital Readiness Assessment validated; Prospect platform adopted, a centralized procurement process has been launched to facilitate deployment and it’s ongoing for both the national and regional AMP projects. Digital strategy pending validation. |
| Outcome 2 Innovative business models based on cost reduction operationalized, with strengthened private sector participation in low-carbon mini-grid development. | Indicator 7: Number of mini-grid pilot(s) implemented that demonstrate a delivery model, cost-reduction measure(s) and/or productive use of electricity (including data on the installed capacity, location coordinates, and commissioning date) | Zero, since the project has not yet started . | The development of the MPP has commenced with support from an international consultant. 2 options proposed: expanding ESPs into more rural areas with solar minigrids and conducting an idea competition for Rural Industrialization with solar minigrids. A national consultant has been engaged to develop a one-year academic program for solar and hybrid minigrid certification/diploma. Recruitment of minigrid educational and vocational training is ongoing. Data on existing curriculums collected to identify gaps and support the development of a new curriculum for adoption by universities and vocational training institutes. | The project’s detailed design plan (the ‘Minigrid Pilot Plan’) for advancing the minigrid pilots is developed, and cleared by UNDP and the Project Board. Any project tendering process, as applicable, for minigrid pilots is launched. | 100% of the planned minigrid pilots, as identified in the project’s minigrid Pilot Plan, are commissioned. |  | MS | On track Development of the MMP initiated, drafting ongoing with the support of an international consultant recruited, and was expected to be completed by July 31 2025. Two pilot options have been proposed – expansion of ESPs into rural areas using solar minigrids and Idea competition for Rural Industrialization powered by solar minigrids. The first option seems the most viable for Somalia and will be presented to the GoS for final approval, after which it will be submitted for clearance by the UNDP and Project Board. 9 pilot sites endorsed during PB meeting in June 2025, grouped to 3 lots, to be finalized based on: -Delivery Model and Cost-Reduction Measures: -Pilots will demonstrate productive use overlays and hybridization of existing diesel mini-grids. -Cost-reduction strategies include demand stimulation, digital monitoring, and innovative financing instruments. -Installed Capacity, Location Coordinates, and Commissioning Dates: These details will be confirmed following site selection, ESIA/ESMP clearance, and procurement. Commissioning is expected to begin in Q4 2025, subject to MPP finalization and validation from stakeholders. |
|  | Indicator 8: Capacity of mini-grid developers and/or operators is enhanced to implement innovative business models and incorporate cost-reduction levers in mini-grid projects | ESPs have limited technical and operational capacity | To be achieved in the second quarter of 2025 and onwards. . | Planned capacity building activities for year 1 and 2 are implemented, in both Somalia and Somaliland. The capacity of targeted recipients is assessed by survey towards the end of year 2. On a scale of 1 to 5, an average score of at least 2 is achieved. - 1 represents a low level of capacity - 5 represents a strong capacity to understand relevant issues and apply knowledge and skills to find effective solutions. | Planned capacity building activities for year 3 and 4 are implemented, in both Somalia and Somaliland. The capacity of targeted recipients is assessed by survey towards the end of the project. On a scale of 1 to 5, an average score of at least 4 is achieved. - 1 represents a low level of capacity - 5 represents a strong capacity to understand relevant issues and apply knowledge and skills to find effective solutions. |  | S | On track Capacity building through education and training has been conducted on a continuous basis, a standardized one-year programme on solar and hybrid minigrid systems has been developed, after consultations with 95 stakeholders from Mogadishu, Garowe and Hargeisa reflecting national priorities and industry needs. The curriculum is awaiting accreditation from the Ministry of Education, upon approval it will be delivered to vocational institutions and universities. Minigrid Pilots under development. AMP has supported the strengthening of capacity of national industry associations, such as SOGEA, promoting peer learning, policy dialogues and continuous stakeholder engagement. SOGEA has benefitted from a robust governance structure produced within the AMP project. Project conducted energy sector mapping, identifying 50 active private providers serving 2.5 million customers. Project has enhanced regional knowledge exchange between the national AMP and regional AMP, through participation in CoPs, lesson sharing and best practices, as well as collaboration on digital strategy development. |
| Outcome 3 Financial sector actors are ready to invest in a pipeline of low-carbon mini-grids and concessional financial mechanisms are in place to incentivize scaled-up investment. | Indicator 9: Capacity of financial institutions is enhanced through training, knowledge sharing, and/or awareness raising events aimed at increasing the financial sector’s capacity to evaluate investments in mini-grids | Domestic financial institutions are not involved in mini-grid funding | As of June 30, 2024, a minigrid techno-economic analysis on DREI has been launched, a joint DREI and national dialogue workshop held, national and international consultants conducted structured interviews. Several Public-Private Partnership (PPP) agreements using Power Purchase Agreements (PPA) are in place. | Planned capacity building activities for year 1 and 2 are implemented, in both Somalia and Somaliland. The capacity of targeted recipients is assessed by survey towards the end of year 2. On a scale of 1 to 5, an average score of at least 2 is achieved. - 1 represents a low level of capacity - 5 represents a strong capacity to understand relevant issues and apply knowledge and skills to find effective solutions. | Planned capacity building activities for year 3 and 4 are implemented, in both Somalia and Somaliland. The capacity of targeted recipients is assessed by survey towards the end of the project. On a scale of 1 to 5, an average score of at least 4 is achieved. - 1 represents a low level of capacity - 5 represents a strong capacity to understand relevant issues and apply knowledge and skills to find effective solutions. |  | S | Five trainings held in Mogadishu on minigrids design, installation, financing, DREI, PUE and softwares. A total of 133 participants benefitted (89 men and 44 women) from government institutions, ESPs, banks academia and NGOs. Mini-grid techno-economic analyses on DREI launched. The evaluators did not identify information on the survey conducted to determine improvement in capacities of trained participants. . |
|  | Indicator 10: Number of government or impact investor-supported financing mechanisms offering concessional finance for low-carbon mini-grids | Diaspora and small investors are not heavily involved in mini-grid funding . | ToRs for an energy finance specialist drafted. | At least one complementary funding instrument is designed to support the participation of the diaspora and small investors in existing financing mechanisms , | Two ESPs in Somalia and two in Somaliland have managed to obtain finance for low-carbon mini-grid projects from the diaspora or small investors. |  | MU | On track Financial market analysis conducted to advance the design of concessional financing mechanisms. A mapping report on existing and planned mini-grid funding, and an analysis of current financing mechanisms has been produced, pending consultation workshops (scheduled for August 2025) |
| Outcome 4 Digital and data are mainstreamed, across stakeholders, into local mini-grid market development. Increased knowledge, awareness and network opportunities in the mini-grid market and among stakeholders, including benefitting from linkages to international good practice. | Indicator 11: A project digital strategy for the project is prepared and implemented by the PMU to contribute to project implementation and local minigrid market development | No progress, since the project has not yet started | Both an international and national consultant engaged, supporting the Digital Readiness Assessment (DRA) to inform the digital strategy. Key enablers identified and digital opportunities organized into 3 groups for the AMP DRA methodology, key stakeholders identified and relevant date and reports collected through a desk review. . | Digital strategy is prepared, in consultation with public and private parties, and close collaboration with the CoPs led by the AMP Regional Project. | The strategy is implemented and staff members in public authorities, including women, are capacitated to utilize the associating tools and reporting procedure. |  | HS | Project succeeded in developing a comprehensive digital strategy, informed by a validated DRA. These were presented at COP29 in Azerbaijan and shared globally through a dedicated AMP webinar. However, it is unclear whether or not staff members in public authorities have been capacitated to utilize the tools presented in the strategy. |
|  | Indicator 12: Number of mini-grid pilot(s) sharing data on mini-grid performance with the regional project and other stakeholders following best practices and guidance provided by the AMP Regional Project | Zero, since the project has not yet started | The national AMP had discussions on the procurement digital platform with the regional AMP, they agreed that they would both jointly procure the Prospect digital platform. Its adoption is pending. | The project’s digital platform is procured and operational, ready for data collection and managed with (i) the project’s mini-grid pilot(s) and (ii) the AMP regional project’s digital platform. | 100% of the planned minigrid pilots, as identified in the project’s Minigrid Pilot Plan, are collecting and sharing data with the project’s digital platform |  | MS | Partly achieved No mini-grids commissioned yet. Quality Assurance and Monitoring Framework is in place and digital strategy. Prospect platform (an open-source energy data system) has been jointly adopted by the national and regional AMP for data sharing, best practices and lessons learned. The AMP regional project and Somalia national project will jointly procure the Prospect platform |

Indicator Assessment Key

| Green= Achieved | Yellow= On target to be achieved | Red= Not on target to be achieved |
| --- | --- | --- |

Several key barriers have constrained progress as supported by evidence from interviews with key project stakeholders:

- Prolonged consultations between government institutions: Significant delays occurred at the inception stage of the project, as a result of conflict between the MoECC and MoEWR. This delay led to a late start in the implementation of activities, which only took off in December of 2023, almost a year after the inception in February 2023. In the process of selecting pilot sites, the government self-selected three sites and this provoked prolonged consultations between government institutions and other stakeholders on a consensus causing even further delays and impacting the timely achievement of certain outcomes.

- Changes in leadership within the MoEWR and generally high turnover in government:   In addition to prolonged consultations, MoEWR which has a major role to play in the project experienced a change in its leadership, which warranted a briefing for the new leadership thereby leading to significant delays in the approval of annual workplans. Somalia experiences a high turnover in senior government officials which also affected the AMP project’s implementation.

- Delayed recruitment and procurement: The recruitment of an international expert to support the implementation of Outcome 2 for example took longer than expected, causing delays.

The MTR team identified several factors contributing to the project’s success so far, including strong commitments shown on the part of the implementing partner and a strong sense of ownership displayed so far from other actors involved. The recruitment of experts to support project implementation such as in the operationalization of minigrid policies and education, committed and highly professional PMU and implementation partners, and strong relationship between them, as well as a good working relationship between the project and national government stakeholders. The technical support provided by the regional AMP project to the Somalia AMP child project equally emerged as a contributing factor to success realized by the project this far.  The MTR equally identified remaining barriers that could jeopardise the attainment of the project’s objectives and these include:

Upcoming elections in Somalia. The upcoming national elections in Somalia, scheduled for 2026, present a potential challenge to the timely implementation and achievement of the project’s objectives. The election period could be accompanied by heightened political tension, shifts in government priorities, and possible administrative disruptions that may delay decision-making, procurement, or approval processes critical to project progress. In addition, changes in leadership or institutional structures could affect the continuity of engagement with key counterparts and delay coordination among implementing partners. These factors collectively pose risks to the construction schedule of the planned mini-grids and to maintain momentum in project execution. Proactive engagement with government counterparts, contingency planning, and close monitoring of the political context are therefore essential to mitigate these potential disruptions.

Delays in Procurement of Service Providers for Minigrid Construction. A key risk that could hinder the timely achievement of the project’s objectives is potential delays in the procurement process managed by UNDP for selecting and contracting service providers to construct the minigrids in the three targeted sites in Somalia. Procurement processes within UNDP are often complex and time-consuming, involving multiple layers of review, due diligence, and compliance with UNDP and donor requirements. Given Somalia’s challenging operating environment, including limited local technical capacity, market constraints, and security-related access issues, the risk of extended procurement timelines is heightened. Such delays could compress the implementation schedule, reduce the time available for testing, commissioning, and operationalization of the minigrids, and ultimately affect the project’s ability to demonstrate results by closure. Proactive procurement planning including the timely preparation and internal validation of the request for proposal (RFP) package, and the organization of a roadshow or a pre-bid conference to explain the eligibility criteria and requirements of the RFP to prospective bidders will be essential to mitigate this risk and maintain progress toward achieving the intended outcomes.

Security transition in Somalia. A potential obstacle to the achievement of the project’s objectives relates to the ongoing security transition in Somalia. The African Union Transition Mission in Somalia (ATMIS) concluded its mandate on 31 December 2024, and as of 1 January 2025, has been succeeded by the new African Union Support and Stabilisation Mission in Somalia (AUSSOM). This transition involves a phased transfer of security responsibilities from the African Union forces to the Somali Security Forces, a process that began in April 2022. While AUSSOM’s role is to provide continued support to the Federal Government of Somalia in maintaining stability and strengthening national security capacities, the transition period may create temporary security gaps or localised instability in some regions. Such conditions could pose challenges for the project’s planned activities—particularly the construction and operation of minigrids in selected sites—by affecting field access, timelines, and the safety of implementing partners and contractors. Continued monitoring of the security situation, close coordination with national authorities, and flexibility in implementation planning will therefore be essential to mitigate this risk.

The MTR also assessed how benefits of successful parts of the project could be extended. The project’s key achievements to date are primarily linked to strengthened institutional capacities within the energy sector. With project support, a Rural Electrification Unit has been established within the Ministry of Energy to address rural energy access and electrification matters. In addition, the regulatory assistance provided through the AMP has enabled NEA to introduce and implement a licensing fee system, marking progress toward a more structured and regulated energy framework.

The project also supported the development of a technical curriculum on solar and hybrid minigrids, aimed at addressing existing skill shortages in the renewable energy sector. The potential impact of this intervention will be further amplified once the course is formally accredited by the Ministry of Education, a process currently in progress. The project can build on this achievement by facilitating collaboration between MoEWR, the Ministry of Education, and selected academic institutions to roll out the accredited curriculum. Partnering with organizations such as the Res4Africa Foundation, which has experience implementing similar minigrid training programs in countries like Mozambique and Eritrea, could further enhance effectiveness and sustainability.

## Project Implementation and Adaptive Management

### Management Arrangements

The overall effectiveness of project management was assessed against the original arrangements described in the ProDoc (see chapter VII in the ProDoc). The AMP Somalia project is implemented under the Direct Implementation Modality (DIM), with the UNDP Country Office in Mogadishu serving as the Implementing Partner (IP). In this role, UNDP will oversee the execution of the UNDP-GEF project, manage the disbursement of funds, and ensure the delivery of project results in accordance with the approved results framework and work plan outlined in the Project Document. No responsible parties were identified during the Project Preparation Grant (PPG) phase. However, the ProDoc made provisions that during implementation, if UNDP determines that specific activities should be executed by national institutions, it will apply the procedures outlined in the Harmonized Approach to Cash Transfer (HACT) framework. This process includes conducting micro-assessments of the prospective institutions to evaluate risks and capacity gaps, followed by the preparation of the appropriate legal instruments for engagement. LoA or Responsible Party Agreements will be developed in accordance with HACT findings and subject to the Country Office’s oversight and approval prior to finalization. During project delivery, UNDP engaged with the MoEWR as the government counterpart for the implementation of some activities of the project as guided by LoAs established annually between UNDP and MoEWR.

The TAC and issue-specific ad-hoc technical working groups (TWGs) involving key projects and national stakeholders play a large role regarding decision-making in the project. On this matter, the TC is tasked to provide overall technical guidance and direction to the project, to provide guidance on new project risks, as well as to advise on major and minor amendments to the project and oversee project progress. The TC meets more frequently, than the Project Board, which may be one of the reasons why progress reports have described decision-making as being responsive.

Project decision-making is guided by a Project Board composed of the GEF Operational Focal Point and representatives from UNDP Country Office and MoEWR. As the project operates under the Direct Implementation Modality (DIM), the Board, chaired by the UNDP Resident Representative is mandated to meet twice annually to approve annual work plans, review progress, and provide strategic guidance and corrective actions as needed. However, at MTR, the project board had only met twice – at the project inception meeting and in June 2025. One notable decision by the Board concerned the selection of pilot sites for the minigrid installations. While the Ministry of Energy initially proposed three sites, UNDP recommended aligning with the project document by broadening the selection to ensure greater competitiveness and flexibility. Following deliberations, the Board agreed on the preselection of nine sites, from which three will ultimately be chosen through a competitive bidding process for the installation and construction of minigrids.

At the time of the mid-term review, no modifications had been made to the project’s management structure. Stakeholders interviewed during the review described the decision-making process as generally transparent, though some decisions—such as resolving the institutional mandate overlap between the Ministries of Energy and Environment (which took around 10 months) and the re-selection of pilot sites (approximately 6 months)—were lengthy. Nonetheless, the rationale behind key decisions is typically well-communicated to government counterparts and remains aligned with the project document, such as the decision to establish an LoA solely with the Ministry of Energy, consistent with its designated role as the lead public authority with the mandate to oversee the Somalia Energy sector, set policies, and strategic frameworks, approve tariffs for the electricity services, and build the technical capacity of electricity service providers in Somalia in consultation with stakeholders through open and transparent processes.

The quality of project execution by the implementing partners was assessed as satisfactory. An LoA is signed annually with the Ministry of Energy, aligned with approved annual workplans, outlining the Ministry’s specific roles and responsibilities in implementation. In some cases, the Ministry takes the lead in planning and executing activities, with UNDP providing support, while in other instances, both entities implement activities jointly. Procurement-intensive activities are primarily managed by UNDP, whereas the Ministry focuses on policy development, capacity-building, and training-related components. Although LoAs are renewed each year, several government counterparts noted that their finalization is often delayed. The evaluation team observed that these delays are likely linked to the late approval of annual workplans, from which the LoAs are derived. Early in the project, workplan approval was further hindered by institutional mandate overlaps between the MoEWR and MoECC, which prolonged the process of defining implementation responsibilities.

The review also assessed whether the executing agency, the implementing partner, UNDP, and other involved partners demonstrated the capacity to deliver benefits to or involve women. The review showed that UNDP and its partners have the capacity to involve women meaningfully and deliver gender-related benefits, as shown through their ability to design, adapt, and implement targeted gender interventions at both community and policy levels in the Gender Action Plan. During implementation, gender was emphasized during trainings and workshops, ensuring the participation of women stakeholders in project engagements, in alignment with the gender policies and gender-sensitive components outlined during project design. In the development of the curriculum for public educational programmes, gender considerations were integrated.

While the project is strong at demonstrating a positive gender balance across staff providing implementation support, this has not been the case relating to its governance structure – project board.  The project currently employs two core staff members—a Project Manager and a Project Associate—both of whom are male. They receive additional technical and administrative support from other members of the UNDP portfolio, including those responsible for monitoring and evaluation (male) and finance (female). The project receives support from the AMP regional team—including the Project Manager, Gender Specialist, and M&E Specialists, all of whom are women, and from the UNDP Regional Bureau for Arab States (RBAS), where both the Regional Technical Advisor (RTA) and the Regional Programme Associate are female. In total, it could be deduced that the project benefits from the contributions of nine personnel, comprising six women and three men. The Project Board composition, as outlined in the Project Document (ProDoc), does not specify the total number of members or the number of representatives from each institution. According to the ProDoc, the Board should include the GEF Operational Focal Point and representatives from the UNDP Country Office (CO) and MoEWR. However, the Project Board meeting held on 18 June 2025 included participants from the following institutions: MoEWR (4), NEA (2), and the UNDP CO (8). While the official meeting report did not provide a gender breakdown of participants, the evaluation team’s review indicated that 13 of the 14 attendees were male and one was female, reflecting a significant gender imbalance within the Project Board. The evaluation notes, however, that gender representation is influenced by the designations made by participating institutions rather than by the project’s direct control.

### Work Planning

The AMP project, as detailed in the ProDoc, established a clear work plan outlining the roles and responsibilities of all partners and stakeholders for the project’s duration. This plan was reviewed and updated in the annual progress report based on parties’ performance and project indicator monitoring, with annual work plans submitted to the TAC for validation.

Project implementation commenced with an inception workshop held on February 13, 2023. However, significant delays followed the inception with most activities not beginning until late 2023. Disputes over institutional mandates between the MoEWR and MoECC, which hosts the GEF Operational Focal Point (OFP), resulted in approximately 10 months of delay in project implementation. Although the project inception meeting was held in February 2023, the LoA between UNDP and the Ministry of Energy was only finalized in December 2023. The Ministry of Environment had requested involvement in certain project activities, while the Project Document clearly designated the MoEWR as the primary government counterpart. The lack of consensus between the two ministries—particularly among their Director Generals and technical teams required escalation to ministerial level. The matter was ultimately resolved when both ministries agreed that the project’s focus aligned more closely with the energy sector, confirming MoEWR as the lead implementing counterpart. Additional delays stemmed from disagreements regarding the selection of pilot sites for the minigrids. The MoEWR initially identified three preferred locations, while UNDP advocated for a larger pool of preselected sites to enable a competitive selection process. This was later resolved with the Government agreeing to preselect nine potential sites, from which three would be finalized for the pilot phase. However, the process resulted in a further six-month delay in project implementation.

Specifically, procurement issues regarding project implementation partners arose because the implementing organization, being a public entity, was subject to strict public procurement requirements.  Work planning for the project remains results-based and is supported by UNDP CO. To maintain alignment between project activities and expected results, PMU prepares annual workplans derived from the multi-annual workplan outlined in the project document, which is directly linked to the project’s results framework. During the mid-term review, the evaluation team found no evidence of any modifications made to the results framework of the AMP Somalia project.

### Finance and Co-Finance

Engagements with the Project Management Unit (PMU) during the mid-term review indicated that the project’s results to date are generally commensurate with expenditures, with cost efficiencies achieved in several areas. Savings generated from the recruitment of international consultants and the completion of institutional assessments have been reallocated to engage an international expert to support MoEWR in developing a Rural Electrification Strategy—a new deliverable requested by the Ministry that was not originally included in the project design. Project efficiency was further enhanced through the strategic recruitment of a highly qualified national consultant who provided technical support to three international consultants across separate assignments: the DREI analysis, the minigrid delivery model, and the digital readiness assessment. This approach—using one consultant to support multiple tasks instead of hiring several was recognized as a valuable lesson learned, and at the time of the MTR, the project team planned to recruit two additional national consultants to provide continuous implementation support for the remainder of the project period.

With respect to financial disbursement, the review found no constraints on fund availability from UNDP’s side. However, there were delays from the government in finalizing the preselection of pilot sites, which consequently postponed activities linked to minigrid construction and the associated fund utilization. The MTR did not identify any significant deviations from the approved project budget.

Relevant financial data is available in the Project Information and Management System (PIMS), which can be accessed at any time as needed. PIMS enables continuous tracking of budget allocations, expenditures, and balances, providing useful insights into project implementation progress. Financial reporting is incorporated into the annual PIR. At the end of each calendar year, a combined delivery report bearing expended budget for the project is elaborated and certified by the implementing partners. UNDP maintains well-defined procedures for the disbursement of project funds. Once the annual work plan is finalized and the corresponding contracts or LoAs are signed, disbursements are made in line with agreed deliverables and milestones. Upon receipt of documentation supporting payment as outlined in the LoA, the details are entered into PIMS and submitted to the Programme Oversight Unit for verification to ensure compliance with internal guidelines and intended use of funds. After clearance and approval by senior management, the budget or payment request is processed through Quantum, after which the disbursement is executed.

With respect to co-financing, the AMP Somalia project benefits from two forms of support: cash co-financing from UNDP and parallel co-financing from other partners, namely the World Bank and the Swedish International Development Agency (SIDA). MoEWR is responsible for implementing the other projects contributing to this parallel co-financing, and close coordination is maintained between these initiatives and the AMP project. However, the MTR team did not receive formal documentation such as co-financing letters confirming the actual level of parallel co-financing materialized for each co-financier as of the time the MTR was being conducted. For UNDP’s cash co-financing, commitments are being tracked, and expenditures monitored to ensure that funds are used as budgeted. UNDP allocates its co-financing on an annual basis in line with the project document and specific project activities. As of the MTR, the co-financing contributions from UNDP amounted to US$521.8 in 2023, US$71,045.98 in 2024, and US$40,439.82 in 2025. These figures are below the projected annual co-financing amounts as indicated in Table 7. Details of the project’s co-financing and level of materialization is presented in Table 8.

Table 7: Budgeted and actual co-financing from UNDP

| Period | UNDP Co-financing budget (USD) | Expense (USD) |
| --- | --- | --- |
| 2023 | 39,500.00 | 521.80 |
| 2024 | 74,000.00 | 71,045.98 |
| 2025 | 324,000.00 | 40,439.82 |
| Total | 437,500 | 112,007.60 |

Table 8: Financing and co-financing monitoring table

| Sources of Co-financing | Name of Co-financer | Type of Co-financing | Co-financing amount confirmed at CEO Endorsement (US$) | Actual Amount Contributed at stage of Midterm Review (US$) | Actual % of Expected Amount |
| --- | --- | --- | --- | --- | --- |
| Recipient Country Government | Ministry of Energy and Water Resources (MoEWR) | In kind | 3,500,000 | 1,750,000 | 50% |
| Donor Agency | World Bank | Grant | 157,200,000 | 87,200,000 | 55%A |
| GEF Agency | UNDP | Grant | 750,000 | 112,007.6 | 15% |
| Donor Agency | SIDA | Grant | 10,000,000 | 8,500,000 | 85% |
|  |  | TOTAL USD | 171,450,000 | 97,562,008 | 57% |

Source: ProDoc, latest co-finance table reported by the project team

Overall, the co-financing approach is assessed as functional only to a limited extent, with substantial weaknesses in the tracking and reporting of co-financing amounts. These issues require urgent attention in the next project phase to ensure transparency, accuracy, and strategic use of co-financing to achieve project objectives. The MTR did not identify any evidence relating to significant or major revisions to the project budget.

### Project Level Monitoring and Evaluation Systems

The MTR team assessed the main monitoring and evaluation (M&E) tools of the project, in terms of their ability to generate the necessary and relevant information for effective oversight. These tools included annually produced project implementation reports, this midterm review report, and the planned terminal evaluation report. The tools presented provided complete information on tracking progress for the project up to this point.

M&E for the AMP Somalia project began during the inception phase. Following a delay between project design and official launch, the inception workshop served to introduce the project to stakeholders, clarify roles and responsibilities, and review baseline indicators, project context, and the multi-annual workplan. By the end of the workshop, the project’s M&E framework was agreed upon. While UNDP operates under its own M&E framework, this has been adapted to the national context. Annual workplans are derived from the multi-annual plan and outline specific responsibilities for UNDP and the Government, represented by MoEWR. Once the annual workplan is approved, detailed Excel-based monitoring tools and risk logs are developed. Project tracking occurs across several levels—linking the country’s programme document, national development strategies, and global frameworks such as the SDGs. The indicators included in the annual workplans feed into these overarching frameworks and are reflected in the monitoring plan attached to the LoAs. The project board endorses both the annual workplans and corresponding budgets, marking the start of annual M&E activities. The Ministry of Energy participates in M&E primarily through oversight and monitoring of their respective LoAs.

Within UNDP, project M&E are supported by both the project’s dedicated M&E function and the oversight unit, which conduct regular supervision and field monitoring. External validation is ensured through third-party monitoring, including spot checks and audits performed by independent firms. Joint field missions involving UNDP and government representatives are also planned as part of the project’s M&E framework. At the regional level, the regional AMP project team provides additional oversight and strategic recommendations. Equally, the RTA from RBAS provides M&E support through conducting in-country monitoring missions and in the review and provision of feedback on PIRs. Discussions with the (PMU) confirmed that while M&E tools are selected based on data requirements, UNDP has a robust set of established instruments, such as surveys among others. For example, surveys will be used in the minigrid pilot studies to collect baseline and performance data.

The financial management of the M&E assigned budget was assessed to understand if adequate and to gauge how efficiently they have been used.  The M&E subcomponent under Component 4 discusses the possibility of procuring international consultants to carry out M&E activities, monitoring the results framework, while paying attention to GEF-specific indicators, and carry out field missions, stakeholder interviews and conducting the midterm evaluation. The international consultants will also assess and document lessons learned and conduct the terminal evaluation at the end of the project. The project budgeted USD 50,000 for the procurement of international consultants for M&E activities, representing about 31% of the total M&E budget. Overall, the resources allocated for M&E for the project was deemed sufficient and rated Highly Satisfactory. However, more resources may be required for participatory monitoring that involves local communities to engage in monitoring at the minigrid pilot sites. The digital platform under component 4 will further strengthen monitoring through the collection of data on use of electricity.

The review also examined the extent to which gender considerations have been integrated into monitoring systems. The M&E framework outlined in the ProDoc includes gender-disaggregated indicators and discusses the collection and analysis of gender-disaggregated data, with gender representation used in monitoring the various indicators.  Gender indicators include women-owned small businesses, female private sector investors, women-led organizations. Concrete gender-related activities achieved so far by the AMP Somalia include gender analysis being conducted at pilot minigrid sites, mapping of women’s associations as stakeholders, encouraging a gender-balanced and gender-sensitive leadership during project implementation. Targeted initiatives such as trainings for female solar technicians have also been successfully done. However, there are still challenges in gender mainstreaming such as breaking the cultural gender-based stereotypes, which would enhance inclusion in projects of such nature.

### Stakeholder Engagement

The project developed strong partnerships by engaging with state entities, private sector actors (ESPs and financial institutions), academic institutions and NGOs as was originally envisaged in the Stakeholder Engagement Plan (SEP). There are continuous efforts by the PMU to broaden stakeholder involvement throughout the implementation. Among the stakeholders, women’s groups showed a strong engagement in the national dialogue and DREI workshops, and their participation helped ensure gender mainstreaming into project implementation.

A separate focus was placed on understanding the level of involvement from national governments. The evaluators found that national government stakeholders are clearly supportive of the AMP project and remain actively involved in its implementation. During interviews, state actors opined that they are aligned with the project’s goals especially when it relates to enhancing the policy and regulatory framework and environment for minigrids. They generally perceive the project as timely, relevant and helpful since it is strongly aligned with the needs of Somalia pertaining to the energy sector in general and minigrids in particular. The state actors confirmed they have been engaged through various channels like the TAC, technical working groups, the steering committee and consultations.

The extent to which public participation and awareness-raising contributed to project progress was also examined. A strong level of stakeholder participation has contributed to the level of success so far achieved by the project, especially in relevant activities such as the national dialogue and DREI workshops (March 2024) which saw the participation of a wide range of stakeholders chosen from the national government institutions, women’s groups, private sector and ESPs among others. This showed a high level of ownership and improved collaboration between key institutions having a stake in the project implementation.

Lastly, the evaluation looked at how the project engaged women and girls, and whether gender-related efforts were adequately integrated. The level of engagement was rated as satisfactory. At the inception phase of the project, a Gender Analysis and GAP were developed to guide the integration of gender considerations into all aspects of the project from the design throughout the implementation phase. A gender specialist was also recruited to lead the process of gender mainstreaming into project activities. The aim of the GAP was to encourage and promote the participation of women and girls, in the activities of the AMP project, close gender gaps in decision-making and economic opportunities while building on the different needs, roles and access to and control over energy resources among men and women. The GAP was to support gender equality by promoting women’s involvement in technical, financial, and policy aspects of the energy transition. Progress reporting indicated that concrete actions on gender mainstreaming had been taken, such as women’s participation in the national dialogue and DREI workshops that were organized as part of the AMP project. Women’s participation has been highlighted under Outcomes 1 and 3 of the project, with a remarkable engagement in five trainings organized which saw the participation of 44 women out of 133 participants (Outcome 3) from various stakeholders. Under Outcome 2, it is expected that women are equitably represented in the established Renewable Energy Sector Association (RESA), while their engagement in consultations for the Digital Readiness Assessment could not be neglected.

### Social and Environmental Standards (Safeguards)

The project’s current risk ratings, as documented in the Social and Environmental Screening Procedure (SESP) from September 2021 (UNDP 2021), were carefully reviewed as part of the midterm review.

The level of agreement on these risk ratings was assessed as high – the SESP identified a total of 21 risks with the following risk ratings: Moderate (12 risks – Risks 2, 3, 5, 6, 7, 8, 9, 10, 11, 12, 13 and 14); and Substantial (9 risks – Risks 1, 4, 15, 16, 17, 18, 19, 20 and 21). The overall risk rating of the project as per the SESP is substantial and the following principles and safeguard standards were triggered: human rights; Gender Equality and Women Empowerment; Accountability; Biodiversity Conservation and Sustainable Natural Resource Management; Climate Change and Disaster Risks; Community Health, Safety and Security; Cultural Heritage; Displacement and Resettlement; Indigenous Peoples; Labour and Working Conditions; and Pollution Prevention and Resource Efficiency.

Progress in implementing the social and environmental management measures outlined in the SESP was also assessed. Based on the SESP for the AMP Somalia project (2021), the following measures shall be implemented:  a stakeholder engagement plan, gender analysis, capacity assessment for duty-bearers and right-holders, and indigenous people’s analysis, with the likelihood that other targeted assessments be carried out including: a cultural heritage analysis, a climate risk assessment, a disaster risk assessment, a hazard assessment and a health impact assessment. . The Gender Action Plan was updated after an external gender specialist supported the project team in 2023 through 2024 and the project’s stakeholder engagement plan has been under implementation. The MTR noted that other targeted assessment such as the environmental and social impact assessment are linked to the minigrid pilots and will only happen once the sites for the pilots have been determined. Similarly, except for the gender action plan and the stakeholder engagement plan, other management plans (e.g. environmental and social management plan) will be elaborated and implemented once sites for minigrids have been selected and installation and construction of the minigrids are ongoing.  The project has an accountability and grievance mechanism but during stakeholder consultations as part of the MTR, majority of consulted stakeholders were unaware of the mechanism. Hence, this is an aspect to be reinforced by the project team at all levels, especially within communities during the construction of the minigrids.

### Reporting

To support effective implementation, the project follows regular reporting mechanisms to ensure timely updates on activities. Annual progress reports (PIRs) are prepared by the project team and shared with project stakeholders. Going forward, the project would benefit from establishing clear targets for each indicator in the GAP, systematically monitoring progress toward these targets, and reporting on the results in the PIR.  Two yearly meetings were envisaged for the Project Board and more frequent meetings for the Technical Advisory Committee to enable the project monitor progress and ensure proper coordination. However, the first Project Board meeting happened in June 2025 although the inception workshop of the project in February 2023 saw the participation of the Project Board members. The MoEWR is required to report on the progress of their tasks to the PMU.

The MTR noted several instances where lessons learned have been effectively integrated into project implementation. For example, one key lesson reflected in the LOAs concerns the recruitment of consultants. The project recognized that engaging a smaller number of highly qualified consultants, embedded within the Ministry of Energy and Water Resources (MoEWR) for the project’s duration to support multiple international experts, is a more efficient and coordinated approach than hiring numerous consultants each assigned to narrow, task-specific roles.

### Communications & Knowledge Management

Internal communication within the project is generally regular and effective as planned. Communications have been kept frequent among stakeholders, though the Project Board has only held one meeting in June 2025 since the project started, as a result of delays during the inception phase.

Internal communication within the project is coordinated through the PMU, Technical Committee, and Steering Committee. Stakeholders engage through regular coordination meetings and email exchanges. Formal meetings are held on a quarterly basis, complemented by more frequent communication through emails and thematic working groups. The Technical Committee convenes more often to address day-to-day implementation matters. Government counterparts confirmed that there is a strong and collaborative relationship between the UNDP Country Office and the MoEWR, which allows the Ministry to easily reach out to UNDP to arrange ad hoc meetings whenever project-related issues arise.

The AMP has made progress in knowledge management, integrating it across all project components. Lessons learned from the DREI trainings, workshops and readiness assessments have been documented and circulated using internal reports, stakeholder presentations and the regional AMP Communities of Practice platform. Knowledge products produced included workshop reports/ summaries, policy brief and training materials which were disseminated among key stakeholders such as government ministries, ESPs and financial institutions. Under Outcome 1, the project supported extensive stakeholder consultations to inform the drafting of the National Mini-Grid Policy and Regulations. These discussions generated key insights on regulatory frameworks and delivery models, which were documented in workshop reports and shared with MoEWR and NEA. For Outcome 2, the project developed a solar and hybrid mini-grid training curriculum through sector mapping and technical consultations, with results disseminated to vocational institutions and private sector stakeholders. Under Outcome 3, capacity-building activities included financial modeling training and structured dialogues with financial institutions, yielding important findings on investment challenges and opportunities. Finally, Outcome 4 advanced the sector’s digital transformation through a Digital Readiness Assessment and knowledge-sharing initiatives that informed the preparation of a national digital strategy for the energy sector. The Project Board Meeting convened in June 2025 functioned as an important platform for knowledge exchange, during which the accomplishments of 2024 and the work plan for 2025 were presented and endorsed. Feedback mechanisms in place for the project includes the grievance redress mechanism (GRM) and surveys administered during workshops although majority of stakeholder consulted were unaware of the project’s GRM. The communication approach was rated as satisfactory.

The evaluation also considered external communication strategies used to inform the public and broader audiences about project progress and impacts. It is primarily managed through the Africa Minigrids program website which is public as well as a dedicated LinkedIn page for AMP projects managed by the regional AMP project and a LinkedIn page for the UNDP Somalia CO where news relating to the Somalia AMP project are published. Activities such as project board meetings have been uploaded on social media platforms such as Facebook, Twitter and Youtube.  The AMP project has also enhanced its visibility through participation at major events such as the 29th session of the UNFCCC Conference of the Parties (COP29), community of practice, national events on minigrid awareness and trainings. The regional AMP Community of Practice meetings held annually (online or in-person) brings together all AMP national projects for experience sharing. For instance, the AMP Somalia project team participated in the AMP community forum co-organised by the AMP regional project and the Energy Access Investment Forum in Lagos, Nigeria. This inaugural in-person Community of Practice event offered valuable opportunities for networking, knowledge exchange, and sharing project achievements. During the sessions, the Somalia team presented the distinctive features of the country’s energy landscape, outlining progress made, existing challenges, and emerging opportunities in a context characterized by the absence of a national grid and a largely unregulated, privately driven electricity sector.  Project visibility is further boosted by events such as the AMP launch, the DREI workshop, and the national dialogue.

A concise summary of the project’s contribution to sustainable development and global environmental benefits is provided as follows: The AMP Somalia project contributes significantly to sustainable development by addressing energy access gaps in rural communities through decentralized renewable energy solutions. Its focus is on piloting innovative minigrid business models, particularly in underserved areas across the country.  Capacity building has been a central feature of the project. AMP has strengthened the technical and business capacities of potential minigrid developers and operators through targeted training. From a global environmental perspective, the project promotes the displacement of fossil fuels through solar PV-battery systems, reducing future GHG emissions in Somalia’s growing off-grid sector – this will however be achieved once construction of the minigrids are completed and they have been commissioned. The project's use of the DREI methodology to identify derisking instruments is aligned with climate finance principles, increasing the long-term investment attractiveness of clean energy in the country. Despite coordination challenges which caused delays, AMP Somalia demonstrates strong potential for delivering socially inclusive and environmentally beneficial energy access models—advancing Sustainable Development Goals (SDGs) 5, 7, and 13 while supporting long-term climate mitigation goals.

Finally, the knowledge products and activities developed during implementation were reviewed against the approved knowledge management (KM) approach. The number and quality of these products were rated as satisfactory.

## Sustainability

The evaluation reviewed whether the risks identified in the Project Document, Annual Project Reviews, and the Quantum Risk Register represent the most critical threats to achieving the project's intended outcomes. The appropriateness and timeliness of the risk ratings were assessed as adequate; they are revised on a quarterly basis. While the identified risks in the risk register are still valid, well captured, and appropriately rated, three additional risks had been identified at the time when the MTR was being conducted. These risks include: delays in procurement for the minigrid pilots; the upcoming 2026 elections in Somalia; and the phasing out of the African Union mission in Somalia.

### Financial Risks to Sustainability

A major project outcome with ongoing financial implications is the commissioning of the mini-grid pilots, which must remain economically viable after project completion. These systems are expected to generate sufficient revenue to sustain their operations. The DREI study for Somalia highlighted that electricity tariff is unregulated and is among the highest in the region (1 USD/kWh). The DREI equally cited high financing risk as a barrier for ESP to engaged in minigrid construction and operation in the country. The AMP Somalia approach builds on the country’s existing private-sector–driven energy model, whereby mini-grids are owned and operated by Energy Service Providers (ESPs). Through the project, ESPs will receive grant support designed to help them operate profitably in peri-urban and rural contexts. This grant will take the form of a results-based financing payment. At the time of the MTR, the National Energy Authority (NEA) was developing a tariff regulation and directive, including a standardized tariff calculation tool to enable ESPs and NEA to jointly determine cost-reflective tariffs that ensure financial viability. The subsidy tender under the pilot will specify a target tariff of USD 0.35/kWh, and bidding ESPs will be required to demonstrate via the tariff calculation spreadsheet that their proposed business model can theoretically reach this price point. To further strengthen affordability and revenue security, the project will promote productive uses of energy (PUE) as a complementary income stream for households and small enterprises. All PUE equipment financed under the pilot will be delivered through a third-party ownership model, whereby the ESP procures and retains ownership of the equipment and leases it to end-users as part of an integrated “energy-as-a-service” offering. This model reduces upfront financial burdens for customers and helps ensure proper maintenance and asset longevity. While the AMP Somalia pilot demonstrates strong potential to reduce electricity tariffs from approximately USD 1/kWh to USD 0.35/kWh, it remains uncertain whether this reduced tariff will be affordable for all households—particularly those not engaged in PUE activities. It is therefore worthwhile for the project to embark on a willingness to pay study in the sites that would be selected in order to determine the capacity of the population to pay for the energy services. The financial risk to sustainability is rated Moderately Likely.

### Socio-Economic Risk to Sustainability

The pre-selection of nine potential sites for the minigrid pilots carefully considered security conditions—ensuring that only relatively stable and government-controlled areas were shortlisted. However, the broader volatility in parts of the country continues to pose a potential political risk to project implementation and long-term operation. Even in areas deemed secure, there remains a risk of intimidation, extortion, or sabotage by non-state actors. During consultations, an electricity service provider cited incidents where they had received threatening communications from individuals reportedly associated with Al-Shabaab, warning them against initiating minigrid construction at a site about 20 km from Mogadishu. Such risks could deter private sector participation, delay construction, and increase operational costs due to heightened security requirements. Sustaining project outcomes will therefore depend on close coordination with local authorities, continuous security risk assessments, and building strong community relationships to foster local ownership and safeguard infrastructure investments. Equally, the prevailing negative perceptions among some local communities regarding the safety and reliability of minigrid systems constitutes a key socio-economic risk to the long-term sustainability of the project. During consultations, electricity service providers reported that in certain areas, communities associate minigrid installations with increased risks of fire outbreaks and incidents of livestock electrocution. Such misconceptions can create resistance to project interventions, limit community acceptance, and reduce willingness to connect to or pay for electricity services. Without proactive engagement, these perceptions may undermine the project’s objective of expanding access to clean and reliable energy. To mitigate this risk, targeted awareness-raising and sensitization campaigns should be conducted to inform communities about the safety standards, operational procedures, and benefits of modern minigrids. Involving community leaders, women’s groups, and local technicians in outreach efforts will help build trust, dispel misconceptions, and foster local ownership—critical factors for the sustainability of minigrid operations beyond the project’s lifespan. Finally, Sustainability will ultimately rely on continuous capacity development and effective local partnerships. The creation of a one-year certification or diploma program on minigrids, currently awaiting accreditation by the Ministry of Education, represents an encouraging step toward building national technical expertise essential for long-term impact. Nonetheless, stakeholders highlighted concerns regarding the limited availability of qualified instructors within Somali academic institutions to implement the program effectively. Despite this challenge, all stakeholders consulted including government entities demonstrated strong commitment to sustaining the project’s outcomes beyond its lifetime, reflecting a high level of ownership and alignment with its long-term vision. Government stakeholders were fully aware of the project and highly supportive of its objectives and activities as they align with the priorities of the nation relating to enhancing rural electrification through the deployment of renewable energy technologies.

Discussions with Energy Service Providers (ESPs) revealed varying levels of interest in participating in the AMP minigrid pilots. Larger and well-established grid operators tend to focus on high-value projects worth hundreds of millions of dollars, which exceed the scale of those promoted under the Somalia AMP initiative. In contrast, smaller companies specializing in minigrids are more inclined to participate in projects of this nature. Moreover, major operators show limited willingness to invest in rural areas due to perceived risks such as insecurity and the low purchasing power of rural communities.

The socio-economic risk to sustainability of the AMP Somalia project is rated Moderately Likely.

### Institutional Framework and Governance Risk to Sustainability

The project has contributed to the development of minigrid policies for both Somalia and Somaliland, establishing a foundation for improved regulation and governance within the electricity sector. Government representatives interviewed during the MTR expressed a strong commitment to applying the newly developed policy and regulatory instruments to strengthen sector oversight. The project has also helped strengthen institutional capacities across Somalia’s energy sector. With its support, a Rural Electrification Unit was created within the Ministry of Energy to better address issues related to rural energy access and electrification. Furthermore, the regulatory assistance provided through the AMP enabled the National Energy Authority (NEA) to develop and implement a licensing fee system, representing a step toward a more formalized and regulated energy framework. Capacity development was also advanced through targeted training for both public- and private-sector personnel. Staff from MOEWR, NEA, and private energy companies received training on mini-grid policy, regulatory processes, tariff modelling, mini-grid technologies, financial and business planning. In Somaliland, Ministry of Energy staff were additionally trained on mini-grid system design using HOMER software, installation and commissioning procedures, health, safety and environmental standards, and productive uses of energy in agriculture and fisheries. These skills are expected to continue benefiting the sector beyond the life of the project, and the AMP mini-grid pilot model offers a basis for replication under future national initiatives.

An identified challenge relates to staff turnover within government institutions, which poses a risk to institutional sustainability. Capacity built among Ministry of Energy and Water Resources (MoEWR) personnel through their involvement in the AMP project may be lost if trained staff transition to other organizations, leaving a skills gap. Based on these factors, the institutional framework and governance risk to sustainability is assessed as Moderately Likely.

### Environmental Risks to Sustainability

The AMP Somalia project faces several environmental risks that could impact the long-term sustainability of its outcomes. A key environmental risk that may affect the long-term sustainability of the minigrid installations in Somalia is flooding, particularly in low-lying or riverine areas prone to seasonal inundation. Somalia experiences recurrent flash floods and riverine flooding and these events are projected to increase in frequency and intensity under climate change scenarios, posing significant risks to energy infrastructure. Flooding can damage generation equipment, distribution lines, and control systems, leading to costly repairs, service disruptions, and prolonged downtime. Prolonged waterlogging can also compromise the structural integrity of foundations, battery storage units, and transformers, while associated debris and sediment can hinder access and maintenance. In coastal zones, storm surges and saline intrusion present additional threats to system components and corrosion-sensitive materials. To mitigate these risks, site selection and engineering design should incorporate detailed hydrological and topographic assessments to avoid flood-prone areas, ensure adequate elevation of key infrastructure, and implement effective stormwater drainage systems. Incorporating climate-resilient design standards—such as elevated platforms for electrical components, reinforced mounting structures, and water-resistant enclosures will be critical. In parallel, developing emergency preparedness and maintenance protocols can help ensure system resilience and operational continuity in the event of extreme weather. Without such measures, flooding could undermine the reliability and economic viability of the minigrid systems, reducing their contribution to long-term energy access and climate resilience in target communities.

Another environmental risk identified relates to wind damage and dust accumulation that could compromise the long-term sustainability of the planned minigrid installations. During stakeholder consultations, Energy Service Providers (ESPs) highlighted that strong winds pose a significant threat to solar infrastructure, citing an example in Hargeisa where solar panels installed at a hospital were completely destroyed by windstorms. Given Somalia’s arid and semi-arid climatic conditions, many project sites are exposed to high wind speeds and frequent dust storms, which can damage mounting structures, reduce panel efficiency, and increase maintenance requirements. To mitigate these risks, robust design and installation standards should be enforced, including wind-resistant mounting structures, appropriate anchoring systems, and site selection that considers prevailing wind patterns. Routine maintenance schedules and capacity-building for local operators should be institutionalized to ensure timely cleaning and inspection. Incorporating environmental risk management into the operations and maintenance (O&M) plan will be critical to ensuring the sustainability and reliability of the minigrid systems in Somalia’s challenging environmental context.

The environmental risk to sustainability of the AMP project is rated Moderately Unlikely.

# CONCLUSIONS AND RECOMMENDATIONS

## Conclusions

At mid-term, the AMP Somalia project has laid an important foundation for expanding access to modern, reliable, and low-carbon energy solutions in a country with no national grid and a heavily privatized, diesel-dependent electricity market. Despite a delayed start caused by institutional mandate conflicts between MoEWR and MoECC and subsequent delays in pilot site preselection, the project has made substantive progress in strengthening the enabling environment, improving institutional capacity, and preparing the groundwork for the deployment of pilot minigrids.

Key strengths of the project include the successful development of core policy and regulatory instruments—such as the national mini-grid policy, tariff and licensing regulations, and the DREI techno-economic analysis—which represent major advances for a sector previously lacking formal regulatory structures. Capacity development has been robust, encompassing government institutions, ESPs, and academic bodies, reinforced by the creation of a Rural Electrification Unit within MoEWR and the development of a national training curriculum on solar and hybrid mini-grids. Strong engagement with the AMP Regional Project has facilitated knowledge exchange, digital transformation efforts, and alignment with international mini-grid best practices.

The project has also demonstrated positive results toward establishing delivery models and policy derisking instruments, expanding digital readiness, and strengthening coordination among public and private stakeholders. Progress towards the achievement of outcomes is largely satisfactory: Outcome 1 and Outcome 4 are on track, while Outcome 2 and Outcome 3 show moderate progress, constrained primarily by delays in procurement and pilot site approval.

However, the project also faces notable weaknesses that threaten timely achievement of results. The project has encountered considerable implementation challenges, particularly stemming from institutional mandate overlaps between MoEWR and MoECC during the initial phase, delaying the approval oft he annual workplan. Additional delays arose from the procurement of international consultants and the government’s protracted process of finalizing preselected sites for the minigrid pilots, collectively slowing progress across all project outcomes particularly for components involving pilot construction, productive use deployment, and financing mechanism operationalization. Although a Gender Action Plan was developed with accompanying indicators, the absence of measurable targets has made it difficult to assess the project’s performance from a gender perspective. The project also demonstrated weaknesses in monitoring the realization of parallel co-financing commitments made during the PPG stage

Sustained efforts to strengthen coordination, establish and monitor gender targets, and accelerate procurement for the minigrid pilots along with an extension of the project’s implementation period will be essential to realizing the project’s full impact and ensuring its long-term sustainability.

## Recommendations

Corrective actions for the design, implementation, monitoring, and evaluation of the project

- Enhance Coordination and Communication: It was noticed at the time of this MTR that the Project Board does not meet as frequently as expected. Since the project began, the PB has held one meeting this year, while it is understandable that there have been delays in implementation, it is also recommended that there are more frequent meetings to monitor progress and make any updates to the project workplans as needed. Coordination meetings should be organized more frequently to discuss any issues affecting the project and address them in a timely manner (Timeline: throughout the second half of the project).

- Enhance gender responsiveness during the second half of project implementation. It is recommended that the Gender Action Plan (GAP) be updated to include specific, measurable targets and baselines aligned with existing indicators. These targets should capture both quantitative and qualitative dimensions of gender equality—such as the number and proportion of women participating in training, consultations, employment opportunities, and decision-making processes related to minigrid development and management. In addition, all project monitoring, reporting, and documentation—including meeting attendance lists, training records, and progress reports—should be systematically sex-disaggregated. This will enable the project team and stakeholders to track gender participation and outcomes more accurately (Timeline: Before the end of Quarter 1 of 2026).

- Strengthen application of the Grievance Redress Mechanism. While a Grievance Redress Mechanism (GRM) has been established for the project, consultations indicate that many stakeholders, including community members and local partners, are unaware of its existence and procedures. To enhance accountability and ensure effective stakeholder engagement, the GRM should be actively publicized and mainstreamed across all project activities during the second half of implementation. It is recommended that the project team: (i) Integrate GRM awareness into all community consultations, training sessions, and project events; (ii) Develop and display posters and information materials in local languages at key project sites, local government offices, and community centers; (iii) Designate a focal point at the local level to receive and document grievances; and (iv) Periodically review and report on grievances received and actions taken to ensure transparency and learning. Strengthening communication and visibility of the GRM will promote inclusiveness, build trust among stakeholders, and help identify and resolve potential conflicts early—thereby supporting the project’s overall sustainability and social acceptability Timeline: immediately and for the remaining duration of the project implementation).

Actions to follow up or reinforce initial benefits from the project

- Strengthen Institutional Capacity for Delivery of the Minigrid Curriculum through Strategic Partnership. While the project has developed a comprehensive one-year diploma/certification curriculum on minigrids, its effective rollout is constrained by the limited availability of qualified instructors within Somali academic institutions. To address this capacity gap and ensure sustainability, it is recommended that the project establish a partnership with the Res4Africa Foundation to support the implementation of the curriculum. Res4Africa has demonstrated experience in developing and delivering renewable energy and minigrid training programs in countries such as Eritrea and Mozambique, providing both technical content and instructor training. Through this collaboration, Res4Africa could assist in training trainers, developing teaching materials, and building institutional competence within targeted vocational and higher education institutions. This approach would ensure a smooth transfer of knowledge and pedagogical skills, enabling Somali institutions to independently deliver accredited minigrid programs in the future. In parallel, the project should facilitate coordination with the Ministry of Education to expedite curriculum accreditation and recognition, ensuring national ownership and long-term integration of the program into Somalia’s technical education framework (Timeline: Before the end of Quarter 1 of 2026).

- Strengthen Tracking and Reporting of Co-Financing Contributions. It is recommended that the project establish a systematic mechanism for tracking and reporting on co-financing commitments made by development partners and other contributors during the design phase. While several donors and stakeholders had pledged financial and in-kind support to complement GEF resources, there is currently no structured process to monitor, verify, and document the actual realization of these contributions. This limits the project’s ability to demonstrate leveraged resources and overall financial performance. To address this, the Project Management Unit (PMU), in collaboration with the Ministry of Energy, should: (i) Develop and maintain a co-financing tracking matrix capturing pledged, received, and expected contributions by source, type (cash or in-kind), and utilization status; (ii) Regularly update and report co-financing data through quarterly and annual progress reports; (iii) Engage with co-financing partners to confirm commitments, clarify disbursement timelines, and identify constraints affecting delivery; and (iv) Integrate co-financing updates into project steering committee meetings to ensure transparency and joint follow-up. Enhanced tracking and communication on co-financing will not only improve financial management and accountability but also help mobilize additional support and sustain donor confidence during the second half of project implementation (Timeline: for the entire duration of the project implementation period).

- Request a 12-Month No-Cost Extension to Ensure Timely and Effective Delivery. It is recommended that the project formally request a 12-month no-cost extension to compensate for the implementation delays experienced during the inception and early operational phases. The project’s initial progress was hindered by institutional mandate overlaps between the Ministry of Energy and the Ministry of Environment, which delayed agreement on implementation arrangements, and by the time required for the pre-selection and validation of pilot minigrid sites. These factors significantly compressed the timeframe available for construction, commissioning, and operational learning. Furthermore, the national elections scheduled for 2026 may temporarily disrupt project activities and decision-making processes, posing an additional risk to timely delivery. The proposed extension would therefore serve as a contingency measure to safeguard against potential political and administrative slowdowns. Securing the extension will also provide the project with adequate time to complete construction of the pilot minigrids, ensure proper testing and operationalization, and document lessons learned from their functioning, critical for replication and scaling within the Africa Minigrid Program framework. This additional period should be accompanied by a revised implementation plan with clear milestones, risk mitigation measures, and strengthened coordination between the key implementing ministries to maintain momentum and accountability during the extended period (Timeline: Before the end of Quarter 1 of 2026).

Proposals for future directions

- Organize pre-bidding meetings to attract qualified bidders. Consultations with Energy Service Providers (ESPs) indicated differing levels of interest in engaging with the AMP minigrid pilots. Larger, well-established grid operators generally prioritize large-scale, high-value projects—often worth hundreds of millions of dollars—beyond the investment scope of the Somalia AMP initiative. Conversely, smaller firms with experience in decentralized energy and minigrid systems have shown greater willingness to participate. Major operators also expressed reluctance to invest in rural locations, citing challenges such as security risks and limited purchasing power among rural populations. To broaden participation and attract capable bidders, the project should consider organizing a roadshow and a pre-bidding meeting (either virtual or in-person) during the procurement stage. These outreach efforts would help publicize opportunities, clarify eligibility and technical criteria, and encourage competitive, well-prepared proposals—thereby reducing procurement delays and enhancing the quality of submissions (Timeline: Before the end of Quarter 4 of 2025).

- Enhance Community Awareness and Sensitization on Minigrid Safety and Benefits. To address the negative perceptions among community members regarding the safety of minigrid systems—particularly concerns about fire risks and electrocution of livestock—it is recommended that the project implement a structured community sensitization and outreach program in all pilot sites. This program should aim to build understanding and trust around minigrid technologies by providing clear information on system safety features, proper installation standards, and operational protocols. Sensitization activities should be participatory and culturally appropriate, involving community leaders, elders, women’s groups, and youth representatives to ensure inclusivity and local ownership. Practical demonstrations, information sessions, and visual materials (in local languages) should be used to explain safe use, maintenance, and the socioeconomic benefits of the minigrids. Collaboration with Energy Service Providers (ESPs) and local authorities is recommended to reinforce safety messages and establish mechanisms for reporting and addressing technical incidents promptly. By improving awareness and confidence in minigrid operations, the project will foster stronger community acceptance, reduce resistance to infrastructure deployment, and enhance the long-term sustainability and local stewardship of the installed systems (Timeline: for the entire duration of the project implementation period).

- Strengthen Climate and Environmental Resilience of Minigrid Infrastructure. To ensure the long-term sustainability and reliability of the minigrid systems, it is recommended that the project integrate climate-resilient design and environmental risk management measures into the construction and operation phases of all installations. Given the risks associated to strong winds and flooding, the design specifications should ensure compliance with wind- and flood-resilient engineering standards. This includes elevated platforms or reinforced foundations in flood-prone areas, wind-resistant mounting structures, proper anchoring of solar panels, and drainage systems to prevent water accumulation around key infrastructure. Furthermore, comprehensive environmental screening and site-specific risk assessments should be conducted for the sites to identify exposure to wind and flood hazards. The results should inform both technical design and community engagement plans. Local operators and community beneficiaries should receive additional training in environmental risk preparedness and routine maintenance, including safe cleaning methods for dust accumulation and early detection of structural damage. Finally, it is recommended that the project develop and implement a climate and environmental risk management protocol as part of its Operations and Maintenance (O&M) framework. This will help ensure regular monitoring, timely maintenance, and adaptive responses to extreme weather events, thereby improving the resilience, efficiency, and lifespan of the minigrid installations once they have been commissioned and beyond the life of the project (Timeline: during construction of the minigrids and prior to project closure).

- Expedite the Procurement Process for Minigrid Implementation. To ensure timely delivery of outputs in the second half of the project, it is recommended that UNDP expedite the procurement process for selecting qualified service providers for the design, construction, and installation of the three-pilot solar minigrids. Delays in procurement represent a critical bottleneck that could significantly hinder progress toward achieving project outcomes and demonstrating proof of concept. To address this, UNDP should:

- Prioritize and fast-track the procurement workflow, including early resolution of administrative or technical bottlenecks;

- Strengthen coordination between the UNDP Country Office, the Project Management Unit (PMU), and the Energy Service Providers (ESPs) to ensure clarity on technical specifications and timelines;

- Adopt proactive procurement planning, including pre-qualification of potential suppliers or use of Long-Term Agreements (LTAs) where feasible; and

- Enhance communication and oversight, with regular progress reviews to track procurement milestones and identify potential delays early.

Accelerating procurement will be essential to maintain implementation momentum, ensure infrastructure readiness, and allow sufficient time for testing, community engagement, and capacity-building before project closure (Timeline: Before the end of Quarter 1 of 2026).

# LIST OF ANNEXES

Annex I: Terms of Reference of the Terminal Evaluation

Annex II: Evaluation Question Matrix

Annex III: Questionnaire used for Data Collection

Annex IV: MTR Rating Scales

Annex V: MTR Itinerary

Annex VI: Stakeholders Consulted

Annex VII: List of Documents Reviewed

Annex VIII: GEF Core Indicators

Annex IX: Signed UNEG Code of Conduct Form

Annex X: Signed MTR Clearance Form

Annex XI: Audit Trail_(attached as a separate file)

Annex XII: Progress towards outcomes analysis

- Terms of Reference of the MTR

Mid-Term Review Terms of Reference

Somalia National Child Project - Africa Minigrids Program (AMP)Midterm Review Terms of Reference

BASIC CONTRACT INFORMATION

Assignment: Conduct the Mid-term Review for the Africa Minigrids Program (AMP) Somalia national project, including review of available document, field mission, interviews with stakeholders, providing recommendations, and issuance of the MTR report.

Duty Station: Home-based with a mission to Somalia, Mogadishu

Type of Contract: Contractual services – firm contracted under an existing Long-Term Agreement (LTA) framework

Starting Date: 1 June 2025

Expected Duration of Assignment: 24 working days spread over 7 weeks

BACKGROUND

- Project Title

Somalia National Child Project under the GEF Africa Minigrids Program

- Project Description

The project’s components:

Component 1. Policy and Regulation

Component 2. Business Model innovation with private sector engagement

Component 3. Scaled-up financing

Component 4. Digital, Knowledge Management (KM) and Monitoring and Evaluation (M&E)

Project’s key stakeholders:

- Ministry of Energy and Water Resources (MoEWR) in Mogadishu;

- National Electricity Authority in Mogadishu

- Somaliland Ministry of Energy and Minerals (MOEM) in Hargeisa;

- Energy Regulatory Commission (ERC) for Somaliland;

- Puntland Ministry of Energy, Minerals and Water (MOEMW) in Garowe;

- Somali Bureau of Standards (SBS); and

- Somaliland Quality Control Commission (SQCC).

Geographical coverage of the project: Nationwide

Total resources:

| Financing Plan |  |
| --- | --- |
| GEF Trust Fund grant | USD 3,276,147 |
|  | USD 750,000 |
| (1) Total Budget administered by UNDP | USD 4,026,147 |
| co-financiers that will deliver project results included in the project results framework (Funds not administered through UNDP accounts) |  |
| In-kind co-finance by the Federal Government of Somalia: Ministry of Energy and Water Resources (MOEWR) | USD 3,500,000 |
| Grant co-finance disbursed under the World Bank’s programs in the energy sector in Somalia | USD 157,200,000 |
| Grant co-finance disbursed under SIDA’s support to programs in the energy sector in Somalia | USD 10,000,000 |
| (2) Total confirmed co-financing to this project not administered by UNDP | USD 170,700,000 |
| (3) Grand-Total Project Financing (1)+(2) | USD 174,726,147 |

- MTR Purpose

The MTR will assess progress towards the achievement of the project objectives and outcomes as specified in the Project Document, and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The MTR will also review the project’s strategy and its risks to sustainability.

The MTR will support understanding the project progress towards the overall target and can be used by the users to take corrective actions if needed as well as scale up the benefits through identified areas stakeholders the users may include the GEF, UNDP, the government of Somalia (led by the Federal Ministry of Energy and Water Resources, National Electricity Authority, ministries of energy in Somaliland and Puntland, Somali Bureau of Standards, and Somaliland Quality Control Commission among other public entities) as well as Electricity Service Providers and Renewable Energy Financiers.

UNDP evaluations must address how the project sought to mainstream gender in development efforts, considered disability issues and applied the rights-based approach.

- DUTIES AND RESPONSIBILITIES

The MTR report must provide evidence-based information that is credible, reliable and useful.

The MTR team will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Social and Environmental Screening Procedure (SESP)), the Project Document, project reports including Annual Project Review/PIRs, project budget revisions, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based review. The MTR team will review the baseline GEF focal area Core Indicators/Tracking Tools submitted to the GEF at CEO endorsement, and the midterm GEF focal area Core Indicators/Tracking Tools that must be completed before the MTR field mission begins.

A mixed method of qualitative and quantitative approaches is recommended. The MTR team is expected to follow a collaborative and participatory approach ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), the UNDP Country Office in Somalia, the Climate Change Mitigation and Energy Regional Technical Advisor, direct beneficiaries, and other key stakeholders.

Engagement of stakeholders is vital to a successful MTR. Stakeholder involvement should include interviews with stakeholders who have project responsibilities, including but not limited to the representative of:

- Ministry of Energy and Water Resources (MoEWR) in Mogadishu;

- National Electricity Authority in Mogadishu

- Somaliland Ministry of Energy and Minerals (MOEM) in Hargeisa;

- Energy Regulatory Commission (ERC) for Somaliland;

- Puntland Ministry of Energy, Minerals and Water (MOEMW) in Garowe

- Somali Bureau of Standards (SBS); and

- Somaliland Quality Control Commission (SQCC).

- Executing agencies, senior officials and task team/ component leaders, key experts and consultants in the subject area, Project Board, project stakeholders, academia, electricity service providers, renewable energy financiers etc.

The specific design and methodology for the MTR should emerge from consultations between the MTR team and the above-mentioned parties regarding what is appropriate and feasible for meeting the MTR’s purpose and objectives and answering the evaluation questions, given limitations of budget, time, and data. The MTR team must, however, use gender-responsive methodologies and tools and ensure that gender equality and women’s empowerment, as well as other cross-cutting issues and SDGs, are incorporated into the MTR report.

The final methodological approach, including interview schedule, field visits, and data to be used in the MTR, the data analysis approach should be clearly outlined in the Inception Report and be fully discussed and agreed upon between UNDP, stakeholders, and the MTR team.

The final MTR report must describe the full MTR approach taken and the rationale for the approach, making explicit the underlying assumptions, challenges, strengths, and weaknesses about the methods and approach of the review.

- Detailed Scope of the MTR

The MTR team will assess the following four categories of project progress. See the Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for extended descriptions.

- Project Strategy

Project Design:

- Review the problem addressed by the project and the underlying assumptions. Review the effect of any incorrect assumptions or changes to the context to achiev the project results as outlined in the Project Document.

- Review the relevance of the project strategy and assess whether it provides the most effective route towards expected/intended results. Were lessons from other relevant projects properly incorporated into the project design?

- Review how the project addresses country priorities. Review country ownership. Was the project concept in line with the national sector development priorities and plans of the country (or of participating countries in the case of multi-country projects)?

- Review decision-making processes: were perspectives of those who would be affected by project decisions, those who could affect the outcomes, and those who could contribute information or other resources to the process, taken into account during project design processes?

- Review the extent to which relevant gender issues were raised in the project design. See Annex 9 of Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines.

  - Were relevant gender issues (e.g. the impact of the project on gender equality in the programme country, involvement of women’s groups, engaging women in project activities) raised in the Project Document?

- If there are major areas of concern, recommend areas for

Results Framework/Logframe:

- Undertake a critical analysis of the project’s logframe indicators and targets, assess how “SMART” the midterm and end-of-project targets are (Specific, Measurable, Attainable, Relevant, Time-bound), and suggest specific amendments/revisions to the targets and indicators as necessary.

- Are the project’s objectives and outcomes or components clear, practical, and feasible within its time frame?

- Examine if progress so far has led to, or could in the future catalyse beneficial development effects (i.e. income generation, gender equality and women’s empowerment, improved governance etc...) that should be included in the project results framework and monitored on an annual basis.

- Ensure broader development and gender aspects of the project are being monitored effectively. Develop and recommend SMART ‘development’ indicators, including sex-disaggregated indicators and indicators that capture development benefits.

- Progress Towards Results

Progress Towards Outcomes Analysis:

- Review the logframe indicators against progress made towards the end-of-project targets; populate the Progress Towards Results Matrix, as described in the Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects; colour code progress in a “traffic light system” based on the level of progress achieved; assign a rating on progress for the project objective and each outcome; make recommendations from the areas marked as “not on target to be achieved” (red).

- Table. Progress Towards Results Matrix (Achievement of outcomes against End-of-project Targets)

| Project Strategy | Indicator | Baseline Level | Level in 1st PIR (self- reported) | Midterm Target | End-of-project Target | Midterm Level & Assessment | Achievement Rating | Justification for Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: | Indicator (if applicable): |  |  |  |  |  |  |  |
| Outcome 1: | Indicator 1: |  |  |  |  |  |  |  |
|  | Indicator 2: |  |  |  |  |  |  |  |
| Outcome 2: | Indicator 3: |  |  |  |  |  |  |  |
|  | Indicator 4: |  |  |  |  |  |  |  |
|  | Etc. |  |  |  |  |  |  |  |
| Etc. |  |  |  |  |  |  |  |  |

- Indicator Assessment Key

| Green= Achieved | Yellow= On target to be achieved | Red= Not on target to be achieved |
| --- | --- | --- |

In addition to the progress towards outcomes analysis:

- Compare and analyse the GEF Tracking Tool/Core Indicators at the Baseline with the one completed right before the Midterm Review.

- Identify remaining barriers to achieving the project objective in the remainder of the project.

- By reviewing the aspects of the project that have already been successful, identify ways in which the project can further expand these benefits.

- Project Implementation and Adaptive Management

Management Arrangements

- Review overall effectiveness of project management as outlined in the Project Document. Have changes been made and are they effective? Are responsibilities and reporting lines clear? Is decision-making transparent and undertaken in a timely manner? Recommend areas for improvement.

- Review the quality of execution of the Executing Agency/Implementing Partner(s) and recommend areas for improvement.

- Review the quality of support provided by the GEF Partner Agency (UNDP) and recommend areas for improvement.

- Do the Executing Agency/Implementing Partner and/or UNDP and other partners have the capacity to deliver benefits to or involve women? If yes, how?

- What is the gender balance of project staff? What steps have been taken to ensure gender balance in project staff?

- What is the gender balance of the Project Board? What steps have been taken to ensure gender balance in the Project Board?

Work Planning

- Review any delays in project start-up and implementation, identify the causes and examine if they have been resolved.

- Are work-planning processes results-based? If not, suggest ways to re-orientate work planning to focus on results?

- Examine the use of the project’s results framework/ logframe as a management tool and review any changes made to it since project start.

Finance and co-finance

- Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions.

- Review the changes to fund allocations as a result of budget revisions and assess the appropriateness and relevance of such revisions.

- Does the project have the appropriate financial controls, including reporting and planning, that allow management to make informed decisions regarding the budget and allow for timely flow of funds?

- Informed by the co-financing monitoring table to be filled out by the Commissioning Unit and project team, provide commentary on co-financing: is co-financing being used strategically to help the objectives of the project? Is the Project Team meeting with all co-financing partners regularly in order to align financing priorities and annual work plans?

| Co-financing source | Co-financing type | Co-financing amount (USD) | Actual Amount Contributed at stage of Midterm Review (USD) | Actual % of Expected Amount |
| --- | --- | --- | --- | --- |
| Ministry of Energy | In-kind | 3,500,000 |  |  |
| World Bank | Grant | 157,200,000 |  |  |
| Swedish Cooperation (Sida) | Grant | 10,000,000 |  |  |
| UNDP | Grant | 750,000 |  |  |
| TOTAL |  | 171,450,000 |  |  |

- Include the separate GEF Co-Financing template (filled out by the Commissioning Unit and project team), which categorizes co-financing amounts by source as ‘investment mobilized’ or  ‘recurrent expenditures’. (This template will be annexed as a separate file.

Project-level monitoring and evaluation systems

- Review the monitoring tools currently being used: Do they provide the necessary information? Do they involve key partners? Are they aligned or mainstreamed with national systems? Do they use existing information? Are they efficient? Are they cost-effective? Are additional tools required? How could they be made more participatory and inclusive?

- Examine the financial management of the project monitoring and evaluation budget. Are sufficient resources being allocated to monitoring and evaluation? Are these resources being allocated effectively?

- Review the extent to which relevant gender issues were incorporated in monitoring systems. See Annex 9 of Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines.

Stakeholder Engagement

- Project management: Has the project developed and leveraged the necessary and appropriate partnerships with direct and tangential stakeholders?

- Participation and country-driven processes: Do local and national government stakeholders support the objectives of the project? Do they continue to have an active role in project decision-making that supports efficient and effective project implementation?

- Participation and public awareness: To what extent has stakeholder involvement and public awareness contributed to the progress towards achievement of project objectives?

- How does the project engage women and girls? Is the project likely to have the same positive and/or negative effects on women and men, girls and boys? Identify, if possible, legal, cultural, or religious constraints on women’s participation in the project. What can the project do to enhance its gender benefits?

Social and Environmental Standards (Safeguards)

- Validate the risks identified in the project’s most current SESP, and those risks’ ratings; are any revisions needed?

- Summarize and assess the revisions made since CEO Endorsement/Approval (if any) to:

  - The project’s overall safeguards risk categorization.

  - The identified types of risks (in the SESP).

  - The individual risk ratings (in the SESP).

  - Describe and assess progress made in the implementation of the project’s social and environmental management measures as outlined in the SESP submitted at CEO Endorsement/Approval (and prepared during implementation, if any), including any revisions to those measures. Such management measures might include Environmental and Social Management Plans (ESMPs) or other management plans, though can also include aspects of a project’s design; refer to Question 6 in the SESP template for a summary of the identified management measures.

A given project should be assessed against the version of UNDP’s safeguards policy that was in effect at the time of the project’s approval.

Reporting

  - Assess how adaptive management changes have been reported by the project management and shared with the Project board.

  - Assess how well the Project Team and partners undertake and fulfil GEF reporting requirements (i.e. how have they addressed poorly-rated PIRs, if applicable?)

  - Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners.

Communication and Knowledge Management

- Review internal project communication with stakeholders: Is communication regular and effective? Are there key stakeholders left out of communication? Are there feedback mechanisms when communication is received? Does this communication with stakeholders contribute to their awareness of project outcomes and activities and investment in the sustainability of project results?

- Review external project communication: Are proper means of communication established or being established to express the project progress and intended impact to the public (is there a web presence, for example? Or did the project implement appropriate outreach and public awareness campaigns?)

- For reporting purposes, write one half-page paragraph that summarizes the project’s progress towards results in terms of contribution to sustainable development benefits, as well as global environmental benefits.

- List knowledge activities/products developed (based on knowledge management approach approved at CEO Endorsement/Approval).

- Sustainability

- Validate whether the risks identified in the Project Document, Annual Project Review/PIRs and the ATLAS Risk Register are the most important and whether the risk ratings applied are appropriate and up to date. If not, explain why.

- Complete the “Risks to achieving outcomes” template (Annex J to these TORs) to summarize risks that might affect the achievement of desired outcomes and the mitigation measures which are planned or already undertaken to address these.

- In addition, assess the following risks to sustainability:

Financial risks to sustainability:

- What is the likelihood of financial and economic resources not being available once the GEF assistance ends (consider potential resources can be from multiple sources, such as the public and private sectors, income generating activities, and other funding that will be adequate financial resources for sustaining project’s outcomes)?

Socio-economic risks to sustainability:

- Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? Is there sufficient public / stakeholder awareness in support of the long-term objectives of the project? Are lessons learned being documented by the Project Team on a continual basis and shared/ transferred to appropriate parties who could learn from the project and potentially replicate and/or scale it in the future?

Institutional Framework and Governance risks to sustainability:

- Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardize sustenance of project benefits? While assessing this parameter, also consider if the required systems/ mechanisms for accountability, transparency, and technical knowledge transfer are in place.

Environmental risks to sustainability:

- Are there any environmental risks that may jeopardize sustenance of project outcomes?

Conclusions and Recommendations

The MTR consultant/team will include a section in the MTR report for evidence-based conclusions, in light of the findings.

Additionally, the MTR consultant/team is expected to make recommendations to the Project Team. Recommendations should be succinct suggestions for critical intervention that are specific, measurable, achievable, and relevant. A recommendation table should be put in the report’s executive summary. The MTR consultant/team should make no more than 15 recommendations total.

Additionally, the evaluation process will incorporate gender equality and women’s empowerment perspectives, as well as other cross-cutting issues such as human rights, disability inclusion and social inclusion.

Ratings

The MTR team will include its ratings of the project’s results and brief descriptions of the associated achievements in a MTR Ratings & Achievement Summary Table in the Executive Summary of the MTR report. See the TOR Annexes for the Rating Table and ratings scales. No rating on Project Strategy and no overall project rating is required.

Table. MTR Ratings & Achievement Summary Table

| Measure | MTR Rating | Achievement Description |
| --- | --- | --- |
| Project Strategy | N/A |  |
| Progress Towards Results | Objective Achievement Rating: (rate 6 pt. scale) |  |
|  | Outcome 1 Achievement Rating: (rate 6 pt. scale) |  |
|  | Outcome 2 Achievement Rating: (rate 6 pt. scale) |  |
|  | Outcome 3 Achievement Rating: (rate 6 pt. scale) |  |
|  | Etc. |  |
| Project Implementation & Adaptive Management | (rate 6 pt. scale) |  |
| Sustainability | (rate 4 pt. scale) |  |

- Expected Outputs and Deliverables

The MTR team shall prepare and submit:

| # | Deliverable | Description | Timing | Responsibilities | Reviewers | Percentage of the total fee |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | MTR Inception Report | MTR team clarifies objectives and methods of Midterm Review | One week after signing the contract and no later than 2 weeks before the MTR mission | The MTR team submits to the Commissioning Unit and project management | Key national stakeholders/UNDP M&E Specialist and NCE RTA | 20% |
| 2 | Evaluation mission and Presentation of findings | MTR mission: stakeholder meetings, interviews, field visits; to be agreed at the inception whether the Team Leader will be able to join the National consultant to undertake this mission or only the NC. - Security clearances to be facilitated in advance - Data Collection and Analysis methodology to be agreed upon before the field mission - presentation of Initial Findings | Mission to commence immediately after the submission & presentation of the MTR Inception Report and initial findings to be presented at end of the field mission | MTR Team presents to project management and the Commissioning Unit |  | 40% |
| 3 | Draft MTR Report | Full draft report (using guidelines on the content outlined in Annex B) with annexes | Within 3 weeks of the MTR mission | Sent to the Commissioning Unit, reviewed by RTA, Project Coordinating Unit, GEF OFP |  |  |
| 4 | Final Report* | Revised report with audit trail detailing how all received comments have (and have not) been addressed in the final MTR report | Within 1 week of receiving UNDP comments on the draft | Sent to the Commissioning Unit |  | 40% |
| Total working days |  |  |  | 24 Working days |  | 100% |

*The final MTR report must be in English. The report should be well-written and edited properly before submission.

The final report must address all the quality checklist questions in section 6 (page 8-12) of UNDP Evaluation Guidelines.

- Institutional Arrangements

The principal responsibility for managing this MTR resides with the Commissioning Unit. The Commissioning Unit for this  project is UNDP Somalia Country Office.

The Commissioning Unit will contract the Consulting Firm contracted under an existing Long-Term Agreement (LTA) framework for the AMP MTRs, and will work with the Regional AMP PMU, and Somalia AMP national project teams to ensure logistical support is provided where necessary for the MTR team. The Commissioning Unit will also provide an updated stakeholder list with contact details (phone and email). the Somalia AMP project management unit  will be responsible for liaising with the MTR team appointed by the Consulting Firm to provide all relevant documents, and, if needed, assist in the stakeholder interviews process and field visits arrangements. The project management unit of AMP Somalia consists of UNDP staff at the UNDP Country Office.

It is important to note that the Consulting Firm will be responsible for organizing and conducting stakeholder interviews, managing logistics for field visits, and handling any other related administrative or logistical tasks required for the assignment.

- Duration of the Work

The total duration of the MTR will be approximately 24 working days over a period of 7 weeks starting from the date of contract signature and shall not exceed three months from when the consultant(s) are hired. The international expert is expected to work for a maximum of 24 person-days while the national expert is expected to work 12 person-days, and the task manager 2 person-days.

The working days indicated in the table below correspond to the timeframe we estimate each activity will take, but depending on the number of experts involved the person-days may be larger. Therefore, several experts may work concurrently during one given working day.

The tentative MTR timeframe is as follows:

| Activity | Number of working days | Completion date |
| --- | --- | --- |
| Document review and preparing the MTR Inception Report | 4 days | 1 week after the initiation of the contract |
| MTR missions: stakeholder meetings, interviews, field visits | 10 days | 2 weeks after the initiation of the contract |
| Presentation of initial findings | 1 day | 3 weeks after the initiation of the contract |
| Preparing draft report (due within 3 weeks of the MTR mission) | 6 days | 6 weeks after the initiation of the contract |
| Finalization of MTR report/ Incorporating audit trail from feedback on draft report (due within 1 week of receiving UNDP comments on the draft) | 3 days | 7 weeks after the initiation of the contract |
| Total | 24 days |  |

The start date of the contract is (01 May 2025).

- Duty station

Home-based with travel to Somalia and its regions including Mogadishu-Banadir and Hargeisa Somaliland or Garowe in Puntland State. The number of locations to be visited by evaluation team will be decided at the inception phase. On a weekly basis, the mid-term review consultant will report to the UNDP Somalia Portfolio Manager while keeping informed on the overall progress and achievements.

Travel:

- International travel will be required to be in Somalia during the MTR mission;

- The BSAFE training course must be completed before the commencement of travel; Herewith is the link to access this training: https://training.dss.un.org/courses/login/index.php. These training modules at this secure internet site are accessible to Consultants, which allows for registration with a private email.

- Individual Consultants are responsible for ensuring they have vaccinations/inoculations when traveling to certain countries, as designated by the UN Medical Director.

- Consultants are required to comply with the UN security directives set forth under https://dss.un.org/dssweb/

- All related travel expenses will be covered and will be reimbursed as per UNDP rules and regulations upon submission of an F-10 claim form and supporting documents.

REQUIRED SKILLS AND EXPERIENCE

- Team Composition and Qualifications of the Successful Applicants

The Consulting Firm will conduct the MTR with the following team: one international-level expert/team leader (with experience and exposure to projects and evaluations in other regions globally), one national-level expert from Somalia and one task manager.

The team leader will have the overall responsibility for the conduction of the MTR exercise as well as quality and timely submission of reports (inception, draft final, audit trial, etc.).

The national team expert will assess emerging trends with respect to regulatory frameworks, budget allocations, capacity building, develop communication with stakeholders who will be interviewed, and work with the project team in developing the MTR workplan and itinerary etc.

The task manager (common to other AMP MTRs), will provide overall program-level quality assurance and relevant linkages in alignment with other MTRs conducted in the scope of AMP.

The experts appointed by the Consulting Firm should not have participated in the project preparation, formulation, and/or implementation (including the writing of the Project Document) and should not have a conflict of interest with the project’s related activities.

The selection of consultants will be aimed at maximizing the overall “team” qualities in the following areas:

- Task Manager

Education

- A master’s degree or higher in a discipline relevant to renewable energy, environmental engineering, environmental science, development planning, project management, or a closely related field.

- Additional relevant certifications and training an added advantage

Experience

- Relevant experience with result-based management evaluation methodologies, with experience in the evaluation of at least 3 similar projects required.

- At least 10 years of professional experience in the design, implementation, monitoring and evaluation of development projects in a relevant technical area.

- Experience in the evaluation of GEF-funded and/or projects implemented by the United Nations an added advantage.

- Experience in renewable energy projects (in particular related to off-grid electrification) preferred.

- Demonstrated understanding of issues related to gender and climate change, with experience in gender sensitive evaluation and analysis required.

- Experience in leading several teams of experts to contribute to an overall similar assignment

- Previous experience in Africa.

Language

- Fluency in written and spoken English and French required.

- International Level Expert

Education

- A master’s degree or higher in a discipline relevant to renewable energy, environmental engineering, environmental science, development planning, project management, or a closely related field.

Experience

- Relevant experience with result-based management evaluation methodologies, with experience in the evaluation of at least 3 similar projects required. Experience in the evaluation of GEF-funded and/or projects implemented by the United Nations an added advantage.

- At least 7 years of professional experience in the design, implementation, monitoring and evaluation of development projects in a relevant technical area. Experience in renewable energy projects (related to off-grid electrification) preferred.

- Demonstrated understanding of issues related to gender and climate change, with experience in gender sensitive evaluation and analysis preferred.

Language

- Fluency in written and spoken English required.

- National Level Expert

Education

- A master’s degree or higher in a discipline relevant to renewable energy, environmental engineering, environmental science, development planning, project management, or a closely related field.

Experience

- Minimum of 5 years' experience supporting the design, implementation, monitoring and evaluation of development projects in the energy sector in result-based management framework required in the country of assignment for this national expert.

- Experience in conducting consultations with energy authorities, NGO’s and other relevant actors in the energy sector in the country of assignment for this national expert desirable.

- Experience in supporting evaluation of GEF-funded and/or projects implemented by the United Nations an added advantage.

- Experience in renewable energy projects (in particular related to off-grid electrification) preferred.

Language

- Fluency in written and spoken English and Somali required.

- Ethics

The MTR team will be held to the highest ethical standards and is required to sign a code of conduct upon acceptance of the assignment. This MTR will be conducted in accordance with the principles outlined in the UNEG ‘Ethical Guidelines for Evaluation’. The MTR team must safeguard the rights and confidentiality of information providers, interviewees and stakeholders through measures to ensure compliance with legal and other relevant codes governing collection of data and reporting on data. The MTR team must also ensure security of collected information before and after the MTR and protocols to ensure anonymity and confidentiality of sources of information where that is expected. The information, knowledge and data gathered in the MTR process must also be solely used for the MTR and not for other uses without the express authorization of UNDP and partners.

- Schedule of Payments

- 20% payment upon satisfactory delivery of Deliverable 1 (final MTR Inception Report) and approval by the Commissioning Unit

- 40% payment upon satisfactory delivery of Deliverable 2 (Presentations) and Deliverable 3 (draft MTR reports) and approval by the Commissioning Unit

- 40% payment upon satisfactory delivery of Deliverable 4 (final MTR reports) and approval by the Commissioning Unit and RTA (via signatures on the TE Report Clearance Forms) and delivery of completed TE Audit Trails

Criteria for issuing the final payment of 40% :

- The final MTR reports include all requirements outlined in the MTR TORs and is in accordance with the MTR guidance.

- The final MTR reports are clearly written, logically organized, and are specific for the respective projects (i.e. text has not been cut & pasted from other MTR reports).

- The Audit Trails include responses to and justification for each comment listed.

Evaluative Matrix

| Evaluative theme | Evaluative Questions | Indicators | Sources | Methodology |
| --- | --- | --- | --- | --- |
| Project Strategy: To what extent is the project strategy relevant to country priorities, country ownership, and the best route towards expected results? |  |  |  |  |
| Design - problem statement | Review the problem addressed by the project and the underlying assumptions. Review the effect of any incorrect assumptions or changes to the context to achieving the project results as outlined in the Project Document. | - alignment of assumption from project document with real-life assessment and experience of stakeholders (poor - good - very good alignment) | - project document, - PIR (context changes) - interviews with project team, project designers and project stakeholders | compilation of the assumptions and risks described in the prodoc; comparison with risks and assumptions identified by project team and stakeholders assessment of alignment between these two assessment; identification of gaps and improvement potential, formulation of recommendations |
| Design - project strategy | Review the relevance of the project strategy and assess whether it provides the most effective route towards expected/intended results. Were lessons from other relevant projects properly incorporated into the project design? | - alignment of theory of change with problem statement (poor - good - very good) - mentioning of lessons learned | - project documents | reconstruction of the theory of change; assessment whether lessons were incorporated identification of potential gaps and formulation of recommendations |
| Design - relevance for country priorities | Review how the project addresses country priorities. Review country ownership. Was the project concept in line with the national sector development priorities and plans of the country (or of participating countries in the case of multi-country projects)? | - alignment of project objective with country priorities (poor - good - very good) | - project documents - national policies, plans and programs (e.g., electrification laws, policies and plans; budgets, loan agreements with MDBs, research studies, NDCs and reporting to the UNFCCC, national development plans) - interviews with project team, project designers and project stakeholders | qualitative discussion of relevant elements of the country's priorities, identification of improvement potential, recommendations. |
| Design - decision making | Review decision-making processes: were perspectives of those who would be affected by project decisions, those who could affect the outcomes, and those who could contribute information or other resources to the process, taken into account during project design processes? | - alignment of development process with UNDP project development standards with respect to the number and inclusivity of stakeholder consultations | - project documents - standard stakeholder categories from inception report and PFD - interviews with project team, project designers and project stakeholders | - stakeholder mapping, and comparison with standard stakeholder groups as discussed in the generic inception report and PFD, categorizing them into affected, influential and resource persons - qualitative description of the process for including these three groups of stakeholders during project design phase - comparison of this process with the UNDP standards for project development (section 3.1 here https://popp.undp.org/procedure/formulate-development-projects) - qualitative description of the process for including these three groups of stakeholders during project implementation phase - comparison of stakeholders included in design phase with those included currently in the project - gap analysis, formulation of recommendations as needed |
| Design - gender | Review the extent to which relevant gender issues were raised in the project design. See Annex 9 of Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines. - Were relevant gender issues (e.g. the impact of the project on gender equality in the programme country, involvement of women’s groups, engaging women in project activities) raised in the Project Document? | - compliance with gender policy (binary indicator: fully - insufficiently) | - project documents, - interviews with project team, project designers and project stakeholders | - qualitative description of alignment with GEF and UNDP gender policies - assessment of quality of Gender Action Plan against requirements |
| Results Framework/Logframe - indicators and targets | Undertake a critical analysis of the project’s logframe indicators and targets, assess how “SMART” the midterm and end-of-project targets are (Specific, Measurable, Attainable, Relevant, Time-bound), and suggest specific amendments/revisions to the targets and indicators as necessary. | - SMARTness of indicators (binary indicator: fully - insufficiently) | - project documents, - interviews with project team, project designers and project stakeholders | - quality and relevance assessment of indicators based on stakeholder perspectives and expert judgement - potential recommendation for revision of indicators |
| Results Framework/Logframe - outcomes | Are the project’s objectives and outcomes or components clear, practical, and feasible within its time frame? | - SMARTness of targets (binary indicator: fully - insufficiently) | - project documents, - interviews with project team, project designers and project stakeholders | - plausibility assessment based on stakeholder perspectives and expert judgement - potential recommendation for revision of indicators |
| Results Framework/Logframe - development outcomes | Examine if progress so far has led to, or could in the future catalyse beneficial development effects (i.e. income generation, gender equality and women’s empowerment, improved governance etc...) that should be included in the project results framework and monitored on an annual basis. | - completeness of indicator coverage on development impacts | - project documents, - interviews with project team, project designers and project stakeholders | - analysis of country context for rural electrification through mini-grids to assess potential contribution of mini-grids to development objectives; - compilation of observed effects during field trip, interviews and analysis of project monitoring documents - formulation of indicator recommendations as appropriate |
| Results Framework/Logframe - measuring gender | Ensure broader development and gender aspects of the project are being monitored effectively. Develop and recommend SMART ‘development’ indicators, including sex-disaggregated indicators and indicators that capture development benefits. | - relevance of indicators wrt gender dimension | - project documents, - interviews with project team, project designers and project stakeholders | - assessment of relevance and quality of indicators on gender - recommendation on indicators as appropriate |
| Progress Towards Results: To what extent have the expected outcomes and objectives of the project been achieved thus far? |  |  |  |  |
| Progress Towards Outcomes Analysis | Review the logframe indicators against progress made towards the end-of-project targets using the Progress Towards Results Matrix and following the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects; | colour code progress in a “traffic light system” based on the level of progress achieved; assign a rating on progress for each outcome; make recommendations from the areas marked as “Not on target to be achieved” (red). | - PIRs - Interviews with project team and stakeholders | - assessment of project implementation speed - comparison of project scope with national potential and historic experiences with similar roll-outs |
| Progress Towards Outcomes Analysis | Has progress been in line with expectations until now? | yes/no | - PIRs - Interviews with project team and stakeholders | Compare and analyse the GEF Core Indicators at the Baseline with the one completed right before the Midterm Review |
| Progress Towards Outcomes Analysis | What are the remaining barriers to achieving the project objective? | narrative comparing barrier removal effectiveness with original barrier analysis | - PIRs - Interviews with project team and stakeholders | Identify remaining barriers to achieving the project objective in the remainder of the project |
| Progress Towards Outcomes Analysis | How can the project become more successful? | narrative reflecting on factors of success and whether it is possible to leverage them more effectively | - PIRs - Interviews with project team and stakeholders | By reviewing the aspects of the project that have already been successful, identify ways in which the project can further expand these benefits |
| Project Implementation and Adaptive Management: Has the project been implemented efficiently, cost-effectively, and been able to adapt to any changing conditions thus far? To what extent are project-level monitoring and evaluation systems, reporting, and project communications supporting the project’s implementation? To what extent has progress been made in the implementation of social and environmental management measures? Have there been changes to the overall project risk rating and/or the identified types of risks as outlined at the CEO Endorsement stage? |  |  |  |  |
| Management Arrangements | Review overall effectiveness of project management as outlined in the Project Document. Have changes been made and are they effective? Are responsibilities and reporting lines clear? Is decision-making transparent and undertaken in a timely manner? Recommend areas for improvement | - narrative reflecting on changes / adaptive management, - decision making transparency (Likert scale 1 - 5) - decision making timeliness (Likert scale 1 - 5) - reporting line transparency (Likert scale 1 - 5) - responsibility transparency (Likert scale 1 - 5) | interview with project team, UNDP CO | rating |
| Management Arrangements | Review the quality of execution of the Executing Agency/Implementing Partner(s) and recommend areas for improvement | Likert Scale (highly satisfactory - highly unsatisfactory) | interview with UNDP | rating |
| Management Arrangements | Review the quality of support provided by the GEF Partner Agency (UNDP) and recommend areas for improvement | - timeliness, - relevance, - clarity and level of ambiguity, - quality of technical advice (including through learning from regional project and other countries) | interviews with project team | rating |
| Management Arrangements | Do the Executing Agency/Implementing Partner and/or UNDP and other partners have the capacity to deliver benefits to or involve women? If yes, how? | - access to women for human resources - access to women as users of energy / mini-grid customers - access to women entrepreneurs and engineers | - interviews with project team and stakeholders - gender counts of gender-disaggregated indicators | narrative description |
| Management Arrangements | What is the gender balance of project staff? What steps have been taken to ensure gender balance in project staff? | percentage | - staffing table - interview with project leader | counting, narrative description |
| Management Arrangements | What is the gender balance of the Project Board? What steps have been taken to ensure gender balance in the Project Board? | percentage | - Board member list - interview with project leader | counting, narrative description |
| work planning | Review any delays in project start-up and implementation, identify the causes and examine if they have been resolved. | - cumulative delay in days | - PIRs, monitoring reports - interviews with project leader, UNDP Country Office, RTA | narrative |
| work planning | Are work-planning processes results-based? If not, suggest ways to re-orientate work planning to focus on results? | Likert Scale (fully results based - not at all results based) | - work plan - interview with project manager | assessment, potentially recommendation |
| work planning | Examine the use of the project’s results framework/ logframe as a management tool and review any changes made to it since project start. | Likert Scale (results framework is only orientation for management - results framework is not used at all) | - work plan - interview with project manager | assessment, potentially recommendation |
| Finance and cofinance | Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions. | Likert Scale (fully cost-effective - not at all cost effective) | - PIRs, monitoring reports - interviews with project leader, UNDP Country Office, RTA | assessment based on alternative spending opportunities, potentially recommendation |
| Finance and cofinance | Review the changes to fund allocations as a result of budget revisions and assess the appropriateness and relevance of such revisions. | Likert Scale (fund allocations are fully appropriate - not at all appropriate) | - PIRs, monitoring reports - interviews with project leader, UNDP Country Office, RTA | assessment based on alternative spending opportunities, potentially recommendation |
| Finance and cofinance | Does the project have the appropriate financial controls, including reporting and planning, that allow management to make informed decisions regarding the budget and allow for timely flow of funds? | Likert Scale (fully cost-effective - not at all cost effective) | - PIRs, monitoring reports - interviews with project leader, UNDP Country Office, RTA | assessment of missed opportunities due to potential lack of financial control by project team, potentially recommendation |
| Finance and cofinance | Is co-financing being used strategically to help the objectives of the project? Is the Project Team meeting with all co-financing partners regularly in order to align financing priorities and annual work plans? | Likert Scale (fully functional cofinancing strategy - not at all functioning) | - co-financing monitoring table to be filled out by the Commissioning Unit and project team - interviews with project leader, UNDP CO, RTA, cofinanciers, other donors, other financial intermediaries | assessment of missed opportunities due to implementation of cofinancing strategy by project team, potentially recommendation |
| Project-level Monitoring and Evaluation Systems | Review the monitoring tools currently being used: Do they provide the necessary information? Do they involve key partners? Are they aligned or mainstreamed with national systems? Do they use existing information? Are they efficient? Are they cost-effective? Are additional tools required? How could they be made more participatory and inclusive? | Likert Scales: - fully complete information - no information - fully aligned with national systems - not aligned with national systems - extremely efficient - extremely inefficient - extremely participatory - extremely exclusive | - monitoring plans / frameworks - monitoring reports - PIRs - interviews with project team, CO, RTA, potentially also local stakeholders (Steering Committee? Board?) | support ratings with narratives on the following questions: Do they provide the necessary information? Do they involve key partners? Are they aligned or mainstreamed with national systems? Do they use existing information? Are they efficient? Are they cost-effective? Are additional tools required? How could they be made more participatory and inclusive? |
| Project-level Monitoring and Evaluation Systems | Examine the financial management of the project monitoring and evaluation budget. Are sufficient resources being allocated to monitoring and evaluation? Are these resources being allocated effectively? | Likert Scale (highly satisfactory - highly unsatisfactory) | - budgetary documents - interview with MEL lead of project team | if needed: recommendation on improvements |
| Project-level Monitoring and Evaluation Systems | Review the extent to which relevant gender issues were incorporated in monitoring systems. See Annex 9 of Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines. | - did stakeholder workshops include discussions on gender issues (all - where applicable - never) - did gender specialists and women representatives participate in stakeholder workshops? (all - where applicable - never) - are the project's results framework indicators disaggregated by sex and whereever possible by age and by socioeconomic group? (yes - no) - Are the project's results framework targets set up to guarantee a sufficient level of gender balance in activities (e.g., quotas for male and female participation)? (yes-no) - Are gender sensitive indicators included in the project's results framework? (all - where applicable - never) | - results framework - monitoring plan - stakeholder workshops participants lists | if needed: recommendation on improvements; recommendation as needed |
| Stakeholder Engagement | Project management: Has the project developed and leveraged the necessary and appropriate partnerships with direct and tangential stakeholders? | Likert Scale (highly satisfactory - highly unsatisfactory) | - interviews with project stakeholders and external observers - literature review on local mini-grid progress and community as well as regulatory environment - documentation on stakeholder feedback provided by the project | narrative description, formulation of recommendations as needed |
| Stakeholder Engagement | Participation and country-driven processes: Do local and national government stakeholders support the objectives of the project? Do they continue to have an active role in project decision-making that supports efficient and effective project implementation? | Likert Scales: - fully supported by the local governments who are engaged during the project - no communication with local governments - fully supported by the national government which is engaged during the project - no communication with national government | - interviews with local governments - interviews with national government (ministry of Energy) - documents showing support of governments | scales with one sentence justification each; recommendation as needed |
| Stakeholder Engagement | Participation and public awareness: To what extent has stakeholder involvement and public awareness contributed to the progress towards achievement of project objectives? | Likert Scales: - all opportunities for participation and outreach have been leveraged - no communication with the outside world - outreach and stakeholder involvement have had optimal contribution to progress - no contribution | - Stakeholder engagement plan - gender action plan - interviews - document analysis | - assessment of outreach activities - evidence based discussion of potential impact of outreach activities |
| Stakeholder Engagement | How does the project engage women and girls? Is the project likely to have the same positive and/or negative effects on women and men, girls and boys? Identify, if possible, legal, cultural, or religious constraints on women’s participation in the project. What can the project do to enhance its gender benefits? | - engagement with women and girls on local level; - level of ambition of the gender action plan (Likert Scale) | - Stakeholder engagement plan - gender action plan - interviews with target communities - gender action plan | rating supported with short narrative description, formulation of recommendations as needed |
| Social and Environmental Standards (Safeguards) | Validate the risks identified in the project’s most current SESP, and those risks’ ratings; are any revisions needed? | - level of agreement of relevant stakeholders with risk rating | - interviews - SESP | narrative, recommendation to (not) adjust risk ratings |
| Social and Environmental Standards (Safeguards) | Summarize and assess the revisions made since CEO Endorsement/Approval (if any) to: - The project’s overall safeguards risk categorization. - The identified types of risks (in the SESP). - The individual risk ratings (in the SESP) . | Likert Scale (highly satisfactory - unsatisfactory) | - PIRs - interview with project leader and UNDP CO, cofinanciers | summary and assessment |
| Social and Environmental Standards (Safeguards) | Describe and assess progress made in the implementation of the project’s social and environmental management measures as outlined in the SESP submitted at CEO Endorsement/Approval (and prepared during implementation, if any), including any revisions to those measures. Such management measures might include Environmental and Social Management Plans (ESMPs) or other management plans, though can also include aspects of a project’s design; refer to Question 6 in the SESP template for a summary of the identified management measures. | Likert Scale (highly satisfactory - highly unsatisfactory) | - SESP - SES management measure implementation reports (monitoring documents or PIR) | description and assessment; recommendations as needed |
| Reporting | Assess how adaptive management changes have been reported by the project management and shared with the Project Board. | Likert Scale (highly satisfactory - highly unsatisfactory) | - SESP - SES management measure implementation reports (monitoring documents or PIR) | description and assessment; recommendations as needed |
| Reporting | Assess how well the Project Team and partners undertake and fulfil GEF reporting requirements (i.e. how have they addressed poorly-rated PIRs, if applicable?) | Likert Scale (highly satisfactory - highly unsatisfactory) | - PIRs - interview with project leader and UNDP CO | description and assessment; recommendations as needed |
| Reporting | Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners. | Likert Scale (highly satisfactory - highly unsatisfactory) | - PIRs - interview with project leader and UNDP CO | description and assessment; recommendations as needed |
| Communications & Knowledge Management | Review internal project communication with stakeholders: Is communication regular and effective? Are there key stakeholders left out of communication? Are there feedback mechanisms when communication is received? Does this communication with stakeholders contribute to their awareness of project outcomes and activities and investment in the sustainability of project results? | Likert Scale (highly satisfactory - highly unsatisfactory) | - PIRs - Interviews with project team and stakeholders | description and assessment; recommendations as needed |
| Communications & Knowledge Management | Review external project communication: Are proper means of communication established or being established to express the project progress and intended impact to the public (is there a web presence, for example? Or did the project implement appropriate outreach and public awareness campaigns?) | Likert Scale (highly satisfactory - highly unsatisfactory) | - PIRs - Interviews with project team and stakeholders | description and assessment; recommendations as needed |
| Communications & Knowledge Management | For reporting purposes, write one half-page paragraph that summarizes the project’s progress towards results in terms of contribution to sustainable development benefits, as well as global environmental benefits. | Likert Scale (highly satisfactory - highly unsatisfactory) |  |  |
| Communications & Knowledge Management | List knowledge activities/products developed (based on knowledge management approach approved at CEO Endorsement/Approval). |  | - knowledge management approach approved at CEO Endorsement - knowledge activities and products | list reflecting comparison of actual KPs with KM approach |
| Sustainability: To what extent are there financial, institutional, socio-economic, and/or environmental risks to sustaining long-term project results? |  |  |  |  |
| general risks to achieving outcomes | Are the risks identified in the Project Document, Annual Project Review/PIRs and the ATLAS Risk Register the most important ones? Are the risk ratings appropriate and up to date? If not, explain why. | Likert Scale (fully appropriate - not at all appropriate) | - interviews - PIR - Atlas Risk Register | Validate whether the risks identified in the Project Document, Annual Project Review/PIRs and the ATLAS Risk Register are the most important and whether the risk ratings applied are appropriate and up to date. If not, explain why. Give Recommendations for adjustment |
| general risks to achieving outcomes | What are risks that might affect the achievement of desired outcomes and the mitigation measures which are planned or already undertaken to address these. |  |  | Complete the “Risks to achieving outcomes” template (Annex J to these TORs) to summarize risks that might affect the achievement of desired outcomes and the mitigation measures which are planned or already undertaken to address these. |
| Financial risks to sustainability | What is the likelihood of financial and economic resources not being available once the GEF assistance ends (consider potential resources can be from multiple sources, such as the public and private sectors, income generating activities, and other funding that will be adequate financial resources for sustaining project’s outcomes)? | Likert Scale (sustainability is highly likely - not at all likely) | - interviews with project team, project developers, prospective mini-grid users, national agencies (financial, rural electrification), local financial institutions, UNDP CO, donors - analysis of business case in context of local regulatory framework and light of ability and willingness to pay of customers |  |
| Socio-economic risks to sustainability | Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? Is there sufficient public / stakeholder awareness in support of the long-term objectives of the project? Are lessons learned being documented by the Project Team on a continual basis and shared/ transferred to appropriate parties who could learn from the project and potentially replicate and/or scale it in the future? | Likert Scale (sustainability is highly likely - not at all likely) | - interviews with project team, project developers, prospective mini-grid users, national agencies (financial, rural electrification), local financial institutions, UNDP CO, donors, CSOs, womens groups | discussion of the various questions, rating of overall likelihood |
| Institutional Framework and Governance risks to sustainability | Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardize sustenance of project benefits? While assessing this parameter, also consider if the required systems/ mechanisms for accountability, transparency, and technical knowledge transfer are in place. | Likert Scale (sustainability is highly likely - not at all likely) | - national electrification strategy and / or plan as well as related documents - interviews with rural electrification agency, ministry of energy, project developers, development banks | Discussion of the suitability and stability of the national electrification regulatory environment, and effectiveness of scale-up activities (see above) |
| Environmental risks to sustainability: | Are there any environmental risks that may jeopardize sustenance of project outcomes? | Likert Scale (sustainability is highly likely - not at all likely) | - climate risk resilience strategy - interviews - observations in the field visits | discussion of potential enviornmental risks (including climate risks) and recommendations as needed |

- List of Documents Reviewed

UNDP. 2022. “ProDoc of the National child project under the GEF Africa Minigrids Program – Somalia”.

UNDP. 2021. “Annex 6: UNDP Social and Environmental and Social Screening Procedures (SESP)”.

UNDP. 2022 "Annex 11 - Gender Analysis and Gender Action Plan".

UNDP. 2022. Annex 9 "Revised Stakeholder Engagement Plan".

UNDP. 2021. "Annex 10: Draft Environmental and Social Management Framework (ESMF)".

UNDP. 2023. “Project Inception Report”.

UNDP. 2025 “AMP Market Mapping”.

ITA. 2024.” Somalia Energy and Electricity”. https://www.trade.gov/country-commercial-guides/somalia-energy-and-electricity

UNDP. 2024. “Project Implementation Report (PIR) - GEF Africa Minigrids Program – Somalia”.

UNDP. 2024. “Somalia National Mini-grids Dialogue Diagnostic Report”.

UNDP. 2025. “Project Implementation Report (PIR) - GEF Africa Minigrids Program – Somalia”.

UNDP 2025. “AMP Meeting Minutes

UNDP 2024. “Mini-grid training report”.

UNDP. 2024. PUE training report.

UNDP. Government Proposed AMP Mini-grid Pilot Selection

UNDP. 2021."Annex 10: Environmental and Social Management Framework (ESMF)".

World Bank. 2025b. “World Bank Open Data”. World Bank Open Data. https://data.worldbank.org/indicator/sl.agr.empl.zs.

Stakeholders Consulted

| S/N | Name of stakeholder | Institution | Gender (M/F) |
| --- | --- | --- | --- |
|  | Abdifatah Abshir Mohamed | Ministry of Energy and Water Resources | M |
|  | Abdirizak Said Farah | Ministry of Energy and Water Resources | M |
|  | Hassan A. Ahmed | UNDP Somalia | M |
|  | Salah Dahir | UNDP Somalia | M |
|  | Abdullahi Ibrahim Ali | UNDP Somalia | M |
|  | Abdullahi Ahmed Mohamed | Blue Sky Energy Company | M |
|  | Mohamed Warsame | Beco | M |
|  | Naima Abdi Bashir | Tamarso Solar Company | F |
|  | Amal Aldababseh | UNDP BPPS | F |
|  | Beatrice Gitongori | UNDP BPPS | F |
|  | Daniele Guzzo | RES4Africa | M |
|  | Abdirisak Mohamed Abdi | Ministry of Energy and Minerals Somaliland | M |
|  | Saed Abiib | Somaliland Renewable Energy Association | M |
|  | Mohamed Yusuf | Somaliland Renewable Energy Association | M |
|  | Abdullahi Dayib Ahmed | National Electricity Authority | M |

MTR Itinerary

| No. | Date& Time Scheduled | Meeting Location | Stakeholder Type | Institution | Name and contacts | Title |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | August 26, 2025 9:00am | UNDP Somalia CO | Implementing Partner | UNDP BPPS | Amal Aldababseh | Technical Advisor |
| 2 | August 28, 2025 10:30am | Online | Implementing Partner | UNDP BPPS | Patricia De La Cueva | SES Technical Advisor |
| 3 | August 25, 2025 1:30pm | UNDP Somalia CO | Implementing Partner | UNDP | Abdullahi Ibrahim Ali Email: abdullahi.ibrahim.ali@undp.org | Country Office Programme Officer |
| 4 | August 25, 2025 3:00pm | UNDP Somalia CO | Implementing Partner | UNDP | Hassan A. Ahmed | Project Manager/Coordinator |
| 5 | August 26, 2025 10:00am | UNDP Somalia CO | Government Partner | Ministry of Energy and Water Resources (MoEWR) in Mogadishu | Abdifah Abshir Ibrahim-MOEWR-FGS- energy@moewr.gov.so; cellphone: | Director of Energy |
| 6 | August 26, 2025 11:30am | UNDP Somalia CO | Government | National Electricity Authority (NEA) in Mogadishu | Abdullahi Dayib Ahmed dg@nea.gov.so | Director General |
| 7 | August 26, 2025 2:00pm | UNDP Somalia CO | Government | Ministry of Education, Culture and Higher Learning (MOECHL) in Mogadishu | Dr. Mohamed Abdi Mohamed | Director of TVET |
| 8 | August 27, 2025 10:00am | Online | Government Partner | Ministry of Energy and Minerals (MOEM) in Hargeisa | Abdirisak Mohamed Abdi: doe.moem@sldgov.org | Director of Energy |
| 9 | August 26, 2025 3:00pm | UNDP Somalia CO | Project Beneficiaries | Somali Green Energy Association (SOGEA) | Name: Eng. Bashir Mohamed Sofe Title: Chairman, Somali Green Energy Association (SOGEA) & CEO, Dalsan Power Email: info@somgea.org Address: Maka Al-Mukarama Street, Isgoyska Dabka, Mogadishu Website: https://somgea.org/contact-us/ | Chairman |
| 10 | August 27, 2025 11:30am | UNDP Somalia CO | Project Beneficiaries | Financial Institution - Dahabshil Bank | Dahabshil Bank: Abdirahman Ahmed Muudey abdirahman.mudeey@dahabshilbank.com | Representative |
| 11 | August 27, 2025 2:00pm | UNDP Somalia CO | Project Beneficiaries | ESP - BECO | BECO: Gamma Warsama Gamma2040@gmail.com + | Representatives |
| 12 | August 27, 2025 2:00pm | UNDP Somalia CO | Project Beneficiaries | ESP - Mogadishu Power | Mogadishu power: Ahmed Jama Mohamed; Axmedjaama3@gmail.com | Representatives |
| 13 | August 27, 2025 2:00pm | UNDP Somalia CO | Project Beneficiaries | ESP - Delta Engineering | Delta Engineering: Abdihakim Sheikdon; abdihakim@deltec.so | Representatives |
| 14 | August 27, 2025 2:00pm | UNDP Somalia CO | Project Beneficiaries | ESP - Blue Sky | Blue Sky: Abdullahi Ahmed Mohamed; abdullahi@blueskyenergy.so | Representatives |
| 15 | August 27, 2025 3:00pm | Online | Project Beneficiaries | Somaliland Electricity Association (SEA) | Idris Hamud Jibril Title: Chairman, Somaliland Electricity Association (SEA) Email: it@sec.govsomaliland.org Website:https://serc.govsomaliland.org/ | Chairman |
| 16 | August 28, 2025 1:00pm | Online | Project Beneficiaries | Financial Institution - Kube Energy | Kube Energy: Mads Uhlin Hansen mads@kubeenergy.com | Representative |
| 17 | August 28, 2025 1:00pm | Online | Project Beneficiaries | Financial Institution - Shurako | Shurako: Sahra Hassan shassan@shuraako.org | Representative |
| 18 | August 28, 2025 2:00pm | Online | International Partners | Micro-Grid Academy / GIZ | Micro-Grid Academy / RES4Africa:Luca traini luca.traini@res4africa.org Email: info@res4africa.org Website: https://res4africa.org | Focal Point |

Version: 24.08.2025

Questionnaire used for Data Collection

# Interview guide: Financing community (development banks, local financial institutions, donors, etc.)

| Project Strategy |  |  |
| --- | --- | --- |
| Design - relevance for country priorities | - What are the relevant country priorities for the RE sector linked to development in general? - How well fitted is the project with regards to the development priorities and national plans? - Do you have any suggestions for improvements for a better alignment? |  |
| Design - decision making | - How were you as financial partner involved during the project design phase? - And how were you involved during the implementation phase? |  |
| Results Framework/Logframe – outcomes | - In your perspective, are the project’s objectives and outcomes feasible within the project’s time frame? |  |
| Results Framework/Logframe - development outcomes | - What are the project’s future beneficial development impacts (i.e. in terms of income generation, gender equality and women’s empowerment, improved governance etc...)? |  |
| Progress Towards Results: |  |  |
| Progress Towards Outcomes Analysis | - Has project progress been in line with your institutions’ expectations until now? |  |
| Progress Towards Outcomes Analysis | - From a financiers perspective, what are the remaining barriers to achieving the project objectives? |  |
| Progress Towards Outcomes Analysis | - What are the project’ factors of success and how can they be leveraged more effectively? |  |
| Project Implementation and Adaptive Management |  |  |
| Management Arrangements | - Is your organization involved in the project decision-making? If yes, in which way? - Do you perceive the decision-making process as transparent and inclusive? |  |
| Work planning | - What were major delays? - What were major reasons for delays? - Have they been solved in a satisfactory way in your view? |  |
| Finance and cofinance | - What is the co-financing arrangement in the project? Which project components does it finance? - With what frequency does the Project Team meet with your as co-financing partners? With what purpose? |  |
| Finance and cofinance | - Do you believe the results achieved were proportionate to the costs incurred? - Were any cost-saving measures identified and implemented? - Have there been challenges in disbursing funds on time? |  |
| Finance and cofinance | - Were there any significant deviations from the original budget? If yes, why? |  |
| Finance and cofinance | - Are there any financial planning or control tools (e.g. dashboards, forecasting) that are used to monitor budget implementation? |  |
| Project-level Monitoring and Evaluation Systems | - What information do Monitoring tools provide? - Do they involve you as financing partners? - How would you rate their efficiency? 1-5 - Are they cost-effective? 1-5 - Do you think any additional M&E tools would be necessary? |  |
| Stakeholder Engagement | - What communication and awareness raising activities has the project undertaken? - How did they contribute to project progress? |  |
| Stakeholder Engagement | - Has the project leveraged the necessary and appropriate partnerships with direct and tangential stakeholders? |  |
| Social and Environmental Standards (Safeguards) | - Validate the risks identified in the project’s most current SESP: - Risk 1… - Risk 2… - And risk ratings: - Rating 1 - Rating 2 - Are any revisions needed? |  |
| Social and Environmental Standards (Safeguards) | - Are there any revisions made since CEO Endorsement/Approval to: - The project’s overall safeguards risk categorization - The identified types of risks (in the SESP) - The individual risk ratings (in the SESP) |  |
| Reporting | - How have lessens from the adaptive management process been documented and shared with your organization? |  |
| Reporting | - How well are GEF reporting requirements addressed by the project team (i.e. how have they addressed poorly-rated PIRs, if applicable?) - How well are your organization’s reporting requirements addressed by the project team? |  |
| Communications & Knowledge Management | Internal project communication: - How does the internal project communication with you as stakeholders take place? - How regular does this communication take place? - Is there feedback mechanisms when communication is received? - Does this communication contribute to your awareness of project outcomes and activities? |  |
| Sustainability |  |  |
| general risks to achieving outcomes | - What are the most important risks that could jeopardize the achievement of the project outcomes? - Have the risk ratings changed during the course of the project – or do they still need to be adjusted? |  |
| Financial risks to sustainability | - Do you see a risk that once the financial project assistance ends, there will not be enough resources to secure the long-term sustainability of the outcomes? (assess the willingness to pay of customers and the tariff structure) |  |
| Socio-economic risks to sustainability | - Are there any social or political risks that may jeopardize sustainability of project outcomes? - What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? - How and how often are lessons learned documented and shared by the Project Team? |  |
| Institutional Framework and Governance risks to sustainability | - How suitable and stable is the national electrification regulatory environment so that it could promote the sustainability and scale-up of project activities? - How would you assess the technical knowledge transfer from the project relevant SHs? - Are there specific systems/ mechanisms for accountability or transparency in place? |  |
| Environmental risks to sustainability | - Are there any potential environmental risks that could jeopardize the long-term sustainability of the project? E.g., climate risks such as that projects might become uninhabitable due to drought/floodings… |  |

# Interview guide: Implementing Stakeholders (Universities, energy agency, minigrid developer, etc.)

| Project Strategy |  |  |
| --- | --- | --- |
| Design - problem statement | - What are the risks and problems that the project was supposed to tackle? - Did the context change on which the project was initially developed upon? |  |
| Design - relevance for country priorities | - Could the minigrid project be better aligned with the country’s and local community’s priorities? |  |
| Design - decision making | - How was your organization involved during the project design phase? - And was your organization involved during the implementation phase? |  |
| Design - gender Results | - To which extent were gender issues included in project design? |  |
| Framework/Logframe - indicators and targets | - Certain outcomes were not backed by indicators, was there a specific reason for it? - Do you have any recommendations on how to improve the logframe indicators? |  |
| Results Framework/Logframe – outcomes | - In your perspective, are the project’s objectives and outcomes feasible within the project’s time frame? |  |
| Results Framework/Logframe - development outcomes | - What are the project’s future beneficial development impacts (i.e. in terms of income generation, gender equality and women’s empowerment, improved governance etc...)? |  |
| Results Framework/Logframe - measuring gender | - How are the specific gender equality or empowerment impacts of the project measured? - Are there specific indicators? |  |
| Progress Towards Results: |  |  |
| Progress Towards Outcomes Analysis | - What are the project components that have already been successfully implemented? |  |
| Progress Towards Outcomes Analysis | - Has project progress been in line with your expectations until now? |  |
| Progress Towards Outcomes Analysis | - What are the remaining barriers to achieving the project objective? |  |
| Progress Towards Outcomes Analysis | - What are the project’s success factors, and how can they be leveraged more effectively? |  |
| Project Implementation and Adaptive Management |  |  |
| Management Arrangements | - Is your organization involved in the project decision-making? If yes, in which way? - Do you think the decision-making process is transparent and inclusive? |  |
| Management Arrangements | - How do you rate the quality of support provided by the UNDP CO regarding: (highly satisfactory - highly unsatisfactory) - timeliness of support - relevance of support - clarity and level of ambiguity - quality of technical advice (including through learning from regional project and other countries) - Where would you want to see improvement in the support? |  |
| Management Arrangements | - How are women involved as users of energy/mini-grid customers? - How are women entrepreneurs and engineers involved in the project? |  |
| work planning | - What were major delays? - What were major reasons for delays? - How have they been solved? |  |
| Finance and cofinance | - Were there any significant deviations from the original budget? If yes, why? |  |
| Finance and cofinance | - What is the co-financing arrangement in the project? Which project components does it finance? |  |
| Project-level Monitoring and Evaluation Systems | - What information do Monitoring tools provide? - Do they involve key partners? Which? - Are they aligned or mainstreamed with national systems? - Do they use existing information? - How would you rate their efficiency? 1-5 - Are they cost-effective? 1-5 - Do you think any additional tools would be necessary? - How could they be made more participatory and inclusive? |  |
| Project-level Monitoring and Evaluation Systems | - Are sufficient financial and/or staff resources allocated to M&E? - Are they allocated effectively? 1-5 |  |
| Stakeholder Engagement | - Has the project leveraged the necessary and appropriate partnerships with direct and tangential stakeholders? |  |
| Social and Environmental Standards (Safeguards) | - Validate the risks identified in the project’s most current SESP: - Risk 1… - Risk 2… - And risk ratings: - Rating 1 - Rating 2 - Are any revisions needed? |  |
| Social and Environmental Standards (Safeguards) | - Are there any revisions made since CEO Endorsement/Approval to: - The project’s overall safeguards risk categorization - The identified types of risks (in the SESP) - The individual risk ratings (in the SESP) |  |
| Communications & Knowledge Management | - How does the internal project communication with you as stakeholders take place? - How regular does this communication take place? - Is there feedback mechanisms when communication is received? - Does this communication contribute to your awareness of project outcomes and activities? |  |
| Sustainability |  |  |
| general risks to achieving outcomes | - What are the most important risks that could jeopardize the achievement of the project outcomes? - Have the risk ratings changed during the course of the project – or do they still need to be adjusted? |  |
| Financial risks to sustainability | - Do you see a risk that once the financial project assistance ends, there will not be enough resources to secure the long-term sustainability of the outcomes? (potential resources can be from multiple sources: the public and private sectors, income generating activities, and other funding that will be adequate financial resources) |  |
| Socio-economic risks to sustainability | - Are there any social or political risks that may jeopardize sustainability of project outcomes? - What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? - Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? - Is there sufficient public / stakeholder awareness in support of the long-term objectives of the project? - How and how often are lessons learned being documented by the Project Team? With whom are these shared? |  |
| Institutional Framework and Governance risks to sustainability | - How suitable and stable is the national electrification regulatory environment so that it could promote the sustainability and scale-up of project activities? - How would you assess the technical knowledge transfer from the project relevant SHs? - Are there specific systems/ mechanisms for accountability or transparency in place? |  |
| Environmental risks to sustainability | - Are there any potential environmental risks that could jeopardize the long-term sustainability of the project? E.g., climate risks such as that projects might become uninhabitable due to drought/floodings… |  |

# Interview guide: Project Team

| Project Strategy |  |  |
| --- | --- | --- |
| Design - problem statement | - What are the risks and problems that the project was supposed to tackle? - Did the context change on which the project was initially developed upon? |  |
| Design - relevance for country priorities | - What are the relevant country priorities for the Rural Electrification sector linked to development in general? - How does the project align with the countries’ development priorities and national plans? - Do you have any suggestions for improvements for a better alignment? |  |
| Design - decision making | - How were the following SH groups involved during the project design phase? - those affected by the project outcomes (e.g., rural community, households) - those contributing information or other resources to the project (e.g., donors, IFIs, universities) - those that could affect the outcomes (e.g., ministries, political actors, private sector, CSOs) - And how were they involved during the implementation phase? |  |
| Design - gender Results | - To which extent were gender issues included in project design? |  |
| Results Framework/Logframe - indicators and targets | - Certain outcomes in the logframe were not backed by indicators, was there a specific reason for it? - Do you have any recommendations on how to improve the logframe indicators? |  |
| Results Framework/Logframe – outcomes | - In your perspective, are the project’s objectives and outcomes feasible within the project’s time frame? |  |
| Results Framework/Logframe - development outcomes | - What are the project’s future beneficial development impacts (i.e. in terms of income generation, gender equality and women’s empowerment, improved governance etc...)? |  |
| Results Framework/Logframe - measuring gender | - How are the specific gender equality or empowerment impacts of the project measured? - Are there specific indicators? |  |
| Progress Towards Results: |  |  |
| Progress Towards Outcomes Analysis | - How advanced is the project in its timeline? - What are the project components that have already been successfully implemented? |  |
| Progress Towards Outcomes Analysis | - Has project progress been in line with expectations until now? |  |
| Progress Towards Outcomes Analysis | - What are the remaining barriers to achieving the project objective? |  |
| Progress Towards Outcomes Analysis | - How can the benefits of the already successful parts of the project be expanded? |  |
| Project Implementation and Adaptive Management |  |  |
| Management Arrangements | - Who is typically involved in decision-making? - Can you describe a recent decision-making process that worked well or poorly? - Have there been any changes to the project’s management structure, decision-making processes, or implementation approach since inception? - In your view, have these changes improved project delivery? Why or why not? - Could you help me rate on a scale from do not agree to highly agree: - Project decision-making processes are transparent to all relevant team members. - Decisions are made in a timely manner, allowing for smooth implementation. - The rationale behind major project decisions is clearly communicated to the team. |  |
| Management Arrangements | - How do you rate the quality of support provided by the UNDP CO regarding: (highly satisfactory - highly unsatisfactory) - timeliness of support - relevance of support - clarity and level of ambiguity - quality of technical advice (including through learning from regional project and other countries) - Where would you want to see improvement in the support? |  |
| Management Arrangements | - How are women generally involved in human resources of the project team? - How are women involved as users of energy/mini-grid customers? - How are women entrepreneurs and engineers involved in the project? |  |
| Management Arrangements | - What is the gender balance of the Project Board? - What steps have been taken to ensure gender balance in the Project Board? |  |
| work planning | - What were major delays? - What were major reasons for delays? - How have they been solved? |  |
| work planning | - When planning your work, do you link your activities to expected results or goals? In which way? - If not, what could help make your planning more results-focused? |  |
| work planning | - Have there been any changes made to the project’s results framework? |  |
| Finance and cofinance | - Do you believe the results already achieved were proportionate to the costs incurred? - Were any cost-saving measures identified and implemented? - Have there been challenges in accessing or disbursing funds on time? |  |
| Finance and cofinance | - Were there any significant deviations from the original budget? If yes, why? |  |
| Finance and cofinance | - How regularly does the project generate financial reports? - Are these reports used to inform management decisions? - Are there clear procedures in place to ensure timely disbursement of funds for planned activities? - Are there any financial planning or control tools (e.g. dashboards, forecasting) that are used to monitor budget implementation? |  |
| Finance and cofinance | - What is the co-financing arrangement in the project? Which project components does it finance? - With what frequency does the Project Team meet with all co-financing partners? With what purpose? |  |
| Project-level Monitoring and Evaluation Systems | - What information do Monitoring tools provide? - Do they involve key partners? Which? In which way? - Are they aligned or mainstreamed with national monitoring systems? - How would you rate their efficiency? 1-5 - Are they cost-effective? 1-5 - Do you think any additional tools would be necessary? - How could they be made more participatory and inclusive? |  |
| Project-level Monitoring and Evaluation Systems | - Are sufficient financial and/or staff resources allocated to M&E? - Are they allocated effectively? 1-5 |  |
| Stakeholder Engagement | - What communication and awareness raising activities with the outside world on the project have been undertaken? - How did they contribute to project progress? |  |
| Stakeholder Engagement | - Did the project specifically engage women and girls? In which way? |  |
| Social and Environmental Standards (Safeguards) | - Please help me to validate the risks identified in the project’s most current SESP: - Risk 1… - Risk 2… - And risk ratings: - Rating 1 - Rating 2 - Are any revisions needed? |  |
| Social and Environmental Standards (Safeguards) | - Are there any revisions made since CEO Endorsement/Approval to: - The project’s overall safeguards risk categorization - The identified types of risks (in the SESP) - The individual risk ratings (in the SESP) |  |
| Reporting | - How have lessens from the adaptive management process been documented, shared or internalized by partners? |  |
| Communications & Knowledge Management | Internal project communication: - How does the internal project communication with stakeholders take place? - How regular does this communication take place? - Are there key stakeholders that were left out of communication along the project timeline? Why? - Are there feedback mechanisms when communication is received? |  |
| Communications & Knowledge Management | External project communication: - Through which means of communication do you express the project progress and intended impact to the public (e.g., is there a web presence, for example?) - Did the project implement outreach and public awareness campaigns? |  |
| Sustainability |  |  |
| Capacity building | - Has someone in the project community been capacitated with knowledge on the minigrid, e.g. on how the solar PV functions or what has to be done in case of breakdown? |  |
| general risks to achieving outcomes | - What are the most important risks that could jeopardize the achievement of the project outcomes? - Have the risk ratings changed during the course of the project – or do they still need to be adjusted? |  |
| Financial risks to sustainability | - Do you see a risk that once the financial project assistance ends, there will not be enough resources to secure the long-term sustainability of the outcomes? (assess the willingness to pay of customers and the tariff structure) |  |
| Socio-economic risks to sustainability | - Are there any social or political risks that may jeopardize sustainability of project outcomes? - What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? - Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? - Is there sufficient public / stakeholder awareness in support of the long-term objectives of the project? - How and how often are lessons learned being documented by the Project Team? With whom are these shared? |  |
| Environmental risks to sustainability | - Are there any potential environmental risks that could jeopardize the long-term sustainability of the project? E.g., climate risks such as that projects might become uninhabitable due to drought/floodings… |  |

MTR Rating Scales

| Ratings for Progress Towards Results: (one rating for each outcome and for the objective) |  |  |
| --- | --- | --- |
| 6 | Highly Satisfactory (HS) | The objective/outcome is expected to achieve or exceed all its end-of-project targets, without major shortcomings. The progress towards the objective/outcome can be presented as “good practice”. |
| 5 | Satisfactory (S) | The objective/outcome is expected to achieve most of its end-of-project targets, with only minor shortcomings. |
| 4 | Moderately Satisfactory (MS) | The objective/outcome is expected to achieve most of its end-of-project targets but with significant shortcomings. |
| 3 | Moderately Unsatisfactory (HU) | The objective/outcome is expected to achieve its end-of-project targets with major shortcomings. |
| 2 | Unsatisfactory (U) | The objective/outcome is expected not to achieve most of its end-of-project targets. |
| 1 | Highly Unsatisfactory (HU) | The objective/outcome has failed to achieve its midterm targets, and is not expected to achieve any of its end-of-project targets. |

| Ratings for Project Implementation & Adaptive Management: (one overall rating) |  |  |
| --- | --- | --- |
| 6 | Highly Satisfactory (HS) | Implementation of all seven components – management arrangements, work planning, finance and co-finance, project-level monitoring and evaluation systems, stakeholder engagement, reporting, and communications – is leading to efficient and effective project implementation and adaptive management. The project can be presented as “good practice”. |
| 5 | Satisfactory (S) | Implementation of most of the seven components is leading to efficient and effective project implementation and adaptive management except for only few that are subject to remedial action. |
| 4 | Moderately Satisfactory (MS) | Implementation of some of the seven components is leading to efficient and effective project implementation and adaptive management, with some components requiring remedial action. |
| 3 | Moderately Unsatisfactory (MU) | Implementation of some of the seven components is not leading to efficient and effective project implementation and adaptive, with most components requiring remedial action. |
| 2 | Unsatisfactory (U) | Implementation of most of the seven components is not leading to efficient and effective project implementation and adaptive management. |
| 1 | Highly Unsatisfactory (HU) | Implementation of none of the seven components is leading to efficient and effective project implementation and adaptive management. |

| Ratings for Sustainability: (one overall rating) |  |  |
| --- | --- | --- |
| 4 | Likely (L) | Negligible risks to sustainability, with key outcomes on track to be achieved by the project’s closure and expected to continue into the foreseeable future |
| 3 | Moderately Likely (ML) | Moderate risks, but expectations that at least some outcomes will be sustained due to the progress towards results on outcomes at the Midterm Review |
| 2 | Moderately Unlikely (MU) | Significant risk that key outcomes will not carry on after project closure, although some outputs and activities should carry on |
| 1 | Unlikely (U) | Severe risks that project outcomes as well as key outputs will not be sustained |

GEF Core Indicators

| REDUCING GHG EMISSIONS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Core Indicator 6 | Greenhouse gas emission mitigated |  |  |  |  |  |  |  |
|  |  |  |  |  | Expected metric tons of CO2e (6.1 + 6.2) |  |  |  |
|  |  |  |  |  | PIF Stage | Endorsement | MTR | TE |
|  | 6. Greenhouse gas emission mitigated (direct+indirect) (6.1+6.2) |  |  |  | 45,400 | 29,577 | 0 |  |
|  | 6.1 Greenhouse gas emission mitigated in the AFOLU sector (direct+indirect) (6.5+6.6) |  |  |  | 967,392 | 594,000 | 0 |  |
|  | 6.2 Greenhouse gas emission mitigated outside AFOLU sector (direct+indirect) (6.7+6.8) |  |  |  | 0 | 0 | 0 |  |
| Indicator 6.5 | Carbon sequestered or emissions avoided in the sector of Agriculture, Forestry, and Other Land Use (direct) |  |  |  |  |  |  |  |
|  | Anticipated start year of accounting |  | 2022 |  | Expected (metric tons of CO2e) |  | Achieved (metric tons of CO2e) |  |
|  | Duration of accounting |  | 20 years |  | PIF Stage | Endorsement | MTR | TE |
|  |  |  |  |  | 29,577 tCO₂eq | 29,577 tCO₂eq | 0 |  |
| Indicator 6.6 | Carbon sequestered or emissions avoided in the sector of Agriculture, Forestry, and Other Land Use (indirect) |  |  |  |  |  |  |  |
|  | Anticipated start year of accounting |  | 2022 |  | Expected (metric tons of CO2e) |  | Achieved (metric tons of CO2e) |  |
|  | Duration of accounting |  | 20 years |  | PIF Stage | Endorsement | MTR | TE |
|  |  |  |  |  | 967,392 tCO₂eq | 594,000 tCO₂eq | 0 |  |
| Indicator 6.7 | Emissions avoided outside AFOLU sector (direct) |  |  |  |  |  |  |  |
|  | Anticipated start year of accounting |  | - |  | Expected (metric tons of CO2e) |  | Achieved (metric tons of CO2e) |  |
|  | Duration of accounting |  | - |  | PIF Stage | Endorsement | MTR | TE |
|  |  |  |  |  | - | - | - |  |
| Indicator 6.8 | Emissions avoided outside AFOLU sector (indirect) |  |  |  |  |  |  |  |
|  | Anticipated start year of accounting |  | - |  | Expected (metric tons of CO2e) |  | Achieved (metric tons of CO2e) |  |
|  | Duration of accounting |  | - |  | PIF Stage | Endorsement | MTR | TE |
|  |  |  |  |  | - | - | - |  |
| Indicator 6.3 | Energy saved (in megajoule) |  |  |  |  |  |  |  |
|  |  |  |  |  | Expected (megajoule) |  | Achieved (megajoule) |  |
|  |  |  |  |  | PIF Stage | Endorsement | MTR | TE |
|  |  |  |  |  | 3,240 MJ | 7,617.6 MJ | 0 |  |
|  |  |  |  |  | 0 | 11,880 MJ | 0 |  |
| Indicator 6.4 | Increase in installed renewable energy capacity per technology (in MW) |  |  |  |  |  |  |  |
|  | Technology (please select from the dropdown list) |  |  |  | Expected (Capacity - MW) |  | Achieved (Capacity - MW) |  |
|  |  |  |  |  | PIF Stage | Endorsement | MTR | TE |
|  | Solar Photovoltaic |  |  |  | 0.9 | 2.116 MW | 0 |  |
|  | Energy Storage |  |  |  | 0 | 3.300 MWh | 0 |  |

| CROSS-CUTTING STRATEGIC AREAS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Core Indicator 11 | People benefiting from GEF-financed investments |  |  |  |  |  |  |  |
|  |  |  |  |  | Number |  |  |  |
|  |  |  |  |  | Expected |  | Achieved |  |
|  |  |  |  |  | PIF Stage | Endorsement | MTR | TE |
|  |  |  |  | Female | 33335 | 33335 | 0 |  |
|  |  |  |  | Male | 33335 | 33335 | 0 |  |
|  |  |  |  | Total | 66670 | 66670 | 0 |  |

Signed UNEG Code of Conduct Form

Independence entails the ability to evaluate without undue influence or pressure by any party (including the hiring unit) and providing evaluators with free access to information on the evaluation subject.  Independence provides legitimacy to and ensures an objective perspective on evaluations. An independent evaluation reduces the potential for conflicts of interest which might arise with self-reported ratings by those involved in the management of the project being evaluated.  Independence is one of ten general principles for evaluations (together with internationally agreed principles, goals and targets: utility, credibility, impartiality, ethics, transparency, human rights and gender equality, national evaluation capacities, and professionalism).

Signed MTR Clearance Form

Midterm Review Report Reviewed and Cleared By:

Commissioning Unit (M&E Focal Point)

Name: _____________________________________________

Signature: __________________________________________     Date: _______________________________

Regional Technical Advisor (Nature, Climate and Energy)

Name: _____________________________________________

Signature: __________________________________________     Date: _______________________________

Audit Trail (attached as a separate file)

ProDoc

Signed LOA 2025

AMP Meeting minutes 2025

World Bank (2023). Access to electricity (% of population) – Somalia, Fed. Rep. LINK

World Bank (2023). Access to electricity, urban (% of Urbain population). LINK

World Bank (2023). Access to electricity, rural (% of rural population). LINK

LINK

See LINK

World Bank (2023). Access to electricity (% of population). LINK

World Economic Forum (2025). The renewables dividend: Why Somalia must bet big on clean power. LINK

Source: Project Document (ProDoc)

ITA, 2025

LINK

LINK

SEP

International Crisis Group (2025). LINK

Populate with data from the Logframe and scorecards

Populate with data from the Project Document

If available

Colour code this column only

Use the 6 point Progress Towards Results Rating Scale: HS, S, MS, MU, U, HU

International Crisis Group (2025).  LINK

PIRS

From PMU and AMP Somalia Finance team

PIR, 2025

Minigrid training report, 2024

See: LINK

See LINK

PIR, 2025 p.72

AMP Somalia Minigrid Pilot Plan

For ideas on innovative and participatory Monitoring and Evaluation strategies and techniques, see UNDP Discussion Paper: Innovations in

Monitoring & Evaluating Results, 05 Nov 2013.

For ideas on innovative and participatory Monitoring and Evaluation strategies and techniques, see UNDP Discussion Paper: Innovations in

Monitoring & Evaluating Results, 05 Nov 2013.

Populate with data from the Logframe and scorecards

Populate with data from the Project Document

If available

Colour code this column only

Use the 6 point Progress Towards Results Rating Scale: HS, S, MS, MU, U, HU

Risks are to be labeled with both the UNDP SES Principles and Standards, and the GEF’s “types of risks and potential impacts”: Climate Change and Disaster; Disadvantaged or Vulnerable Individuals or Groups; Disability Inclusion; Adverse Gender-Related impact, including Gender-based Violence and Sexual Exploitation; Biodiversity Conservation and the Sustainable Management of Living Natural Resources; Restrictions on Land Use and Involuntary Resettlement; Indigenous Peoples; Cultural Heritage; Resource Efficiency and Pollution Prevention; Labor and Working Conditions; Community Health, Safety and Security.

The Commissioning Unit is obligated to issue payments to the MTR team as soon as the terms under the ToR are fulfilled.  If there is an ongoing discussion regarding the quality and completeness of the final deliverables that cannot be resolved between the Commissioning Unit and the MTR team, the Regional M&E Advisor and Vertical Fund Directorate will be consulted.  If needed, the Commissioning Unit’s senior management, Procurement Services Unit and Legal Support Office will be notified as well so that a decision can be made about whether or not to withhold payment of any amounts that may be due to the evaluator(s), suspend or terminate the contract and/or remove the individual contractor from any applicable rosters. See the UNDP Individual Contract Policy for further details:

https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PSU_Individual%20Contract_Individual%20Contract%20Policy.docx&action=default