Sustainable Fisheries Development in the Red Sea and Gulf of Aden (SFISH) Project

Project number: 00141814

Annual Report (January – December 2024)

Submitted to

The World Bank

Grant No. E056-RY

Data Sheet

| Country | Yemen |  |
| --- | --- | --- |
| Donor (s) | The World Bank |  |
| Project details | Project title: | Sustainable Fisheries Development (SFISH) in the Red Sea and Gulf of Aden |
|  | Project ID | 00141814 |
|  | Project Start Date | October 2022 |
|  | Project End Date | June 2026 |
| Total budget | $ 41,150,000 |  |
| Total expenditure | Expenditures January to December 2024: $ 13,716,367.13 out of $ 25,781,149.59 of the total tranches received |  |
| UNDP Contacts | Zena Ali Ahmed Resident Representative UNDP Yemen Email: Zena.ali-ahmad@undp.org |  |
| Responsible Party | SMEPS (The Small and Micro Enterprise Promotion Service) PWP (Public Works Project) |  |
| Period covered by the report | January 2024 - December 2024 |  |

Contents

1.	Executive Summary:	6

2.	Background:	7

3.	Progress towards development results:	8

3.1	Project Output 1: Improved resilience of the fishery value chain for sustained livelihoods	8

3.1.1	Fishers and micro and medium enterprises benefitted from voucher inputs/micro grants to develop fishery value chain activities:	10

3.1.2	Women and youth with enhanced skills with grants to establish fishery enterprises and access to market opportunities:	10

3.1.3	Fishery Supply chain enablers supported with training and fund matching to improve their production:	11

3.1.4	Fishery associations and cooperatives supported for improved production and services:	11

3.1.5	Restoration and development of key fishery assets:	12

3.1.6	Beneficiaries from training and capacity building to develop the fishery value chain, responsible fishing practices, and fishery management:	15

3.2	Project Output 2: Developed governance systems and knowledge for effective management and climate resilience of fisheries	16

3.2.1	Sub-national fishery governance committees established:	16

3.2.2	Sub-national fishery entities that are using the simplified matrix:	16

3.2.3	A study on fishery sector diversification and development of a business model developed and disseminated:	17

3.2.4	Sub-national fishery management plans developed:	17

4.	Monitoring and Evaluation:	18

5.	Environmental and Social Risk Management:	20

5.1	Overview of ESF Tools for SFISH:	20

5.2	ESF Instruments:	20

5.3	Monitoring and Compliance:	21

5.4	Strengthening the Social Cohesion in Dhubab District:	22

5.5	Labor Management Procedure:	22

5.6	PPE Distribution:	22

5.6.1	SMEPS Distribution:	22

5.6.2	PWP Distribution:	22

5.7	Capacity Building and Awareness:	23

5.7.1	PWP Training Activities:	23

5.7.2	SMEPS Awareness Programs:	23

5.8	Stakeholder Engagement:	23

5.8.1	UNDP-Led Consultations:	23

5.8.2	SMEPS Engagements:	24

5.8.3	PWP Initiatives:	24

5.9	Insights from Stakeholder Engagement (UNDP, PWP, SMEPS):	24

5.10	Grievance Mechanism (GM):	25

5.10.1	SMEPS GM Contacts:	25

5.10.2	PWP GM Contacts:	26

5.10.3	Summary of Received Messages during the reporting period:	26

5.10.3.1	GM Messages per Governorates and Type (SMEPS):	26

5.10.3.2	Type of Complaints Messages (SMEPS):	26

5.10.3.3	Type of Complaints Messages (PWP):	26

5.11	Project Incidents:	27

5.11.1	PWP Incident Log:	28

5.11.2	SMEPS Incident Log:	28

6.	Communications and Visibility:	29

7.	Procurement:	31

8.	Partnerships:	32

9.	Risks and Mitigation Measures:	33

10.	Challenges:	33

11.	Lessons Learned:	33

12.	Financial Summary:	34

13.	Annexes:	34

List of Tables:

Table 1: Project Development Objective	7

Table 2: Component 2 M&E Table	9

Table 3: Landing Sites Status	13

Table 4: PDO	18

Table 5: Output M&E Table	19

Table 6: ESMPs status	20

Table 7: PPE Distribution	22

Table 8: UNDP-Led Consultations	23

Table 9:  Stakeholder Engagement Insights	24

Table 10: GM Messages per Governorates and Type (SMEPS)	25

Table 11: Type of Complaints Messages (SMEPS)	26

Table 12: Type of Complaints Messages (PWP)	26

Table 13: PWP Incident Log	27

Table 14: SMEPS Incident Log	27

Table 15: Incident Details	28

Table 16: Human Stories Highlight	30

Abbreviations and Acronyms

| BoQs | Bill of Quantities |
| --- | --- |
| DFA | De Facto Authorities |
| ESS | Environmental and Social Safeguards |
| ESF | Environmental and Social Framework |
| ESAP | Environmental and Social Action Plan |
| ESMF | Environmental and Social Management Framework |
| ESMP | Environmental and Social Management Plan |
| FAO | Food and Agriculture Organization of the United Nations |
| FWG | Fisheries Working Group |
| GAF | General Authority of Fisheries |
| GM | Grievance Mechanism |
| GoY | Government of Yemen |
| HSSE | Health Safety Security & Environment |
| IDA | International Development Association |
| IDPs | Internally Displaced Persons |
| IRG | Internationally Recognized Government |
| ISM | Implementation Support Mission |
| DIS | Data Information System |
| MoAIFW | Ministry of Agriculture, Irrigation & Fishery Wealth |
| MTR | Mid-Term Review |
| OHS | Occupational Health and Safety |
| PAD | Project Appraisal Document |
| PDO | Project Development Objective |
| PWP | Public Works Project |
| SEA/SH | Sexual Exploitation and Abuse/Sexual Harassment |
| SIERY | Strengthening Institutional & Economic Resilience in Yemen |
| SMEs | Small and medium-sized enterprises (SMEs) or small and medium-sized businesses (SMBs) |
| SMEPS | Small Micro Enterprise Promotion Service |
| TOR | Terms of Reference |
| TPMA | Third Party Monitoring Agency |
| UNDP | United Nations Development Programme |
| WB | World Bank |

# Executive Summary

The World Bank (WB) and the United Nations Development Programme (UNDP) signed a financing agreement on 21 June 2022, to implement the Sustainable Fishery Development in the Red Sea and Gulf of Aden (SFISH) project. This agreement (effective as of 17 August 2022) allocates a budget of US$ 41.15 million to enhance fishery production, reduce post-harvest losses, improve climate resilience, and increase market access in Yemen. The project aims to restore livelihoods in the fisheries sector and create economic opportunities for men and women while fostering sustainable governance systems to ensure climate-resilient fisheries management.

The SFISH project is designed to achieve two primary outcomes: (1) strengthening the fishery value chain in Yemen and (2) developing capacity for effective fishery management in alignment with Yemen's fisheries sector strategy. By June 2024, the project transitioned from the preparatory to the implementation phase, initiating civil works at six sites, disbursing business grants, supporting Small & Medium Enterprises (SMEs), and enhancing coordination with the Ministry of Agriculture, Irrigation, and Fisheries Wealth (MoAIFW) and the General Authority of Fishery (GAF).

The fifth Implementation Support Mission (ISM) was held from 08 – 12 December 2024, in Amman, Jordan, bringing together WB, UNDP, Small & Micro-Enterprise Promotion Service (SMEPS), Public Works Project (PWP), and senior officials from MoAIFW and GAF. The forum assessed progress and developed agreed action points. The collaboration resulted in critical adjustments, aligning the project with Yemen’s evolving conditions. There are also bi-monthly coordination meetings among UNDP, MoAIFW, GAF, SMEPS, and PWP ongoing, promoting real-time problem-solving and cross-agency alignment.

Key achievements during January–December 2024 include:

- A total of 5,197 individuals were trained in sustainable fishing practices, food processing, and value chain management, with 28 percent of participants being women.

- Disbursement of grants to 2,172 micro-producers, including 1,319 fishermen and 853 women and youth.

- Distribution of grants to 633 supply chain enablers and six fisheries cooperatives.

- Preliminary findings indicated an average income increase of 40.9 percent across beneficiaries, with micro-producers achieving a 64 percent increase and women beneficiaries achieving a 22.7 percent increase.

- Delivery of occupational health and safety (OHS) materials to 831 women and youth and 633 supply chain enablers and five cooperatives.

- Formation of 25 community committees with 130 members (including 65 women) across Taiz, Hadhramout, Al Mahrah and Aden.

- Completed Screening process for the second batch nominated list of fishermen, women, and youth in targeted governorates.

- Progress on landing sites: six under implementation, one in technical evaluation phase, one in final design and Bill of Quantities (BoQs) review and one in tender announcement phase.

Since its inception, SFISH has reached 2,805 out of 5,600 beneficiaries, spanning fishermen, supply chain enablers, women, and youth.

The project also engaged a Third-Party Monitoring Agency (TPMA) and undertook site assessments in all targeted governorates and initiated a Mid-Term Review (MTR) to evaluate progress, ensure alignment with objectives and provide actionable recommendations.

# Background

SFISH operates in four southern coastal governorates: Aden, Al Mahrah, Hadramout, and Taiz. These areas were selected based on their reliance on fisheries for livelihoods, high poverty levels, food insecurity, and accessibility for development interventions. The project prioritizes communities with limited previous exposure to fishery development initiatives while considering environmental risks like overfishing and coastal degradation. Women, particularly those from marginalized social groups, are engaged in fisheries-related work, though their participation remains constrained.

Yemen’s political instability, exacerbated by ongoing conflict, poses significant challenges. In June 2024, De Facto Authorities (DFA) forces detained UN staff and NGO personnel, escalating tensions and impacting the humanitarian and development sectors. Despite these disruptions, SFISH remains unaffected, as it operates in International Recognised Government (IRG) of Yemen-controlled areas.

Rising Red Sea tensions have disrupted maritime operations, leading to delays, increased costs and risks for Yemen’s economy. This instability affects fishing communities, adding to their vulnerabilities. Concurrently, a banking crisis in May 2024 saw the IRG blacklist key Sana’a-based banks, causing liquidity issues and depreciation of the Yemeni rial. UNDP transitioned its financial operations to AlKuraimi Islamic Bank and is monitoring developments to ensure project continuity.

The compounded challenges—political instability, economic shocks, and maritime disruptions—have further strained Yemen’s fisheries sector. Navigational hazards and economic pressures disproportionately affect coastal communities, threatening livelihoods dependent on fisheries. SFISH remains committed to addressing these challenges through adaptive management, enhanced coordination, and sustainable interventions.

# Progress towards development results

## Project Output 1: Improved resilience of the fishery value chain for sustained livelihoods

Summary achievement against project targets

| Fishery value chain strengthened in Yemen |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator Name | Baseline |  | Actual (Current) |  | Closing Period |  |
|  | Value | Month/Year | Value | Date | Value | Month/Year |
| Beneficiaries of job-focused interventions (Number) | 0.00 | Aug/2022 | 2,805 | December 2024 | 5600.00 | Jun/2026 |
| Beneficiaries of job-focused interventions - Female (Number) | 0.00 |  | 853 |  | 1680.00 |  |
| Beneficiary households experienced at least ten percent increase in their per capita household income from the baseline situation (Percentage) | $ 256/ YER 64,132 per trip for fishermen $ 345/YER 86,456 per month for women $5,570 average profit / month for supply chain enablers and cooperatives | Aug/2022 | 40.9% | December 2024 | 60.00 | Jun/2026 |
| Sub-national climate informed participatory fishery management plans implemented (Number) | 0.00 | Aug/2022 | 0.00 | December 2024 | 2.00 | Jun/2026 |

Table 1: Project Development Objective

| Component 2: Improving Economic Opportunities, Food Security and Effective Management of Fishery Production in Yemen |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator Name | Baseline |  | Actual (Current) |  | Closing Period |  |
|  | Value | Month/Year | Value | Date | Value | Month/Year |
| Fishers and micro and medium enterprises benefitted from voucher inputs/micro grants to develop fishery value chain activities (Number) | 0.00 | Aug/2022 | 2172 | December 2024 | 4,200.00 | Jun/2026 |
| Women and youth with enhanced skills with grants to establish fishery enterprises and access to market opportunities (Number) | 0.00 | Aug/2022 | 835 | December 2024 | 1,600.00 | Jun/2026 |
| Women with enhanced skills provided with grants to establish fishery enterprises and access to market opportunities (Number) | 0.00 | Aug/2022 | 0 |  | 480.00 | Jul/2026 |
| Fishery associations and cooperatives supported for improved production and services (Number) | 0.00 | Aug/2022 | 6 | December 2024 | 35.00 | Jun/2026 |
| Fishery infrastructure rehabilitated/restored with enhanced climate resilience (Number) | 0.00 | Aug/2022 | 0.0 (6 landing sites under rehablitation) | December 2024 | 9.00 | Jun/2026 |
| Annual fishery management reports produced documenting fishery governance actions (Number) | 0.00 | Aug/2022 | 0.00 | December 2024 | 4.00 | Jun/2026 |
| Beneficiaries from training and capacity building to develop the fishery value chain, responsible fishing practices, and fishery management (Number) | 0.00 | Aug/2022 | 74,398 | December 2024 | 100,000.00 | Jun/2026 |
| Women participation (Percentage) | 0.00 |  | 28% |  | 30.00 |  |

Table 2: Component 2 M&E Table

Description of Results

### Fishers and micro and medium enterprises benefitted from voucher inputs/micro grants to develop fishery value chain activities:

The project supported 2,598 fishermen by providing technical training and grants aimed at improving their productivity and resilience in the fishery value chain. Fishermen received hands-on training in modern fishing practices, engine maintenance, professional and hygenic  fish handling, and preservation techniques. A total of 1,319 fishermen were provided with grants, including essential assets such as boat engines (1,267) and fishing equipment (52), addressing key production challenges. The average value of the individual grant was USD 1,300.

The results of these interventions were significant. Based on a sample size of 350, fishermen reported a 64 percent increase in revenue, driven by improved fish preservation techniques and optimized handling practices. These changes allowed fishermen to reduce post-harvest losses and extend the shelf life of their catch, thus enhancing income stability and market access. Training assessments reflected a 38 percent increase in technical knowledge, highlighting the project's effectiveness in equipping beneficiaries with practical skills for sustainable fishing and business management.

### Women and youth with enhanced skills with grants to establish fishery enterprises and access to market opportunities.

The SFISH project trained 1,234 women and youth in fishery-related skills, including food processing, fishery by-product development, and business management. These interventions aimed to empower women and youth as active participants in the fishery value chain. Among these, 853 women and youth received grants tailored to their business needs, such as food processing equipment, packaging tools and other assets to improve production and marketability. The average value of the individual grant was USD 1,057.

The grants and training have translated into tangible economic benefits. 220 sampled women beneficiaries experienced an average income increase of 22.7 percent, reflecting enhanced profitability and improved access to markets. Beneficiaries also reported significant improvements in customer reach and product diversification, with evidence of higher sales and better income stability. The training led to a 43 percent improvement in technical knowledge, enabling beneficiaries to adopt sustainable and innovative approaches in their enterprises. These interventions not only enhanced the livelihoods of women and youth but also contributed to gender inclusivity within the fishery sector.

### Fishery Supply chain enablers supported with training and fund matching to improve their production:

The project targeted 920 fishery supply chain enablers to enhance their operational efficiency, production quality, and resilience within the fisheries value chain. By the end of 2024, 633 supply chain enablers received a combination of specialized training and matching grants tailored to their business needs. Training sessions focused on business continuity management, financial planning, risk management, and small business development, equipping participants with the knowledge to identify gaps and capitalize on opportunities.

Of these 633, 588 grants are on average USD 6,000. In these cases, there is no matching contribution from the final recipient. However, with the 45 remaing grants the value is USD 12,000 with a matching contribution by the end user of a further USD 12,000 or even more.

Key Outcomes:

- Training programs led to a 25 percent increase in business knowledge, as reflected in pre- and post-assessments, and garnered a 94 percent satisfaction rate among participants.

- Grants provided support for upgrading operational capacities, including the procurement of assets essential for their roles in the supply chain. These assets varied across transport, storage, and retailing, such as vehicles, refrigeration equipment, solar panel systems, insulated storage containers and packaging tools.

- Businesses reported enhanced operational performance and increased production quality, contributing to greater market competitiveness.

18 percent sampled supply chain enablers experienced an average income increase of 36 percent, reflecting the direct impact of training and asset transfers on their profitability and market reach. The grants enabled beneficiaries to improve production efficiency, reduce costs, and expand their business networks, further strengthening their role as vital contributors to the fisheries value chain.

### Fishery associations and cooperatives supported for improved production and services:

The project targeted 30 fisheries cooperatives and five large cooperatives to enhance their production capabilities, institutional capacities, and service delivery. The five larger cooperatives are also engaged in the fishery sector but are simply larger entities. By the end of 2024, out of the 14 approved fisheries cooperatives identified, six of them have signed grant agreements and begun receiving support, with plans to support the remaining cooperativesin 2025.

Fisheries cooperatives benefited from comprehensive training programs designed to equip them with essential skills in business continuity management, risk mitigation, and governance. These sessions improved their financial planning, compliance with cooperative regulations, and leadership capacities, ensuring they could manage resources effectively.

Matching grants provided to the cooperatives supported a variety of critical needs, including transportation vehicles, ice insulators, fishing equipment, boat, engines, rehabilitations, IT equipment, asset maintenance, safety kits, and furnishings, etc. These diverse forms of support directly contributed to improving production quality and service delivery.

The interventions have significantly strengthened the capacity of fisheries cooperatives to deliver improved services to their members and participate more actively in the fisheries value chain. For example, by acquiring essential assets such as transportation vehicles and ice insulators, cooperatives improved their logistics and storage capabilities. Fishing equipment and engines enhanced their productivity, while rehabilitations and IT equipment modernized their facilities and operational systems.

The improvement in infrastructure and capacity will enable cooperatives to better manage resources, increase production efficiency, and comply with market standards. These upgrades have positioned cooperatives for long-term sustainability, greater economic resilience, and enhanced competitiveness in the fisheries sector.

Key challenges included weak financial capabilities among smaller cooperatives, which hindered their ability to meet the required matching contributions for grants. The project addressed this by reducing contribution requirements and linking cooperatives to financial service providers to facilitate access to additional funding.

Institutional governance issues, such as non-compliance with annual re-election requirements, were mitigated through targeted advisory support and capacity-building workshops. Coordination with local authorities also ensured adherence to cooperative regulations, enhancing their governance structures.

To further support the development of fisheries cooperatives, the SFISH project will deliver advanced institutional capacity-building training programs to all 35 targeted cooperatives. This training will focus on governance, financial management and operational sustainability.

Moreover, the project will also develop standardized templates for governance, financial management, and operational policies. These tools will enhance transparency, accountability, and overall operational effectiveness.

Finally, the project team will continue to provide advisory and monitoring support to ensure best practices are adopted and sustained. Facilitating market linkages will remain a priority, enabling cooperatives to connect with exporters and traders to maximize their impact.

### Restoration and development of key fishery assets.

The SFISH project aims to rehabilitate and restore fishery infrastructure across Yemen. These projects are designed to enhance climate resilience, improve fisheries production, and support local fishing communities economically and socially. The program integrates modern, climate-adaptive infrastructure with sustainable solutions, such as renewable energy systems, waste management, and flood control mechanisms.

As of December 2024, significant progress has been achieved in various fish landing sites, with some projects in the implementation phase, others in tendering, and a few at the design stage. The following sections provide detailed updates on the status, progress, and unique features of each landing site.

|  | Governorates | Landing Site | Allocated Budget $ | Contract Cost $ | Variance | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Hadhramout | Al-Qarn | 868,000 | 973,754.95 | -105,755 | Signed |
| 2 | Hadhramout | Al-Rayida | 766,000 | 433,975.44 | +332,024 | Signed |
| 3 | Hadhramout | Al-Hami | 444,000 | 516,738.60 | -72,739 | Signed |
| 4 | Hadhramout | Rowkub | 454,000 | 341,148.00 | +112,852 | Signed |
| 5 | Taiz | Al-Ordi | 838,000 | 384,148.80 | +453,851 | Signed |
| 6 | Aden | Dockyard | 500,000 | 424,110.00 | +75,890 | Signed |
| 7 | Aden | Foqum | 500,000 |  | 500,000 | Final review before tender |
| 8 | Al-Mahra | Saqar | 379,500 |  | 379,500 | Evaluation review phase |
| 9 | Al-Mahra | Domkh | 585,000 |  | 585,000 | Announcement |
|  | TOTAL |  | 5,334,500 | 3,073,875.8 | 2,260,634 |  |

Table 3: Landing Sites Status

Detailed Updates:

      - Bab-Almandab  / Al-Ordi Fish Landing Site

Located in Taiz Governorate near the strategic Bab-Almandab strait, this fish landing site is being rehabilitated to meet modern standards while incorporating climate resilience. Moreover, improved waste management systems are being introduced to prevent environmental degradation and maintain a clean and safe operational environment. The site will significantly benefit the local fishing community by reducing post-harvest losses and enhancing the handling and storage of fish, ultimately supporting sustainable fisheries practices.

- Contract Amount: $384,148.80

- Percentage of Work Completed: 15.00 percent

- Time Elapsed: 1.5 months out of seven months (Completion date: 12 June  2025)

      - Rowkub Fish Landing Site

Situated in Hadhramout Governorate, Rowkub fish landing site is undergoing major rehabilitation to address climate-related challenges, such as floods. The rehabilition of infrastructure incorporates flood-resilient designs and energy-efficient systems, ensuring the site’s long-term sustainability. The project also includes the restoration of critical facilities, such as auction yards and storage units. These improvements aim to enhance operational safety and capacity for fishers, especially during extreme weather conditions. The enhanced facilities are expected to boost economic opportunities for the local community by providing better access to markets.

- Contract Amount: $341,148.00

- Percentage of Work Completed: 12.12 percent

- Time Elapsed: 0.5 months out of seven months (Completion date: 15 July  2025)

      - Al-Rayida Fish Landing Site

Located in Hadhramout Governorate, Al-Rayida fish landing site is undergoing rehablitation with a strong emphasis on climate resilience and operational efficiency. The rehabilitation includes the construction of auction yards, storage facilities, and administrative buildings with flood-control mechanisms and climate-adaptive designs. Solid and liquid waste management systems are also being integrated to ensure environmental sustainability. These advances will streamline operations at the site. The project is set to significantly improve the livelihoods of fishers in the area.

- Contract Amount: $433,975.44

- Percentage of Work Completed: 29.24 percent

- Time Elapsed: four months out of seven months (Completion date: 28 March 2025)

      - Al-Qarn Fish Landing Site

Al-Qarn fish landing site, also in Hadhramout Governorate, is undergoing extensive rehabilitation to enhance its resilience and functionality. The project focuses on constructing robust infrastructure using boulder masonry and reinforced concrete, ensuring durability against climate-related risks. Auction areas and storage capacities will be upgraded with climate-resilient materials. This site will play a crucial role in strengthening the fisheries production and value chain for local fishers, promoting eco-friendly practices, and ensuring long-term sustainability.

- Contract Amount: $973,754.95

- Percentage of Work Completed: 46.24 percent

- Time Elapsed: six months out of 12 months (Completion date: 12 June  2025)

      - Al-Hami Fish Landing Site

Located in Hadhramout Governorate, Al-Hami fish landing site is undergoing rehablition with a focus on energy efficiency and climate resilience. The site will feature modernized facilities, including health-compliant infrastructure to improve the handling and processing of fish. By addressing key challenges such as floods, the project aims to increase the site’s productivity and market opportunities for local fishers. Once completed, this site will serve as a vital resource for the fishing community.

- Contract Amount: $516,738.60

- Percentage of Work Completed: 56.29 percent

- Time Elapsed: six months out of 10 months (Completion date: April 26, 2025)

      - Dockyard Fish Landing Site

At the Dockyard fish landing site located in Aden Governorate, the project focuses on the provision of an ice plant with a capacity of 10 tons, equipped with storage refrigerators and a solar energy system. The facility is designed to operate using a hybrid energy system, combining solar power. The contract for this project was signed during December 2024, and it aims to support the Dockyard Landing site by providing sustainable and efficient ice production facilities critical for fish preservation and handling.

- Contract Amount: $424,110.00

- Percentage of Work Completed: 0 percent (Contract signed 30 December 2024)

- Time Elapsed: 0 percent

      - Saqar Fish Landing Site

Located in Al-Mahra Governorate, the tender announcement for the Saqar fish landing site was concluded at the beginning of January 2025 and is currently under review. The project will focus on developing modern, climate-resilient infrastructure to support local fishers and enhance the sustainability of fisheries in the region.

      - Domkh Fish Landing Site

Also situated in Al-Mahra Governorate, the tender announcement for the Domkh fish landing site is expected to conclude at the end of January 2025. Once awarded, the project will aim to construct advanced, climate-resilient fishery infrastructure to benefit the fishing community.

      - Foqum Fish Landing Site

Located in Aden Governorate, the Foqum landing site is currently at the last stages of design and Bill of Quantities (BoQs) review. This project will incorporate advanced design features and sustainable solutions to ensure its operational efficiency and resilience to climate-related challenges.

### Beneficiaries from training and capacity building to develop the fishery value chain, responsible fishing practices, and fishery management

The project aims to build the capacity of 100,000 beneficiaries, equipping them with the skills, knowledge, and tools to engage effectively in the fishery value chain, adopt responsible fishing practices, and enhance fisheries management. By the end of 2024, 5,197 individuals, of which 1,474 were women, had been trained across various technical, operational, and governance areas. This included:

- 2,598 fishermen (micro-producers) trained in sustainable fishing practices, advanced technologies, engine maintenance, and fish handling techniques.

- 1,234 women micro-producers equipped with skills in food processing, fishery by-product development, and small-scale enterprise management.

- 829 supply chain enablers and cooperative members trained in business continuity management, financial planning, and logistics.

- 286 community committee members trained in governance, stakeholder engagement, and risk management.

- 250 field consultants and advisors trained to support project implementation and beneficiaries on the ground.

It is worth noting that  5,197 individuals have been trained, however, not all of these individuals have received grants.

In addition to direct training, more than 592,724 individuals benefited from awareness campaigns and outreach initiatives. These programs covered critical topics, such as nutrition, sustainable fishing practices, and climate resilience. Among the broader audience, 69,192 individuals were engaged through physical trainings/awareness campaigns conducted at schools, households, and community gatherings. These trainings/campaigns focused on promoting the nutritional benefits of fish, climate adaptation measures and marine environment preservation. For instance, on World Fisheries Day, the team collaborated with schools to raise awareness about sustainable fishing and encouraged students to engage in environmental cleanup activities.

The SFISH project also incorporated social and environmental safeguards into its training and awareness activities. A total of 3,966 beneficiaries received awareness on Sexual Exploitation and Sexual Harassment (SEA/SH), Environmental and Social (E&S) standards, and Gender Mainstreaming. Among these, 2,542 beneficiaries (831 women) were provided with Occupational Health and Safety (OHS) tools to promote safe practices in fisheries operations. Training modules included topics such as reporting mechanisms for SEA/SH incidents, gender inclusion in fisheries and safety measures for handling and processing fish.

## Project Output 2: Developed governance systems and knowledge for effective management and climate resilience of fisheries

Summary achievement against project targets

Description of Results

### Sub-national fishery governance committees established.

The project initially aimed to establish gender-balanced sub-national fishery governance committees across multiple regions, targeting 18 elected members, including five women. As of March 2024, four committees were formed through coordination with MoAIFW and GAF, transparent elections, and training sessions on fisheries management and climate change adaptation. However, MoAIFW indicated that legal endorsement of these committees would require financial commitments beyond their capacity, redirecting the matter to GAF.

The assessment of the project team is that it will be extremely challenging for these committees to become functional, unless some form of stipend is paid to the participants. In addition, such a body at the regional level is likely to clash with the relevant GAF partner. Rather, it makes more sense at the community level to establish local committees that can lead on piloting practical community based initiatives. This was briefly discussed during the ISM and is expanded upon further in section 3.2.4 on the Fisheries Management Plans.

### Sub-national fishery entities that are using the simplified matrix

The establishment of a Data Information System (DIS) for MoAIFW is a key activity. Following extensive discussions with relevant stakeholders, UNDP proposed utilizing an existing system developed by FAO, known as the Calipseo system, rather than developing and installing a completely new system. After consultations with the World Bank and MoAIFW, it was agreed to proceed with this approach.

The budget allocated under this component will be utilized to enhance the infrastructure within the ministry and the General Authority of Fishery (GAF) to support the installation and effective operation of the Calipseo system. Moreover, the budget will cover the costs of enumerators who will conduct data collection at various landing sites, ensuring the system is populated with accurate and timely information to support decision-making in the fisheries sector.

### A study on fishery sector diversification and development of a business model developed and disseminated

The study aims to explore strategies for diversifying the fisheries sector, enhancing its sustainability and resilience against economic and environmental challenges. More specifically, the study will focus upon mariculture and its potential for application by communities at the local level in Yemen. Initially, a consultancy firm was contracted to execute the study. However, the firm failed to meet the required standards, and the contract was terminated. Subsequently, WorldFish, an international research organization, was approached as a potential partner but despite showing interest and engaging in initial discussions, the organization did not want to engage at the end. Therefore, with the support of the World Bank, UNDP head-hunted an international and a local consultant to complete this study. The international consultant has now been contracted and the local consultant is in the process of being recruited. Once engaged, the consultants will gather data, analyze trends, and develop a comprehensive business model, providing actionable recommendations to guide future diversification efforts in the fisheries sector with a specific focus on mariculture. In addition, the plan is to identify communities where activities can be piloted.

### Sub-national fishery management plans developed

The activity focuses on developing fishery management plans as part of a sustainable fishery management approach. This activity is planned for two of the target GAFs Aden (covering Aden, Abyan and Lahj) and Hadramout (covering Hadramout, Shabwah and Socotra).

Following discussions with the World Bank, the strategy shifted from regional to community-based plans to better address local needs and ensure effective implementation. For Aden GAF, following a procurement process, the consulting company AFCAR were engaged and has submitted an inception report and are currently working on the second deliverable. This will provide an assessment of seven communities in the Gulf of Aden region (Aden, Lahj, and Abyan) identified in the inception report and make recommendations as to the three communities where there is potential to develop Fisheries Management Plans. The thinking behind this concept is to support local communities to better manage their resources in a sustainable manner. This is an approach that has been successfully implemented in a number of other countries such as Mauritus and Lebanon. The work is progressing well but despite AFCAR being a capable and diligent partner, there are challenges with regard to their understanding of community management.

The next phase will focus on Hadhramout with Al-Qarn being the initial target site. Here, the plan is to attempt a slight different methodogy and rather than engaging a consulting company, UNDP will employ a local consultant. This individual will ideally be from the community itself and will initially work on developing a stakeholder analysis of the community before engaging in more detailed discussions and negotiations with regard to a fisheries management plan. If and when technical support is required, it will be provided. However, the entry point and focus for all negotiation with the community will be the local consultant. Once this approach has been piloted in Al-Qarn, it will also be implemented in Al-Hami and Al-Rayida.

# Monitoring and Evaluation

| The SFISH project, which began implementation in October 2022, has achieved an average progress rate of 52% across all components, except for the construction component, compared to 60% elapsed project time. With 40% of the time remaining, significant challenges lie ahead, especially concerning the agreed modifications in the governance component. The shift to community-based approaches and other adjustments, will require careful coordination and adaptive strategies to ensure that the project meets its objectives within the remaining timeframe. Below are the Project Development Objective (PDO) updates: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Fishery value chain strengthened in Yemen |  |  |  |  |  |  |
| Indicator Name | Baseline |  | Actual (Current) |  | Closing Period |  |
|  | Value | Month/Year | Value | Date | Value | Month/Year |
| Beneficiaries of job-focused interventions (Number) | 0.00 | Aug/2022 | 2,805 (1319+853+633) | December 2024 | 5600.00 | Jun/2026 |
| Beneficiaries of job-focused interventions - Female (Number) | 0.00 |  | 853 |  | 1680.00 |  |
| Beneficiary households experienced at least ten percent increase in their per capita household income from the baseline situation (Percentage) | $ 256/ YER 64,132 per trip for fishermen $ 345/YER 86,456 per month for women $ 5,570 average profit / month for supply chain enablers and cooperatives | Aug/2022 | 40.9% | December 2024 | 60.00 | Jun/2026 |
| Sub-national climate informed participatory fishery management plans implemented (Number) | 0.00 | Aug/2022 | 0.00 | December 2024 | 2.00 | Jun/2026 |

Table 4: PDO

| Component 2: Improving Economic Opportunities, Food Security and Effective Management of Fishery Production in Yemen |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator Name | Baseline |  | Actual (Current) |  | Closing Period |  |
|  | Value | Month/Year | Value | Date | Value | Month/Year |
| Fishers and micro and medium enterprices benefitted from voucher inputs/micro grants to develop fishery value chain activities (Number) | 0.00 | Aug/2022 | 2172 (1319+853) | December 2024 | 4,200.00 | Jun/2026 |
| Women and youth with enhanced skills with grants to establish fishery enterprises and access to market opportunities (Number) | 0.00 | Aug/2022 | 835 | December 2024 | 1,600.00 | Jun/2026 |
| Women with enhanced skills provided with grants to establish fishery enterprises and access to market opportunities (Number) | 0.00 | Aug/2022 | 0 |  | 480.00 | Jul/2026 |
| Fishery associations and cooperatives supported for improved production and services (Number) | 0.00 | Aug/2022 | 6 | December 2024 | 35.00 | Jun/2026 |
| Fishery infrastructure rehabilitated/restored with enhanced climate resilience (Number) | 0.00 | Aug/2022 | 0.0 ( 6 landing sites under rehablitation) | December 2024 | 9.00 | Jun/2026 |
| Annual fishery management reports produced documenting fishery governance actions (Number) | 0.00 | Aug/2022 | 0.00 | December 2024 | 4.00 | Jun/2026 |
| Beneficiaries from training and capacity building to develop the fishery value chain, responsible fishing practices, and fishery management (Number) | 0.00 | Aug/2022 | 74,398 | December 2024 | 100,000.00 | Jun/2026 |
| Women participation (Percentage) | 0.00 |  | 28% (20.828) |  | 30.00 |  |

Table 5: Output M&E Table

# Environmental and Social Risk Management

### Overview of ESF Tools for SFISH

The SFISH project utilizes various Environmental & Social Framework (ESF)  tools to guide its implementation and ensure compliance with environmental and social standards. These tools are:

- Environmental and Social Management Framework (ESMF): A comprehensive framework guiding all activities.

- Environmental and Social Management Plans (ESMPs): Detailed plans for specific landing sites.

- Labor Management Plans (LMP): Ensures fair and safe labor practices.

- Stakeholder Engagement Plans (SEP): Facilitates inclusive participation.

- Gender Action Plan (GAP). Ensures the gender aspect of the project is suitably addressed.

- Security Management Plan (SMP): Ensures safety and security for stakeholders.

- Environmental and Social Commitment Plan (ESCP): Outlines commitments to meet ESF standards.

Detailed disclosable documents are available at the UNDP project page.

### ESF Instruments

The SFISH project has developed and implemented several ESMPs and other instruments across various locations. Additionally, PWP ensures that Environmental & Social Safeguard (ESS) requirements are integrated into the tendering processes for all fish landing subprojects, enhancing compliance from the outset. The progress of these instruments is as follows:

| Instrument | Date | Status |
| --- | --- | --- |
| ESMP 01- Al-Qarn | February 2024 | Cleared |
| ESMP-02-Al-Ordi | Oct 2024 | Cleared |
| ESMP-03-Rowkub | Sep 2024 | Cleared |
| ESMP04-Al-Rayida | July 2024 | Cleared |
| ESMP-05-Rakhut | - | Developed, but the site was later canceled. |
| ESMP-06-Saqar | January 2024 | Under WB Review |
| ESMP-07-Al-Hami | July 2024 | Cleared |
| ESAP-08-Dockyard | July 2024 | Cleared |
| ESMP-09-Al-Domkh | January 2024 | Under WB Review |
| ESMP-10-Foqum | - | Under Development |

Table 6: ESMPs status

The clearance process for ESMPs is expedited and given priority by the ESF team of  PWP and UNDP, ensuring reviews are completed promptly to prevent delays in field operations. After the Al-Qarn ESMP, which took a significant amount of time in 2023, the joint efforts of PWP, UNDP, and the WB identified ways to expedite the clearance process for ESMPs. The two pending landing sites under review were designated, and their designs were finalized only recently. The ESMP can only be developed and submitted to the WB ESF team after the engineering design is completed and the scope of work is fully identified, as the ESMP will require risk mitigation measures that correspond to the proposed designs.

### Monitoring and Compliance

Monitoring activities ensure adherence to ESMP provisions, including emergency preparedness, waste management, and occupational health and safety (OHS) measures. Key compliance measures include:

- Emergency Plans and First Aid Kits.

- Visible GM posters and complaint boxes.

- Provision of safe drinking water and Personal Protective Equipment (PPE).

Daily compliance is overseen by Health, Safety, Security and Enviroment (HSSE) staff, with regular field visits conducted by PWP safeguarding officers, as there is at least one dedicated staff at each site.

Spot-checks for New Potential Landing Sites

The spot-checks aimed to evaluate the fisheries context and determine the eligibility of new landing sites for potential interventions. Regular monitoring of nine nominated subprojects in four governorates revealed issues requiring immediate resolution. Two potential landing sites were excluded in the pre-selection stage due to environmental and social concerns, namely Al Dharbah in Aden (environmental reasons), and Al-Aradhyia (ownership and social reasons).

Key sites visited by UNDP included the following sites:

- Al Mahra & Hadramout (August 2024): Al-Dumik, Saqar, and Rakhut.

- Taiz, Hudaydah, and Lahj (September 2024): Al-Ordhi, Al-Khawkha, and Ras Al-Ara.

- Aden Sites: Foqum, Amran, Al-Aradhya, and Al-Dharbah, visited at different times throughout the year without the need for dedicated missions since they are in the same location as UNDP’s Sub-office.

These assessments informed decisions about potential project activities and informed the decision to select the landing sites in the Al-Mahara and Aden, in a manner that fit the World Bank’s investment criteria and minimum Environmental and Social Standards requirements.

### Strengthening Social Cohesion in Dhubab District

To address unverified reports and concerns over community tensions in Bab Al-Mandab around one of the landing sites, Al Ordhi, from a neighboring landing site in a nearby village, Ghoriara. Proactive measures were taken by the UNDP ESF team to verify if there were any substantive indicators of social tensions or conflict. Missions to the two communities strengthened the positive perception of the project, cleared any misconceptions and ensured that

- Both communities expressed full support for the rehabilitation of the Al Ordhi landing site.

- Public consultations enhanced acceptance and buy-in.

- Community committees were trained in conflict management.

These stakeholder engagements with the beneficiaries have strengthened the community synergy and support for the project and helped to clear any misunderstandings and provided assurance to the UNDP project management on the feasibility of the intervention.

### Labor Management Procedure

Robust labor management procedures have been implemented to ensure fair working conditions, including:

- Verification of worker age through government-issued ID cards.

- Signing of a Code of Conduct by all workers.

- Gender-sensitive facilities and separate amenities for women.

- Market-aligned wages and daily toolbox talks to emphasize safety.

### PPE Distribution

### SMEPS Distribution

Personal Protective Equipment (PPE) was distributed to various beneficiary groups:

| No | Component | Total Consultants | Total Male Consultants | Total Female Consultants |
| --- | --- | --- | --- | --- |
| 1 | Fishermen | 77 | 77 | 0 |
| 2 | Women & Youth | 40 | 0 | 40 |
| 3 | SMEs | 23 | 20 | 3 |
| Total |  | 140 | 97 | 43 |

Table 7: PPE Distribution

### PWP Distribution

Over 1,350 PPE kits were provided to workers, tailored to their specific roles and site activities.

- Items include helmets with visors, safety shoes, gloves, high-visibility vests, and respiratory protection gear like dust masks.

- Daily toolbox talks have reinforced safety protocols, fostering a culture of responsibility and risk awareness among the workforces.

### Capacity Building and Awareness

### PWP Training Activities

Training modules covered key topics, such as ESMP implementation, OHS, and grievance mechanisms. A total of 1,164 individuals participated, including community members and project staff.

### SMEPS Awareness Programs

Comprehensive training for consultants and community committees addressed critical topics, including OHS, gender awareness, and grievance mechanisms.

### Stakeholder Engagement

Stakeholder engagement has been a critical component of the SFISH project, designed to foster inclusivity and transparency across all activities. Through consultations, focus group discussions and public awareness campaigns the project has established a robust dialogue with local communities and stakeholders.

### UNDP-led Consultations:

A total of 42 stakeholder meetings were conducted across five governorates (Taiz, Aden, Hadramout, Al Mahra, and Hudaydah), engaging 488 participants (423 men, 65 women). These consultations provided a platform to discuss project objectives, gather community feedback, and address concerns effectively.

| Governorate | Number of Meetings | Key Participants | Focus Topics |
| --- | --- | --- | --- |
| Taiz | 10 | Local fishing cooperatives, community leaders, small-scale fishers, women engaged in the fisheries value chain. | Infrastructure needs, capacity building, women’s engagement in income-generating activities. |
| Aden | 5 | Private sector representatives, youth groups, fisheries community. | Public-private partnerships, women’s participation in value chain, addressing post-harvest losses. |
| Hadramout | 12 | Coastal community members, fish processors, fishery cooperatives, fish exporters. | Sustainable resource management, reducing environmental impacts, strengthening export value chains, capacity building, fish handling/packaging practices. |
| Al Mahra | 9 | Fishers, local authorities. | Marine resource management, addressing marginalized communities’ challenges, inclusive development. |
| Hudaydah | 6 | Internally displaced persons (IDPs), local cooperatives, fish market stakeholders, women’s groups. | Supporting IDPs, improving cold storage, gender-inclusive fisheries development. |

Table 8: UNDP-Led Consultations

### SMEPS Engagements:

SMEPS expanded stakeholder engagement efforts, reaching 8,578 participants. This included 4,311 men and 4,267 women, with a focus on empowering micro-producers, women, and youth through targeted capacity-building and support programs.

### PWP Initiatives:

PWP organized 36 consultation meetings across 10 districts in four governorates, involving 760 participants (557 men, 203 women). This effort emphasized inclusivity, with women representing 27 percent of participants. Additionally, 10 community committees were established, comprising 41 men and 19 women, to facilitate localized project oversight.

### Insights from Stakeholder Engagement (UNDP, PWP, SMEPS)

Many insights from the three partners in the field—UNDP, PWP, and SMEPS—are similar. There is a common emphasis from the public on critical aspects of environmental and social sustainability within the fisheries sector. Stakeholder engagements shed light on broader issues that hinder the socioeconomic development of vulnerable populations. Below is a synthesis of the insights gathered from stakeholder engagements conducted by all partners.

| Category | Discussed Risks | Proposed Mitigations |
| --- | --- | --- |
| Infrastructure Deficiency | Lack of auction halls, ice plants, and storage facilities. | Construct auction halls, establish ice plants, and build portable/permanent cold storage units. |
| Weak Associations | Poor governance in fisheries associations. | Strengthen governance, marketing, and financial management through training. |
| Women’s Participation | Limited recognition and support for women in fisheries. | Provide training and resources for women in fish processing and marketing. |
| Market Access Challenges | Limited transportation and market connections. | Establish transportation networks and expand access to regional markets. |
| Destructive Practices | Overfishing, use of harmful techniques (e.g. explosives). | Advocate for sustainable fishing practices, enforce bans on harmful methods. |
| Landing Site Sustainability | Environmental degradation, lack of facilities. | Develop sustainable and climate-resilient infrastructure. |
| Operation & Maintenance | Poor upkeep of facilities, lack of funding for repairs. | Train personnel, allocate budgets for maintenance and upkeep. |
| Waste Management | Improper disposal of fish waste, pollution. | Set up waste processing units, promote segregation and disposal systems, raise awareness. |
| Community Grievance Handling | Inadequate grievance systems. | Train community committees on handling grievances and feedback. |
| Illegal Fishing Practices | Unregistered fishermen, non-compliance with regulations. | Strengthen enforcement of regulations through monitoring and awareness campaigns. |
| Equipment Issues | Outdated and unsafe fishing equipment. | Introduce modern, eco-friendly fishing tools to improve efficiency and safety. |
| Safety Awareness | Lack of safety protocols and emergency preparedness. | Conduct OHS training, emergency drills, and distribute safety manuals and first aid kits. |

Table 9:  Stakeholder Engagement Insights

### Grievance Mechanism (GM)

To uphold the principles of accountability and transparency across all activities, the project has established a robust grievance system that has been developed over time to be effective and efficient. This system aims to strengthen the relationship between implementing partners’ staff, beneficiaries, communities, and partners by offering remote access solutions while maintaining strict data protection policies. The system includes various mechanisms, such as Short Message Service (SMS) texts, WhatsApp, phone calls, helplines, email, social media, and word-of-mouth.

A robust Grievance Mechanism ensures issues are logged and resolved within 14 days.

UNDP, through SMEPS and PWP, ensures that all beneficiaries, community committees, facilitators, coordinators, and field officers are aware of and encouraged to use the grievance system. The team shares the GM contact information with surveyors, consultants, and community members to facilitate the submission of complaints, issues, suggestions, and feedback at any time, as well as to measure their satisfaction.

### SMEPS GM Contacts:

- Hotline: Toll-free number: 8005550

- Call, WhatsApp & SMS: 01-415586 / 774002215

- Email: feedback@SMEPS.org.ye

### PWP GM Contacts:

- Hotline: Toll-free number: 8002626

- Call, WhatsApp & SMS: 77526262

- Email: a.sharhan@pwpyemen.org

A robust Grievance Mechanism ensures issues are logged and resolved within 14 days.

### Summary of Received Messages during the reporting period:

- SMEPS has registered 213 grievances.

- PWP has logged 12 grievances.

- UNDP has handled 27 unresolved cases from SMEPS.

### GM Messages per Governorates and Type (SMEPS)

| Governorate | Cumulative Messages |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | Complaints | Request for information | Suggestion | Positive feedback | Request for support |  |
| Aden | 39 | 8 | 0 | 3 | 0 | 50 |
| Al-Mahrah | 30 | 4 | 0 | 1 | 1 | 36 |
| Hadramout | 93 | 18 | 3 | 18 | 0 | 132 |
| Taiz | 51 | 25 | 6 | 5 | 4 | 91 |
| Sub-Total | 213 | 55 | 9 | 27 | 5 | 309 |
| Total | 309 |  |  |  |  |  |

Table 10: GM Messages per Governorates and Type (SMEPS)

### Type of Complaints Messages (SMEPS)

| Complaints Classification | No. of Messages |
| --- | --- |
| Financial | 55 |
| Targeting | 105 |
| Administrative | 2 |
| Contractual | 4 |
| Social | 3 |
| OHS | 6 |
| Technical | 38 |
| Total | 213 |

Table 11: Type of Complaints Messages (SMEPS)

### Type of Complaints Messages (PWP):

| Complaints Classification | No. of Messages |
| --- | --- |
| Financial | 2 |
| General | 10 |
| Total | 12 |

Table 12: Type of Complaints Messages (PWP)

Out of 12 complaints received, addressed and closed, 10 are under general category (suggestions, new inquiries), and two from financial workers demanding additional fees from contractors.

On October 27, 2024, beneficiaries in Ash Shihr District submitted 27 formal complaints to UNDP, highlighting miscommunication, procurement issues, and delays under the SFISH project. UNDP verified the concerns and escalated them, sharing a detailed report with the World Bank.

The incidents reported in Ash Shihr have been categorized into three primary areas: asset issues, procurement challenges and payment delays. These incidents have prompted corrective actions to address the concerns of beneficiaries and improve the implementation processes. Below is a detailed table summarizing the incidents and the corrective actions taken:

| Incident Place | Details | Status | Corrective Actions Taken |
| --- | --- | --- | --- |
| Ash Shihr District, Hadhramout Gov. | Asset Issues: Issues with defective or uninspected equipment. | Ongoing | So far, some defective refrigeration units have been replaced, while others are awaiting resolution. Ongoing discussions with beneficiaries aim to address the remaining issues, alongside improvements to warranty documentation processes. |
|  | Procurement Challenges: Lack of flexibility and clarity in procurement modalities. | Ongoing | SMEPS is finalizing procurement flexibility measures (e.g. coupon systems) to provide more options for beneficiaries and will share these with UNDP. |
|  | Payment Delays: Delays in disbursing payments for products prepared for events. | Done | SMEPS disbursed all pending amounts and shared receipts with UNDP. |

### Project Incidents

During the reporting period, the following incidents were recorded and addressed. The incidents have been categorized and summarized below. Corrective actions included halting the use of motorcycles unless essential, providing consultants with safety training and distributing PPE such as helmets. These challenges emphasize the importance of prioritizing staff safety and strengthening preventative measures in project operations.

### PWP Incident Log

| Category | Count |
| --- | --- |
| Fatalities | 0 |
| Lost Time Injuries (LTIs) | 0 |
| Restricted Work Cases | 0 |
| Medical Treatment Cases | 0 |
| Incident without injury + First Aid Case | 6 |
| Total | 6 |

Table 13: PWP Incident Log

### SMEPS Incident Log

| Category | Count |
| --- | --- |
| Fatalities | 1 |
| Lost Time Injuries (LTIs) | 0 |
| Restricted Work Cases | 0 |
| Medical Treatment Cases | 0 |
| Incident without injury + First Aid Case | 2 |
| Total | 3 |

Table 14: SMEPS Incident Log

| Type of incident | Involved | Date of incident | Primary cause | Status | Corrective Actions taken |
| --- | --- | --- | --- | --- | --- |
| Acts of Violence/ Kidnapping | SMEPS Consultant | 11/1/2024 | It is the belief of the programme staff that the training program likely with the community leader's beliefs about gender roles, leading to the kidnapping. | Closed | - Withdrawal from the district |
| Fatality | SMEPS Consultant | 20/4/2024 | Motor vehicle accident | Closed | - Reducing the risks of traffic accidents: Strengthening awareness of traffic safety, provision of PPE for consultants using appropriate gear such as helmets. - Compensation policy and life insurance is being revised for future cases, and inclusion of the family of the consultant in SMEPS programming as beneficiaries. |

Table 15: Incident Details

# Communications and Visibility:

The SFISH project integrates communication and visibility as key components to showcase its objectives, progress, and achievements. By embedding key messages in all communication products, and through targeted campaigns, storytelling, social media outreach, and visibility materials, the project highlights its impact on resilience, governance, and inclusive development in Yemen’s fisheries sector, fostering awareness and stakeholder engagement. More detailed information is provide in Annex Four.

To ensure the success of these efforts, the project developed a comprehensive Communication and Visibility Strategy, a detailed Communication Action Plan, and a standardized Visibility Template and guidelines. These tools guide the consistent application of communication practices, ensuring alignment with project objectives and enhance the effectiveness of outreach initiatives.

UNDP Yemen, SMEPS, and PWP have continued highlighting the SFISH’s partnership and its interventions to support Yemen’s fisheries sector. A project media bank, developed in collaboration with SMEPS, is regularly updated to assist in monitoring media activities and share effectively.

The SFISH project, in collaboration with PWP, documented the rehabilitation process of fish landing sites currently under rehabilitation, such as Al-Qarn, Al-Hami, and Al-Raiyda. This included capturing "before" and "during" intervention stages to showcase progress and community impact. These materials will support the production of a final video after the rehabilitation's completion, highlighting the improved functionality and sustainability of these vital sites.

An awareness campaign led by SMEPS reached 69,192 individuals through field visits and awareness activities, promoting nutrition and climate change adaptation. Key messages emphasized balanced diets and sustainable practices using brochures and community engagement. Highlights included school collaborations on marine preservation during World Fisheries Day and active participation in the "Al-Balda season" festival, reaching thousands with fish nutrition and climate awareness messages. (Posts on X Link1 Link2)

The SFISH project featured in marking eight years of collaboration between the World Bank's International Development Association and UNDP Yemen. A social media campaign that celebrated these achievements in empowering Yemen’s fisheries was implemented. A video titled "Celebrating 8 Years of Partnership: Empowering Yemen's Fisheries" was shared on X, highlighting transformative outcomes and SFISH project interventions. A booklet was also developed, featuring success stories and the partnership’s impact on livelihoods, sustainability, and resilience in Yemen’s fisheries sector.

A series of human stories have been developed highlighting transformative journeys as illustrated in the table below:

| Story name | Photo | Link |
| --- | --- | --- |
| Abdo’s story: Mokha’s mobile fish vendor |  | Abdo’s story: Mokha’s mobile fish vendor ¦ United Nations Development Programme |
| Fatima’s fish business success in Yemen |  | Fatima’s fish business success in Yemen ¦ United Nations Development Programme |
| Towards environmental stewardship through reducing fish waste in Mukalla, Yemen |  | Towards environmental stewardship through reducing fish waste in Mukalla, Yemen ¦ United Nations Development Programme |
| From catch to consumption: Supporting the fishery sector in Yemen Anwaar: Championing a nautical legacy. |  | From catch to consumption: Supporting the fishery sector in Yemen ¦ United Nations Development Programme |

Table 16: Human Stories Highlight

# Procurement

During the last ISM held from 8 - 12 December  2024, it was agreed with the WB that the updated Procurement Plan and procurement datasheet, required quarterly updates.

UNDP Procurement Status

- Producing Two Sub-National Fishery Management Plans

  - The consultancy service for developing 1st phase fishery management plans was contracted.

- Establishing Sub-National Fishery Governance Committees

  - The consultancy service to support the establishment of sub-national fishery governance committees (GAF) was finalized.

- Fishery Sector Diversification and Business Model Development

  - A study on fishery sector diversification and the development of a business model was completed on May 1, 2024, however, the contract has been terminated. Currently, two contracts, a national and international consultant will be signed.

- Mid-Term Review by International Fishery Expert

  - An international expert conducted a mid-term review of the fishery program.

- National MTR Evaluators

  - Two national evaluators completed their assignments.

- National Data Collection and Governance Documentation

  - A data collection specialist washired but the contract has been canceled after three months It was decided that a more efficient methodology for this activity would be implementing in partnership with FAO. Currently, the project is developing a UN-to-UN agreement with FAO to develop a data management system.

- SFISH Visibility Materials

  - Visibility materials were procured.

- Industrial Refrigeration Engineer Services

  - Industrial refrigeration engineering services were delivered.

- Representation for Fisheries Program in Hadramout and Al Mahrah

  - Representation services for the fisheries program in Hadramout and Al Mahrah were contracted.

# Partnerships

Collaboration with MoAIFW as well as GAF, serves as a cornerstone for the project's success. This partnership fosters institutional learning, capacity building, and long-term sustainability within the fisheries sector, ensuring that the project's benefits are enduring and impactful.

To amplify project outcomes, continuous efforts are directed toward strengthening the collaboration between UNDP and the implementing partners, SMEPS and PWP. This synergy exemplifies a shared commitment to a unified approach, enabling the achievement of ambitious goals and objectives. There have been challenges in the relationship with the implementing partners and these are mainly associated with the scale and scope of the project and are reflected in section 10. The UNDP team has taken mitigation measures to address these issues and first and foremost amongst these is a stronger collaboration amongst all project partners, namely MoAIFW, GAF, SMEPS, PWP and UNDP. This has been facilitated by more regular communication and interactions which has built a clearer understanding.

UNDP has also developed strong partnerships with other international organizations active in the fisheries sector. There is a twofold focus at the regional and local level. UNDP acting as co-chair of the Fisheries Working Group, jointly with Germany, presents a great opportunity and forum via which to engage with other actors. Also, at the local level, the project actively seeks out and builds relationships with other players. At present, there is a strong coordination with FAO and GIZ and the team is developing the relationship with other actors, such as Expertise Francais, CARE and Mercy Corps.

From an internal coordination perspective, the UNDP SFISH team is taking measures to establish better synergies with other projects engaging in the fisheries sector. Here the obvious candidate is Strengthening Institutional & Economic Resilience in Yemen (SIERY) project given that this project works at the local level in the location where SFISH is active.  Already there have been several information sharing meetings.

In terms of interacting with the rpivate sector and community-level engagements, there are existing relationships but these need to be strengthened. During 2025, the project will work on improving and streamlining interactions at the community level as well as on engaging with the private sector.  In particular the focus at community level will work on developing local level fishery management plans.

At the local level, the main counterpart is GAF. However, especially given the size and the scope of the project and accompanying distributions, Local Authorities are also engaged. In this respect, the implementing partners reach out, inform and, where appropriate, include them. There have been challenges in this regard, as reflected in section 10, but with negotiation and discussions, these have been overcome.

Finally, there is an opportunity for the development of practical mutually beneficial relationships with educational institutions. In particular, universities could play a role in research and monitoring with regard to activities the project is implementing. This was discussed at the ISM and will be explored during 2025.

# Risks and Mitigation Measures:

UNDP’s Enterprise Risk Management Policy applies to risks across all levels of the organization, including project level. Risks at the project level are tracked through the Project Risk Register. A detailed Risk Log is provided as Annex Two.

Risk is defined as the effects of uncertainty on organizational objectives. An effect can be positive and/or negative.

# Challenges

- Weak banking systems and inflation complicate project finances and delay payments to partners.

- Ongoing conflict disrupts governance and stability, leading to potential delays and operational uncertainty.

- Conflict-related import delays increase costs and harm project credibility with key partners.

- The absence of local expertise and reluctance of international firms to operate in Yemen hinder project delivery and the introduction of innovative fisheries practices.

- Transitioning from regional to community-based management plans requires additional time for community engagement and planning.

- Financial constraints at MoAIFW have stalled formal endorsements of governance-related activities.

- Logistical challenges, including contractor delays and coordination with stakeholders in particular the different levels of government.

- Local Authorities can be obstructive particularly with regards the support to the SMEs. This requires careful management ensuring they are informed and involved but at the same time not permitted to takeover the whole process.

# Lessons Learned:

- Effective coordination with stakeholders, such as GAF and MoAIFW, plays a pivotal role in aligning objectives and ensuring smooth implementation, particularly in governance and planning components.

- The absence of local expertise and reluctance of international firms to operate in Yemen underline the need for investing in capacity-building programs to empower local communities and reduce reliance on external expertise.

- The need for a more coordinated approach at the local level. In this regard it has been agreed that in future the Value Chain support will be more closely linked with the Landing site locations.

- While the project is addressing sustainability, this requires more attention in particular with regard to planned management of landing sites and exploration regarding possibilities at the community level.

- More follow-up is required with women beneficiaries and there are plans for production groups and linking them with the market. Just training women on food processing and establishing them with a grant is not sufficient for them to become active in the local market.

# Financial Summary:

The total expenditure for the reporting period is $ 13,716,367.13 which includes $1,287,153.58 for the UNDP component and project management and $11,769,108.84 for SMEPS and PWP. The total contribution received during the reporting period was $ 14,127,071.12

The total expenditure for the project as of 31 December  2024, is $17,302,732.95 and that includes $ 2,240,533.81 for UNDP, $14,278,300.30 for SMEPS and PWP. This represents 42 percent of the original budget of $41,150,000. The total contribution received as of Dec 31, 2024, is $25,781,149.59.

# Annexes:

- Annex 01 Financial Report

- Annex 02: Risk Log

- Annex 03: Procurement Plan

- Annex 04: List of links (Communication)

1319 Fishermen, 853 Women, 633 Supply Chain Enablers

1319 Fishermen, 853 Women

This activity has been integrated into the women and youth component to include an additional 480 women, bringing the total target to 1,680. The proposal was approved by the World Bank on November 6, 2024.

5197 (disaggregation under section 3.1.4) + (11,532*6) = 74,398

Total number of fishermen trained. 1279 fishermen trained but not received grants

This is based upon before and after assessment

Total number of women trained

Pre-Post test conducted for the beneficiaries trained

28% of women trained across all components including field consultants and community committees.

11,532 direct beneficiaries and 57,660 indirect reaches.

5197 (disaggregation under section 3.1.4) + (11,532*6) = 74,398

9 selected landing sites in addition to Rakhut.

Note: Due to the exclusion of the Rakhut landing site, PWP addressed the gap by equipping the community committee with sanitation tools, capacity-building training, and other necessary resources. Additionally, the committee was linked with Mahra GAF to ensure its active involvement in any upcoming interventions.

11,532 direct beneficiaries and 57,660 indirectly.

https://www.yemenmonitor.com/en/Details/ArtMID/908/ArticleID/116958

Annex 03

Annex 02

Annex 01