PROGRESS REPORT

Project to Support the Haitian National Police for Port Security

March – June 2025

- Context and justification

The security situation in Haiti has continued to deteriorate, with armed groups expanding their control over strategic areas, particularly in and around Port-au-Prince. This has severely impacted critical infrastructure, including ports, which face frequent infiltration and disruption by transnational criminal networks involved in arms and drug trafficking.

This unstable environment undermines port operations, disrupts supply chains, and deters maritime traffic, exacerbating logistical challenges. Despite their strategic role in economic recovery and the importation of essential goods, Haitian ports remain highly vulnerable due to weak security systems and limited oversight, particularly in private ports. The Haitian National Police (HNP) lacks the necessary infrastructure, equipment, and surveillance capacity to ensure port security.

Ports in Haiti are of strategic importance for ensuring the continuity of supply chains and supporting national economic recovery. However, their vulnerability remains high due to underdeveloped security systems and inadequate control mechanisms. The operational capacity of the Haitian National Police (HNP) in these areas is significantly limited by chronic under-equipment, the absence of infrastructure dedicated to port security, and serious deficiencies in surveillance systems. In addition, private ports largely fall outside the effective control of the State, particularly in terms of customs enforcement, making them high-risk entry points for prohibited items such as drugs, weapons, and ammunition.

In response, UNDP, with funding from the Government of Japan (5,000,000.00 USD), launched the "Project to Support the Haitian National Police for Port Security". The project aims to strengthen the HNP's operational presence in port zones by providing infrastructure and equipment, thereby contributing to the stabilization of port activities, national recovery, and improved access to essential goods. It also supports ongoing efforts under the broader HNP capacity building programme in partnership with UNODC.

- Progress of activities

As part of the implementation of the “Project to Support the Haitian National Police for Port Security”, significant progress was made during the reporting period, marking an important step toward achieving the project's objective of strengthening the Haitian National Police’s (HNP) operational capacity in port areas.

A joint field visit was conducted with Colonel Morgan, representative of the Ministry of Defense and Public Security (MMSS), to assess the specific needs related to the development of the designated site for the establishment of a dedicated port security facility. This mission enabled a shared assessment of the site’s current condition, the identification of technical and logistical constraints, and the formulation of preliminary recommendations to guide the upcoming development phase.

Following this visit, the UNDP team, in collaboration with the HNP focal point, developed the Terms of Reference (ToR) required to carry out detailed technical studies for the site development. The ToR outlines the objectives, expected deliverables, proposed methodologies, and the technical and environmental requirements that the selected engineering firm must meet.

In line with UNDP procurement procedures, all required administrative and technical documentation including the ToR, concept note, and estimated budget was submitted to the procurement unit to initiate the selection process for a qualified engineering consultancy firm. This step formally launches the procurement process to contract a service provider responsible for conducting the studies that will precede infrastructure works.

These developments reflect the project's commitment to a structured and standards-based implementation approach, while ensuring the active involvement of relevant national authorities at every stage of the process.

- Challenges

The project team, in collaboration with the Haitian National Police (HNP), conducted several site visits to the port areas. These visits highlighted key challenges related to the security context:

- Persistent insecurity in port areas: Secure access to intervention sites remains highly constrained, exposing project staff and operational partners to elevated risks.

- Increased security requirements for movements: Travel to port facilities systematically requires the use of armored vehicles escorted by police personnel.

- Logistical and organizational constraints: Frequent unavailability of police escorts and armored vehicles causes delays in operations, thereby impacting the project’s activity schedule.

These security-related constraints represent significant challenges to the continuity and effectiveness of field interventions.

- Activities in perspective

Regarding the infrastructures, this project will be carried out in two (2) distinct phases. Technical studies and execution of works. In the coming period, the project will launch the procurement process for the technical studies required for the development of the designated port security site. This will lead to the award of a contract to a qualified engineering firm.

Once the contract is signed, the technical studies will begin, with an estimated duration of 90 calendar days. These studies will define the detailed design, technical specifications, and environmental requirements, serving as a key prerequisite for the subsequent construction phase.

- Results framework

| EXPECTED OUTPUTS | Output | Target | Archived value as of 30 June 2025 | Means of verification | Notes |
| --- | --- | --- | --- | --- | --- |
| Preparation and planning | 1.1 Conduct a detailed site assessment | 1 | 1 | Assessment report | A joint field visit was conducted with Colonel Morgan, representative of the Ministry of Defense and Public Security (MMSS), to assess the specific needs related to the development of the designated site for the establishment of a dedicated port security facility. |
|  | 1.2 Organize meetings with police forces, local authorities, and international partners to present the plan. | 2 | 1 | Meeting minutes | Meeting organized with HNP, including the HNP focal points. |
|  | 1.3 Develop a detailed rehabilitation plan including costs, resources and work schedule. | 1 | 1 | ToR | Call for tenders for technical studies ongoing. |
| 2. Infrastructure réhabilitation | 2.1 Rehabilitate the premises of the National Ports Authority and other sites suitable for securing the selected ports | 2 |  |  | Not yet programmed |
|  | 2.2 Install security systems such as fencing, surveillance cameras, and lighting. | 1 set |  |  | Not yet programmed |
| 3. Provision of materials and equipment | 3.1 Prepare the specifications of materials and equipment with the HNP | 1 |  |  | Not yet programmed |
|  | 3.2 Acquire and install office equipment; trained police officers to manage them. | 1 set |  |  | Not yet programmed |

- Risk monitoring and mitigation

| # | Identified risk | Likelihood | Impact | Mitigation measures | Status |
| --- | --- | --- | --- | --- | --- |
| 01 | Escalation of armed violence or criminal activity in port zones, posing operational risks to infrastructure deployment and field-level coordination | High | High | - Close coordination with HNP - Monitor the security situation with the Haitian National Police - Adjust intervention plans as needed | Under review |
| 02 | Delays in the procurement process (technical studies or construction works) | Medium | High | - Close follow-up with the procurement unit - Early preparation of ToR by project team and prompt follow up | Ongoing |
| 03 | Weak coordination among key institutions (HNP, APN, Customs, etc.) | Medium | Moderate | - Regular meetings with stakeholders (HNP Focal Point, HNP Director, Customs, APN) | Planed |
| 04 | Local inflation and market volatility impacting project cost estimates and procurement budgets | Medium | High | - Inclusion of budget flexibility margins - Budget adjustments in coordination with the partners. | To monitor |

- Work plan

| Expected results | Planned activities | Timeframe 2025 |  |  |  |  |  | Timeframe 2026 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| 1: Improved APH-HNP infrastructures | 1.1: Call for tenders for technical studies |  |  |  |  |  |  |  |  |  |
|  | 1.2: Technical studies |  |  |  |  |  |  |  |  |  |
|  | 1.3: Tender process for work execution |  |  |  |  |  |  |  |  |  |
|  | 1.4: Implementation |  |  |  |  |  |  |  |  |  |
| 2: Increasing police presence in port areas and Provision of materials and equipment | 2.1 Acquisition of materials and equipment to facilitate the work of nearly 150 police officers: training for police officers |  |  |  |  |  |  |  |  |  |

- Financial situation

The project’s allocated budget amounts to 5,000,000.00 USD. To date, no expenditures have been incurred, in line with the implementation schedule and pending the completion of contractual procedures.

The procurement process is currently underway to recruit the firm responsible for conducting the technical studies necessary for the port site development. This critical step will enable the actual commencement of operational activities and the initiation of related project expenditures.

It should be noted that rigorous budget monitoring is in place to ensure the efficient use of resources in compliance with sound financial management practices.

- Conclusions

Despite a complex security environment and significant logistical constraints, the project has laid the groundwork for the preparation of the technical studies essential to the secure development of port infrastructure. Close collaboration between UNDP, the Haitian National Police (HNP), and key partners, including the General Administration of Customs (AGD), has made it possible to clearly identify needs and initiate the first administrative and contractual steps.

The upcoming phases, particularly the completion of the technical studies will represent a critical milestone in advancing project implementation and achieving its objectives to improve port security, a key driver of national economic recovery.

The project remains committed to adapting its interventions to ongoing challenges, with a continued focus on strengthening local capacities and ensuring a lasting impact on the country’s stability and security.